## Project Stocktaking Template
| PROJECT DETAILS | PROJECT DETAILS | PROJECT DETAILS | PROJECT DETAILS | PROJECT DETAILS | PROJECT DETAILS | PROJECT LOCATION | PROJECT LOCATION | PROJECT LOCATION | IMPLEMENTATION DETAILS | IMPLEMENTATION DETAILS | IMPLEMENTATION DETAILS | IMPLEMENTATION DETAILS | IMPLEMENTATION DETAILS | IMPLEMENTATION DETAILS | IMPLEMENTATION DETAILS | FINANCIAL INFORMATION | FINANCIAL INFORMATION | FINANCIAL INFORMATION | FINANCIAL INFORMATION | FINANCIAL INFORMATION | DISBURSEMENT | DISBURSEMENT | DISBURSEMENT | DISBURSEMENT | EXPENDITURE | EXPENDITURE | EXPENDITURE | PROJECT STATUS | PROJECT STATUS | PROJECT STATUS | ACTIONS FOR STALLED | ACTIONS FOR STALLED | ACTIONS FOR STALLED | ACTIONS FOR STALLED | RISKS AND RECOMMENDATIONS | RISKS AND RECOMMENDATIONS | RISKS AND RECOMMENDATIONS | CLIMATE & DISASTER RISK SCREENING | CLIMATE & DISASTER RISK SCREENING | ENVIRONMENTAL, SOCIAL, OHS & GENDER SCREENING | ENVIRONMENTAL, SOCIAL, OHS & GENDER SCREENING | TECHNICAL, FINANCIAL & ECONOMIC VIABILITY SCREENING | TECHNICAL, FINANCIAL & ECONOMIC VIABILITY SCREENING | ADDITIONAL REMARKS
S/No. | Project Name/Title | Project Description | Project Goal/Objective | Project Output | Project Code (Budget line) | Budget Item Name | Sub-County | Ward | Geographic Location (Latitude & Longitude) | Sector/ Vote Name | Department, Directorate, Units, Agencies | Implementing Department/Agency / Muncipalities | Date of Approval/Financial Approval | Project Start Date | Expected Project Completion Date | Actual Project Completion Date | Estimated Project Cost (Kshs.) | Approved Project Cost | Funds available in the specific year | Project Funding Source | If Development Partners, Please specify . | County Government component in the Project Cost (Kshs.) | Development Partner component in the Project Cost (Kshs.) | Total Disbursed Funds as at 30th June 2024 (Kshs.) | Percentage (%) Disbursed Amount = (Disbursed/ Approved) | Expenditure to date | Pending Bill/Outstanding commitment not paid but work done | Project Balance (Kshs.) i.e (Approved Project Cost - Disbursed Amount) | Project Status at the time of the Exercise (i.e Completed, Ongoing, Stalled) | % completion for ongoing/stalled projects | If Stalled, what is the percentage (%) completion at the time of stalling (Physical completion status) | If stalled give reasons; | Year the project stalled | Time required to complete the stalled project (in months) | Estimated cost required to complete the stalled project (in Kshs.) | Is the project still appering in the budget or is it still receiving funds in the annual budgets? (Yes/No) | Recommendation for the Stalled Project (Complete/ Cancel/ Defer) | Identify the Risks associated with the stalled/completed/ongoing project ie. (Contractual/legal/Financial/Environmental etc.) | Has this project been screened for Climate & Disaster Risks? Yes/No | If yes, what action has been taken to mitigate? IF Not, give reasons and the immediate plans for conducting the screening. | Has the project been screened for Environmental, Social, Occupational Health, Safety and gender risks | If yes, what action has been taken to mitigate? IF Not, give reasons and the immediate plans for conducting the screening. | Has the project been screened for Technical, Financial, and Economic Viability and a fesibility report been prepared? (yes/No) | If yes, what action has been taken to mitigate? IF Not, what is being used to measure viability of the project? Additionally, indicate immediate plans on when the screening and feasibility study will be undertaken | REMARKS
1 | Administration, Planning and Support Services | Construction of official Residence for The Deputy Governor | To construct official Residence for The Deputy Governor | Official Residence for The Deputy Governor constructed | 3110201 | Residential Buildings (including hostels) | HQ | HQ | N/A | 4561 | OFFICE OF THE GOVENOR AND DEPUTY GOVERNOR | OFFICE OF THE GOVENOR AND DEPUTY GOVERNOR | N/A | 2021/22 | 2021/22 | N/A | 30000000 | 20000000 | 20000000 | Equitable | N/A | 20000000 | 0 | 0 | 0 | 0 | 20000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
2 | Construction Of Non-Residential Building In Mlimani | Construction Of Non-Residential Building In Mlimani | To construct Non-Residential Building In Mlimani | Non-Residential Building In Mlimani constructed | 3110299 | Construction of Buildings - Ot | HQ | HQ | -0.173672, 35.862823 | 4561 | OFFICE OF THE GOVENOR AND DEPUTY GOVERNOR | OFFICE OF THE GOVENOR AND DEPUTY GOVERNOR | N/A | 2019/20 | 2019/20 | 2019/20 | 288557450 | 2976732.8 | 2976732.8 | N/A | N/A | 2976732.8 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3 | Construction of Non-Residential Building-Mlimani | Construction of Non-Residential Building-Mlimani | To construct Non-Residential Building-Mlimani | Non-Residential Building-Mlimani constructed | 3110299 | Construction of Buildings - Ot | HQ | HQ | -0.173672, 35.862823 | 4561 | OFFICE OF THE GOVENOR AND DEPUTY GOVERNOR | OFFICE OF THE GOVENOR AND DEPUTY GOVERNOR | N/A | 2021/22 | 2021/22 | 2021/22 | 288557450 | 21141422.3 | 21141422.3 | N/A | N/A | 21141422.3 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4 | Completion and equipping of Non-Residential Building-Milimani | Completion and equipping of Non-Residential Building-Milimani | To complete and equip Non-Residential Building-Milimani | Non-Residential Building-Milimani completed and equipped | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4561 | OFFICE OF THE GOVENOR AND DEPUTY GOVERNOR | OFFICE OF THE GOVENOR AND DEPUTY GOVERNOR | N/A | 2024/25 | 2024/25 | 2024/25 | 288557450 | 40467176 | 20467176 | N/A | N/A | 20467176 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | Yes | Done | Yes | Done | Yes | Done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
5 | Equipping of Non-Residential Building in Mlimani | Equipping of Non-Residential Building in Mlimani | To equip Non-Residential Building in Mlimani with necessary facilities and equipment | Non-Residential Building in Mlimani equipped | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4561 | OFFICE OF THE GOVENOR AND DEPUTY GOVERNOR | OFFICE OF THE GOVENOR AND DEPUTY GOVERNOR | N/A | 2022/23 | 2022/23 | 2022/23 | 50000000 | 0 | 50000000 | N/A | N/A | 50000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
6 | Completion of Non-Residential Building-Milimani – equipping | Completion of Non-Residential Building-Milimani – equipping | To complete Non-Residential Building-Milimani – equipping | Non-Residential Building-Milimani – equipping completed | 3110299 | Construction of Buildings - Ot | HQ | HQ | -0.173672, 35.862823 | 4561 | OFFICE OF THE GOVERNOR AND DEPUTY GOVERNOR | OFFICE OF THE GOVERNOR AND DEPUTY GOVERNOR | N/A | 2023/24 | 2023/24 | 2023/24 | 288557450 | 70467176 | 70467176 | N/A | N/A | 70467176 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | Yes | Done | Yes | Done | Yes | Done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
7 | Construction of Non-Residential Building-Mlimani | Construction of Non-Residential Building-Mlimani | To construct Non-Residential Building-Mlimani | Non-Residential Building-Mlimani constructed | 3110299 | Construction of Buildings - Ot | HQ | HQ | -0.173672, 35.862823 | 4561 | OFFICE OF THE GOVERNOR AND DEPUTY GOVERNOR | OFFICE OF THE GOVERNOR AND DEPUTY GOVERNOR | N/A | 2022/23 | 2022/23 | 2022/23 | 288557450 | 23432328.46 | 23432328.46 | N/A | N/A | 23432328.46 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
8 | Equipping of Non-Residential Building in Mlimani | Equipping of Non-Residential Building in Mlimani | To equip Non-Residential Building in Mlimani with necessary facilities and equipment | Non-Residential Building in Mlimani equipped | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4561 | OFFICE OF THE GOVERNOR AND DEPUTY GOVERNOR | OFFICE OF THE GOVERNOR AND DEPUTY GOVERNOR | N/A | 2022/23 | 2022/23 | 2022/23 | 50000000 | 50000000 | 50000000 | N/A | N/A | 50000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
9 | Construction of Nasha Market Sheds | Construction of Nasha Market Sheds | To construct Nasha Market Sheds | Nasha Market Sheds constructed | 2211314 | Write Offs/ Bad Debt Expenses from Previous Years (Pending Bills) | HQ | HQ | -0.173672, 35.862823 | 4562 | FINANCE AND ECONOMIC PLANNING | FINANCE AND ECONOMIC PLANNING | N/A | 2014/15 | 2014/15 | 2014/15 | 9614626 | 0 | 9614626.05 | N/A | N/A | 9614626.05 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
10 | County Debt Management (as per the County Medium Term Debt Management Strategy Paper) | County Debt Management (as per the County Medium Term Debt Management Strategy Paper) | To implement county debt management (as per the county medium term debt management strategy paper) for improved service delivery | County Debt Management (as per the County Medium Term Debt Management Strategy Paper) completed | 2211314 | Write Offs/ Bad Debt Expenses from Previous Years (Pending Bills) | HQ | HQ | -0.173672, 35.862823 | 4562 | FINANCE AND ECONOMIC PLANNING | FINANCE AND ECONOMIC PLANNING | N/A | 2020/21 | 2024/25 | 2024/25 | 275000000 | 962125231.82 | 940438342.82 | N/A | N/A | 940438342.82 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
11 | County Spatial Plan | County Spatial Plan | To implement county spatial plan for improved service delivery | County Spatial Plan completed | 2211314 | Write Offs/ Bad Debt Expenses from Previous Years (Pending Bills) | HQ | HQ | -0.173672, 35.862823 | 4562 | FINANCE AND ECONOMIC PLANNING | FINANCE AND ECONOMIC PLANNING | N/A | 2019/20 | 2019/20 | 2019/20 | 20000000 | 11885570.6 | 11885570.6 | N/A | N/A | 11885570.6 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
12 | Court decrees and ELRC rulings | Court decrees and ELRC rulings | To implement court decrees and elrc rulings for improved service delivery | Court decrees and ELRC rulings completed | 2211314 | Write Offs/ Bad Debt Expenses from Previous Years (Pending Bills) | HQ | HQ | -0.173672, 35.862823 | 4562 | FINANCE AND ECONOMIC PLANNING | FINANCE AND ECONOMIC PLANNING | N/A | 2024/25 | 2024/25 | 2024/25 | 13826872.68 | 0 | 13826872.68 | N/A | N/A | 13826872.68 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
13 | Court Decrees | Court Decrees | To implement court decrees for improved service delivery | Court Decrees completed | 2211314 | Write Offs/ Bad Debt Expenses from Previous Years (Pending Bills) | HQ | HQ | -0.173672, 35.862823 | 4562 | FINANCE AND ECONOMIC PLANNING | FINANCE AND ECONOMIC PLANNING | N/A | 2021/22 | 2021/22 | 2021/22 | 40168416 | 0 | 40168416 | N/A | N/A | 40168416 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
14 | KPLC debt resolution | KPLC debt resolution | To implement kplc debt resolution for improved service delivery | KPLC debt resolution completed | 2211314 | Write Offs/ Bad Debt Expenses from Previous Years (Pending Bills) | HQ | HQ | -0.173672, 35.862823 | 4562 | FINANCE AND ECONOMIC PLANNING | FINANCE AND ECONOMIC PLANNING | N/A | 2024/25 | 2024/25 | 2024/25 | 100000000 | 80000000 | 80000000 | N/A | N/A | 80000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
15 | Kenya Devolution Support Programme Level II | Kenya Devolution Support Programme Level II | To implement development programme activities under Kenya Devolution Support Programme Level II | Programme activities completed | 2630201 | N/A | HQ | HQ | -0.173672, 35.862823 | 4562 | FINANCE AND ECONOMIC PLANNING | FINANCE AND ECONOMIC PLANNING | N/A | 2019/20 | 2021/22 | 2021/22 | 120374189 | 448497694.82 | 0 | N/A | N/A | 0 | 466935367.7 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
16 | Construction of County Treasury Building | Construction of County Treasury Building | To construct County Treasury Building | County Treasury Building constructed | 3110299 | Construction of Buildings - Ot | HQ | HQ | -0.173672, 35.862823 | 4562 | FINANCE AND ECONOMIC PLANNING | FINANCE AND ECONOMIC PLANNING | N/A | 2024/25 | 2024/25 | 2024/25 | 1107500000 | 340129634 | 264194761.65 | N/A | N/A | 264194761.65 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | Yes | Done | Yes | Done | Yes | Done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
17 | Construction Of County Treasury Office Block | Construction Of County Treasury Office Block | To construct County Treasury Office Block | County Treasury Office Block constructed | 3110299 | Construction of Buildings - Ot | HQ | HQ | -0.173672, 35.862823 | 4562 | FINANCE AND ECONOMIC PLANNING | FINANCE AND ECONOMIC PLANNING | N/A | 2023/24 | 2023/24 | 2023/24 | 886000000 | 0 | 39545811.32 | N/A | N/A | 39545811.32 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | Yes | Done | Yes | Done | Yes | Done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
18 | Construction of County Treasury | Construction of County Treasury | To construct County Treasury | County Treasury constructed | 3110299 | Construction of Buildings - Ot | HQ | HQ | -0.173672, 35.862823 | 4562 | FINANCE AND ECONOMIC PLANNING | FINANCE AND ECONOMIC PLANNING | N/A | 2021/22 | 2022/23 | 2022/23 | 886000000 | 85999483.35 | 85999483.35 | N/A | N/A | 85999483.35 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | Yes | Done | Yes | Done | Yes | Done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
19 | Completion of refurbishment of Subcounty Office in Naivasha | Completion of refurbishment of Subcounty Office in Naivasha | To complete refurbishment of Subcounty Office in Naivasha | Refurbishment of Subcounty Office in Naivasha completed | 3110302 | Refurbishment of Non-Residential Buildings | HQ | HQ | -0.173672, 35.862823 | 4562 | FINANCE AND ECONOMIC PLANNING | FINANCE AND ECONOMIC PLANNING | N/A | 2023/24 | 2023/24 | 2023/24 | 18000000 | 14000000 | 14000000 | N/A | N/A | 14000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
20 | Refurbishment of Subcounty Office in Naivasha | Refurbishment of Subcounty Office in Naivasha | To implement refurbishment of subcounty office in naivasha for improved service delivery | Refurbishment of Subcounty Office in Naivasha completed | 3110302 | Refurbishment of Non-Residential Buildings | HQ | HQ | -0.173672, 35.862823 | 4562 | FINANCE AND ECONOMIC PLANNING | FINANCE AND ECONOMIC PLANNING | N/A | 2022/23 | 2022/23 | 2022/23 | 4000000 | 0 | 4000000 | N/A | N/A | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
21 | Renovation of Nakuru East Revenue Offices | Renovation of Nakuru East Revenue Offices | To rehabilitate Nakuru East Revenue Offices to restore functionality | Nakuru East Revenue Offices rehabilitated | 3110399 | Refurbishment of Buildgs - Oth | HQ | HQ | -0.173672, 35.862823 | 4562 | FINANCE AND ECONOMIC PLANNING | FINANCE AND ECONOMIC PLANNING | N/A | 2024/25 | 2024/25 | 2024/25 | 2800000 | 2800000 | 1000000 | N/A | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
22 | Completion of solarization of Revenue offices | Completion of solarization of Revenue offices | To complete solarization of Revenue offices | Solarization of Revenue offices completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4562 | FINANCE AND ECONOMIC PLANNING | FINANCE AND ECONOMIC PLANNING | N/A | 2024/25 | 2024/25 | 2024/25 | 15000000 | 10000000 | 5000000 | N/A | N/A | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
23 | Installation of backup Solar system at the New Town Hall Building and Public Works Building | Installation of backup Solar system at the New Town Hall Building and Public Works Building | To install backup Solar system at the New Town Hall Building and Public Works Building | Backup Solar system at the New Town Hall Building and Public Works Building installed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4562 | FINANCE AND ECONOMIC PLANNING | FINANCE AND ECONOMIC PLANNING | N/A | 2022/23 | 2022/23 | 2022/23 | 22565560 | 22565560 | 46435228 | N/A | N/A | 46435228 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
24 | Purchase and fabrication of Containers (2no.) For Bulk Filing for Accounts and Economic Planning | Purchase and fabrication of Containers (2no.) For Bulk Filing for Accounts and Economic Planning | To procure and fabrication of Containers (2no.) For Bulk Filing for Accounts and Economic Planning | And fabrication of Containers (2no.) For Bulk Filing for Accounts and Economic Planning procured | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4562 | FINANCE AND ECONOMIC PLANNING | FINANCE AND ECONOMIC PLANNING | N/A | 2023/24 | 2023/24 | 2023/24 | 1200000 | 0 | 3475000 | N/A | N/A | 3475000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
25 | Purchase of Alternative Power Supply (Solar Panels) for Powering of Revenue Server | Purchase of Alternative Power Supply (Solar Panels) for Powering of Revenue Server | To procure Alternative Power Supply (Solar Panels) for Powering of Revenue Server | Alternative Power Supply (Solar Panels) for Powering of Revenue Server procured | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4562 | FINANCE AND ECONOMIC PLANNING | FINANCE AND ECONOMIC PLANNING | N/A | 2021/22 | 2021/22 | 2021/22 | 1000000 | 0 | 1000000 | N/A | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
26 | Purchase Of Containers (4no.) to serve as Revenue Offices | Purchase Of Containers (4no.) to serve as Revenue Offices | To procure Containers (4no.) to serve as Revenue Offices | Containers (4no.) to serve as Revenue Offices procured | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4562 | FINANCE AND ECONOMIC PLANNING | FINANCE AND ECONOMIC PLANNING | N/A | 2024/25 | 2024/25 | 2024/25 | 5600000 | 2800000 | 2800000 | N/A | N/A | 2800000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
27 | Renovation of County Chambers | Renovation of County Chambers | To rehabilitate County Chambers to restore functionality | County Chambers rehabilitated | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4562 | FINANCE AND ECONOMIC PLANNING | FINANCE AND ECONOMIC PLANNING | N/A | 2020/21 | 2020/21 | 2020/21 | 8123205 | 2172550 | 2172550 | N/A | N/A | 2172550 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
28 | Renovation of Revenue Office at County Headquarters | Renovation of Revenue Office at County Headquarters | To rehabilitate Revenue Office at County Headquarters to restore functionality | Revenue Office at County Headquarters rehabilitated | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4562 | FINANCE AND ECONOMIC PLANNING | FINANCE AND ECONOMIC PLANNING | N/A | 2021/22 | 2021/22 | 2021/22 | 3800750 | 3800750 | 3800750 | N/A | N/A | 3800750 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
29 | Solarization of Revenue Offices | Solarization of Revenue Offices | To implement solarization of revenue offices for improved service delivery | Solarization of Revenue Offices completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4562 | FINANCE AND ECONOMIC PLANNING | FINANCE AND ECONOMIC PLANNING | N/A | 2023/24 | 2023/24 | 2023/24 | 5000000 | 0 | 1477200 | N/A | N/A | 1477200 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
30 | Acquisition of a Revenue System Server and 20KVA backup power supply | Acquisition of a Revenue System Server and 20KVA backup power supply | To procure a Revenue System Server and 20KVA backup power supply | A Revenue System Server and 20KVA backup power supply procured | 3111002 | Purchase of Computers, Printers and other IT Equipment | HQ | HQ | -0.173672, 35.862823 | 4562 | FINANCE AND ECONOMIC PLANNING | FINANCE AND ECONOMIC PLANNING | N/A | 2022/23 | 2022/23 | 2022/23 | 8560000 | 4280000 | 8780000 | N/A | N/A | 8780000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
31 | Acquisition Of ICT Equipment for Revenue Collection Gadgets | Acquisition Of ICT Equipment for Revenue Collection Gadgets | To procure ICT Equipment for Revenue Collection Gadgets | ICT Equipment for Revenue Collection Gadgets procured | 3111002 | Purchase of Computers, Printers and other IT Equipment | HQ | HQ | -0.173672, 35.862823 | 4562 | FINANCE AND ECONOMIC PLANNING | FINANCE AND ECONOMIC PLANNING | N/A | 2023/24 | 2023/24 | 2023/24 | 9700000 | 0 | 3433200 | N/A | N/A | 3433200 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
32 | Acquisition of ICT Equipment for Revenue Collection | Acquisition of ICT Equipment for Revenue Collection | To procure ICT Equipment for Revenue Collection | ICT Equipment for Revenue Collection procured | 3111002 | Purchase of Computers, Printers and other IT Equipment | HQ | HQ | -0.173672, 35.862823 | 4562 | FINANCE AND ECONOMIC PLANNING | FINANCE AND ECONOMIC PLANNING | N/A | 2024/25 | 2024/25 | 2024/25 | 10000000 | 10000000 | 10000000 | N/A | N/A | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
33 | Equipping of County Chambers | Equipping of County Chambers | To equip County Chambers with necessary facilities and equipment | County Chambers equipped | 3111099 | N/A | HQ | HQ | -0.173672, 35.862823 | 4562 | FINANCE AND ECONOMIC PLANNING | FINANCE AND ECONOMIC PLANNING | N/A | 2022/23 | 2022/23 | 2022/23 | 5000000 | 5000000 | 5000000 | N/A | N/A | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
34 | 4.3% Administrative Cost of Revenue Management System (Outstanding) | 4.3% Administrative Cost of Revenue Management System (Outstanding) | To implement 4.3% administrative cost of revenue management system (outstanding) for improved service delivery | 4.3% Administrative Cost of Revenue Management System (Outstanding) completed | 3111112 | Purchase of Software | HQ | HQ | -0.173672, 35.862823 | 4562 | FINANCE AND ECONOMIC PLANNING | FINANCE AND ECONOMIC PLANNING | N/A | 2022/23 | 2023/24 | 2023/24 | 81700000 | 80700000 | 81660273.29 | N/A | N/A | 81660273.29 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
35 | 4.3% Administrative Cost of Revenue Management System | 4.3% Administrative Cost of Revenue Management System | To implement 4.3% administrative cost of revenue management system for improved service delivery | 4.3% Administrative Cost of Revenue Management System completed | 3111112 | Purchase of Software | HQ | HQ | -0.173672, 35.862823 | 4562 | FINANCE AND ECONOMIC PLANNING | FINANCE AND ECONOMIC PLANNING | N/A | 2021/22 | 2024/25 | 2024/25 | 74400000 | 109400000 | 98400000 | N/A | N/A | 98400000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
36 | Acquisition of a fleet management system | Acquisition of a fleet management system | To procure a fleet management system | A fleet management system procured | 3111112 | Purchase of Software | HQ | HQ | -0.173672, 35.862823 | 4562 | FINANCE AND ECONOMIC PLANNING | FINANCE AND ECONOMIC PLANNING | N/A | 2022/23 | 2022/23 | 2022/23 | 8500000 | 8500000 | 13500000 | N/A | N/A | 13500000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
37 | Acquisition of Audit Management Software | Acquisition of Audit Management Software | To procure Audit Management Software | Audit Management Software procured | 3111112 | Purchase of Software | HQ | HQ | -0.173672, 35.862823 | 4562 | FINANCE AND ECONOMIC PLANNING | FINANCE AND ECONOMIC PLANNING | N/A | 2022/23 | 2022/23 | 2022/23 | 10000000 | 10000000 | 10000000 | N/A | N/A | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
38 | Development and Implementation of Revenue System (4.3% admin) | Development and Implementation of Revenue System (4.3% admin) | To implement development and implementation of revenue system (4.3% admin) for improved service delivery | Development and Implementation of Revenue System (4.3% admin) completed | 3111112 | Purchase of Software | HQ | HQ | -0.173672, 35.862823 | 4562 | FINANCE AND ECONOMIC PLANNING | FINANCE AND ECONOMIC PLANNING | N/A | 2022/23 | 2022/23 | 2022/23 | 85140000 | 70140000 | 70140000 | N/A | N/A | 70140000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
39 | Development and Implementation of Revenue System (Phase II) | Development and Implementation of Revenue System (Phase II) | To implement development and implementation of revenue system (phase ii) for improved service delivery | Development and Implementation of Revenue System (Phase II) completed | 3111112 | Purchase of Software | HQ | HQ | -0.173672, 35.862823 | 4562 | FINANCE AND ECONOMIC PLANNING | FINANCE AND ECONOMIC PLANNING | N/A | 2021/22 | 2021/22 | 2021/22 | 25000000 | 25000000 | 25000000 | N/A | N/A | 25000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
40 | Development of an Inventory management system | Development of an Inventory management system | To develop an Inventory management system | An Inventory management system developed | 3111112 | Purchase of Software | HQ | HQ | -0.173672, 35.862823 | 4562 | FINANCE AND ECONOMIC PLANNING | FINANCE AND ECONOMIC PLANNING | N/A | 2022/23 | 2022/23 | 2022/23 | 4000000 | 0 | 1316900 | N/A | N/A | 1316900 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
41 | Development Of Asset Management System | Development Of Asset Management System | To develop Asset Management System | Asset Management System developed | 3111112 | Purchase of Software | HQ | HQ | -0.173672, 35.862823 | 4562 | FINANCE AND ECONOMIC PLANNING | FINANCE AND ECONOMIC PLANNING | N/A | 2021/22 | 2023/24 | 2023/24 | 15000000 | 10000000 | 15000000 | N/A | N/A | 15000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
42 | Fleet Management System | Fleet Management System | To implement fleet management system for improved service delivery | Fleet Management System completed | 3111112 | Purchase of Software | HQ | HQ | -0.173672, 35.862823 | 4562 | FINANCE AND ECONOMIC PLANNING | FINANCE AND ECONOMIC PLANNING | N/A | 2023/24 | 2023/24 | 2023/24 | 10000000 | 0 | 9399999.55 | N/A | N/A | 9399999.55 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
43 | Maintenance of Project Implementation Management System | Maintenance of Project Implementation Management System | To implement maintenance of project implementation management system for improved service delivery | Maintenance of Project Implementation Management System completed | 3111112 | Purchase of Software | HQ | HQ | -0.173672, 35.862823 | 4562 | FINANCE AND ECONOMIC PLANNING | FINANCE AND ECONOMIC PLANNING | N/A | 2021/22 | 2021/22 | 2021/22 | 1200000 | 1200000 | 1200000 | N/A | N/A | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
44 | Completion and operationalization of valuation roll | Completion and operationalization of valuation roll | To complete and operationalization of valuation roll | And operationalization of valuation roll completed | 3111499 | Research & Feasibility Studies | HQ | HQ | -0.173672, 35.862823 | 4562 | FINANCE AND ECONOMIC PLANNING | FINANCE AND ECONOMIC PLANNING | N/A | 2023/24 | 2023/24 | 2023/24 | 10000000 | 0 | 5000000 | N/A | N/A | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
45 | Valuation Of Assets | Valuation Of Assets | To implement valuation of assets for improved service delivery | Valuation Of Assets completed | 3111499 | Research & Feasibility Studies | HQ | HQ | -0.173672, 35.862823 | 4562 | FINANCE AND ECONOMIC PLANNING | FINANCE AND ECONOMIC PLANNING | N/A | 2023/24 | 2023/24 | 2023/24 | 20000000 | 0 | 5000000 | N/A | N/A | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
46 | Reroofing of Office, Installation of metal grills and Refurbishment of offices | Reroofing of Office, Installation of metal grills and Refurbishment of offices | To implement reroofing of office, installation of metal grills and refurbishment of offices for improved service delivery | Reroofing of Office, Installation of metal grills and Refurbishment of offices completed | 3110399 | Refurbishment of Buildgs - Oth | HQ | HQ | -0.173672, 35.862823 | 4563 | COUNTY PUBLIC SERVICE BOARD | COUNTY PUBLIC SERVICE BOARD | N/A | 2020/21 | 2020/21 | 2020/21 | 5177144 | 5177144 | 5177144 | N/A | N/A | 5177144 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
47 | Installation of CCTV cameras at the Board Offices | Installation of CCTV cameras at the Board Offices | To install CCTV cameras at the Board Offices | CCTV cameras at the Board Offices installed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4563 | COUNTY PUBLIC SERVICE BOARD | COUNTY PUBLIC SERVICE BOARD | N/A | 2024/25 | 2024/25 | 2024/25 | 2000000 | 2000000 | 2000000 | N/A | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
48 | Installation of grills on doors and windows | Installation of grills on doors and windows | To install grills on doors and windows | Grills on doors and windows installed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4563 | COUNTY PUBLIC SERVICE BOARD | COUNTY PUBLIC SERVICE BOARD | N/A | 2021/22 | 2021/22 | 2021/22 | 1000000 | 821556 | 821556 | N/A | N/A | 821556 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
49 | Setup Video conferencing and automation of Offices | Setup Video conferencing and automation of Offices | To implement setup video conferencing and automation of offices for improved service delivery | Setup Video conferencing and automation of Offices completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4563 | COUNTY PUBLIC SERVICE BOARD | COUNTY PUBLIC SERVICE BOARD | N/A | 2021/22 | 2023/24 | 2023/24 | 4000000 | 6500000 | 6500000 | N/A | N/A | 6500000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
50 | Development of Online Application Platform | Development of Online Application Platform | To develop Online Application Platform | Online Application Platform developed | 3111112 | Purchase of Software | HQ | HQ | -0.173672, 35.862823 | 4563 | COUNTY PUBLIC SERVICE BOARD | COUNTY PUBLIC SERVICE BOARD | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1500000 | 1500000 | N/A | N/A | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
51 | Preventive and Promotive Health Services | Health Outstanding Contract Retention - development | To implement health outstanding contract retention - development for access to quality healthcare services | Health Outstanding Contract Retention - development completed | 2211314 | Write Offs/ Bad Debt Expenses from Previous Years (Pending Bills) | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | N/A | 10341099.05 | 10341099.05 | 10341099.05 | N/A | N/A | 10341099.05 | 0 | 5926796 | 57.3 | 5926796 | 0 | 4414303.05 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
52 | Health Curative and Rehabilitative Services | Conditional Fund for Leasing of Medical Equipment | To implement conditional fund for leasing of medical equipment for access to quality healthcare services | Conditional Fund for Leasing of Medical Equipment completed | 2630201 | N/A | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2023/24 | 2023/24 | 124723404 | 388659574 | 0 | Grant | Grant | 0 | 388659574 | 124723404 | 32.1 | 124723404 | 0 | 263936170 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
53 | Preventive and Promotive Health Services | Counterpart funding - DANIDA | To implement counterpart funding - danida for access to quality healthcare services | Counterpart funding - DANIDA completed | 2630201 | N/A | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2024/25 | N/A | 17874000 | 56023809 | 56023809 | Equitable | N/A | 56023809 | 0 | 14895000 | 26.6 | 14895000 | 822309 | 41128809 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
54 | Preventive and Promotive Health Services | DANIDA Capital Transfers to Health Centres and Dispensaries | To implement danida capital transfers to health centres and dispensaries for access to quality healthcare services | DANIDA Capital Transfers to Health Centres and Dispensaries completed | 2630201 | N/A | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2023/24 | N/A | 19115250 | 132047582 | 0 | Grant | Grant | 0 | 163603351 | 20068710 | 15.2 | 20068710 | 19115250 | 111978872 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
55 | Preventive and Promotive Health Services | Nutrition International Grant | To implement nutrition international grant for access to quality healthcare services | Nutrition International Grant completed | 2630201 | N/A | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2022/23 | N/A | 15000000 | 31812691.05 | 0 | Grant | Grant | 0 | 31812691.05 | 1831759 | 5.8 | 1831759 | 1831759 | 29980932.05 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
56 | Preventive and Promotive Health Services | Nutrition International | To implement nutrition international for access to quality healthcare services | Nutrition International completed | 2630201 | N/A | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | N/A | 10000000 | 25000000 | 0 | Grant | Grant | 0 | 29810236.4 | 3482613 | 13.9 | 3482613 | 12310236 | 21517387 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
57 | Preventive and Promotive Health Services | World Bank Transforming Health Systems for Universal Care (THS-UC) | To implement development programme activities under World Bank Transforming Health Systems for Universal Care (THS-UC) | Programme activities completed | 2630201 | N/A | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2018/19 | 2021/22 | 2021/22 | 79792976 | 181400416.9 | 0 | Grant | Grant | 0 | 181463252.1 | 79342370 | 43.7 | 79342370 | 62835 | 102058046.9 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
58 | Preventive and Promotive Health Services | Rehabilitation of Kabatini health centre (painting works) | To rehabilitate Kabatini health centre (painting works) to restore functionality | Kabatini health centre (painting works) rehabilitated | 3110101 | N/A | Bahati | Kabatini | -0.213417 36.162894 2030.4000244140625 14.807999610900879 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 399350 | 79.9 | 399350 | 500000 | 100650 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Kundoki. Assessor remarks: Partially in good condition.
59 | Preventive and Promotive Health Services | Completion of youth friendly center at Rhonda clinic | To complete youth friendly center at Rhonda clinic | Youth friendly center at Rhonda clinic completed | 3110101 | N/A | Nakuru West | Kaptembwo | -0.304752, 36.055188 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 1999530 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999530 | 100 | 1999530 | 2000000 | 470 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: It met the needs of the residents. Contractor: PEZINA ENTERPRISES. Assessor remarks: Complete but has defective tiles needs renovation.
60 | Preventive and Promotive Health Services | Equipping of youth friendly center at Rhonda clinic | To equip youth friendly center at Rhonda clinic with necessary facilities and equipment | Youth friendly center at Rhonda clinic equipped | 3110101 | N/A | Nakuru West | Kaptembwo | -0.304752, 36.055188 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: It met the needs of the residents. Contractor: PEZINA ENTERPRISES. Assessor remarks: Complete but has defective tiles needs renovation.
61 | Preventive and Promotive Health Services | Construction of Echariria dispensary staff house (one unit) | To construct Echariria dispensary staff house (one unit) | Echariria dispensary staff house (one unit) constructed | 3110201 | Residential Buildings (including hostels) | Gilgil | Eburru/Mbaruk | -0.333685, 36.188753 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | N/A | 1500000 | 0 | 1418170 | Equitable | Ward Fund | 1418170 | 0 | 2858181 | 0 | 2858181 | 1488170 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: It was not met. Viable: It was viable project, if it would have started.. Assessor remarks: No value for money.
62 | Preventive and Promotive Health Services | Construction of staff quarters at Silibwet Dispensary | To construct staff quarters at Silibwet Dispensary | Staff quarters at Silibwet Dispensary constructed | 3110201 | Residential Buildings (including hostels) | Kuresoi South | Keringet | -0.514258, 35.717688 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | 2025 | 2000000 | 0 | 1794270 | Equitable | Ward Fund | 1794270 | 0 | 250000 | 0 | 250000 | 1794270 | 0 | Stalled | 25 | N/A | Intent to terminate issued | 2022 | N/A | N/A | Yes | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Stalled.
63 | Preventive and Promotive Health Services | Construction of Ndabibi Health Centre staff quarters | To construct Ndabibi Health Centre staff quarters | Ndabibi Health Centre staff quarters constructed | 3110201 | Residential Buildings (including hostels) | Naivasha | Maiella | -0.832803 36.203925 1761.6 19.399999618530273 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | 2021/22 | 3500000 | 1216775.6 | 1216775.6 | Equitable | Ward Fund | 1216775.6 | 0 | 978678 | 80.4 | 978678 | 238098 | 238097.6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Maintenance Required.
64 | Preventive and Promotive Health Services | Construction Of Staff Houses at Munyu Dispensary | To construct Staff Houses at Munyu Dispensary | Staff Houses at Munyu Dispensary constructed | 3110201 | Residential Buildings (including hostels) | Naivasha | Naivasha East | -0.827971 36.535905 2475 6.122000217437744 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | N/A | 1594529 | 0 | 1554529 | Equitable | Ward Fund | 1554529 | 0 | 955255 | 0 | 955255 | 1594529 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes. Assessor remarks: Project not uet started.
65 | Preventive and Promotive Health Services | Completion and equipping of Sinendet dispensary | To complete and equip Sinendet dispensary | Sinendet dispensary completed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Amalo | -0.676255 35.657373 2458.322998046875 8.564000129699707 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2017/18 | 2017/18 | 2017/18 | 1000000 | 230 | 230 | Equitable | N/A | 230 | 0 | 999770 | 434682.6 | 999770 | 230 | -999540 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: done.
66 | Preventive and Promotive Health Services | Purchase and installation and commissioning of a digital X-Ray machine for Bahati Sub-County hospital | To procure and install and commissioning of a digital X-Ray machine for Bahati Sub-County hospital | And commissioning of a digital X-Ray machine for Bahati Sub-County hospital procured and installed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Bahati | Bahati | -0.170153, 36.123563 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 5000000 | 5000000 | 5000000 | Equitable | Ward Fund | 5000000 | 0 | 4913793 | 98.3 | 4913793 | 86207 | 86207 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Oultral sound machine. Viable: Yes. Assessor remarks: In good working conditions.
67 | Preventive and Promotive Health Services | Construction of an outpatient Unit at Mwariki Health Centre and installation of electricity | To construct an outpatient Unit at Mwariki Health Centre and installation of electricity | An outpatient Unit at Mwariki Health Centre and installation of electricity constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | Barut | -0.349277, 36.055207 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2022 | 3000000 | 64320 | 64320 | Equitable | N/A | 64320 | 0 | 2935680 | 4564.2 | 2935680 | 64320 | -2871360 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Well completed.
68 | Preventive and Promotive Health Services | Constructtion of chain link fence and a gate at Kigonor Dispensary | To implement constructtion of chain link fence and a gate at kigonor dispensary for access to quality healthcare services | Constructtion of chain link fence and a gate at Kigonor Dispensary completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | Barut | -0.324324 36.054632 0 2000 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | N/A | 2000000 | 0 | 2000000 | Equitable | Ward Fund | 2000000 | 0 | 520384 | 0 | 520384 | 118749 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Lemyna works co ltd. Assessor remarks: The fence is good.
69 | Preventive and Promotive Health Services | Constructtion of Perimeter wall at Kigonor Dispensary | To implement constructtion of perimeter wall at kigonor dispensary for access to quality healthcare services | Constructtion of Perimeter wall at Kigonor Dispensary completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | Barut | -0.327111 36.05619 1770.5999755859375 87.5999984741211 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | N/A | 2000000 | 2000000 | 2000000 | Equitable | Ward Fund | 2000000 | 0 | 2622935 | 131.1 | 2622935 | 2000000 | -622935 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: No contractor. Assessor remarks: Project was done.
70 | Preventive and Promotive Health Services | Renovation of Barut Dispensary | To rehabilitate Barut Dispensary to restore functionality | Barut Dispensary rehabilitated | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | Barut | -0.327064 36.056176 1770 43.60900115966797 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | 2021/22 | 300000 | 44108.35 | 44108.35 | Equitable | N/A | 44108.35 | 0 | 29957 | 67.9 | 29957 | 44108 | 14151.35 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Foresight commecial services. Assessor remarks: Equipment are operational.
71 | Preventive and Promotive Health Services | completion of mugwathi Githioro dispensary | To complete mugwathi Githioro dispensary | Mugwathi Githioro dispensary completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Bahati | Dundori | -0.273842, 36.200992 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/2019 | 20000000 | 1508138 | 1508138 | Equitable | Ward Fund | 1508138 | 0 | 1508138 | 100 | 1508138 | 1508138 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Sanka builders and decorators. Assessor remarks: Good condition.
72 | Preventive and Promotive Health Services | Construction of Giachonge Dispensary (outpatient and toilet) | To construct Giachonge Dispensary (outpatient and toilet) | Giachonge Dispensary (outpatient and toilet) constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Bahati | Dundori | -0.237126, 36.167582 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2023/2024 | 4000000 | 0 | 1135128.5 | Equitable | Ward Fund | 1135128.5 | 0 | 2845463 | 0 | 2845463 | 1135129 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
73 | Preventive and Promotive Health Services | Construction of Githioro dispensary | To construct Githioro dispensary | Githioro dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Bahati | Dundori | -0.273677, 36.201615 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2017/18 | 2017/18 | 2017/2018 | 10000000 | 1751092 | 1751092 | Equitable | N/A | 1751092 | 0 | 8096028 | 462.3 | 8096028 | 1751092 | -6344936 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Sanka builders and decorators. Assessor remarks: Good.
74 | Preventive and Promotive Health Services | Construction of MCH at Kiwamu Health Centre | To construct MCH at Kiwamu Health Centre | MCH at Kiwamu Health Centre constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Bahati | Dundori | -0.237345, 36.167237 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2015/16 | 2015/16 | 2015/2016 | 6000000 | 1288167.9 | 1288167.9 | Equitable | Ward Fund | 1288167.9 | 0 | 4203337 | 326.3 | 4203337 | 1288168 | -2915169.1 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
75 | Preventive and Promotive Health Services | Construction of Kasambara dispensary | To construct Kasambara dispensary | Kasambara dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Eburru/Mbaruk | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | 2021/22 | 3000000 | 2999900 | 2999900 | Equitable | N/A | 2999900 | 0 | 2858181 | 95.3 | 2858181 | 2999900 | 141719 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
76 | Preventive and Promotive Health Services | Completion of Elburgon Subcounty hospital | To complete Elburgon Subcounty hospital | Elburgon Subcounty hospital completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Elburgon | -0.305934, 35.80787 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | - | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 4013329 | 100.3 | 4013329 | 6600000 | -13329 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: -project in good condition-.
77 | Preventive and Promotive Health Services | Completion works at Kasarani Dispensary | To complete works at Kasarani Dispensary | Works at Kasarani Dispensary completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Elburgon | -0.272217 35.816592 2382.3 13.600000381469727 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | N/A | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
78 | Preventive and Promotive Health Services | Construction of Kapsita Dispensary | To construct Kapsita Dispensary | Kapsita Dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Elburgon | -0.294954 35.766447 0 2799.9990234375 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2016/17 | 2016/17 | N/A | 2000000 | 2000000 | 2000000 | Equitable | Ward Fund | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
79 | Preventive and Promotive Health Services | Construction of Ndimu Dispensary | To construct Ndimu Dispensary | Ndimu Dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Elburgon | -0.279925 35.765083 0 2299.9990234375 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | N/A | 4500000 | 0 | 4500000 | Equitable | Ward Fund | 4500000 | 0 | 515700 | 0 | 515700 | 2000000 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: Pikverd supplies. Assessor remarks: Ongoing well.
80 | Preventive and Promotive Health Services | Construction Of Kikopey Dispensary (Lab) | To construct Kikopey Dispensary (Lab) | Kikopey Dispensary (Lab) constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Gilgil | -0.48148, 36.291843 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | N/A | 3000000 | 0 | 3000000 | Equitable | Ward Fund | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not yet strated. Viable: Not yet started. Assessor remarks: Not yet strated, there is need for construction of an incinerator, open burning of medical waste observed, there is need for construction of a storage facility,.
81 | Preventive and Promotive Health Services | Renovation of post theater ward at Gilgil sub county hospital | To rehabilitate post theater ward at Gilgil sub county hospital to restore functionality | Post theater ward at Gilgil sub county hospital rehabilitated | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Gilgil | -0.504913, 36.322796 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 530 | 530 | Equitable | N/A | 530 | 0 | 1999470 | 377258.5 | 1999470 | 530 | -1998940 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Mbiwa construction limited. Assessor remarks: In good state.
82 | Health Curative and Rehabilitative Services | Completion of a surgical ward at Olenguruone Hospital | To complete a surgical ward at Olenguruone Hospital | A surgical ward at Olenguruone Hospital completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 2023/24 | 6000000 | 0 | 6000000 | N/A | N/A | 6000000 | 0 | 750000 | 100 | 750000 | 0 | -750000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
83 | Health Curative and Rehabilitative Services | Completion of Elburgon Subcounty hospital | To complete Elburgon Subcounty hospital | Elburgon Subcounty hospital completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2023/24 | 2023/24 | 10600000 | 14600000 | 25200000 | N/A | N/A | 25200000 | 0 | 750000 | 5.1 | 750000 | 0 | 13850000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
84 | Preventive and Promotive Health Services | Completion of Gilgil Maternity | To complete Gilgil Maternity | Gilgil Maternity completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | N/A | 700000 | 0 | 700000 | Equitable | N/A | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
85 | Health Curative and Rehabilitative Services | Completion of ICU/HDU unit in Naivasha Sub County Hospital | To complete ICU/HDU unit in Naivasha Sub County Hospital | ICU/HDU unit in Naivasha Sub County Hospital completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | 2021/22 | 15000000 | 0 | 8553468 | N/A | N/A | 8553468 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
86 | Preventive and Promotive Health Services | Completion of Maai Mahiu Hospital | To complete Maai Mahiu Hospital | Maai Mahiu Hospital completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | N/A | 44951418 | 0 | 44951418 | Equitable | N/A | 44951418 | 0 | 750000 | 100 | 750000 | 0 | -750000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
87 | Health Curative and Rehabilitative Services | Completion of outpatient block at Elburgon Sub Sounty hospital | To complete outpatient block at Elburgon Sub Sounty hospital | Outpatient block at Elburgon Sub Sounty hospital completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2020/21 | 2020/21 | N/A | 38075070 | 0 | 2187912.05 | N/A | N/A | 2187912.05 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
88 | Preventive and Promotive Health Services | Completion of Outpatients complex (PGH) | To complete Outpatients complex (PGH) | Outpatients complex (PGH) completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | N/A | 760879085 | 0 | 769747.45 | Equitable | N/A | 769747.45 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
89 | Preventive and Promotive Health Services | Completion of Subukia Hospital | To complete Subukia Hospital | Subukia Hospital completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | N/A | 52000000 | 0 | 52000000 | Equitable | N/A | 52000000 | 0 | 750000 | 100 | 750000 | 0 | -750000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
90 | Preventive and Promotive Health Services | Completion, Refurbishment and Expansion of Kabazi Level 4 Hospital | To implement completion, refurbishment and expansion of kabazi level 4 hospital for access to quality healthcare services | Completion, Refurbishment and Expansion of Kabazi Level 4 Hospital completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | N/A | 15500000 | 14842350 | 14842350 | Equitable | N/A | 14842350 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
91 | Preventive and Promotive Health Services | Construction and equipping of laboratory and and connection to power Simboiyon health centre in Waseges Ward | To construct and equip laboratory and and connection to power Simboiyon health centre in Waseges Ward | Laboratory and and connection to power Simboiyon health centre in Waseges Ward constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2016/17 | 2016/17 | N/A | 700000 | 699850 | 699850 | Equitable | N/A | 699850 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
92 | Health Curative and Rehabilitative Services | Construction of a Level IV Hospital in Kuresoi North Sub County Phase II | To construct a Level IV Hospital in Kuresoi North Sub County Phase II | A Level IV Hospital in Kuresoi North Sub County Phase II constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | 2024/25 | 75000000 | 50000000 | 20000000 | N/A | N/A | 20000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
93 | Preventive and Promotive Health Services | Construction of a Level IV Hospital in Kuresoi North Sub County | To construct a Level IV Hospital in Kuresoi North Sub County | A Level IV Hospital in Kuresoi North Sub County constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | N/A | 250000000 | 0 | 50000000 | Equitable | N/A | 50000000 | 0 | 750000 | 100 | 750000 | 0 | -750000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
94 | Health Curative and Rehabilitative Services | Construction of a Level IV Hospital in Rongai Sub County Phase II | To construct a Level IV Hospital in Rongai Sub County Phase II | A Level IV Hospital in Rongai Sub County Phase II constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | 2024/25 | 75000000 | 50000000 | 20000000 | N/A | N/A | 20000000 | 0 | 750000 | 1.5 | 750000 | 0 | 49250000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
95 | Preventive and Promotive Health Services | Construction of a Level IV Hospital in Rongai Sub County | To construct a Level IV Hospital in Rongai Sub County | A Level IV Hospital in Rongai Sub County constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | N/A | 250000000 | 0 | 50000000 | Equitable | N/A | 50000000 | 0 | 750000 | 100 | 750000 | 0 | -750000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
96 | Health Curative and Rehabilitative Services | Construction of Buildings - (FIF Facilities) | To construct Buildings - (FIF Facilities) | Buildings - (FIF Facilities) constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2022/23 | N/A | 30000000 | 30000000 | 0 | FIF | N/A | 0 | 30000000 | 3956192 | 13.2 | 3956192 | 26043808 | 26043808 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
97 | Health Curative and Rehabilitative Services | Construction of Buildings - (FIF) | To construct Buildings - (FIF) | Buildings - (FIF) constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | N/A | 175000000 | 175000000 | 0 | FIF | N/A | 0 | 175000000 | 3321916 | 1.9 | 3321916 | 26043808 | 171678084 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
98 | Health Curative and Rehabilitative Services | Construction of buildings - Inpatient complex - PGH (FIF) | To construct buildings - Inpatient complex - PGH (FIF) | Buildings - Inpatient complex - PGH (FIF) constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | N/A | 600000000 | 80000000 | 0 | FIF | FIF | 0 | 260000000 | 3321916 | 4.2 | 3321916 | 26043808 | 76678084 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
99 | Health Curative and Rehabilitative Services | Construction of buildings - Outpatients complex (PGH) | To construct buildings - Outpatients complex (PGH) | Buildings - Outpatients complex (PGH) constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2020/21 | 2020/21 | N/A | 599890644 | 634154 | 0 | N/A | N/A | 0 | 634154 | 3956192 | 623.9 | 3956192 | 26043808 | -3322038 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
100 | Health Curative and Rehabilitative Services | Construction of inpatient / outpatient block at Elementaita hospital | To construct inpatient / outpatient block at Elementaita hospital | Inpatient / outpatient block at Elementaita hospital constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | 2021/22 | 30000000 | 30000000 | 20000000 | N/A | N/A | 20000000 | 0 | 750000 | 2.5 | 750000 | 0 | 29250000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
101 | Preventive and Promotive Health Services | Construction of Lare Health Centre | To construct Lare Health Centre | Lare Health Centre constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | N/A | 7000000 | 6858950 | 6858950 | Equitable | N/A | 6858950 | 0 | 750000 | 10.9 | 750000 | 0 | 6108950 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
102 | Preventive and Promotive Health Services | Construction of Level 4 Hospital in Maai Mahiu | To construct Level 4 Hospital in Maai Mahiu | Level 4 Hospital in Maai Mahiu constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | N/A | 154528397 | 3436599.16 | 0 | Equitable | N/A | 0 | 3436599.16 | 750000 | 21.8 | 750000 | 0 | 2686599.16 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
103 | Health Curative and Rehabilitative Services | Construction of maternity and equipping of Menengai Crater Dispensary | To construct maternity and equipping of Menengai Crater Dispensary | Maternity and equipping of Menengai Crater Dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | N/A | 10000000 | 10000000 | 5000000 | N/A | N/A | 5000000 | 0 | 0 | 0 | 0 | 9890259 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
104 | Preventive and Promotive Health Services | Construction of Maternity at Gilgil sub county Hospital | To construct Maternity at Gilgil sub county Hospital | Maternity at Gilgil sub county Hospital constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | 2021/22 | 50000000 | 4284697 | 4284697 | Equitable | N/A | 4284697 | 0 | 750000 | 17.5 | 750000 | 0 | 3534697 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
105 | Preventive and Promotive Health Services | Construction of Maternity at Gilgil subcounty Hospital | To construct Maternity at Gilgil subcounty Hospital | Maternity at Gilgil subcounty Hospital constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 36737200 | 3206219.5 | 0 | Equitable | N/A | 0 | 3206219.5 | 750000 | 23.4 | 750000 | 0 | 2456219.5 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
106 | Preventive and Promotive Health Services | Construction of Mauche Hospital | To construct Mauche Hospital | Mauche Hospital constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | N/A | 10000000 | 0 | 10000000 | Equitable | N/A | 10000000 | 0 | 750000 | 100 | 750000 | 9890259 | -750000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
107 | Health Curative and Rehabilitative Services | Construction of Mithonge dispensary | To construct Mithonge dispensary | Mithonge dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | N/A | 10000000 | 9890259 | 9890259 | N/A | N/A | 9890259 | 0 | 3321916 | 33.6 | 3321916 | 9890259 | 6568343 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
108 | Health Curative and Rehabilitative Services | Construction of Nagum dispensary | To construct Nagum dispensary | Nagum dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | N/A | 5000000 | 5000000 | 5000000 | N/A | N/A | 5000000 | 0 | 3321916 | 66.4 | 3321916 | 9890259 | 1678084 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
109 | Health Curative and Rehabilitative Services | Construction of Njoro Level 4 Hospital | To construct Njoro Level 4 Hospital | Njoro Level 4 Hospital constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2023/24 | N/A | 148902024 | 116832249.95 | 174737599.05 | N/A | N/A | 174737599.05 | 0 | 750000 | 0.6 | 750000 | 9890259 | 116082249.95 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
110 | Health Curative and Rehabilitative Services | Construction of OPD at Olenguruone Sub County Hospital | To construct OPD at Olenguruone Sub County Hospital | OPD at Olenguruone Sub County Hospital constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | N/A | 100000000 | 14157885 | 33568285 | N/A | N/A | 33568285 | 0 | 750000 | 5.3 | 750000 | 0 | 13407885 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
111 | Health Curative and Rehabilitative Services | Construction of OPD at Sirikwa Health Centre | To construct OPD at Sirikwa Health Centre | OPD at Sirikwa Health Centre constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | N/A | 15000000 | 15000000 | 15000000 | N/A | N/A | 15000000 | 0 | 750000 | 5 | 750000 | 9890259 | 14250000 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
112 | Health Curative and Rehabilitative Services | Construction of Subukia District Hospital | To construct Subukia District Hospital | Subukia District Hospital constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | 2021/22 | 25000000 | 25000000 | 10000000 | N/A | N/A | 10000000 | 0 | 750000 | 3 | 750000 | 26043808 | 24250000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
113 | Preventive and Promotive Health Services | Construction of Upper Solai hospital | To construct Upper Solai hospital | Upper Solai hospital constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | N/A | 30000000 | 30000000 | 15000000 | Equitable | N/A | 15000000 | 0 | 750000 | 2.5 | 750000 | 26043808 | 29250000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
114 | Preventive and Promotive Health Services | Expansion and rehabilition of Langalanga Sub County hospital | To expand and rehabilition of Langalanga Sub County hospital to increase capacity | And rehabilition of Langalanga Sub County hospital expanded | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | N/A | 30000000 | 11900000 | 11900000 | Equitable | N/A | 11900000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
115 | Preventive and Promotive Health Services | Purchase of land and Construction of a Level IV Hospital in Kuresoi North Sub County | To acquire land and construct a Level IV Hospital in Kuresoi North Sub County | Land acquired and a Level IV Hospital in Kuresoi North Sub County constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | N/A | 250000000 | 50000000 | 50000000 | Equitable | N/A | 50000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
116 | Preventive and Promotive Health Services | Upgrading of Molo Sub County Hospital | To upgrade Molo Sub County Hospital through tarmacking for improved road connectivity | Molo Sub County Hospital tarmacked and upgraded | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2022/23 | N/A | 150095777 | 208197197.35 | 272445648.25 | Equitable | N/A | 272445648.25 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
117 | Preventive and Promotive Health Services | Construction of Dispensary Mwiciringiri in Hells Gate Ward | To construct Dispensary Mwiciringiri in Hells Gate Ward | Dispensary Mwiciringiri in Hells Gate Ward constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Hells Gate | -0.807183, 36.509336 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | N/A | 6000000 | 0 | 417410.7 | Equitable | Ward Fund | 417410.7 | 0 | 2359547 | 0 | 2359547 | 417411 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: MERICH INTERNATIONAL LIMITED. Assessor remarks: The project was completed in 2023.
118 | Preventive and Promotive Health Services | Rehabilitation of Karagita dispensary | To rehabilitate Karagita dispensary to restore functionality | Karagita dispensary rehabilitated | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Hells Gate | -0.77672, 36.431946 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | N/A | 1400000 | 0 | 1400000 | Equitable | Ward Fund | 1400000 | 0 | 445750 | 0 | 445750 | 1400000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: The project Will be done at a cost of 1,400,000.
119 | Preventive and Promotive Health Services | Renovation And Equipping of Ruguru Dispensary Maternity | To rehabilitate Equipping of Ruguru Dispensary Maternity to restore functionality | Equipping of Ruguru Dispensary Maternity rehabilitated | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Bahati | Kabatini | -0.165201, 36.177493 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | N/A | 2500000 | 1436780 | 2500000 | Equitable | Ward Fund | 2500000 | 0 | 1999991 | 139.2 | 1999991 | 2500000 | -563211 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: No yet. Viable: Yes. Assessor remarks: It's ongoing at 70% renovation done , Equipping not yet done.
120 | Preventive and Promotive Health Services | Proposed Construction of Rironi Health centre | To undertake the proposed Construction of Rironi Health centre | Proposed Construction of Rironi Health centre implemented | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Kamara | -0.1811, 35.712733 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 3200000 | 271597 | 271597 | Equitable | N/A | 271597 | 0 | 1766373 | 650.4 | 1766373 | 271597 | -1494776 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes but it didn't meet the needs. Contractor: Unknown. Assessor remarks: Project needs to be completed operationalised.
121 | Preventive and Promotive Health Services | Construction of a laboratory at Ingobor Health Centre | To construct a laboratory at Ingobor Health Centre | A laboratory at Ingobor Health Centre constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | Kapkures | -0.324324 36.036613 0 2000 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | 2021/22 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2499590 | 100 | 2499590 | 5 | 410 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: No. Viable: Very viable. Require electricity and lab technician and Operationaliza. Assessor remarks: Building well done. Needs electricity and lab technician to operate.
122 | Preventive and Promotive Health Services | Construction of one storey building at Rhonda Maternity (to include pharmacy, laboratory, Dental and outpatient section) | To construct one storey building at Rhonda Maternity (to include pharmacy, laboratory, Dental and outpatient section) | One storey building at Rhonda Maternity (to include pharmacy, laboratory, Dental and outpatient section) constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | Kaptembwo | -0.305068, 36.055296 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | 2022/23 | 15000000 | 0 | 920000 | Equitable | Ward Fund | 920000 | 0 | 12774820 | 0 | 12774820 | 920000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes it met the needs of the residents. Contractor: TETRAWIDE ENTERPRISES LTD. Assessor remarks: Complete, but there are exposed wires due to vandalism.
123 | Preventive and Promotive Health Services | Renovation of theater room and laboratory at Rhoda clinic | To rehabilitate theater room and laboratory at Rhoda clinic to restore functionality | Theater room and laboratory at Rhoda clinic rehabilitated | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | Kaptembwo | -0.305152, 36.055388 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 1550 | 1550 | Equitable | N/A | 1550 | 0 | 2998450 | 193448.4 | 2998450 | 1550 | -2996900 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes it met the needs of residents. Contractor: U11. Assessor remarks: Complete, leaking roof and defective tiles needs renovation.
124 | Preventive and Promotive Health Services | Completion of Female Ward at Keringet Sub County Hospital | To complete Female Ward at Keringet Sub County Hospital | Female Ward at Keringet Sub County Hospital completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Keringet | -0.426246 35.687178 2685.7001953125 26.399999618530273 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | N/A | 1000000 | 0 | 997090 | Equitable | Ward Fund | 997090 | 0 | 1882833 | 0 | 1882833 | 997090 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Working.
125 | Preventive and Promotive Health Services | Completion of Kapbarus Dispensary and Construction of Pit Latrine | To complete Kapbarus Dispensary and Construction of Pit Latrine | Kapbarus Dispensary and Construction of Pit Latrine completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Keringet | -0.546278, 35.705597 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | 2025 | 1000000 | 0 | 999800 | Equitable | Ward Fund | 999800 | 0 | 637515 | 0 | 637515 | 999800 | 0 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Almost complete.
126 | Preventive and Promotive Health Services | Completion Of Kapkores Dispensary | To complete Kapkores Dispensary | Kapkores Dispensary completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Keringet | -0.546712 35.705567 2483.5 39.5 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 2023/24 | 750000 | 750000 | 750000 | Equitable | Ward Fund | 750000 | 0 | 637515 | 85 | 637515 | 112485 | 112485 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
127 | Preventive and Promotive Health Services | Construction of Kapsimbeiywa Outpatient Dispensary | To construct Kapsimbeiywa Outpatient Dispensary | Kapsimbeiywa Outpatient Dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Keringet | -0.48591, 35.724342 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | 2024 | 3900000 | 3739074.4 | 3739074.4 | Equitable | Ward Fund | 3739074.4 | 0 | 3674607 | 98.3 | 3674607 | 64467 | 64467.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operating.
128 | Preventive and Promotive Health Services | Construction Of Male Ward Keringet Hospital | To construct Male Ward Keringet Hospital | Male Ward Keringet Hospital constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Keringet | -0.426185, 35.687153 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 2025 | 1800000 | 1800000 | 1800000 | Equitable | Ward Fund | 1800000 | 0 | 1882833 | 104.6 | 1882833 | 1800000 | -82833 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good not yet used.
129 | Preventive and Promotive Health Services | Completion Of Engashura Health Centre at Kiamaina sub location | To complete Engashura Health Centre at Kiamaina sub location | Engashura Health Centre at Kiamaina sub location completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Bahati | Kiamaina | -0.258538 36.134637 1891.9000244140625 64.0999984741211 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | N/A | 1800000 | 1719300 | 1800000 | Equitable | Ward Fund | 1800000 | 0 | 0 | 0 | 0 | 1719300 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Not yet. Assessor remarks: Contractor on site.
130 | Preventive and Promotive Health Services | Construction and equipping of a Modern Maternity at Engashura Health Centre | To construct and equip a Modern Maternity at Engashura Health Centre | A Modern Maternity at Engashura Health Centre constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Bahati | Kiamaina | -0.258505, 36.134606 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | N/A | 4800000 | 4800000 | 4800000 | Equitable | N/A | 4800000 | 0 | 0 | 0 | 0 | 4800000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The project had stalled but new contractor is on site.
131 | Preventive and Promotive Health Services | Upgrading and equipping of Mutarakwa Health Facility and Maternity section | To upgrade and equipping of Mutarakwa Health Facility and Maternity section through tarmacking for improved road connectivity | And equipping of Mutarakwa Health Facility and Maternity section tarmacked and upgraded | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Kihingo | -0.475245, 35.988137 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | 2023 | 3500000 | 9843750 | 10000000 | Equitable | Ward Fund | 10000000 | 0 | 0 | 0 | 0 | 3343750 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Requires equipping of the facility.
132 | Preventive and Promotive Health Services | Completion of Cheptuech Dispensary | To complete Cheptuech Dispensary | Cheptuech Dispensary completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Kiptagich | -0.656364 35.601863 2385.7000000000003 15.5 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | N/A | 1000000 | 1000000 | 1000000 | Equitable | Equitable | 1000000 | 0 | 1021185 | 102.1 | 1021185 | 899416 | -21185 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Viable but needs not yet met. Assessor remarks: Need to be equipped.
133 | Preventive and Promotive Health Services | Design and construction of Chebotoi dispensary | To design and construct Chebotoi dispensary | Chebotoi dispensary designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Kiptagich | -0.553555, 35.636309 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2017/18 | 2017/18 | It stalled | 4000000 | 1416950 | 1416950 | Equitable | Ward Fund | 1416950 | 0 | 2183050 | 154.1 | 2183050 | 1416950 | -766100 | Stalled | 25 | 100 | More funds required to put up a new block | 2017 | N/A | -766100 | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes but the needs of the residents are not met. Contractor: AI contrators. Assessor remarks: The project stalled and it is vandalized.
134 | Preventive and Promotive Health Services | Completion of githima dispensary | To complete githima dispensary | Githima dispensary completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Kiptororo | -0.357906, 35.55465 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | N/A | 637784 | 93805.55 | 93805.55 | Equitable | Equitable | 93805.55 | 0 | 543281 | 579.2 | 543281 | 93806 | -449475.45 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires minor repair.
135 | Preventive and Promotive Health Services | Construction Of Murinduko Dispensary | To construct Murinduko Dispensary | Murinduko Dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Kiptororo | -0.322428 35.543765 2615.219 3.438999891281128 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 4084035 | 352646.6 | 352646.6 | Equitable | N/A | 352646.6 | 0 | 1554159 | 440.7 | 1554159 | 352647 | -1201512.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Good. Objective met: Yes. Viable: No. Assessor remarks: Kongoi dispensary lacks sanitary facility ,fence and staff house.
136 | Preventive and Promotive Health Services | Construction of modern Dispensary at Kihoto area | To construct modern Dispensary at Kihoto area | Modern Dispensary at Kihoto area constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Lake View | -0.727934, 36.432601 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | N/A | 4000000 | 4000000 | 4000000 | Equitable | Equitable | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes has not meet the needs. Assessor remarks: The project did not start there is a court case for the land ment for dispensing construction.
137 | Preventive and Promotive Health Services | Rehabilitation of Murunyu Health Centre | To rehabilitate Murunyu Health Centre to restore functionality | Murunyu Health Centre rehabilitated | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Bahati | Lanet/Umoja | -0.247732, 36.154206 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 2023/24 | 1000000 | 1000000 | 1000000 | Equitable | Ward Fund | 1000000 | 0 | 960271 | 96 | 960271 | 39729 | 39729 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Facility needs staffing.
138 | Preventive and Promotive Health Services | Renovation of the Industrial Area Clinic | To rehabilitate the Industrial Area Clinic to restore functionality | The Industrial Area Clinic rehabilitated | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | London | -0.282574 36.043851 1842.300048828125 13 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | N/A | 1400000 | 0 | 1400000 | Equitable | Ward Fund | 1400000 | 0 | 0 | 0 | 0 | 1400000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: The project is under construction.
139 | Preventive and Promotive Health Services | Construction of Moi Ndabi Health Centre-Expansion | To construct Moi Ndabi Health Centre-Expansion | Moi Ndabi Health Centre-Expansion constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maiella | -0.804803 36.246244 0 22.5 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | 2021/22 | 3500000 | 226558.85 | 226558.85 | Equitable | N/A | 226558.85 | 0 | 3272346 | 1444.4 | 3272346 | 226559 | -3045787.15 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Eruc Africa Ltd. Assessor remarks: In use.
140 | Preventive and Promotive Health Services | Expansion of Kipkonyo Health Centre | To expand Kipkonyo Health Centre to increase capacity | Kipkonyo Health Centre expanded | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maiella | -0.88682 36.198362 2353.60009765625 18 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | N/A | 3000000 | 2936060 | 2936060 | Equitable | Ward Fund | 2936060 | 0 | 3272346 | 111.5 | 3272346 | 2936060 | -336286 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Not Utilised..Project in a devastating Condition.
141 | Preventive and Promotive Health Services | Kasarani dispensary staff house repair and septic system | To implement kasarani dispensary staff house repair and septic system for access to quality healthcare services | Kasarani dispensary staff house repair and septic system completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Malewa West | -0.702703, 36.291018 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 1723711 | 29719.15 | 29719.15 | Equitable | N/A | 29719.15 | 0 | 1693992 | 5700 | 1693992 | 29719 | -1664272.85 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yea. Viable: Yes. Assessor remarks: Work well done.
142 | Preventive and Promotive Health Services | Construction of Segut Dispensary | To construct Segut Dispensary | Segut Dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Mariashoni | -0.361136, 35.788569 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 1989024 | 100173 | 100173 | Equitable | N/A | 100173 | 0 | 1888851 | 1885.6 | 1888851 | 100173 | -1788678 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Not operating.
143 | Preventive and Promotive Health Services | Construction of a pharmacy, waiting area and pit latrines at Mau Narok health centre | To construct a pharmacy, waiting area and pit latrines at Mau Narok health centre | A pharmacy, waiting area and pit latrines at Mau Narok health centre constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Mau Narok | -0.600012, 36.007202 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 1999794 | 1999794 | Equitable | N/A | 1999794 | 0 | 1999910 | 100 | 1999910 | 2000000 | -116 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: not met. Viable: not viable. Assessor remarks: project stalled.
144 | Preventive and Promotive Health Services | Construction of Dispensary at Segutiet | To construct Dispensary at Segutiet | Dispensary at Segutiet constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Mau Narok | -0.577825, 36.052545 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | N/A | 2500000 | 534438 | 534438 | Equitable | N/A | 534438 | 0 | 1962735 | 367.3 | 1962735 | 534438 | -1428297 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: No. Assessor remarks: Needs equiping.
145 | Preventive and Promotive Health Services | Construction of storey observation wards at Mau Health centre | To construct storey observation wards at Mau Health centre | Storey observation wards at Mau Health centre constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Mau Narok | -0.600012, 36.007202 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | N/A | 8500000 | 8500000 | 8500000 | Equitable | N/A | 8500000 | 0 | 1999910 | 23.5 | 1999910 | 8500000 | 6500090 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: ok.
146 | Preventive and Promotive Health Services | Completion of Taita Health Centre | To complete Taita Health Centre | Taita Health Centre completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Mauche | -0.516665, 35.962688 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | 2025 | 10000000 | 0 | 10000000 | Equitable | Ward Fund | 10000000 | 0 | 0 | 0 | 0 | 10000000 | 0 | Stalled | 75 | N/A | Intent to terminate issued | 2022 | N/A | N/A | Yes | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Ongoing construction.
147 | Preventive and Promotive Health Services | Completion of Menengai Dispensary Maternity building | To complete Menengai Dispensary Maternity building | Menengai Dispensary Maternity building completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru East | Menengai | -0.26625, 36.100624 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | 2018/19 | 5000000 | 4761165 | 4761165 | Equitable | Ward Fund | 4761165 | 0 | 4761165 | 100 | 4761165 | 4761165 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Pypro company limited.
148 | Preventive and Promotive Health Services | Construction of Maternity wing at Menengai Health Centre | To construct Maternity wing at Menengai Health Centre | Maternity wing at Menengai Health Centre constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru East | Menengai | -0.266242, 36.100625 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 218/19 | 3500000 | 0 | 2822983 | Equitable | Ward Fund | 2822983 | 0 | 1632017 | 0 | 1632017 | 2867983 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: No. Viable: No. Assessor remarks: Vired.
149 | Preventive and Promotive Health Services | Completion of Mang'u maternity | To complete Mang'u maternity | Mang'u maternity completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Menengai West | -0.166762 36.007934 0 600 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 1999824 | 1999824 | Equitable | Ward Fund | 1999824 | 0 | 1999824 | 100 | 1999824 | 1999824 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs renovation.
150 | Preventive and Promotive Health Services | Construction of Kamungei Dispensary | To construct Kamungei Dispensary | Kamungei Dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Menengai West | -0.2466 36.013657 2010.9 9.5 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | N/A | 4000000 | 0 | 3614260 | Equitable | Ward Fund | 3614260 | 0 | 999920 | 0 | 999920 | 3614260 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
151 | Preventive and Promotive Health Services | Maternity Wards Menengai Dispensary - On Going | To implement maternity wards menengai dispensary - on going for access to quality healthcare services | Maternity Wards Menengai Dispensary - On Going completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Menengai West | -0.140657 36.017808 1906.8999999999999 11 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2016/17 | 2016/17 | N/A | 2247896 | 0 | 1207916 | Equitable | Ward Fund | 1207916 | 0 | 999980 | 0 | 999980 | 1247916 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
152 | Preventive and Promotive Health Services | Construction Of Kibunja Dispensary | To construct Kibunja Dispensary | Kibunja Dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Molo | -0.380641 35.796196 2793.679531111378 6 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 2023/24 | 3873974 | 0 | 3813974 | Equitable | Ward Fund | 3813974 | 0 | 877800 | 0 | 877800 | 3873974 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Partially. Viable: Partially. Assessor remarks: The toilet is non existent.
153 | Health Curative and Rehabilitative Services | Fencing and equipping of Kivunja Dispensary | To secure and equipping of Kivunja Dispensary through fencing | And equipping of Kivunja Dispensary fenced and secured | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Molo Central | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | N/A | 2700000 | 0 | 2700000 | Equitable | N/A | 2700000 | 0 | 27024982 | 0 | 27024982 | 85136868 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
154 | Preventive and Promotive Health Services | Completion and Equipping of Ngecha Dispensary | To complete and equip Ngecha Dispensary | Ngecha Dispensary completed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Mosop | -0.248851 35.939649 2052.10009765625 13.512999534606934 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | 2022/23 | 3000000 | 2783570.8 | 2783570.8 | Equitable | Ward Fund | 2783570.8 | 0 | 2783571 | 100 | 2783571 | 2783571 | -0.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: It was viable. Contractor: JODIAH TRANDERS LIMITED. Assessor remarks: Good workmanship.
155 | Preventive and Promotive Health Services | Completion of Ngecha Dispensary | To complete Ngecha Dispensary | Ngecha Dispensary completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Mosop | -0.248851 35.939649 2052.10009765625 13.512999534606934 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 500000 | 500000 | Equitable | Ward Fund | 500000 | 0 | 499990 | 100 | 499990 | 500000 | 10 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: It was viable. Contractor: JODIAH TRANDERS LIMITED. Assessor remarks: Good workmanship.
156 | Preventive and Promotive Health Services | Construction of a laboratory room at Lelechwet Dispensary | To construct a laboratory room at Lelechwet Dispensary | A laboratory room at Lelechwet Dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Mosop | -0.221061, 35.827744 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 2024 | 1530000 | 0 | 1530000 | Equitable | Ward Fund | 1530000 | 0 | 1499300 | 0 | 1499300 | 1530000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: Under procurement. Assessor remarks: Not yet started.
157 | Preventive and Promotive Health Services | Construction of a laboratory room at Ogilgei Health center | To construct a laboratory room at Ogilgei Health center | A laboratory room at Ogilgei Health center constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Mosop | -0.29607, 35.958762 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 2024 | 1400000 | 0 | 1400000 | Equitable | Ward Fund | 1400000 | 0 | 211969 | 0 | 211969 | 1400000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Viable. Contractor: Not yet BQ being prepared. Assessor remarks: Not yet tendered.
158 | Preventive and Promotive Health Services | Construction of Maternity Block at Sumeek Dispensary | To construct Maternity Block at Sumeek Dispensary | Maternity Block at Sumeek Dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Mosop | -0.254891, 35.877142 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | 2023 | 3000000 | 2752510 | 2752510 | Equitable | Ward Fund | 2752510 | 0 | 2752510 | 100 | 2752510 | 2752510 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Triple front. Assessor remarks: Good workmanship.
159 | Preventive and Promotive Health Services | Construction and equipping of Komothai dispensary | To construct and equip Komothai dispensary | Komothai dispensary constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Murindat | -0.467272, 36.371306 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 3999950 | 3999950 | 3999950 | Equitable | N/A | 3999950 | 0 | 3968360 | 99.2 | 3968360 | 3999950 | 31590 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: RONISAR ENTERPRISES, PEPSI AFRICA GENERAL MERCHANT LTD. Assessor remarks: Operational.
160 | Preventive and Promotive Health Services | Construction of Gatundu -Merironi dispensary | To construct Gatundu -Merironi dispensary | Gatundu -Merironi dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Murindat | -0.503131, 36.390597 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 2396460 | 1150960 | 1150960 | Equitable | N/A | 1150960 | 0 | 1049950 | 91.2 | 1049950 | 1150960 | 101010 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: GLASAMMURS CONSTRUCTION LIMITED. Assessor remarks: In good condition.
161 | Preventive and Promotive Health Services | Construction of gitare dispensary phase 1 | To construct gitare dispensary phase 1 | Gitare dispensary phase 1 constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Murindat | -0.40869, 36.310599 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 91164 | 91164 | Equitable | N/A | 91164 | 0 | 2908836 | 3190.8 | 2908836 | 91164 | -2817672 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
162 | Preventive and Promotive Health Services | Renovation of karunga dispensary | To rehabilitate karunga dispensary to restore functionality | Karunga dispensary rehabilitated | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Murindat | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 1600 | 1600 | Equitable | N/A | 1600 | 0 | 1998400 | 124900 | 1998400 | 1600 | -1996800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
163 | Preventive and Promotive Health Services | Completion and equipping of Kiambogo Dispensary | To complete and equip Kiambogo Dispensary | Kiambogo Dispensary completed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Naivasha East | -0.868092, 36.520197 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 2025 | 1500000 | 0 | 1500000 | Equitable | Ward Fund | 1500000 | 0 | 636000 | 0 | 636000 | 1500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Facility not eqquiped and was cinverted from an ecd class.
164 | Preventive and Promotive Health Services | Completion of Sulmac Dispensary | To complete Sulmac Dispensary | Sulmac Dispensary completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Naivasha East | -0.867433 36.53546 2475 6.632999897003174 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | N/A | 1000000 | 1000000 | 1000000 | Equitable | Equitable | 1000000 | 0 | 491490 | 49.1 | 491490 | 3500000 | 508510 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Not yet. Assessor remarks: Incomplete no provision of septic tank and water connection.
165 | Preventive and Promotive Health Services | Construction of Laboratory of Munyu Dispensary | To construct Laboratory of Munyu Dispensary | Laboratory of Munyu Dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Naivasha East | -0.827825, 36.535894 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | 2024 | 1000000 | 999600 | 999600 | Equitable | N/A | 999600 | 0 | 955255 | 95.6 | 955255 | 999600 | 44345 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Objective met but currently not serving the purpose. Viable: Should be operationalized. Assessor remarks: No running water, waste water not connected to septic tank.
166 | Preventive and Promotive Health Services | Construction of Munyu Dispensary Laboratory | To construct Munyu Dispensary Laboratory | Munyu Dispensary Laboratory constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Naivasha East | -0.827785, 36.535826 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | 2023-24 | 1500000 | 668400 | 668400 | Equitable | Ward Fund | 668400 | 0 | 668400 | 100 | 668400 | 668400 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Laboratory not equipped and waste water not connected to septic tank.
167 | Preventive and Promotive Health Services | Construction of Muraigushu Dispensary | To construct Muraigushu Dispensary | Muraigushu Dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Naivasha East | -0.742122, 36.530536 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | Ongoing | 3500000 | 3500000 | 9000000 | Equitable | Ward Fund | 9000000 | 0 | 668400 | 19.1 | 668400 | 3500000 | 2831600 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Not yet. Assessor remarks: On going.
168 | Preventive and Promotive Health Services | Construction of Mwega dispensary and Toilet | To construct Mwega dispensary and Toilet | Mwega dispensary and Toilet constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Naivasha East | -0.78485, 36.541935 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | 2022 | 3000000 | 2998150 | 2998150 | Equitable | N/A | 2998150 | 0 | 2798021 | 93.3 | 2798021 | 200129 | 200129 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Not yet. Assessor remarks: No t yet equipped, no electricity connection and septic tank.
169 | Preventive and Promotive Health Services | Construction of wards at Sision Maternity | To construct wards at Sision Maternity | Wards at Sision Maternity constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Naivasha East | -0.867373, 36.535493 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2020 | 2000000 | 294533.9 | 294533.9 | Equitable | N/A | 294533.9 | 0 | 1705466 | 579 | 1705466 | 294534 | -1410932.1 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
170 | Preventive and Promotive Health Services | Rehabilitation of Sision Dispensary | To rehabilitate Sision Dispensary to restore functionality | Sision Dispensary rehabilitated | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Naivasha East | -0.867319, 36.535158 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | 2022 | 500000 | 491890 | 491890 | Equitable | N/A | 491890 | 0 | 491490 | 99.9 | 491490 | 491890 | 400 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Fissure boards.
171 | Preventive and Promotive Health Services | Upgrading of Munyu Health Centre phase I | To upgrade Munyu Health Centre phase I through tarmacking for improved road connectivity | Munyu Health Centre phase I tarmacked and upgraded | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Naivasha East | -0.827643, 36.535812 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 25 march 2025 | 10000000 | 0 | 10000000 | Equitable | Ward Fund | 10000000 | 0 | 0 | 0 | 0 | 10000000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: M/s eclat merchants. Assessor remarks: Project require extra funding to operation.
172 | Preventive and Promotive Health Services | Completion Of Muguga Dispensary and Construction of a Perimeter Wall | To complete Muguga Dispensary and Construction of a Perimeter Wall | Muguga Dispensary and Construction of a Perimeter Wall completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru East | Nakuru East | -0.309521, 36.145567 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 2023/2024 | 3700000 | 3700000 | 3700000 | Equitable | Ward Fund | 3700000 | 0 | 3635655 | 98.3 | 3635655 | 64345 | 64345 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Heads up systems. Viable: Yes. Assessor remarks: Equipment needed.
173 | Preventive and Promotive Health Services | Completion of Perimeter wall, installation of Electricity and Pipping of Njokerio Dispensary | To complete Perimeter wall, installation of Electricity and Pipping of Njokerio Dispensary | Perimeter wall, installation of Electricity and Pipping of Njokerio Dispensary completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Njoro | -0.389818 35.931233 2298.1 6.099999904632568 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 2023/24 | 6000000 | 6000000 | 6000000 | Equitable | Ward Fund | 6000000 | 0 | 0 | 0 | 0 | 6000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good state.
174 | Preventive and Promotive Health Services | Rehabilitation of Piave Dispensary | To rehabilitate Piave Dispensary to restore functionality | Piave Dispensary rehabilitated | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Njoro | -0.341618, 35.992603 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 2024 | 5000000 | 0 | 5000000 | Equitable | Ward Fund | 5000000 | 0 | 0 | 0 | 0 | 4775220 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Amigrowth venture Kenya Ltd. Assessor remarks: Good work done.
175 | Preventive and Promotive Health Services | Construction of Narasha dispensary | To construct Narasha dispensary | Narasha dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Olkaria | -0.913132, 36.276833 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1697135 | 84.9 | 1697135 | 2000000 | 302865 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: No since its not functional. Assessor remarks: The project is not operational.
176 | Preventive and Promotive Health Services | Construction of Olkaria Dispensary at Kamere | To construct Olkaria Dispensary at Kamere | Olkaria Dispensary at Kamere constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Olkaria | -0.815472 36.322517 1881.300048828125 9.899999618530273 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 1697135 | 56.6 | 1697135 | 3000000 | 1302865 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes if done it will benefit the youth. Assessor remarks: There was land issues thus not done.
177 | Preventive and Promotive Health Services | Completion of gacharage dispensary | To complete gacharage dispensary | Gacharage dispensary completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Sirikwa | -0.289234 35.63603 2712.264136918813 13 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 2211394 | 2194200 | 2194200 | Equitable | N/A | 2194200 | 0 | 2194200 | 100 | 2194200 | 2211394 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is in use though it has no water supply.
178 | Preventive and Promotive Health Services | Completion of maternity wing at Kapsetek Dispensary | To complete maternity wing at Kapsetek Dispensary | Maternity wing at Kapsetek Dispensary completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Soin | -0.085275 35.944498 1671.6 11.399999618530273 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | N/A | 2000000 | 2000000 | 2000000 | Equitable | Equitable | 2000000 | 0 | 349972 | 17.5 | 349972 | 3900000 | 1650028 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
179 | Preventive and Promotive Health Services | Construction Of a Maternity Wing at Kapsetek Dispensary | To construct a Maternity Wing at Kapsetek Dispensary | A Maternity Wing at Kapsetek Dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Soin | -0.083409 35.873848 1801 9.5 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | N/A | 3900000 | 3900000 | 7800000 | Equitable | Equitable | 7800000 | 0 | 349972 | 9 | 349972 | 3900000 | 3550028 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require water supply.
180 | Preventive and Promotive Health Services | Construction of a toilet at kapsetek dispensary | To construct a toilet at kapsetek dispensary | A toilet at kapsetek dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Soin | -0.083928, 35.874083 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 30/12/3024 | 350000 | 28 | 28 | Equitable | Ward Fund | 28 | 0 | 349972 | 1249900 | 349972 | 28 | -349944 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: M/S Laron Investment. Assessor remarks: The project is ongoing.
181 | Preventive and Promotive Health Services | Construction Of a Waiting Bay, 4-Door Toilet and Renovation of Losibil Dispensary | To construct a Waiting Bay, 4-Door Toilet and Renovation of Losibil Dispensary | A Waiting Bay, 4-Door Toilet and Renovation of Losibil Dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Soin | -0.096327 35.935707 1687 7.5 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 2023/24 | 2000000 | 0 | 2000000 | Equitable | Ward Fund | 2000000 | 0 | 349972 | 0 | 349972 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Assessor remarks: Construction to start soon.
182 | Preventive and Promotive Health Services | Renovation works at Majani Mingi Dispensary and construction of toilet | To rehabilitate works at Majani Mingi Dispensary and construction of toilet to restore functionality | Works at Majani Mingi Dispensary and construction of toilet rehabilitated | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Soin | -0.041777, 36.02443 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 1198135 | 1198135 | 1198135 | Equitable | N/A | 1198135 | 0 | 1198135 | 100 | 1198135 | 1200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Project on Use.
183 | Preventive and Promotive Health Services | Completion of Construction Work at Lomolo Dispensary | To complete Construction Work at Lomolo Dispensary | Construction Work at Lomolo Dispensary completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Soin | 0.016519, 36.03349 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | 2022/2023 | 1700000 | 1700000 | 1700000 | Equitable | N/A | 1700000 | 0 | 1615936 | 95.1 | 1615936 | 28 | 84064 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: OISUUN Investment Ltd. Assessor remarks: Need to have additional staff.
184 | Preventive and Promotive Health Services | Construction and equipping of new Outpatient Block at Kipsyenan Dispensary | To construct and equip new Outpatient Block at Kipsyenan Dispensary | New Outpatient Block at Kipsyenan Dispensary constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Soin | -0.085629 35.944492 1695 137.35000610351562 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | 2022/23 | 5000000 | 4921335 | 4921335 | Equitable | Ward Fund | 4921335 | 0 | 4921711 | 100 | 4921711 | 4921335 | -376 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Dakuki Construction. Assessor remarks: Equipping of OPD, Fencing of the facility, Construction and equipping of a laboratory, Construction of staff houses, Construction of ablution block.
185 | Preventive and Promotive Health Services | Edgewood dispensary - equipping and purchase of furniture and fittings | To implement edgewood dispensary - equipping and purchase of furniture and fittings for access to quality healthcare services | Edgewood dispensary - equipping and purchase of furniture and fittings completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Subukia | Subukia | 0.004847, 36.207636 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 11/02/2022 | 674464 | 674464 | 674464 | Equitable | N/A | 674464 | 0 | 674350 | 100 | 674350 | 674464 | 114 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes.. Viable: Yes. The furniture serves the health facility workers. Contractor: Information not available. Assessor remarks: The furniture is in good condition..
186 | Preventive and Promotive Health Services | Edgewood dispensary | To implement edgewood dispensary for access to quality healthcare services | Edgewood dispensary completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Subukia | Subukia | 0.004801, 36.207485 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 04/01/2017 | 2000000 | 1654.1 | 1654.1 | Equitable | N/A | 1654.1 | 0 | 1998346 | 120811.7 | 1998346 | 1654 | -1996691.9 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes.. Viable: Yes. The facility serves the community. Contractor: Information not available. Assessor remarks: Good work.
187 | Preventive and Promotive Health Services | Renovation of Subukia Level IV Hospital | To rehabilitate Subukia Level IV Hospital to restore functionality | Subukia Level IV Hospital rehabilitated | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Subukia | Subukia | 0.002771 36.229894 1992.0999755859375 61.25199890136719 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | N/A | 3300000 | 0 | 6600000 | Equitable | Ward Fund | 6600000 | 0 | 2536538 | 100 | 2536538 | 3300000 | -2536538 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Yet to start. Objective met: It will be met when complete. Viable: Yes, it will improve the quality of life of the people. Contractor: Not known. Assessor remarks: Project is going on well.
188 | Preventive and Promotive Health Services | Completion Of Kepkosigen Dispensary | To complete Kepkosigen Dispensary | Kepkosigen Dispensary completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.431008, 35.687609 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 2023/24 | 700000 | 700000 | 700000 | Equitable | Ward Fund | 700000 | 0 | 697800 | 99.7 | 697800 | 2200 | 2200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Stalled project and no operational.
189 | Preventive and Promotive Health Services | Construction of chemaner male ward | To construct chemaner male ward | Chemaner male ward constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.445126 35.609035 0 2200 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 2360000 | 1080862.05 | 1080862.05 | Equitable | Ward Fund | 1080862.05 | 0 | 733372 | 67.9 | 733372 | 347490 | 347490.05 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: Yes but not meet the need. Assessor remarks: Converted to staff quarters.
190 | Preventive and Promotive Health Services | Construction of Kabongoi Dispensary | To construct Kabongoi Dispensary | Kabongoi Dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.47504 35.631932 0 2400 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2020/21 | 2020/21 | N/A | 2408155 | 2408155 | 2408155 | Equitable | Ward Fund | 2408155 | 0 | 1901087 | 78.9 | 1901087 | 2408155 | 507068 | Stalled | 75 | 78.9 | Intent to terminate issued | 2020 | N/A | 507068 | Yes | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: Yes. Assessor remarks: Complete not equipped.
191 | Preventive and Promotive Health Services | Construction of Karandit Dispensary | To construct Karandit Dispensary | Karandit Dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.47504 35.631932 0 2400 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | N/A | 2000000 | 1998350 | 1998350 | Equitable | Ward Fund | 1998350 | 0 | 1901087 | 95.1 | 1901087 | 1998350 | 97263 | Stalled | 75 | 95.1 | Intent to terminate issued | 2021 | N/A | 97263 | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: Yes. Assessor remarks: Complete not equipped.
192 | Preventive and Promotive Health Services | Construction of outpatient in Korao Health center | To construct outpatient in Korao Health center | Outpatient in Korao Health center constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.499357, 35.58955 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 1894435 | 1894435 | Equitable | N/A | 1894435 | 0 | 1376318 | 72.7 | 1376318 | 1894435 | 518117 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes but not meet the need. Assessor remarks: Stalled project.
193 | Preventive and Promotive Health Services | Construction of Taita maternity | To construct Taita maternity | Taita maternity constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.445126 35.609035 0 2200 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | N/A | 2000000 | 0 | 1998335 | Equitable | Ward Fund | 1998335 | 0 | 733372 | 0 | 733372 | 1998335 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: Yes but not meet the need. Assessor remarks: Converted to staff quarters.
194 | Preventive and Promotive Health Services | Construction of public toilet at Randi center | To construct public toilet at Randi center | Public toilet at Randi center constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Turi | -0.296227 35.768977 2362 8.5 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 800000 | 870 | 870 | Equitable | N/A | 870 | 0 | 799130 | 91854 | 799130 | 870 | -798260 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The problem was done.
195 | Preventive and Promotive Health Services | Construction of toilets, piping system and renovation of houses and construction of waiting bay at Mukorobosi Dispensary | To construct toilets, piping system and renovation of houses and construction of waiting bay at Mukorobosi Dispensary | Toilets, piping system and renovation of houses and construction of waiting bay at Mukorobosi Dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Turi | -1.281229, 36.821402 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 1998500 | 1998500 | Equitable | N/A | 1998500 | 0 | 1998500 | 100 | 1998500 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: YES. Viable: YES. Assessor remarks: FUNCTIONAL.
196 | Preventive and Promotive Health Services | Renovation of Kiambiriria Health Centre | To rehabilitate Kiambiriria Health Centre to restore functionality | Kiambiriria Health Centre rehabilitated | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Turi | -0.323408, 35.698105 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1050 | 1050 | Equitable | N/A | 1050 | 0 | 998950 | 95138.1 | 998950 | 1050 | -997900 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The facility is very well built, has drugs but in need of staff.
197 | Preventive and Promotive Health Services | Renovation of Tumaini dispensary and equipping | To rehabilitate Tumaini dispensary and equipping to restore functionality | Tumaini dispensary and equipping rehabilitated | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Visoi | -0.125197 35.935737 1744.699951171875 6.599999904632568 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | 2021/22 | 1500000 | 1237250 | 1237250 | Equitable | N/A | 1237250 | 0 | 1198450 | 96.9 | 1198450 | 1237250 | 38800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
198 | Preventive and Promotive Health Services | Construction and equipping of Kabati Dispensary laboratory | To construct and equip Kabati Dispensary laboratory | Kabati Dispensary laboratory constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Viwandani | -0.721884, 36.444183 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 4500000 | 349731 | 349731 | Equitable | N/A | 349731 | 0 | 349731 | 100 | 349731 | 349731 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yed. Assessor remarks: The project was completed and functional.
199 | Preventive and Promotive Health Services | Construction of Hope Well dispensary | To construct Hope Well dispensary | Hope Well dispensary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Viwandani | -0.710429, 36.4312 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 2862545 | 2862545 | 2862545 | Equitable | N/A | 2862545 | 0 | 2862545 | 100 | 2862545 | 3000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Very Good. Objective met: Yes. Viable: Viable. Assessor remarks: About to start.
200 | Preventive and Promotive Health Services | Renovation of maternity rooms at Dundori health center | To rehabilitate maternity rooms at Dundori health center to restore functionality | Maternity rooms at Dundori health center rehabilitated | 3110299 | Construction of Buildings - Ot | Bahati | Dundori | -0.252601, 36.233631 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | 2024/2025 | 2000000 | 0 | 2000000 | Equitable | Equitable | 2000000 | 0 | 536500 | 0 | 536500 | 263500 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: Contractor pace is slow.
201 | Completion of Githiorio Health Centre | Completion of Githiorio Health Centre | To complete Githiorio Health Centre | Githiorio Health Centre completed | 3110299 | Construction of Buildings - Ot | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | 2021/22 | 35000000 | 1958780.7 | 1958780.7 | N/A | N/A | 1958780.7 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
202 | Construction of Naivasha morgue | Construction of Naivasha morgue | To construct Naivasha morgue | Naivasha morgue constructed | 3110299 | Construction of Buildings - Ot | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | 2024/25 | 5900000 | 0 | 5900000 | N/A | N/A | 5900000 | 0 | 3321916 | 100 | 3321916 | 9890259 | -3321916 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
203 | Construction of OPD at Olenguruone Sub County Hospital | Construction of OPD at Olenguruone Sub County Hospital | To construct OPD at Olenguruone Sub County Hospital | OPD at Olenguruone Sub County Hospital constructed | 3110299 | Construction of Buildings - Ot | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | 2021/22 | 100000000 | 19988315 | 19988315 | N/A | N/A | 19988315 | 0 | 750000 | 3.8 | 750000 | 0 | 19238315 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
204 | Construction of OPD at Olenguruone Subcounty hospital | Construction of OPD at Olenguruone Subcounty hospital | To construct OPD at Olenguruone Subcounty hospital | OPD at Olenguruone Subcounty hospital constructed | 3110299 | Construction of Buildings - Ot | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2018/19 | 2023/24 | 2023/24 | 100000000 | 57757547.4 | 35000000 | N/A | N/A | 35000000 | 22757547.4 | 750000 | 1.3 | 750000 | 0 | 57007547.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
205 | Purchase and supply of a modern mortuary refrigerator at County Public Mortuary and Olenguruone Sub County Hospital Mortuary | Purchase and supply of a modern mortuary refrigerator at County Public Mortuary and Olenguruone Sub County Hospital Mortuary | To procure and supply a modern mortuary refrigerator at County Public Mortuary and Olenguruone Sub County Hospital Mortuary | A modern mortuary refrigerator at County Public Mortuary and Olenguruone Sub County Hospital Mortuary procured and supplied | 3110299 | Construction of Buildings - Ot | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | 2021/22 | 9000000 | 9000000 | 9000000 | N/A | N/A | 9000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
206 | Purchase and supply of a modern mortuary refrigerator at Olenguruone Sub County Hospital | Purchase and supply of a modern mortuary refrigerator at Olenguruone Sub County Hospital | To procure and supply a modern mortuary refrigerator at Olenguruone Sub County Hospital | A modern mortuary refrigerator at Olenguruone Sub County Hospital procured and supplied | 3110299 | Construction of Buildings - Ot | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | 2021/22 | 9000000 | 0 | 9000000 | N/A | N/A | 9000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
207 | Preventive and Promotive Health Services | Renovation of Mitimingi Dispensary staff house | To rehabilitate Mitimingi Dispensary staff house to restore functionality | Mitimingi Dispensary staff house rehabilitated | 3110301 | Refurbishment of Residential Buildings | Gilgil | Elementaita | -0.528532, 36.075332 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | 2021/22 | 800000 | 780197 | 780197 | Equitable | Ward Fund | 780197 | 0 | 665224 | 85.3 | 665224 | 114973 | 114973 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: Yes. Assessor remarks: Not Operational.
208 | Preventive and Promotive Health Services | Renovation of Mwariki Dispensary | To rehabilitate Mwariki Dispensary to restore functionality | Mwariki Dispensary rehabilitated | 3110302 | Refurbishment of Non-Residential Buildings | Nakuru West | Barut | -0.324324, 36.036613 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 2024 | 1000000 | 0 | 1000000 | Equitable | Ward Fund | 1000000 | 0 | 29957 | 0 | 29957 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: NICLAW BUILDERS. Assessor remarks: Good.
209 | Preventive and Promotive Health Services | Rehabilitation of Eburru Health Centre | To rehabilitate Eburru Health Centre to restore functionality | Eburru Health Centre rehabilitated | 3110302 | Refurbishment of Non-Residential Buildings | Gilgil | Eburru-Mbaruk | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | N/A | 2000000 | 2000000 | 2000000 | Equitable | Equitable | 2000000 | 0 | 1199840 | 60 | 1199840 | 300000 | 800160 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
210 | Preventive and Promotive Health Services | Refurbishment of Health Buildings - Others | To implement refurbishment of health buildings - others for access to quality healthcare services | Refurbishment of Health Buildings - Others completed | 3110302 | Refurbishment of Non-Residential Buildings | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2018/19 | 2018/19 | N/A | 50000000 | 0 | 1657080 | Equitable | N/A | 1657080 | 0 | 5400882 | 0 | 5400882 | 1657080 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
211 | Preventive and Promotive Health Services | Renovation of Longonot Dispensary | To rehabilitate Longonot Dispensary to restore functionality | Longonot Dispensary rehabilitated | 3110302 | Refurbishment of Non-Residential Buildings | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | N/A | 1500000 | 0 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 9890259 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
212 | Preventive and Promotive Health Services | Renovation Of Rhonda Clinic Maternity Wing and installation of cabros | To rehabilitate Rhonda Clinic Maternity Wing and installation of cabros to restore functionality | Rhonda Clinic Maternity Wing and installation of cabros rehabilitated | 3110302 | Refurbishment of Non-Residential Buildings | Nakuru West | Kaptembwo | -0.30494, 36.055279 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 2023/24 | 2000000 | 0 | 2000000 | Equitable | Ward Fund | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Very viable it's the only health center in the entire ward. Contractor: TIECIM LIMITED. Assessor remarks: Defective doors ,drainage outside needs to be done.
213 | Preventive and Promotive Health Services | Renovation and Equipping of Lisuri Dispensary | To rehabilitate Equipping of Lisuri Dispensary to restore functionality | Equipping of Lisuri Dispensary rehabilitated | 3110302 | Refurbishment of Non-Residential Buildings | Njoro | Kihingo | -0.497442, 35.997313 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | 2023 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1855154 | 92.8 | 1855154 | 0 | 144846 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: S&MU construction company. Assessor remarks: Good.tank stand require repair.construction of toilets.
214 | Preventive and Promotive Health Services | Renovation, Equipping and Operationalization of Kayole Dispensary Laboratory | To implement renovation, equipping and operationalization of kayole dispensary laboratory for access to quality healthcare services | Renovation, Equipping and Operationalization of Kayole Dispensary Laboratory completed | 3110302 | Refurbishment of Non-Residential Buildings | Naivasha | Lake View | -0.751714, 36.457225 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 2023/24 | 1200000 | 1200000 | 1200000 | Equitable | Ward Fund | 1200000 | 0 | 947790 | 79 | 947790 | 1200000 | 252210 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Good. Objective met: No. Viable: Yes. Assessor remarks: Tile the floor, equipe the facility,raise the working tables to a height.
215 | Preventive and Promotive Health Services | Renovation of Murunyu dispensary and construction of public toilet and perimeter wall | To rehabilitate Murunyu dispensary and construction of public toilet and perimeter wall to restore functionality | Murunyu dispensary and construction of public toilet and perimeter wall rehabilitated | 3110302 | Refurbishment of Non-Residential Buildings | Bahati | Lanet Umoja | -0.247975, 36.151303 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | 2024 | 2506689 | 5013378 | 7520067 | Equitable | Ward Fund | 7520067 | 0 | 0 | 0 | 0 | 2506689 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes,viable. Assessor remarks: Ready for functionality.
216 | Preventive and Promotive Health Services | Rehabilitation of Namucha Maternity | To rehabilitate Namucha Maternity to restore functionality | Namucha Maternity rehabilitated | 3110302 | Refurbishment of Non-Residential Buildings | Naivasha | Maai Mahiu | -1.063258, 36.557072 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | N/A | 2000000 | 2000000 | 2000000 | Equitable | Equitable | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: Degrading building,the project should be expedited ,transfer from kajiado to Nakuru county already done.more funds should be availed.
217 | Preventive and Promotive Health Services | Refurbishment of Menengai Dispensary and equipping of Menengai Maternity | To implement refurbishment of menengai dispensary and equipping of menengai maternity for access to quality healthcare services | Refurbishment of Menengai Dispensary and equipping of Menengai Maternity completed | 3110302 | Refurbishment of Non-Residential Buildings | Nakuru East | Menengai | -0.26625, 36.100624 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | 2024/25 | 5055898 | 5055898 | 5055898 | Equitable | Equitable | 5055898 | 0 | 4761165 | 94.2 | 4761165 | 4761165 | 294733 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: Lumiseal enterprise. Assessor remarks: Rude and arrogant contractor.
218 | Preventive and Promotive Health Services | Renovation Works at Ogilgei Health Centre | To rehabilitate Works at Ogilgei Health Centre to restore functionality | Works at Ogilgei Health Centre rehabilitated | 3110302 | Refurbishment of Non-Residential Buildings | Rongai | Mosop | -0.296337, 35.958873 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | 2023 | 1200000 | 0 | 980751 | Equitable | Ward Fund | 980751 | 0 | 211969 | 0 | 211969 | 980751 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: Good workmanship.
219 | Preventive and Promotive Health Services | Renovation and Equipping of an Outpatient hospital block at Nessuit Health centre | To rehabilitate Equipping of an Outpatient hospital block at Nessuit Health centre to restore functionality | Equipping of an Outpatient hospital block at Nessuit Health centre rehabilitated | 3110302 | Refurbishment of Non-Residential Buildings | Njoro | Nessuit | -0.393259, 35.89877 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | 2022/23 | 2000000 | 0 | 2000000 | Equitable | Ward Fund | 2000000 | 0 | 1701945 | 0 | 1701945 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: The project hasn't started yet.
220 | Preventive and Promotive Health Services | Refurbishment/ And Equipping of Nakuru West Health Center | To implement refurbishment/ and equipping of nakuru west health center for access to quality healthcare services | Refurbishment/ And Equipping of Nakuru West Health Center completed | 3110302 | Refurbishment of Non-Residential Buildings | Nakuru West | Shabab | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | N/A | 1500000 | 0 | 1500000 | Equitable | N/A | 1500000 | 0 | 2958500 | 0 | 2958500 | 1500000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
221 | Preventive and Promotive Health Services | Renovation Of Wei Dispensary | To rehabilitate Wei Dispensary to restore functionality | Wei Dispensary rehabilitated | 3110302 | Refurbishment of Non-Residential Buildings | Subukia | Waseges | 0.032413 36.24133 1984.5 8.100000381469727 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 2023/24 | 1500000 | 0 | 1200000 | Equitable | Ward Fund | 1200000 | 0 | 0 | 0 | 0 | 1200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The dispensary is in good condition.
222 | Preventive and Promotive Health Services | Renovation of outpatient wing Chepakundi Dispensary | To rehabilitate outpatient wing Chepakundi Dispensary to restore functionality | Outpatient wing Chepakundi Dispensary rehabilitated | 3110399 | Refurbishment of Buildgs - Oth | Kuresoi South | Amalo | -0.677653, 35.656037 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | 2024 | 1200000 | 1170040 | 1170040 | Equitable | Ward Fund | 1170040 | 0 | 1141943 | 97.6 | 1141943 | 28098 | 28097 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: Yes. Assessor remarks: project completed.
223 | Preventive and Promotive Health Services | Repairs And Renovation at Kongasis Health Center | To implement repairs and renovation at kongasis health center for access to quality healthcare services | Repairs And Renovation at Kongasis Health Center completed | 3110399 | Refurbishment of Buildgs - Oth | Gilgil | Eburru/Mbaruk | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 2023/24 | 1000000 | 1000000 | 1000000 | Equitable | Ward Fund | 1000000 | 0 | 991589 | 99.2 | 991589 | 8411 | 8411 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
224 | Health Curative and Rehabilitative Services | Rehabilitation of Buildings - (FIF) | To rehabilitate Buildings - (FIF) to restore functionality | Buildings - (FIF) rehabilitated | 3110399 | Refurbishment of Buildgs - Oth | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | N/A | 50000000 | 45000000 | 0 | FIF | FIF | 0 | 45000000 | 3321916 | 7.4 | 3321916 | 26043808 | 41678084 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
225 | Health Curative and Rehabilitative Services | Renovation of the burn unit in Nyamamithi dispensary | To rehabilitate the burn unit in Nyamamithi dispensary to restore functionality | The burn unit in Nyamamithi dispensary rehabilitated | 3110399 | Refurbishment of Buildgs - Oth | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | N/A | 6500000 | 2933106 | 5933106 | FIF | FIF | 5933106 | 0 | 0 | 0 | 0 | 9890259 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
226 | Health Curative and Rehabilitative Services | Renovation works at Kabatini Dispensary in Kabatini Ward | To rehabilitate works at Kabatini Dispensary in Kabatini Ward to restore functionality | Works at Kabatini Dispensary in Kabatini Ward rehabilitated | 3110399 | Refurbishment of Buildgs - Oth | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2020/21 | 2020/21 | N/A | 500000 | 490105 | 490105 | FIF | FIF | 490105 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
227 | Preventive and Promotive Health Services | Renovation Of Segut Dispensary | To rehabilitate Segut Dispensary to restore functionality | Segut Dispensary rehabilitated | 3110399 | Refurbishment of Buildgs - Oth | Molo | Mariashoni | -0.359282 35.7879 2717.8478243641125 9.5 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 2023/24 | 700000 | 0 | 700000 | Equitable | Ward Fund | 700000 | 0 | 1888851 | 0 | 1888851 | 700000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Not sustainable.
228 | Preventive and Promotive Health Services | Renovation Of Sision Dispensary Staff Houses | To rehabilitate Sision Dispensary Staff Houses to restore functionality | Sision Dispensary Staff Houses rehabilitated | 3110399 | Refurbishment of Buildgs - Oth | Naivasha | Naivasha East | -0.867269, 36.535162 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 2024 | 1000000 | 1000000 | 1000000 | Equitable | Ward Fund | 1000000 | 0 | 491490 | 49.1 | 491490 | 1000000 | 508510 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Bad. Objective met: Not yet. Viable: Not yet. Assessor remarks: Incomplete awaiting partitioning and tiles installation.
229 | Preventive and Promotive Health Services | Refurbishment Of Sidai Dispensary | To implement refurbishment of sidai dispensary for access to quality healthcare services | Refurbishment Of Sidai Dispensary completed | 3110399 | Refurbishment of Buildgs - Oth | Subukia | Subukia | -0.01921, 36.196123 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 12/11/24 | 1200000 | 1200000 | 1200000 | Equitable | Ward Fund | 1200000 | 0 | 1998346 | 166.5 | 1998346 | 1200000 | -798346 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes.. Viable: The facility roofs are now okay.. Contractor: Information not available. Assessor remarks: Good work in the renovation..
230 | Preventive and Promotive Health Services | Olenguruone Sub County Hospital water project-sub tank harvesting | To implement olenguruone sub county hospital water project-sub tank harvesting for access to quality healthcare services | Olenguruone Sub County Hospital water project-sub tank harvesting completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Amalo | -0.590917, 35.68616 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | 2023 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: no. Viable: no. Assessor remarks: project not done.
231 | Preventive and Promotive Health Services | Purchase of 10,000 litres plastic tank and other water connections at Kiwamu Health Centre | To procure 10,000 litres plastic tank and other water connections at Kiwamu Health Centre | 10,000 litres plastic tank and other water connections at Kiwamu Health Centre procured | 3110502 | Water Supplies and Sewerage | Bahati | Dundori | -0.237027, 36.167567 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | 2022/2023 | 500000 | 0 | 490100 | Equitable | Ward Fund | 490100 | 0 | 1049618 | 0 | 1049618 | 490100 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yet. Contractor: Marimaya investment ltd. Assessor remarks: Good condition.
232 | Preventive and Promotive Health Services | Connection of Ruguru Dispensary Maternity with water | To implement connection of ruguru dispensary maternity with water for access to quality healthcare services | Connection of Ruguru Dispensary Maternity with water completed | 3110502 | Water Supplies and Sewerage | Bahati | Kabatini | -0.164737, 36.17769 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | N/A | 500000 | 500000 | 500000 | Equitable | Equitable | 500000 | 0 | 0 | 0 | 0 | 2500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes it will. Viable: Yes it will. Assessor remarks: Site handing over done awaiting implementation.
233 | Preventive and Promotive Health Services | Construction of water tank and piping at Lalwet Dispensary | To construct water tank and piping at Lalwet Dispensary | Water tank and piping at Lalwet Dispensary constructed | 3110502 | Water Supplies and Sewerage | Nakuru West | Kapkures | -0.335095, 36.025977 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | 2022/23 | 1000000 | 0 | 1000000 | Equitable | Ward Fund | 1000000 | 0 | 1999600 | 0 | 1999600 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: installed but piping is faulty.
234 | Preventive and Promotive Health Services | Completion of Bahati Health Centre Kitchen | To complete Bahati Health Centre Kitchen | Bahati Health Centre Kitchen completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Bahati | -0.153648, 36.153593 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | 2022/23 | 1000000 | 0 | 1000000 | Equitable | Ward Fund | 1000000 | 0 | 3316491 | 0 | 3316491 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Require equipping.
235 | Preventive and Promotive Health Services | Completion of Bahati Sub County Hospital Mortuary | To complete Bahati Sub County Hospital Mortuary | Bahati Sub County Hospital Mortuary completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Bahati | -0.153829 36.145158 2044.5 32.861000061035156 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | N/A | 3000000 | 3000000 | 3000000 | Equitable | Equitable | 3000000 | 0 | 371316 | 12.4 | 371316 | 382800 | 2628684 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: Partially. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Need replacement with a shade.
236 | Preventive and Promotive Health Services | Completion of Eco Public Toilet Bahati Sub-County hospital | To complete Eco Public Toilet Bahati Sub-County hospital | Eco Public Toilet Bahati Sub-County hospital completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Bahati | -0.169768 36.123245 1919.9000244140625 23.655000686645508 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 382800 | 382800 | Equitable | N/A | 382800 | 0 | 371316 | 97 | 371316 | 382800 | 11484 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete and functional.
237 | Preventive and Promotive Health Services | Construction Of a Mortuary at Bahati Sub-County Hospital | To construct a Mortuary at Bahati Sub-County Hospital | A Mortuary at Bahati Sub-County Hospital constructed | 3110504 | Other Infrastructure and Civil Works | Bahati | Bahati | -0.169779, 36.123233 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | N/A | 5000000 | 0 | 5000000 | Equitable | Ward Fund | 5000000 | 0 | 371316 | 0 | 371316 | 5000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: Mugima. Assessor remarks: Ongoing.
238 | Preventive and Promotive Health Services | Fencing of Bahati Health Centre | To secure Bahati Health Centre through fencing | Bahati Health Centre fenced and secured | 3110504 | Other Infrastructure and Civil Works | Bahati | Bahati | -0.153985 36.15371 2067.2001953125 20 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | N/A | 4000000 | 0 | 572641.15 | Equitable | Ward Fund | 572641.15 | 0 | 3316491 | 0 | 3316491 | 572641 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Mugima. Assessor remarks: To complete the whole facility.
239 | Preventive and Promotive Health Services | Renovation of Fence at Maili Kumi Sub County Hospital | To rehabilitate Fence at Maili Kumi Sub County Hospital to restore functionality | Fence at Maili Kumi Sub County Hospital rehabilitated | 3110504 | Other Infrastructure and Civil Works | Bahati | Bahati | -0.174048 36.134856 2007.2628652101453 5.146999835968018 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | 2021/22 | 1000000 | 142888.9 | 142888.9 | Equitable | N/A | 142888.9 | 0 | 97044 | 67.9 | 97044 | 142889 | 45844.9 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: It is viable. Assessor remarks: The projects is not in use.
240 | Preventive and Promotive Health Services | Completion of Barut Dispensary laboratory (installation of working tables, benches, drawers and drainage inside laboratory) | To complete Barut Dispensary laboratory (installation of working tables, benches, drawers and drainage inside laboratory) | Barut Dispensary laboratory (installation of working tables, benches, drawers and drainage inside laboratory) completed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Barut | -0.327065, 36.056175 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | 2024/2025 | 750000 | 750000 | 750000 | Equitable | Equitable | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Mwaura David. Assessor remarks: The little is stored in the moh office..
241 | Preventive and Promotive Health Services | Construction and equipping of dispensary/maternity at barut ward | To construct and equip dispensary/maternity at barut ward | Dispensary/maternity at barut ward constructed and equipped | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Barut | -0.327065, 36.056176 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2021/2022 | 3499465 | 515266.05 | 515266.05 | Equitable | N/A | 515266.05 | 0 | 349946 | 67.9 | 349946 | 515266 | 165320.05 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Jojewa Enterprises. Assessor remarks: Usable.
242 | Preventive and Promotive Health Services | Construction Of Chain Link Fence & Construction of Gate at Burgei Dispensary | To construct Chain Link Fence & Construction of Gate at Burgei Dispensary | Chain Link Fence & Construction of Gate at Burgei Dispensary constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Barut | -0.338728, 36.037972 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 2024 | 639133 | 639133 | 639133 | Equitable | Ward Fund | 639133 | 0 | 520384 | 81.4 | 520384 | 118749 | 118749 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Raindrops Contractors. Assessor remarks: Good state.
243 | Preventive and Promotive Health Services | Construction Of Perimeter Wall at Barut Dispensary | To construct Perimeter Wall at Barut Dispensary | Perimeter Wall at Barut Dispensary constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Barut | -0.327107, 36.056123 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 2023/24 | 3100000 | 3100000 | 3100000 | Equitable | Ward Fund | 3100000 | 0 | 2622935 | 84.6 | 2622935 | 477065 | 477065 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Frace ventures limited. Assessor remarks: Functional.
244 | Preventive and Promotive Health Services | Construction of a waiting bay with benches and electricity at Bondeni Level IV Hospital and Maternity | To construct a waiting bay with benches and electricity at Bondeni Level IV Hospital and Maternity | A waiting bay with benches and electricity at Bondeni Level IV Hospital and Maternity constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | -0.295657, 36.079913 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | 2024/25 | 1500000 | 1500000 | 1500000 | Equitable | Equitable | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Still at construction process. Viable: Yes. Assessor remarks: On going.
245 | Preventive and Promotive Health Services | Construction of Container Toilets/cabro lions garden | To construct Container Toilets/cabro lions garden | Container Toilets/cabro lions garden constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 2500000 | 150100 | 150100 | Equitable | N/A | 150100 | 0 | 2349900 | 1565.6 | 2349900 | 150100 | -2199800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
246 | Preventive and Promotive Health Services | Renovation of a theater at bondeni maternity | To rehabilitate a theater at bondeni maternity to restore functionality | A theater at bondeni maternity rehabilitated | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | -0.295654, 36.079935 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 978350 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 932131 | 93.2 | 932131 | 1000000 | 67869 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
247 | Preventive and Promotive Health Services | Renovation of public toilets at Abongoloya Estate | To rehabilitate public toilets at Abongoloya Estate to restore functionality | Public toilets at Abongoloya Estate rehabilitated | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | N/A | 2000000 | 2000000 | 2000000 | Equitable | Equitable | 2000000 | 0 | 932131 | 46.6 | 932131 | 1000000 | 1067869 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
248 | Preventive and Promotive Health Services | Construction of a shade at Bavuni/Mugwathi community playground and Wanyororo Cemetery | To construct a shade at Bavuni/Mugwathi community playground and Wanyororo Cemetery | A shade at Bavuni/Mugwathi community playground and Wanyororo Cemetery constructed | 3110504 | Other Infrastructure and Civil Works | Bahati | Dundori | -0.252786 36.183911 2006.5999755859375 15 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | 2021/22 | 600000 | 599260 | 599260 | Equitable | N/A | 599260 | 0 | 581282 | 97 | 581282 | 599260 | 17978 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Alidawn ltd. Assessor remarks: Good should be operationalized.
249 | Preventive and Promotive Health Services | Construction of a toilet at Wanyororo/Mugwathi cemetery | To construct a toilet at Wanyororo/Mugwathi cemetery | A toilet at Wanyororo/Mugwathi cemetery constructed | 3110504 | Other Infrastructure and Civil Works | Bahati | Dundori | -0.253038 36.182841 2006.5999755859375 34.400001525878906 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | 2021/22 | 300000 | 299720 | 299720 | Equitable | N/A | 299720 | 0 | 290728 | 97 | 290728 | 299720 | 8992 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Kundoki enterprises. Assessor remarks: Good.
250 | Preventive and Promotive Health Services | Construction Of Ablution Block at Dundori Health Centre | To construct Ablution Block at Dundori Health Centre | Ablution Block at Dundori Health Centre constructed | 3110504 | Other Infrastructure and Civil Works | Bahati | Dundori | -0.252584, 36.233635 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 2023/2024 | 800000 | 0 | 263500 | Equitable | Ward Fund | 263500 | 0 | 536500 | 0 | 536500 | 263500 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Denken building and construction company. Assessor remarks: In good state.
251 | Preventive and Promotive Health Services | Construction of septic tank and drainage works at Githioro Health centre | To construct septic tank and drainage works at Githioro Health centre | Septic tank and drainage works at Githioro Health centre constructed | 3110504 | Other Infrastructure and Civil Works | Bahati | Dundori | -0.273657, 36.201633 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | 2021/2022 | 5000000 | 1049617.9 | 1049617.9 | Equitable | Ward Fund | 1049617.9 | 0 | 1049618 | 100 | 1049618 | 1049618 | -0.1 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Sanka builders and decorators. Assessor remarks: Good condition.
252 | Preventive and Promotive Health Services | Construction Of Septic Tank at Dundori Health Center | To construct Septic Tank at Dundori Health Center | Septic Tank at Dundori Health Center constructed | 3110504 | Other Infrastructure and Civil Works | Bahati | Dundori | -0.252584, 36.233635 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 2023/2024 | 1700000 | 1700000 | 1700000 | Equitable | Ward Fund | 1700000 | 0 | 1700000 | 100 | 1700000 | 263500 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Denken building and construction company. Assessor remarks: In good state.
253 | Preventive and Promotive Health Services | Construction of toilet at Giachonge dispensary | To construct toilet at Giachonge dispensary | Toilet at Giachonge dispensary constructed | 3110504 | Other Infrastructure and Civil Works | Bahati | Dundori | -0.253047, 36.182863 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | 2021/2022 | 500000 | 495200 | 495200 | Equitable | N/A | 495200 | 0 | 480344 | 97 | 480344 | 495200 | 14856 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
254 | Preventive and Promotive Health Services | Construction of Septic Tank at Eburru Health Centre | To construct Septic Tank at Eburru Health Centre | Septic Tank at Eburru Health Centre constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Eburru/Mbaruk | -0.646154, 36.271816 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 21-22 | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 1199840 | 399.9 | 1199840 | 300000 | -899840 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Bad. Objective met: No. Viable: No value for money. Contractor: Unspecified. Assessor remarks: No such project exist.
255 | Preventive and Promotive Health Services | Fencing of new canaan dispensary phase 1 | To secure new canaan dispensary phase 1 through fencing | New canaan dispensary phase 1 fenced and secured | 3110504 | Other Infrastructure and Civil Works | Gilgil | Eburru/Mbaruk | -0.341013, 36.150603 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 31-07-2023 | 200000 | 200000 | 200000 | Equitable | N/A | 200000 | 0 | 499400 | 249.7 | 499400 | 200000 | -299400 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Eruc Africa Limited. Assessor remarks: Fairy done.
256 | Preventive and Promotive Health Services | Construction of staff houses for Kiptangwanyi Dispensary | To construct staff houses for Kiptangwanyi Dispensary | Staff houses for Kiptangwanyi Dispensary constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Elementaita | -0.567261, 36.114487 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 3500000 | 3484320 | 3484320 | Equitable | N/A | 3484320 | 0 | 3484320 | 100 | 3484320 | 3500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Well done.
257 | Preventive and Promotive Health Services | Construction of staff quarters and Equipping at Muthaiti dispensary | To construct staff quarters and Equipping at Muthaiti dispensary | Staff quarters and Equipping at Muthaiti dispensary constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Elementaita | -0.617292, 36.147138 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 3500000 | 501029 | 501029 | Equitable | N/A | 501029 | 0 | 2998971 | 598.6 | 2998971 | 501029 | -2497942 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: No. Assessor remarks: Not operational.
258 | Preventive and Promotive Health Services | Construction of staff quarters at Munanda dispensary | To construct staff quarters at Munanda dispensary | Staff quarters at Munanda dispensary constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Elementaita | -0.617292, 36.147138 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 4000000 | 90 | 90 | Equitable | N/A | 90 | 0 | 2999910 | 3333233.3 | 2999910 | 90 | -2999820 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: No. Assessor remarks: Not operational.
259 | Preventive and Promotive Health Services | Construction of waiting bay and generator house at Kiptangwanyi | To construct waiting bay and generator house at Kiptangwanyi | Waiting bay and generator house at Kiptangwanyi constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Elementaita | -0.567259, 36.116535 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | N/A | 1500000 | 1500000 | 1500000 | Equitable | Equitable | 1500000 | 0 | 3484320 | 232.3 | 3484320 | 3500000 | -1984320 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
260 | Preventive and Promotive Health Services | Construction of waiting bay at Kiambogo Dispensary | To construct waiting bay at Kiambogo Dispensary | Waiting bay at Kiambogo Dispensary constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Elementaita | -0.602438, 36.130715 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | N/A | 1200000 | 1200000 | 1200000 | Equitable | Equitable | 1200000 | 0 | 4483308 | 373.6 | 4483308 | 90 | -3283308 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Bad. Objective met: Project has not yet started. Viable: Project has not yet started.. Assessor remarks: Project has not yet started.
261 | Preventive and Promotive Health Services | Electricity Connection, Wiring of Three Units and Completion of Drainage and Plumbing at Muthaiti Dispensary | To implement electricity connection, wiring of three units and completion of drainage and plumbing at muthaiti dispensary for access to quality healthcare services | Electricity Connection, Wiring of Three Units and Completion of Drainage and Plumbing at Muthaiti Dispensary completed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Elementaita | -0.617558, 36.14627 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 2023/24 | 750000 | 750000 | 750000 | Equitable | Ward Fund | 750000 | 0 | 746770 | 99.6 | 746770 | 3230 | 3230 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: No. Viable: Yes, although has not been operationalized. Assessor remarks: Electricity connection not done yet..
262 | Preventive and Promotive Health Services | Expansion of Kiptangwany Health Facility | To expand Kiptangwany Health Facility to increase capacity | Kiptangwany Health Facility expanded | 3110504 | Other Infrastructure and Civil Works | Gilgil | Elementaita | -0.567, 36.11696 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | N/A | 7000000 | 0 | 7000000 | Equitable | N/A | 7000000 | 0 | 0 | 0 | 0 | 7000000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
263 | Preventive and Promotive Health Services | Fencing of Muthaiti/ Munanda/Mugaa Elementaita dispensaries | To secure Muthaiti/ Munanda/Mugaa Elementaita dispensaries through fencing | Muthaiti/ Munanda/Mugaa Elementaita dispensaries fenced and secured | 3110504 | Other Infrastructure and Civil Works | Gilgil | Elementaita | -0.489548, 36.155317 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 4000000 | 3149990 | 3149990 | Equitable | N/A | 3149990 | 0 | 3149990 | 100 | 3149990 | 3200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Fence done at Mugaa dispensary.
264 | Preventive and Promotive Health Services | Kiambogo dispensary refurbishment - refurbishment and equipping of kiambogo dispensary | To implement kiambogo dispensary refurbishment - refurbishment and equipping of kiambogo dispensary for access to quality healthcare services | Kiambogo dispensary refurbishment - refurbishment and equipping of kiambogo dispensary completed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Elementaita | -0.602163, 36.131095 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 4500000 | 0 | 727214 | Equitable | Ward Fund | 727214 | 0 | 3272817 | 0 | 3272817 | 727214 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good working conditions..
265 | Preventive and Promotive Health Services | Partition Of Rooms and Equipping with Furniture of Old Maternity Block at Miti Mingi Dispensary | To implement partition of rooms and equipping with furniture of old maternity block at miti mingi dispensary for access to quality healthcare services | Partition Of Rooms and Equipping with Furniture of Old Maternity Block at Miti Mingi Dispensary completed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Elementaita | -0.518112, 36.108533 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | N/A | 500000 | 500000 | 500000 | Equitable | Ward Fund | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Not done.
266 | Preventive and Promotive Health Services | Purchase and Installation of Power Backup at Kiambogo Health Centre | To procure and install Power Backup at Kiambogo Health Centre | Power Backup at Kiambogo Health Centre procured and installed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Elementaita | -0.273657, 36.201903 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 2022/2023 | 500000 | 500000 | 500000 | Equitable | Ward Fund | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Marimaya investment ltd. Assessor remarks: Project has not yet commenced.
267 | Preventive and Promotive Health Services | Construction of a Sewer line in Kimathi Estate | To construct a Sewer line in Kimathi Estate | A Sewer line in Kimathi Estate constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Flamingo | -0.305464 36.078831 1793.3 6.300000190734863 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 2500000 | 931 | 931 | Equitable | N/A | 931 | 0 | 2499069 | 268428.5 | 2499069 | 931 | -2498138 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Operational.
268 | Preventive and Promotive Health Services | Construction of Modern container (40ft) toilet with Cabro and construction of a septic tank at Lakeview Estate (KWS) | To construct Modern container (40ft) toilet with Cabro and construction of a septic tank at Lakeview Estate (KWS) | Modern container (40ft) toilet with Cabro and construction of a septic tank at Lakeview Estate (KWS) constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Flamingo | -0.308199 36.079199 1788.5 27.468000411987305 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | 2021/22 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1278541 | 85.2 | 1278541 | 1500000 | 221459 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Not yet. Contractor: CHIBON SUPLLIES LTD. Assessor remarks: Not complete , Not in operation.
269 | Preventive and Promotive Health Services | Rehabilitation and connection to sewer of 1 no toilet block at kimathi estate | To rehabilitate connection to sewer of 1 no toilet block at kimathi estate to restore functionality | Connection to sewer of 1 no toilet block at kimathi estate rehabilitated | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Flamingo | -0.303761, 36.078667 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/2021 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1196440 | 99.7 | 1196440 | 1200000 | 3560 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not provided. Assessor remarks: Completed and in use.
270 | Preventive and Promotive Health Services | Rehabilitation and connection to sewer of 4. No of toilet blocks at Kimathi Estate | To rehabilitate connection to sewer of 4. No of toilet blocks at Kimathi Estate to restore functionality | Connection to sewer of 4. No of toilet blocks at Kimathi Estate rehabilitated | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Flamingo | -0.303761, 36.078667 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | 2020/2021 | 4800000 | 4800000 | 4800000 | Equitable | N/A | 4800000 | 0 | 4690104 | 97.7 | 4690104 | 1200000 | 109896 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not provided. Assessor remarks: Completed and in use.
271 | Preventive and Promotive Health Services | Rehabilitation of 5 toilets at kimathi Estate | To rehabilitate 5 toilets at kimathi Estate to restore functionality | 5 toilets at kimathi Estate rehabilitated | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Flamingo | -0.303736, 36.078702 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/2020 | 8500000 | 300100 | 300100 | Equitable | N/A | 300100 | 0 | 5699900 | 1899.3 | 5699900 | 300100 | -5399800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: In use and in good condition.
272 | Preventive and Promotive Health Services | Completion of fence and construction of waiting bay at Karura Dispensary | To complete fence and construction of waiting bay at Karura Dispensary | Fence and construction of waiting bay at Karura Dispensary completed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Gilgil | -0.503777 36.326579 1989.300048828125 4.453999996185303 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | N/A | 1000000 | 0 | 1000000 | Equitable | Ward Fund | 1000000 | 0 | 263450 | 0 | 263450 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Esp market ongoing.
273 | Preventive and Promotive Health Services | Construction of waiting bay shade, Chain link fencing and gate installation at Karura dispensary | To construct waiting bay shade, Chain link fencing and gate installation at Karura dispensary | Waiting bay shade, Chain link fencing and gate installation at Karura dispensary constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Gilgil | -0.486113 36.339979 1968.391845703125 5.25 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | 2021/22 | 1000000 | 387908 | 387908 | Equitable | N/A | 387908 | 0 | 263450 | 67.9 | 263450 | 387908 | 124458 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: No play equipments, need for electricity connection, water connection and additional classroom.
274 | Preventive and Promotive Health Services | Construction of waiting bay shade with seats at Kikopey Health Center | To construct waiting bay shade with seats at Kikopey Health Center | Waiting bay shade with seats at Kikopey Health Center constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Gilgil | -0.481819, 36.290367 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | 2021/22 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 499700 | 99.9 | 499700 | 387908 | 300 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Pezina enterprises. Assessor remarks: There was no County tag/sign board on the project..
275 | Preventive and Promotive Health Services | Gilgil cemetery container toilets and tanks with stand | To implement gilgil cemetery container toilets and tanks with stand for access to quality healthcare services | Gilgil cemetery container toilets and tanks with stand completed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Gilgil | -0.510381, 36.324675 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 1998800 | 1998800 | Equitable | N/A | 1998800 | 0 | 1938836 | 97 | 1938836 | 1998800 | 59964 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/S Natash Limited. Assessor remarks: Operational and installation good condition.
276 | Health Curative and Rehabilitative Services | Completion of Maai Mahiu Hospital (Auxiliary works, Perimeter wall, Morgue, Laundry, Kitchen & Storm water drainage) | To complete Maai Mahiu Hospital (Auxiliary works, Perimeter wall, Morgue, Laundry, Kitchen & Storm water drainage) | Maai Mahiu Hospital (Auxiliary works, Perimeter wall, Morgue, Laundry, Kitchen & Storm water drainage) completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | N/A | 35000000 | 30000000 | 30000000 | N/A | N/A | 30000000 | 0 | 0 | 0 | 0 | 0 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
277 | Preventive and Promotive Health Services | Construction of an Ablution block at Subukia National Shrine | To construct an Ablution block at Subukia National Shrine | An Ablution block at Subukia National Shrine constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 2023/24 | 5000000 | 0 | 594144.5 | N/A | N/A | 594144.5 | 0 | 2533450 | 100 | 2533450 | 0 | -2533450 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
278 | Health Curative and Rehabilitative Services | Construction of covered walkway in Bondeni | To construct covered walkway in Bondeni | Covered walkway in Bondeni constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | N/A | 3650000 | 0 | 3650000 | N/A | N/A | 3650000 | 0 | 3321916 | 100 | 3321916 | 9890259 | -3321916 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
279 | Health Curative and Rehabilitative Services | Construction of generator houses (Mirugi Kariuki, Githioro, Keringet, Langalanga, Kiptangwanyi, Njoro, Maai Mahiu & Bondeni) | To construct generator houses (Mirugi Kariuki, Githioro, Keringet, Langalanga, Kiptangwanyi, Njoro, Maai Mahiu & Bondeni) | Generator houses (Mirugi Kariuki, Githioro, Keringet, Langalanga, Kiptangwanyi, Njoro, Maai Mahiu & Bondeni) constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | N/A | 2800000 | 0 | 2800000 | N/A | N/A | 2800000 | 0 | 0 | 0 | 0 | 0 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
280 | Health Curative and Rehabilitative Services | Construction of new Outpatient Ablution Block in Njoro SC Hospital | To construct new Outpatient Ablution Block in Njoro SC Hospital | New Outpatient Ablution Block in Njoro SC Hospital constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | N/A | 5000000 | 4000000 | 4000000 | N/A | N/A | 4000000 | 0 | 750000 | 18.8 | 750000 | 0 | 3250000 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
281 | Preventive and Promotive Health Services | Construction of public toilets at the Bus/Matatu Parks | To construct public toilets at the Bus/Matatu Parks | Public toilets at the Bus/Matatu Parks constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 4000000 | 2533450 | 2533450 | N/A | N/A | 2533450 | 0 | 2533450 | 100 | 2533450 | 9890259 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
282 | Preventive and Promotive Health Services | Construction of Septic Tank at Keringet Sub County Hospital | To construct Septic Tank at Keringet Sub County Hospital | Septic Tank at Keringet Sub County Hospital constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 1882832.03 | 2000000 | 2000000 | N/A | N/A | 2000000 | 0 | 750000 | 37.5 | 750000 | 0 | 1250000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
283 | Health Curative and Rehabilitative Services | Equipping, Renovation and Installation of 3-Phase Electricity at Langa Langa Hospital | To implement equipping, renovation and installation of 3-phase electricity at langa langa hospital for access to quality healthcare services | Equipping, Renovation and Installation of 3-Phase Electricity at Langa Langa Hospital completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | N/A | 4000000 | 0 | 4000000 | N/A | N/A | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
284 | Health Curative and Rehabilitative Services | Fencing of Annex hospital land | To secure Annex hospital land through fencing | Annex hospital land fenced and secured | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | N/A | 30000000 | 0 | 30000000 | N/A | N/A | 30000000 | 0 | 750000 | 100 | 750000 | 0 | -750000 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
285 | Health Curative and Rehabilitative Services | Fencing of Barnabas IDP dispensary in Eburru/Mbaruk Ward | To secure Barnabas IDP dispensary in Eburru/Mbaruk Ward through fencing | Barnabas IDP dispensary in Eburru/Mbaruk Ward fenced and secured | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2020/21 | 2020/21 | N/A | 500000 | 499400 | 499400 | N/A | N/A | 499400 | 0 | 0 | 0 | 0 | 0 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
286 | Health Curative and Rehabilitative Services | Gilgil hospital-wiring and generator | To implement gilgil hospital-wiring and generator for access to quality healthcare services | Gilgil hospital-wiring and generator completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | N/A | 4000000 | 0 | 1211339.2 | N/A | N/A | 1211339.2 | 0 | 0 | 0 | 0 | 0 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
287 | Health Curative and Rehabilitative Services | Other Developments - (FIF Facilities) | To implement other developments - (fif facilities) for access to quality healthcare services | Other Developments - (FIF Facilities) completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2023/24 | N/A | 170000000 | 240000000 | 0 | FIF | N/A | 0 | 228734837 | 10122860 | 4.2 | 10122860 | 70000000 | 229877140 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
288 | Health Curative and Rehabilitative Services | Proposed Construction Of Incinerator And Septic Tank At Ruguru Dispensary In Kabatini Ward | To undertake the proposed Construction Of Incinerator And Septic Tank At Ruguru Dispensary In Kabatini Ward | Proposed Construction Of Incinerator And Septic Tank At Ruguru Dispensary In Kabatini Ward implemented | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 418810.9 | 418810.9 | N/A | N/A | 418810.9 | 0 | 0 | 0 | 0 | 0 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
289 | Preventive and Promotive Health Services | Fencing Of Nyamathi Dispensary | To secure Nyamathi Dispensary through fencing | Nyamathi Dispensary fenced and secured | 3110504 | Other Infrastructure and Civil Works | Naivasha | Hells Gate | -0.780696, 36.512667 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 2023/24 | 600000 | 600000 | 600000 | Equitable | Ward Fund | 600000 | 0 | 445750 | 74.3 | 445750 | 600000 | 154250 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Vency enterprises limited. Assessor remarks: The project is in good condition.
290 | Preventive and Promotive Health Services | Construction of a waiting bay at Muriundu Dispensary | To construct a waiting bay at Muriundu Dispensary | A waiting bay at Muriundu Dispensary constructed | 3110504 | Other Infrastructure and Civil Works | Bahati | Kabatini | -0.231682, 36.155385 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | 2025 | 1200000 | 1200000 | 1000000 | Equitable | Equitable | 1000000 | 0 | 2483264 | 206.9 | 2483264 | 44196 | -1283264 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: Kirgit ventures limited. Assessor remarks: Complete yes to be commissioned.
291 | Preventive and Promotive Health Services | Fencing of Kabatini hospital | To secure Kabatini hospital through fencing | Kabatini hospital fenced and secured | 3110504 | Other Infrastructure and Civil Works | Bahati | Kabatini | -0.213583, 36.162957 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2021 | 2000000 | 271520.4 | 271520.4 | Equitable | N/A | 271520.4 | 0 | 729109 | 268.5 | 729109 | 271520 | -457588.6 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Jogra hardware & construction ltd. Assessor remarks: It was done but the funds were not enough to complete one side.
292 | Preventive and Promotive Health Services | Painting of kabatini health center | To implement painting of kabatini health center for access to quality healthcare services | Painting of kabatini health center completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Kabatini | -0.213099, 36.162837 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 30th may 2023 | 399350 | 399350 | 399350 | Equitable | N/A | 399350 | 0 | 2000000 | 500.8 | 2000000 | 399350 | -1600650 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Jogra hardware and construction. Assessor remarks: Painting was done very well.
293 | Preventive and Promotive Health Services | Construction of Kirima Laboratory and fencing | To construct Kirima Laboratory and fencing | Kirima Laboratory and fencing constructed | 3110504 | Other Infrastructure and Civil Works | Subukia | Kabazi | -0.14539, 36.04312 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | 31/7/2025 | 1500000 | 0 | 1500000 | Equitable | Equitable | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Humble touch designers. Assessor remarks: Well maintained.
294 | Preventive and Promotive Health Services | Construction of placenta disposal unit and installation solar powered security lights at Solai Health Centre | To construct placenta disposal unit and installation solar powered security lights at Solai Health Centre | Placenta disposal unit and installation solar powered security lights at Solai Health Centre constructed | 3110504 | Other Infrastructure and Civil Works | Subukia | Kabazi | -0.106772 36.057525 1617.2 12.600000381469727 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | N/A | 293160 | 293160 | 293160 | Equitable | Equitable | 293160 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: Start back engineering and consultancy company ltdncy. Assessor remarks: Requires completion.
295 | Preventive and Promotive Health Services | Construction of a perimeter wall at Ingobor Health centre | To construct a perimeter wall at Ingobor Health centre | A perimeter wall at Ingobor Health centre constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kapkures | -0.324324, 36.036613 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 5 | 5 | Equitable | N/A | 5 | 0 | 1499995 | 29999900 | 1499995 | 5 | -1499990 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Security was enhanced. Assessor remarks: Well done and functional.
296 | Preventive and Promotive Health Services | Completion and equipping youth health friendly center | To complete and equip youth health friendly center | Youth health friendly center completed and equipped | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kaptembwo | -0.30474 36.055271 1794.3205995676594 60 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | N/A | 3000000 | 500055 | 500055 | Equitable | N/A | 500055 | 0 | 496000 | 99.2 | 496000 | 500055 | 4055 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: It met the needs of the residents. Contractor: VILALOXA STORES. Assessor remarks: It's fully equipped.
297 | Preventive and Promotive Health Services | Construction of pit latrines at kapkores dispensary | To construct pit latrines at kapkores dispensary | Pit latrines at kapkores dispensary constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Keringet | -0.466652 35.652975 2634.7999999999997 17 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 250000 | 250000 | 250000 | Equitable | N/A | 250000 | 0 | 250000 | 100 | 250000 | 250000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operation al.
298 | Preventive and Promotive Health Services | Construction of pit latrines at tegat dispensary | To construct pit latrines at tegat dispensary | Pit latrines at tegat dispensary constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Keringet | -0.466652 35.652975 2634.7999999999997 17 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 250000 | 250000 | 250000 | Equitable | N/A | 250000 | 0 | 250000 | 100 | 250000 | 250000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operation al.
299 | Preventive and Promotive Health Services | Renovation of tegat and kapkores dispensaries | To rehabilitate tegat and kapkores dispensaries to restore functionality | Tegat and kapkores dispensaries rehabilitated | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Keringet | -0.466475 35.653347 2574.2999999999997 6.599999904632568 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 412900 | 60793 | 60793 | Equitable | N/A | 60793 | 0 | 352087 | 579.2 | 352087 | 60793 | -291294 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
300 | Preventive and Promotive Health Services | Renovation, drainage and electrification of Kihingo Maternity Health centre | To implement renovation, drainage and electrification of kihingo maternity health centre for access to quality healthcare services | Renovation, drainage and electrification of Kihingo Maternity Health centre completed | 3110504 | Other Infrastructure and Civil Works | Njoro | Kihingo | -0.440317, 35.974925 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | 2022 | 1140364 | 1140364 | 1140364 | Equitable | N/A | 1140364 | 0 | 1099710 | 96.4 | 1099710 | 0 | 40654 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires Renovation.
301 | Preventive and Promotive Health Services | Renovation of Kihingo centre toilet structure | To rehabilitate Kihingo centre toilet structure to restore functionality | Kihingo centre toilet structure rehabilitated | 3110504 | Other Infrastructure and Civil Works | Njoro | Kihingo | -0.43402, 35.972217 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | 2024 | 594009 | 0 | 594009 | Equitable | Ward Fund | 594009 | 0 | 0 | 0 | 0 | 594009 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires maintenance.
302 | Preventive and Promotive Health Services | Construction of Kiplemeiywo and Kokwet toilets | To construct Kiplemeiywo and Kokwet toilets | Kiplemeiywo and Kokwet toilets constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.534567, 35.579018 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | 2025 | 1900000 | 1900000 | 1900000 | Equitable | Equitable | 1900000 | 0 | 1021185 | 53.7 | 1021185 | 3562 | 878815 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Yes. Assessor remarks: The toilets need to be painted..
303 | Preventive and Promotive Health Services | Construction of Githima dispensary nurse residential house | To construct Githima dispensary nurse residential house | Githima dispensary nurse residential house constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Kiptororo | -0.325895, 35.49856 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2020/21 | 2020/21 | N/A | 1494150 | 1494150 | 1494150 | Equitable | N/A | 1494150 | 0 | 543281 | 36.4 | 543281 | 1494150 | 950869 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
304 | Preventive and Promotive Health Services | Murinduko Dispensary-Maternity Wing - On Going | To implement murinduko dispensary-maternity wing - on going for access to quality healthcare services | Murinduko Dispensary-Maternity Wing - On Going completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Kiptororo | -0.3246 35.498852 2546.3 22.100000381469727 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 3200000 | 948599.45 | 948599.45 | Equitable | Ward Fund | 948599.45 | 0 | 948599 | 100 | 948599 | 0 | 0.45 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The project is not functioning.
305 | Preventive and Promotive Health Services | Construction of 5 sanitary blocks in Kivumbini 1 and 2 | To construct 5 sanitary blocks in Kivumbini 1 and 2 | 5 sanitary blocks in Kivumbini 1 and 2 constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Kivumbini | -0.298136, 36.083323 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | 2021/22 | 10000000 | 9889232 | 9889232 | Equitable | N/A | 9889232 | 0 | 9592555 | 97 | 9592555 | 9889232 | 296677 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Improved sanitation.
306 | Preventive and Promotive Health Services | Construction of four sanitation blocks at Kivumbini I & II estate | To construct four sanitation blocks at Kivumbini I & II estate | Four sanitation blocks at Kivumbini I & II estate constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Kivumbini | -0.298107, 36.083567 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2024 | 10000000 | 1408217.4 | 1408217.4 | Equitable | Ward Fund | 1408217.4 | 0 | 3628118 | 257.6 | 3628118 | 1408217 | -2219900.6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Contractor: king reflectors. Assessor remarks: project functional.
307 | Preventive and Promotive Health Services | Construction of sanitation block at kivumbini 1 | To construct sanitation block at kivumbini 1 | Sanitation block at kivumbini 1 constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Kivumbini | -0.298107, 36.083567 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2024 | 1880540 | 1880540 | 1880540 | Equitable | Ward Fund | 1880540 | 0 | 1880540 | 100 | 1880540 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Contractor: king reflectors. Assessor remarks: project functional.
308 | Preventive and Promotive Health Services | Construction of sanitation block at kivumbini 2 | To construct sanitation block at kivumbini 2 | Sanitation block at kivumbini 2 constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Kivumbini | -0.298107, 36.083567 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2024 | 1880540 | 1880540 | 1880540 | Equitable | Ward Fund | 1880540 | 0 | 1880540 | 100 | 1880540 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Contractor: king reflectors. Assessor remarks: project functional.
309 | Preventive and Promotive Health Services | Construction of perimeter wall at Kayole dispensary | To construct perimeter wall at Kayole dispensary | Perimeter wall at Kayole dispensary constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Lakeview | -0.751713, 36.457225 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 2500000 | 2770 | 2770 | Equitable | N/A | 2770 | 0 | 2497230 | 90152.7 | 2497230 | 2770 | -2494460 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Repair the gate.
310 | Preventive and Promotive Health Services | Construction of Waiting Bay and installation of screens at Kayole Dispensary | To construct Waiting Bay and installation of screens at Kayole Dispensary | Waiting Bay and installation of screens at Kayole Dispensary constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Lakeview | -0.751833, 36.456913 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1428852 | 95.3 | 1428852 | 1500000 | 71148 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Provide benches, repair the floor to a smooth finish to allow easy cleaning, paint dirty walls.
311 | Preventive and Promotive Health Services | Construction of shed at ndimu ndimu hospital | To construct shed at ndimu ndimu hospital | Shed at ndimu ndimu hospital constructed | 3110504 | Other Infrastructure and Civil Works | Bahati | Lanet/Umoja | -0.303119, 36.171653 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | 2021/22 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 498700 | 99.7 | 498700 | 0 | 1300 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes ,very viable. Assessor remarks: Functional.
312 | Preventive and Promotive Health Services | Equipping Of Murunyu Health Center & Construction Staff Toilet, Waiting Bay and Tanks | To equip Murunyu Health Center & Construction Staff Toilet, Waiting Bay and Tanks with necessary facilities and equipment | Murunyu Health Center & Construction Staff Toilet, Waiting Bay and Tanks equipped | 3110504 | Other Infrastructure and Civil Works | Bahati | Lanet/Umoja | -0.2479, 36.15204 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 2023/2024 | 3000000 | 0 | 3000000 | Equitable | Ward Fund | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes but needs staffing and equiping. Assessor remarks: Not operational.
313 | Preventive and Promotive Health Services | Construction of a Laboratory Area and patient's toilet at Industrial Area (Viwanda) Health Center | To construct a Laboratory Area and patient's toilet at Industrial Area (Viwanda) Health Center | A Laboratory Area and patient's toilet at Industrial Area (Viwanda) Health Center constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | London | -0.282698, 36.043792 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | No there | 1100000 | 1100000 | 1100000 | Equitable | N/A | 1100000 | 0 | 2494189 | 226.7 | 2494189 | 1100000 | -1394189 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes. Assessor remarks: The projec was handed over to the contractor but it has not started.
314 | Preventive and Promotive Health Services | Construction of a six door Modern toilet at Industrial area clinic | To construct a six door Modern toilet at Industrial area clinic | A six door Modern toilet at Industrial area clinic constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | London | -0.283, 36.043838 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | N/A | 1400000 | 0 | 1400000 | Equitable | Ward Fund | 1400000 | 0 | 2494189 | 0 | 2494189 | 1400000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: Site handed over to contractor-yet to start ,photos taken of where the toilet should be constricted.
315 | Preventive and Promotive Health Services | Construction of patient's toilet at FITC Dispensary | To construct patient's toilet at FITC Dispensary | Patient's toilet at FITC Dispensary constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | London | -0.28233, 36.053786 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | 2022/23 | 1000000 | 0 | 1000000 | Equitable | Ward Fund | 1000000 | 0 | 1999932 | 0 | 1999932 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes but not the toilet. Viable: Yes. Assessor remarks: The waiting bay is good but the toilet is not functioning.
316 | Preventive and Promotive Health Services | Construction of waiting bay & patient's toilet at FITC Dispensary | To construct waiting bay & patient's toilet at FITC Dispensary | Waiting bay & patient's toilet at FITC Dispensary constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | London | -0.28233, 36.053786 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | 2022/23 | 1000000 | 1000000 | 1000000 | Equitable | Ward Fund | 1000000 | 0 | 1999932 | 200 | 1999932 | 1000000 | -999932 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes but not the toilet. Viable: Yes. Assessor remarks: The waiting bay is good but the toilet is not functioning.
317 | Preventive and Promotive Health Services | Renovation Of Public Toilets at North Cemetery & Installation of Water Tank 10,000litres | To rehabilitate Public Toilets at North Cemetery & Installation of Water Tank 10,000litres to restore functionality | Public Toilets at North Cemetery & Installation of Water Tank 10,000litres rehabilitated | 3110504 | Other Infrastructure and Civil Works | Nakuru West | London | -0.278494, 36.072995 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 2025 | 600000 | 0 | 600000 | Equitable | Ward Fund | 600000 | 0 | 0 | 0 | 0 | 600000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Good job.
318 | Preventive and Promotive Health Services | Longonot Dispensary-Replacing Asbestos with Iron Sheets,gutters and others | To implement longonot dispensary-replacing asbestos with iron sheets,gutters and others for access to quality healthcare services | Longonot Dispensary-Replacing Asbestos with Iron Sheets,gutters and others completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maai Mahiu | -0.884377, 36.497402 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | N/A | 1500000 | 738000 | 738000 | Equitable | N/A | 738000 | 0 | 762000 | 103.3 | 762000 | 738000 | -24000 | Stalled | 75 | 100 | To be retendered | 2019 | N/A | -24000 | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes.. Viable: Yes. Assessor remarks: Gutters not yet installed, the roof is good condition..
319 | Preventive and Promotive Health Services | Maai Mahiu Health Centre-Construction of staff houses | To implement maai mahiu health centre-construction of staff houses for access to quality healthcare services | Maai Mahiu Health Centre-Construction of staff houses completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maai Mahiu | -0.976952, 36.584984 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 1915 | 1915 | Equitable | N/A | 1915 | 0 | 2998085 | 156558 | 2998085 | 1915 | -2996170 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good state.
320 | Preventive and Promotive Health Services | Construction of a 2-door pit latrine at Maiella Health Centre | To construct a 2-door pit latrine at Maiella Health Centre | A 2-door pit latrine at Maiella Health Centre constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maiella | -0.887702, 36.200573 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | 2025 | 600000 | 600000 | 600000 | Equitable | Equitable | 600000 | 0 | 3272346 | 545.4 | 3272346 | 226559 | -2672346 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Not yet. Assessor remarks: Work in Progress.
321 | Preventive and Promotive Health Services | Construction of a waiting bay at Karati Health Centre | To construct a waiting bay at Karati Health Centre | A waiting bay at Karati Health Centre constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Malewa West | -0.630631, 36.41662 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | N/A | 1200000 | 1200000 | 1200000 | Equitable | Equitable | 1200000 | 0 | 1304913 | 108.7 | 1304913 | 195087 | -104913 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Bad. Objective met: No. Viable: Yes. Assessor remarks: The contractor has not reported but the contract is awarded.
322 | Preventive and Promotive Health Services | Construction of Karate dispensary toilet | To construct Karate dispensary toilet | Karate dispensary toilet constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Malewa West | -0.702703, 36.471211 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | 2021/22 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 499400 | 99.9 | 499400 | 0 | 600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yea. Assessor remarks: In good condition.
323 | Preventive and Promotive Health Services | Improvement of laboratory, maternity block and equipping of Karati dispensary. | To implement improvement of laboratory, maternity block and equipping of karati dispensary. for access to quality healthcare services | Improvement of laboratory, maternity block and equipping of Karati dispensary. completed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Malewa West | -0.702703 36.291018 0 2000 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | 2022/23 | 2000000 | 1997800 | 1997800 | Equitable | Ward Fund | 1997800 | 0 | 1997525 | 100 | 1997525 | 275 | 275 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
324 | Preventive and Promotive Health Services | Construction Of a Chain link Fence at Kapsinendet and Segut Dispensaries | To construct a Chain link Fence at Kapsinendet and Segut Dispensaries | A Chain link Fence at Kapsinendet and Segut Dispensaries constructed | 3110504 | Other Infrastructure and Civil Works | Molo | Mariashoni | -0.361072, 35.788611 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 2023/24 | 2000000 | 2000000 | 2000000 | Equitable | Ward Fund | 2000000 | 0 | 1926280 | 96.3 | 1926280 | 2000000 | 73720 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Offers security for public infrastructure.
325 | Preventive and Promotive Health Services | Construction of four door toilet at Marioshoni Health center | To construct four door toilet at Marioshoni Health center | Four door toilet at Marioshoni Health center constructed | 3110504 | Other Infrastructure and Civil Works | Molo | Mariashoni | -0.368689, 35.820567 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | 2021/22 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 600000 | 100 | 600000 | 151759 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
326 | Preventive and Promotive Health Services | Construction of Mariashoni Center public toilet | To construct Mariashoni Center public toilet | Mariashoni Center public toilet constructed | 3110504 | Other Infrastructure and Civil Works | Molo | Mariashoni | -0.378378, 35.820601 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | N/A | 1000000 | 1000000 | 1000000 | Equitable | Equitable | 1000000 | 0 | 600000 | 60 | 600000 | 0 | 400000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Not yet. Assessor remarks: Not done.
327 | Preventive and Promotive Health Services | Construction Of Sanitary Facility at Segut Dispensary | To construct Sanitary Facility at Segut Dispensary | Sanitary Facility at Segut Dispensary constructed | 3110504 | Other Infrastructure and Civil Works | Molo | Mariashoni | -0.361136, 35.788569 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 2023/24 | 1000000 | 0 | 1000000 | Equitable | Ward Fund | 1000000 | 0 | 1888851 | 0 | 1888851 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: No service.
328 | Preventive and Promotive Health Services | Construction of dispensary in Tipis | To construct dispensary in Tipis | Dispensary in Tipis constructed | 3110504 | Other Infrastructure and Civil Works | Njoro | Mau Narok | -0.597785 35.999365 2574.8999999999996 3.4000000953674316 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 3590190 | 3590190 | 3590190 | Equitable | N/A | 3590190 | 0 | 3590190 | 100 | 3590190 | 3600000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: Not viable. Assessor remarks: Bad state of repair.
329 | Preventive and Promotive Health Services | Construction of modern Public toilet at Mau Narok | To construct modern Public toilet at Mau Narok | Modern Public toilet at Mau Narok constructed | 3110504 | Other Infrastructure and Civil Works | Njoro | Mau Narok | -0.600012, 36.007202 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 607 | 607 | Equitable | N/A | 607 | 0 | 1499393 | 247017 | 1499393 | 607 | -1498786 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: viable. Assessor remarks: good state of repair.
330 | Preventive and Promotive Health Services | Construction of Pit Latrines at Kianjoya and Likia Dispensaries | To construct Pit Latrines at Kianjoya and Likia Dispensaries | Pit Latrines at Kianjoya and Likia Dispensaries constructed | 3110504 | Other Infrastructure and Civil Works | Njoro | Mau Narok | -0.53502, 35.967093 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | 2022/2023 | 1244806 | 1197370 | 1197370 | Equitable | Ward Fund | 1197370 | 0 | 1197370 | 100 | 1197370 | 1197370 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Assessor remarks: In good state of repair.
331 | Preventive and Promotive Health Services | Construction of 4 door toilet for outpatient at Kimugul, Teret and Kaptich Dispensary | To construct 4 door toilet for outpatient at Kimugul, Teret and Kaptich Dispensary | 4 door toilet for outpatient at Kimugul, Teret and Kaptich Dispensary constructed | 3110504 | Other Infrastructure and Civil Works | Njoro | Mauche | -0.492798, 35.966837 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | 2025 | 3500000 | 3500000 | 2700000 | Equitable | Equitable | 2700000 | 0 | 504400 | 14.4 | 504400 | 100 | 2995600 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Not started.
332 | Preventive and Promotive Health Services | Construction of Toilet at Mosop Dispensary | To construct Toilet at Mosop Dispensary | Toilet at Mosop Dispensary constructed | 3110504 | Other Infrastructure and Civil Works | Njoro | Mauche | -0.551906 35.991392 2525.7 12.5 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | 2022/23 | 565427 | 504500 | 504500 | Equitable | Ward Fund | 504500 | 0 | 504400 | 100 | 504400 | 100 | 100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Don't know. Assessor remarks: Yet to be used.
333 | Preventive and Promotive Health Services | Completion of menengai dispensary perimeter wall | To complete menengai dispensary perimeter wall | Menengai dispensary perimeter wall completed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Menengai | -0.266242, 36.100628 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 498000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 483060 | 96.6 | 483060 | 500000 | 16940 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ascom ventures. Assessor remarks: Completed.
334 | Preventive and Promotive Health Services | Construction of teachers market toilet | To construct teachers market toilet | Teachers market toilet constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Menengai | -0.266244, 36.100635 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2023/25 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499590 | 100 | 1499590 | 1500000 | 410 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: Prime rift traders. Assessor remarks: Completed.
335 | Preventive and Promotive Health Services | Fencing of Menengai Dispensary | To secure Menengai Dispensary through fencing | Menengai Dispensary fenced and secured | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Menengai | -0.275604, 36.11132 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 6745 | 6745 | Equitable | N/A | 6745 | 0 | 1493255 | 22138.7 | 1493255 | 6745 | -1486510 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs repainting.
336 | Preventive and Promotive Health Services | Construction of kirobon toilets(coolant) | To construct kirobon toilets(coolant) | Kirobon toilets(coolant) constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Menengai West | -0.269996 36.031468 1924.8 4.900000095367432 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 79 | 79 | Equitable | N/A | 79 | 0 | 999921 | 1265722.8 | 999921 | 79 | -999842 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
337 | Preventive and Promotive Health Services | Construction of Modern Shed with Concrete seats at Molo Cemetery | To construct Modern Shed with Concrete seats at Molo Cemetery | Modern Shed with Concrete seats at Molo Cemetery constructed | 3110504 | Other Infrastructure and Civil Works | Molo | Molo | -0.380641 35.796196 2793.679531111378 6 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | N/A | 2500000 | 2500000 | 2500000 | Equitable | Ward Fund | 2500000 | 0 | 0 | 0 | 0 | 2500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Partially. Viable: Partially. Assessor remarks: The toilet is non existent.
338 | Preventive and Promotive Health Services | Construction of a kitchen for the sachangwan dispensary | To construct a kitchen for the sachangwan dispensary | A kitchen for the sachangwan dispensary constructed | 3110504 | Other Infrastructure and Civil Works | Molo | Molo Central | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 877800 | 877800 | 877800 | Equitable | N/A | 877800 | 0 | 2533450 | 288.6 | 2533450 | 9890259 | -1655650 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
339 | Preventive and Promotive Health Services | Completion and equipping of ngecha health center | To complete and equip ngecha health center | Ngecha health center completed and equipped | 3110504 | Other Infrastructure and Civil Works | Rongai | Mosop | -0.296143 35.958896 2109.1000000000004 8.399999618530273 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 499990 | 499990 | 499990 | Equitable | N/A | 499990 | 0 | 499990 | 100 | 499990 | 500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: Good.
340 | Preventive and Promotive Health Services | Completion and equipping of Rongai Turi health center | To complete and equip Rongai Turi health center | Rongai Turi health center completed and equipped | 3110504 | Other Infrastructure and Civil Works | Rongai | Mosop | -0.296143 35.958896 2109.1000000000004 8.399999618530273 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 497600 | 99.5 | 497600 | 500000 | 2400 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: Good.
341 | Preventive and Promotive Health Services | Completion and equipping of Roret bridge health center | To complete and equip Roret bridge health center | Roret bridge health center completed and equipped | 3110504 | Other Infrastructure and Civil Works | Rongai | Mosop | -0.296143 35.958896 2109.1000000000004 8.399999618530273 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 499990 | 499990 | 499990 | Equitable | N/A | 499990 | 0 | 499990 | 100 | 499990 | 500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: Good.
342 | Preventive and Promotive Health Services | Completion works (Staffs electricity and lab equipments) at lelechwet dispensary | To complete works (Staffs electricity and lab equipments) at lelechwet dispensary | Works (Staffs electricity and lab equipments) at lelechwet dispensary completed | 3110504 | Other Infrastructure and Civil Works | Rongai | Mosop | -0.248851 35.939649 2052.10009765625 13.512999534606934 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 499480 | 499480 | 499480 | Equitable | N/A | 499480 | 0 | 499480 | 100 | 499480 | 500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: It was viable. Contractor: JODIAH TRANDERS LIMITED. Assessor remarks: Good workmanship.
343 | Preventive and Promotive Health Services | Construction of 3 no. consultation rooms and 4 no. door pit latrine in Ngondi dispensary | To construct 3 no. consultation rooms and 4 no. door pit latrine in Ngondi dispensary | 3 no. consultation rooms and 4 no. door pit latrine in Ngondi dispensary constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Mosop | -0.279335, 35.884997 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2025 | 1666523 | 4999568.7 | 6606091.7 | Equitable | Ward Fund | 6606091.7 | 0 | 733477 | 14.7 | 733477 | 1666523 | 4266091.7 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: It was viable. Contractor: Not awarded. Assessor remarks: Under procurement.
344 | Preventive and Promotive Health Services | Construction of Ngondu Dispensary Toilet | To construct Ngondu Dispensary Toilet | Ngondu Dispensary Toilet constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Mosop | -0.279402, 35.884872 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | 2023 | 500000 | 499860 | 499860 | Equitable | N/A | 499860 | 0 | 484864 | 97 | 484864 | 499860 | 14996 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Kiemo holding limited. Assessor remarks: Good workmanship.
345 | Preventive and Promotive Health Services | Equipping and fencing Lelechwet Dispensary | To equip and fencing Lelechwet Dispensary with necessary facilities and equipment | And fencing Lelechwet Dispensary equipped | 3110504 | Other Infrastructure and Civil Works | Rongai | Mosop | -0.220954, 35.82763 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | 2025 | 2700000 | 2700000 | 2700000 | Equitable | Equitable | 2700000 | 0 | 1499300 | 55.5 | 1499300 | 1900000 | 1200700 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Project well ongoing.
346 | Preventive and Promotive Health Services | Ngondu dispensary works; Equipping, Electricity connection, water connection and fencing of the compound | To implement ngondu dispensary works; equipping, electricity connection, water connection and fencing of the compound for access to quality healthcare services | Ngondu dispensary works; Equipping, Electricity connection, water connection and fencing of the compound completed | 3110504 | Other Infrastructure and Civil Works | Rongai | Mosop | -0.25037 35.841817 1902.9000244140625 13.128999710083008 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | 2022/23 | 1400000 | 1400000 | 1400000 | Equitable | N/A | 1400000 | 0 | 1206097 | 86.1 | 1206097 | 0 | 193903 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes it was viable. Contractor: Privim contractors and suppliers. Assessor remarks: In good condition.
347 | Preventive and Promotive Health Services | Rongai -Turi Dispensary works: Construction of a toilet, Fencing the Compound, Electricity Connection and Shelves Reinforcement | To implement rongai -turi dispensary works: construction of a toilet, fencing the compound, electricity connection and shelves reinforcement for access to quality healthcare services | Rongai -Turi Dispensary works: Construction of a toilet, Fencing the Compound, Electricity Connection and Shelves Reinforcement completed | 3110504 | Other Infrastructure and Civil Works | Rongai | Mosop | -0.25037 35.841817 1902.9000244140625 13.128999710083008 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | 2022/23 | 1800000 | 0 | 1790020 | Equitable | Ward Fund | 1790020 | 0 | 0 | 0 | 0 | 1790020 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes it was viable. Contractor: Privim contractors and suppliers. Assessor remarks: In good condition.
348 | Preventive and Promotive Health Services | Construction of Gatundu -Merironi dispensary phase II, toilets, fencing , installation of gate and 10,000 litres water tank and electrification of the facility and two security lights | To construct Gatundu -Merironi dispensary phase II, toilets, fencing , installation of gate and 10,000 litres water tank and electrification of the facility and two security lights | Gatundu -Merironi dispensary phase II, toilets, fencing , installation of gate and 10,000 litres water tank and electrification of the facility and two security lights constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Murindat | -0.497603, 36.397703 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 1999365 | 204409.15 | 204409.15 | Equitable | N/A | 204409.15 | 0 | 1794956 | 878.1 | 1794956 | 204409 | -1590546.85 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: ERUC AFRIC LIMITED. Assessor remarks: Streetlights not installed.
349 | Preventive and Promotive Health Services | Completion of Sision maternity | To complete Sision maternity | Sision maternity completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Naivasha East | -0.867383, 36.535491 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2021-2022 | 1499885 | 149988.5 | 149988.5 | Equitable | N/A | 149988.5 | 0 | 1349897 | 900 | 1349897 | 149989 | -1199908.5 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Not yet. Viable: Not yet. Assessor remarks: No water connection and septic tank.
350 | Preventive and Promotive Health Services | Construction of Sulmac Dispensary toilets and laboratory | To construct Sulmac Dispensary toilets and laboratory | Sulmac Dispensary toilets and laboratory constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Naivasha East | -0.818103 36.545141 2484.934814453125 46.69300079345703 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | N/A | 3000000 | 0 | 2788205 | Equitable | N/A | 2788205 | 0 | 668400 | 0 | 668400 | 2788205 | 0 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: OPD block very small with structural craks.
351 | Preventive and Promotive Health Services | Fencing of Kinungi Dispensary | To secure Kinungi Dispensary through fencing | Kinungi Dispensary fenced and secured | 3110504 | Other Infrastructure and Civil Works | Naivasha | Naivasha East | -0.817923, 36.54494 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | 2021-22 | 637509 | 637509 | 637509 | Equitable | N/A | 637509 | 0 | 636000 | 99.8 | 636000 | 136317 | 1509 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Fencing done by chainlink instead of masonry walling.
352 | Preventive and Promotive Health Services | Fencing of Sision Dispensary and Maternity | To secure Sision Dispensary and Maternity through fencing | Sision Dispensary and Maternity fenced and secured | 3110504 | Other Infrastructure and Civil Works | Naivasha | Naivasha East | -0.867319, 36.535416 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | 2024 | 1000000 | 925800 | 925800 | Equitable | Ward Fund | 925800 | 0 | 789483 | 85.3 | 789483 | 136317 | 136317 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project was combined with 2022-23.
353 | Preventive and Promotive Health Services | Construction of perimeter wall at free area lanet dispensary | To construct perimeter wall at free area lanet dispensary | Perimeter wall at free area lanet dispensary constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Nakuru East | -0.292567 36.119342 1840.9000244140625 17.683000564575195 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 2 | 2 | Equitable | N/A | 2 | 0 | 1199998 | 59999900 | 1199998 | 2 | -1199996 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Dakuki consruction ltd. Assessor remarks: Project ok.
354 | Preventive and Promotive Health Services | Construction Of Perimeter Wall at Mirugi Kariuki Sub County Hospital | To construct Perimeter Wall at Mirugi Kariuki Sub County Hospital | Perimeter Wall at Mirugi Kariuki Sub County Hospital constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Nakuru East | -0.373036, 36.151009 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 2023/2024 | 2000000 | 2000000 | 1716880.6 | Equitable | Ward Fund | 1716880.6 | 0 | 283119 | 14.2 | 283119 | 2000000 | 1716881 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Redfin constrction limited. Assessor remarks: Well done.
355 | Preventive and Promotive Health Services | Purchase Of Benches for Lanet Health Centre Waiting Bay and construction of a shade | To procure Benches for Lanet Health Centre Waiting Bay and construction of a shade | Benches for Lanet Health Centre Waiting Bay and construction of a shade procured | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Nakuru East | -0.292672, 36.118378 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 2023/2024 | 500000 | 0 | 500000 | Equitable | Ward Fund | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Needy.
356 | Preventive and Promotive Health Services | Construction of two (2) door toilet for the public at Nessuit Health Centre | To construct two (2) door toilet for the public at Nessuit Health Centre | Two (2) door toilet for the public at Nessuit Health Centre constructed | 3110504 | Other Infrastructure and Civil Works | Njoro | Nessuit | -0.39344, 35.899306 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | 2024/25 | 500000 | 500000 | 500000 | Equitable | Equitable | 500000 | 0 | 1701945 | 340.4 | 1701945 | 2000000 | -1201945 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The pit was dug but reaching around 9 feet water came out, the current latrine being used is in bad condition, the site of construction has been condoned off awaiting the water level reduce or consult on way forwad.
357 | Preventive and Promotive Health Services | Construction of two (2) door toilet for the staff at Nessuit Health Centre | To construct two (2) door toilet for the staff at Nessuit Health Centre | Two (2) door toilet for the staff at Nessuit Health Centre constructed | 3110504 | Other Infrastructure and Civil Works | Njoro | Nessuit | -0.39344, 35.899306 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | 2024/25 | 500000 | 500000 | 500000 | Equitable | Equitable | 500000 | 0 | 1701945 | 340.4 | 1701945 | 2000000 | -1201945 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The pit was dug but reaching around 9 feet water came out, the current latrine being used is in bad condition, the site of construction has been condoned off awaiting the water level reduce or consult on way forwad.
358 | Preventive and Promotive Health Services | Installation of Perimeter Wall at Nessuit Health Centre | To install Perimeter Wall at Nessuit Health Centre | Perimeter Wall at Nessuit Health Centre installed | 3110504 | Other Infrastructure and Civil Works | Njoro | Nessuit | -0.392896 35.898763 2388.13560622558 27.98659896850586 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 2023/24 | 2000000 | 2000000 | 2000000 | Equitable | Ward Fund | 2000000 | 0 | 1701945 | 85.1 | 1701945 | 2000000 | 298055 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: No. Viable: No. Contractor: PETMAK INVESTMENTS COMPANY LTD. Assessor remarks: The wall was constructed and it covered part of the intended distance, during construction a section of the wall fell due to heavy rainfall which led to the wall not being complete as earlier intended, a section of the wall was also not painted as expected..
359 | Preventive and Promotive Health Services | Rehabilitation and Equipping of Nessuit Maternity | To rehabilitate Equipping of Nessuit Maternity to restore functionality | Equipping of Nessuit Maternity rehabilitated | 3110504 | Other Infrastructure and Civil Works | Njoro | Nessuit | -0.393429 35.899456 2477.7296299869195 52.435916900634766 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 1000000 | 2710 | 2710 | Equitable | N/A | 2710 | 0 | 997290 | 36800.4 | 997290 | 2710 | -994580 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The maternity is operational.
360 | Preventive and Promotive Health Services | Sinking and construction of a pit latrine and purchase of 10000 litres water tank at Nessuit Health centre | To implement sinking and construction of a pit latrine and purchase of 10000 litres water tank at nessuit health centre for access to quality healthcare services | Sinking and construction of a pit latrine and purchase of 10000 litres water tank at Nessuit Health centre completed | 3110504 | Other Infrastructure and Civil Works | Njoro | Nessuit | -0.393077, 35.899547 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | 2021/22 | 850000 | 850000 | 850000 | Equitable | N/A | 850000 | 0 | 1701945 | 200.2 | 1701945 | 850000 | -851945 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is fully operational.
361 | Preventive and Promotive Health Services | Completion of Perimeter wall, installation of Electricity and Pipping of Njokerio Dispensary | To complete Perimeter wall, installation of Electricity and Pipping of Njokerio Dispensary | Perimeter wall, installation of Electricity and Pipping of Njokerio Dispensary completed | 3110504 | Other Infrastructure and Civil Works | Njoro | Njoro | -0.389818 35.931233 2298.1 6.099999904632568 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 2023/24 | 6000000 | 6000000 | 6000000 | Equitable | Ward Fund | 6000000 | 0 | 0 | 0 | 0 | 6000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good state.
362 | Preventive and Promotive Health Services | Construction Of Sasumua Dispensary Toilets | To construct Sasumua Dispensary Toilets | Sasumua Dispensary Toilets constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Nyota | -0.389098 35.653772 2746.7001953125 14.800000190734863 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 2023/24 | 800000 | 800000 | 800000 | Equitable | Ward Fund | 800000 | 0 | 758480 | 94.8 | 758480 | 41520 | 41520 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes. Assessor remarks: Stalled,.
363 | Preventive and Promotive Health Services | Fencing Of Githirika Dispensary | To secure Githirika Dispensary through fencing | Githirika Dispensary fenced and secured | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Nyota | -0.36156, 35.632497 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 2023-2024 | 500000 | 500000 | 500000 | Equitable | Ward Fund | 500000 | 0 | 442284 | 88.5 | 442284 | 57716 | 57716 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Macknox Contractors & General Supplies Ltd.. Assessor remarks: Good.
364 | Preventive and Promotive Health Services | Construction of dispensary quarters at Narasha | To construct dispensary quarters at Narasha | Dispensary quarters at Narasha constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Olkaria | -0.913047, 36.275996 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 8.2 | 8.2 | Equitable | N/A | 8.2 | 0 | 2999992 | 36585268.3 | 2999992 | 8 | -2999983.8 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: Was viable but did not meet the needs since its not operational. Assessor remarks: The facility not in use.
365 | Preventive and Promotive Health Services | Buying of Fabricated four 40ft containers to be used as a Dispensary at Kamere | To procure Fabricated four 40ft containers to be used as a Dispensary at Kamere | Fabricated four 40ft containers to be used as a Dispensary at Kamere procured | 3110504 | Other Infrastructure and Civil Works | Naivasha | Olkaria | -0.819698 36.322931 1932.699951171875 35.104000091552734 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | N/A | 3000000 | 3000000 | 3000000 | Equitable | Ward Fund | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Viable. Once the project is finished since there is no other hospital. Assessor remarks: The containers are being refurbished but handing over done.
366 | Preventive and Promotive Health Services | Construction of a perimeter wall at Nakuru West clinic | To construct a perimeter wall at Nakuru West clinic | A perimeter wall at Nakuru West clinic constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Shabab | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 502320 | 502320 | Equitable | N/A | 502320 | 0 | 2497650 | 497.2 | 2497650 | 502320 | -1995330 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
367 | Preventive and Promotive Health Services | Electricity connection at Majani Mingi dispensary | To implement electricity connection at majani mingi dispensary for access to quality healthcare services | Electricity connection at Majani Mingi dispensary completed | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.045624, 36.027621 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | N/A | 40000 | 40000 | 40000 | Equitable | N/A | 40000 | 0 | 439500 | 1098.8 | 439500 | 40000 | -399500 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Electricity connected and working.
368 | Preventive and Promotive Health Services | Equipping of Majani Mingi Dispensary | To equip Majani Mingi Dispensary with necessary facilities and equipment | Majani Mingi Dispensary equipped | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.041777 36.02443 1637.6999999999998 2094.485107421875 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 462444.4 | 462444.4 | Equitable | Ward Fund | 462444.4 | 0 | 439500 | 95 | 439500 | 462444 | 22944.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Project on use.
369 | Preventive and Promotive Health Services | Fencing Of Majani Mingi Dispensary | To secure Majani Mingi Dispensary through fencing | Majani Mingi Dispensary fenced and secured | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.04561 36.027826 1647 8 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 2023/24 | 700000 | 0 | 700000 | Equitable | Ward Fund | 700000 | 0 | 439500 | 0 | 439500 | 700000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The fencing is ongoing.
370 | Preventive and Promotive Health Services | Electricity Installation Set Kobor Dispensary | To implement electricity installation set kobor dispensary for access to quality healthcare services | Electricity Installation Set Kobor Dispensary completed | 3110504 | Other Infrastructure and Civil Works | Rongai | Solai | -0.02844 36.13565 1686.9853515625 563.385986328125 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | N/A | 300000 | 300000 | 300000 | Equitable | Ward Fund | 300000 | 0 | 0 | 0 | 0 | 300000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The ceiling has been infested by Bats and it needs to be replaced..
371 | Preventive and Promotive Health Services | Fencing of KFA dispensary | To secure KFA dispensary through fencing | KFA dispensary fenced and secured | 3110504 | Other Infrastructure and Civil Works | Rongai | Solai | -0.037387 36.107986 1650.18505859375 12.383000373840332 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | 2021/22 | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 681540 | 97.4 | 681540 | 700000 | 18460 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
372 | Preventive and Promotive Health Services | Design and Construction of two toilets at the town centre | To design and construct two toilets at the town centre | Two toilets at the town centre designed and constructed | 3110504 | Other Infrastructure and Civil Works | Subukia | Subukia | 0.001269 36.231898 1992.4000244140625 18.350000381469727 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2017/18 | 2017/18 | 2017/18 | 2500000 | 1250000 | 1250000 | Equitable | N/A | 1250000 | 0 | 1250000 | 100 | 1250000 | 1250000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes.. Viable: Yes, the project serves the boda boda riders in the area.. Contractor: Information not available. Assessor remarks: The boda boda shades are in use.
373 | Preventive and Promotive Health Services | Purchase and supply of a power generator of Subukia | To procure and supply a power generator of Subukia | A power generator of Subukia procured and supplied | 3110504 | Other Infrastructure and Civil Works | Subukia | Subukia | 0.002614, 36.230329 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | 30/08/2024 | 2000000 | 2000000 | 2000000 | Equitable | Ward Fund | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Vired | 25 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. The generator supports power supply by breaching power shortages or disruptions.r blackouts ensuring continuous supply of power.. Viable: Residents and clients at the facility have expressed satisfaction following uninterrupted power supply.. Assessor remarks: The Kshs 2M funds allocated for the purchase of the generator were transferred to other uses at the same facility, specifically the renovation works at the Subukia Sub-county hospital, old wing..
374 | Preventive and Promotive Health Services | Construction of Ongiek Karandit Dispensary 4 door toilet | To construct Ongiek Karandit Dispensary 4 door toilet | Ongiek Karandit Dispensary 4 door toilet constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Tinet | -0.47504, 35.631932 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | N/A | 950493 | 950493 | 950493 | Equitable | Equitable | 950493 | 0 | 1901087 | 200 | 1901087 | 1998350 | -950594 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Ongoing project.
375 | Preventive and Promotive Health Services | Construction of Turi Dispensary | To construct Turi Dispensary | Turi Dispensary constructed | 3110504 | Other Infrastructure and Civil Works | Molo | Turi | -0.279658, 35.754132 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | N/A | 3500000 | 3500000 | 3500000 | Equitable | Equitable | 3500000 | 0 | 799130 | 22.8 | 799130 | 870 | 2700870 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: The department to follow up with the lands department.
376 | Preventive and Promotive Health Services | Mona Dispensary Fencing and Construction of a pit latrine | To implement mona dispensary fencing and construction of a pit latrine for access to quality healthcare services | Mona Dispensary Fencing and Construction of a pit latrine completed | 3110504 | Other Infrastructure and Civil Works | Molo | Turi | -0.295575, 35.706518 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | 2021/22 | 1200000 | 336439.2 | 336439.2 | Equitable | N/A | 336439.2 | 0 | 848511 | 252.2 | 848511 | 336439 | -512071.8 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
377 | Preventive and Promotive Health Services | Muyeshi Dispensary roof renovation | To implement muyeshi dispensary roof renovation for access to quality healthcare services | Muyeshi Dispensary roof renovation completed | 3110504 | Other Infrastructure and Civil Works | Molo | Turi | -0.304594, 35.719307 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | 2021/22 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 500000 | 100 | 500000 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: County Government of Nakuru to facilitate the process of acquiring a title.
378 | Preventive and Promotive Health Services | Completion and equipping of laboratory at prisons dispensary | To complete and equip laboratory at prisons dispensary | Laboratory at prisons dispensary completed and equipped | 3110504 | Other Infrastructure and Civil Works | Naivasha | Viwandani | -0.702788, 36.443555 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 997600 | 997600 | 997600 | Equitable | N/A | 997600 | 0 | 997600 | 100 | 997600 | 1006958 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Assessor remarks: Project completed.
379 | Preventive and Promotive Health Services | Fencing and equipping of Hopewell dispensary | To secure and equipping of Hopewell dispensary through fencing | And equipping of Hopewell dispensary fenced and secured | 3110504 | Other Infrastructure and Civil Works | Naivasha | Viwandani | -0.710429, 36.431198 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | N/A | 5000000 | 0 | 5000000 | Equitable | Ward Fund | 5000000 | 0 | 105095 | 0 | 105095 | 5000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Partially. Viable: Partially. Assessor remarks: Not equipped and chain link fence.
380 | Preventive and Promotive Health Services | Fencing of ICT hub and Hopewell Dispensary | To secure ICT hub and Hopewell Dispensary through fencing | ICT hub and Hopewell Dispensary fenced and secured | 3110504 | Other Infrastructure and Civil Works | Naivasha | Viwandani | -0.710431, 36.431201 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | 2021/22 | 1500000 | 1477200 | 1477200 | Equitable | N/A | 1477200 | 0 | 1334929 | 90.4 | 1334929 | 1477200 | 142271 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Partially. Viable: Not yet started. Assessor remarks: No ICT HUB.
381 | Preventive and Promotive Health Services | Connection of water and electricity to Kahuti Dispensary | To implement connection of water and electricity to kahuti dispensary for access to quality healthcare services | Connection of water and electricity to Kahuti Dispensary completed | 3110504 | Other Infrastructure and Civil Works | Subukia | Waseges | 0.032338, 36.241098 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | 2022/23 | 1000000 | 934113 | 1000000 | Equitable | Ward Fund | 1000000 | 0 | 0 | 0 | 0 | 934113 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: Yes. Assessor remarks: Not Operational.
382 | Preventive and Promotive Health Services | Construction and equipping of laboratory and power at Olgilgei Dispensary and fensing and renovation | To construct and equip laboratory and power at Olgilgei Dispensary and fensing and renovation | Laboratory and power at Olgilgei Dispensary and fensing and renovation constructed and equipped | 3110504 | Other Infrastructure and Civil Works | Subukia | Waseges | 0.116735 36.274342 1803.2 9.800000190734863 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 1000000 | 1000000 | 2000000 | Equitable | Ward Fund | 2000000 | 0 | 629865 | 63 | 629865 | 1000000 | 370135 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Maintenance.
383 | Preventive and Promotive Health Services | Construction and equipping of laboratory and power at Olgilgei Dispensary | To construct and equip laboratory and power at Olgilgei Dispensary | Laboratory and power at Olgilgei Dispensary constructed and equipped | 3110504 | Other Infrastructure and Civil Works | Subukia | Waseges | 0.116735 36.274342 1803.2 9.800000190734863 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 700000 | 700000 | 700000 | Equitable | Ward Fund | 700000 | 0 | 629865 | 90 | 629865 | 699700 | 70135 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Maintenance.
384 | Preventive and Promotive Health Services | Construction of perimeter wall and purchase installation of gate at Mwariki Dispensary | To construct perimeter wall and purchase installation of gate at Mwariki Dispensary | Perimeter wall and purchase installation of gate at Mwariki Dispensary constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Barut | -0.348647, 36.055368 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | 2025 | 2500000 | 2500000 | 2500000 | Equitable | Equitable | 2500000 | 0 | 2622935 | 104.9 | 2622935 | 2000000 | -122935 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Yet to start,chain link was constructed by community.
385 | Preventive and Promotive Health Services | Installation Of Electricity at Burgei Dispensary | To install Electricity at Burgei Dispensary | Electricity at Burgei Dispensary installed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Barut | -0.33872, 36.037972 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 2024 | 300000 | 300000 | 300000 | Equitable | Ward Fund | 300000 | 0 | 2622935 | 874.3 | 2622935 | 300000 | -2322935 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: A few are defective..
386 | Preventive and Promotive Health Services | Construction of a public toilet at Kongasis auction market and fence | To construct a public toilet at Kongasis auction market and fence | A public toilet at Kongasis auction market and fence constructed | 3110599 | Other Infrastructure and Civil Works | Gilgil | Eburru/Mbaruk | -0.552511, 36.151373 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 21-22 | 600000 | 5440 | 5440 | Equitable | N/A | 5440 | 0 | 594560 | 10929.4 | 594560 | 5440 | -589120 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Unspecified. Assessor remarks: Used.
387 | Preventive and Promotive Health Services | Construction Of Thugunui Dispensary Toilet | To construct Thugunui Dispensary Toilet | Thugunui Dispensary Toilet constructed | 3110599 | Other Infrastructure and Civil Works | Gilgil | Eburru/Mbaruk | -0.000773, 36.164078 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 8/7/2024 | 850000 | 850000 | 850000 | Equitable | Ward Fund | 850000 | 0 | 2858181 | 336.3 | 2858181 | 850000 | -2008181 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Ye. Viable: The project is viable but needs to be operationalised.. Contractor: Summer merchant. Assessor remarks: Good workmanship.
388 | Preventive and Promotive Health Services | Construction of toilets at Mbaruk Market | To construct toilets at Mbaruk Market | Toilets at Mbaruk Market constructed | 3110599 | Other Infrastructure and Civil Works | Gilgil | Eburru/Mbaruk | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 600000 | 948 | 948 | Equitable | N/A | 948 | 0 | 162640 | 17156.1 | 162640 | 948 | -161692 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
389 | Preventive and Promotive Health Services | Construction of a public toilet at Elementaita trading centre | To construct a public toilet at Elementaita trading centre | A public toilet at Elementaita trading centre constructed | 3110599 | Other Infrastructure and Civil Works | Gilgil | Elementaita | -0.487923, 36.156894 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 999266 | 999266 | Equitable | Ward Fund | 999266 | 0 | 3991670 | 399.5 | 3991670 | 999266 | -2992404 | Stalled | 0 | 100 | Stalled -10%. Retendering of works in progress | 2019 | N/A | -2992404 | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Project was veried.
390 | Preventive and Promotive Health Services | Fencing of Munanda Dispensary and gate installation | To secure Munanda Dispensary and gate installation through fencing | Munanda Dispensary and gate installation fenced and secured | 3110599 | Other Infrastructure and Civil Works | Gilgil | Elementaita | -0.59592, 36.112046 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | N/A | 1000000 | 1000000 | 1000000 | Equitable | Equitable | 1000000 | 0 | 499960 | 50 | 499960 | 3200000 | 500040 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Well done.
391 | Preventive and Promotive Health Services | Fencing Of Cemetery Public Toilet in Gilgil | To secure Cemetery Public Toilet in Gilgil through fencing | Cemetery Public Toilet in Gilgil fenced and secured | 3110599 | Other Infrastructure and Civil Works | Gilgil | Gilgil | -0.510428, 36.324651 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 2023/24 | 500000 | 500000 | 500000 | Equitable | Ward Fund | 500000 | 0 | 435465 | 87.1 | 435465 | 64535 | 64535 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Njorum Rapado Venture Ltd. Assessor remarks: ..
392 | Preventive and Promotive Health Services | Construction Of an insulator at Nyamathi Dispensary | To construct an insulator at Nyamathi Dispensary | An insulator at Nyamathi Dispensary constructed | 3110599 | Other Infrastructure and Civil Works | Naivasha | Hells Gate | -0.776793, 36.431677 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | N/A | 600000 | 600000 | 600000 | Equitable | Ward Fund | 600000 | 0 | 545600 | 90.9 | 545600 | 54400 | 54400 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: The project was changed. Viable: The project was changed. Assessor remarks: The construction of insulator cannot happen in a facility.
393 | Preventive and Promotive Health Services | Construction Of Burning Chamber, Ash Pit and Elevated Water Stands at Muriundo Dispensary | To construct Burning Chamber, Ash Pit and Elevated Water Stands at Muriundo Dispensary | Burning Chamber, Ash Pit and Elevated Water Stands at Muriundo Dispensary constructed | 3110599 | Other Infrastructure and Civil Works | Bahati | Kabatini | -0.231904, 36.155351 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 2024 | 1000000 | 1000000 | 1000000 | Equitable | Ward Fund | 1000000 | 0 | 955804 | 95.6 | 955804 | 44196 | 44196 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ndegenye limited. Assessor remarks: Elevated tank was done but burning chamber and ash pit was not done because the dispensary does not allow a burning chamber neema restricted,the money meant for ash chamber was used to buy pump and renovation of OPD block.
394 | Preventive and Promotive Health Services | Construction of public toilets at Keringet town | To construct public toilets at Keringet town | Public toilets at Keringet town constructed | 3110599 | Other Infrastructure and Civil Works | Kuresoi South | Keringet | -0.426397 35.693612 2683.500244140625 5.900000095367432 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 723.6 | 723.6 | Equitable | N/A | 723.6 | 0 | 1199276 | 165737.4 | 1199276 | 724 | -1198552.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Constructed at 1.2 m.
395 | Preventive and Promotive Health Services | Completion of fencing of Maiella Health Centre with chain link | To complete fencing of Maiella Health Centre with chain link | Fencing of Maiella Health Centre with chain link completed | 3110599 | Other Infrastructure and Civil Works | Naivasha | Maiella | -0.88767, 36.199668 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | 2025 | 500000 | 500000 | 500000 | Equitable | Equitable | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Yes. Assessor remarks: Fencing done 100meters.More Funds to be allocated to Complete the whole fencing of the health center.
396 | Preventive and Promotive Health Services | Fencing of Ngondi Dispensary and installation of a gate | To secure Ngondi Dispensary and installation of a gate through fencing | Ngondi Dispensary and installation of a gate fenced and secured | 3110599 | Other Infrastructure and Civil Works | Naivasha | Maiella | -0.832055, 36.204617 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | 2025 | 800000 | 800000 | 800000 | Equitable | Equitable | 800000 | 0 | 0 | 0 | 0 | 1500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: Partially. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: Ongoing...Work in Progress.
397 | Preventive and Promotive Health Services | Construction Of a Chain Link Fencing with Concrete Poles 400metre-Karati Health Center | To construct a Chain Link Fencing with Concrete Poles 400metre-Karati Health Center | A Chain Link Fencing with Concrete Poles 400metre-Karati Health Center constructed | 3110599 | Other Infrastructure and Civil Works | Gilgil | Malewa West | -0.702703 36.291018 0 2000 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 2023/24 | 1500000 | 1500000 | 1500000 | Equitable | Ward Fund | 1500000 | 0 | 1304913 | 87 | 1304913 | 195087 | 195087 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Partly. Viable: Partly. Assessor remarks: Need good management.
398 | Preventive and Promotive Health Services | Renovation -Fencing of Fallen Stone Fence (Small Section) Stones Available at Kasarani Dispensary | To rehabilitate -Fencing of Fallen Stone Fence (Small Section) Stones Available at Kasarani Dispensary to restore functionality | -Fencing of Fallen Stone Fence (Small Section) Stones Available at Kasarani Dispensary rehabilitated | 3110599 | Other Infrastructure and Civil Works | Gilgil | Malewa West | -0.702703, 36.291018 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 2023/24 | 500000 | 0 | 500000 | Equitable | Ward Fund | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
399 | Preventive and Promotive Health Services | Construction of placenta pit (Sumeek Dispensary) | To construct placenta pit (Sumeek Dispensary) | Placenta pit (Sumeek Dispensary) constructed | 3110599 | Other Infrastructure and Civil Works | Rongai | Mosop | -0.254902, 35.877116 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | Yet to start under procurement | 200000 | 200000 | 200000 | Equitable | Equitable | 200000 | 0 | 2752510 | 1376.3 | 2752510 | 2752510 | -2552510 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Viable. Contractor: Not indicated. Assessor remarks: Not tendered.
400 | Preventive and Promotive Health Services | Fencing of Kinungi Dispensary with chain link | To secure Kinungi Dispensary with chain link through fencing | Kinungi Dispensary with chain link fenced and secured | 3110599 | Other Infrastructure and Civil Works | Naivasha | Naivasha East | -0.817923, 36.54494 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | 2021-22 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 636000 | 63.6 | 636000 | 136317 | 364000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Fencing done by chainlink instead of masonry walling.
401 | Preventive and Promotive Health Services | Completion of Mirugi Kariuki Sub-County Hospital perimeter wall | To complete Mirugi Kariuki Sub-County Hospital perimeter wall | Mirugi Kariuki Sub-County Hospital perimeter wall completed | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Nakuru East | -0.374067, 36.15009 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | 2024/2025 | 2000000 | 2000000 | 2000000 | Equitable | Equitable | 2000000 | 0 | 283119 | 14.2 | 283119 | 2000000 | 1716881 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Njumuru enterprises. Assessor remarks: Work done perfectly.
402 | Preventive and Promotive Health Services | Equipping Lanet Health Centre waiting bay with additional benches | To equip Lanet Health Centre waiting bay with additional benches with necessary facilities and equipment | Lanet Health Centre waiting bay with additional benches equipped | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Nakuru East | -0.292735 36.118406 1839.5 20 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | N/A | 545927 | 545927 | 545927 | Equitable | N/A | 545927 | 0 | 0 | 0 | 0 | 545927 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: Not done.
403 | Preventive and Promotive Health Services | Installation of electricity Njokerio Dispensary | To install electricity Njokerio Dispensary | Electricity Njokerio Dispensary installed | 3110599 | Other Infrastructure and Civil Works | Njoro | Njoro | -0.389818 35.931233 2298.1 6.099999904632568 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | N/A | 1000000 | 0 | 1000000 | Equitable | Equitable | 1000000 | 0 | 1999138 | 100 | 1999138 | 6000000 | -1999138 | Vired | 90 | N/A | N/A | N/A | N/A | N/A | Yes | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good state.
404 | Preventive and Promotive Health Services | Water Piping in Njokerio Dispensary | To implement water piping in njokerio dispensary for access to quality healthcare services | Water Piping in Njokerio Dispensary completed | 3110599 | Other Infrastructure and Civil Works | Njoro | Njoro | -0.389818 35.931233 2298.1 6.099999904632568 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | N/A | 500000 | 0 | 500000 | Equitable | Equitable | 500000 | 0 | 1999138 | 100 | 1999138 | 862 | -1999138 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good state.
405 | Preventive and Promotive Health Services | Construction of Toilet in Githima market | To construct Toilet in Githima market | Toilet in Githima market constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Shabab | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 6 | 6 | Equitable | N/A | 6 | 0 | 1499994 | 24999900 | 1499994 | 6 | -1499988 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
406 | Preventive and Promotive Health Services | Fencing of Lomolo B dispensary | To secure Lomolo B dispensary through fencing | Lomolo B dispensary fenced and secured | 3110599 | Other Infrastructure and Civil Works | Rongai | Soin | 0.01609, 36.03341 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | N/A | 800000 | 0 | 800000 | Equitable | Equitable | 800000 | 0 | 439500 | 100 | 439500 | 700000 | -439500 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The fence is in good condition.
407 | Preventive and Promotive Health Services | Fencing of Majani Mingi Dispensary | To secure Majani Mingi Dispensary through fencing | Majani Mingi Dispensary fenced and secured | 3110599 | Other Infrastructure and Civil Works | Rongai | Soin | -0.04561 36.027826 1647 8 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | 2024/25 | 500000 | 500000 | 500000 | Equitable | Ward Fund | 500000 | 0 | 439500 | 87.9 | 439500 | 700000 | 60500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The fencing is ongoing.
408 | Preventive and Promotive Health Services | Construction of Doctors Quarter at Edgewood Dispensary | To construct Doctors Quarter at Edgewood Dispensary | Doctors Quarter at Edgewood Dispensary constructed | 3110599 | Other Infrastructure and Civil Works | Subukia | Subukia | 0.004649, 36.207554 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | Not started | 2000000 | 2000000 | 2000000 | Equitable | Equitable | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Contractor: Information not available.. Assessor remarks: The staffhouse is yet to start.
409 | Preventive and Promotive Health Services | Beautification, fencing, water connection and levelling of Kabati Cemetery | To implement beautification, fencing, water connection and levelling of kabati cemetery for access to quality healthcare services | Beautification, fencing, water connection and levelling of Kabati Cemetery completed | 3110599 | Other Infrastructure and Civil Works | Naivasha | Viwandani | -0.722312, 36.447328 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | N/A | 5000000 | 0 | 5000000 | Equitable | N/A | 5000000 | 0 | 0 | 0 | 0 | 5000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: The project is viable but has not started. Assessor remarks: The project has not started.
410 | Preventive and Promotive Health Services | Construction of a perimeter wall fence at Wei Dispensary | To construct a perimeter wall fence at Wei Dispensary | A perimeter wall fence at Wei Dispensary constructed | 3110599 | Other Infrastructure and Civil Works | Subukia | Waseges | 0.032413 36.24133 1984.5 8.100000381469727 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | N/A | 3000000 | 3000000 | 3000000 | Equitable | Equitable | 3000000 | 0 | 0 | 0 | 0 | 934113 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The dispensary is in good condition.
411 | Equipping of Nakuru West Health Centre office with furniture | Equipping of Nakuru West Health Centre office with furniture | To equip Nakuru West Health Centre office with furniture with necessary facilities and equipment | Nakuru West Health Centre office with furniture equipped | 3111099 | N/A | Nakuru West | Shabab | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | 2024/25 | 700000 | 700000 | 700000 | Grant | Grant | 700000 | 0 | 2958500 | 422.6 | 2958500 | 1500000 | -2258500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
412 | Preventive and Promotive Health Services | Equipping of Kigonor Community Dispensary | To equip Kigonor Community Dispensary with necessary facilities and equipment | Kigonor Community Dispensary equipped | 3111101 | Purchase of Medical and Dental Equipment | Nakuru West | Barut | -0.327064 36.056176 1770 43.60900115966797 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1500 | 1500 | Equitable | N/A | 1500 | 0 | 998500 | 66566.7 | 998500 | 1500 | -997000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Foresight commecial services. Assessor remarks: Equipment are operational.
413 | Preventive and Promotive Health Services | Equipping of maternity at barut ward | To equip maternity at barut ward with necessary facilities and equipment | Maternity at barut ward equipped | 3111101 | Purchase of Medical and Dental Equipment | Nakuru West | Barut | -0.326905, 36.056307 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/2021 | 1496470 | 1496470 | 1496470 | Equitable | N/A | 1496470 | 0 | 1496470 | 100 | 1496470 | 1500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Foresight Commercial Services. Assessor remarks: Usable.
414 | Preventive and Promotive Health Services | Equipping of mwariki health center | To equip mwariki health center with necessary facilities and equipment | Mwariki health center equipped | 3111101 | Purchase of Medical and Dental Equipment | Nakuru West | Barut | -0.34819, 36.055632 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2019 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The equipments in sound condition.
415 | Preventive and Promotive Health Services | Equipping Of Kiwamu Health Center | To equip Kiwamu Health Center with necessary facilities and equipment | Kiwamu Health Center equipped | 3111101 | Purchase of Medical and Dental Equipment | Bahati | Dundori | -0.237045, 36.167621 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 2016/2017 | 1000000 | 1000000 | 1000000 | Equitable | Ward Fund | 1000000 | 0 | 4203337 | 420.3 | 4203337 | 1000000 | -3203337 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
416 | Preventive and Promotive Health Services | Fencing of barnabas IDP dispensary | To secure barnabas IDP dispensary through fencing | Barnabas IDP dispensary fenced and secured | 3111101 | Purchase of Medical and Dental Equipment | Gilgil | Eburru/Mbaruk | -0.339112, 36.158842 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2020/21 | 2020/21 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 499400 | 99.9 | 499400 | 500000 | 600 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes , it was objective.. Viable: It was viable .. Assessor remarks: Not existing.
417 | Preventive and Promotive Health Services | Equipping Of Langalanga Hospital | To equip Langalanga Hospital with necessary facilities and equipment | Langalanga Hospital equipped | 3111101 | Purchase of Medical and Dental Equipment | Nakuru East | Flamingo | -0.302689, 36.072812 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 2023/24 | 2000000 | 2000000 | 2000000 | Equitable | Ward Fund | 2000000 | 0 | 11510664 | 575.5 | 11510664 | 2000000 | -9510664 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
418 | Health Curative and Rehabilitative Services | Equipping of New OPD at P.G.H Hospital - FIF | To equip New OPD at P.G.H Hospital - FIF with necessary facilities and equipment | New OPD at P.G.H Hospital - FIF equipped | 3111101 | Purchase of Medical and Dental Equipment | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | N/A | 82161850 | 0 | 0 | FIF | FIF | 0 | 57161850 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
419 | Health Curative and Rehabilitative Services | Operationalization and Equipping of Hospitals - FIF | To implement operationalization and equipping of hospitals - fif for access to quality healthcare services | Operationalization and Equipping of Hospitals - FIF completed | 3111101 | Purchase of Medical and Dental Equipment | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | N/A | 117000000 | 0 | 0 | Equitable | N/A | 0 | 59838150 | 27024982 | 100 | 27024982 | 85136868 | -27024982 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
420 | Health Curative and Rehabilitative Services | Operationalization and Equipping of Hospitals | To implement operationalization and equipping of hospitals for access to quality healthcare services | Operationalization and Equipping of Hospitals completed | 3111101 | Purchase of Medical and Dental Equipment | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | N/A | 112161850 | 0 | 25298718 | Equitable | N/A | 25298718 | 0 | 27024982 | 100 | 27024982 | 85136868 | -27024982 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
421 | Health Curative and Rehabilitative Services | Operationalization and Equipping of Outpatient complex - PGH (FIF) | To implement operationalization and equipping of outpatient complex - pgh (fif) for access to quality healthcare services | Operationalization and Equipping of Outpatient complex - PGH (FIF) completed | 3111101 | Purchase of Medical and Dental Equipment | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | N/A | 300000000 | 190000000 | 0 | FIF | FIF | 0 | 190000000 | 27024982 | 14.2 | 27024982 | 85136868 | 162975018 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
422 | Preventive and Promotive Health Services | Other Development (HQ) Equipping new facilities | To implement other development (hq) equipping new facilities for access to quality healthcare services | Other Development (HQ) Equipping new facilities completed | 3111101 | Purchase of Medical and Dental Equipment | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2022/23 | N/A | 100000000 | 36325158 | 37056837 | Equitable | N/A | 37056837 | 0 | 16430900 | 45.2 | 16430900 | 731679 | 19894258 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
423 | Health Curative and Rehabilitative Services | Purchase of Equipment for Naivasha Mortuary | To procure Equipment for Naivasha Mortuary | Equipment for Naivasha Mortuary procured | 3111101 | Purchase of Medical and Dental Equipment | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | N/A | 8500000 | 17000000 | 25500000 | N/A | N/A | 25500000 | 0 | 692500 | 4.1 | 692500 | 35324805 | 16307500 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
424 | Health Curative and Rehabilitative Services | Purchase of medical and dental equipment (FIF) | To procure medical and dental equipment (FIF) | Medical and dental equipment (FIF) procured | 3111101 | Purchase of Medical and Dental Equipment | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2024/25 | N/A | 190000000 | 455000000 | 0 | FIF | FIF | 0 | 455000000 | 76381394 | 16.8 | 76381394 | 21343623 | 378618606 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
425 | Preventive and Promotive Health Services | Purchase of medical and dental equipment for various new Health Centres (HQ) | To procure medical and dental equipment for various new Health Centres (HQ) | Medical and dental equipment for various new Health Centres (HQ) procured | 3111101 | Purchase of Medical and Dental Equipment | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | N/A | 4000000 | 0 | 4000000 | Equitable | N/A | 4000000 | 0 | 32239074 | 100 | 32239074 | 4000000 | -32239074 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
426 | Health Curative and Rehabilitative Services | Purchase of medical and dental equipment (PGH OPD, Naivasha, Gilgil maternity, Elburgon Maternity and County food Lab) | To procure medical and dental equipment (PGH OPD, Naivasha, Gilgil maternity, Elburgon Maternity and County food Lab) | Medical and dental equipment (PGH OPD, Naivasha, Gilgil maternity, Elburgon Maternity and County food Lab) procured | 3111101 | Purchase of Medical and Dental Equipment | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | N/A | 112161850 | 7500000 | 52161850 | FIF | FIF | 52161850 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
427 | Health Curative and Rehabilitative Services | Purchase of medical and dental equipment (PGH) | To procure medical and dental equipment (PGH) | Medical and dental equipment (PGH) procured | 3111101 | Purchase of Medical and Dental Equipment | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | N/A | 40000000 | 0 | 5589642 | FIF | FIF | 5589642 | 0 | 55588849 | 100 | 55588849 | 21343623 | -55588849 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
428 | Health Curative and Rehabilitative Services | Purchase of medical and medical equipment (Nakuru West) | To procure medical and medical equipment (Nakuru West) | Medical and medical equipment (Nakuru West) procured | 3111101 | Purchase of Medical and Dental Equipment | HQ | HQ | -0.75186, 36.45704 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 25000000 | 78884 | 0 | N/A | N/A | 0 | 78884 | 49824 | 63.2 | 49824 | 78884 | 29060 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Repair the gate it is broken.
429 | Health Curative and Rehabilitative Services | Purchase of medical and medical equipment (PGH) | To procure medical and medical equipment (PGH) | Medical and medical equipment (PGH) procured | 3111101 | Purchase of Medical and Dental Equipment | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2020/21 | 2020/21 | N/A | 44627168 | 6505176.3 | 0 | FIF | FIF | 0 | 6505176.3 | 55588849 | 854.5 | 55588849 | 78884 | -49083672.7 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
430 | Preventive and Promotive Health Services | Purchase of Medical Equipments & dental Equipment for various new health centres (HQ) | To procure Medical Equipments & dental Equipment for various new health centres (HQ) | Medical Equipments & dental Equipment for various new health centres (HQ) procured | 3111101 | Purchase of Medical and Dental Equipment | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | N/A | 48000000 | 0 | 6109472.2 | Equitable | N/A | 6109472.2 | 0 | 32239074 | 100 | 32239074 | 6109472 | -32239074 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
431 | Preventive and Promotive Health Services | Equipping Of Mwicirigiri Dispensary and Construction of a Water Tank | To equip Mwicirigiri Dispensary and Construction of a Water Tank with necessary facilities and equipment | Mwicirigiri Dispensary and Construction of a Water Tank equipped | 3111101 | Purchase of Medical and Dental Equipment | Naivasha | Hells Gate | -0.80768, 36.509436 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | N/A | 3000000 | 0 | 3000000 | Equitable | Ward Fund | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: The project has not yet started, it was rolled over from 23-24.
432 | Preventive and Promotive Health Services | Equipping of Muriundu dispensary | To equip Muriundu dispensary with necessary facilities and equipment | Muriundu dispensary equipped | 3111101 | Purchase of Medical and Dental Equipment | Bahati | Kabatini | -0.231664 36.155492 1975.63720703125 17.485000610351562 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | 2021/22 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 968300 | 96.8 | 968300 | 2500000 | 31700 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
433 | Preventive and Promotive Health Services | Equipping at Lalwet Dispensary | To equip at Lalwet Dispensary with necessary facilities and equipment | At Lalwet Dispensary equipped | 3111101 | Purchase of Medical and Dental Equipment | Nakuru West | Kapkures | -0.324324, 36.036613 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 400 | 400 | Equitable | N/A | 400 | 0 | 1999600 | 499900 | 1999600 | 400 | -1999200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: No. Lack of Lab Technician. Viable: Not met. Being a Level 2 does not have. Assessor remarks: Equipments were supplied but are not in use. Stored..
434 | Preventive and Promotive Health Services | Equipping of dental, eye, laboratory and water installation in the new storey building at Rhonda Maternity | To equip dental, eye, laboratory and water installation in the new storey building at Rhonda Maternity with necessary facilities and equipment | Dental, eye, laboratory and water installation in the new storey building at Rhonda Maternity equipped | 3111101 | Purchase of Medical and Dental Equipment | Nakuru West | Kaptembwo | -0.305109, 36.055308 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | N/A | 10000000 | 10000000 | 10000000 | Equitable | Equitable | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not yet started. Viable: Not yet started. Assessor remarks: If started it's a very viable project.
435 | Preventive and Promotive Health Services | Equipping Of Female/Male Ward Keringet Hospital | To equip Female/Male Ward Keringet Hospital with necessary facilities and equipment | Female/Male Ward Keringet Hospital equipped | 3111101 | Purchase of Medical and Dental Equipment | Kuresoi South | Keringet | -0.426178, 35.68694 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 2025 | 728000 | 0 | 728000 | Equitable | Ward Fund | 728000 | 0 | 0 | 0 | 0 | 728000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
436 | Preventive and Promotive Health Services | Design and construction of Chebotoi Dispensary | To design and construct Chebotoi Dispensary | Chebotoi Dispensary designed and constructed | 3111101 | Purchase of Medical and Dental Equipment | Kuresoi South | Kiptagich | -0.553555, 35.636309 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2017/18 | 2017/18 | It stalled | 4000000 | 0 | 1416950 | Equitable | Ward Fund | 1416950 | 0 | 2183050 | 0 | 2183050 | 1416950 | 0 | Stalled | 25 | N/A | More funds required to put up a new block | 2017 | N/A | N/A | Yes | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes but the needs of the residents are not met. Contractor: AI contrators. Assessor remarks: The project stalled and it is vandalized.
437 | Preventive and Promotive Health Services | Equipping of kiborowo dispensary | To equip kiborowo dispensary with necessary facilities and equipment | Kiborowo dispensary equipped | 3111101 | Purchase of Medical and Dental Equipment | Kuresoi South | Kiptagich | -0.534972 35.579442 2391.5 11.699999809265137 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 998750 | 998750 | Equitable | Ward Fund | 998750 | 0 | 963700 | 96.5 | 963700 | 1000000 | 35050 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Assessor remarks: Functional.
438 | Preventive and Promotive Health Services | Equipping Of Kiplemeiywo Dispensary | To equip Kiplemeiywo Dispensary with necessary facilities and equipment | Kiplemeiywo Dispensary equipped | 3111101 | Purchase of Medical and Dental Equipment | Kuresoi South | Kiptagich | -0.534972 35.579442 2391.5 11.699999809265137 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | N/A | 1000000 | 1000000 | 1000000 | Equitable | Ward Fund | 1000000 | 0 | 963700 | 96.4 | 963700 | 1000000 | 36300 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Assessor remarks: Functional.
439 | Preventive and Promotive Health Services | Equipping of Githima dispensary | To equip Githima dispensary with necessary facilities and equipment | Githima dispensary equipped | 3111101 | Purchase of Medical and Dental Equipment | Kuresoi North | Kiptororo | -0.315257, 35.48315 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 972220 | 85780 | 85780 | Equitable | N/A | 85780 | 0 | 972220 | 1133.4 | 972220 | 85780 | -886440 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Yes. Assessor remarks: The facility needs electricity connection and fencing of the facility.
440 | Preventive and Promotive Health Services | Equipping of Kongoi dispensary and Kipkewa dispensary | To equip Kongoi dispensary and Kipkewa dispensary with necessary facilities and equipment | Kongoi dispensary and Kipkewa dispensary equipped | 3111101 | Purchase of Medical and Dental Equipment | Kuresoi North | Kiptororo | -0.31518 35.482992 2509 17 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1993400 | 99.7 | 1993400 | 85780 | 6600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: It is complete and operational.
441 | Preventive and Promotive Health Services | Equipping of Maiella Maternity | To equip Maiella Maternity with necessary facilities and equipment | Maiella Maternity equipped | 3111101 | Purchase of Medical and Dental Equipment | Naivasha | Maiella | -0.88774, 36.199487 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | 2025 | 1600000 | 1600000 | 1600000 | Equitable | Equitable | 1600000 | 0 | 0 | 0 | 0 | 1500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: Yes. Condition: Yet to start. Objective met: NO. Viable: NO. Assessor remarks: Equipping yet to be done.
442 | Preventive and Promotive Health Services | Equipping of Ngondi Dispensary laboratory | To equip Ngondi Dispensary laboratory with necessary facilities and equipment | Ngondi Dispensary laboratory equipped | 3111101 | Purchase of Medical and Dental Equipment | Naivasha | Maiella | -0.83119 36.203515 0 156.89999389648438 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | N/A | 1500000 | 0 | 1500000 | Equitable | Ward Fund | 1500000 | 0 | 1399870 | 0 | 1399870 | 1500000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Yet to start. Objective met: Not yet. Viable: Not Yet. Assessor remarks: Microscope calibration to be done.No lab technician.
443 | Preventive and Promotive Health Services | Equipping of Ngondi Maternity | To equip Ngondi Maternity with necessary facilities and equipment | Ngondi Maternity equipped | 3111101 | Purchase of Medical and Dental Equipment | Naivasha | Maiella | -0.88774, 36.199487 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | 2025 | 1500000 | 1500000 | 1500000 | Equitable | Equitable | 1500000 | 0 | 1997670 | 133.2 | 1997670 | 1500000 | -497670 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: Yes. Condition: Yet to start. Objective met: NO. Viable: NO. Assessor remarks: Equipping yet to be done.
444 | Preventive and Promotive Health Services | Equipping of Kapsinandet Health center | To equip Kapsinandet Health center with necessary facilities and equipment | Kapsinandet Health center equipped | 3111101 | Purchase of Medical and Dental Equipment | Molo | Mariashoni | -0.381256, 35.795671 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | 2021/22 | 1000000 | 164186.2 | 164186.2 | Equitable | N/A | 164186.2 | 0 | 835814 | 509.1 | 835814 | 164186 | -671627.8 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Working properly.
445 | Preventive and Promotive Health Services | Equipping of laboratory at Marioshoni Health Center | To equip laboratory at Marioshoni Health Center with necessary facilities and equipment | Laboratory at Marioshoni Health Center equipped | 3111101 | Purchase of Medical and Dental Equipment | Molo | Mariashoni | -0.368563 35.820929 2660.758744199764 7 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | 2021/22 | 600000 | 151758.6 | 151758.6 | Equitable | N/A | 151758.6 | 0 | 448241 | 295.4 | 448241 | 151759 | -296482.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partly. Viable: Yes. Assessor remarks: Minimal operation lack of lab technician.
446 | Preventive and Promotive Health Services | Equipping of Laboratory at Menengai dispensary | To equip Laboratory at Menengai dispensary with necessary facilities and equipment | Laboratory at Menengai dispensary equipped | 3111101 | Purchase of Medical and Dental Equipment | Nakuru East | Menengai | -0.266251, 36.100624 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 1001550 | 535033.65 | 535033.65 | Equitable | N/A | 535033.65 | 0 | 479527 | 89.6 | 479527 | 535034 | 55506.65 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Emeeland contractors. Assessor remarks: Completed.
447 | Preventive and Promotive Health Services | Equipping of a Laboratory at Ol-Rongai Dispensary | To equip a Laboratory at Ol-Rongai Dispensary with necessary facilities and equipment | A Laboratory at Ol-Rongai Dispensary equipped | 3111101 | Purchase of Medical and Dental Equipment | Rongai | Menengai West | -0.140853, 36.0179 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 2023/24 | 2000000 | 0 | 2000000 | Equitable | Ward Fund | 2000000 | 0 | 2499870 | 0 | 2499870 | 2000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yet to start. Viable: Yet to start. Assessor remarks: Yet to start.
448 | Preventive and Promotive Health Services | Equipping Ngecha Dispensary and connecting a corridor | To equip Ngecha Dispensary and connecting a corridor with necessary facilities and equipment | Ngecha Dispensary and connecting a corridor equipped | 3111101 | Purchase of Medical and Dental Equipment | Rongai | Mosop | -0.248469, 35.939694 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | 2025 | 1650000 | 1650000 | 1650000 | Equitable | Equitable | 1650000 | 0 | 2783571 | 168.7 | 2783571 | 1900000 | -1133571 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not met. Viable: It was Viable. Contractor: Not awarded. Assessor remarks: Not yet awarded, framework being prepared.
449 | Preventive and Promotive Health Services | Equipping of Ngondu Dispensary | To equip Ngondu Dispensary with necessary facilities and equipment | Ngondu Dispensary equipped | 3111101 | Purchase of Medical and Dental Equipment | Rongai | Mosop | -0.279242, 35.884895 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 2025 | 1900000 | 1900000 | 1900000 | Equitable | Ward Fund | 1900000 | 0 | 2783571 | 146.5 | 2783571 | 1900000 | -883571 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not met. Viable: It is viable. Assessor remarks: Yet to start, B/Q being prepared.
450 | Preventive and Promotive Health Services | Equipping of Ogilgei Health Centre - outpatient wing | To equip Ogilgei Health Centre - outpatient wing with necessary facilities and equipment | Ogilgei Health Centre - outpatient wing equipped | 3111101 | Purchase of Medical and Dental Equipment | Rongai | Mosop | -0.296195, 35.958817 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | 2025 | 500000 | 500000 | 500000 | Equitable | Equitable | 500000 | 0 | 211969 | 42.4 | 211969 | 980751 | 288031 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Viable. Contractor: Not yet BQ being prepared. Assessor remarks: Not tendered.
451 | Preventive and Promotive Health Services | Equipping Sumeek Maternity | To equip Sumeek Maternity with necessary facilities and equipment | Sumeek Maternity equipped | 3111101 | Purchase of Medical and Dental Equipment | Rongai | Mosop | -0.254992, 35.877064 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | 2025 | 1900000 | 1900000 | 1900000 | Equitable | Equitable | 1900000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Viable. Contractor: Not indicated. Assessor remarks: Yet to start framework being prepared.
452 | Preventive and Promotive Health Services | Roret dispensary equipping | To implement roret dispensary equipping for access to quality healthcare services | Roret dispensary equipping completed | 3111101 | Purchase of Medical and Dental Equipment | Rongai | Mosop | -0.271928 36.006104 1965.5999755859375 85.30000305175781 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | N/A | 500000 | 0 | 500000 | Equitable | Ward Fund | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: Good.
453 | Preventive and Promotive Health Services | Equipping of Gatundu -Merironi dispensary | To equip Gatundu -Merironi dispensary with necessary facilities and equipment | Gatundu -Merironi dispensary equipped | 3111101 | Purchase of Medical and Dental Equipment | Gilgil | Murindat | -0.497603, 36.397703 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 27400 | 27400 | Equitable | N/A | 27400 | 0 | 1472600 | 5374.5 | 1472600 | 27400 | -1445200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
454 | Preventive and Promotive Health Services | Equipping of Gitare dispensary | To equip Gitare dispensary with necessary facilities and equipment | Gitare dispensary equipped | 3111101 | Purchase of Medical and Dental Equipment | Gilgil | Murindat | -0.40869, 36.310599 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 1476970 | 23030 | 23030 | Equitable | N/A | 23030 | 0 | 1476970 | 6413.2 | 1476970 | 23030 | -1453940 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
455 | Preventive and Promotive Health Services | Equipping of Mwega and Sulmac dispensary | To equip Mwega and Sulmac dispensary with necessary facilities and equipment | Mwega and Sulmac dispensary equipped | 3111101 | Purchase of Medical and Dental Equipment | Naivasha | Naivasha East | -0.784823, 36.541841 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | N/A | 1000000 | 0 | 1000000 | Equitable | Ward Fund | 1000000 | 0 | 636000 | 0 | 636000 | 1000000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: Equiping not yet done.
456 | Preventive and Promotive Health Services | Equipping of Sision Maternity | To equip Sision Maternity with necessary facilities and equipment | Sision Maternity equipped | 3111101 | Purchase of Medical and Dental Equipment | Naivasha | Naivasha East | -0.867355, 36.535495 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2021 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 462000 | 92.4 | 462000 | 500000 | 38000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: No provision of maternity beds, drugs trolley, delivery packs.
457 | Preventive and Promotive Health Services | Equipping of Muguga Dispensary | To equip Muguga Dispensary with necessary facilities and equipment | Muguga Dispensary equipped | 3111101 | Purchase of Medical and Dental Equipment | Nakuru East | Nakuru East | -0.310132, 36.145932 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | N/A | 2000000 | 2000000 | 2000000 | Equitable | Equitable | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: Yes. Condition: Very Good. Objective met: Not yet. Viable: Yes. Contractor: 2024/2025. Assessor remarks: Equipment needed.
458 | Health Curative and Rehabilitative Services | Equipping of Nakuru West clinic | To equip Nakuru West clinic with necessary facilities and equipment | Nakuru West clinic equipped | 3111101 | Purchase of Medical and Dental Equipment | Nakuru West | Shabab | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | N/A | 3000000 | 41500 | 41500 | Equitable | N/A | 41500 | 0 | 2958500 | 7128.9 | 2958500 | 41500 | -2917000 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
459 | Health Curative and Rehabilitative Services | Purchase Of Physiotherapy Equipment for PLWD At Nakuru West Health Center | To procure Physiotherapy Equipment for PLWD At Nakuru West Health Center | Physiotherapy Equipment for PLWD At Nakuru West Health Center procured | 3111101 | Purchase of Medical and Dental Equipment | Nakuru West | Shabab | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | N/A | 350000 | 350000 | 350000 | Equitable | N/A | 350000 | 0 | 0 | 0 | 0 | 350000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
460 | Preventive and Promotive Health Services | Equipping of Gacharage Dispensary | To equip Gacharage Dispensary with necessary facilities and equipment | Gacharage Dispensary equipped | 3111101 | Purchase of Medical and Dental Equipment | Kuresoi North | Sirikwa | -0.289145, 35.636123 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | N/A | 1500000 | 1500000 | 1500000 | Equitable | Ward Fund | 1500000 | 0 | 2194200 | 146.3 | 2194200 | 1500000 | -694200 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes,but currently it has not addressed the needs of the locals. Assessor remarks: The project has not been undertaken.
461 | Preventive and Promotive Health Services | Equipping Of Kapket Maternity | To equip Kapket Maternity with necessary facilities and equipment | Kapket Maternity equipped | 3111101 | Purchase of Medical and Dental Equipment | Kuresoi South | Tinet | -0.496823, 35.648673 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | N/A | 1500000 | 0 | 1500000 | Equitable | Ward Fund | 1500000 | 0 | 0 | 0 | 0 | 1500000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: Yet to start.
462 | Preventive and Promotive Health Services | Equipping Of Karandit Dispensary | To equip Karandit Dispensary with necessary facilities and equipment | Karandit Dispensary equipped | 3111101 | Purchase of Medical and Dental Equipment | Kuresoi South | Tinet | -0.478599, 35.63979 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | N/A | 1500000 | 0 | 1500000 | Equitable | Ward Fund | 1500000 | 0 | 1901087 | 0 | 1901087 | 1500000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes it was viable but not meet the need since it was not equipped. Assessor remarks: Not equipped.
463 | Preventive and Promotive Health Services | Equipping of muyesh dispensary | To equip muyesh dispensary with necessary facilities and equipment | Muyesh dispensary equipped | 3111101 | Purchase of Medical and Dental Equipment | Molo | Turi | -0.302072 35.720327 2489 687.0120239257812 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2020/21 | 2020/21 | 2020/21 | 499850 | 420 | 420 | Equitable | N/A | 420 | 0 | 499580 | 118947.6 | 499580 | 420 | -499160 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yea. Viable: Yes. Assessor remarks: No title. The county government of Nakuru to facilitate the process of acquiring a title.
464 | Preventive and Promotive Health Services | Purchase and supply of laboratory equipment and reagents at Barut Dispensary | To procure and supply laboratory equipment and reagents at Barut Dispensary | Laboratory equipment and reagents at Barut Dispensary procured and supplied | 3111107 | Purchase of Laboratory Equipment | Nakuru West | Barut | -0.327064, 36.056176 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | 2024/2025 | 750000 | 750000 | 750000 | Equitable | Equitable | 750000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: No reagents supplied to the facility hence no photo taken.
465 | Preventive and Promotive Health Services | Purchase of supply of laboratory equipment at Kayole Dispensary | To procure supply of laboratory equipment at Kayole Dispensary | Supply of laboratory equipment at Kayole Dispensary procured | 3111107 | Purchase of Laboratory Equipment | Naivasha | Lake View | -0.751713, 36.457225 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | N/A | 2000000 | 2000000 | 2000000 | Equitable | Equitable | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes. Assessor remarks: Equipment not yet supplied.
466 | Preventive and Promotive Health Services | Equipping Of Kabati Laboratory | To equip Kabati Laboratory with necessary facilities and equipment | Kabati Laboratory equipped | 3111107 | Purchase of Laboratory Equipment | Naivasha | Viwandani | -0.720522, 36.445398 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | N/A | 1500000 | 1500000 | 1500000 | Equitable | Ward Fund | 1500000 | 0 | 349731 | 23.3 | 349731 | 1500000 | 1150269 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Not yet. Assessor remarks: Yet to start.
467 | Purchase of generators for alternative power source in Keringet, Bondeni, Langalanga and Njoro facilities | Purchase of generators for alternative power source in Keringet, Bondeni, Langalanga and Njoro facilities | To procure generators for alternative power source in Keringet, Bondeni, Langalanga and Njoro facilities | Generators for alternative power source in Keringet, Bondeni, Langalanga and Njoro facilities procured | 3111110 | Purchase of Generators | HQ | HQ | -0.173672, 35.862823 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2023/24 | 2023/24 | 2023/24 | 12000000 | 12000000 | 12000000 | N/A | N/A | 12000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
468 | Health Curative and Rehabilitative Services | Acquisition, installation and commissioning of a 2000 litre/pm oxygen plant in PGH | To implement acquisition, installation and commissioning of a 2000 litre/pm oxygen plant in pgh for access to quality healthcare services | Acquisition, installation and commissioning of a 2000 litre/pm oxygen plant in PGH completed | 3111120 | Purchase of Specialized Plant. - | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2020/21 | 2020/21 | N/A | 125834075 | 16262480.65 | 135282475.65 | FIF | FIF | 135282475.65 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
469 | Health Curative and Rehabilitative Services | Completion of acquisition, installation and commissioning of a 2000 litre/pm oxygen plant in PGH | To complete acquisition, installation and commissioning of a 2000 litre/pm oxygen plant in PGH | Acquisition, installation and commissioning of a 2000 litre/pm oxygen plant in PGH completed | 3111120 | Purchase of Specialized Plant. - | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | N/A | 125834075 | 7020117 | 7020117 | FIF | FIF | 7020117 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
470 | Health Curative and Rehabilitative Services | Purchase and supply of a modern mortuary refrigerator at County Public Mortuary and Olenguruone Sub County Hospital Mortuary | To procure and supply a modern mortuary refrigerator at County Public Mortuary and Olenguruone Sub County Hospital Mortuary | A modern mortuary refrigerator at County Public Mortuary and Olenguruone Sub County Hospital Mortuary procured and supplied | 3111120 | Purchase of Specialized Plant. - | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | N/A | 9000000 | 9000000 | 9000000 | FIF | FIF | 9000000 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
471 | Health Curative and Rehabilitative Services | Purchase of plant and machinery (FIF) | To procure plant and machinery (FIF) | Plant and machinery (FIF) procured | 3111120 | Purchase of Specialized Plant. - | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2024/25 | N/A | 141042000 | 271042000 | 0 | FIF | FIF | 0 | 271042000 | 692500 | 0.3 | 692500 | 35324805 | 270349500 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
472 | Health Curative and Rehabilitative Services | Purchase of plant and machinery (Nakuru west) | To procure plant and machinery (Nakuru west) | Plant and machinery (Nakuru west) procured | 3111120 | Purchase of Specialized Plant. - | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | N/A | 5000000 | 27931 | 0 | FIF | FIF | 0 | 27931 | 360749 | 1291.6 | 360749 | 27931 | -332818 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
473 | Preventive and Promotive Health Services | Construction of incinerator (Sumeek Dispensary) | To construct incinerator (Sumeek Dispensary) | Incinerator (Sumeek Dispensary) constructed | 3111120 | Purchase of Specialized Plant. - | Rongai | Mosop | -0.254889, 35.876806 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2024/25 | 2024/25 | Yet to start | 500000 | 500000 | 500000 | Equitable | Equitable | 500000 | 0 | 2752510 | 550.5 | 2752510 | 2752510 | -2252510 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Viable. Contractor: Not indicated. Assessor remarks: It cannot be implemented due to Nema restrictions.
474 | Completion of land purchase of Maai Mahiu Health centre | Completion of land purchase of Maai Mahiu Health centre | To complete land purchase of Maai Mahiu Health centre | Land purchase of Maai Mahiu Health centre completed | 3130101 | Acquisition of Land | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2022/23 | 2022/23 | 2022/23 | 150000 | 150000 | 150000 | Grant | Grant | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
475 | Preventive and Promotive Health Services | Construction of toilets at Kaplambai Dispensary | To construct toilets at Kaplambai Dispensary | Toilets at Kaplambai Dispensary constructed | 4130299 | N/A | Kuresoi South | Amalo | -0.663208 35.620325 2426.7999999999997 4.699999809265137 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 926.8 | 926.8 | Equitable | N/A | 926.8 | 0 | 999073 | 107798.1 | 999073 | 927 | -998146.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: no. Viable: no. Assessor remarks: project completed but facility not operational due to lack of medical staff.
476 | Preventive and Promotive Health Services | completion of mugwathi Githioro dispensary | To complete mugwathi Githioro dispensary | Mugwathi Githioro dispensary completed | 4130299 | N/A | Bahati | Dundori | -0.273842, 36.200992 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/2019 | 20000000 | 1508137.8 | 1508137.8 | Equitable | Ward Fund | 1508137.8 | 0 | 1508138 | 100 | 1508138 | 1508138 | -0.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Sanka builders and decorators. Assessor remarks: Good condition.
477 | Preventive and Promotive Health Services | Construction of Githioro dispensary | To construct Githioro dispensary | Githioro dispensary constructed | 4130299 | N/A | Bahati | Dundori | -0.273677, 36.201615 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2017/18 | 2017/18 | 2017/2018 | 10000000 | 1751091.6 | 1751091.6 | Equitable | N/A | 1751091.6 | 0 | 8096028 | 462.3 | 8096028 | 1751092 | -6344936.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Sanka builders and decorators. Assessor remarks: Good.
478 | Preventive and Promotive Health Services | Construction of MCH at Kiwamu Health Centre | To construct MCH at Kiwamu Health Centre | MCH at Kiwamu Health Centre constructed | 4130299 | N/A | Bahati | Dundori | -0.237345, 36.167237 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2015/16 | 2015/16 | 2015/2016 | 6000000 | 5491504.7 | 5491504.7 | Equitable | Ward Fund | 5491504.7 | 0 | 4203337 | 76.5 | 4203337 | 1288168 | 1288167.7 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
479 | Preventive and Promotive Health Services | Construction of Kapsita Dispensary | To construct Kapsita Dispensary | Kapsita Dispensary constructed | 4130299 | N/A | Molo | Elburgon | -0.294954 35.766447 0 2799.9990234375 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2016/17 | 2016/17 | N/A | 2000000 | 2000000 | 2000000 | Equitable | Ward Fund | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
480 | Preventive and Promotive Health Services | Expanson of Arimi Dispensary (maternity wing) | To implement expanson of arimi dispensary (maternity wing) for access to quality healthcare services | Expanson of Arimi Dispensary (maternity wing) completed | 4130299 | N/A | Molo | Elburgon | -0.284884, 35.845889 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2018/19 | 2018/19 | - | 2500000 | 558067.2 | 558067.2 | Equitable | N/A | 558067.2 | 0 | 515700 | 92.4 | 515700 | 558067 | 42367.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: No maternity wing.
481 | Preventive and Promotive Health Services | Kiambogo dispensary refurbishment - refurbishment and equipping of kiambogo dispensary | To implement kiambogo dispensary refurbishment - refurbishment and equipping of kiambogo dispensary for access to quality healthcare services | Kiambogo dispensary refurbishment - refurbishment and equipping of kiambogo dispensary completed | 4130299 | N/A | Gilgil | Elementaita | -0.602163, 36.131095 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 4500000 | 727214 | 727214 | Equitable | Ward Fund | 727214 | 0 | 3272817 | 450 | 3272817 | 727214 | -2545603 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good working conditions..
482 | Preventive and Promotive Health Services | Rehabilitation and equipping of maternity ward and inpatient at Langa Langa sub county hospital | To rehabilitate equipping of maternity ward and inpatient at Langa Langa sub county hospital to restore functionality | Equipping of maternity ward and inpatient at Langa Langa sub county hospital rehabilitated | 4130299 | N/A | Nakuru East | Flamingo | -0.303564, 36.072862 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 4000000 | 134874 | 134874 | Equitable | N/A | 134874 | 0 | 11510664 | 8534.4 | 11510664 | 134874 | -11375790 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Functional.
483 | Construction of Maternity at Gilgil subcounty Hospital | Construction of Maternity at Gilgil subcounty Hospital | To construct Maternity at Gilgil subcounty Hospital | Maternity at Gilgil subcounty Hospital constructed | 4130299 | N/A | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 36737200 | 3206219.5 | 0 | N/A | N/A | 0 | 3206219.5 | 750000 | 23.4 | 750000 | 0 | 2456219.5 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
484 | Preventive and Promotive Health Services | Proposed Completion Of Kasarani Dispensary In Malewa West Ward Gilgil Subcounty, | To undertake the proposed Completion Of Kasarani Dispensary In Malewa West Ward Gilgil Subcounty, | Proposed Completion Of Kasarani Dispensary In Malewa West Ward Gilgil Subcounty, implemented | 4130299 | N/A | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | N/A | 723711 | 14631 | 14631 | N/A | N/A | 14631 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
485 | Preventive and Promotive Health Services | Proposed Construction Of Incinerator And Septic Tank At Ruguru Dispensary In Kabatini Ward | To undertake the proposed Construction Of Incinerator And Septic Tank At Ruguru Dispensary In Kabatini Ward | Proposed Construction Of Incinerator And Septic Tank At Ruguru Dispensary In Kabatini Ward implemented | 4130299 | N/A | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 1000000 | 1000000 | N/A | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
486 | Preventive and Promotive Health Services | Proposed Refurbishment To Buildings And Construction Of Gate House At Bahati House At Bahati District Hospital In Bahati Ward | To undertake the proposed Refurbishment To Buildings And Construction Of Gate House At Bahati House At Bahati District Hospital In Bahati Ward | Proposed Refurbishment To Buildings And Construction Of Gate House At Bahati House At Bahati District Hospital In Bahati Ward implemented | 4130299 | N/A | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2018/19 | 2018/19 | N/A | 2000000 | 1014010 | 1014010 | N/A | N/A | 1014010 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
487 | Preventive and Promotive Health Services | Refurbishment of Health Buildings - Others | To implement refurbishment of health buildings - others for access to quality healthcare services | Refurbishment of Health Buildings - Others completed | 4130299 | N/A | HQ | HQ | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2018/19 | 2018/19 | N/A | 50000000 | 8507287.5 | 8507287.5 | Equitable | N/A | 8507287.5 | 0 | 5400882 | 63.5 | 5400882 | 1657080 | 3106405.5 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
488 | Preventive and Promotive Health Services | Construction of public toilet in Kabatini | To construct public toilet in Kabatini | Public toilet in Kabatini constructed | 4130299 | N/A | Bahati | Kabatini | -0.213214 36.162865 2030 82.5 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2015/16 | 2015/16 | 2015/16 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 600000 | 100 | 600000 | 600000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
489 | Preventive and Promotive Health Services | Proposed Construction of Rironi Health centre | To undertake the proposed Construction of Rironi Health centre | Proposed Construction of Rironi Health centre implemented | 4130299 | N/A | Kuresoi North | Kamara | -0.1811, 35.712733 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 3200000 | 271597.4 | 271597.4 | Equitable | N/A | 271597.4 | 0 | 1766373 | 650.4 | 1766373 | 271597 | -1494775.6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes but it didn't meet the needs. Contractor: Unknown. Assessor remarks: Project needs to be completed operationalised.
490 | Preventive and Promotive Health Services | Completion and equiping of Kapkures Maternity wing | To complete and equiping of Kapkures Maternity wing | And equiping of Kapkures Maternity wing completed | 4130299 | N/A | Nakuru West | Kapkures | -0.310643, 36.038628 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2015/16 | 2015/16 | 2015/2016 | 2941998.6 | 7679.55 | 7679.55 | Equitable | N/A | 7679.55 | 0 | 1798260 | 23416.2 | 1798260 | 7680 | -1790580.45 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Contractor: Sageo investment. Assessor remarks: Well implimented.
491 | Preventive and Promotive Health Services | Construction of Youth Friendly Health Centre Unit | To construct Youth Friendly Health Centre Unit | Youth Friendly Health Centre Unit constructed | 4130299 | N/A | Nakuru West | Kaptembwo | -0.30479 36.055153 1791.5 14.612000465393066 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2017/18 | 2017/18 | 2017/18 | 5000000 | 1515728 | 1515728 | Equitable | N/A | 1515728 | 0 | 1479928 | 97.6 | 1479928 | 1515728 | 35800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Very viable, it has helped the youths Very much,but defective toilets and urinals. Contractor: ZIBO COMPANY. Assessor remarks: Complete.
492 | Preventive and Promotive Health Services | Completion of Kapbarus Dispensary and Construction of Pit Latrine | To complete Kapbarus Dispensary and Construction of Pit Latrine | Kapbarus Dispensary and Construction of Pit Latrine completed | 4130299 | N/A | Kuresoi South | Keringet | -0.546278, 35.705597 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2021/22 | 2021/22 | 2025 | 1000000 | 1000000 | 1000000 | Equitable | Ward Fund | 1000000 | 0 | 637515 | 63.8 | 637515 | 999800 | 362485 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Almost complete.
493 | Preventive and Promotive Health Services | Refurbishment of Chebara Dispensary | To implement refurbishment of chebara dispensary for access to quality healthcare services | Refurbishment of Chebara Dispensary completed | 4130299 | N/A | Kuresoi South | Keringet | -0.47732, 35.679745 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2033 | 810000 | 11099 | 11099 | Equitable | N/A | 11099 | 0 | 798901 | 7198 | 798901 | 11099 | -787802 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
494 | Preventive and Promotive Health Services | Construction of Kiplembeiyo Dispensary | To construct Kiplembeiyo Dispensary | Kiplembeiyo Dispensary constructed | 4130299 | N/A | Kuresoi South | Kiptagich | -0.534595 35.578933 2463.8 54.5 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 3561.5 | 3561.5 | Equitable | N/A | 3561.5 | 0 | 1021185 | 28672.9 | 1021185 | 3562 | -1017623.5 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Don't know. Assessor remarks: There is no electricity and gate..
495 | Preventive and Promotive Health Services | Design and construction of Chebotoi dispensary | To design and construct Chebotoi dispensary | Chebotoi dispensary designed and constructed | 4130299 | N/A | Kuresoi South | Kiptagich | -0.553555, 35.636309 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2017/18 | 2017/18 | It stalled | 4000000 | 1416949.6 | 1416949.6 | Equitable | Ward Fund | 1416949.6 | 0 | 2183050 | 154.1 | 2183050 | 1416950 | -766100.4 | Stalled | 25 | 100 | More funds required to put up a new block | 2017 | N/A | -766100.4 | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes but the needs of the residents are not met. Contractor: AI contrators. Assessor remarks: The project stalled and it is vandalized.
496 | Preventive and Promotive Health Services | Construction Of Consultation Rooms In Kiptororo Dispensary | To construct Consultation Rooms In Kiptororo Dispensary | Consultation Rooms In Kiptororo Dispensary constructed | 4130299 | N/A | Kuresoi North | Kiptororo | -0.377203, 35.505747 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2014/15 | 2014/15 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 1554159 | 51.8 | 1554159 | 3000000 | 1445841 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: Partially. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The 3 rooms are incomplete,it requires good roofing plastering painting and fiting of window pane.
497 | Preventive and Promotive Health Services | Construction Of Murinduko Dispensary | To construct Murinduko Dispensary | Murinduko Dispensary constructed | 4130299 | N/A | Kuresoi North | Kiptororo | -0.322428 35.543765 2615.219 3.438999891281128 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 4084035 | 1906806 | 1906806 | Equitable | N/A | 1906806 | 0 | 1554159 | 81.5 | 1554159 | 352647 | 352647 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Good. Objective met: Yes. Viable: No. Assessor remarks: Kongoi dispensary lacks sanitary facility ,fence and staff house.
498 | Preventive and Promotive Health Services | Murinduko Dispensary-Maternity Wing - On Going | To implement murinduko dispensary-maternity wing - on going for access to quality healthcare services | Murinduko Dispensary-Maternity Wing - On Going completed | 4130299 | N/A | Kuresoi North | Kiptororo | -0.3246 35.498852 2546.3 22.100000381469727 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 3200000 | 3199957 | 3199957 | Equitable | Ward Fund | 3199957 | 0 | 948599 | 29.6 | 948599 | 0 | 2251358 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The project is not functioning.
499 | Preventive and Promotive Health Services | Expansion of moi Ndabi dispensary | To expand moi Ndabi dispensary to increase capacity | Moi Ndabi dispensary expanded | 4130299 | N/A | Naivasha | Maiella | -0.832803 36.203925 1761.6 19.399999618530273 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/17 | 3400000 | 1400583.4 | 1400583.4 | Equitable | N/A | 1400583.4 | 0 | 1399870 | 99.9 | 1399870 | 1400583 | 713.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Maintenance Required.
500 | Preventive and Promotive Health Services | Sero maternity | To implement sero maternity for access to quality healthcare services | Sero maternity completed | 4130299 | N/A | Naivasha | Maiella | -0.824917 36.203913 0 400 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2015/16 | 2015/16 | 2015/16 | 2000000 | 2330 | 2330 | Equitable | N/A | 2330 | 0 | 1997670 | 85736.9 | 1997670 | 2330 | -1995340 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: Yes. Condition: Good. Objective met: Not Yet. Viable: Not Yet. Assessor remarks: Awaiting for the Supply of items by the contractor.
501 | Preventive and Promotive Health Services | Design and construction of laboratory and drug store for Marioshoni health centre | To design and construct laboratory and drug store for Marioshoni health centre | Laboratory and drug store for Marioshoni health centre designed and constructed | 4130299 | N/A | Molo | Mariashoni | -0.368528, 35.821334 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 1656.4 | 1656.4 | Equitable | N/A | 1656.4 | 0 | 1998344 | 120643.8 | 1998344 | 1656 | -1996687.6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
502 | Preventive and Promotive Health Services | Construction and equipping of Taita dispensary | To construct and equip Taita dispensary | Taita dispensary constructed and equipped | 4130299 | N/A | Njoro | Mauche | -0.516652, 35.962658 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2022 | 10000000 | 506400.6 | 506400.6 | Equitable | N/A | 506400.6 | 0 | 5249461 | 1036.6 | 5249461 | 506401 | -4743060.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Ongoing.
503 | Preventive and Promotive Health Services | Construction of Maternity wing at Menengai Health Centre | To construct Maternity wing at Menengai Health Centre | Maternity wing at Menengai Health Centre constructed | 4130299 | N/A | Nakuru East | Menengai | -0.266242, 36.100625 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 218/19 | 3500000 | 4500000 | 4500000 | Equitable | Ward Fund | 4500000 | 0 | 1632017 | 36.3 | 1632017 | 2867983 | 2867983 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: No. Viable: No. Assessor remarks: Vired.
504 | Preventive and Promotive Health Services | Maternity Wards Menengai Dispensary - On Going | To implement maternity wards menengai dispensary - on going for access to quality healthcare services | Maternity Wards Menengai Dispensary - On Going completed | 4130299 | N/A | Rongai | Menengai West | -0.140657 36.017808 1906.8999999999999 11 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2016/17 | 2016/17 | N/A | 2247896 | 2247896 | 2247896 | Equitable | Ward Fund | 2247896 | 0 | 999980 | 44.5 | 999980 | 1247916 | 1247916 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
505 | Preventive and Promotive Health Services | Completion of Women and Pediatric Wards at Molo District Hospital | To complete Women and Pediatric Wards at Molo District Hospital | Women and Pediatric Wards at Molo District Hospital completed | 4130299 | N/A | Molo | Molo Central | N/A | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2016/17 | 2016/17 | N/A | 2000000 | 62.6 | 62.6 | Equitable | N/A | 62.6 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
506 | Preventive and Promotive Health Services | Rongai Turi health centre - Renovation of staff houses, piping, and construction of a pit latrine | To implement rongai turi health centre - renovation of staff houses, piping, and construction of a pit latrine for access to quality healthcare services | Rongai Turi health centre - Renovation of staff houses, piping, and construction of a pit latrine completed | 4130299 | N/A | Rongai | Mosop | -0.252618 35.833533 2133.2999999999997 21 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 232287.6 | 232287.6 | Equitable | N/A | 232287.6 | 0 | 1767712 | 761 | 1767712 | 232288 | -1535424.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Ndowfra. Assessor remarks: Good.
507 | Preventive and Promotive Health Services | Proposed Outpatient Block at Muguga Health Centre | To undertake the proposed Outpatient Block at Muguga Health Centre | Proposed Outpatient Block at Muguga Health Centre implemented | 4130299 | N/A | Nakuru East | Nakuru East | -0.310143, 36.145533 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2016/2017 | 2375679.8 | 547432.8 | 547432.8 | Equitable | N/A | 547432.8 | 0 | 953474 | 174.2 | 953474 | 547433 | -406041.2 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Euphemia general supplies. Assessor remarks: Project ok.
508 | Preventive and Promotive Health Services | Njokerio Dispensary | To implement njokerio dispensary for access to quality healthcare services | Njokerio Dispensary completed | 4130299 | N/A | Njoro | Njoro | -0.38976, 35.931253 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2016/17 | 2016/17 | 2015 | 2000000 | 862 | 862 | Equitable | N/A | 862 | 0 | 1999138 | 231918.6 | 1999138 | 862 | -1998276 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: In good state.
509 | Preventive and Promotive Health Services | Design and Construction of two toilets at the town centre | To design and construct two toilets at the town centre | Two toilets at the town centre designed and constructed | 4130299 | N/A | Subukia | Subukia | 0.001269 36.231898 1992.4000244140625 18.350000381469727 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2017/18 | 2017/18 | 2017/18 | 2500000 | 1299353.6 | 1299353.6 | Equitable | N/A | 1299353.6 | 0 | 1250000 | 96.2 | 1250000 | 1250000 | 49353.6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes.. Viable: Yes, the project serves the boda boda riders in the area.. Contractor: Information not available. Assessor remarks: The boda boda shades are in use.
510 | Preventive and Promotive Health Services | Construction of Ngesumin-moricho dispensary Nurse station | To construct Ngesumin-moricho dispensary Nurse station | Ngesumin-moricho dispensary Nurse station constructed | 4130299 | N/A | Rongai | Visoi | -0.205477 35.849033 1900.9000244140625 56.099998474121094 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 30 | 30 | Equitable | N/A | 30 | 0 | 999970 | 3333233.3 | 999970 | 30 | -999940 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Bad condition.
511 | Preventive and Promotive Health Services | Construction and equipping of Kabati Dispensary | To construct and equip Kabati Dispensary | Kabati Dispensary constructed and equipped | 4130299 | N/A | Naivasha | Viwandani | -0.72189, 36.444124 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 5000000 | 105095 | 105095 | Equitable | N/A | 105095 | 0 | 105095 | 100 | 105095 | 105095 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Completed and functional.
512 | Preventive and Promotive Health Services | Construction and equipping of laboratory and and connection to power Simboiyon health centre | To construct and equip laboratory and and connection to power Simboiyon health centre | Laboratory and and connection to power Simboiyon health centre constructed and equipped | 4130299 | N/A | Subukia | Waseges | 0.116735 36.274342 1803.2 9.800000190734863 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2016/17 | 2016/17 | N/A | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 629865 | 90 | 629865 | 700000 | 70135 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Maintenance.
513 | Preventive and Promotive Health Services | Construction and equipping of laboratory and power at Olgilgei Dispensary | To construct and equip laboratory and power at Olgilgei Dispensary | Laboratory and power at Olgilgei Dispensary constructed and equipped | 4130299 | N/A | Subukia | Waseges | 0.116735 36.274342 1803.2 9.800000190734863 | 4565 | HEALTH SERVICES | HEALTH SERVICES | N/A | 2016/17 | 2016/17 | N/A | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 629865 | 90 | 629865 | 699700 | 70135 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Maintenance.
514 | Trade Outstanding Contract Retention - development | Trade Outstanding Contract Retention - development | To implement trade outstanding contract retention - development for economic growth and market access | Trade Outstanding Contract Retention - development completed | 2211314 | Write Offs/ Bad Debt Expenses from Previous Years (Pending Bills) | HQ | HQ | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2022/23 | 2022/23 | N/A | 270674.2 | 270674.2 | 270674.2 | N/A | N/A | 270674.2 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
515 | County Aggregation Centres and Industrial Parks counterpart funding | County Aggregation Centres and Industrial Parks counterpart funding | To implement county aggregation centres and industrial parks counterpart funding for economic growth and market access | County Aggregation Centres and Industrial Parks counterpart funding completed | 2630203 | N/A | HQ | HQ | -0.173672, 35.862823 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2022/23 | 2022/23 | 2022/23 | 100000000 | 0 | 100000000 | N/A | N/A | 100000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
516 | Rehabilitation of Tourism Information Centre | Rehabilitation of Tourism Information Centre | To rehabilitate Tourism Information Centre to restore functionality | Tourism Information Centre rehabilitated | 3110399 | Refurbishment of Buildgs - Oth | HQ | HQ | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2022/23 | 2022/23 | N/A | 4000000 | 0 | 1827143 | N/A | N/A | 1827143 | 0 | 2000000 | 0 | 2000000 | 18483845 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
517 | Rehabilitation of Weights and Measures Office | Rehabilitation of Weights and Measures Office | To rehabilitate Weights and Measures Office to restore functionality | Weights and Measures Office rehabilitated | 3110399 | Refurbishment of Buildgs - Oth | HQ | HQ | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2022/23 | 2022/23 | 2022/23 | 4000000 | 3000000 | 3000000 | N/A | N/A | 3000000 | 0 | 2000000 | 66.7 | 2000000 | 18483845 | 1000000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
518 | Drilling, Equipping Karai Market Borehole and Construction of Water Tower at Naivasha East, Naivasha Sub County | Drilling, Equipping Karai Market Borehole and Construction of Water Tower at Naivasha East, Naivasha Sub County | To implement drilling, equipping karai market borehole and construction of water tower at naivasha east, naivasha sub county for economic growth and market access | Drilling, Equipping Karai Market Borehole and Construction of Water Tower at Naivasha East, Naivasha Sub County completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | -0.173672, 35.862823 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | 2021/22 | 10000000 | 9968504 | 9968504 | N/A | N/A | 9968504 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
519 | Market Rehabilitation and Development | Construction of a toilet at Wanyororo Market, Bahati Market and Ahero Market | To construct a toilet at Wanyororo Market, Bahati Market and Ahero Market | A toilet at Wanyororo Market, Bahati Market and Ahero Market constructed | 3110504 | Other Infrastructure and Civil Works | Bahati | Bahati | -0.157108, 36.104851 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2022/23 | 2022/23 | N/A | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1249460 | 69.4 | 1249460 | 540230 | 550540 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
520 | Market Rehabilitation and Development | Construction of market sheds at Ahero and Wanyororo Markets | To construct market sheds at Ahero and Wanyororo Markets | Market sheds at Ahero and Wanyororo Markets constructed | 3110504 | Other Infrastructure and Civil Works | Bahati | Bahati | -0.157415, 36.105226 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2022/23 | 2022/23 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1249460 | 62.5 | 1249460 | 1805990 | 750540 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Project properly done.
521 | Construction, equipping and installation of electricity for Market Admin’s Office | Construction, equipping and installation of electricity for Market Admin’s Office | To construct and equip and installation of electricity for Market Admin’s Office | And installation of electricity for Market Admin’s Office constructed and equipped | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Barut | -0.324324, 36.054632 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2022/23 | 2022/23 | 2023 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Already installed.
522 | Construction of market shade, toilets and electricity installation at park view market | Construction of market shade, toilets and electricity installation at park view market | To construct market shade, toilets and electricity installation at park view market | Market shade, toilets and electricity installation at park view market constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Barut | 0.36542, 36.05435 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2020/21 | 2020/21 | 2023 | 3000000 | 2983365 | 2983365 | Equitable | N/A | 2983365 | 0 | 2983365 | 100 | 2983365 | 2983365 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Mugima enterprise. Assessor remarks: Completed.
523 | Construction of market stalls at Barut center | Construction of market stalls at Barut center | To construct market stalls at Barut center | Market stalls at Barut center constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Barut | -0.324324, 36.054632 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2022/23 | 2022/23 | 2023 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1472370 | 98.2 | 1472370 | 1472370 | 27630 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Amperi Limited. Assessor remarks: The stalls are in good working condition.
524 | Construction of toilets at Park View Market | Construction of toilets at Park View Market | To construct toilets at Park View Market | Toilets at Park View Market constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Barut | 0.36542, 36.05435 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2020/21 | 2020/21 | 2023 | 1200000 | 0 | 1200000 | Equitable | N/A | 1200000 | 0 | 2983365 | 0 | 2983365 | 1200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Mugima enterprise. Assessor remarks: Completed.
525 | Completion of Kinamba market toilet | Completion of Kinamba market toilet | To complete Kinamba market toilet | Kinamba market toilet completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Biashara-Naivasha | -0.722688, 36.474592 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | 2023 | 1000000 | 999590 | 999590 | Equitable | N/A | 999590 | 0 | 999590 | 100 | 999590 | 999590 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ndakuki contractors.. Assessor remarks: The market should be operational for value of money..
526 | Construction of Kirima vegetables shed | Construction of Kirima vegetables shed | To construct Kirima vegetables shed | Kirima vegetables shed constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Biashara-Naivasha | -0.631887, 36.488957 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | 2022 | 1000000 | 998490 | 998490 | Equitable | N/A | 998490 | 0 | 1988190 | 199.1 | 1988190 | 998490 | -989700 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Not done .hence needs to be done..
527 | Fencing and murraming of Kinamba Market | Fencing and murraming of Kinamba Market | To secure and murraming of Kinamba Market through fencing | And murraming of Kinamba Market fenced and secured | 3110504 | Other Infrastructure and Civil Works | Naivasha | Biashara-Naivasha | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | N/A | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 1893480 | 0 | 1893480 | 2000000 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
528 | Construction of Elementaita youth stalls | Construction of Elementaita youth stalls | To construct Elementaita youth stalls | Elementaita youth stalls constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Elementaita | -0.489341, 36.156986 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2020/21 | 2020/21 | N/A | 1400000 | 1299600 | 1299600 | Equitable | N/A | 1299600 | 0 | 3870671 | 297.8 | 3870671 | 1299600 | -2571071 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Veried.
529 | Construction of market shades | Construction of market shades | To construct market shades | Market shades constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Gilgil | -0.504716, 36.328314 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 1925610 | 1925610 | Equitable | N/A | 1925610 | 0 | 1925610 | 100 | 1925610 | 1925610 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Cider collections. Assessor remarks: In good state.
530 | Construction of Mitumba sheds in Gilgil Mitumba market | Construction of Mitumba sheds in Gilgil Mitumba market | To construct Mitumba sheds in Gilgil Mitumba market | Mitumba sheds in Gilgil Mitumba market constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Gilgil | -0.503915, 36.327841 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2022/23 | 2022/23 | 2023/24 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3924356 | 98.1 | 3924356 | 3924356 | 75644 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: Yes. Assessor remarks: Demolished to pave way for ESP market.
531 | Construction of youth lockups in Gilgil Ward | Construction of youth lockups in Gilgil Ward | To construct youth lockups in Gilgil Ward | Youth lockups in Gilgil Ward constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Gilgil | -0.499145, 36.322475 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2022/23 | 2022/23 | 2022/23 | 1300000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 1202810 | 92.5 | 1202810 | 1202810 | 97190 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Raindrop contractors. Assessor remarks: Functional.
532 | Market Rehabilitation and Development | Additional Stalls at Yangale Market in Soin Ward | To implement additional stalls at yangale market in soin ward for economic growth and market access | Additional Stalls at Yangale Market in Soin Ward completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2020/21 | 2020/21 | N/A | 2000000 | 1991020 | 1991020 | N/A | N/A | 1991020 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
533 | Completion of Karai Smart Fish Market | Completion of Karai Smart Fish Market | To complete Karai Smart Fish Market | Karai Smart Fish Market completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2022/23 | 2022/23 | N/A | 15000000 | 10000000 | 10000000 | Equitable | N/A | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
534 | Completion of Kiptangwanyi Market existing Shed | Completion of Kiptangwanyi Market existing Shed | To complete Kiptangwanyi Market existing Shed | Kiptangwanyi Market existing Shed completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2022/23 | 2022/23 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
535 | Completion of Nasher market boxes | Completion of Nasher market boxes | To complete Nasher market boxes | Nasher market boxes completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2022/23 | 2022/23 | N/A | 10000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 5989050 | 199.6 | 5989050 | 800000 | -2989050 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
536 | Completion of Njoro market sheds | Completion of Njoro market sheds | To complete Njoro market sheds | Njoro market sheds completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2022/23 | 2022/23 | N/A | 10000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 5989050 | 199.6 | 5989050 | 800000 | -2989050 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
537 | Concrete works and construction of water point in Molo market | Concrete works and construction of water point in Molo market | To implement concrete works and construction of water point in molo market for economic growth and market access | Concrete works and construction of water point in Molo market completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 800000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
538 | Market Rehabilitation and Development | Construction of 2 sheds, Water point, Erection of fence and installation of water tanks and electricity in Njoro market | To construct 2 sheds, Water point, Erection of fence and installation of water tanks and electricity in Njoro market | 2 sheds, Water point, Erection of fence and installation of water tanks and electricity in Njoro market constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | N/A | 15000000 | 10000000 | 10000000 | N/A | N/A | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
539 | Construction of Gilgil market shades | Construction of Gilgil market shades | To construct Gilgil market shades | Gilgil market shades constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | N/A | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 0 | 0 | 0 | 800000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
540 | Market Rehabilitation and Development | Construction of market shed, Water point, Erection of fence and installation of 10,000L water tanks and electricity in Kinungi market | To construct market shed, Water point, Erection of fence and installation of 10,000L water tanks and electricity in Kinungi market | Market shed, Water point, Erection of fence and installation of 10,000L water tanks and electricity in Kinungi market constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | N/A | 5000000 | 5000000 | 5000000 | N/A | N/A | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
541 | Market Rehabilitation and Development | Construction of market sheds and installation of 10,000L water tank at Kihingo market | To construct market sheds and installation of 10,000L water tank at Kihingo market | Market sheds and installation of 10,000L water tank at Kihingo market constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | N/A | 5000000 | 5000000 | 5000000 | N/A | N/A | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
542 | Construction of Naivasha Fish Market | Construction of Naivasha Fish Market | To construct Naivasha Fish Market | Naivasha Fish Market constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2020/21 | 2020/21 | N/A | 10000000 | 3631685 | 3631685 | Equitable | N/A | 3631685 | 0 | 0 | 0 | 0 | 800000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
543 | Market Rehabilitation and Development | Construction of toilet at Naivasha wholesale site ground | To construct toilet at Naivasha wholesale site ground | Toilet at Naivasha wholesale site ground constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2019/20 | 2019/20 | N/A | 11000000 | 1500000 | 1500000 | N/A | N/A | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
544 | Construction of Waseges Market | Construction of Waseges Market | To construct Waseges Market | Waseges Market constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | N/A | 5000000 | 4800000 | 4800000 | Equitable | N/A | 4800000 | 0 | 0 | 0 | 0 | 800000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
545 | Design and Construction Of Bahati Stalls | Design and Construction Of Bahati Stalls | To design and construct Bahati Stalls | Bahati Stalls designed and constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | N/A | 800000 | 800000 | 800000 | N/A | N/A | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
546 | Design and Construction Of Banana Stalls For Wakulima Market | Design and Construction Of Banana Stalls For Wakulima Market | To design and construct Banana Stalls For Wakulima Market | Banana Stalls For Wakulima Market designed and constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | N/A | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
547 | Design and Construction Of Longonot Stalls | Design and Construction Of Longonot Stalls | To design and construct Longonot Stalls | Longonot Stalls designed and constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | N/A | 3000000 | 2936930 | 2936930 | N/A | N/A | 2936930 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
548 | Design and Construction Of Nasher Market Stalls | Design and Construction Of Nasher Market Stalls | To design and construct Nasher Market Stalls | Nasher Market Stalls designed and constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | N/A | 10000000 | 10000000 | 10000000 | Equitable | N/A | 10000000 | 0 | 0 | 0 | 0 | 800000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
549 | Design and Construction Of Solai and Ndungiri Markets | Design and Construction Of Solai and Ndungiri Markets | To design and construct Solai and Ndungiri Markets | Solai and Ndungiri Markets designed and constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | N/A | 8000000 | 0 | 8000000 | Equitable | N/A | 8000000 | 0 | 0 | 0 | 0 | 800000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
550 | Design and Construction Of Wakulima Market Shades | Design and Construction Of Wakulima Market Shades | To design and construct Wakulima Market Shades | Wakulima Market Shades designed and constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | N/A | 10000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 0 | 0 | 0 | 800000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
551 | Market Rehabilitation and Development | Market rehabilitation | To implement market rehabilitation for economic growth and market access | Market rehabilitation completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2022/23 | 2022/23 | N/A | 15268250 | 8968250 | 8968250 | N/A | N/A | 8968250 | 0 | 2700072 | 30.1 | 2700072 | 580000 | 6268178 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
552 | Market Rehabilitation and Development | Proposed Construction of 4 No. Market Shed, Pavillion, Animal Paddocks, 2 No Office Block and Chainlink Fencing at Banita Market, Soin Ward, Rongai Sub County | To undertake the proposed Construction of 4 No. Market Shed, Pavillion, Animal Paddocks, 2 No Office Block and Chainlink Fencing at Banita Market, Soin Ward, Rongai Sub County | Proposed Construction of 4 No. Market Shed, Pavillion, Animal Paddocks, 2 No Office Block and Chainlink Fencing at Banita Market, Soin Ward, Rongai Sub County implemented | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2018/19 | 2020/21 | N/A | 10283413.1 | 1435479 | 1435479 | N/A | N/A | 1435479 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
553 | Market Rehabilitation and Development | Proposed Construction of Market Sheds and Renovation Works at Mosop Ward | To undertake the proposed Construction of Market Sheds and Renovation Works at Mosop Ward | Proposed Construction of Market Sheds and Renovation Works at Mosop Ward implemented | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | N/A | 3000000 | 0 | 3000000 | N/A | N/A | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
554 | Proposed Construction of Market Sheds in Elementaita Ward | Proposed Construction of Market Sheds in Elementaita Ward | To undertake the proposed Construction of Market Sheds in Elementaita Ward | Proposed Construction of Market Sheds in Elementaita Ward implemented | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2018/19 | 2020/21 | N/A | 5000000 | 634833.96 | 634833.96 | Equitable | N/A | 634833.96 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
555 | Market Rehabilitation and Development | Purchase and installation of 2 (10,000 litres) Water tanks at Rongai Acacia Dairy Cooperative in Rongai | To procure and install 2 (10,000 litres) Water tanks at Rongai Acacia Dairy Cooperative in Rongai | 2 (10,000 litres) Water tanks at Rongai Acacia Dairy Cooperative in Rongai procured and installed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | N/A | 700000 | 700000 | 700000 | N/A | N/A | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
556 | Market Rehabilitation and Development | Refurbishment and equipping of kea Amos Market into a Jua Kali Enterprise centre | To implement refurbishment and equipping of kea amos market into a jua kali enterprise centre for economic growth and market access | Refurbishment and equipping of kea Amos Market into a Jua Kali Enterprise centre completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | N/A | 2500000 | 2500000 | 2500000 | N/A | N/A | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
557 | Market Rehabilitation and Development | Refurbishment and equipping of Subukia ESP Market into an Enterprise centre | To implement refurbishment and equipping of subukia esp market into an enterprise centre for economic growth and market access | Refurbishment and equipping of Subukia ESP Market into an Enterprise centre completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | N/A | 3000000 | 3000000 | 1000000 | N/A | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
558 | Rehabilitation of Drainage Works at Rhonda Market | Rehabilitation of Drainage Works at Rhonda Market | To rehabilitate Drainage Works at Rhonda Market to restore functionality | Drainage Works at Rhonda Market rehabilitated | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2020/21 | 2020/21 | N/A | 1450000 | 1450000 | 1450000 | Equitable | N/A | 1450000 | 0 | 5989050 | 413 | 5989050 | 18483845 | -4539050 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
559 | Rehabilitation of Mburu Gichua Market Toilet | Rehabilitation of Mburu Gichua Market Toilet | To rehabilitate Mburu Gichua Market Toilet to restore functionality | Mburu Gichua Market Toilet rehabilitated | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2020/21 | 2020/21 | N/A | 1000000 | 988850 | 988850 | Equitable | N/A | 988850 | 0 | 5989050 | 605.7 | 5989050 | 18483845 | -5000200 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
560 | Rehabilitation of Naivasha Wholesale site toilet | Rehabilitation of Naivasha Wholesale site toilet | To rehabilitate Naivasha Wholesale site toilet to restore functionality | Naivasha Wholesale site toilet rehabilitated | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2020/21 | 2020/21 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 5989050 | 598.9 | 5989050 | 0 | -4989050 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
561 | Rehabilitation of Nasha Market water goods and roof drains works | Rehabilitation of Nasha Market water goods and roof drains works | To rehabilitate Nasha Market water goods and roof drains works to restore functionality | Nasha Market water goods and roof drains works rehabilitated | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2020/21 | 2020/21 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 5989050 | 598.9 | 5989050 | 18483845 | -4989050 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
562 | Market Rehabilitation and Development | Solarization of Borehole At Kiremba Farmers Cooperative Society | To implement solarization of borehole at kiremba farmers cooperative society for economic growth and market access | Solarization of Borehole At Kiremba Farmers Cooperative Society completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2022/23 | 2022/23 | N/A | 5000000 | 5000000 | 5000000 | N/A | N/A | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
563 | Construction of market shed at Kabatini Market | Construction of market shed at Kabatini Market | To construct market shed at Kabatini Market | Market shed at Kabatini Market constructed | 3110504 | Other Infrastructure and Civil Works | Bahati | Kabatini | -0.232429, 36.147492 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | 2021 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999999 | 100 | 1999999 | 2000000 | 1 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Jemach limited. Assessor remarks: Operational,more stalls are required.
564 | Construction of Arahuka Market | Construction of Arahuka Market | To construct Arahuka Market | Arahuka Market constructed | 3110504 | Other Infrastructure and Civil Works | Subukia | Kabazi | -0.159188 36.045365 2081.3 10.899999618530273 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2022/23 | 2022/23 | 2022/23 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2970700 | 99 | 2970700 | 2970700 | 29300 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: Peca services ltd. Assessor remarks: To be operationalized.
565 | Raising of perimeter fence and erecting razor wire in rhonda market | Raising of perimeter fence and erecting razor wire in rhonda market | To implement raising of perimeter fence and erecting razor wire in rhonda market for economic growth and market access | Raising of perimeter fence and erecting razor wire in rhonda market completed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kaptembwo | -0.311701, 36.059638 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | 2021/22 | 3624703 | 3624703 | 3624703 | Equitable | N/A | 3624703 | 0 | 0 | 0 | 0 | 3624703 | 0 | Vired | 25 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No,it's not functional. Viable: Yes,had it been functional. Contractor: U177. Assessor remarks: Part of the wall has been demolished and vandalized gate.
566 | Construction of pit latrines and urinal at soitaran market | Construction of pit latrines and urinal at soitaran market | To construct pit latrines and urinal at soitaran market | Pit latrines and urinal at soitaran market constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Keringet | -0.49943, 35.724502 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2020/21 | 2020/21 | 2022 | 500000 | 499837 | 499837 | Equitable | N/A | 499837 | 0 | 499837 | 100 | 499837 | 499837 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In use.
567 | Market Rehabilitation and Development | Construction of sheds, toilets, pit latrines at Keringet bus park | To construct sheds, toilets, pit latrines at Keringet bus park | Sheds, toilets, pit latrines at Keringet bus park constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Keringet | -0.427113 35.692842 2683.500244140625 57.48400115966797 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 499837 | 50 | 499837 | 1000000 | 500163 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Not constructed.
568 | Fencing of keringet market | Fencing of keringet market | To secure keringet market through fencing | Keringet market fenced and secured | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Keringet | -0.425497, 35.693785 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | 2022 | 900000 | 900000 | 900000 | Equitable | N/A | 900000 | 0 | 4521428 | 502.4 | 4521428 | 900000 | -3621428 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: No. Viable: No. Assessor remarks: Vandalized.
569 | Completion of Burma stalls | Completion of Burma stalls | To complete Burma stalls | Burma stalls completed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Kivumbini | -0.297885, 36.08281 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | 2021/22 | 1000000 | 996100 | 996100 | Equitable | N/A | 996100 | 0 | 996100 | 100 | 996100 | 996100 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Protect traders from harsh weather conditions.
570 | Renovation of the vandalised doors on the curio shops along the Jack-mortuary street. | Renovation of the vandalised doors on the curio shops along the Jack-mortuary street. | To rehabilitate the vandalised doors on the curio shops along the Jack-mortuary street to restore functionality | The vandalised doors on the curio shops along the Jack-mortuary street rehabilitated | 3110504 | Other Infrastructure and Civil Works | Nakuru West | London | -0.279751, 36.074921 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | N/A | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 0 | 0 | 0 | 400000 | 0 | Vired | 25 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The stalls were vandalised and salvaged materials moved to nakuru west subcounty offices and Area MCAs office..
571 | Construction of Maiella market shed and toilet | Construction of Maiella market shed and toilet | To construct Maiella market shed and toilet | Maiella market shed and toilet constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maiella | -0.893718, 36.198463 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | 2022 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3365400 | 96.2 | 3365400 | 3500000 | 134600 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Yes. Contractor: Rivtoc Contractors Ltd. Assessor remarks: Project not connected to Power.
572 | Market Rehabilitation and Development | Construction of Ndabibi Market | To construct Ndabibi Market | Ndabibi Market constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maiella | -0.804803 36.246244 0 22.5 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2022/23 | 2022/23 | N/A | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 2657154 | 75.9 | 2657154 | 842846 | 842846 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Eruc Africa Ltd. Assessor remarks: In use.
573 | Completion of Kasarani septic tank in the market | Completion of Kasarani septic tank in the market | To complete Kasarani septic tank in the market | Kasarani septic tank in the market completed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Malewa West | -0.702703 36.309037 0 2000 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Vired | 25 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Partly. Viable: Partly. Assessor remarks: Need good management.
574 | Construction of toilet at Kasarani market | Construction of toilet at Kasarani market | To construct toilet at Kasarani market | Toilet at Kasarani market constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Malewa West | -0.702703 36.291018 0 2000 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2018/19 | 2018/19 | N/A | 500000 | 699973 | 699973 | Equitable | N/A | 699973 | 0 | 0 | 0 | 0 | 699973 | 0 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Partly. Viable: Partly. Assessor remarks: Need good management.
575 | Construction of mangu market | Construction of mangu market | To construct mangu market | Mangu market constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Menengai West | -0.166756, 36.010995 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2019/20 | 2019/20 | 2021/22 | 3044694 | 2998000 | 2998000 | Equitable | N/A | 2998000 | 0 | 979740 | 32.7 | 979740 | 2998000 | 2018260 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Lam_ac. Assessor remarks: Functional.
576 | Construction of Olrongai market toilets | Construction of Olrongai market toilets | To construct Olrongai market toilets | Olrongai market toilets constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Menengai West | -0.146645, 36.009212 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | 2021/22 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 979740 | 98 | 979740 | 2998000 | 20260 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
577 | Construction of Free Area wholesale market, toilet and a gate | Construction of Free Area wholesale market, toilet and a gate | To construct Free Area wholesale market, toilet and a gate | Free Area wholesale market, toilet and a gate constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Nakuru East | -0.292872, 36.120464 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | 2021/2022 | 3000000 | 2999905 | 2999905 | Equitable | N/A | 2999905 | 0 | 2999905 | 100 | 2999905 | 2999905 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: SAMUES MERCHANTS. Assessor remarks: One side requires blocking to avoid rain. No gate was identified.
578 | Design and construction of Free Area market stalls | Design and construction of Free Area market stalls | To design and construct Free Area market stalls | Free Area market stalls designed and constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Nakuru East | -0.293184, 36.120217 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | 2021/2022 | 5000000 | 4827142.8 | 4999999.8 | Equitable | N/A | 4999999.8 | 0 | 4827143 | 100 | 4827143 | 4827143 | -0.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Dermerc ventures. Assessor remarks: Project ok.
579 | Extension of Free Area wholesale market | Extension of Free Area wholesale market | To expand Free Area wholesale market to increase capacity | Free Area wholesale market expanded | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Nakuru East | -0.292917, 36.120258 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | 2021/2022 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2999905 | 100 | 2999905 | 3000000 | 95 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Lumiseal enterprises. Assessor remarks: Traders need to be settled.
580 | Rehabilitation of free area fresh food market (toilets, gates, fencing ) | Rehabilitation of free area fresh food market (toilets, gates, fencing ) | To rehabilitate free area fresh food market (toilets, gates, fencing ) to restore functionality | Free area fresh food market (toilets, gates, fencing ) rehabilitated | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Nakuru East | -0.29259, 36.119569 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2020/21 | 2020/21 | 2020/2021 | 2558423 | 2492535 | 2492535 | Equitable | N/A | 2492535 | 0 | 2492535 | 100 | 2492535 | 2492535 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: No. Viable: No. Contractor: Greatrift general merchant. Assessor remarks: Toilet condemned and not in use.A permanent fence needed. A gate not installed.
581 | Construction of a toilet at Kamwaura market | Construction of a toilet at Kamwaura market | To construct a toilet at Kamwaura market | A toilet at Kamwaura market constructed | 3110504 | Other Infrastructure and Civil Works | Njoro | Njoro | -0.281801, 35.868582 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | 2016 | 1200000 | 1099800 | 1099800 | Equitable | N/A | 1099800 | 0 | 1099800 | 100 | 1099800 | 1099800 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: No available. Assessor remarks: Worn out due to the rains.
582 | Building of Market Shed at narasha | Building of Market Shed at narasha | To implement building of market shed at narasha for economic growth and market access | Building of Market Shed at narasha completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Olkaria | -0.91605, 36.26702 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | N/A | 998770 | 998770 | 998770 | Equitable | N/A | 998770 | 0 | 711889 | 71.3 | 711889 | 286881 | 286881 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional and well built.
583 | Market Rehabilitation and Development | Construction of fish market stalls | To construct fish market stalls | Fish market stalls constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Olkaria | -0.817264, 36.326217 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2019/20 | 2019/20 | 2019/20 | 4834865 | 612400 | 612400 | Equitable | N/A | 612400 | 0 | 4209000 | 687.3 | 4209000 | 612400 | -3596600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Viable but the model is not secure for the purpose. Contractor: Northern city. Assessor remarks: Completed but not operational.
584 | Construction of Market stalls at Narasha centre | Construction of Market stalls at Narasha centre | To construct Market stalls at Narasha centre | Market stalls at Narasha centre constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Olkaria | -0.915578 36.268129 2000.88 1.8179999589920044 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | 2021/22 | 3000000 | 2854600 | 2854600 | Equitable | N/A | 2854600 | 0 | 2854600 | 100 | 2854600 | 2854600 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional few people have business there.
585 | Construction of market stalls at Rapland area | Construction of market stalls at Rapland area | To construct market stalls at Rapland area | Market stalls at Rapland area constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Olkaria | -0.938128 36.364994 1907.631103515625 14.281000137329102 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | 2021/22 | 2500000 | 2404700 | 2404700 | Equitable | N/A | 2404700 | 0 | 2854600 | 118.7 | 2854600 | 2404700 | -449900 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Tes. Assessor remarks: Completed awaiting electricity.
586 | Construction of modern market stalls at game mwisho | Construction of modern market stalls at game mwisho | To construct modern market stalls at game mwisho | Modern market stalls at game mwisho constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Rhonda | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2020/21 | 2020/21 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 2960772 | 197.4 | 2960772 | 1500000 | -1460772 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
587 | Roofing of Nakuru west market | Roofing of Nakuru west market | To implement roofing of nakuru west market for economic growth and market access | Roofing of Nakuru west market completed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Shabab | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | N/A | 2878898 | 2878898 | 2878898 | Equitable | N/A | 2878898 | 0 | 2843760 | 98.8 | 2843760 | 0 | 35138 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
588 | Market Rehabilitation and Development | Construction of market toilets and lockups in Kivoronjo center | To construct market toilets and lockups in Kivoronjo center | Market toilets and lockups in Kivoronjo center constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Solai | 0.115358 36.222233 1849.1999999999998 6.300000190734863 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | 2021/22 | 1800000 | 1711590 | 1711590 | Equitable | N/A | 1711590 | 0 | 1711590 | 100 | 1711590 | 1711590 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
589 | Construction of Nyamamithi Market stalls | Construction of Nyamamithi Market stalls | To construct Nyamamithi Market stalls | Nyamamithi Market stalls constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Solai | 0.001937 36.155355 1712.5999755859375 18.322999954223633 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2022/23 | 2022/23 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 987090 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ms Laron investment limited. Assessor remarks: Complete and operational.
590 | Market Rehabilitation and Development | Rehabilitation of muricho market toilet | To rehabilitate muricho market toilet to restore functionality | Muricho market toilet rehabilitated | 3110504 | Other Infrastructure and Civil Works | Rongai | Visoi | -0.149943 35.881463 1841.6 9.300000190734863 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 400000 | 399500 | 399500 | Equitable | N/A | 399500 | 0 | 399500 | 100 | 399500 | 399500 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Very good.
591 | Construction of Guest Inn market sheds at Viwandani Ward | Construction of Guest Inn market sheds at Viwandani Ward | To construct Guest Inn market sheds at Viwandani Ward | Guest Inn market sheds at Viwandani Ward constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Viwandani | -0.718566 36.435168 1899.5 17.726999282836914 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 3965912 | 132.2 | 3965912 | 3000000 | -965912 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Assessor remarks: Complete.
592 | Construction of market shed at open air market at Viwandani Ward | Construction of market shed at open air market at Viwandani Ward | To construct market shed at open air market at Viwandani Ward | Market shed at open air market at Viwandani Ward constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Viwandani | -0.714783, 36.433901 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | 2021/22 | 4000000 | 2995000 | 2995000 | Equitable | N/A | 2995000 | 0 | 2995000 | 100 | 2995000 | 2995000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Assessor remarks: Operational.
593 | Additional fund for Simboyon market shades | Additional fund for Simboyon market shades | To implement additional fund for simboyon market shades for economic growth and market access | Additional fund for Simboyon market shades completed | 3110504 | Other Infrastructure and Civil Works | Subukia | Waseges | 0.080873 36.244899 0 20.445999145507812 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2020/21 | 2020/21 | N/A | 318219 | 318219 | 318219 | Equitable | N/A | 318219 | 0 | 1300000 | 408.5 | 1300000 | 318219 | -981781 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
594 | Market Rehabilitation and Development | Construction of market shed at Ndatho IDP Farm | To construct market shed at Ndatho IDP Farm | Market shed at Ndatho IDP Farm constructed | 3110504 | Other Infrastructure and Civil Works | Subukia | Waseges | 0.080873 36.244899 0 20.445999145507812 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2022/23 | 2022/23 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1300000 | 86.7 | 1300000 | 1368340 | 200000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
595 | Construction of market Sheds at Polepole Centre, Kahuruko and Mumoi centers | Construction of market Sheds at Polepole Centre, Kahuruko and Mumoi centers | To construct market Sheds at Polepole Centre, Kahuruko and Mumoi centers | Market Sheds at Polepole Centre, Kahuruko and Mumoi centers constructed | 3110504 | Other Infrastructure and Civil Works | Subukia | Waseges | 0.188127 36.235617 1657.3 12.899999618530273 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | 2021/22 | 4000000 | 3850000 | 3850000 | Equitable | N/A | 3850000 | 0 | 3850000 | 100 | 3850000 | 3850000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
596 | Construction of lockups at olenguruone market | Construction of lockups at olenguruone market | To construct lockups at olenguruone market | Lockups at olenguruone market constructed | 3110599 | Other Infrastructure and Civil Works | Kuresoi South | Amalo | -0.589072, 35.685198 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2020/21 | 2020/21 | 2022 | 3370224 | 3370224 | 3370224 | Equitable | N/A | 3370224 | 0 | 0 | 0 | 0 | 3370224 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Good. Objective met: no. Viable: yes, if it was constructed. Assessor remarks: no lockups was constructed.
597 | Construction of market stalls at barut ward | Construction of market stalls at barut ward | To construct market stalls at barut ward | Market stalls at barut ward constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Barut | 0.32432, 36.05463 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2020/21 | 2020/21 | 2023 | 1854938 | 1850000 | 1850000 | Equitable | N/A | 1850000 | 0 | 1850000 | 100 | 1850000 | 1850000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ventair constructed. Assessor remarks: Completed.
598 | Construction of shade at sukuma wiki section in wakulima market | Construction of shade at sukuma wiki section in wakulima market | To construct shade at sukuma wiki section in wakulima market | Shade at sukuma wiki section in wakulima market constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | -0.285277, 36.077248 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2019/20 | 2019/20 | 2021/22 | 1500000 | 1424265 | 1424265 | Equitable | N/A | 1424265 | 0 | 1424265 | 100 | 1424265 | 1424265 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Philed wells ltd. Assessor remarks: Need for rehabilitation.
599 | Construction of Kinamba Market | Construction of Kinamba Market | To construct Kinamba Market | Kinamba Market constructed | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2019/20 | 2019/20 | N/A | 10000000 | 2386240 | 2386240 | Equitable | N/A | 2386240 | 0 | 0 | 0 | 0 | 800000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
600 | Development and Management of Markets | Equipping Bondeni Local Shoe Manufacturing Centre | To equip Bondeni Local Shoe Manufacturing Centre with necessary facilities and equipment | Bondeni Local Shoe Manufacturing Centre equipped | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
601 | Development and Management of Markets | Fencing of Elementaita Hot springs and establishment of ablution block | To secure Elementaita Hot springs and establishment of ablution block through fencing | Elementaita Hot springs and establishment of ablution block fenced and secured | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | N/A | 5000000 | 4998000 | 4998000 | Equitable | N/A | 4998000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
602 | Development and Management of Markets | Rehabilitation Of Markets | To rehabilitate Markets to restore functionality | Markets rehabilitated | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | N/A | 10500000 | 10500000 | 7500000 | Equitable | N/A | 7500000 | 0 | 5989050 | 57 | 5989050 | 18483845 | 4510950 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
603 | Construction of Lalwet stalls | Construction of Lalwet stalls | To construct Lalwet stalls | Lalwet stalls constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Kapkures | -0.288288, 36.05451 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 2499900 | 2499900 | Equitable | N/A | 2499900 | 0 | 2499900 | 100 | 2499900 | 2499900 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Viable. But has not been done. Assessor remarks: Not done. There was no land by time of budgeting in 2020 and the land has just been bought recently 2025..
604 | Construction of Tulwet stalls | Construction of Tulwet stalls | To construct Tulwet stalls | Tulwet stalls constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Kapkures | -0.288288, 36.05451 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 2499900 | 250 | 2499900 | 1000000 | -1499900 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Viable. But has not been done. Assessor remarks: Not done. There was no land by time of budgeting in 2020 and the land has just been bought recently 2025..
605 | Additional fund for improving of fish stalls in Rhonda market | Additional fund for improving of fish stalls in Rhonda market | To implement additional fund for improving of fish stalls in rhonda market for economic growth and market access | Additional fund for improving of fish stalls in Rhonda market completed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Kaptembwo | -0.311198, 36.059481 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3459200 | 86.5 | 3459200 | 4000000 | 540800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Yet to start.
606 | Construction of modern curio shops opposite PGH Nakuru Level 5 hospital | Construction of modern curio shops opposite PGH Nakuru Level 5 hospital | To construct modern curio shops opposite PGH Nakuru Level 5 hospital | Modern curio shops opposite PGH Nakuru Level 5 hospital constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | London | -0.274897 36.052632 1870.7651048924022 72.9000015258789 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2020/21 | 2020/21 | N/A | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 0 | 0 | 0 | 2500000 | 0 | Vired | 25 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Were vandalised.
607 | Rehabilitation and maintenance of Kiratina market | Rehabilitation and maintenance of Kiratina market | To rehabilitate maintenance of Kiratina market to restore functionality | Maintenance of Kiratina market rehabilitated | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Menengai | -0.272594 36.096523 1897.699951171875 10.166999816894531 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2019/20 | 2019/20 | N/A | 3499975 | 3499975 | 3499975 | Equitable | N/A | 3499975 | 0 | 0 | 0 | 0 | 3499975 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
608 | Construction of Market sheds and toilet at Kiambogo market | Construction of Market sheds and toilet at Kiambogo market | To construct Market sheds and toilet at Kiambogo market | Market sheds and toilet at Kiambogo market constructed | 3110599 | Other Infrastructure and Civil Works | Naivasha | Naivasha East | -0.871002, 36.51092 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | 2022 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2849915 | 95 | 2849915 | 1242000 | 150085 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Not fuctional trade department to market operational.
609 | Construction of Free area mtumba stalls | Construction of Free area mtumba stalls | To construct Free area mtumba stalls | Free area mtumba stalls constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Nakuru East | -0.293153, 36.120236 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2020/21 | 2020/21 | 2020/2021 | 3000000 | 2995000 | 2995000 | Equitable | N/A | 2995000 | 0 | 2995000 | 100 | 2995000 | 2995000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Magnate limited. Assessor remarks: Project ok.
610 | Purchase of weighing machines (Standards) for Weights and Measures | Purchase of weighing machines (Standards) for Weights and Measures | To procure weighing machines (Standards) for Weights and Measures | Weighing machines (Standards) for Weights and Measures procured | 3111010 | N/A | HQ | HQ | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | N/A | 1000000 | 1000000 | 1000000 | N/A | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
611 | Purchase and installation of 3000 litre milk cooler in Dundori Farmers Cooperative Society | Purchase and installation of 3000 litre milk cooler in Dundori Farmers Cooperative Society | To procure and install 3000 litre milk cooler in Dundori Farmers Cooperative Society | 3000 litre milk cooler in Dundori Farmers Cooperative Society procured and installed | 3111120 | Purchase of Specialized Plant. - | HQ | HQ | -0.173672, 35.862823 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | 2021/22 | 8000000 | 8000000 | 8000000 | N/A | N/A | 8000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
612 | Purchase and installation of 3000 litre milk cooler in Mukasu Farmers Cooperative in Kuresoi North | Purchase and installation of 3000 litre milk cooler in Mukasu Farmers Cooperative in Kuresoi North | To procure and install 3000 litre milk cooler in Mukasu Farmers Cooperative in Kuresoi North | 3000 litre milk cooler in Mukasu Farmers Cooperative in Kuresoi North procured and installed | 3111120 | Purchase of Specialized Plant. - | HQ | HQ | -0.173672, 35.862823 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | 2021/22 | 8000000 | 8000000 | 8000000 | N/A | N/A | 8000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
613 | Purchase and installation of 3000 litre milk cooler in Soitaran and Arutani Farmers Cooperative Society | Purchase and installation of 3000 litre milk cooler in Soitaran and Arutani Farmers Cooperative Society | To procure and install 3000 litre milk cooler in Soitaran and Arutani Farmers Cooperative Society | 3000 litre milk cooler in Soitaran and Arutani Farmers Cooperative Society procured and installed | 3111120 | Purchase of Specialized Plant. - | HQ | HQ | -0.173672, 35.862823 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | 2021/22 | 8000000 | 0 | 8000000 | N/A | N/A | 8000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
614 | Purchase and installation of Pasteurizer and milk ATM set in Molo dairy Farmers Cooperative in Molo | Purchase and installation of Pasteurizer and milk ATM set in Molo dairy Farmers Cooperative in Molo | To procure and install Pasteurizer and milk ATM set in Molo dairy Farmers Cooperative in Molo | Pasteurizer and milk ATM set in Molo dairy Farmers Cooperative in Molo procured and installed | 3111120 | Purchase of Specialized Plant. - | HQ | HQ | -0.173672, 35.862823 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 2000000 | 2000000 | N/A | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
615 | Rehabilitation of coffee factory at Mutungati Farmers Cooperative in Bahati | Rehabilitation of coffee factory at Mutungati Farmers Cooperative in Bahati | To rehabilitate coffee factory at Mutungati Farmers Cooperative in Bahati to restore functionality | Coffee factory at Mutungati Farmers Cooperative in Bahati rehabilitated | 3111299 | Rehabilitation & Renovation - | HQ | HQ | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2021/22 | 2021/22 | N/A | 6000000 | 5799010 | 5799010 | N/A | N/A | 5799010 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
616 | Purchase of land for Langalanga Centre Market | Purchase of land for Langalanga Centre Market | To acquire land for Langalanga Centre Market | Land for Langalanga Centre Market acquired | 3130101 | Acquisition of Land | Gilgil | Murindat | -0.49925, 36.370528 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 7000000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 2400000 | 100 | 2400000 | 2400000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: Peter Wambugu. Assessor remarks: Land purchased.
617 | Construction of professional shoe shine stalls | Construction of professional shoe shine stalls | To construct professional shoe shine stalls | Professional shoe shine stalls constructed | 4130299 | N/A | Kuresoi South | Amalo | -0.588741, 35.685356 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2016/17 | 2016/17 | 2022 | 996953.3 | 996953 | 996953 | Equitable | N/A | 996953 | 0 | 0 | 0 | 0 | 996953 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: not yet started. Viable: not yet stared. Assessor remarks: it doesn't exist.
618 | Construction of modern toilet at Kinamba market | Construction of modern toilet at Kinamba market | To construct modern toilet at Kinamba market | Modern toilet at Kinamba market constructed | 4130299 | N/A | Naivasha | Biashara-Naivasha | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 1982535 | 1982535 | Equitable | N/A | 1982535 | 0 | 1982535 | 100 | 1982535 | 1982535 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
619 | Construction of Nasher market stalls | Construction of Nasher market stalls | To construct Nasher market stalls | Nasher market stalls constructed | 4130299 | N/A | Nakuru East | Biashara-Nakuru | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2019/20 | 2019/20 | 2019/20 | 900000 | 900000 | 900000 | Equitable | N/A | 900000 | 0 | 9633950 | 1070.4 | 9633950 | 900000 | -8733950 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
620 | Purchase of rollers for the Youth | Purchase of rollers for the Youth | To procure rollers for the Youth | Rollers for the Youth procured | 4130299 | N/A | Nakuru East | Biashara-Nakuru | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 1996950 | 1996950 | Equitable | N/A | 1996950 | 0 | 1996950 | 100 | 1996950 | 1996950 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
621 | construction and installation of gates at Githioro market | construction and installation of gates at Githioro market | To construct and installation of gates at Githioro market | And installation of gates at Githioro market constructed | 4130299 | N/A | Bahati | Dundori | -0.263495, 36.188863 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/2019 | 448311 | 429790 | 429790 | Equitable | N/A | 429790 | 0 | 429790 | 100 | 429790 | 429790 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: Yes. Contractor: Feroda limited. Assessor remarks: Gates vandalised, no good will from community.
622 | Construction of Elementaita youth stalls | Construction of Elementaita youth stalls | To construct Elementaita youth stalls | Elementaita youth stalls constructed | 4130299 | N/A | Gilgil | Elementaita | -0.489341, 36.156986 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2020/21 | 2020/21 | N/A | 1400000 | 1299600 | 1299600 | Equitable | N/A | 1299600 | 0 | 3870671 | 297.8 | 3870671 | 1299600 | -2571071 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Veried.
623 | Construction of Gilgil market shades and gate | Construction of Gilgil market shades and gate | To construct Gilgil market shades and gate | Gilgil market shades and gate constructed | 4130299 | N/A | Gilgil | Gilgil | -0.50477, 36.328393 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2020/21 | 2020/21 | 2020/21 | 3374100 | 2987503 | 2987503 | Equitable | N/A | 2987503 | 0 | 2833220 | 94.8 | 2833220 | 2987503 | 154283 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: CALLBEST LOGISTICS. Assessor remarks: Needs rehabilitation and drainage works.
624 | Construction of Kampi Moto Market | Construction of Kampi Moto Market | To construct Kampi Moto Market | Kampi Moto Market constructed | 4130299 | N/A | HQ | HQ | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2020/21 | 2020/21 | N/A | 10000000 | 4991080 | 4991080 | Equitable | N/A | 4991080 | 0 | 0 | 0 | 0 | 800000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
625 | Construction of market in Kiptangwanyi | Construction of market in Kiptangwanyi | To construct market in Kiptangwanyi | Market in Kiptangwanyi constructed | 4130299 | N/A | HQ | HQ | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2019/20 | 2019/20 | 2019/20 | 5000000 | 2000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 0 | 0 | 0 | 800000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
626 | Generator and cream separator- Suka farmers Cooperative | Generator and cream separator- Suka farmers Cooperative | To implement generator and cream separator- suka farmers cooperative for economic growth and market access | Generator and cream separator- Suka farmers Cooperative completed | 4130299 | N/A | HQ | HQ | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2020/21 | 2020/21 | 2020/21 | 8000000 | 4935150 | 4935150 | Equitable | N/A | 4935150 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
627 | Market Rehabilitation and Development | Market Rehabilitation | To implement market rehabilitation for economic growth and market access | Market Rehabilitation completed | 4130299 | N/A | HQ | HQ | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2019/20 | 2019/20 | N/A | 4000000 | 2700075 | 2700075 | N/A | N/A | 2700075 | 0 | 2700072 | 100 | 2700072 | 580000 | 3 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
628 | Proposed Construction of 4 No. Market Shed, Pavillion, Animal Paddocks, 2 No Office Block and Chainlink Fencing at Banita Market, Soin Ward, Rongai Sub County | Proposed Construction of 4 No. Market Shed, Pavillion, Animal Paddocks, 2 No Office Block and Chainlink Fencing at Banita Market, Soin Ward, Rongai Sub County | To undertake the proposed Construction of 4 No. Market Shed, Pavillion, Animal Paddocks, 2 No Office Block and Chainlink Fencing at Banita Market, Soin Ward, Rongai Sub County | Proposed Construction of 4 No. Market Shed, Pavillion, Animal Paddocks, 2 No Office Block and Chainlink Fencing at Banita Market, Soin Ward, Rongai Sub County implemented | 4130299 | N/A | HQ | HQ | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2018/19 | 2020/21 | 2020/21 | 10283413.1 | 1435479 | 1435479 | Equitable | N/A | 1435479 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
629 | Proposed Construction of Market Sheds in Elementaita Ward | Proposed Construction of Market Sheds in Elementaita Ward | To undertake the proposed Construction of Market Sheds in Elementaita Ward | Proposed Construction of Market Sheds in Elementaita Ward implemented | 4130299 | N/A | HQ | HQ | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2018/19 | 2020/21 | 2020/21 | 5000000 | 634833.96 | 634833.96 | Equitable | N/A | 634833.96 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
630 | Proposed Construction of Markets Sheds, Fencing, Pit Latrine and Gate House at Olenguruone Market, Amalo Ward, Kuresoi South Sub County | Proposed Construction of Markets Sheds, Fencing, Pit Latrine and Gate House at Olenguruone Market, Amalo Ward, Kuresoi South Sub County | To undertake the proposed Construction of Markets Sheds, Fencing, Pit Latrine and Gate House at Olenguruone Market, Amalo Ward, Kuresoi South Sub County | Proposed Construction of Markets Sheds, Fencing, Pit Latrine and Gate House at Olenguruone Market, Amalo Ward, Kuresoi South Sub County implemented | 4130299 | N/A | HQ | HQ | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2018/19 | 2020/21 | 2020/21 | 12000000 | 6091798 | 6091798 | Equitable | N/A | 6091798 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
631 | Proposed Laying of Cabros at Olenguruone Market Stage, Amalo Ward, Kuresoi South Sub County | Proposed Laying of Cabros at Olenguruone Market Stage, Amalo Ward, Kuresoi South Sub County | To undertake the proposed Laying of Cabros at Olenguruone Market Stage, Amalo Ward, Kuresoi South Sub County | Proposed Laying of Cabros at Olenguruone Market Stage, Amalo Ward, Kuresoi South Sub County implemented | 4130299 | N/A | HQ | HQ | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2018/19 | 2020/21 | 2020/21 | 8000000 | 4885227.1 | 4885227.1 | Equitable | N/A | 4885227.1 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
632 | Refurbishment & Drainages works at Top Market - Nakuru East | Refurbishment & Drainages works at Top Market - Nakuru East | To implement refurbishment & drainages works at top market - nakuru east for economic growth and market access | Refurbishment & Drainages works at Top Market - Nakuru East completed | 4130299 | N/A | HQ | HQ | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2019/20 | 2019/20 | 2019/20 | 8000000 | 1050960 | 1050960 | Equitable | N/A | 1050960 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
633 | Rehabilitation of Elburgon market | Rehabilitation of Elburgon market | To rehabilitate Elburgon market to restore functionality | Elburgon market rehabilitated | 4130299 | N/A | HQ | HQ | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 5989050 | 598.9 | 5989050 | 18483845 | -4989050 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
634 | Rehabilitation of shaabab Market roof | Rehabilitation of shaabab Market roof | To rehabilitate shaabab Market roof to restore functionality | Shaabab Market roof rehabilitated | 4130299 | N/A | HQ | HQ | N/A | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 1959100 | 1959100 | Equitable | N/A | 1959100 | 0 | 5989050 | 305.7 | 5989050 | 18483845 | -4029950 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
635 | Drainage works in Heshima market | Drainage works in Heshima market | To implement drainage works in heshima market for economic growth and market access | Drainage works in Heshima market completed | 4130299 | N/A | Bahati | Kiamaina | -0.243576, 36.11146 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2019/20 | 2019/20 | 2019/20 | 1100000 | 1099200 | 1099200 | Equitable | N/A | 1099200 | 0 | 1099200 | 100 | 1099200 | 1099200 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires renovation.
636 | Construction of toilet at Kasarani market | Construction of toilet at Kasarani market | To construct toilet at Kasarani market | Toilet at Kasarani market constructed | 4130299 | N/A | Gilgil | Malewa West | -0.702703 36.291018 0 2000 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2018/19 | 2018/19 | N/A | 500000 | 699973 | 699973 | Equitable | N/A | 699973 | 0 | 0 | 0 | 0 | 699973 | 0 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Partly. Viable: Partly. Assessor remarks: Need good management.
637 | Levelling, fensing and construction of a toilet at ol rongai market | Levelling, fensing and construction of a toilet at ol rongai market | To implement levelling, fensing and construction of a toilet at ol rongai market for economic growth and market access | Levelling, fensing and construction of a toilet at ol rongai market completed | 4130299 | N/A | Rongai | Menengai West | -0.166756 36.010995 1806.5 400 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2019/20 | 2019/20 | N/A | 3000000 | 2999500 | 2999500 | Equitable | N/A | 2999500 | 0 | 2999499 | 100 | 2999499 | 3000000 | 1 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Microvision. Assessor remarks: Operational.
638 | Construction of Animal markets in Kiambogo Centre | Construction of Animal markets in Kiambogo Centre | To construct Animal markets in Kiambogo Centre | Animal markets in Kiambogo Centre constructed | 4130299 | N/A | Naivasha | Naivasha East | -0.871023, 36.510932 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2020/21 | 2020/21 | 2022 | 1500000 | 1242000 | 1242000 | Equitable | N/A | 1242000 | 0 | 1242000 | 100 | 1242000 | 1242000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Not operational.
639 | Rehabilitation of Ihindu Market sheds | Rehabilitation of Ihindu Market sheds | To rehabilitate Ihindu Market sheds to restore functionality | Ihindu Market sheds rehabilitated | 4130299 | N/A | Naivasha | Naivasha East | -0.840475, 36.549935 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2016/17 | 2016/17 | 2021-22 | 1053131.36 | 1052085 | 1052085 | Equitable | N/A | 1052085 | 0 | 1052070 | 100 | 1052070 | 1052085 | 15 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require regular maintenance.
640 | Building of market shade at Narasha | Building of market shade at Narasha | To implement building of market shade at narasha for economic growth and market access | Building of market shade at Narasha completed | 4130299 | N/A | Naivasha | Olkaria | -0.91594 36.267962 1948.27 1.2860000133514404 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 998770 | 998770 | Equitable | N/A | 998770 | 0 | 711889 | 71.3 | 711889 | 998770 | 286881 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: The people are not using. Assessor remarks: Not standard.
641 | Building of market stalls at Raplands | Building of market stalls at Raplands | To implement building of market stalls at raplands for economic growth and market access | Building of market stalls at Raplands completed | 4130299 | N/A | Naivasha | Olkaria | -0.938119, 36.364961 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2019/20 | 2019/20 | 2019/20 | 3300044 | 3287672 | 3287672 | Equitable | N/A | 3287672 | 0 | 3287672 | 100 | 3287672 | 3287672 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Completed awaiting electricity.
642 | Market Rehabilitation and Development | Construction of fish market stalls | To construct fish market stalls | Fish market stalls constructed | 4130299 | N/A | Naivasha | Olkaria | -0.817264, 36.326217 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2019/20 | 2019/20 | 2019/20 | 4834865 | 4821400 | 4821400 | Equitable | N/A | 4821400 | 0 | 4209000 | 87.3 | 4209000 | 612400 | 612400 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Viable but the model is not secure for the purpose. Contractor: Northern city. Assessor remarks: Completed but not operational.
643 | Fencing of subukia market | Fencing of subukia market | To secure subukia market through fencing | Subukia market fenced and secured | 4130299 | N/A | Subukia | Subukia | 0.00313 36.229321 1992.0999755859375 32.0989990234375 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2017/18 | 2017/18 | 2017/18 | 3100000 | 2058336 | 2058336 | Equitable | N/A | 2058336 | 0 | 2058372 | 100 | 2058372 | 2058336 | -36 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes, the safety and security issues at the facility resolved.. Viable: Yes, the premises and facilities at the market are secured by provision of fence.. Contractor: Details not availed. Assessor remarks: Proposed fencing works completed as per contract period.
644 | Construction of market shade in Turi market | Construction of market shade in Turi market | To construct market shade in Turi market | Market shade in Turi market constructed | 4130299 | N/A | Molo | Turi | -0.282631, 35.758417 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2020/21 | 2020/21 | 2020/21 | 900000 | 899000 | 899000 | Equitable | N/A | 899000 | 0 | 899000 | 100 | 899000 | 899000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not fully operational.
645 | Construction of a market shed at retail market | Construction of a market shed at retail market | To construct a market shed at retail market | A market shed at retail market constructed | 4130299 | N/A | Naivasha | Viwandani | -0.714599, 36.434192 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 1995020 | 1995020 | Equitable | N/A | 1995020 | 0 | 1995020 | 100 | 1995020 | 1995020 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Very viable. Assessor remarks: Operational.
646 | Construction of Market Sheds | Construction of Market Sheds | To construct Market Sheds | Market Sheds constructed | 4130299 | N/A | Naivasha | Viwandani | -0.71517 36.434405 1901.0999755859375 4.126999855041504 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Assessor remarks: Operational.
647 | Rehabilitation of toilets in Viwandani market | Rehabilitation of toilets in Viwandani market | To rehabilitate toilets in Viwandani market to restore functionality | Toilets in Viwandani market rehabilitated | 4130299 | N/A | Naivasha | Viwandani | -0.714472, 36.434091 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2018/19 | 2018/19 | 2018/19 | 7000000 | 366850 | 366850 | Equitable | N/A | 366850 | 0 | 366850 | 100 | 366850 | 366850 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Assessor remarks: Operational.
648 | Construction of Kanyotu market shade | Construction of Kanyotu market shade | To construct Kanyotu market shade | Kanyotu market shade constructed | 4130299 | N/A | Subukia | Waseges | 0.033662 36.226952 1960 8.899999618530273 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1497707 | 1497707 | Equitable | N/A | 1497707 | 0 | 1497707 | 100 | 1497707 | 1497707 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: Complete.
649 | Construction of market shade at Simboyon markets | Construction of market shade at Simboyon markets | To construct market shade at Simboyon markets | Market shade at Simboyon markets constructed | 4130299 | N/A | Subukia | Waseges | 0.080873 36.244899 0 20.445999145507812 | 4566 | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | TRADE, INDUSTRIALIZATION, COOPERATIVES AND TOURISM | N/A | 2020/21 | 2020/21 | 2020/21 | 1300000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 1300000 | 100 | 1300000 | 1300000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
650 | Infrastructure, Development and Maintenance | Roads Outstanding Contract Retention - development | To implement roads outstanding contract retention - development for road connectivity and accessibility | Roads Outstanding Contract Retention - development completed | 2211314 | Write Offs/ Bad Debt Expenses from Previous Years (Pending Bills) | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 25823134.3 | 25823134.09 | 25823134.09 | Equitable | N/A | 25823134.09 | 0 | 25823134 | 100 | 25823134 | 0 | 0.09 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
651 | Infrastructure, Development and Maintenance | Conditional Grant - Road Maintenance Levy Fund | To implement Road Maintenance Levy Fund as per conditional grant requirements | Road Maintenance Levy Fund implemented | 2630201 | N/A | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | N/A | 290544581 | 5546375.19 | 5546375.19 | RMLF | RMLF | 5546375.19 | 0 | 3423570 | 61.7 | 3423570 | 79595019 | 2122805.19 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
652 | Infrastructure, Development and Maintenance | Conditional Grant-Road Maintenance Levy Fund | To implement Road Maintenance Levy Fund as per conditional grant requirements | Road Maintenance Levy Fund implemented | 2630201 | N/A | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2020/21 | N/A | 287797571 | 607407472.55 | 0 | RMLF | RMLF | 0 | 607407472.55 | 15258043 | 2.5 | 15258043 | 79595019 | 592149429.55 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
653 | Infrastructure, Development and Maintenance | Road Maintenance Levy Fund | To implement road maintenance levy fund for road connectivity and accessibility | Road Maintenance Levy Fund completed | 2630201 | N/A | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | N/A | 290544581 | 118116986 | 171544581 | RMLF | RMLF | 171544581 | 0 | 15258043 | 12.9 | 15258043 | 79595019 | 102858943 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
654 | Infrastructure, Development and Maintenance | Cabro and drainage works at Kuresoi trading centre access roads in Kiptororo Ward Kuresoi North Sub-County. | To implement cabro and drainage works at kuresoi trading centre access roads in kiptororo ward kuresoi north sub-county. for road connectivity and accessibility | Cabro and drainage works at Kuresoi trading centre access roads in Kiptororo Ward Kuresoi North Sub-County. completed | 2630203 | N/A | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 49990784 | 0 | 0 | RMLF | RMLF | 0 | 49990784 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
655 | Infrastructure, Development and Maintenance | Conditional Grant - Road Maintenance Levy Fund | To implement Road Maintenance Levy Fund as per conditional grant requirements | Road Maintenance Levy Fund implemented | 2630203 | N/A | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 290544581 | 838140391.76 | 280544580.87 | RMLF | RMLF | 280544580.87 | 587416565.17 | 3423570 | 0.4 | 3423570 | 79595019 | 834716821.76 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
656 | Infrastructure, Development and Maintenance | Construction of 2 No. bridges to connect Arash and Tetu Villages in Subukia Ward, Subukia Sub-County. | To construct 2 No. bridges to connect Arash and Tetu Villages in Subukia Ward, Subukia Sub-County | 2 No. bridges to connect Arash and Tetu Villages in Subukia Ward, Subukia Sub-County constructed | 2630203 | N/A | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 10497470 | 0 | 0 | RMLF | RMLF | 0 | 10497470 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
657 | Infrastructure, Development and Maintenance | Construction of 24M span footbridge at Kavililia in Waseges Ward, Subukia Sub- County. | To construct 24M span footbridge at Kavililia in Waseges Ward, Subukia Sub- County | 24M span footbridge at Kavililia in Waseges Ward, Subukia Sub- County constructed | 2630203 | N/A | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 3171060 | 0 | 0 | RMLF | RMLF | 0 | 3171060 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
658 | Infrastructure, Development and Maintenance | Construction of acceleration and deceleration lanes at PGH Level 5 in London Ward, Nakuru East Sub-County. | To construct acceleration and deceleration lanes at PGH Level 5 in London Ward, Nakuru East Sub-County | Acceleration and deceleration lanes at PGH Level 5 in London Ward, Nakuru East Sub-County constructed | 2630203 | N/A | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 49992312.87 | 0 | 0 | RMLF | RMLF | 0 | 49992312.87 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
659 | Infrastructure, Development and Maintenance | Construction of Kamara Bridge in Kamara Ward, Kuresoi North Sub-County. | To construct Kamara Bridge in Kamara Ward, Kuresoi North Sub-County | Kamara Bridge in Kamara Ward, Kuresoi North Sub-County constructed | 2630203 | N/A | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 5900013.42 | 0 | 0 | RMLF | RMLF | 0 | 5900013.42 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
660 | Infrastructure, Development and Maintenance | Construction of Kapkembu Bridge in Tinet Ward, Kuresoi South Sub-County. | To construct Kapkembu Bridge in Tinet Ward, Kuresoi South Sub-County | Kapkembu Bridge in Tinet Ward, Kuresoi South Sub-County constructed | 2630203 | N/A | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 5999085 | 0 | 0 | RMLF | RMLF | 0 | 5999085 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
661 | Infrastructure, Development and Maintenance | Decommissioning of Kilo Old Bridge and construction of a New Bridge at River Makaria in Lare Ward, Njoro Sub-County. | To implement decommissioning of kilo old bridge and construction of a new bridge at river makaria in lare ward, njoro sub-county. for road connectivity and accessibility | Decommissioning of Kilo Old Bridge and construction of a New Bridge at River Makaria in Lare Ward, Njoro Sub-County. completed | 2630203 | N/A | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 6000000 | 0 | 0 | RMLF | RMLF | 0 | 6000000 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
662 | Infrastructure, Development and Maintenance | Drainage works across Kiamaina Ward in Kiamaina Ward, Bahati Sub-County. | To implement drainage works across kiamaina ward in kiamaina ward, bahati sub-county. for road connectivity and accessibility | Drainage works across Kiamaina Ward in Kiamaina Ward, Bahati Sub-County. completed | 2630203 | N/A | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 36992342 | 0 | 0 | RMLF | RMLF | 0 | 36992342 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
663 | Infrastructure, Development and Maintenance | Proposed Construction of Bridges at Rare Maai Mahiu Road Ereri Road Concreting of Kamore Longonot Road in Maai Mahiu Ward and Moi Ndabi Bridge in Maiella Ward Naivasha Sub-County | To undertake the proposed Construction of Bridges at Rare Maai Mahiu Road Ereri Road Concreting of Kamore Longonot Road in Maai Mahiu Ward and Moi Ndabi Bridge in Maiella Ward Naivasha Sub-County | Proposed Construction of Bridges at Rare Maai Mahiu Road Ereri Road Concreting of Kamore Longonot Road in Maai Mahiu Ward and Moi Ndabi Bridge in Maiella Ward Naivasha Sub-County implemented | 2630203 | N/A | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | N/A | 16643870 | 0 | 0 | RMLF | RMLF | 0 | 1398658.75 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
664 | Infrastructure, Development and Maintenance | Proposed grading and spot improvement of greensteds-old nakuru-nairobi road in eburu-mbaruk ward, gilgil sub - county | To undertake the proposed grading and spot improvement of greensteds-old nakuru-nairobi road in eburu-mbaruk ward, gilgil sub - county | Proposed grading and spot improvement of greensteds-old nakuru-nairobi road in eburu-mbaruk ward, gilgil sub - county implemented | 2630203 | N/A | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | N/A | 6400900 | 0 | 0 | RMLF | RMLF | 0 | 302387.35 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
665 | Infrastructure, Development and Maintenance | Proposed improvement (part) to bitumen standard of the existing Heshima Road in Kiamaina Ward Bahati Sub-County | To undertake the proposed improvement (part) to bitumen standard of the existing Heshima Road in Kiamaina Ward Bahati Sub-County | Proposed improvement (part) to bitumen standard of the existing Heshima Road in Kiamaina Ward Bahati Sub-County implemented | 2630203 | N/A | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 17544030 | 0 | 0 | RMLF | RMLF | 0 | 13133317.2 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
666 | Infrastructure, Development and Maintenance | Proposed Maintenance and Drain Improvement at Kiti near PCEA Shalom Kiti Church in Kiamaina Ward and Rountine Maintenance Spot Improvement and Culvert Installation of Kwa Gitu-CDF Tank Access Road at Bahati Ward Bahati Sub-County | To undertake the proposed Maintenance and Drain Improvement at Kiti near PCEA Shalom Kiti Church in Kiamaina Ward and Rountine Maintenance Spot Improvement and Culvert Installation of Kwa Gitu-CDF Tank Access Road at Bahati Ward Bahati Sub-County | Proposed Maintenance and Drain Improvement at Kiti near PCEA Shalom Kiti Church in Kiamaina Ward and Rountine Maintenance Spot Improvement and Culvert Installation of Kwa Gitu-CDF Tank Access Road at Bahati Ward Bahati Sub-County implemented | 2630203 | N/A | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | N/A | 11483157 | 0 | 0 | RMLF | RMLF | 0 | 3915688.6 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
667 | Infrastructure, Development and Maintenance | Proposed part improvement of the Nessuit Junction -Ndoswa in Mariashoni Ward Molo Sub-county | To undertake the proposed part improvement of the Nessuit Junction -Ndoswa in Mariashoni Ward Molo Sub-county | Proposed part improvement of the Nessuit Junction -Ndoswa in Mariashoni Ward Molo Sub-county implemented | 2630203 | N/A | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 2611270 | 0 | 0 | RMLF | RMLF | 0 | 2611270 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
668 | Infrastructure, Development and Maintenance | Proposed part tarmacking of Kaloleni Road in Molo Ward Molo Sub-County | To undertake the proposed part tarmacking of Kaloleni Road in Molo Ward Molo Sub-County | Proposed part tarmacking of Kaloleni Road in Molo Ward Molo Sub-County implemented | 2630203 | N/A | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 25047277 | 0 | 0 | RMLF | RMLF | 0 | 9940365.83 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
669 | Infrastructure, Development and Maintenance | Proposed pothole patching of part of the Free Area Tosti Spin Knit Road in Nakuru East Ward Nakuru East Sub-County | To undertake the proposed pothole patching of part of the Free Area Tosti Spin Knit Road in Nakuru East Ward Nakuru East Sub-County | Proposed pothole patching of part of the Free Area Tosti Spin Knit Road in Nakuru East Ward Nakuru East Sub-County implemented | 2630203 | N/A | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 4549825 | 0 | 0 | RMLF | RMLF | 0 | 4549825 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
670 | Infrastructure, Development and Maintenance | Proposed Rehabilitation of Molo Bus Park and Rehabilitation of Molo Town Access Road in Molo Ward and Routine Maintenance and Spot Improvement of Comfort Feeds Saptet Centre St Joseph Primary School Road in Elburgon Ward Molo Sub County | To undertake the proposed Rehabilitation of Molo Bus Park and Rehabilitation of Molo Town Access Road in Molo Ward and Routine Maintenance and Spot Improvement of Comfort Feeds Saptet Centre St Joseph Primary School Road in Elburgon Ward Molo Sub County | Proposed Rehabilitation of Molo Bus Park and Rehabilitation of Molo Town Access Road in Molo Ward and Routine Maintenance and Spot Improvement of Comfort Feeds Saptet Centre St Joseph Primary School Road in Elburgon Ward Molo Sub County implemented | 2630203 | N/A | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | N/A | 22872750 | 0 | 0 | RMLF | RMLF | 0 | 2647706.55 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
671 | Infrastructure, Development and Maintenance | Proposed Rehabilitation of Shabab Stage and Main Stage in Biashara Ward Nakuru East Sub County | To undertake the proposed Rehabilitation of Shabab Stage and Main Stage in Biashara Ward Nakuru East Sub County | Proposed Rehabilitation of Shabab Stage and Main Stage in Biashara Ward Nakuru East Sub County implemented | 2630203 | N/A | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | N/A | 9675500 | 0 | 0 | RMLF | RMLF | 0 | 7548916.55 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
672 | Infrastructure, Development and Maintenance | Proposed Reinstatement and Spot Improvement of Gioto-Molo line Estate Road | To undertake the proposed Reinstatement and Spot Improvement of Gioto-Molo line Estate Road | Proposed Reinstatement and Spot Improvement of Gioto-Molo line Estate Road implemented | 2630203 | N/A | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 7237240 | 0 | 0 | RMLF | RMLF | 0 | 4018615.85 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
673 | Infrastructure, Development and Maintenance | Proposed Routine Maintenance and Spot Improvement of Gacharage- Temoyetta Secondary - Temoyetta DEB and Construction of Bosire Road Box Culvert in Nyota Ward Kuresoi North Sub | To undertake the proposed Routine Maintenance and Spot Improvement of Gacharage- Temoyetta Secondary - Temoyetta DEB and Construction of Bosire Road Box Culvert in Nyota Ward Kuresoi North Sub | Proposed Routine Maintenance and Spot Improvement of Gacharage- Temoyetta Secondary - Temoyetta DEB and Construction of Bosire Road Box Culvert in Nyota Ward Kuresoi North Sub implemented | 2630203 | N/A | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | N/A | 9990975 | 0 | 0 | RMLF | RMLF | 0 | 2255431.6 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
674 | Infrastructure, Development and Maintenance | Proposed Routine Maintenance & Spot Improvement of Kabazi Centre - Hospital Road in Kabazi Ward Subukia Sub County | To undertake the proposed Routine Maintenance & Spot Improvement of Kabazi Centre - Hospital Road in Kabazi Ward Subukia Sub County | Proposed Routine Maintenance & Spot Improvement of Kabazi Centre - Hospital Road in Kabazi Ward Subukia Sub County implemented | 2630203 | N/A | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 18032850 | 0 | 0 | RMLF | RMLF | 0 | 4963378.88 | 5237600 | 0 | 5237600 | 5237600 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
675 | Infrastructure, Development and Maintenance | Proposed Routine Maintenance & Spot Improvement of Keringet Market Road in Keringet Ward Kuresoi South Sub County | To undertake the proposed Routine Maintenance & Spot Improvement of Keringet Market Road in Keringet Ward Kuresoi South Sub County | Proposed Routine Maintenance & Spot Improvement of Keringet Market Road in Keringet Ward Kuresoi South Sub County implemented | 2630203 | N/A | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 20610342 | 0 | 0 | RMLF | RMLF | 0 | 14401899 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
676 | Infrastructure, Development and Maintenance | Proposed Spot Improvement of Kamemo Kirima Kahiga Tetu Kirengero Munanda Sidai Road AIC Maombi Primary Kwa Cucu and Kamumo Bridge (Gwa Karani Bridge) in Subukia Ward, Kabazi Ward and Waseges Ward Subukia Sub County | To undertake the proposed Spot Improvement of Kamemo Kirima Kahiga Tetu Kirengero Munanda Sidai Road AIC Maombi Primary Kwa Cucu and Kamumo Bridge (Gwa Karani Bridge) in Subukia Ward, Kabazi Ward and Waseges Ward Subukia Sub County | Proposed Spot Improvement of Kamemo Kirima Kahiga Tetu Kirengero Munanda Sidai Road AIC Maombi Primary Kwa Cucu and Kamumo Bridge (Gwa Karani Bridge) in Subukia Ward, Kabazi Ward and Waseges Ward Subukia Sub County implemented | 2630203 | N/A | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | N/A | 10501316 | 0 | 0 | RMLF | RMLF | 0 | 590395.9 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
677 | Infrastructure, Development and Maintenance | Proposed Tarmack of Molo Shop Frontage | To undertake the proposed Tarmack of Molo Shop Frontage | Proposed Tarmack of Molo Shop Frontage implemented | 2630203 | N/A | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 8550740 | 0 | 0 | RMLF | RMLF | 0 | 5753895.53 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
678 | Infrastructure, Development and Maintenance | Proposed tarmacking of Salgaa Shopping Centre Access Road in Mosop Ward Rongai Sub-County | To undertake the proposed tarmacking of Salgaa Shopping Centre Access Road in Mosop Ward Rongai Sub-County | Proposed tarmacking of Salgaa Shopping Centre Access Road in Mosop Ward Rongai Sub-County implemented | 2630203 | N/A | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 41177010 | 0 | 0 | RMLF | RMLF | 0 | 770433.11 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
679 | Infrastructure, Development and Maintenance | Rehabilitation of Wakulima Market access road in Biashara Ward, Nakuru East Sub-County. | To rehabilitate Wakulima Market access road in Biashara Ward, Nakuru East Sub-County to restore functionality | Wakulima Market access road in Biashara Ward, Nakuru East Sub-County rehabilitated | 2630203 | N/A | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 15260729.58 | 0 | 0 | RMLF | RMLF | 0 | 15260729.58 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
680 | Infrastructure, Development and Maintenance | Routine maintenance and construction of drifts along Karofa Olenguruone road in Amalo Ward, Kuresoi South Sub-County. | To maintain construction of drifts along Karofa Olenguruone road in Amalo Ward, Kuresoi South Sub-County in serviceable condition | Construction of drifts along Karofa Olenguruone road in Amalo Ward, Kuresoi South Sub-County maintained | 2630203 | N/A | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 8000000 | 0 | 0 | RMLF | RMLF | 0 | 8000000 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
681 | Infrastructure, Development and Maintenance | Streetlighting along A8 from NYH-Njoro turn off | To implement streetlighting along a8 from nyh-njoro turn off for road connectivity and accessibility | Streetlighting along A8 from NYH-Njoro turn off completed | 2630203 | N/A | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 36000000 | 0 | 0 | RMLF | RMLF | 0 | 36000000 | 0 | 0 | 0 | 32222700 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
682 | KTDA allocation for road works in Kiptagich, Amalo and Tinet Wards | KTDA allocation for road works in Kiptagich, Amalo and Tinet Wards | To implement ktda allocation for road works in kiptagich, amalo and tinet wards for road connectivity and accessibility | KTDA allocation for road works in Kiptagich, Amalo and Tinet Wards completed | 2640599 | Other Capital Grants and Trans | HQ | HQ | -0.173672, 35.862823 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 58000000 | 0 | 0 | N/A | N/A | 0 | 58000000 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
683 | KTDA allocation for road works in Kiptagich, Amalo,and Tinet wards | KTDA allocation for road works in Kiptagich, Amalo,and Tinet wards | To implement ktda allocation for road works in kiptagich, amalo,and tinet wards for road connectivity and accessibility | KTDA allocation for road works in Kiptagich, Amalo,and Tinet wards completed | 2640599 | Other Capital Grants and Trans | HQ | HQ | -0.173672, 35.862823 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2024/25 | 66876079 | 0 | 0 | N/A | N/A | 0 | 66876079 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
684 | Infrastructure, Development & Maintenance | Construction & Rehabilitation of buildings (Fire station) | To construct & Rehabilitation of buildings (Fire station) | & Rehabilitation of buildings (Fire station) constructed | 3110299 | Construction of Buildings - Ot | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 50000000 | 7500000 | 7500000 | Equitable | N/A | 7500000 | 0 | 20181765 | 269.1 | 20181765 | 7500000 | -12681765 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
685 | Infrastructure, Development & Maintenance | Construction & Rehabilitation of buildings (Water Reserviour) | To construct & Rehabilitation of buildings (Water Reserviour) | & Rehabilitation of buildings (Water Reserviour) constructed | 3110299 | Construction of Buildings - Ot | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 10000000 | 4537500 | 4537500 | Equitable | N/A | 4537500 | 0 | 20000000 | 440.8 | 20000000 | 4537500 | -15462500 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
686 | Internal Maintenance of Public Works Building HQ | Internal Maintenance of Public Works Building HQ | To implement internal maintenance of public works building hq for road connectivity and accessibility | Internal Maintenance of Public Works Building HQ completed | 3110302 | Refurbishment of Non-Residential Buildings | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 8000000 | 535690 | 535690 | Equitable | N/A | 535690 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
687 | Infrastructure, Development and Maintenance | Rehabilitation Of Public Works Building | To rehabilitate Public Works Building to restore functionality | Public Works Building rehabilitated | 3110302 | Refurbishment of Non-Residential Buildings | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 8598985 | 8598985 | 8598985 | Equitable | N/A | 8598985 | 0 | 4414833 | 51.3 | 4414833 | 10000000 | 4184152 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
688 | Maintenance of Public Works Building | Maintenance of Public Works Building | To implement maintenance of public works building for road connectivity and accessibility | Maintenance of Public Works Building completed | 3110399 | Refurbishment of Buildgs - Oth | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2024/25 | 1550000 | 1550000 | 1550000 | Equitable | N/A | 1550000 | 0 | 0 | 0 | 0 | 5000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
689 | Infrastructure, Development and Maintenance | Rehabilitation and equipping of County Garage | To rehabilitate equipping of County Garage to restore functionality | Equipping of County Garage rehabilitated | 3110399 | Refurbishment of Buildgs - Oth | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 22500000 | 22500000 | 45000000 | Equitable | N/A | 45000000 | 0 | 4000000 | 17.8 | 4000000 | 5271862 | 18500000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
690 | Infrastructure, Development and Maintenance | Opening of new access roads at Unity and Kihoto access corridor through Imarisha Barabara | To improve the condition of new access roads at Unity and Kihoto access corridor through Imarisha Barabara | New access roads at Unity and Kihoto access corridor through Imarisha Barabara improved | 3110402 | Access Roads | Naivasha | Lake View | -0.761101, 36.459004 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2024/25 | 2186284 | 2186284 | 2086284 | Equitable | N/A | 2086284 | 0 | 2000000 | 91.5 | 2000000 | 0 | 186284 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Access corridor was not done.
691 | Infrastructure, Development and Maintenance | Improvement of access roads in Maai Mahiu | To implement improvement of access roads in maai mahiu for road connectivity and accessibility | Improvement of access roads in Maai Mahiu completed | 3110402 | Access Roads | Naivasha | Maai Mahiu | -1.003901, 36.536522 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 980876 | 19.6 | 980876 | 3494096 | 4019124 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs maintenance.
692 | Infrastructure, Development and Maintenance | Opening of Roads in Maciaro area | To improve the condition of Roads in Maciaro area | Roads in Maciaro area improved | 3110402 | Access Roads | Rongai | Menengai West | -0.22606, 36.019001 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: In poor condition needs grading.
693 | Infrastructure, Development and Maintenance | Grading and gravelling of access roads in Waseges Ward | To improve road infrastructure by grading and murraming access roads in Waseges Ward | Access roads in Waseges Ward graded and murramed | 3110402 | Access Roads | Subukia | Waseges | 0.15953 36.255852 1775.1 16.299999237060547 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 525000 | 13.1 | 525000 | 375000 | 3475000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
694 | Infrastructure, Development and Maintenance | Grading And Murraming of Access Roads- Imarisha Barabara in Amalo Ward | To improve road infrastructure by grading and murraming Access Roads- Imarisha Barabara in Amalo Ward | Access Roads- Imarisha Barabara in Amalo Ward graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Amalo | -0.572432, 35.70536 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2024 | 1898246 | 1898246 | 1898246 | Equitable | N/A | 1898246 | 0 | 1898246 | 100 | 1898246 | 171930 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: partially. Viable: partially. Assessor remarks: project completed but road requires murraming.
695 | Infrastructure, Development and Maintenance | Grading And Murraming of Alberto-Kap Edward Road | To improve road infrastructure by grading and murraming Alberto-Kap Edward Road | Alberto-Kap Edward Road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Amalo | -0.560487, 35.690065 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2024 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1419350 | 94.6 | 1419350 | 80650 | 80650 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: project completed.
696 | Infrastructure, Development and Maintenance | Grading and Murraming of Kapkorio ECDE - Cattle dip Road, Kiptaragon-Kwendo, Kimugul Kware, Nyambugo-Kongasis TCB, AIC-Pangani, Kabigenet-Kabimit Roads | To improve road infrastructure by grading and murraming Kapkorio ECDE - Cattle dip Road, Kiptaragon-Kwendo, Kimugul Kware, Nyambugo-Kongasis TCB, AIC-Pangani, Kabigenet-Kabimit Roads | Kapkorio ECDE - Cattle dip Road, Kiptaragon-Kwendo, Kimugul Kware, Nyambugo-Kongasis TCB, AIC-Pangani, Kabigenet-Kabimit Roads graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Amalo | -0.646077, 35.671962 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2024 | 6550000 | 6550000 | 6550000 | Equitable | N/A | 6550000 | 0 | 6499119 | 99.2 | 6499119 | 50881 | 50881 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: partially. Viable: partially. Assessor remarks: require murraming works.
697 | Infrastructure, Development and Maintenance | Grading And Murraming of Kiptaragon Primary-AGC Sinendet | To improve road infrastructure by grading and murraming Kiptaragon Primary-AGC Sinendet | Kiptaragon Primary-AGC Sinendet graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Amalo | -0.562766, 35.683805 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2024 | 1600000 | 1600000 | 1600000 | Equitable | N/A | 1600000 | 0 | 1600000 | 100 | 1600000 | 1070680 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: partially. Viable: partially. Assessor remarks: road requires murraming and maintenance works.
698 | Infrastructure, Development and Maintenance | Grading and Murraming of Kiptenden-Daraja Mbili Road | To improve road infrastructure by grading and murraming Kiptenden-Daraja Mbili Road | Kiptenden-Daraja Mbili Road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Amalo | -0.58684, 35.676332 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2023 | 3000000 | 2777059 | 2777059 | Equitable | N/A | 2777059 | 0 | 2645858 | 95.3 | 2645858 | 2777059 | 131201 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
699 | Infrastructure, Development and Maintenance | Grading And Murraming of Olenguruone-Chesoen Road | To improve road infrastructure by grading and murraming Olenguruone-Chesoen Road | Olenguruone-Chesoen Road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Amalo | -0.603686 35.675974 2501.574462890625 24.68600082397461 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 2000000 | 3200000 | 3200000 | Equitable | N/A | 3200000 | 0 | 3028070 | 94.6 | 3028070 | 171930 | 171930 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: in good condition ,only the bridge is in bad state can't connect the two place.
700 | Infrastructure, Development and Maintenance | Grading And Murraming of Prof Kemei Sinendet Road | To improve road infrastructure by grading and murraming Prof Kemei Sinendet Road | Prof Kemei Sinendet Road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Amalo | -0.558753, 35.697297 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2024 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 171930 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: project completed.
701 | Infrastructure, Development and Maintenance | Grading and Murraming of roads in Amalo Ward | To improve road infrastructure by grading and murraming roads in Amalo Ward | Roads in Amalo Ward graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Amalo | -0.572382 35.70538 2574.4 8.600000381469727 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 9071556 | 9071556 | 9071556 | Equitable | N/A | 9071556 | 0 | 1898246 | 20.9 | 1898246 | 171930 | 7173310 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: yes. Viable: partially. Assessor remarks: project completed but road requires murraming.
702 | Infrastructure, Development and Maintenance | Grading and Murraming of Sachangwan -Ngeny road | To improve road infrastructure by grading and murraming Sachangwan -Ngeny road | Sachangwan -Ngeny road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Amalo | -0.59666, 35.687903 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2023 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: Yes. Condition: Bad. Objective met: partially. Viable: partially. Assessor remarks: road requires grading and murraming.
703 | Infrastructure, Development and Maintenance | Construction of drainages across wanyororo center road and Grading and murraming of jowakim-usembo primary school road | To construct drainages across wanyororo center road and Grading and murraming of jowakim-usembo primary school road | Drainages across wanyororo center road and Grading and murraming of jowakim-usembo primary school road constructed | 3110499 | Construction of Roads - Other | Bahati | Bahati | -0.151991 36.102211 1851.5703125 4.656000137329102 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 1811040 | 1811040 | Equitable | N/A | 1811040 | 0 | 1723705 | 95.2 | 1723705 | 1811040 | 87335 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The projects is good.
704 | Infrastructure, Development and Maintenance | Grading and murraming of Karunga Ahero road | To improve road infrastructure by grading and murraming Karunga Ahero road | Karunga Ahero road graded and murramed | 3110499 | Construction of Roads - Other | Bahati | Bahati | -0.125377 36.159563 2037.5999755859375 5.599999904632568 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 1801694.41 | 1801694.41 | Equitable | N/A | 1801694.41 | 0 | 1800906 | 100 | 1800906 | 788 | 788.41 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs to redone.
705 | Grading and murraming of Mwisho wa Lami-Wamiruri road | Grading and murraming of Mwisho wa Lami-Wamiruri road | To improve road infrastructure by grading and murraming Mwisho wa Lami-Wamiruri road | Mwisho wa Lami-Wamiruri road graded and murramed | 3110499 | Construction of Roads - Other | Bahati | Bahati | -0.158331, 36.11871 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1900000 | 1713600.91 | 1713600.91 | Equitable | N/A | 1713600.91 | 0 | 1677575 | 97.9 | 1677575 | 1713601 | 36025.91 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need grading.
706 | Infrastructure, Development and Maintenance | Grading and murraming of roads in Bahati Ward through Imarisha Barabara Program | To improve road infrastructure by grading and murraming roads in Bahati Ward through Imarisha Barabara Program | Roads in Bahati Ward through Imarisha Barabara Program graded and murramed | 3110499 | Construction of Roads - Other | Bahati | Bahati | -0.187189, 36.123237 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 1000000 | 1000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: In use but in poor condition due to on going rains.
707 | Infrastructure, Development and Maintenance | Hire of Machineries for rehabilitation of roads | To implement hire of machineries for rehabilitation of roads for road connectivity and accessibility | Hire of Machineries for rehabilitation of roads completed | 3110499 | Construction of Roads - Other | Bahati | Bahati | -0.188762, 36.122215 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 2300000 | 2199150 | 2199150 | Equitable | N/A | 2199150 | 0 | 2198528 | 100 | 2198528 | 623 | 622 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: In use.
708 | Infrastructure, Development and Maintenance | Hire of machinery for roads rehabilitation | To implement hire of machinery for roads rehabilitation for road connectivity and accessibility | Hire of machinery for roads rehabilitation completed | 3110499 | Construction of Roads - Other | Bahati | Bahati | -0.180245, 36.124494 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 2800000 | 2800000 | 2800000 | Equitable | N/A | 2800000 | 0 | 2339265 | 83.5 | 2339265 | 623 | 460735 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good.
709 | Infrastructure, Development and Maintenance | Hiring of equipment for roads rehabilitation in Bahati ward | To implement hiring of equipment for roads rehabilitation in bahati ward for road connectivity and accessibility | Hiring of equipment for roads rehabilitation in Bahati ward completed | 3110499 | Construction of Roads - Other | Bahati | Bahati | -0.193907, 36.127711 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 1999905 | 40 | 1999905 | 623 | 3000095 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Drainage to be improved.
710 | Infrastructure, Development and Maintenance | Hiring of equipments for Roads Rehabilitation in Bahati Ward | To implement hiring of equipments for roads rehabilitation in bahati ward for road connectivity and accessibility | Hiring of equipments for Roads Rehabilitation in Bahati Ward completed | 3110499 | Construction of Roads - Other | Bahati | Bahati | -0.193907, 36.127711 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999905 | 100 | 1999905 | 623 | 95 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Drainage to be improved.
711 | Infrastructure, Development and Maintenance | Rehabilitation Of Roads in Bahati Ward | To rehabilitate Roads in Bahati Ward to restore functionality | Roads in Bahati Ward rehabilitated | 3110499 | Construction of Roads - Other | Bahati | Bahati | -0.19699, 36.129745 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 6049630 | 0 | 586334.95 | Equitable | N/A | 586334.95 | 0 | 4463295 | 100 | 4463295 | 586335 | -4463295 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Being used.
712 | Infrastructure, Development and Maintenance | Grading And Murraming of Access Roads- Imarisha Barabara in Barut Ward | To improve road infrastructure by grading and murraming Access Roads- Imarisha Barabara in Barut Ward | Access Roads- Imarisha Barabara in Barut Ward graded and murramed | 3110499 | Construction of Roads - Other | Nakuru West | Barut | -0.3242, 36.042 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2025 | 1000000 | 0 | 200000 | Equitable | N/A | 200000 | 0 | 300000 | 100 | 300000 | 200000 | -300000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: VIVO/POPOTE. Assessor remarks: Done.
713 | Infrastructure, Development and Maintenance | Grading, fueling & murraming – Imarisha barabara programme | To implement grading, fueling & murraming – imarisha barabara programme for road connectivity and accessibility | Grading, fueling & murraming – Imarisha barabara programme completed | 3110499 | Construction of Roads - Other | Nakuru West | Barut | -0.3424, 36.42 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2023 | 2029188 | 529188 | 2029188 | Equitable | N/A | 2029188 | 0 | 300000 | 56.7 | 300000 | 200000 | 229188 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: No. Viable: No. Assessor remarks: It's yet to start.
714 | Infrastructure, Development & Maintenance | Grading and culverts for Kangema access road | To improve road accessibility by grading and culverts for Kangema access road | And culverts for Kangema access road graded | 3110499 | Construction of Roads - Other | Naivasha | Biashara-Naivasha | -0.70772, 36.506897 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2022 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1783503 | 89.2 | 1783503 | 2273598 | 216497 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Jolynn company. Assessor remarks: Needs to be graded murraming and compaction.
715 | Infrastructure, Development and Maintenance | Grading and gravelling of access roads in Nyonjoro | To improve road infrastructure by grading and murraming access roads in Nyonjoro | Access roads in Nyonjoro graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Biashara-Naivasha | -0.671162, 36.493103 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 1778530 | 59.3 | 1778530 | 2077943 | 1221470 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yet to start. Assessor remarks: The project site handover done to the contractor but yet to start..
716 | Infrastructure, Development and Maintenance | Grading and gravelling of Rutere, Gituru and Ndoroto roads | To improve road infrastructure by grading and murraming Rutere, Gituru and Ndoroto roads | Rutere, Gituru and Ndoroto roads graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Biashara-Naivasha | -0.69316, 36.529568 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2025 | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 4625852 | 77.1 | 4625852 | 13100000 | 1374148 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Yes. Assessor remarks: Mostly roads were not gravelled..hence needs to be done.
717 | Infrastructure, Development & Maintenance | Grading and murraming of Highland access roads | To improve road infrastructure by grading and murraming Highland access roads | Highland access roads graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Biashara-Naivasha | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2077943 | 2077943 | 2077943 | Equitable | N/A | 2077943 | 0 | 1778530 | 85.6 | 1778530 | 2077943 | 299413 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
718 | Infrastructure, Development and Maintenance | Grading and murraming of roads in Upper Biashara | To improve road infrastructure by grading and murraming roads in Upper Biashara | Roads in Upper Biashara graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Biashara-Naivasha | -0.647397, 36.499202 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2025 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 2219740 | 44.4 | 2219740 | 13100000 | 2780260 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Extension of the projects to other areas,drainagea.
719 | Infrastructure, Development and Maintenance | Grading And Murraming of Roads Through Imarisha Barabara Programme | To improve road infrastructure by grading and murraming Roads Through Imarisha Barabara Programme | Roads Through Imarisha Barabara Programme graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Biashara-Naivasha | -0.665173, 36.479593 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2025 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 13100000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Proper drainage needs to be redone,through stone pitching.
720 | Infrastructure, Development & Maintenance | Grading and murraming of Rutere and Kirima access roads | To improve road infrastructure by grading and murraming Rutere and Kirima access roads | Rutere and Kirima access roads graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Biashara-Naivasha | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 4625852 | 92.5 | 4625852 | 2077943 | 374148 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
721 | Infrastructure, Development & Maintenance | Grading and murraming of White Weru road | To improve road infrastructure by grading and murraming White Weru road | White Weru road graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Biashara-Naivasha | -0.685052, 36.531753 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2022 | 2550000 | 2550000 | 2550000 | Equitable | N/A | 2550000 | 0 | 2219740 | 87 | 2219740 | 2550000 | 330260 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Needs to be redone with gravelling,and drainages.
722 | Infrastructure, Development & Maintenance | Grading and murraming of Wirugamie access road | To improve road infrastructure by grading and murraming Wirugamie access road | Wirugamie access road graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Biashara-Naivasha | -0.644803, 36.510712 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2022 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2895748 | 96.5 | 2895748 | 2077943 | 104252 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs to be redone.
723 | Infrastructure, Development & Maintenance | Grading, Gravelling and compaction of Kinamba town Roads | To implement grading, gravelling and compaction of kinamba town roads for road connectivity and accessibility | Grading, Gravelling and compaction of Kinamba town Roads completed | 3110499 | Construction of Roads - Other | Naivasha | Biashara-Naivasha | -0.7239, 36.512203 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2022 | 3091003 | 2996475 | 2996475 | Equitable | N/A | 2996475 | 0 | 2996475 | 100 | 2996475 | 2996475 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs grading.
724 | Infrastructure, Development & Maintenance | Grading, Gravelling and compaction of Mutethia access road | To implement grading, gravelling and compaction of mutethia access road for road connectivity and accessibility | Grading, Gravelling and compaction of Mutethia access road completed | 3110499 | Construction of Roads - Other | Naivasha | Biashara-Naivasha | -0.7239, 36.512203 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2022 | 2500000 | 2359350 | 2359350 | Equitable | N/A | 2359350 | 0 | 2359350 | 100 | 2359350 | 2359350 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs grading.
725 | Infrastructure, Development and Maintenance | Grading, gravelling and drainage of Italian-Kwa White Road | To implement grading, gravelling and drainage of italian-kwa white road for road connectivity and accessibility | Grading, gravelling and drainage of Italian-Kwa White Road completed | 3110499 | Construction of Roads - Other | Naivasha | Biashara-Naivasha | -0.699413, 36.520042 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2025 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 2996475 | 85.6 | 2996475 | 2996475 | 503525 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Road in poor state needs through attention..
726 | Grading, murraming and installation of culverts in White highland road | Grading, murraming and installation of culverts in White highland road | To implement grading, murraming and installation of culverts in white highland road for road connectivity and accessibility | Grading, murraming and installation of culverts in White highland road completed | 3110499 | Construction of Roads - Other | Naivasha | Biashara-Naivasha | -0.706577, 36.515368 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2021 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3766343 | 94.2 | 3766343 | 4000000 | 233657 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Poorly done,needs complete overhaul and repair .and a serious drainage issues during rainy season.
727 | Infrastructure, Development and Maintenance | Hire of equipment for grading and murraming of roads in Lower Biashara | To implement hire of equipment for grading and murraming of roads in lower biashara for road connectivity and accessibility | Hire of equipment for grading and murraming of roads in Lower Biashara completed | 3110499 | Construction of Roads - Other | Naivasha | Biashara-Naivasha | -0.714892, 36.507788 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2025 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 5000000 | 100 | 5000000 | 5000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Dakuki. Assessor remarks: Extension of the project to other areas..
728 | Infrastructure, Development and Maintenance | Hire of Machinery for roads rehabilitation Gituru B and St Paul | To implement hire of machinery for roads rehabilitation gituru b and st paul for road connectivity and accessibility | Hire of Machinery for roads rehabilitation Gituru B and St Paul completed | 3110499 | Construction of Roads - Other | Naivasha | Biashara-Naivasha | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 2298490 | 0 | 2228490 | Equitable | N/A | 2228490 | 0 | 0 | 0 | 0 | 2298490 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
729 | Infrastructure, Development and Maintenance | Hiring of equipment for Kinamba and Goodfaith access roads | To implement hiring of equipment for kinamba and goodfaith access roads for road connectivity and accessibility | Hiring of equipment for Kinamba and Goodfaith access roads completed | 3110499 | Construction of Roads - Other | Naivasha | Biashara-Naivasha | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 5000000 | 100 | 5000000 | 5000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
730 | Infrastructure, Development & Maintenance | Road rehabilitation (hire of machinery for Gituamba and Kahuruko roads | To implement road rehabilitation (hire of machinery for gituamba and kahuruko roads for road connectivity and accessibility | Road rehabilitation (hire of machinery for Gituamba and Kahuruko roads completed | 3110499 | Construction of Roads - Other | Naivasha | Biashara-Naivasha | -0.73099, 36.47753 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2022 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 5000000 | 100 | 5000000 | 5000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.. Assessor remarks: Needs proper drainage ,drainages and gravelling..
731 | Infrastructure, Development & Maintenance | Dundori Roads rehabilitation (hire of machinery and equipments) | To implement dundori roads rehabilitation (hire of machinery and equipments) for road connectivity and accessibility | Dundori Roads rehabilitation (hire of machinery and equipments) completed | 3110499 | Construction of Roads - Other | Bahati | Dundori | -0.27406, 36.190413 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/2021 | 1500000 | 1825079 | 1825079 | Equitable | N/A | 1825079 | 0 | 1825079 | 100 | 1825079 | 1825079 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ms strafield contractors ltd. Assessor remarks: Require maintenance and drainage.
732 | Infrastructure, Development and Maintenance | Grading and gravelling of Dundori access roads | To improve road infrastructure by grading and murraming Dundori access roads | Dundori access roads graded and murramed | 3110499 | Construction of Roads - Other | Bahati | Dundori | -0.26376, 36.191805 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/2018 | 3200000 | 1789870 | 1789870 | Equitable | N/A | 1789870 | 0 | 1785904 | 99.8 | 1785904 | 1789870 | 3966 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ms Gatemax enterprises limited. Assessor remarks: Good.
733 | Grading and levelling of Endarasha/ Market/Jua kali road | Grading and levelling of Endarasha/ Market/Jua kali road | To improve road accessibility by grading and levelling of Endarasha/ Market/Jua kali road | And levelling of Endarasha/ Market/Jua kali road graded | 3110499 | Construction of Roads - Other | Bahati | Dundori | -0.254689, 36.236709 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/2020 | 2000000 | 550 | 550 | Equitable | N/A | 550 | 0 | 1903850 | 346154.5 | 1903850 | 550 | -1903300 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Ms splendid builder's and contractors ltd. Assessor remarks: Good since was done again under Imarisha Barabara.
734 | Infrastructure, Development and Maintenance | Grading And Murraming of Roads Through Imarisha Barabara Programme | To improve road infrastructure by grading and murraming Roads Through Imarisha Barabara Programme | Roads Through Imarisha Barabara Programme graded and murramed | 3110499 | Construction of Roads - Other | Bahati | Dundori | -0.225577, 36.183773 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/2024 | 1900000 | 0 | 760000 | Equitable | N/A | 760000 | 0 | 1140000 | 100 | 1140000 | 760000 | -1140000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Vivo energy. Assessor remarks: Good condition.
735 | Infrastructure, Development and Maintenance | Grading and murraming through Imarisha barabara | To improve road infrastructure by grading and murraming through Imarisha barabara | Through Imarisha barabara graded and murramed | 3110499 | Construction of Roads - Other | Bahati | Dundori | -0.225577, 36.183773 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2023/2024 | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 1140000 | 100 | 1140000 | 760000 | -1140000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Vivo energy. Assessor remarks: Good condition.
736 | Infrastructure, Development & Maintenance | Hire Of Equipments For Dundori Access Roads | To implement hire of equipments for dundori access roads for road connectivity and accessibility | Hire Of Equipments For Dundori Access Roads completed | 3110499 | Construction of Roads - Other | Bahati | Dundori | -0.2751, 36.190724 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/2022 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499553 | 100 | 1499553 | 1789870 | 447 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ms strafield contractors ltd. Assessor remarks: Require maintenance.
737 | Infrastructure, Development & Maintenance | Hire Of Equipments For Giachonge Access Roads | To implement hire of equipments for giachonge access roads for road connectivity and accessibility | Hire Of Equipments For Giachonge Access Roads completed | 3110499 | Construction of Roads - Other | Bahati | Dundori | -0.2751, 36.190724 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/2022 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1496400 | 99.8 | 1496400 | 2000000 | 3600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ms strafield contractors ltd. Assessor remarks: Require maintenance.
738 | Infrastructure, Development & Maintenance | Hire Of Equipments For Githioro Access Roads | To implement hire of equipments for githioro access roads for road connectivity and accessibility | Hire Of Equipments For Githioro Access Roads completed | 3110499 | Construction of Roads - Other | Bahati | Dundori | -0.2751, 36.190724 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/2022 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1497850 | 99.9 | 1497850 | 2000000 | 2150 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ms strafield contractors ltd. Assessor remarks: Require maintenance.
739 | Infrastructure, Development & Maintenance | Hire Of Equipments For Magwathi Access Roads | To implement hire of equipments for magwathi access roads for road connectivity and accessibility | Hire Of Equipments For Magwathi Access Roads completed | 3110499 | Construction of Roads - Other | Bahati | Dundori | -0.2751, 36.190724 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/2022 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1997550 | 99.9 | 1997550 | 2000000 | 2450 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ms strafield contractors ltd. Assessor remarks: Require maintenance.
740 | Hire of equipments through boresha barabara | Hire of equipments through boresha barabara | To implement hire of equipments through boresha barabara for road connectivity and accessibility | Hire of equipments through boresha barabara completed | 3110499 | Construction of Roads - Other | Bahati | Dundori | -0.257888, 36.236098 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/2021 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999300 | 100 | 1999300 | 2000000 | 700 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Ms cCenmi Marchants. Assessor remarks: Dilapidated road.
741 | Infrastructure, Development and Maintenance | Hire of machineries for roads rehabilitation | To implement hire of machineries for roads rehabilitation for road connectivity and accessibility | Hire of machineries for roads rehabilitation completed | 3110499 | Construction of Roads - Other | Bahati | Dundori | -0.26795, 36.194385 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2024-2025 | 2400000 | 0 | 2404768 | Equitable | N/A | 2404768 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good, require murraming.
742 | Infrastructure, Development and Maintenance | Installation of culverts across the ward | To improve drainage and road access through culvert installation at across the ward | Culverts installed at across the ward | 3110499 | Construction of Roads - Other | Bahati | Dundori | -0.26339, 36.187338 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2024/2025 | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 106553 | 100 | 106553 | 2000000 | -106553 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Merich International Ltd. Assessor remarks: Good.
743 | Infrastructure, Development and Maintenance | Murraming and culverts in Dundori access roads | To implement murraming and culverts in dundori access roads for road connectivity and accessibility | Murraming and culverts in Dundori access roads completed | 3110499 | Construction of Roads - Other | Bahati | Dundori | -0.262973, 36.18662 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/2021 | 1000000 | 943870 | 943870 | Equitable | N/A | 943870 | 0 | 943870 | 100 | 943870 | 943870 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs routine maintenance.
744 | Infrastructure, Development and Maintenance | Murraming and culverts in Githioro access roads | To implement murraming and culverts in githioro access roads for road connectivity and accessibility | Murraming and culverts in Githioro access roads completed | 3110499 | Construction of Roads - Other | Bahati | Dundori | -0.262973, 36.18662 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/2021 | 1000000 | 978180 | 978180 | Equitable | N/A | 978180 | 0 | 978180 | 100 | 978180 | 978180 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs routine maintenance.
745 | Infrastructure, Development and Maintenance | Murraming and culverts in Mugwathi Giachonge access roads | To implement murraming and culverts in mugwathi giachonge access roads for road connectivity and accessibility | Murraming and culverts in Mugwathi Giachonge access roads completed | 3110499 | Construction of Roads - Other | Bahati | Dundori | -0.262973, 36.18662 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/2021 | 1000000 | 975250 | 975250 | Equitable | N/A | 975250 | 0 | 975250 | 100 | 975250 | 975250 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs routine maintenance.
746 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Githioro - St. Monica Access Roads in Dundori Ward Bahati Sub County | To maintain Spot Improvement of Githioro - St. Monica Access Roads in Dundori Ward Bahati Sub County in serviceable condition | Spot Improvement of Githioro - St. Monica Access Roads in Dundori Ward Bahati Sub County maintained | 3110499 | Construction of Roads - Other | Bahati | Dundori | -0.261632, 36.190737 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/2017 | 988200 | 988200 | 988200 | Equitable | N/A | 988200 | 0 | 1382968 | 139.9 | 1382968 | 988200 | -394768 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: M/s Heights. Assessor remarks: In bad condition require maintenance.
747 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Githioro - St. Munica Access Roads in Dundori Ward Bahati Sub County | To maintain Spot Improvement of Githioro - St. Munica Access Roads in Dundori Ward Bahati Sub County in serviceable condition | Spot Improvement of Githioro - St. Munica Access Roads in Dundori Ward Bahati Sub County maintained | 3110499 | Construction of Roads - Other | Bahati | Dundori | -0.261632, 36.190737 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/2017 | 988200 | 988200 | 988200 | Equitable | N/A | 988200 | 0 | 1382968 | 139.9 | 1382968 | 988200 | -394768 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: M/s Heights. Assessor remarks: In bad condition require maintenance.
748 | Routine Maintenance and Spot Improvement of Mathare Access Roads in Dundori Ward Bahati Sub County | Routine Maintenance and Spot Improvement of Mathare Access Roads in Dundori Ward Bahati Sub County | To maintain Spot Improvement of Mathare Access Roads in Dundori Ward Bahati Sub County in serviceable condition | Spot Improvement of Mathare Access Roads in Dundori Ward Bahati Sub County maintained | 3110499 | Construction of Roads - Other | Bahati | Dundori | -0.22335, 36.174868 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/2017 | 1488879.3 | 1488879.3 | 1488879.3 | Equitable | N/A | 1488879.3 | 0 | 1382968 | 92.9 | 1382968 | 1488879 | 105911.3 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Lanu contractors ltd. Assessor remarks: Road needs maintenance.
749 | Infrastructure, Development and Maintenance | Routine maintenance of roads in Eburru Mbaruk ward | To maintain roads in Eburru Mbaruk ward in serviceable condition | Roads in Eburru Mbaruk ward maintained | 3110499 | Construction of Roads - Other | Gilgil | Eburru-Mbaruk | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 8000000 | 0 | 8000000 | Equitable | N/A | 8000000 | 0 | 3453237 | 0 | 3453237 | 5000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
750 | Infrastructure, Development & Maintenance | Eburru Mbaruk road works (Hiring of equipments, grading, gravelling) and installation of culverts) | To implement eburru mbaruk road works (hiring of equipments, grading, gravelling) and installation of culverts) for road connectivity and accessibility | Eburru Mbaruk road works (Hiring of equipments, grading, gravelling) and installation of culverts) completed | 3110499 | Construction of Roads - Other | Gilgil | Eburru/Mbaruk | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 14500000 | 14500000 | 14500000 | Equitable | N/A | 14500000 | 0 | 14497065 | 100 | 14497065 | 0 | 2935 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
751 | Infrastructure, Development and Maintenance | Grading and murraming of Cypress-Songoloi junction | To improve road infrastructure by grading and murraming Cypress-Songoloi junction | Cypress-Songoloi junction graded and murramed | 3110499 | Construction of Roads - Other | Gilgil | Eburru/Mbaruk | -0.635963, 36.2568 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 22-23 | 1000000 | 944300 | 944300 | Equitable | N/A | 944300 | 0 | 944300 | 100 | 944300 | 944300 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: Partially. Condition: Bad. Objective met: No. Viable: No. Contractor: Unspecified. Assessor remarks: Road in bad state.
752 | Infrastructure, Development & Maintenance | Grading and murraming of Galile to Transformer road | To improve road infrastructure by grading and murraming Galile to Transformer road | Galile to Transformer road graded and murramed | 3110499 | Construction of Roads - Other | Gilgil | Eburru/Mbaruk | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 945200 | 945200 | Equitable | N/A | 945200 | 0 | 945200 | 100 | 945200 | 945200 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
753 | Infrastructure, Development & Maintenance | Grading and murraming of Kiamolo-Pipeline roads | To improve road infrastructure by grading and murraming Kiamolo-Pipeline roads | Kiamolo-Pipeline roads graded and murramed | 3110499 | Construction of Roads - Other | Gilgil | Eburru/Mbaruk | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 765000 | 765000 | 765000 | Equitable | N/A | 765000 | 0 | 756900 | 98.9 | 756900 | 760600 | 8100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
754 | Infrastructure, Development & Maintenance | Grading and murraming of Kiamolo-Pipeline road | To improve road infrastructure by grading and murraming Kiamolo-Pipeline road | Kiamolo-Pipeline road graded and murramed | 3110499 | Construction of Roads - Other | Gilgil | Eburru/Mbaruk | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 800000 | 760600 | 760600 | Equitable | N/A | 760600 | 0 | 760600 | 100 | 760600 | 760600 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
755 | Infrastructure, Development and Maintenance | Grading and Murraming of Roads in Eburru/Mbaruk Ward | To improve road infrastructure by grading and murraming Roads in Eburru/Mbaruk Ward | Roads in Eburru/Mbaruk Ward graded and murramed | 3110499 | Construction of Roads - Other | Gilgil | Eburru/Mbaruk | -0.555031, 36.1555513 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 22-23 | 3800000 | 3800000 | 3800000 | Equitable | N/A | 3800000 | 0 | 3453237 | 90.9 | 3453237 | 5000000 | 346763 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Unspecified. Assessor remarks: Need repair.
756 | Infrastructure, Development and Maintenance | Grading And Murraming of Roads Through Imarisha Barabara Programme | To improve road infrastructure by grading and murraming Roads Through Imarisha Barabara Programme | Roads Through Imarisha Barabara Programme graded and murramed | 3110499 | Construction of Roads - Other | Gilgil | Eburru/Mbaruk | -0.36545, 36.178161 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 5000000 | 4700000 | 4700000 | Equitable | N/A | 4700000 | 0 | 4700000 | 100 | 4700000 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes, only expand the road. Contractor: 23/24. Assessor remarks: Fairy done.
757 | Infrastructure, Development & Maintenance | Grading and murraming of Stage I - corner mbaya Road | To improve road infrastructure by grading and murraming Stage I - corner mbaya Road | Stage I - corner mbaya Road graded and murramed | 3110499 | Construction of Roads - Other | Gilgil | Eburru/Mbaruk | -0.348556, 36.178127 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 19/20 | 2669078 | 1602019.55 | 1602019.55 | Equitable | N/A | 1602019.55 | 0 | 1472275 | 91.9 | 1472275 | 1602020 | 129744.55 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Partially. Viable: No. Bad state. Contractor: Unspecified. Assessor remarks: Road need murraming and expansion.
758 | Infrastructure, Development & Maintenance | Installation of culverts across the ward | To improve drainage and road access through culvert installation at across the ward | Culverts installed at across the ward | 3110499 | Construction of Roads - Other | Gilgil | Eburru/Mbaruk | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 936400 | 936400 | Equitable | N/A | 936400 | 0 | 936400 | 100 | 936400 | 936400 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
759 | Infrastructure, Development and Maintenance | Murraming Of Roads in Eburru Mbaruk | To implement murraming of roads in eburru mbaruk for road connectivity and accessibility | Murraming Of Roads in Eburru Mbaruk completed | 3110499 | Construction of Roads - Other | Gilgil | Eburru/Mbaruk | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 6600000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 3453237 | 69.1 | 3453237 | 5000000 | 1546763 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
760 | Infrastructure, Development & Maintenance | Road Rehabilitation - Purchase and Supply of Murram | To implement road rehabilitation - purchase and supply of murram for road connectivity and accessibility | Road Rehabilitation - Purchase and Supply of Murram completed | 3110499 | Construction of Roads - Other | Gilgil | Eburru/Mbaruk | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | N/A | 600000 | 0 | 600000 | Equitable | N/A | 600000 | 0 | 0 | 0 | 0 | 600000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
761 | Infrastructure, Development and Maintenance | Grading and murraming through Imarisha barabara | To improve road infrastructure by grading and murraming through Imarisha barabara | Through Imarisha barabara graded and murramed | 3110499 | Construction of Roads - Other | Molo | Elburgon | -0.303366, 35.81419 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | - | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
762 | Infrastructure, Development and Maintenance | Grading,murraming,installation of culverts and gabions in elburgon roads | To implement grading,murraming,installation of culverts and gabions in elburgon roads for road connectivity and accessibility | Grading,murraming,installation of culverts and gabions in elburgon roads completed | 3110499 | Construction of Roads - Other | Molo | Elburgon | -0.294954 35.766447 0 2799.9990234375 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 6000000 | 0 | 6000000 | Equitable | N/A | 6000000 | 0 | 965294 | 100 | 965294 | 1186660 | -965294 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
763 | Infrastructure, Development and Maintenance | Hire of machinery and purchase of murram for Arimi, Chieponde, Kasarani Comrade, Eastleigh, Jerusalem, Turi farmers Roads | To implement hire of machinery and purchase of murram for arimi, chieponde, kasarani comrade, eastleigh, jerusalem, turi farmers roads for road connectivity and accessibility | Hire of machinery and purchase of murram for Arimi, Chieponde, Kasarani Comrade, Eastleigh, Jerusalem, Turi farmers Roads completed | 3110499 | Construction of Roads - Other | Molo | Elburgon | -0.303366, 35.81419 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | - | 3900088 | 3900088 | 3900088 | Equitable | N/A | 3900088 | 0 | 3900088 | 100 | 3900088 | 3900088 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
764 | Infrastructure, Development and Maintenance | Hire of Machinery for Elburgon Ward road works | To implement hire of machinery for elburgon ward road works for road connectivity and accessibility | Hire of Machinery for Elburgon Ward road works completed | 3110499 | Construction of Roads - Other | Molo | Elburgon | -0.294731 35.799338 0 838.1790161132812 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 14000000 | 12000000 | 8000000 | Equitable | N/A | 8000000 | 0 | 10419348 | 86.8 | 10419348 | 0 | 1580652 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
765 | Infrastructure, Development and Maintenance | Hiring of machinery for Elburgon road works | To implement hiring of machinery for elburgon road works for road connectivity and accessibility | Hiring of machinery for Elburgon road works completed | 3110499 | Construction of Roads - Other | Molo | Elburgon | -0.294731 35.799338 0 838.1790161132812 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | N/A | 10421155 | 10421155 | 10421155 | Equitable | N/A | 10421155 | 0 | 10419348 | 100 | 10419348 | 0 | 1807 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
766 | Infrastructure, Development and Maintenance | Kapsita Road Works- Grading and Murraming | To implement kapsita road works- grading and murraming for road connectivity and accessibility | Kapsita Road Works- Grading and Murraming completed | 3110499 | Construction of Roads - Other | Molo | Elburgon | -0.289915, 35.773951 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | - | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2241920 | 89.7 | 2241920 | 258080 | 258080 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
767 | Murraming of Kapsita Mitate road | Murraming of Kapsita Mitate road | To implement murraming of kapsita mitate road for road connectivity and accessibility | Murraming of Kapsita Mitate road completed | 3110499 | Construction of Roads - Other | Molo | Elburgon | -0.307435, 35.749389 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | - | 1100000 | 1100000 | 1100000 | Equitable | N/A | 1100000 | 0 | 1100000 | 100 | 1100000 | 1100000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
768 | Routine Maintenance and Spot Improvement of Matuiku Estate Roads in Elburgon Ward Molo Sub County | Routine Maintenance and Spot Improvement of Matuiku Estate Roads in Elburgon Ward Molo Sub County | To maintain Spot Improvement of Matuiku Estate Roads in Elburgon Ward Molo Sub County in serviceable condition | Spot Improvement of Matuiku Estate Roads in Elburgon Ward Molo Sub County maintained | 3110499 | Construction of Roads - Other | Molo | Elburgon | -0.302023, 35.813376 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | - | 1500000 | 1499000 | 1499000 | Equitable | N/A | 1499000 | 0 | 1298411 | 86.6 | 1298411 | 200589 | 200589 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
769 | Infrastructure, Development and Maintenance | Supply of murram at Kasarani road | To implement supply of murram at kasarani road for road connectivity and accessibility | Supply of murram at Kasarani road completed | 3110499 | Construction of Roads - Other | Molo | Elburgon | -0.294048, 35.802135 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | - | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 1000000 | 100 | 1000000 | 2000000 | -1000000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Ys. Assessor remarks: Good roads.
770 | Infrastructure, Development & Maintenance | Supply of murram at Ndimu primary road | To implement supply of murram at ndimu primary road for road connectivity and accessibility | Supply of murram at Ndimu primary road completed | 3110499 | Construction of Roads - Other | Molo | Elburgon | -0.258464, 35.763718 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | - | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Road motorable.
771 | Infrastructure, Development and Maintenance | Supply of murram for Nyakiambi Karunga road | To implement supply of murram for nyakiambi karunga road for road connectivity and accessibility | Supply of murram for Nyakiambi Karunga road completed | 3110499 | Construction of Roads - Other | Molo | Elburgon | -0.284884, 35.845889 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | - | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 996682 | 99.7 | 996682 | 1000000 | 3318 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
772 | Infrastructure, Development and Maintenance | Construction of Kiptangwanyi drainages | To construct Kiptangwanyi drainages | Kiptangwanyi drainages constructed | 3110499 | Construction of Roads - Other | Gilgil | Elementaita | -0.563416 36.116992 1960.699951171875 0.6940000057220459 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | N/A | 8000000 | 689016.2 | 689016.2 | Equitable | N/A | 689016.2 | 0 | 6424879 | 932.5 | 6424879 | 689016 | -5735862.8 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
773 | Infrastructure, Development and Maintenance | Grading and murraming of roads through Imarisha Barabara programme | To improve road infrastructure by grading and murraming roads through Imarisha Barabara programme | Roads through Imarisha Barabara programme graded and murramed | 3110499 | Construction of Roads - Other | Gilgil | Elementaita | -0.584135, 36.114333 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 2000000 | 0 | 800000 | Equitable | N/A | 800000 | 0 | 1200000 | 100 | 1200000 | 800000 | -1200000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
774 | Infrastructure, Development and Maintenance | Grading and murraming through Imarisha barabara | To improve road infrastructure by grading and murraming through Imarisha barabara | Through Imarisha barabara graded and murramed | 3110499 | Construction of Roads - Other | Gilgil | Elementaita | -0.584135, 36.114333 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 2038437 | 0 | 2038437 | Equitable | N/A | 2038437 | 0 | 1200000 | 100 | 1200000 | 800000 | -1200000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
775 | Infrastructure, Development and Maintenance | Grading & Murraming of Access roads within the Ward | To improve road accessibility by grading & Murraming of Access roads within the Ward | & Murraming of Access roads within the Ward graded | 3110499 | Construction of Roads - Other | Gilgil | Elementaita | -0.586295 36.086254 2013.107 0.7870000004768372 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 5000000 | 100 | 5000000 | 3500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Needs urgent attention.
776 | Infrastructure, Development & Maintenance | Grading sport gravelling of Munada Kanorero - Munyaka Road (2015/16) | To improve road accessibility by grading sport gravelling of Munada Kanorero - Munyaka Road (2015/16) | Sport gravelling of Munada Kanorero - Munyaka Road (2015/16) graded | 3110499 | Construction of Roads - Other | Gilgil | Elementaita | -0.601874 36.106719 2106.511 0.8220000267028809 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 7000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2997152 | 99.9 | 2997152 | 3000000 | 2848 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Needs urgent attention.
777 | Infrastructure, Development and Maintenance | Hire of equipments for maintenance of access roads in Elementaita ward | To implement hire of equipments for maintenance of access roads in elementaita ward for road connectivity and accessibility | Hire of equipments for maintenance of access roads in Elementaita ward completed | 3110499 | Construction of Roads - Other | Gilgil | Elementaita | -0.559358 36.111862 1961.0999755859375 19.200000762939453 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 22308736 | 22308736 | 22308736 | Equitable | N/A | 22308736 | 0 | 22308736 | 100 | 22308736 | 15308736 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Most of it has been carried away by Rain.
778 | Infrastructure, Development and Maintenance | Hiring of Equipments for maintenance of access roads in Elementaita ward | To implement hiring of equipments for maintenance of access roads in elementaita ward for road connectivity and accessibility | Hiring of Equipments for maintenance of access roads in Elementaita ward completed | 3110499 | Construction of Roads - Other | Gilgil | Elementaita | -0.559358 36.111862 1961.0999755859375 19.200000762939453 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 5000000 | 100 | 5000000 | 15308736 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Most of it has been carried away by Rain.
779 | Installation of floodlights at Kiambogo, Kanorero, Mitimingi and Kiptangwanyi | Installation of floodlights at Kiambogo, Kanorero, Mitimingi and Kiptangwanyi | To install floodlights at Kiambogo, Kanorero, Mitimingi and Kiptangwanyi | Floodlights at Kiambogo, Kanorero, Mitimingi and Kiptangwanyi installed | 3110499 | Construction of Roads - Other | Gilgil | Elementaita | -0.59724, 36.131596 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 2403972 | 2403972 | 2403972 | Equitable | N/A | 2403972 | 0 | 2289625 | 95.2 | 2289625 | 2403972 | 114347 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
780 | Infrastructure, Development & Maintenance | Rehabilitation of roads through hire of equipment and machinery in Elementaita ward | To rehabilitate roads through hire of equipment and machinery in Elementaita ward to restore functionality | Roads through hire of equipment and machinery in Elementaita ward rehabilitated | 3110499 | Construction of Roads - Other | Gilgil | Elementaita | -0.595223, 36.121223 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3800952 | 95 | 3800952 | 4000000 | 199048 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Routine maintenance is required.
781 | Infrastructure, Development and Maintenance | Road Rehabilitation - Purchase and Supply of Murram | To implement road rehabilitation - purchase and supply of murram for road connectivity and accessibility | Road Rehabilitation - Purchase and Supply of Murram completed | 3110499 | Construction of Roads - Other | Gilgil | Elementaita | -0.584117 36.108603 2110.400146484375 1.0089999437332153 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | N/A | 1200000 | 0 | 1200000 | Equitable | N/A | 1200000 | 0 | 0 | 0 | 0 | 1200000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Doing well.
782 | Infrastructure, Development and Maintenance | Drainage works of 300 meters of Nyamira Drive in Race Course Estate | To implement drainage works of 300 meters of nyamira drive in race course estate for road connectivity and accessibility | Drainage works of 300 meters of Nyamira Drive in Race Course Estate completed | 3110499 | Construction of Roads - Other | Nakuru East | Flamingo | -0.305175, 36.071498 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/2022 | 2500000 | 2467100 | 2467100 | Equitable | N/A | 2467100 | 0 | 2465788 | 99.9 | 2465788 | 2467100 | 1312 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not provided. Assessor remarks: In good state.
783 | Infrastructure, Development and Maintenance | Grading and murraming at Langa langa and Freehold estates | To improve road infrastructure by grading and murraming at Langa langa and Freehold estates | At Langa langa and Freehold estates graded and murramed | 3110499 | Construction of Roads - Other | Nakuru East | Flamingo | -0.30763, 36.071062 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | Not provided | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Completed.
784 | Infrastructure, Development and Maintenance | Proposed upgrading to Bitumen standard of road connecting Chrisco to Kisumu road in Flamingo Ward | To undertake the proposed upgrading to Bitumen standard of road connecting Chrisco to Kisumu road in Flamingo Ward | Proposed upgrading to Bitumen standard of road connecting Chrisco to Kisumu road in Flamingo Ward implemented | 3110499 | Construction of Roads - Other | Nakuru East | Flamingo | -0.30474 36.07626 1753.5 100 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 9991630 | 0 | 9991630 | Equitable | N/A | 9991630 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Functional.
785 | Infrastructure, Development & Maintenance | Recarpetting of Chrisco road from Othaya road junction to Chrisco unction | To implement recarpetting of chrisco road from othaya road junction to chrisco unction for road connectivity and accessibility | Recarpetting of Chrisco road from Othaya road junction to Chrisco unction completed | 3110499 | Construction of Roads - Other | Nakuru East | Flamingo | -0.305203, 36.071575 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | Fy2021-2022 | 2300000 | 2300000 | 2300000 | Equitable | N/A | 2300000 | 0 | 0 | 0 | 0 | 2300000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Operational.
786 | Infrastructure, Development and Maintenance | Re-Tarmacking Of 300 M Of Nyamira Drive In Racecourse Estate | To implement re-tarmacking of 300 m of nyamira drive in racecourse estate for road connectivity and accessibility | Re-Tarmacking Of 300 M Of Nyamira Drive In Racecourse Estate completed | 3110499 | Construction of Roads - Other | Nakuru East | Flamingo | -0.305175, 36.071498 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2021/2022 | 3800000 | 8839.23 | 8839.23 | Equitable | N/A | 8839.23 | 0 | 3426965 | 38769.9 | 3426965 | 8839 | -3418125.77 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not provided. Assessor remarks: In good state.
787 | Infrastructure, Development & Maintenance | Re-tarmacking of 415 meters road off Eldoret road at Friends Church to St. Joseph Catholic and back to Eldoret via Josmil supermarket in Race Course Estate | To implement re-tarmacking of 415 meters road off eldoret road at friends church to st. joseph catholic and back to eldoret via josmil supermarket in race course estate for road connectivity and accessibility | Re-tarmacking of 415 meters road off Eldoret road at Friends Church to St. Joseph Catholic and back to Eldoret via Josmil supermarket in Race Course Estate completed | 3110499 | Construction of Roads - Other | Nakuru East | Flamingo | -0.310834, 36.070996 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/2022 | 10000000 | 9991630 | 9991630 | Equitable | N/A | 9991630 | 0 | 0 | 0 | 0 | 9991630 | 0 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: In use and in good state.
788 | Infrastructure, Development and Maintenance | Boresha barabara fuel and murram | To implement boresha barabara fuel and murram for road connectivity and accessibility | Boresha barabara fuel and murram completed | 3110499 | Construction of Roads - Other | Gilgil | Gilgil | -0.478819 36.330936 2027.699951171875 9.418000221252441 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 705665 | 88.2 | 705665 | 94335 | 94335 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Needs maintainance.
789 | Infrastructure, Development & Maintenance | Construction of modern boda boda shades gilgil Ward | To construct modern boda boda shades gilgil Ward | Modern boda boda shades gilgil Ward constructed | 3110499 | Construction of Roads - Other | Gilgil | Gilgil | -0.500033 36.322175 1978.9000244140625 20.899999618530273 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 2700000 | 2700000 | 2700000 | Equitable | N/A | 2700000 | 0 | 2495600 | 92.4 | 2495600 | 600000 | 204400 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
790 | Infrastructure, Development & Maintenance | Gilgil Roads rehabilitation (hire of machinery and equipments) | To implement gilgil roads rehabilitation (hire of machinery and equipments) for road connectivity and accessibility | Gilgil Roads rehabilitation (hire of machinery and equipments) completed | 3110499 | Construction of Roads - Other | Gilgil | Gilgil | -0.504809 36.322724 1991 11.029999732971191 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1496900 | 99.8 | 1496900 | 1500000 | 3100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Petronic Automatic. Assessor remarks: Extention of power from the main power house to the outpatient facility to serve the whole hospital.
791 | Infrastructure, Development and Maintenance | Grading and gravelling, compaction of Milimani/Rereshwa road and installation of culverts. | To improve road accessibility by grading and gravelling, compaction of Milimani/Rereshwa road and installation of culverts | And gravelling, compaction of Milimani/Rereshwa road and installation of culverts graded | 3110499 | Construction of Roads - Other | Gilgil | Gilgil | -0.491475, 36.343686 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/2020 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1970182 | 98.5 | 1970182 | 2000000 | 29818 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Partially. Viable: Viable. Assessor remarks: Needs maintainance and culverts.
792 | Infrastructure, Development & Maintenance | Grading and gravelling, drainage of kambi Somali under pass and site A Roads and installation of culvert roads | To improve road accessibility by grading and gravelling, drainage of kambi Somali under pass and site A Roads and installation of culvert roads | And gravelling, drainage of kambi Somali under pass and site A Roads and installation of culvert roads graded | 3110499 | Construction of Roads - Other | Gilgil | Gilgil | -0.508071, 36.319004 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1855387 | 92.8 | 1855387 | 2000000 | 144613 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: The road needs maintainance.
793 | Infrastructure, Development and Maintenance | Grading and murraming of Kikopey access roads through Imarisha barabara programme | To improve road infrastructure by grading and murraming Kikopey access roads through Imarisha barabara programme | Kikopey access roads through Imarisha barabara programme graded and murramed | 3110499 | Construction of Roads - Other | Gilgil | Gilgil | -0.448634 36.282639 1893.47802734375 12.605999946594238 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 600000 | 60 | 600000 | 400000 | 400000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ripasol enterprises. Assessor remarks: In good state.
794 | Infrastructure, Development and Maintenance | Grading And Murraming of Roads Through Imarisha Barabara Programme | To improve road infrastructure by grading and murraming Roads Through Imarisha Barabara Programme | Roads Through Imarisha Barabara Programme graded and murramed | 3110499 | Construction of Roads - Other | Gilgil | Gilgil | -0.509335 36.317226 2005.0999755859375 5.428999900817871 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 1000000 | 0 | 400000 | Equitable | N/A | 400000 | 0 | 600000 | 100 | 600000 | 400000 | -600000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Elias company limited. Assessor remarks: Road needs maintainance.
795 | Grading and murraming of Teachers A-Bishop avenue roads and culverts | Grading and murraming of Teachers A-Bishop avenue roads and culverts | To improve road infrastructure by grading and murraming Teachers A-Bishop avenue roads and culverts | Teachers A-Bishop avenue roads and culverts graded and murramed | 3110499 | Construction of Roads - Other | Gilgil | Gilgil | -0.489145, 36.328342 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1722690 | 86.1 | 1722690 | 277310 | 277310 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Maintainance and culverts needed.
796 | Infrastructure, Development and Maintenance | Grading, gravelling and compaction of Kanyawa-Goodwill road and installation of culverts | To implement grading, gravelling and compaction of kanyawa-goodwill road and installation of culverts for road connectivity and accessibility | Grading, gravelling and compaction of Kanyawa-Goodwill road and installation of culverts completed | 3110499 | Construction of Roads - Other | Gilgil | Gilgil | -0.491475, 36.343686 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/2020 | 2000000 | 1989950 | 1989950 | Equitable | N/A | 1989950 | 0 | 1989814 | 100 | 1989814 | 1989950 | 136 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Partially. Viable: Viable. Assessor remarks: Needs maintainance and culverts.
797 | Infrastructure, Development & Maintenance | Grading, gravelling and compaction of Kekopey Masai and P.C.E.A church and installation of culverts | To implement grading, gravelling and compaction of kekopey masai and p.c.e.a church and installation of culverts for road connectivity and accessibility | Grading, gravelling and compaction of Kekopey Masai and P.C.E.A church and installation of culverts completed | 3110499 | Construction of Roads - Other | Gilgil | Gilgil | -0.480768, 36.301989 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1809547 | 90.5 | 1809547 | 2000000 | 190453 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Mengro production Limited. Assessor remarks: Needs maintainance.
798 | Infrastructure, Development and Maintenance | Grading gravelling and compaction of Teachers B-Flower farm road and installation of culverts | To improve road accessibility by grading gravelling and compaction of Teachers B-Flower farm road and installation of culverts | Gravelling and compaction of Teachers B-Flower farm road and installation of culverts graded | 3110499 | Construction of Roads - Other | Gilgil | Gilgil | -0.491475, 36.343686 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/2020 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1931872 | 96.6 | 1931872 | 2000000 | 68128 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Partially. Viable: Viable. Assessor remarks: Needs maintainance and culverts.
799 | Infrastructure, Development and Maintenance | Grading, Gravelling Murraming Maji Moto-Sugunui Road, | To implement grading, gravelling murraming maji moto-sugunui road, for road connectivity and accessibility | Grading, Gravelling Murraming Maji Moto-Sugunui Road, completed | 3110499 | Construction of Roads - Other | Gilgil | Gilgil | -0.448634 36.282639 1893.47802734375 12.605999946594238 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1331708 | 88.8 | 1331708 | 168293 | 168292 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ripasol enterprises. Assessor remarks: In good state.
800 | Infrastructure, Development and Maintenance | Grading, Gravelling Murraming Nganga Kihonge Road, | To implement grading, gravelling murraming nganga kihonge road, for road connectivity and accessibility | Grading, Gravelling Murraming Nganga Kihonge Road, completed | 3110499 | Construction of Roads - Other | Gilgil | Gilgil | -0.479424, 36.314981 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 2500000 | 0 | 2500000 | Equitable | N/A | 2500000 | 0 | 1333031 | 100 | 1333031 | 2500000 | -1333031 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Dakuki Construction co Limited. Assessor remarks: Maintainance.
801 | Infrastructure, Development and Maintenance | Grading, Gravelling Murraming NYS Ngomongo Road | To implement grading, gravelling murraming nys ngomongo road for road connectivity and accessibility | Grading, Gravelling Murraming NYS Ngomongo Road completed | 3110499 | Construction of Roads - Other | Gilgil | Gilgil | -0.479424, 36.314981 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1333031 | 88.9 | 1333031 | 166970 | 166969 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Dakuki Construction co Limited. Assessor remarks: Maintainance.
802 | Infrastructure, Development & Maintenance | Grading, murraming and compaction and construction of culverts at Kambi Somali Site B Roads | To implement grading, murraming and compaction and construction of culverts at kambi somali site b roads for road connectivity and accessibility | Grading, murraming and compaction and construction of culverts at Kambi Somali Site B Roads completed | 3110499 | Construction of Roads - Other | Gilgil | Gilgil | -0.508052, 36.318981 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/2022 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2986532 | 99.6 | 2986532 | 3623 | 13468 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: The road needs maintainance.
803 | Infrastructure, Development & Maintenance | Grading, murraming and compaction and construction of culverts at Mbeggi Roads Teachers A&B roads | To implement grading, murraming and compaction and construction of culverts at mbeggi roads teachers a&b roads for road connectivity and accessibility | Grading, murraming and compaction and construction of culverts at Mbeggi Roads Teachers A&B roads completed | 3110499 | Construction of Roads - Other | Gilgil | Gilgil | -0.508052, 36.318981 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/2022 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3643409 | 91.1 | 3643409 | 168 | 356591 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: The road needs maintainance.
804 | Infrastructure, Development and Maintenance | Grading, murraming and culverts installation of Hedex road | To implement grading, murraming and culverts installation of hedex road for road connectivity and accessibility | Grading, murraming and culverts installation of Hedex road completed | 3110499 | Construction of Roads - Other | Gilgil | Gilgil | -0.475875, 36.295151 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2024/25 | 2600000 | 2600000 | 2600000 | Equitable | N/A | 2600000 | 0 | 5999562 | 230.8 | 5999562 | 6000000 | -3399562 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yet to start. Assessor remarks: Yet to start.
805 | Infrastructure, Development & Maintenance | Hire of machines for grading, murraming and installation of culverts | To implement hire of machines for grading, murraming and installation of culverts for road connectivity and accessibility | Hire of machines for grading, murraming and installation of culverts completed | 3110499 | Construction of Roads - Other | Gilgil | Gilgil | -0.514378 36.113223 1835.4000244140625 6 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 5999562 | 100 | 5999562 | 6000000 | 438 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
806 | Infrastructure, Development & Maintenance | Hire of Machines for Kikopey, Mashinani Roads | To implement hire of machines for kikopey, mashinani roads for road connectivity and accessibility | Hire of Machines for Kikopey, Mashinani Roads completed | 3110499 | Construction of Roads - Other | Gilgil | Gilgil | -0.488644 36.333341 1994.699951171875 7.136000156402588 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 4500000 | 4500000 | 4500000 | Equitable | N/A | 4500000 | 0 | 4499573 | 100 | 4499573 | 0 | 427 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Needs Maintainance.
807 | Infrastructure, Development and Maintenance | Hiring of machinery for roads rehabilitation and culverts installation at Kambi Somali, Site & GG | To implement hiring of machinery for roads rehabilitation and culverts installation at kambi somali, site & gg for road connectivity and accessibility | Hiring of machinery for roads rehabilitation and culverts installation at Kambi Somali, Site & GG completed | 3110499 | Construction of Roads - Other | Gilgil | Gilgil | -0.495816, 36.321586 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 4200000 | 4200000 | 3000000 | Equitable | N/A | 3000000 | 0 | 5999562 | 142.8 | 5999562 | 6000000 | -1799562 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Viable did not meet expectations. Assessor remarks: Needs culverts as there are drainage challenges and no culverts were installed.
808 | Infrastructure, Development and Maintenance | Hiring of machinery for roads rehabilitation at Upper Kikopey and View Point in Gilgil ward | To implement hiring of machinery for roads rehabilitation at upper kikopey and view point in gilgil ward for road connectivity and accessibility | Hiring of machinery for roads rehabilitation at Upper Kikopey and View Point in Gilgil ward completed | 3110499 | Construction of Roads - Other | Gilgil | Gilgil | -0.475096, 36.286927 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2024/25 | 2500000 | 0 | 2500000 | Equitable | N/A | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Viable. Assessor remarks: Affected by rains in some parts. Need culverts.
809 | Infrastructure, Development & Maintenance | Installation of Culverts, road repair and maintenance in Gilgil Town | To install Culverts, road repair and maintenance in Gilgil Town | Culverts, road repair and maintenance in Gilgil Town installed | 3110499 | Construction of Roads - Other | Gilgil | Gilgil | -0.504917 36.3261 1973.5999755859375 10.064000129699707 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 1996399 | 1996399 | 1996399 | Equitable | N/A | 1996399 | 0 | 1998595 | 100.1 | 1998595 | 2938906 | -2196 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: Objective not met. Contractor: Workmanship international co.ltd. Assessor remarks: The office is not equipped and is in an insecure location.
810 | Repairs, maintenance of existing roads, installation of culverts in Gilgil town | Repairs, maintenance of existing roads, installation of culverts in Gilgil town | To implement repairs, maintenance of existing roads, installation of culverts in gilgil town for road connectivity and accessibility | Repairs, maintenance of existing roads, installation of culverts in Gilgil town completed | 3110499 | Construction of Roads - Other | Gilgil | Gilgil | -0.503546 36.321522 1991.5999755859375 10.17300033569336 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1686831 | 1195700 | 1195700 | Equitable | N/A | 1195700 | 0 | 1194674 | 99.9 | 1194674 | 1195700 | 1026 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No project. Viable: No project. Assessor remarks: No project on site.
811 | Infrastructure, Development and Maintenance | Construction Of 10 Boda Boda Shed In Menengai West | To construct 10 Boda Boda Shed In Menengai West | 10 Boda Boda Shed In Menengai West constructed | 3110499 | Construction of Roads - Other | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 3500000 | 0 | 3500000 | Equitable | N/A | 3500000 | 0 | 0 | 0 | 0 | 4000000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
812 | Infrastructure, Development and Maintenance | Construction of 2 boda boda sheds | To construct 2 boda boda sheds | 2 boda boda sheds constructed | 3110499 | Construction of Roads - Other | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | N/A | 600000 | 0 | 600000 | Equitable | N/A | 600000 | 0 | 6978545 | 0 | 6978545 | 4000000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
813 | Infrastructure, Development and Maintenance | Construction of a boda boda shade at Rongai stage F and Molo river | To construct a boda boda shade at Rongai stage F and Molo river | A boda boda shade at Rongai stage F and Molo river constructed | 3110499 | Construction of Roads - Other | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | N/A | 600000 | 0 | 600000 | Equitable | N/A | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
814 | Infrastructure, Development and Maintenance | Construction Of Boda Boda Shade At Hope Well | To construct Boda Boda Shade At Hope Well | Boda Boda Shade At Hope Well constructed | 3110499 | Construction of Roads - Other | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 409283 | 0 | 409283 | Equitable | N/A | 409283 | 0 | 0 | 0 | 0 | 4000000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
815 | Infrastructure, Development and Maintenance | Construction of motorbike sheds | To construct motorbike sheds | Motorbike sheds constructed | 3110499 | Construction of Roads - Other | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | N/A | 700000 | 0 | 700000 | Equitable | N/A | 700000 | 0 | 6978545 | 0 | 6978545 | 4000000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
816 | Infrastructure, Development & Maintenance | Grading and murraming of Good Shepherd - DC Mwaura Road | To improve road infrastructure by grading and murraming Good Shepherd - DC Mwaura Road | Good Shepherd - DC Mwaura Road graded and murramed | 3110499 | Construction of Roads - Other | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
817 | Infrastructure, Development & Maintenance | Grading and murraming of Kinene - Stoo road | To improve road infrastructure by grading and murraming Kinene - Stoo road | Kinene - Stoo road graded and murramed | 3110499 | Construction of Roads - Other | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
818 | Infrastructure, Development & Maintenance | Grading and murraming of Ndoroto road | To improve road infrastructure by grading and murraming Ndoroto road | Ndoroto road graded and murramed | 3110499 | Construction of Roads - Other | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | N/A | 15000000 | 0 | 13100000 | Equitable | N/A | 13100000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
819 | Infrastructure, Development & Maintenance | Grading, murraming, compaction and culverts of Menyi Gituru Road | To implement grading, murraming, compaction and culverts of menyi gituru road for road connectivity and accessibility | Grading, murraming, compaction and culverts of Menyi Gituru Road completed | 3110499 | Construction of Roads - Other | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | N/A | 20000000 | 20000000 | 20000000 | Equitable | N/A | 20000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
820 | Infrastructure, Development and Maintenance | Grading of roads through Imarisha barabara programme | To improve road accessibility by grading roads through Imarisha barabara programme | Roads through Imarisha barabara programme graded | 3110499 | Construction of Roads - Other | HQ | HQ | -0.530098, 36.383684 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 12000000 | 12000000 | 12000000 | Equitable | N/A | 12000000 | 0 | 11217000 | 93.5 | 11217000 | 783000 | 783000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Imarisha barabara. Assessor remarks: Good.
821 | Infrastructure, Development and Maintenance | Internal Maintenance of rural and urban roads Program (MRUP) [Imarisha Barabara Program] | To implement internal maintenance of rural and urban roads program (mrup) [imarisha barabara program] for road connectivity and accessibility | Internal Maintenance of rural and urban roads Program (MRUP) [Imarisha Barabara Program] completed | 3110499 | Construction of Roads - Other | HQ | HQ | -0.530572, 36.384016 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2024/25 | 2023/24 | 28500000 | 53500000 | 49958746 | Equitable | N/A | 49958746 | 0 | 27276176 | 51 | 27276176 | 783000 | 26223824 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Imarisha program. Assessor remarks: Good.
822 | Infrastructure, Development and Maintenance | Proposed grading and spot improvement of greensteds-old nakuru-nairobi road in eburu-mbaruk ward, gilgil sub - county | To undertake the proposed grading and spot improvement of greensteds-old nakuru-nairobi road in eburu-mbaruk ward, gilgil sub - county | Proposed grading and spot improvement of greensteds-old nakuru-nairobi road in eburu-mbaruk ward, gilgil sub - county implemented | 3110499 | Construction of Roads - Other | HQ | HQ | -0.530098, 36.383684 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2023/24 | 6400900 | 6400900 | 6400900 | Equitable | N/A | 6400900 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Imarisha barabara. Assessor remarks: Good.
823 | Infrastructure, Development and Maintenance | Proposed Grading & Gravelling of Atwoli Climb next to the Barrier Road in Menengai West Ward and Construction of Drainages at Tree Farm Road in Mosop Ward Rongai Sub-County | To undertake the proposed Grading & Gravelling of Atwoli Climb next to the Barrier Road in Menengai West Ward and Construction of Drainages at Tree Farm Road in Mosop Ward Rongai Sub-County | Proposed Grading & Gravelling of Atwoli Climb next to the Barrier Road in Menengai West Ward and Construction of Drainages at Tree Farm Road in Mosop Ward Rongai Sub-County implemented | 3110499 | Construction of Roads - Other | HQ | HQ | -0.530098, 36.383684 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2023/24 | 9327200 | 9327200 | 9327200 | Equitable | N/A | 9327200 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Imarisha barabara. Assessor remarks: Good.
824 | Infrastructure, Development and Maintenance | Proposed improvement (part) to bitumen standard of the existing Heshima Road in Kiamaina Ward Bahati Sub-County | To undertake the proposed improvement (part) to bitumen standard of the existing Heshima Road in Kiamaina Ward Bahati Sub-County | Proposed improvement (part) to bitumen standard of the existing Heshima Road in Kiamaina Ward Bahati Sub-County implemented | 3110499 | Construction of Roads - Other | HQ | HQ | -0.530098, 36.383684 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2023/24 | 17544030 | 13133317.2 | 0 | Equitable | N/A | 0 | 13133317.2 | 0 | 0 | 0 | 0 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Imarisha barabara. Assessor remarks: Good.
825 | Infrastructure, Development and Maintenance | Proposed improvement/culverting of Tee Trading Centre to Gashuma Trading Centre (6km) and Munanda-Kiambogo- Muthaiti Road (4km) in Elementaita Ward Gilgil Sub-County | To undertake the proposed improvement/culverting of Tee Trading Centre to Gashuma Trading Centre (6km) and Munanda-Kiambogo- Muthaiti Road (4km) in Elementaita Ward Gilgil Sub-County | Proposed improvement/culverting of Tee Trading Centre to Gashuma Trading Centre (6km) and Munanda-Kiambogo- Muthaiti Road (4km) in Elementaita Ward Gilgil Sub-County implemented | 3110499 | Construction of Roads - Other | HQ | HQ | -0.530098, 36.383684 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2023/24 | 9899300 | 4747.65 | 0 | Equitable | N/A | 0 | 4747.65 | 0 | 0 | 0 | 0 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Imarisha barabara. Assessor remarks: Good.
826 | Infrastructure, Development and Maintenance | Proposed Maintenance and Drain Improvement at Kiti near PCEA Shalom Kiti Church in Kiamaina Ward and Rountine Maintenance Spot Improvement and Culvert Installation of Kwa Gitu-CDF Tank Access Road at Bahati Ward Bahati Sub-County | To undertake the proposed Maintenance and Drain Improvement at Kiti near PCEA Shalom Kiti Church in Kiamaina Ward and Rountine Maintenance Spot Improvement and Culvert Installation of Kwa Gitu-CDF Tank Access Road at Bahati Ward Bahati Sub-County | Proposed Maintenance and Drain Improvement at Kiti near PCEA Shalom Kiti Church in Kiamaina Ward and Rountine Maintenance Spot Improvement and Culvert Installation of Kwa Gitu-CDF Tank Access Road at Bahati Ward Bahati Sub-County implemented | 3110499 | Construction of Roads - Other | HQ | HQ | -0.530098, 36.383684 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2023/24 | 11483157 | 11483157 | 11483157 | Equitable | N/A | 11483157 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Imarisha barabara. Assessor remarks: Good.
827 | Infrastructure, Development & Maintenance | Proposed opening of industrial park roads 11 km phase 1 in Maai Mahiu Naivasha sub county | To undertake the proposed opening of industrial park roads 11 km phase 1 in Maai Mahiu Naivasha sub county | Proposed opening of industrial park roads 11 km phase 1 in Maai Mahiu Naivasha sub county implemented | 3110499 | Construction of Roads - Other | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 3321100 | 3321100 | 3321100 | Equitable | N/A | 3321100 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
828 | Infrastructure, Development & Maintenance | Proposed opening of industrial park roads 11 km phase 2 in Maai Mahiu Naivasha sub county | To undertake the proposed opening of industrial park roads 11 km phase 2 in Maai Mahiu Naivasha sub county | Proposed opening of industrial park roads 11 km phase 2 in Maai Mahiu Naivasha sub county implemented | 3110499 | Construction of Roads - Other | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 3686000 | 3686000 | 3686000 | Equitable | N/A | 3686000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
829 | Infrastructure, Development & Maintenance | Proposed opening of industrial park roads 11 km phase 3 in Maai Mahiu Naivasha sub county | To undertake the proposed opening of industrial park roads 11 km phase 3 in Maai Mahiu Naivasha sub county | Proposed opening of industrial park roads 11 km phase 3 in Maai Mahiu Naivasha sub county implemented | 3110499 | Construction of Roads - Other | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 3788625 | 3788625 | 3788625 | Equitable | N/A | 3788625 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
830 | Infrastructure, Development & Maintenance | Proposed opening of industrial park roads 11 km phase 4 in Maai Mahiu Naivasha sub county | To undertake the proposed opening of industrial park roads 11 km phase 4 in Maai Mahiu Naivasha sub county | Proposed opening of industrial park roads 11 km phase 4 in Maai Mahiu Naivasha sub county implemented | 3110499 | Construction of Roads - Other | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 3790700 | 3790700 | 3790700 | Equitable | N/A | 3790700 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
831 | Infrastructure, Development & Maintenance | Proposed opening of industrial park roads 11 km phase 5 in Maai Mahiu Naivasha sub county | To undertake the proposed opening of industrial park roads 11 km phase 5 in Maai Mahiu Naivasha sub county | Proposed opening of industrial park roads 11 km phase 5 in Maai Mahiu Naivasha sub county implemented | 3110499 | Construction of Roads - Other | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 3670120 | 3670120 | 3670120 | Equitable | N/A | 3670120 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
832 | Infrastructure, Development & Maintenance | Proposed opening of industrial park roads 11 km phase 6 in Maai Mahiu Naivasha sub county | To undertake the proposed opening of industrial park roads 11 km phase 6 in Maai Mahiu Naivasha sub county | Proposed opening of industrial park roads 11 km phase 6 in Maai Mahiu Naivasha sub county implemented | 3110499 | Construction of Roads - Other | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 1000650 | 1000650 | 1000650 | Equitable | N/A | 1000650 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
833 | Infrastructure, Development and Maintenance | Proposed part improvement of the Nessuit Junction -Ndoswa in Mariashoni Ward Molo Sub-county | To undertake the proposed part improvement of the Nessuit Junction -Ndoswa in Mariashoni Ward Molo Sub-county | Proposed part improvement of the Nessuit Junction -Ndoswa in Mariashoni Ward Molo Sub-county implemented | 3110499 | Construction of Roads - Other | HQ | HQ | -0.530098, 36.383684 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2023/24 | 2611270 | 2611270 | 0 | Equitable | N/A | 0 | 2611270 | 0 | 0 | 0 | 0 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Imarisha barabara. Assessor remarks: Good.
834 | Infrastructure, Development and Maintenance | Proposed part tarmacking of Kaloleni Road in Molo Ward Molo Sub-County | To undertake the proposed part tarmacking of Kaloleni Road in Molo Ward Molo Sub-County | Proposed part tarmacking of Kaloleni Road in Molo Ward Molo Sub-County implemented | 3110499 | Construction of Roads - Other | HQ | HQ | -0.530098, 36.383684 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2023/24 | 25047277 | 9940365.83 | 0 | Equitable | N/A | 0 | 9940365.83 | 0 | 0 | 0 | 0 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Imarisha barabara. Assessor remarks: Good.
835 | Infrastructure, Development and Maintenance | Proposed pothole patching of part of the Free Area Tosti Spin Knit Road in Nakuru East Ward Nakuru East Sub-County | To undertake the proposed pothole patching of part of the Free Area Tosti Spin Knit Road in Nakuru East Ward Nakuru East Sub-County | Proposed pothole patching of part of the Free Area Tosti Spin Knit Road in Nakuru East Ward Nakuru East Sub-County implemented | 3110499 | Construction of Roads - Other | HQ | HQ | -0.530098, 36.383684 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2023/24 | 4549825 | 4549825 | 0 | Equitable | N/A | 0 | 4549825 | 0 | 0 | 0 | 0 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Imarisha barabara. Assessor remarks: Good.
836 | Infrastructure, Development and Maintenance | Proposed Reinstatement and Spot Improvement of Gioto-Molo line Estate Road | To undertake the proposed Reinstatement and Spot Improvement of Gioto-Molo line Estate Road | Proposed Reinstatement and Spot Improvement of Gioto-Molo line Estate Road implemented | 3110499 | Construction of Roads - Other | HQ | HQ | -0.530098, 36.383684 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2023/24 | 7237240 | 4018615.85 | 0 | Equitable | N/A | 0 | 4018615.85 | 0 | 0 | 0 | 0 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Imarisha barabara. Assessor remarks: Good.
837 | Infrastructure, Development and Maintenance | Proposed Routine Maintenance And Spot Improvement Of CDC Jeremy Road in Murindat Ward Gilgil Sub-County | To undertake the proposed Routine Maintenance And Spot Improvement Of CDC Jeremy Road in Murindat Ward Gilgil Sub-County | Proposed Routine Maintenance And Spot Improvement Of CDC Jeremy Road in Murindat Ward Gilgil Sub-County implemented | 3110499 | Construction of Roads - Other | HQ | HQ | -0.530098, 36.383684 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2023/24 | 2026300 | 2026300 | 2026300 | Equitable | N/A | 2026300 | 0 | 5237600 | 258.5 | 5237600 | 5237600 | -3211300 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Imarisha barabara. Assessor remarks: Good.
838 | Infrastructure, Development and Maintenance | Proposed Routine Maintenance And Spot Improvement Of Cheptuech - Cheptagum Road In Kiptagich Ward Kuresoi South Sub County | To undertake the proposed Routine Maintenance And Spot Improvement Of Cheptuech - Cheptagum Road In Kiptagich Ward Kuresoi South Sub County | Proposed Routine Maintenance And Spot Improvement Of Cheptuech - Cheptagum Road In Kiptagich Ward Kuresoi South Sub County implemented | 3110499 | Construction of Roads - Other | HQ | HQ | -0.530098, 36.383684 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2023/24 | 998510 | 998510 | 998510 | Equitable | N/A | 998510 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Imarisha barabara. Assessor remarks: Good.
839 | Infrastructure, Development and Maintenance | Proposed Routine Maintenance And Spot Improvement Of Chepwet - Mlango 1 Km And Rehema Kabishorit Road In Kiptagich Ward In Kuresoi South Sub-County. | To undertake the proposed Routine Maintenance And Spot Improvement Of Chepwet - Mlango 1 Km And Rehema Kabishorit Road In Kiptagich Ward In Kuresoi South Sub-County | Proposed Routine Maintenance And Spot Improvement Of Chepwet - Mlango 1 Km And Rehema Kabishorit Road In Kiptagich Ward In Kuresoi South Sub-County implemented | 3110499 | Construction of Roads - Other | HQ | HQ | -0.530098, 36.383684 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2023/24 | 2492736 | 2492736 | 2492736 | Equitable | N/A | 2492736 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Imarisha barabara. Assessor remarks: Good.
840 | Infrastructure, Development and Maintenance | Proposed Routine Maintenance And Spot Improvement Of Chigamba Phase II HQ Vote Head In Kiptagich Ward In Kuresoi South Sub-County. | To undertake the proposed Routine Maintenance And Spot Improvement Of Chigamba Phase II HQ Vote Head In Kiptagich Ward In Kuresoi South Sub-County | Proposed Routine Maintenance And Spot Improvement Of Chigamba Phase II HQ Vote Head In Kiptagich Ward In Kuresoi South Sub-County implemented | 3110499 | Construction of Roads - Other | HQ | HQ | -0.530098, 36.383684 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2023/24 | 2994909.25 | 2994909.25 | 2994909.25 | Equitable | N/A | 2994909.25 | 0 | 5237600 | 174.9 | 5237600 | 5237600 | -2242690.75 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Imarisha barabara. Assessor remarks: Good.
841 | Infrastructure, Development and Maintenance | Proposed Routine Maintenance and Spot Improvement of Gacharage- Temoyetta Secondary - Temoyetta DEB and Construction of Bosire Road Box Culvert in Nyota Ward Kuresoi North Sub | To undertake the proposed Routine Maintenance and Spot Improvement of Gacharage- Temoyetta Secondary - Temoyetta DEB and Construction of Bosire Road Box Culvert in Nyota Ward Kuresoi North Sub | Proposed Routine Maintenance and Spot Improvement of Gacharage- Temoyetta Secondary - Temoyetta DEB and Construction of Bosire Road Box Culvert in Nyota Ward Kuresoi North Sub implemented | 3110499 | Construction of Roads - Other | HQ | HQ | -0.530098, 36.383684 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2023/24 | 9990975 | 9990975 | 9990975 | Equitable | N/A | 9990975 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Imarisha barabara. Assessor remarks: Good.
842 | Infrastructure, Development and Maintenance | Proposed Routine Maintenance And Spot Improvement Of Gishangi Junction Kiamburi Murindat Gilgil Sub-County | To undertake the proposed Routine Maintenance And Spot Improvement Of Gishangi Junction Kiamburi Murindat Gilgil Sub-County | Proposed Routine Maintenance And Spot Improvement Of Gishangi Junction Kiamburi Murindat Gilgil Sub-County implemented | 3110499 | Construction of Roads - Other | HQ | HQ | -0.530098, 36.383684 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2023/24 | 2180000 | 2180000 | 2180000 | Equitable | N/A | 2180000 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Imarisha barabara. Assessor remarks: Good.
843 | Infrastructure, Development and Maintenance | Proposed Routine Maintenance and Spot Improvement of Karia-ini Maji- Moto Kwa Nugu in Gilgil Ward, Murindat Ward and Eburru Mbaruk Ward Respectively and Proposed Routine Maintenance and Spot Improvement at NYS Gatamaiyu- Nyakinyua Road Malewa West Ward Gilgil Sub County | To undertake the proposed Routine Maintenance and Spot Improvement of Karia-ini Maji- Moto Kwa Nugu in Gilgil Ward, Murindat Ward and Eburru Mbaruk Ward Respectively and Proposed Routine Maintenance and Spot Improvement at NYS Gatamaiyu- Nyakinyua Road Malewa West Ward Gilgil Sub County | Proposed Routine Maintenance and Spot Improvement of Karia-ini Maji- Moto Kwa Nugu in Gilgil Ward, Murindat Ward and Eburru Mbaruk Ward Respectively and Proposed Routine Maintenance and Spot Improvement at NYS Gatamaiyu- Nyakinyua Road Malewa West Ward Gilgil Sub County implemented | 3110499 | Construction of Roads - Other | HQ | HQ | -0.530098, 36.383684 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2023/24 | 18311149 | 18311149 | 18311149 | Equitable | N/A | 18311149 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Imarisha barabara. Assessor remarks: Good.
844 | Infrastructure, Development and Maintenance | Proposed Routine Maintenance And Spot Improvement Of Karunga Ngeteti Road Gilgil Sub-County | To undertake the proposed Routine Maintenance And Spot Improvement Of Karunga Ngeteti Road Gilgil Sub-County | Proposed Routine Maintenance And Spot Improvement Of Karunga Ngeteti Road Gilgil Sub-County implemented | 3110499 | Construction of Roads - Other | HQ | HQ | -0.530098, 36.383684 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2023/24 | 2239100 | 2239100 | 2239100 | Equitable | N/A | 2239100 | 0 | 5237600 | 233.9 | 5237600 | 5237600 | -2998500 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Imarisha barabara. Assessor remarks: Good.
845 | Infrastructure, Development and Maintenance | Proposed Routine Maintenance and Spot Improvement of Olenguruone Kapchorwa Karofa Road in Amalo Ward Kuresoi South Sub-County | To undertake the proposed Routine Maintenance and Spot Improvement of Olenguruone Kapchorwa Karofa Road in Amalo Ward Kuresoi South Sub-County | Proposed Routine Maintenance and Spot Improvement of Olenguruone Kapchorwa Karofa Road in Amalo Ward Kuresoi South Sub-County implemented | 3110499 | Construction of Roads - Other | HQ | HQ | -0.530098, 36.383684 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2023/24 | 11526000 | 11526000 | 11526000 | Equitable | N/A | 11526000 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Imarisha barabara. Assessor remarks: Good.
846 | Infrastructure, Development and Maintenance | Proposed Routine Maintenance And Spot Improvement Of Sigor-Emitik Road In Kiptagich Ward Kuresoi South Sub County | To undertake the proposed Routine Maintenance And Spot Improvement Of Sigor-Emitik Road In Kiptagich Ward Kuresoi South Sub County | Proposed Routine Maintenance And Spot Improvement Of Sigor-Emitik Road In Kiptagich Ward Kuresoi South Sub County implemented | 3110499 | Construction of Roads - Other | HQ | HQ | -0.530098, 36.383684 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2023/24 | 3498214 | 3498214 | 3498214 | Equitable | N/A | 3498214 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Imarisha barabara. Assessor remarks: Good.
847 | Infrastructure, Development and Maintenance | Proposed Routine Maintenance And Spot Improvement Of Singorwet-Konoin Road In Kiptagich Ward Kuresoi South Sub County | To undertake the proposed Routine Maintenance And Spot Improvement Of Singorwet-Konoin Road In Kiptagich Ward Kuresoi South Sub County | Proposed Routine Maintenance And Spot Improvement Of Singorwet-Konoin Road In Kiptagich Ward Kuresoi South Sub County implemented | 3110499 | Construction of Roads - Other | HQ | HQ | -0.530098, 36.383684 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2023/24 | 1998435 | 1998435 | 1998435 | Equitable | N/A | 1998435 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Imarisha barabara. Assessor remarks: Good.
848 | Infrastructure, Development and Maintenance | Proposed Routine Maintenance & Spot Improvement of Kabazi Centre - Hospital Road in Kabazi Ward Subukia Sub County | To undertake the proposed Routine Maintenance & Spot Improvement of Kabazi Centre - Hospital Road in Kabazi Ward Subukia Sub County | Proposed Routine Maintenance & Spot Improvement of Kabazi Centre - Hospital Road in Kabazi Ward Subukia Sub County implemented | 3110499 | Construction of Roads - Other | HQ | HQ | -0.530098, 36.383684 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2023/24 | 18032850 | 4963378.88 | 0 | Equitable | N/A | 0 | 4963378.88 | 5237600 | 105.5 | 5237600 | 5237600 | -274221.12 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Imarisha barabara. Assessor remarks: Good.
849 | Infrastructure, Development and Maintenance | Proposed Routine Maintenance & Spot Improvement of Keringet Market Road in Keringet Ward Kuresoi South Sub County | To undertake the proposed Routine Maintenance & Spot Improvement of Keringet Market Road in Keringet Ward Kuresoi South Sub County | Proposed Routine Maintenance & Spot Improvement of Keringet Market Road in Keringet Ward Kuresoi South Sub County implemented | 3110499 | Construction of Roads - Other | HQ | HQ | -0.530098, 36.383684 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2023/24 | 20610342 | 14401899 | 0 | Equitable | N/A | 0 | 14401899 | 0 | 0 | 0 | 0 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Imarisha barabara. Assessor remarks: Good.
850 | Infrastructure, Development and Maintenance | Proposed Routine Of Komoito- Tea Zone/Kap Tipis Line - Chebtebes Road H.Q Vote Head In Kiptagich Ward Naivasha Sub- County. | To undertake the proposed Routine Of Komoito- Tea Zone/Kap Tipis Line - Chebtebes Road H.Q Vote Head In Kiptagich Ward Naivasha Sub- County | Proposed Routine Of Komoito- Tea Zone/Kap Tipis Line - Chebtebes Road H.Q Vote Head In Kiptagich Ward Naivasha Sub- County implemented | 3110499 | Construction of Roads - Other | HQ | HQ | -0.530098, 36.383684 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2023/24 | 2812520 | 2812520 | 2812520 | Equitable | N/A | 2812520 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Imarisha barabara. Assessor remarks: Good.
851 | Infrastructure, Development and Maintenance | Proposed Spot Improvement of Kamemo Kirima Kahiga Tetu Kirengero Munanda Sidai Road AIC Maombi Primary Kwa Cucu and Kamumo Bridge (Gwa Karani Bridge) in Subukia Ward, Kabazi Ward and Waseges Ward Subukia Sub County | To undertake the proposed Spot Improvement of Kamemo Kirima Kahiga Tetu Kirengero Munanda Sidai Road AIC Maombi Primary Kwa Cucu and Kamumo Bridge (Gwa Karani Bridge) in Subukia Ward, Kabazi Ward and Waseges Ward Subukia Sub County | Proposed Spot Improvement of Kamemo Kirima Kahiga Tetu Kirengero Munanda Sidai Road AIC Maombi Primary Kwa Cucu and Kamumo Bridge (Gwa Karani Bridge) in Subukia Ward, Kabazi Ward and Waseges Ward Subukia Sub County implemented | 3110499 | Construction of Roads - Other | HQ | HQ | -0.530098, 36.383684 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2023/24 | 10501316 | 10501316 | 10501316 | Equitable | N/A | 10501316 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Imarisha barabara. Assessor remarks: Good.
852 | Proposed supply, installation, and commissioning of 5No. 13m Highmast at Biashara Ward Naivasha Sub county | Proposed supply, installation, and commissioning of 5No. 13m Highmast at Biashara Ward Naivasha Sub county | To undertake the proposed supply, installation, and commissioning of 5No. 13m Highmast at Biashara Ward Naivasha Sub county | Proposed supply, installation, and commissioning of 5No. 13m Highmast at Biashara Ward Naivasha Sub county implemented | 3110499 | Construction of Roads - Other | HQ | HQ | -0.502552, 36.367833 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2016/17 | 2100000 | 2100000 | 2100000 | Equitable | N/A | 2100000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Raylight. Assessor remarks: Operational.
853 | Infrastructure, Development and Maintenance | Proposed Tarmack of Molo Shop Frontage | To undertake the proposed Tarmack of Molo Shop Frontage | Proposed Tarmack of Molo Shop Frontage implemented | 3110499 | Construction of Roads - Other | HQ | HQ | -0.530098, 36.383684 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2023/24 | 8550740 | 5753895.53 | 0 | Equitable | N/A | 0 | 5753895.53 | 0 | 0 | 0 | 0 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Imarisha barabara. Assessor remarks: Good.
854 | Infrastructure, Development and Maintenance | Proposed Tarmacking of Elburgon Hospital Road in Elburgon Ward Molo Sub County | To undertake the proposed Tarmacking of Elburgon Hospital Road in Elburgon Ward Molo Sub County | Proposed Tarmacking of Elburgon Hospital Road in Elburgon Ward Molo Sub County implemented | 3110499 | Construction of Roads - Other | HQ | HQ | -0.530098, 36.383684 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2023/24 | 36465464 | 12792428.4 | 0 | Equitable | N/A | 0 | 12792428.4 | 0 | 0 | 0 | 0 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Imarisha barabara. Assessor remarks: Good.
855 | Infrastructure, Development and Maintenance | Proposed tarmacking of Salgaa Shopping Centre Access Road in Mosop Ward Rongai Sub-County | To undertake the proposed tarmacking of Salgaa Shopping Centre Access Road in Mosop Ward Rongai Sub-County | Proposed tarmacking of Salgaa Shopping Centre Access Road in Mosop Ward Rongai Sub-County implemented | 3110499 | Construction of Roads - Other | HQ | HQ | -0.530098, 36.383684 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2023/24 | 41177010 | 23538092.21 | 0 | Equitable | N/A | 0 | 23538092.21 | 0 | 0 | 0 | 0 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Imarisha barabara. Assessor remarks: Good.
856 | Infrastructure, Development and Maintenance | Rehabilitation of urban and rural access roads | To rehabilitate urban and rural access roads to restore functionality | Urban and rural access roads rehabilitated | 3110499 | Construction of Roads - Other | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 50502876 | 10000000 | 10000000 | Equitable | N/A | 10000000 | 0 | 10000000 | 100 | 10000000 | 85167 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
857 | Infrastructure, Development and Maintenance | Routine Maintenance and Spot Improvement :Tarmacking and Extension of Menengai Climb Road to Capital Hill Hotel (0.5km )in Nakuru East Sub County | To maintain Spot Improvement :Tarmacking and Extension of Menengai Climb Road to Capital Hill Hotel (0.5km )in Nakuru East Sub County in serviceable condition | Spot Improvement :Tarmacking and Extension of Menengai Climb Road to Capital Hill Hotel (0.5km )in Nakuru East Sub County maintained | 3110499 | Construction of Roads - Other | HQ | HQ | -0.530098, 36.383684 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2023/24 | 10504000 | 10504000 | 494717 | Equitable | N/A | 494717 | 0 | 5237600 | 49.9 | 5237600 | 5237600 | 5266400 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Imarisha barabara. Assessor remarks: Good.
858 | Infrastructure, Development & Maintenance | Grading and gravelling of Karai roads | To improve road infrastructure by grading and murraming Karai roads | Karai roads graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Hells Gate | -0.766414, 36.477187 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1828960 | 91.4 | 1828960 | 420062 | 171040 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Project cost 2,000,000.
859 | Infrastructure, Development and Maintenance | Grading And Murraming of Access Roads- Imarisha Barabara in Hells Gate Ward | To improve road infrastructure by grading and murraming Access Roads- Imarisha Barabara in Hells Gate Ward | Access Roads- Imarisha Barabara in Hells Gate Ward graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Hells Gate | -0.786009, 36.453805 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 6000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 4553540 | 91.1 | 4553540 | 446460 | 446460 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is accessible opening the area to having new structures.
860 | Infrastructure, Development & Maintenance | Grading and murraming of Laini Nyamathi primary road | To improve road infrastructure by grading and murraming Laini Nyamathi primary road | Laini Nyamathi primary road graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Hells Gate | -0.78745, 36.508636 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2418750 | 96.8 | 2418750 | 2500000 | 81250 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project was well done.
861 | Infrastructure, Development and Maintenance | Grading and murraming of Mirera Inn-Sanctuary Road | To improve road infrastructure by grading and murraming Mirera Inn-Sanctuary Road | Mirera Inn-Sanctuary Road graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Hells Gate | -0.786791, 36.451923 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 3752327 | 420062.35 | 420062.35 | Equitable | N/A | 420062.35 | 0 | 420062 | 100 | 420062 | 420062 | 0.35 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is passable and a boost to the community.
862 | Infrastructure, Development & Maintenance | Grading and murraming of Muita-Old Catholic | To improve road infrastructure by grading and murraming Muita-Old Catholic | Muita-Old Catholic graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Hells Gate | -0.788528, 36.439292 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2221807 | 88.9 | 2221807 | 420062 | 278193 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is accessible but needs light grading.
863 | Infrastructure, Development & Maintenance | Grading and murraming of Mwiciringiri mirera road | To improve road infrastructure by grading and murraming Mwiciringiri mirera road | Mwiciringiri mirera road graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Hells Gate | -0.820065, 36.513418 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2791040 | 93 | 2791040 | 3000000 | 208960 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: The road really needs rehabilitation and bush clearing.
864 | Infrastructure, Development and Maintenance | Grading And Murraming of Roads Through Imarisha Barabara Programme | To improve road infrastructure by grading and murraming Roads Through Imarisha Barabara Programme | Roads Through Imarisha Barabara Programme graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Hells Gate | -0.801873, 36.431582 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 4553540 | 0 | 4553540 | 446460 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: The project has not started.
865 | Infrastructure, Development & Maintenance | Grading and murraming of Sactuary Full Gospel road | To improve road infrastructure by grading and murraming Sactuary Full Gospel road | Sactuary Full Gospel road graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Hells Gate | -0.793857, 36.436324 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2282495 | 2282495 | 2282495 | Equitable | N/A | 2282495 | 0 | 2167320 | 95 | 2167320 | 2282495 | 115175 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is still accessible needs few spot filling.
866 | Infrastructure, Development and Maintenance | Grading, murraming and compaction of Dr Ngige road | To implement grading, murraming and compaction of dr ngige road for road connectivity and accessibility | Grading, murraming and compaction of Dr Ngige road completed | 3110499 | Construction of Roads - Other | Naivasha | Hells Gate | -0.787577, 36.450102 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 1768978 | 1768978 | Equitable | N/A | 1768978 | 0 | 1768978 | 100 | 1768978 | 1768978 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is passable a big help to the villages around.
867 | Infrastructure, Development and Maintenance | Grading, murraming and compaction of Miti mingi road | To implement grading, murraming and compaction of miti mingi road for road connectivity and accessibility | Grading, murraming and compaction of Miti mingi road completed | 3110499 | Construction of Roads - Other | Naivasha | Hells Gate | -0.787577, 36.450102 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 2233240 | 2233240 | Equitable | N/A | 2233240 | 0 | 2233240 | 100 | 2233240 | 2233240 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is passable a big help to the villages around.
868 | Infrastructure, Development and Maintenance | Grading, murraming and compaction of Mwafrika-Makutano road | To implement grading, murraming and compaction of mwafrika-makutano road for road connectivity and accessibility | Grading, murraming and compaction of Mwafrika-Makutano road completed | 3110499 | Construction of Roads - Other | Naivasha | Hells Gate | -0.787577, 36.450102 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 2215345 | 2215345 | Equitable | N/A | 2215345 | 0 | 2215345 | 100 | 2215345 | 2215345 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is passable a big help to the villages around.
869 | Infrastructure, Development and Maintenance | Grading, murraming and compaction of Polytechnic Nginga road | To implement grading, murraming and compaction of polytechnic nginga road for road connectivity and accessibility | Grading, murraming and compaction of Polytechnic Nginga road completed | 3110499 | Construction of Roads - Other | Naivasha | Hells Gate | -0.787577, 36.450102 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 1773909 | 1773909 | Equitable | N/A | 1773909 | 0 | 1773909 | 100 | 1773909 | 1773909 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is passable a big help to the villages around.
870 | Infrastructure, Development and Maintenance | Grading, murraming and compaction of Rubiri road | To implement grading, murraming and compaction of rubiri road for road connectivity and accessibility | Grading, murraming and compaction of Rubiri road completed | 3110499 | Construction of Roads - Other | Naivasha | Hells Gate | -0.787577, 36.450102 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 1795128 | 1795128 | Equitable | N/A | 1795128 | 0 | 1795128 | 100 | 1795128 | 1795128 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is passable a big help to the villages around.
871 | Infrastructure, Development and Maintenance | Hiring of machinery for maintenance of roads within Hells Gate Ward | To implement hiring of machinery for maintenance of roads within hells gate ward for road connectivity and accessibility | Hiring of machinery for maintenance of roads within Hells Gate Ward completed | 3110499 | Construction of Roads - Other | Naivasha | Hells Gate | -0.797312, 36.424472 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 6500000 | 6500000 | 6500000 | Equitable | N/A | 6500000 | 0 | 991800 | 15.3 | 991800 | 97990 | 5508200 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is now accessible unlike before.
872 | Infrastructure, Development and Maintenance | Hiring of maintenance equipment for road rehabilitation | To implement hiring of maintenance equipment for road rehabilitation for road connectivity and accessibility | Hiring of maintenance equipment for road rehabilitation completed | 3110499 | Construction of Roads - Other | Naivasha | Hells Gate | -0.799032, 36.423672 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 8000000 | 4079625 | 4079625 | Equitable | N/A | 4079625 | 0 | 3868213 | 94.8 | 3868213 | 211412 | 211412 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project was at a cost of 4,079,625.
873 | Infrastructure, Development & Maintenance | Proposed Routine Maintenance, Grading and Murraming of Hellsgate access road in Hells Gate Ward-Naivasha Sub County | To undertake the proposed Routine Maintenance, Grading and Murraming of Hellsgate access road in Hells Gate Ward-Naivasha Sub County | Proposed Routine Maintenance, Grading and Murraming of Hellsgate access road in Hells Gate Ward-Naivasha Sub County implemented | 3110499 | Construction of Roads - Other | Naivasha | Hells Gate | -0.787946, 36.439583 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 2873088 | 0 | 1527803.95 | Equitable | N/A | 1527803.95 | 0 | 3953280 | 100 | 3953280 | 1527804 | -3953280 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The Cost of the project was 1,527,804.
874 | Infrastructure, Development and Maintenance | Road rehabilitation - hire of machinery for road works | To implement road rehabilitation - hire of machinery for road works for road connectivity and accessibility | Road rehabilitation - hire of machinery for road works completed | 3110499 | Construction of Roads - Other | Naivasha | Hells Gate | -0.780264 36.444553 1948.199951171875 6.586999893188477 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 0 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Cost of the project 3,000,000.
875 | Infrastructure, Development and Maintenance | Road Rehabilitation-Hire Of Machineries For Road Works | To implement road rehabilitation-hire of machineries for road works for road connectivity and accessibility | Road Rehabilitation-Hire Of Machineries For Road Works completed | 3110499 | Construction of Roads - Other | Naivasha | Hells Gate | -0.771668 36.46336 1951.199951171875 5.129000186920166 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Project cost 3,000,000.
876 | Infrastructure, Development and Maintenance | Construction of Boda boda sheds in Kabatini | To construct Boda boda sheds in Kabatini | Boda boda sheds in Kabatini constructed | 3110499 | Construction of Roads - Other | Bahati | Kabatini | -0.216572 36.163938 2027.0999755859375 24.496999740600586 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 500000 | 0 | 499898 | Equitable | N/A | 499898 | 0 | 0 | 0 | 0 | 499898 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: M/s alidawn limited. Assessor remarks: The shade was demolished during fencing of the esp market.
877 | Infrastructure, Development & Maintenance | Grading and murraming of Engashura Gishagi road | To improve road infrastructure by grading and murraming Engashura Gishagi road | Engashura Gishagi road graded and murramed | 3110499 | Construction of Roads - Other | Bahati | Kabatini | -0.222688, 36.170243 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2020 | 2000000 | 1694982 | 1694982 | Equitable | N/A | 1694982 | 0 | 1694984 | 100 | 1694984 | 1694982 | -2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes then. Viable: Yes. Assessor remarks: The road is operational but requires routine maintenance and bush clearing.
878 | Infrastructure, Development and Maintenance | Grading and murraming through Imarisha barabara | To improve road infrastructure by grading and murraming through Imarisha barabara | Through Imarisha barabara graded and murramed | 3110499 | Construction of Roads - Other | Bahati | Kabatini | -0.231839, 36.148099 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2024 | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 1694984 | 100 | 1694984 | 1694982 | -1694984 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
879 | Infrastructure, Development & Maintenance | Grading, Gravelling and construction of drainage system at Kambo Road | To implement grading, gravelling and construction of drainage system at kambo road for road connectivity and accessibility | Grading, Gravelling and construction of drainage system at Kambo Road completed | 3110499 | Construction of Roads - Other | Bahati | Kabatini | -0.19033, 36.182873 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2018 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2000000 | 80 | 2000000 | 2500000 | 500000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Culverts functional but the drainage should be redone.
880 | Infrastructure, Development and Maintenance | Grading & Gravelling of Githioro Gichagi Road | To improve road accessibility by grading & Gravelling of Githioro Gichagi Road | & Gravelling of Githioro Gichagi Road graded | 3110499 | Construction of Roads - Other | Bahati | Kabatini | -0.23912 36.149773 1952.30859375 7.533999919891357 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 1100000 | 1100000 | 1100000 | Equitable | N/A | 1100000 | 0 | 877918 | 79.8 | 877918 | 222082 | 222082 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes by then. Viable: Yes. Assessor remarks: Road towards engashura primary is almost impassable needs routine maintenance , (bulk project).
881 | Infrastructure, Development and Maintenance | Grading & Gravelling of Mwaki Mugi Sub-Location Access Roads | To improve road accessibility by grading & Gravelling of Mwaki Mugi Sub-Location Access Roads | & Gravelling of Mwaki Mugi Sub-Location Access Roads graded | 3110499 | Construction of Roads - Other | Bahati | Kabatini | -0.21877, 36.122839 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2024 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 222082 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires routine maintenance and drainage.
882 | Infrastructure, Development and Maintenance | Hire of machinery for roads grading & rehabilitation | To implement hire of machinery for roads grading & rehabilitation for road connectivity and accessibility | Hire of machinery for roads grading & rehabilitation completed | 3110499 | Construction of Roads - Other | Bahati | Kabatini | -0.233983 36.154465 1965.599609375 11.258999824523926 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Yes by then. Viable: Yes. Assessor remarks: Road needs routine maintenance (bulk project).
883 | Infrastructure, Development and Maintenance | Installation of culverts at Zakaria access road and Murunyu Police post | To improve drainage and road access through culvert installation at Zakaria access road and Murunyu Police post | Culverts installed at Zakaria access road and Murunyu Police post | 3110499 | Construction of Roads - Other | Bahati | Kabatini | -0.216169 36.164536 2031.300048828125 77.5999984741211 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 400000 | 341470 | 341470 | Equitable | N/A | 341470 | 0 | 341470 | 100 | 341470 | 341470 | 0 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Partially. Viable: Yes. Contractor: Bitro construction ltd. Assessor remarks: Nawasco was handed over but there are unable to manage because of an ongoing court case,.
884 | Infrastructure, Development and Maintenance | Installation of streetlights across Kabatini ward | To improve lighting and safety through installation of solar streetlights at across Kabatini ward | Solar streetlights installed at across Kabatini ward | 3110499 | Construction of Roads - Other | Bahati | Kabatini | -0.230574, 36.163072 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2024 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 742900 | 49.5 | 742900 | 1500000 | 757100 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational, sensor should be checked.
885 | Infrastructure, Development & Maintenance | Murraming and grading of Kigera Road | To implement murraming and grading of kigera road for road connectivity and accessibility | Murraming and grading of Kigera Road completed | 3110499 | Construction of Roads - Other | Bahati | Kabatini | -0.202596, 36.158646 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2020 | 2500000 | 50.4 | 50.4 | Equitable | N/A | 50.4 | 0 | 2495370 | 4951131 | 2495370 | 50 | -2495319.6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s jateneve enterprises limited. Assessor remarks: Operational.
886 | Infrastructure, Development & Maintenance | Rehabilitation of Kabatini Ward Access Roads - Hire of Equipments, Machineries and murraming | To rehabilitate Kabatini Ward Access Roads - Hire of Equipments, Machineries and murraming to restore functionality | Kabatini Ward Access Roads - Hire of Equipments, Machineries and murraming rehabilitated | 3110499 | Construction of Roads - Other | Bahati | Kabatini | -0.237526, 36.151243 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2022 | 7000000 | 7000000 | 7000000 | Equitable | N/A | 7000000 | 0 | 6998830 | 100 | 6998830 | 0 | 1170 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The roads requires murraming and drainage.
887 | Infrastructure, Development and Maintenance | Rehabilitation of Roads in Kabatini (500 Fuel and 500 Purchase of murram) | To rehabilitate Roads in Kabatini (500 Fuel and 500 Purchase of murram) to restore functionality | Roads in Kabatini (500 Fuel and 500 Purchase of murram) rehabilitated | 3110499 | Construction of Roads - Other | Bahati | Kabatini | -0.228536, 36.151571 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2024 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: M/s popote Vivo. Assessor remarks: Operational.
888 | Enhancement Of Fuel (Murram And Machinery) | Enhancement Of Fuel (Murram And Machinery) | To implement enhancement of fuel (murram and machinery) for road connectivity and accessibility | Enhancement Of Fuel (Murram And Machinery) completed | 3110499 | Construction of Roads - Other | Subukia | Kabazi | -0.08223 36.16987 0 1381 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 3900000 | 2411560 | 2411560 | Equitable | N/A | 2411560 | 0 | 2410440 | 100 | 2410440 | 2411560 | 1120 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: Not indicated. Assessor remarks: Machine was brought but transferred to subukia Valley coffee factory.
889 | Infrastructure, Development and Maintenance | Grading and murraming of Akuisi-Berea Road | To improve road infrastructure by grading and murraming Akuisi-Berea Road | Akuisi-Berea Road graded and murramed | 3110499 | Construction of Roads - Other | Subukia | Kabazi | -0.1648, 36.127 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2025/26 | 4000000 | 4000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 3386875 | 84.7 | 3386875 | 3386875 | 613125 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: It's a viable project once completed. Contractor: Not indicated. Assessor remarks: Awaiting rain season to end for project to commence.
890 | Infrastructure, Development and Maintenance | Grading, murraming and culverting of roads in Kabazi through Imarisha Barabara programme | To implement grading, murraming and culverting of roads in kabazi through imarisha barabara programme for road connectivity and accessibility | Grading, murraming and culverting of roads in Kabazi through Imarisha Barabara programme completed | 3110499 | Construction of Roads - Other | Subukia | Kabazi | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 700600 | 35 | 700600 | 753183 | 1299400 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
891 | Infrastructure, Development & Maintenance | Grading, Murraming And Culverts Of Access Roads In Kabazi | To implement grading, murraming and culverts of access roads in kabazi for road connectivity and accessibility | Grading, Murraming And Culverts Of Access Roads In Kabazi completed | 3110499 | Construction of Roads - Other | Subukia | Kabazi | -0.100577 36.127123 0 296.77459716796875 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 3934983 | 753183 | 753183 | Equitable | N/A | 753183 | 0 | 700600 | 93 | 700600 | 753183 | 52583 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Requires drainage works.
892 | Infrastructure, Development and Maintenance | Hire of machinery and purchase of fuel for access roads across Kabazi Ward | To implement hire of machinery and purchase of fuel for access roads across kabazi ward for road connectivity and accessibility | Hire of machinery and purchase of fuel for access roads across Kabazi Ward completed | 3110499 | Construction of Roads - Other | Subukia | Kabazi | -0.100577 36.127123 0 296.77459716796875 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 4994812 | 4994812 | 4994812 | Equitable | N/A | 4994812 | 0 | 4994574 | 100 | 4994574 | 3386875 | 238 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Requires drainage works.
893 | Infrastructure, Development & Maintenance | Kabazi-Gitura Road Improvement | To implement kabazi-gitura road improvement for road connectivity and accessibility | Kabazi-Gitura Road Improvement completed | 3110499 | Construction of Roads - Other | Subukia | Kabazi | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 990100 | 990100 | Equitable | N/A | 990100 | 0 | 989405 | 99.9 | 989405 | 990100 | 695 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
894 | Infrastructure, Development & Maintenance | Kihoto, Kabazi Secondary And Maombi Roads Improvement | To implement kihoto, kabazi secondary and maombi roads improvement for road connectivity and accessibility | Kihoto, Kabazi Secondary And Maombi Roads Improvement completed | 3110499 | Construction of Roads - Other | Subukia | Kabazi | -0.09011, 36.16711 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2600000 | 2543700 | 2543700 | Equitable | N/A | 2543700 | 0 | 2543700 | 100 | 2543700 | 2543700 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Requires drainage works.
895 | Infrastructure, Development and Maintenance | Road Rehabiltation -Hire of Machinery and Purchase of fuel and murram for access roads across Kabazi Ward | To implement road rehabiltation -hire of machinery and purchase of fuel and murram for access roads across kabazi ward for road connectivity and accessibility | Road Rehabiltation -Hire of Machinery and Purchase of fuel and murram for access roads across Kabazi Ward completed | 3110499 | Construction of Roads - Other | Subukia | Kabazi | -0.100577 36.127123 0 296.77459716796875 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 4994811 | 4994811 | 4994811 | Equitable | N/A | 4994811 | 0 | 4513065 | 90.4 | 4513065 | 0 | 481746 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Requires drainage works.
896 | Infrastructure, Development & Maintenance | Construction of Muchorwe Miti Tano road | To construct Muchorwe Miti Tano road | Muchorwe Miti Tano road constructed | 3110499 | Construction of Roads - Other | Kuresoi North | Kamara | -0.07866 35.672895 2565.1 2.9000000953674316 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1125810 | 93.8 | 1125810 | 1200000 | 74190 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Tank provided. No pitlatrines.
897 | Infrastructure, Development and Maintenance | Grading & gravelling of Access roads through Imarisha barabara programme - hire of machinery within the Ward | To improve road accessibility by grading & gravelling of Access roads through Imarisha barabara programme - hire of machinery within the Ward | & gravelling of Access roads through Imarisha barabara programme - hire of machinery within the Ward graded | 3110499 | Construction of Roads - Other | Kuresoi North | Kamara | -0.08666 35.685103 2506.4 3.700000047683716 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Unknown. Assessor remarks: Needs maintenance.
898 | Infrastructure, Development & Maintenance | Grading, Murraming & Culveting Of Kimugul Leba, Baraka Shallom, Rironi-Twin, Chesuben -Kwa Aron, Casino, Kazamoyo-Dispensary, Kiboko-Kiwanja Ndege and sinendet Roads | To implement grading, murraming & culveting of kimugul leba, baraka shallom, rironi-twin, chesuben -kwa aron, casino, kazamoyo-dispensary, kiboko-kiwanja ndege and sinendet roads for road connectivity and accessibility | Grading, Murraming & Culveting Of Kimugul Leba, Baraka Shallom, Rironi-Twin, Chesuben -Kwa Aron, Casino, Kazamoyo-Dispensary, Kiboko-Kiwanja Ndege and sinendet Roads completed | 3110499 | Construction of Roads - Other | Kuresoi North | Kamara | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 6000000 | 212206 | 212206 | Equitable | N/A | 212206 | 0 | 212206 | 100 | 212206 | 212206 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
899 | Infrastructure, Development and Maintenance | Grading, murraming of Kabianga/Kiplelecho road | To implement grading, murraming of kabianga/kiplelecho road for road connectivity and accessibility | Grading, murraming of Kabianga/Kiplelecho road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Kamara | -0.134483, 35.60105 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 20th June, 2025 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 1491780 | 49.7 | 1491780 | 1500000 | 1508220 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: ARDENT LOGISTICS. Assessor remarks: Good work.
900 | Infrastructure, Development & Maintenance | Grading of new roads in Kamara ward | To improve road accessibility by grading new roads in Kamara ward | New roads in Kamara ward graded | 3110499 | Construction of Roads - Other | Kuresoi North | Kamara | -0.097348 35.675729 2535.7001953125 49.63999938964844 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1976750 | 98.8 | 1976750 | 2000000 | 23250 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Maintenance needed.
901 | Infrastructure, Development & Maintenance | Gravelling of Bureti road | To implement gravelling of bureti road for road connectivity and accessibility | Gravelling of Bureti road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Kamara | -0.091485 35.684655 2526.9 3.700000047683716 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1358004 | 1358004 | Equitable | N/A | 1358004 | 0 | 1358004 | 100 | 1358004 | 1358004 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Unknown. Assessor remarks: Needs maintenance.
902 | Infrastructure, Development & Maintenance | Gravelling of Choronok road | To implement gravelling of choronok road for road connectivity and accessibility | Gravelling of Choronok road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Kamara | -0.194323, 35.678015 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2021/23 | 1000000 | 973382.4 | 973382.4 | Equitable | N/A | 973382.4 | 0 | 866056 | 89 | 866056 | 973382 | 107326.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Unknown. Assessor remarks: The road needs recarpeting, culverts, drainage and expansion.
903 | Infrastructure, Development & Maintenance | Gravelling of Jogoo - Rironi road | To implement gravelling of jogoo - rironi road for road connectivity and accessibility | Gravelling of Jogoo - Rironi road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Kamara | -0.091485 35.684655 2526.9 3.700000047683716 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1357595 | 1357595 | Equitable | N/A | 1357595 | 0 | 1357595 | 100 | 1357595 | 1357595 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Unknown. Assessor remarks: Needs maintenance.
904 | Infrastructure, Development & Maintenance | Gravelling of Kabianga Koisegem road | To implement gravelling of kabianga koisegem road for road connectivity and accessibility | Gravelling of Kabianga Koisegem road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Kamara | -0.164543 35.706225 2567.9 4.5 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1491780 | 99.5 | 1491780 | 1500000 | 8220 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Partially. Viable: Yes. Contractor: Not indicated. Assessor remarks: Needs maintenance.
905 | Infrastructure, Development & Maintenance | Gravelling of Kamara mau road | To implement gravelling of kamara mau road for road connectivity and accessibility | Gravelling of Kamara mau road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Kamara | -0.132015 35.678952 2546 4.300000190734863 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1200000 | 100 | 1200000 | 1200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Not indicated. Assessor remarks: Needs maintenance. Poor drainage.
906 | Infrastructure, Development & Maintenance | Gravelling of Kamara road | To implement gravelling of kamara road for road connectivity and accessibility | Gravelling of Kamara road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Kamara | -0.132015 35.678952 2546 4.300000190734863 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Not indicated. Assessor remarks: Needs maintenance. Poor drainage.
907 | Infrastructure, Development & Maintenance | Gravelling of Kiptenden - Kabianga road | To implement gravelling of kiptenden - kabianga road for road connectivity and accessibility | Gravelling of Kiptenden - Kabianga road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Kamara | -0.084693 35.672665 2494 5.699999809265137 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 1500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Unknown. Assessor remarks: Needs maintenance.
908 | Gravelling of Koige Jogoo road | Gravelling of Koige Jogoo road | To implement gravelling of koige jogoo road for road connectivity and accessibility | Gravelling of Koige Jogoo road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Kamara | -0.165487, 35.712508 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 886760 | 886760 | Equitable | N/A | 886760 | 0 | 886760 | 100 | 886760 | 886760 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Unknown. Assessor remarks: Needs maintenance.
909 | Gravelling of Lower Haraka road | Gravelling of Lower Haraka road | To implement gravelling of lower haraka road for road connectivity and accessibility | Gravelling of Lower Haraka road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Kamara | -0.1489, 35.676812 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 200/21 | 1000000 | 919820 | 919820 | Equitable | N/A | 919820 | 0 | 919820 | 100 | 919820 | 919820 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Yes. Contractor: Unknown. Assessor remarks: Needs repairs and maintenance.
910 | Infrastructure, Development & Maintenance | Gravelling of Maraba road | To implement gravelling of maraba road for road connectivity and accessibility | Gravelling of Maraba road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Kamara | -0.132015 35.678952 2546 4.300000190734863 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 973114 | 973114 | Equitable | N/A | 973114 | 0 | 973114 | 100 | 973114 | 973114 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Not indicated. Assessor remarks: Needs maintenance. Poor drainage.
911 | Infrastructure, Development & Maintenance | Gravelling of Mau road | To implement gravelling of mau road for road connectivity and accessibility | Gravelling of Mau road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Kamara | -0.132015 35.678952 2546 4.300000190734863 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2348676 | 2247805 | 2247805 | Equitable | N/A | 2247805 | 0 | 2247805 | 100 | 2247805 | 2247805 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Not indicated. Assessor remarks: Needs maintenance. Poor drainage.
912 | Infrastructure, Development & Maintenance | Gravelling of Mau sub location road | To implement gravelling of mau sub location road for road connectivity and accessibility | Gravelling of Mau sub location road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Kamara | -0.17195 35.678957 2519.7999999999997 3.9000000953674316 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1285930 | 107.2 | 1285930 | 1200000 | -85930 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partialy. Contractor: ECLAT MERCHANTS LTD. Assessor remarks: Needs routine maintenance.
913 | Infrastructure, Development & Maintenance | Gravelling of Mau Summit road | To implement gravelling of mau summit road for road connectivity and accessibility | Gravelling of Mau Summit road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Kamara | -0.17195 35.678957 2519.7999999999997 3.9000000953674316 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 975311 | 975311 | Equitable | N/A | 975311 | 0 | 975311 | 100 | 975311 | 975311 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partialy. Contractor: ECLAT MERCHANTS LTD. Assessor remarks: Needs routine maintenance.
914 | Gravelling of Mititano and Boror road | Gravelling of Mititano and Boror road | To implement gravelling of mititano and boror road for road connectivity and accessibility | Gravelling of Mititano and Boror road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Kamara | -0.17527, 35.70579 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2015/16 | 1000000 | 974555 | 974555 | Equitable | N/A | 974555 | 0 | 974555 | 100 | 974555 | 974555 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Not indicated. Assessor remarks: Needs maintenance.
915 | Gravelling of Olenguruoni Kapsimo Two road | Gravelling of Olenguruoni Kapsimo Two road | To implement gravelling of olenguruoni kapsimo two road for road connectivity and accessibility | Gravelling of Olenguruoni Kapsimo Two road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Kamara | -0.084835, 35.671908 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 2386676 | 2386676 | Equitable | N/A | 2386676 | 0 | 2386676 | 100 | 2386676 | 2386676 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Unknown. Assessor remarks: Needs maintenance.
916 | Gravelling of Sigowet Kipsinendet road | Gravelling of Sigowet Kipsinendet road | To implement gravelling of sigowet kipsinendet road for road connectivity and accessibility | Gravelling of Sigowet Kipsinendet road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Kamara | -0.096665, 35.687013 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1445821 | 1445821 | Equitable | N/A | 1445821 | 0 | 1445821 | 100 | 1445821 | 1445821 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Not indicated. Assessor remarks: Needs repairs and maintenance.
917 | Infrastructure, Development & Maintenance | Gravelling of Tarakwet Kiwanja road | To implement gravelling of tarakwet kiwanja road for road connectivity and accessibility | Gravelling of Tarakwet Kiwanja road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Kamara | -0.162348, 35.691225 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2019/20 | 1000000 | 916337 | 916337 | Equitable | N/A | 916337 | 0 | 916337 | 100 | 916337 | 916337 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Assessor remarks: Needs maintenance.
918 | Gravelling of Twin Pick to Jogoo Road | Gravelling of Twin Pick to Jogoo Road | To implement gravelling of twin pick to jogoo road for road connectivity and accessibility | Gravelling of Twin Pick to Jogoo Road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Kamara | -0.17825 35.711258 2501.3 4.5 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 6063.1 | 6063.1 | Equitable | N/A | 6063.1 | 0 | 1492937 | 24623.3 | 1492937 | 6063 | -1486873.9 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Unknown. Assessor remarks: Needs maintenance.
919 | Infrastructure, Development and Maintenance | Hiring of equipments/machines for roadworks and land scaping | To implement hiring of equipments/machines for roadworks and land scaping for road connectivity and accessibility | Hiring of equipments/machines for roadworks and land scaping completed | 3110499 | Construction of Roads - Other | Kuresoi North | Kamara | -0.169962 35.689027 2522.8 13.899999618530273 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3754605 | 93.9 | 3754605 | 4000000 | 245395 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes if implemented. Assessor remarks: Needs to be started.
920 | Infrastructure, Development & Maintenance | Installation of culverts across Kamara ward | To improve drainage and road access through culvert installation at across Kamara ward | Culverts installed at across Kamara ward | 3110499 | Construction of Roads - Other | Kuresoi North | Kamara | -0.20148, 35.71698 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2020/21 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1976750 | 131.8 | 1976750 | 1500000 | -476750 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Not indicated. Assessor remarks: Needs maintenance.
921 | Infrastructure, Development & Maintenance | Re-carpeting of roads in Kamara ward | To upgrade roads in Kamara ward through tarmacking for improved road connectivity | Roads in Kamara ward tarmacked and upgraded | 3110499 | Construction of Roads - Other | Kuresoi North | Kamara | -0.097348 35.675729 2535.7001953125 49.63999938964844 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1800000 | 100 | 1800000 | 1800000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Maintenance needed.
922 | Infrastructure, Development and Maintenance | Construction & Improvement of Roads Through Imarisha Barabara Programme | To construct & Improvement of Roads Through Imarisha Barabara Programme | & Improvement of Roads Through Imarisha Barabara Programme constructed | 3110499 | Construction of Roads - Other | Nakuru West | Kapkures | -0.288288, 36.018474 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 1200000 | 0 | 480000 | Equitable | N/A | 480000 | 0 | 720000 | 100 | 720000 | 480000 | -720000 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Yes, for a moment. Viable: Yes. But needs drainage and Murraming. Assessor remarks: Road done but destroyed by rains again.
923 | Infrastructure, Development and Maintenance | Grading and murraming of feeder road at Slaughter house Kapkures center | To improve road infrastructure by grading and murraming feeder road at Slaughter house Kapkures center | Feeder road at Slaughter house Kapkures center graded and murramed | 3110499 | Construction of Roads - Other | Nakuru West | Kapkures | -0.306306, 36.036551 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 1500000 | 1465750 | 1465750 | Equitable | N/A | 1465750 | 0 | 1463700 | 99.9 | 1463700 | 2050 | 2050 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Viable. Improved transportation and mobility. Assessor remarks: Done but has been destroyed some sections by rains.
924 | Infrastructure, Development and Maintenance | Hire of Machinery and Bush Clearing at Kapkures Ward | To implement hire of machinery and bush clearing at kapkures ward for road connectivity and accessibility | Hire of Machinery and Bush Clearing at Kapkures Ward completed | 3110499 | Construction of Roads - Other | Nakuru West | Kapkures | -0.306306, 36.036551 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 1700000 | 0 | 1700000 | Equitable | N/A | 1700000 | 0 | 0 | 0 | 0 | 1700000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Viable. But has not been implemented. Assessor remarks: Has not yet been done.
925 | Infrastructure, Development and Maintenance | Grading and murraming of roads at rhonda resource center and quarry area | To improve road infrastructure by grading and murraming roads at rhonda resource center and quarry area | Roads at rhonda resource center and quarry area graded and murramed | 3110499 | Construction of Roads - Other | Nakuru West | Kaptembwo | -0.315356 36.052954 1787.300048828125 26.322999954223633 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 5500000 | 5500000 | 13000000 | Equitable | N/A | 13000000 | 0 | 1921309 | 34.9 | 1921309 | 5500000 | 3578691 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not yet started. Viable: Yes,once started it will ease mobility. Contractor: Not awarded. Assessor remarks: Not yet started.
926 | Infrastructure, Development and Maintenance | Gravelling and murraming of roads around Kaptembwo Community Resource Centre | To implement gravelling and murraming of roads around kaptembwo community resource centre for road connectivity and accessibility | Gravelling and murraming of roads around Kaptembwo Community Resource Centre completed | 3110499 | Construction of Roads - Other | Nakuru West | Kaptembwo | -0.317962, 36.053028 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2024/25 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1921309 | 96.1 | 1921309 | 78691 | 78691 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Viable since once complete will mobility. Assessor remarks: ONGOING PROJECT.
927 | Infrastructure, Development and Maintenance | Maintenance Of Drainage Systems across Kaptembwo Ward | To implement maintenance of drainage systems across kaptembwo ward for road connectivity and accessibility | Maintenance Of Drainage Systems across Kaptembwo Ward completed | 3110499 | Construction of Roads - Other | Nakuru West | Kaptembwo | -0.302447, 36.059036 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 2182000 | 2182000 | 2182000 | Equitable | N/A | 2182000 | 0 | 2100000 | 96.2 | 2100000 | 82000 | 82000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: It's a viable project it met the needs of the residents. Contractor: M/S LIRAYA ENTERPRISES. Assessor remarks: IN GOOD CONDITION.
928 | Infrastructure, Development and Maintenance | Grading And Murraming Duka Moja-Sise Road | To improve road infrastructure by grading and murraming Duka Moja-Sise Road | Duka Moja-Sise Road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Keringet | -0.479018, 35.701297 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2024 | 1600000 | 1600000 | 3200000 | Equitable | N/A | 3200000 | 0 | 1160100 | 72.5 | 1160100 | 1600000 | 439900 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Road is passible and in use.
929 | Infrastructure, Development and Maintenance | Grading And Murraming Mzee Moja Kaston Road | To improve road infrastructure by grading and murraming Mzee Moja Kaston Road | Mzee Moja Kaston Road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Keringet | -0.415935, 35.710202 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2025 | 1800000 | 0 | 1800000 | Equitable | N/A | 1800000 | 0 | 2013460 | 100 | 2013460 | 1800000 | -2013460 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Passable.
930 | Grading and murraming of Bandiat Manyibei Amab road | Grading and murraming of Bandiat Manyibei Amab road | To improve road infrastructure by grading and murraming Bandiat Manyibei Amab road | Bandiat Manyibei Amab road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Keringet | -0.521822, 35.733788 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1300000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 1160100 | 89.2 | 1160100 | 1300000 | 139900 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Passable.
931 | Infrastructure, Development and Maintenance | Grading and murraming of Cutline to Kibangui pri school road, Saptet polytechnic road to Daraja Mawe road, Kapsimbeiywo-Bondet road, Mosiat-Quarry-Bandiat road, Keringet-Bararget road, Tembwo-Tachasis road | To improve road infrastructure by grading and murraming Cutline to Kibangui pri school road, Saptet polytechnic road to Daraja Mawe road, Kapsimbeiywo-Bondet road, Mosiat-Quarry-Bandiat road, Keringet-Bararget road, Tembwo-Tachasis road | Cutline to Kibangui pri school road, Saptet polytechnic road to Daraja Mawe road, Kapsimbeiywo-Bondet road, Mosiat-Quarry-Bandiat road, Keringet-Bararget road, Tembwo-Tachasis road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Keringet | -0.303966, 36.082876 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 11600000 | 10530781.5 | 10530781.5 | Equitable | N/A | 10530781.5 | 0 | 10530782 | 100 | 10530782 | 10530782 | -0.5 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Passable.
932 | Infrastructure, Development & Maintenance | Grading and murraming of Kapkwen Kabungut Canaan road | To improve road infrastructure by grading and murraming Kapkwen Kabungut Canaan road | Kapkwen Kabungut Canaan road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Keringet | -0.463515, 35.71759 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2023 | 1600000 | 1466400 | 1466400 | Equitable | N/A | 1466400 | 0 | 1408514 | 96.1 | 1408514 | 1466400 | 57886 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Passable.
933 | Infrastructure, Development & Maintenance | Grading and murraming of Kapsimbeiwo Chepitet road | To improve road infrastructure by grading and murraming Kapsimbeiwo Chepitet road | Kapsimbeiwo Chepitet road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Keringet | -0.485568, 35.718275 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2022 | 1122417 | 925800 | 925800 | Equitable | N/A | 925800 | 0 | 891958 | 96.3 | 891958 | 925800 | 33842 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Passable.
934 | Infrastructure, Development and Maintenance | Grading And Murraming of Kosyin-Kapmathayo Road | To improve road infrastructure by grading and murraming Kosyin-Kapmathayo Road | Kosyin-Kapmathayo Road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Keringet | -0.427534, 35.689041 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2025 | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 2013460 | 100 | 2013460 | 1000000 | -2013460 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
935 | Infrastructure, Development and Maintenance | Grading and murraming of sachangwan-malingson roas | To improve road infrastructure by grading and murraming sachangwan-malingson roas | Sachangwan-malingson roas graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Keringet | -0.452768, 35.691671 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2023 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2974630 | 99.2 | 2974630 | 999532 | 25370 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
936 | Infrastructure, Development & Maintenance | Grading and murraming of Siongiroi Tertit, Lelaibei Kampi Chura road | To improve road infrastructure by grading and murraming Siongiroi Tertit, Lelaibei Kampi Chura road | Siongiroi Tertit, Lelaibei Kampi Chura road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Keringet | -0.516748, 35.732193 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1600000 | 1432200 | 1432200 | Equitable | N/A | 1432200 | 0 | 1413030 | 98.7 | 1413030 | 1432200 | 19170 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Passable.
937 | Infrastructure, Development and Maintenance | Grading and murraming of Sisei-Monoch-Jeremiah Road and Morusoi-Boturrah-Faith Church Road | To improve road infrastructure by grading and murraming Sisei-Monoch-Jeremiah Road and Morusoi-Boturrah-Faith Church Road | Sisei-Monoch-Jeremiah Road and Morusoi-Boturrah-Faith Church Road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Keringet | -0.50589, 35.698535 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2025 | 2800000 | 2800000 | 2800000 | Equitable | N/A | 2800000 | 0 | 891958 | 31.9 | 891958 | 925800 | 1908042 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
938 | Infrastructure, Development & Maintenance | Grading and murraming of Tendwetn Kiptenden Danger road | To improve road infrastructure by grading and murraming Tendwetn Kiptenden Danger road | Tendwetn Kiptenden Danger road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Keringet | -0.51114, 35.696668 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2023 | 2500000 | 2347500 | 2347500 | Equitable | N/A | 2347500 | 0 | 2212232 | 94.2 | 2212232 | 2347500 | 135268 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
939 | Infrastructure, Development & Maintenance | Grading and murraming of Teta Centre juu Shamba ndovu road | To improve road infrastructure by grading and murraming Teta Centre juu Shamba ndovu road | Teta Centre juu Shamba ndovu road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Keringet | -0.513345 35.705565 2677.8 9 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 2222025 | 92.6 | 2222025 | 1904300 | 177975 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
940 | Infrastructure, Development and Maintenance | Grading and murraming of Tulwet Jeptagum road | To improve road infrastructure by grading and murraming Tulwet Jeptagum road | Tulwet Jeptagum road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Keringet | -0.485652, 35.71835 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2024 | 2000000 | 1904300 | 1904300 | Equitable | N/A | 1904300 | 0 | 1904300 | 100 | 1904300 | 1904300 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
941 | Infrastructure, Development and Maintenance | Grading and murraming through Imarisha barabara | To improve road infrastructure by grading and murraming through Imarisha barabara | Through Imarisha barabara graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Keringet | -0.449577, 35.690528 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2025 | 5000000 | 5000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 4400000 | 88 | 4400000 | 999532 | 600000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
942 | Infrastructure, Development and Maintenance | Grading & murraming of Boarding Kapmatayo road | To improve road accessibility by grading & murraming of Boarding Kapmatayo road | & murraming of Boarding Kapmatayo road graded | 3110499 | Construction of Roads - Other | Kuresoi South | Keringet | -0.427534, 35.689041 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2025 | 3000000 | 0 | 986540 | Equitable | N/A | 986540 | 0 | 2013460 | 100 | 2013460 | 986540 | -2013460 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
943 | Infrastructure, Development and Maintenance | Grading & murraming of Kikingi Tatu to Bararget road | To improve road accessibility by grading & murraming of Kikingi Tatu to Bararget road | & murraming of Kikingi Tatu to Bararget road graded | 3110499 | Construction of Roads - Other | Kuresoi South | Keringet | -0.41001, 35.733117 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2024 | 4551797 | 4551797 | 4551797 | Equitable | N/A | 4551797 | 0 | 4488550 | 98.6 | 4488550 | 63247 | 63247 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
944 | Infrastructure, Development and Maintenance | Grading & murraming of Ndabibit Catholic to Ndabibit primary school road | To improve road accessibility by grading & murraming of Ndabibit Catholic to Ndabibit primary school road | & murraming of Ndabibit Catholic to Ndabibit primary school road graded | 3110499 | Construction of Roads - Other | Kuresoi South | Keringet | -0.45489, 35.688295 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2024 | 1000000 | 918600 | 918600 | Equitable | N/A | 918600 | 0 | 918600 | 100 | 918600 | 918600 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: Not yet started.
945 | Infrastructure, Development and Maintenance | Hire of equipments roads rehabilitation | To implement hire of equipments roads rehabilitation for road connectivity and accessibility | Hire of equipments roads rehabilitation completed | 3110499 | Construction of Roads - Other | Kuresoi South | Keringet | -0.546763 35.705472 2481.8 12.699999809265137 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 1500000 | 0 | 1500000 | Equitable | N/A | 1500000 | 0 | 4400000 | 100 | 4400000 | 4400000 | -4400000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not in operation.
946 | Infrastructure, Development & Maintenance | Hire of roadwork equipments at wet rate for road rehabilitation in Keringet ward | To implement hire of roadwork equipments at wet rate for road rehabilitation in keringet ward for road connectivity and accessibility | Hire of roadwork equipments at wet rate for road rehabilitation in Keringet ward completed | 3110499 | Construction of Roads - Other | Kuresoi South | Keringet | -0.43194, 35.708098 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2022 | 4400000 | 4400000 | 4400000 | Equitable | N/A | 4400000 | 0 | 4400000 | 100 | 4400000 | 4400000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Done.
947 | Infrastructure, Development & Maintenance | Hiring of wet road equipments | To implement hiring of wet road equipments for road connectivity and accessibility | Hiring of wet road equipments completed | 3110499 | Construction of Roads - Other | Kuresoi South | Keringet | -0.441352, 35.649258 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2022 | 1000050 | 1000050 | 1000050 | Equitable | N/A | 1000050 | 0 | 1000050 | 100 | 1000050 | 1000050 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yrs. Assessor remarks: Bad.
948 | Infrastructure, Development and Maintenance | Rehabilitation Of Bondok-Tembwet (Chebaraa) | To rehabilitate Bondok-Tembwet (Chebaraa) to restore functionality | Bondok-Tembwet (Chebaraa) rehabilitated | 3110499 | Construction of Roads - Other | Kuresoi South | Keringet | -0.478648, 35.678128 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2024 | 500000 | 0 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
949 | Infrastructure, Development and Maintenance | Rehabilitation Of Chabaraa-Sororik Road | To rehabilitate Chabaraa-Sororik Road to restore functionality | Chabaraa-Sororik Road rehabilitated | 3110499 | Construction of Roads - Other | Kuresoi South | Keringet | -0.464533, 35.677402 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2024 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
950 | Road rehabilitation (hire of machinery (wet rate) for rehabilitation of Keringet ward access roads) | Road rehabilitation (hire of machinery (wet rate) for rehabilitation of Keringet ward access roads) | To implement road rehabilitation (hire of machinery (wet rate) for rehabilitation of keringet ward access roads) for road connectivity and accessibility | Road rehabilitation (hire of machinery (wet rate) for rehabilitation of Keringet ward access roads) completed | 3110499 | Construction of Roads - Other | Kuresoi South | Keringet | -0.432205, 35.678418 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2021 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 3000000 | 100 | 3000000 | 3000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
951 | Infrastructure, Development & Maintenance | Grading and gravelling of Kaporus-Kapkali Road | To improve road infrastructure by grading and murraming Kaporus-Kapkali Road | Kaporus-Kapkali Road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Keringet | -0.544877, 35.703545 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2023 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 3000000 | 100 | 3000000 | 3000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
952 | Infrastructure, Development & Maintenance | Grading and murraming of Chepkubei road | To improve road infrastructure by grading and murraming Chepkubei road | Chepkubei road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Keringet | -0.421188, 35.696143 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2022 | 999532 | 999532 | 999532 | Equitable | N/A | 999532 | 0 | 999532 | 100 | 999532 | 999532 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yrs. Assessor remarks: Good.
953 | Infrastructure, Development & Maintenance | Grading and murraming of Tendwet Ngunyunyat road | To improve road infrastructure by grading and murraming Tendwet Ngunyunyat road | Tendwet Ngunyunyat road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Keringet | -0.501345, 35.701217 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2022 | 1199950 | 1199950 | 1199950 | Equitable | N/A | 1199950 | 0 | 1199950 | 100 | 1199950 | 1199950 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
954 | Infrastructure, Development & Maintenance | Gituamba sub location road works (grading, murraming, compacting and drainage works which are labour based Visavis hire of Equipments) | To implement gituamba sub location road works (grading, murraming, compacting and drainage works which are labour based visavis hire of equipments) for road connectivity and accessibility | Gituamba sub location road works (grading, murraming, compacting and drainage works which are labour based Visavis hire of Equipments) completed | 3110499 | Construction of Roads - Other | Bahati | Kiamaina | -0.252092, 36.134277 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 1694982.5 | 1694982.5 | Equitable | N/A | 1694982.5 | 0 | 1694983 | 100 | 1694983 | 1694983 | -0.5 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes being continuous maintenance. Assessor remarks: Roads maintenance.
955 | Infrastructure, Development and Maintenance | Grading And Murraming of Access Roads- Imarisha Barabara Programme in Kiamaina Ward | To improve road infrastructure by grading and murraming Access Roads- Imarisha Barabara Programme in Kiamaina Ward | Access Roads- Imarisha Barabara Programme in Kiamaina Ward graded and murramed | 3110499 | Construction of Roads - Other | Bahati | Kiamaina | -0.238165, 36.119615 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 5000000 | 0 | 2903610 | Equitable | N/A | 2903610 | 0 | 2400000 | 100 | 2400000 | 2903610 | -2400000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Routine maintenance.
956 | Infrastructure, Development and Maintenance | Grading and murraming of Haigwa access roads | To improve road infrastructure by grading and murraming Haigwa access roads | Haigwa access roads graded and murramed | 3110499 | Construction of Roads - Other | Bahati | Kiamaina | -0.253273, 36.138837 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 397325 | 0 | 397325 | 102675 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: A new road done last month.
957 | Infrastructure, Development and Maintenance | Hire Of Equipment For Road Maintenance | To implement hire of equipment for road maintenance for road connectivity and accessibility | Hire Of Equipment For Road Maintenance completed | 3110499 | Construction of Roads - Other | Bahati | Kiamaina | -0.231404 36.117086 1940.9000244140625 77.5999984741211 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 1600000 | 1600000 | 1600000 | Equitable | N/A | 1600000 | 0 | 1469300 | 91.8 | 1469300 | 130700 | 130700 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is currently in use.
958 | Infrastructure, Development and Maintenance | Hire of machinery for roads maintenance at Gituamba Sub Location in Kiamaina Ward | To implement hire of machinery for roads maintenance at gituamba sub location in kiamaina ward for road connectivity and accessibility | Hire of machinery for roads maintenance at Gituamba Sub Location in Kiamaina Ward completed | 3110499 | Construction of Roads - Other | Bahati | Kiamaina | -0.237255, 36.123055 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes the roads are passable. Viable: Yes. Assessor remarks: Ongoing project.
959 | Infrastructure, Development and Maintenance | Hire of machinery for roads maintenance at Kiamaina Sub Location in Kiamaina Ward | To implement hire of machinery for roads maintenance at kiamaina sub location in kiamaina ward for road connectivity and accessibility | Hire of machinery for roads maintenance at Kiamaina Sub Location in Kiamaina Ward completed | 3110499 | Construction of Roads - Other | Bahati | Kiamaina | -0.237255, 36.123055 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes the roads are passable. Viable: Yes. Assessor remarks: Ongoing project.
960 | Infrastructure, Development and Maintenance | Hire of machinery for roads maintenance at Menengai Sub Location in Kiamaina Ward | To implement hire of machinery for roads maintenance at menengai sub location in kiamaina ward for road connectivity and accessibility | Hire of machinery for roads maintenance at Menengai Sub Location in Kiamaina Ward completed | 3110499 | Construction of Roads - Other | Bahati | Kiamaina | -0.237255, 36.123055 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes the roads are passable. Viable: Yes. Assessor remarks: Ongoing project.
961 | Infrastructure, Development and Maintenance | Hire of machinery for roads maintenance at Rurii Sub Location in Kiamaina Ward | To implement hire of machinery for roads maintenance at rurii sub location in kiamaina ward for road connectivity and accessibility | Hire of machinery for roads maintenance at Rurii Sub Location in Kiamaina Ward completed | 3110499 | Construction of Roads - Other | Bahati | Kiamaina | -0.237255, 36.123055 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes the roads are passable. Viable: Yes. Assessor remarks: Ongoing project.
962 | Infrastructure, Development and Maintenance | Hire of machinery for roads maintenance at Workers Sub Location in Kiamaina Ward | To implement hire of machinery for roads maintenance at workers sub location in kiamaina ward for road connectivity and accessibility | Hire of machinery for roads maintenance at Workers Sub Location in Kiamaina Ward completed | 3110499 | Construction of Roads - Other | Bahati | Kiamaina | -0.237255, 36.123055 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes the roads are passable. Viable: Yes. Assessor remarks: Ongoing project.
963 | Infrastructure, Development and Maintenance | Installation of 5 No streetlights in Kiamaina Sub Location | To install 5 No streetlights in Kiamaina Sub Location | 5 No streetlights in Kiamaina Sub Location installed | 3110499 | Construction of Roads - Other | Bahati | Kiamaina | -0.231527, 36.116893 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 2250000 | 0 | 2250000 | Equitable | N/A | 2250000 | 0 | 1170025 | 100 | 1170025 | 29975 | -1170025 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Not yet done. Assessor remarks: The project is yet to start.
964 | Infrastructure, Development and Maintenance | Installation of 5 No streetlights in Rurii Sub Location | To install 5 No streetlights in Rurii Sub Location | 5 No streetlights in Rurii Sub Location installed | 3110499 | Construction of Roads - Other | Bahati | Kiamaina | -0.231527, 36.116893 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 2250000 | 0 | 2250000 | Equitable | N/A | 2250000 | 0 | 1149621 | 100 | 1149621 | 2400000 | -1149621 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Not yet done. Assessor remarks: The project is yet to start.
965 | Infrastructure, Development and Maintenance | Installation of 5 No streetlights in Upper Menengai Sub Location and Upper Kiamaina Sub Location | To install 5 No streetlights in Upper Menengai Sub Location and Upper Kiamaina Sub Location | 5 No streetlights in Upper Menengai Sub Location and Upper Kiamaina Sub Location installed | 3110499 | Construction of Roads - Other | Bahati | Kiamaina | -0.246687 36.095885 2189.800048828125 5.699999809265137 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 2250000 | 0 | 2250000 | Equitable | N/A | 2250000 | 0 | 1170025 | 100 | 1170025 | 29975 | -1170025 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Lights functioning.
966 | Infrastructure, Development and Maintenance | Installation of 5 No streetlights in Workers Sub Location | To install 5 No streetlights in Workers Sub Location | 5 No streetlights in Workers Sub Location installed | 3110499 | Construction of Roads - Other | Bahati | Kiamaina | -0.231527, 36.116893 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 2250000 | 0 | 2250000 | Equitable | N/A | 2250000 | 0 | 1170025 | 100 | 1170025 | 2400000 | -1170025 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Not yet done. Assessor remarks: The project is yet to start.
967 | Infrastructure, Development and Maintenance | Installation of 6 No streetlights in Gituamba Sub Location | To install 6 No streetlights in Gituamba Sub Location | 6 No streetlights in Gituamba Sub Location installed | 3110499 | Construction of Roads - Other | Bahati | Kiamaina | -0.231527, 36.116893 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 2700000 | 0 | 2700000 | Equitable | N/A | 2700000 | 0 | 1149621 | 100 | 1149621 | 50379 | -1149621 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Not yet done. Assessor remarks: The project is yet to start.
968 | Infrastructure, Development and Maintenance | Installation of 9 No streetlights in Menengai Sub Location | To install 9 No streetlights in Menengai Sub Location | 9 No streetlights in Menengai Sub Location installed | 3110499 | Construction of Roads - Other | Bahati | Kiamaina | -0.231527, 36.116893 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 4050000 | 0 | 4050000 | Equitable | N/A | 4050000 | 0 | 1149621 | 100 | 1149621 | 2400000 | -1149621 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Not yet done. Assessor remarks: The project is yet to start.
969 | Infrastructure, Development & Maintenance | Kiamaina sub location road works (grading, murraming, compacting and drainage works which are labour based Visavis hire of Equipments) | To implement kiamaina sub location road works (grading, murraming, compacting and drainage works which are labour based visavis hire of equipments) for road connectivity and accessibility | Kiamaina sub location road works (grading, murraming, compacting and drainage works which are labour based Visavis hire of Equipments) completed | 3110499 | Construction of Roads - Other | Bahati | Kiamaina | -0.252092, 36.134277 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2500000 | 100 | 2500000 | 2500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes being continuous maintenance. Assessor remarks: Roads maintenance.
970 | Infrastructure, Development & Maintenance | Kiamaina Ward Roads Rehabilitation and labour Based Drainage Works - Hiring of Machinery and equipment | To implement kiamaina ward roads rehabilitation and labour based drainage works - hiring of machinery and equipment for road connectivity and accessibility | Kiamaina Ward Roads Rehabilitation and labour Based Drainage Works - Hiring of Machinery and equipment completed | 3110499 | Construction of Roads - Other | Bahati | Kiamaina | -0.246042 36.117933 1898.300048828125 7 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 4999515 | 100 | 4999515 | 0 | 485 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Routine maintenance.
971 | Infrastructure, Development & Maintenance | Menengai sub location road works (grading, murraming, compacting and drainage works which are labour based Visavis hire of Equipments) | To implement menengai sub location road works (grading, murraming, compacting and drainage works which are labour based visavis hire of equipments) for road connectivity and accessibility | Menengai sub location road works (grading, murraming, compacting and drainage works which are labour based Visavis hire of Equipments) completed | 3110499 | Construction of Roads - Other | Bahati | Kiamaina | -0.252092, 36.134277 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2500000 | 100 | 2500000 | 2500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes being continuous maintenance. Assessor remarks: Roads maintenance.
972 | Infrastructure, Development and Maintenance | Murraming And Compaction Of Mchanganyiko Access Roads | To implement murraming and compaction of mchanganyiko access roads for road connectivity and accessibility | Murraming And Compaction Of Mchanganyiko Access Roads completed | 3110499 | Construction of Roads - Other | Bahati | Kiamaina | -0.261981 36.105315 1904.5999755859375 58.125999450683594 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 397325 | 79.5 | 397325 | 102675 | 102675 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires routine maintenance.
973 | Infrastructure, Development and Maintenance | Murraming and compaction of Mchanganyiko access road | To implement murraming and compaction of mchanganyiko access road for road connectivity and accessibility | Murraming and compaction of Mchanganyiko access road completed | 3110499 | Construction of Roads - Other | Bahati | Kiamaina | -0.261981 36.105315 1904.5999755859375 58.125999450683594 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 397325 | 79.5 | 397325 | 500000 | 102675 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires routine maintenance.
974 | Infrastructure, Development and Maintenance | Purchase of culverts for emergency drainage mitigations in the ward | To procure culverts for emergency drainage mitigations in the ward | Culverts for emergency drainage mitigations in the ward procured | 3110499 | Construction of Roads - Other | Bahati | Kiamaina | -0.231627 36.116888 1940.699951171875 39.599998474121094 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 752037 | 752037 | 752037 | Equitable | N/A | 752037 | 0 | 750000 | 99.7 | 750000 | 752037 | 2037 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Not yet done. Assessor remarks: The project is yet to start.
975 | Purchase of murram for Kiamaina roads projects | Purchase of murram for Kiamaina roads projects | To procure murram for Kiamaina roads projects | Murram for Kiamaina roads projects procured | 3110499 | Construction of Roads - Other | Bahati | Kiamaina | -0.231544, 36.116881 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 500000 | 0 | 500000 | Equitable | N/A | 500000 | 0 | 500000 | 100 | 500000 | 500000 | -500000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The murram was used for Kiamaina access roads.
976 | Infrastructure, Development & Maintenance | Rurii sub location road works (grading, murraming, compacting and drainage works which are labour based Visavis hire of Equipments) | To implement rurii sub location road works (grading, murraming, compacting and drainage works which are labour based visavis hire of equipments) for road connectivity and accessibility | Rurii sub location road works (grading, murraming, compacting and drainage works which are labour based Visavis hire of Equipments) completed | 3110499 | Construction of Roads - Other | Bahati | Kiamaina | -0.252092, 36.134277 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2500000 | 100 | 2500000 | 2500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes being continuous maintenance. Assessor remarks: Roads maintenance.
977 | Infrastructure, Development & Maintenance | Workers sub location road works (grading, murraming, compacting and drainage works which are labour based Visavis hire of Equipments) | To implement workers sub location road works (grading, murraming, compacting and drainage works which are labour based visavis hire of equipments) for road connectivity and accessibility | Workers sub location road works (grading, murraming, compacting and drainage works which are labour based Visavis hire of Equipments) completed | 3110499 | Construction of Roads - Other | Bahati | Kiamaina | -0.252092, 36.134277 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2496750 | 99.9 | 2496750 | 2500000 | 3250 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes being continuous maintenance. Assessor remarks: Roads maintenance.
978 | Infrastructure, Development and Maintenance | Culverts installation | To implement culverts installation for road connectivity and accessibility | Culverts installation completed | 3110499 | Construction of Roads - Other | Njoro | Kihingo | -0.4793 35.978443 2296.400146484375 20 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 1000000 | 964560 | 964560 | Equitable | N/A | 964560 | 0 | 959922 | 99.5 | 959922 | 964560 | 4638 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Maintenance.
979 | Infrastructure, Development and Maintenance | Grading And Murraming of Access Roads- Imarisha Barabara in Kihingo Ward | To improve road infrastructure by grading and murraming Access Roads- Imarisha Barabara in Kihingo Ward | Access Roads- Imarisha Barabara in Kihingo Ward graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Kihingo | -0.454165, 35.975353 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2024 | 500000 | 0 | 200000 | Equitable | N/A | 200000 | 0 | 300000 | 100 | 300000 | 200000 | -300000 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Partially. Viable: Partially. Assessor remarks: Bad condition.
980 | Infrastructure, Development and Maintenance | Grading and Murraming of Kabaka, Mutirima road, Waka Road and Kabaka road Old Mutiume to Mugomoini to Mutumbura road and Wendani Mugumoini to Mutumburu road | To improve road infrastructure by grading and murraming Kabaka, Mutirima road, Waka Road and Kabaka road Old Mutiume to Mugomoini to Mutumbura road and Wendani Mugumoini to Mutumburu road | Kabaka, Mutirima road, Waka Road and Kabaka road Old Mutiume to Mugomoini to Mutumbura road and Wendani Mugumoini to Mutumburu road graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Kihingo | -0.437727, 35.980398 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2024 | 7500000 | 5107560 | 5107560 | Equitable | N/A | 5107560 | 0 | 5106265 | 100 | 5106265 | 1295 | 1295 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires maintenance.
981 | Infrastructure, Development & Maintenance | Grading And Murraming Of Maranatha Gwa Kimwaki Road | To improve road infrastructure by grading and murraming Maranatha Gwa Kimwaki Road | Maranatha Gwa Kimwaki Road graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Kihingo | -0.476213 35.988603 2288 17.100000381469727 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2500000 | 100 | 2500000 | 2500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: At that time yes. Viable: Yes. Assessor remarks: Requires bush clearing grading murraming and compaction.
982 | Infrastructure, Development and Maintenance | Grading, Murraming And Compaction Of Access Road In Kihingo And Machinery | To implement grading, murraming and compaction of access road in kihingo and machinery for road connectivity and accessibility | Grading, Murraming And Compaction Of Access Road In Kihingo And Machinery completed | 3110499 | Construction of Roads - Other | Njoro | Kihingo | -0.498422, 35.998627 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2024 | 2368382 | 2368382 | 2368382 | Equitable | N/A | 2368382 | 0 | 2368382 | 100 | 2368382 | 2368382 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Maintenance.
983 | Infrastructure, Development & Maintenance | Grading, Murraming And Compaction Of Stoo Mbili Munanda Mutiume Road | To implement grading, murraming and compaction of stoo mbili munanda mutiume road for road connectivity and accessibility | Grading, Murraming And Compaction Of Stoo Mbili Munanda Mutiume Road completed | 3110499 | Construction of Roads - Other | Njoro | Kihingo | -0.45582 35.983998 2286.60009765625 13.199999809265137 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 1500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires maintenance.
984 | Infrastructure, Development and Maintenance | Grading, Murraming & compaction of access roads in Kihingo Ward | To implement grading, murraming & compaction of access roads in kihingo ward for road connectivity and accessibility | Grading, Murraming & compaction of access roads in Kihingo Ward completed | 3110499 | Construction of Roads - Other | Njoro | Kihingo | -0.498422, 35.998627 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2024 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2368382 | 78.9 | 2368382 | 2368382 | 631618 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Maintenance.
985 | Infrastructure, Development & Maintenance | Hire Of Equipments For Road Works | To implement hire of equipments for road works for road connectivity and accessibility | Hire Of Equipments For Road Works completed | 3110499 | Construction of Roads - Other | Njoro | Kihingo | -0.458195 35.977055 2338.8 12.800000190734863 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 3000000 | 100 | 3000000 | 3000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: DAKES CONTRACTOR. Assessor remarks: Requires maintenance.
986 | Infrastructure, Development & Maintenance | Hire of road work equipments in Zone A | To implement hire of road work equipments in zone a for road connectivity and accessibility | Hire of road work equipments in Zone A completed | 3110499 | Construction of Roads - Other | Njoro | Kihingo | -0.45226 35.996057 2172.8999999999996 4.900000095367432 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2498726 | 99.9 | 2498726 | 2373502 | 1274 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: DAKES CONTRACTOR. Assessor remarks: Requires maintenance.
987 | Infrastructure, Development & Maintenance | Hire of road work equipments in Zone B | To implement hire of road work equipments in zone b for road connectivity and accessibility | Hire of road work equipments in Zone B completed | 3110499 | Construction of Roads - Other | Njoro | Kihingo | -0.45226 35.996057 2172.8999999999996 4.900000095367432 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2499486 | 100 | 2499486 | 2373502 | 514 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: DAKES CONTRACTOR. Assessor remarks: Requires maintenance.
988 | Infrastructure, Development & Maintenance | Hire of road work equipments in Zone C | To implement hire of road work equipments in zone c for road connectivity and accessibility | Hire of road work equipments in Zone C completed | 3110499 | Construction of Roads - Other | Njoro | Kihingo | -0.45226 35.996057 2172.8999999999996 4.900000095367432 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2499825 | 100 | 2499825 | 2373502 | 175 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: DAKES CONTRACTOR. Assessor remarks: Requires maintenance.
989 | Infrastructure, Development & Maintenance | Hire of road work equipments in Zone D | To implement hire of road work equipments in zone d for road connectivity and accessibility | Hire of road work equipments in Zone D completed | 3110499 | Construction of Roads - Other | Njoro | Kihingo | -0.45226 35.996057 2172.8999999999996 4.900000095367432 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2499955 | 100 | 2499955 | 2373502 | 45 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: DAKES CONTRACTOR. Assessor remarks: Requires maintenance.
990 | Infrastructure, Development & Maintenance | Hire of road work equipments in Zone E | To implement hire of road work equipments in zone e for road connectivity and accessibility | Hire of road work equipments in Zone E completed | 3110499 | Construction of Roads - Other | Njoro | Kihingo | -0.45226 35.996057 2172.8999999999996 4.900000095367432 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2499969 | 100 | 2499969 | 2373502 | 31 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: DAKES CONTRACTOR. Assessor remarks: Requires maintenance.
991 | Infrastructure, Development & Maintenance | Hire Of Road Works Equipments | To implement hire of road works equipments for road connectivity and accessibility | Hire Of Road Works Equipments completed | 3110499 | Construction of Roads - Other | Njoro | Kihingo | -0.458195 35.977055 2338.8 12.800000190734863 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2373502 | 2373502 | 2373502 | Equitable | N/A | 2373502 | 0 | 2373502 | 100 | 2373502 | 2373502 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: DAKES CONTRACTOR. Assessor remarks: Requires maintenance.
992 | Infrastructure, Development and Maintenance | Hiring of machineries for roads rehabilitation | To implement hiring of machineries for roads rehabilitation for road connectivity and accessibility | Hiring of machineries for roads rehabilitation completed | 3110499 | Construction of Roads - Other | Njoro | Kihingo | -0.45226 35.996057 2172.8999999999996 4.900000095367432 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 3758350 | 0 | 3758350 | Equitable | N/A | 3758350 | 0 | 8022670 | 100 | 8022670 | 377330 | -8022670 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: DAKES CONTRACTOR. Assessor remarks: Requires maintenance.
993 | Infrastructure, Development and Maintenance | Hiring of machineries for roads works rehabilitation in Kihingo Ward | To implement hiring of machineries for roads works rehabilitation in kihingo ward for road connectivity and accessibility | Hiring of machineries for roads works rehabilitation in Kihingo Ward completed | 3110499 | Construction of Roads - Other | Njoro | Kihingo | -0.474192 35.992925 2289.7 13.357000350952148 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 8400000 | 8400000 | 8400000 | Equitable | N/A | 8400000 | 0 | 8022670 | 95.5 | 8022670 | 377330 | 377330 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires maintenance.
994 | Infrastructure, Development and Maintenance | Roads rehabilitation through Imarisha barabara programme | To implement roads rehabilitation through imarisha barabara programme for road connectivity and accessibility | Roads rehabilitation through Imarisha barabara programme completed | 3110499 | Construction of Roads - Other | Njoro | Kihingo | -0.502697 36.010552 2271.3999999999996 3 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2024/25 | 5000000 | 5000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 5000000 | 100 | 5000000 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: Partially. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Not started.
995 | Stoo Mbili Access Roads | Stoo Mbili Access Roads | To implement stoo mbili access roads for road connectivity and accessibility | Stoo Mbili Access Roads completed | 3110499 | Construction of Roads - Other | Njoro | Kihingo | -0.458195 35.977055 2338.8 12.800000190734863 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1521944 | 1334321 | 1334321 | Equitable | N/A | 1334321 | 0 | 0 | 0 | 0 | 1334321 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: DAKES CONTRACTOR. Assessor remarks: Requires maintenance.
996 | Infrastructure, Development & Maintenance | Supply Of Murram For Roads | To implement supply of murram for roads for road connectivity and accessibility | Supply Of Murram For Roads completed | 3110499 | Construction of Roads - Other | Njoro | Kihingo | -0.458195 35.977055 2338.8 12.800000190734863 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: DAKES CONTRACTOR. Assessor remarks: Requires maintenance.
997 | Infrastructure, Development and Maintenance | Grading and gravelling of Chebotoi- Kibirech road | To improve road infrastructure by grading and murraming Chebotoi- Kibirech road | Chebotoi- Kibirech road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Kiptagich | -0.552683, 35.635952 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 980159 | 980159 | Equitable | N/A | 980159 | 0 | 980159 | 100 | 980159 | 980159 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and needs met. Assessor remarks: Functional.
998 | Infrastructure, Development and Maintenance | Grading and murraming of Banana Road | To improve road infrastructure by grading and murraming Banana Road | Banana Road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Kiptagich | -0.592928, 35.636138 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2023 | 1000000 | 914725 | 914725 | Equitable | N/A | 914725 | 0 | 914725 | 100 | 914725 | 914725 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and meets the needs of the residents. Contractor: Don't know. Assessor remarks: The project is complete and functional.
999 | Infrastructure, Development and Maintenance | Grading and murraming of Cheptuech-Kabungunot-Cheptebes Road | To improve road infrastructure by grading and murraming Cheptuech-Kabungunot-Cheptebes Road | Cheptuech-Kabungunot-Cheptebes Road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Kiptagich | -0.591147 35.645857 2486.2999999999997 8.399999618530273 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 3000000 | 2674430 | 2674430 | Equitable | N/A | 2674430 | 0 | 2674430 | 100 | 2674430 | 2674430 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes and needs met. Assessor remarks: In good condition.
1000 | Infrastructure, Development and Maintenance | Grading and murraming of Gikamba road | To improve road infrastructure by grading and murraming Gikamba road | Gikamba road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Kiptagich | -0.592928, 35.636138 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2023 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 3972828 | 794.6 | 3972828 | 500000 | -3472828 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and meets the needs of the residents. Contractor: Don't know. Assessor remarks: The project is complete and functional.
1001 | Infrastructure, Development and Maintenance | Grading and murraming of Irongo saoset | To improve road infrastructure by grading and murraming Irongo saoset | Irongo saoset graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Kiptagich | -0.586868 35.6182 2503.6 22.5 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 1500000 | 1322625 | 1322625 | Equitable | N/A | 1322625 | 0 | 1322625 | 100 | 1322625 | 1322625 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and needs met. Assessor remarks: In good condition.
1002 | Infrastructure, Development & Maintenance | Grading and murraming of Kapcheluoch-Tea Zone Road | To improve road infrastructure by grading and murraming Kapcheluoch-Tea Zone Road | Kapcheluoch-Tea Zone Road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Kiptagich | -0.643788, 35.602347 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2022 | 1000000 | 995085 | 995085 | Equitable | N/A | 995085 | 0 | 995085 | 100 | 995085 | 995085 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable but high rainfall is a challenge and doesn't adequately meet the needs of the residents. Contractor: Don't know. Assessor remarks: The project is complete but high rainfall is destroying it.
1003 | Infrastructure, Development and Maintenance | Grading and murraming of Kelungula-Saptonok road | To improve road infrastructure by grading and murraming Kelungula-Saptonok road | Kelungula-Saptonok road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Kiptagich | -0.58695 35.617962 2455.6 24.299999237060547 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 1000000 | 999662 | 999662 | Equitable | N/A | 999662 | 0 | 999662 | 100 | 999662 | 999662 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes, it is viable. Contractor: Don't know. Assessor remarks: The project is good and it is operational.
1004 | Infrastructure, Development and Maintenance | Grading and murraming of Kipkongor road | To improve road infrastructure by grading and murraming Kipkongor road | Kipkongor road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Kiptagich | -0.592928, 35.636138 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2023 | 1000000 | 999425 | 999425 | Equitable | N/A | 999425 | 0 | 984690 | 98.5 | 984690 | 999425 | 14735 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and meets the needs of the residents. Contractor: Don't know. Assessor remarks: The project is complete and functional.
1005 | Infrastructure, Development and Maintenance | Grading and murraming of Kipsunyan-Lelchwet-Emitik Road | To improve road infrastructure by grading and murraming Kipsunyan-Lelchwet-Emitik Road | Kipsunyan-Lelchwet-Emitik Road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Kiptagich | -0.639332, 35.59822 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 1500000 | 1293325 | 1293325 | Equitable | N/A | 1293325 | 0 | 1293325 | 100 | 1293325 | 1293325 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: No. Viable: Yes but needs not met. Assessor remarks: Good during dry session but poor during Rainy season.
1006 | Infrastructure, Development & Maintenance | Grading and murraming of Kiptagich center access roads | To improve road infrastructure by grading and murraming Kiptagich center access roads | Kiptagich center access roads graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Kiptagich | -0.570045, 35.622817 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2022 | 1429390 | 1399000 | 1399000 | Equitable | N/A | 1399000 | 0 | 1363704 | 97.5 | 1363704 | 1399000 | 35296 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and meets the residents needs. Contractor: Don't know. Assessor remarks: The project is complete and functional.
1007 | Infrastructure, Development and Maintenance | Grading and murraming of Koisegut-Ainamoi Road | To improve road infrastructure by grading and murraming Koisegut-Ainamoi Road | Koisegut-Ainamoi Road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Kiptagich | -0.592928, 35.636138 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2023 | 2000000 | 1998080 | 1998080 | Equitable | N/A | 1998080 | 0 | 1954250 | 97.8 | 1954250 | 1998080 | 43830 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and meets the needs of the residents. Contractor: Don't know. Assessor remarks: The project is complete and functional.
1008 | Infrastructure, Development and Maintenance | Grading And Murraming of Kokwet Oromoit Feeder Roads | To improve road infrastructure by grading and murraming Kokwet Oromoit Feeder Roads | Kokwet Oromoit Feeder Roads graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Kiptagich | -0.608392 35.600555 2382.4 90.5 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 3568147 | 100 | 3568147 | 2000000 | -3568147 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes, it meets the needs of the residents. Contractor: Don't know. Assessor remarks: The road needs to be repaired.
1009 | Infrastructure, Development and Maintenance | Grading and murraming of Lelpanga road | To improve road infrastructure by grading and murraming Lelpanga road | Lelpanga road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Kiptagich | -0.592928, 35.636138 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2023 | 1000000 | 999425 | 999425 | Equitable | N/A | 999425 | 0 | 988500 | 98.9 | 988500 | 999425 | 10925 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and meets the needs of the residents. Contractor: Don't know. Assessor remarks: The project is complete and functional.
1010 | Infrastructure, Development and Maintenance | Grading and murraming of mlango road | To improve road infrastructure by grading and murraming mlango road | Mlango road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Kiptagich | -0.592928, 35.636138 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2023 | 750000 | 365913 | 365913 | Equitable | N/A | 365913 | 0 | 322102 | 88 | 322102 | 365913 | 43811 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and meets the needs of the residents. Contractor: Don't know. Assessor remarks: The project is complete and functional.
1011 | Infrastructure, Development and Maintenance | Grading and Murraming of Mulango, Kipsogon Cheptagum SDA, Kibirech, Kapwilly-Saoset Pri-Chungurdi road | To improve road infrastructure by grading and murraming Mulango, Kipsogon Cheptagum SDA, Kibirech, Kapwilly-Saoset Pri-Chungurdi road | Mulango, Kipsogon Cheptagum SDA, Kibirech, Kapwilly-Saoset Pri-Chungurdi road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Kiptagich | -0.598296, 35.639386 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2024 | 4800000 | 4800000 | 4800000 | Equitable | N/A | 4800000 | 0 | 4663250 | 97.2 | 4663250 | 136750 | 136750 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes and it meets the residents needs. Contractor: Don't know. Assessor remarks: The project is complete and functional.
1012 | Infrastructure, Development and Maintenance | Grading and murraming of Saoset chebotoi road | To improve road infrastructure by grading and murraming Saoset chebotoi road | Saoset chebotoi road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Kiptagich | -0.608392 35.600555 2382.4 90.5 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 999500 | 999500 | Equitable | N/A | 999500 | 0 | 999120 | 100 | 999120 | 999500 | 380 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes, it meets the needs of the residents. Contractor: Don't know. Assessor remarks: The road needs to be repaired.
1013 | Infrastructure, Development and Maintenance | Grading and murraming of saoset road | To improve road infrastructure by grading and murraming saoset road | Saoset road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Kiptagich | -0.592928, 35.636138 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2023 | 1000000 | 977715 | 977715 | Equitable | N/A | 977715 | 0 | 977715 | 100 | 977715 | 977715 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and meets the needs of the residents. Contractor: Don't know. Assessor remarks: The project is complete and functional.
1014 | Infrastructure, Development & Maintenance | Grading and murraming of Saptet-Kiptagich-Kapchesimet Road | To improve road infrastructure by grading and murraming Saptet-Kiptagich-Kapchesimet Road | Saptet-Kiptagich-Kapchesimet Road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Kiptagich | -0.571085 35.613306 2486.000244140625 14.100000381469727 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 1999849 | 1999849 | Equitable | N/A | 1999849 | 0 | 1998833 | 99.9 | 1998833 | 1999849 | 1016 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and meets the residents needs. Contractor: Don't know. Assessor remarks: The project is complete and functional.
1015 | Infrastructure, Development and Maintenance | Grading and murraming of SDA cheptuech-segutek cheptebes | To improve road infrastructure by grading and murraming SDA cheptuech-segutek cheptebes | SDA cheptuech-segutek cheptebes graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Kiptagich | -0.591147 35.645857 2486.2999999999997 8.399999618530273 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 4800000 | 0 | 4708000 | Equitable | N/A | 4708000 | 0 | 2674430 | 100 | 2674430 | 4708000 | -2674430 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes and needs met. Assessor remarks: In good condition.
1016 | Infrastructure, Development and Maintenance | Grading and murraming of Suburb Bondet road | To improve road infrastructure by grading and murraming Suburb Bondet road | Suburb Bondet road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Kiptagich | -0.592928, 35.636138 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2023 | 800000 | 799600 | 799600 | Equitable | N/A | 799600 | 0 | 799595 | 100 | 799595 | 799600 | 5 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and meets the needs of the residents. Contractor: Don't know. Assessor remarks: The project is complete and functional.
1017 | Infrastructure, Development and Maintenance | Grading and murraming of Wamgong road | To improve road infrastructure by grading and murraming Wamgong road | Wamgong road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Kiptagich | -0.592928, 35.636138 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2023 | 800000 | 799201 | 799201 | Equitable | N/A | 799201 | 0 | 799970 | 100.1 | 799970 | 799201 | -769 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and meets the needs of the residents. Contractor: Don't know. Assessor remarks: The project is complete and functional.
1018 | Infrastructure, Development and Maintenance | Grading and murraming of Wamkong Road | To improve road infrastructure by grading and murraming Wamkong Road | Wamkong Road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Kiptagich | -0.592928, 35.636138 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2023 | 1500000 | 1359675 | 1359675 | Equitable | N/A | 1359675 | 0 | 1359675 | 100 | 1359675 | 1359675 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and meets the needs of the residents. Contractor: Don't know. Assessor remarks: The project is complete and functional.
1019 | Infrastructure, Development and Maintenance | Grading and murraming of Zakai Soi Ararwet road | To improve road infrastructure by grading and murraming Zakai Soi Ararwet road | Zakai Soi Ararwet road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Kiptagich | -0.58695 35.617962 2455.6 24.299999237060547 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 800000 | 799700 | 799700 | Equitable | N/A | 799700 | 0 | 799201 | 99.9 | 799201 | 799700 | 499 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes, it is viable. Contractor: Don't know. Assessor remarks: The project is good and it is operational.
1020 | Infrastructure, Development and Maintenance | Hiring of Machineries for Imarisha barabara (Silot Siele, Kibirech and Maramara road) | To implement hiring of machineries for imarisha barabara (silot siele, kibirech and maramara road) for road connectivity and accessibility | Hiring of Machineries for Imarisha barabara (Silot Siele, Kibirech and Maramara road) completed | 3110499 | Construction of Roads - Other | Kuresoi South | Kiptagich | -0.551298 35.636388 2541.1 14.300000190734863 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and needs met. Assessor remarks: Functional.
1021 | Infrastructure, Development & Maintenance | Kiptagich Roads rehabilitation (hire of machinery and equipments) | To implement kiptagich roads rehabilitation (hire of machinery and equipments) for road connectivity and accessibility | Kiptagich Roads rehabilitation (hire of machinery and equipments) completed | 3110499 | Construction of Roads - Other | Kuresoi South | Kiptagich | -0.51523 35.718283 2655.3 4.599999904632568 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 0 | 0 | 0 | 800000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yrs. Assessor remarks: Pump failed.
1022 | Infrastructure, Development and Maintenance | Construction Of Amani-Sundu River Road | To construct Amani-Sundu River Road | Amani-Sundu River Road constructed | 3110499 | Construction of Roads - Other | Kuresoi North | Kiptororo | -0.324981, 35.546804 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 1272998 | 100 | 1272998 | 3000000 | -1272998 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The work was done but needs maintainance.
1023 | Infrastructure, Development and Maintenance | Construction Of Chorwa - Cheptemomnok Feeder Road | To construct Chorwa - Cheptemomnok Feeder Road | Chorwa - Cheptemomnok Feeder Road constructed | 3110499 | Construction of Roads - Other | Kuresoi North | Kiptororo | -0.302533 35.5297 0 800 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 0 | Stalled | 75 | N/A | Defaulf notice 1&2 | 2023 | N/A | N/A | Yes | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yess but without toilet it will be closed by pho. Assessor remarks: The banda is complete without paint and the area pho has issued notice for construction of a toilet.
1024 | Infrastructure, Development and Maintenance | Construction Of Dandora -Chepkoburot Feeder Road | To construct Dandora -Chepkoburot Feeder Road | Dandora -Chepkoburot Feeder Road constructed | 3110499 | Construction of Roads - Other | Kuresoi North | Kiptororo | -0.300981 35.531995 2587.10009765625 60 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 1272998 | 100 | 1272998 | 3000000 | -1272998 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Due for repair. Viable: Yes. Assessor remarks: Floor improvement.
1025 | Infrastructure, Development and Maintenance | Construction Of Ogilge-Nakiririet Road | To construct Ogilge-Nakiririet Road | Ogilge-Nakiririet Road constructed | 3110499 | Construction of Roads - Other | Kuresoi North | Kiptororo | -0.377203 35.505747 0 800 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 1500000 | 1500000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 1500000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The bridge was constructed but no gurd rails.
1026 | Infrastructure, Development and Maintenance | Construction Of Sundu River -Chebonde Road | To construct Sundu River -Chebonde Road | Sundu River -Chebonde Road constructed | 3110499 | Construction of Roads - Other | Kuresoi North | Kiptororo | -0.324981, 35.546804 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The work was done but needs maintainance.
1027 | Infrastructure, Development & Maintenance | Grading and gravelling of Kipkewa-Kiamashama road | To improve road infrastructure by grading and murraming Kipkewa-Kiamashama road | Kipkewa-Kiamashama road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi North | Kiptororo | -0.325623, 35.503235 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1459962 | 1448643 | 1448643 | Equitable | N/A | 1448643 | 0 | 1448643 | 100 | 1448643 | 1448643 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: It requires routine maintenance,and additional culvert.
1028 | Infrastructure, Development and Maintenance | Grading And Murraming of Access Roads- Imarisha Barabara in Kiptororo Ward | To improve road infrastructure by grading and murraming Access Roads- Imarisha Barabara in Kiptororo Ward | Access Roads- Imarisha Barabara in Kiptororo Ward graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi North | Kiptororo | -0.351533 35.471193 2449 6.199999809265137 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 1400000 | 0 | 600000 | Equitable | N/A | 600000 | 0 | 900000 | 100 | 900000 | 600000 | -900000 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Spor improvement and culvert installation works are due.
1029 | Infrastructure, Development and Maintenance | Grading and murraming of Frankways - Tarangonik - Githima road | To improve road infrastructure by grading and murraming Frankways - Tarangonik - Githima road | Frankways - Tarangonik - Githima road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi North | Kiptororo | -0.296035, 35.506105 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1931400 | 96.6 | 1931400 | 3000000 | 68600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: No. Viable: Yes. Assessor remarks: Routine maintenance and spot improvement is required.poor drainage.
1030 | Infrastructure, Development & Maintenance | Grading and murraming of Githima factory-Frankyway roads | To improve road infrastructure by grading and murraming Githima factory-Frankyway roads | Githima factory-Frankyway roads graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi North | Kiptororo | -0.351533 35.471193 2449 6.199999809265137 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 1802235 | 1802235 | Equitable | N/A | 1802235 | 0 | 1801260 | 99.9 | 1801260 | 1802235 | 975 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Spor improvement and culvert installation works are due.
1031 | Infrastructure, Development and Maintenance | Grading and murraming of Keo primary-Kapkilel road | To improve road infrastructure by grading and murraming Keo primary-Kapkilel road | Keo primary-Kapkilel road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi North | Kiptororo | -0.29459, 35.493035 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1459962 | 1459962 | Equitable | N/A | 1459962 | 0 | 1459962 | 100 | 1459962 | 1459962 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Routine maintenance is required.
1032 | Infrastructure, Development and Maintenance | Grading and murraming of Kongoi-Chebuiyet-kiplongony road | To improve road infrastructure by grading and murraming Kongoi-Chebuiyet-kiplongony road | Kongoi-Chebuiyet-kiplongony road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi North | Kiptororo | -0.324487, 35.545722 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 1459962 | 100 | 1459962 | 3000000 | -1459962 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Routine maintenance and spot improvement is required.
1033 | Infrastructure, Development and Maintenance | Grading and murraming of Kongoi-Kio, Chemare-Bartakatiet, Ogilgei-Bochege and Chumbek-Mororbei road through Imarisha programme | To improve road infrastructure by grading and murraming Kongoi-Kio, Chemare-Bartakatiet, Ogilgei-Bochege and Chumbek-Mororbei road through Imarisha programme | Kongoi-Kio, Chemare-Bartakatiet, Ogilgei-Bochege and Chumbek-Mororbei road through Imarisha programme graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi North | Kiptororo | -0.380313 35.508142 0 1399.9990234375 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 8800000 | 8800000 | 8800000 | Equitable | N/A | 8800000 | 0 | 7684500 | 87.3 | 7684500 | 0 | 1115500 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road work was done.
1034 | Infrastructure, Development and Maintenance | Grading and murraming of Kures- Bartagatiet road | To improve road infrastructure by grading and murraming Kures- Bartagatiet road | Kures- Bartagatiet road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi North | Kiptororo | -0.396168, 35.491532 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 1459962 | 100 | 1459962 | 3000000 | -1459962 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Routine maintenance and spot improvement is required.
1035 | Infrastructure, Development and Maintenance | Grading and murraming of Kuresoi Tea - Kio primary road | To improve road infrastructure by grading and murraming Kuresoi Tea - Kio primary road | Kuresoi Tea - Kio primary road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi North | Kiptororo | -0.29459, 35.493035 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1459962 | 146 | 1459962 | 1000000 | -459962 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Routine maintenance is required.
1036 | Infrastructure, Development & Maintenance | Grading and Murraming of Mutapa Githima Road, Mwaragania-Weromere Road, Chorwa-Githima Road, Kongoi Amani Center Road, Muhirori Sawmill and Rehoboth Church Road, Githima -Kapmobii Kones Road | To improve road infrastructure by grading and murraming Mutapa Githima Road, Mwaragania-Weromere Road, Chorwa-Githima Road, Kongoi Amani Center Road, Muhirori Sawmill and Rehoboth Church Road, Githima -Kapmobii Kones Road | Mutapa Githima Road, Mwaragania-Weromere Road, Chorwa-Githima Road, Kongoi Amani Center Road, Muhirori Sawmill and Rehoboth Church Road, Githima -Kapmobii Kones Road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi North | Kiptororo | -0.301051, 35.520304 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | N/A | 9639850 | 0 | 2831790 | Equitable | N/A | 2831790 | 0 | 6484120 | 100 | 6484120 | 2831790 | -6484120 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yess. Viable: Yess. Assessor remarks: The road is possible,only need expansion and calverts.
1037 | Infrastructure, Development and Maintenance | Grading And Murraming of Roads Through Imarisha Barabara Programme | To improve road infrastructure by grading and murraming Roads Through Imarisha Barabara Programme | Roads Through Imarisha Barabara Programme graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi North | Kiptororo | -0.385728, 35.498835 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 900000 | 100 | 900000 | 600000 | -900000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Regular maintenance of the road is required.
1038 | Infrastructure, Development & Maintenance | Grading, murraming and compaction of Githima banda to Kapsiele road | To implement grading, murraming and compaction of githima banda to kapsiele road for road connectivity and accessibility | Grading, murraming and compaction of Githima banda to Kapsiele road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Kiptororo | -0.302533, 35.5297 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1600000 | 1418630 | 1418630 | Equitable | N/A | 1418630 | 0 | 1418630 | 100 | 1418630 | 1418630 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Requires maintenance.
1039 | Infrastructure, Development and Maintenance | Grading, murraming and compaction of Kio centre - Githima dispensary road | To implement grading, murraming and compaction of kio centre - githima dispensary road for road connectivity and accessibility | Grading, murraming and compaction of Kio centre - Githima dispensary road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Kiptororo | -0.302533, 35.5297 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1200000 | 100 | 1200000 | 1200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In a good stare.
1040 | Infrastructure, Development and Maintenance | Grading, murraming and compaction of Migingo Taragonie village road | To implement grading, murraming and compaction of migingo taragonie village road for road connectivity and accessibility | Grading, murraming and compaction of Migingo Taragonie village road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Kiptororo | -0.307553, 35.489587 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1600000 | 1379382 | 1379382 | Equitable | N/A | 1379382 | 0 | 1379382 | 100 | 1379382 | 1379382 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Yes. Assessor remarks: Routine maintenance and spot improvement is required.
1041 | Infrastructure, Development and Maintenance | Hiring of machineries for road works | To implement hiring of machineries for road works for road connectivity and accessibility | Hiring of machineries for road works completed | 3110499 | Construction of Roads - Other | Kuresoi North | Kiptororo | -0.361215 35.460108 2439.3999999999996 4.599999904632568 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3500000 | 100 | 3500000 | 3500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Routine maintenance and spot improvement works required. Culvert instalation for three sections to improve on drainages..
1042 | Kiptororo Roads rehabilitation (Hire of machinery and equipments) | Kiptororo Roads rehabilitation (Hire of machinery and equipments) | To implement kiptororo roads rehabilitation (hire of machinery and equipments) for road connectivity and accessibility | Kiptororo Roads rehabilitation (Hire of machinery and equipments) completed | 3110499 | Construction of Roads - Other | Kuresoi North | Kiptororo | -0.377203, 35.505747 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 1200323 | 1200323 | 1200323 | Equitable | N/A | 1200323 | 0 | 0 | 0 | 0 | 1200323 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project was completed.
1043 | Infrastructure, Development & Maintenance | Expansion Of Shuleni Tarmac Road In Kivumbini Ward | To expand Shuleni Tarmac Road In Kivumbini Ward to increase capacity | Shuleni Tarmac Road In Kivumbini Ward expanded | 3110499 | Construction of Roads - Other | Nakuru East | Kivumbini | -0.304157, 36.082921 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | july 2022 | 5600001 | 2133064 | 2133064 | Equitable | N/A | 2133064 | 0 | 2132182 | 100 | 2132182 | 2133064 | 882 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: yes,. Viable: yes. Assessor remarks: chipped with potholes.
1044 | Infrastructure, Development and Maintenance | Grading and murraming of Kivumbini roads through imarisha barabara | To improve road infrastructure by grading and murraming Kivumbini roads through imarisha barabara | Kivumbini roads through imarisha barabara graded and murramed | 3110499 | Construction of Roads - Other | Nakuru East | Kivumbini | -0.29865 36.082456 1786.699951171875 72.9000015258789 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Improved transportation.
1045 | Infrastructure, Development and Maintenance | Hire of machinery for grading and murraming of Kivumbini roads | To implement hire of machinery for grading and murraming of kivumbini roads for road connectivity and accessibility | Hire of machinery for grading and murraming of Kivumbini roads completed | 3110499 | Construction of Roads - Other | Nakuru East | Kivumbini | -0.294222, 36.090869 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | June 2025 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yed. Viable: Yes. Assessor remarks: Improved accessibility within the ward.
1046 | Infrastructure, Development and Maintenance | Murraming and drainages Of Road Joining Mumias Road in Lower Makuti Area | To implement murraming and drainages of road joining mumias road in lower makuti area for road connectivity and accessibility | Murraming and drainages Of Road Joining Mumias Road in Lower Makuti Area completed | 3110499 | Construction of Roads - Other | Nakuru East | Kivumbini | -0.29865 36.082456 1786.699951171875 72.9000015258789 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3119134 | 89.1 | 3119134 | 380867 | 380866 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Improved transportation.
1047 | Infrastructure, Development & Maintenance | Re- Tarmacking Of Roads In Kivumbini Ward | To implement re- tarmacking of roads in kivumbini ward for road connectivity and accessibility | Re- Tarmacking Of Roads In Kivumbini Ward completed | 3110499 | Construction of Roads - Other | Nakuru East | Kivumbini | -0.304117, 36.082753 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | july2022 | 2400000 | 2001400 | 2001400 | Equitable | N/A | 2001400 | 0 | 2100500 | 105 | 2100500 | 2001400 | -99100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes,provided access to other areas. Assessor remarks: functional but particularly chipped.
1048 | Infrastructure, Development and Maintenance | Grading and murraming of Kayole Road | To improve road infrastructure by grading and murraming Kayole Road | Kayole Road graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Lake View | -0.762495, 36.464028 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 10000000 | 10000000 | 10000000 | Equitable | N/A | 10000000 | 0 | 2961419 | 29.6 | 2961419 | 38581 | 7038581 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good status.
1049 | Infrastructure, Development and Maintenance | Grading and murraming of Lake View access roads | To improve road infrastructure by grading and murraming Lake View access roads | Lake View access roads graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Lake View | -0.726785, 36.439953 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 6000000 | 6000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 2961419 | 49.4 | 2961419 | 5000353 | 3038581 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
1050 | Infrastructure, Development and Maintenance | Grading and Murraming of maili mbili estate roads | To improve road infrastructure by grading and murraming maili mbili estate roads | Maili mbili estate roads graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Lake View | -0.749043, 36.443726 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2961419 | 98.7 | 2961419 | 38581 | 38581 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
1051 | Infrastructure, Development and Maintenance | Grading and Murraming of Roads in Kihoto Area | To improve road infrastructure by grading and murraming Roads in Kihoto Area | Roads in Kihoto Area graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Lake View | -0.729055, 36.431492 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 1700000 | 3700000 | 3700000 | Equitable | N/A | 3700000 | 0 | 3700000 | 100 | 3700000 | 38581 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Some parts are submerged by water.
1052 | Infrastructure, Development and Maintenance | Grading, Murraming and Installation of Culverts at Lower Kayole (Unity) And Upper Kayole | To implement grading, murraming and installation of culverts at lower kayole (unity) and upper kayole for road connectivity and accessibility | Grading, Murraming and Installation of Culverts at Lower Kayole (Unity) And Upper Kayole completed | 3110499 | Construction of Roads - Other | Naivasha | Lake View | -0.765318, 36.451464 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 2500000 | 4500000 | 4500000 | Equitable | N/A | 4500000 | 0 | 4054953 | 90.1 | 4054953 | 445047 | 445047 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes but it’s not in good state. Viable: Ues. Assessor remarks: Need rehabilitation and culverts.
1053 | Infrastructure, Development and Maintenance | Grading, Murraming at Kayole Area Access Roads | To implement grading, murraming at kayole area access roads for road connectivity and accessibility | Grading, Murraming at Kayole Area Access Roads completed | 3110499 | Construction of Roads - Other | Naivasha | Lake View | -0.733738, 36.432899 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 5000353 | 0 | 5000353 | Equitable | N/A | 5000353 | 0 | 2961419 | 100 | 2961419 | 5000353 | -2961419 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Usable though some place are submerged.
1054 | Infrastructure, Development and Maintenance | Hire of Machinery for roads rehabilitation | To implement hire of machinery for roads rehabilitation for road connectivity and accessibility | Hire of Machinery for roads rehabilitation completed | 3110499 | Construction of Roads - Other | Naivasha | Lake View | -0.734358, 36.445651 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
1055 | Infrastructure, Development and Maintenance | Rehabilitation of police line road in Lakeview ward | To rehabilitate police line road in Lakeview ward to restore functionality | Police line road in Lakeview ward rehabilitated | 3110499 | Construction of Roads - Other | Naivasha | Lake View | -0.724505, 36.430771 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 5/8/2025 | 5000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 1105480 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Kagua prime limited. Assessor remarks: Complete.
1056 | Construction of motor bikes sheds in Lakeview ward | Construction of motor bikes sheds in Lakeview ward | To construct motor bikes sheds in Lakeview ward | Motor bikes sheds in Lakeview ward constructed | 3110499 | Construction of Roads - Other | Naivasha | Lakeview | -0.728236, 36.443564 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1495485 | 99.7 | 1495485 | 1500000 | 4515 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
1057 | Infrastructure, Development & Maintenance | Grading and gravelling of Catholic, PCEA and game roaf at unity farm | To improve road infrastructure by grading and murraming Catholic, PCEA and game roaf at unity farm | Catholic, PCEA and game roaf at unity farm graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Lakeview | -0.747324, 36.44922 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2249090 | 90 | 2249090 | 2500000 | 250910 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In use but need rehabilitation.
1058 | Infrastructure, Development & Maintenance | Grading and gravelling of dumping Road at unity | To improve road infrastructure by grading and murraming dumping Road at unity | Dumping Road at unity graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Lakeview | -0.762495, 36.464028 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 3396260 | 356233 | 356233 | Equitable | N/A | 356233 | 0 | 356233 | 100 | 356233 | 356233 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
1059 | Infrastructure, Development and Maintenance | Grading and gravelling of Kihoto access road | To improve road infrastructure by grading and murraming Kihoto access road | Kihoto access road graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Lakeview | -0.731075, 36.440704 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 2970792 | 84.9 | 2970792 | 3500000 | 529208 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs drainage system.
1060 | Infrastructure, Development and Maintenance | Grading and gravelling of Lakeview estates Road | To improve road infrastructure by grading and murraming Lakeview estates Road | Lakeview estates Road graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Lakeview | -0.726785, 36.439953 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 1784364 | 1784364 | 1784364 | Equitable | N/A | 1784364 | 0 | 1605550 | 90 | 1605550 | 1784364 | 178814 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
1061 | Grading and gravelling of Landing beach and Manera road | Grading and gravelling of Landing beach and Manera road | To improve road infrastructure by grading and murraming Landing beach and Manera road | Landing beach and Manera road graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Lakeview | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2229750 | 89.2 | 2229750 | 2500000 | 270250 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1062 | Grading and gravelling of Shamahoho Road at Kayole | Grading and gravelling of Shamahoho Road at Kayole | To improve road infrastructure by grading and murraming Shamahoho Road at Kayole | Shamahoho Road at Kayole graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Lakeview | -0.753103, 36.461344 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 648088 | 92.6 | 648088 | 700000 | 51912 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Accessible.
1063 | Infrastructure, Development & Maintenance | Grading and gravelling of Suberico Road in Lakeview ward | To improve road infrastructure by grading and murraming Suberico Road in Lakeview ward | Suberico Road in Lakeview ward graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Lakeview | -0.726585, 36.443845 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1454811 | 1454811 | 1454811 | Equitable | N/A | 1454811 | 0 | 1313000 | 90.3 | 1313000 | 1454811 | 141811 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need drainages.
1064 | Infrastructure, Development & Maintenance | Grading and murraming of Waagata's road, Wamwangi's road, Essy's road, Adams road, Georges road, Unity school road, Sky high road, Good Shepherd road and Koinange road | To improve road infrastructure by grading and murraming Waagata's road, Wamwangi's road, Essy's road, Adams road, Georges road, Unity school road, Sky high road, Good Shepherd road and Koinange road | Waagata's road, Wamwangi's road, Essy's road, Adams road, Georges road, Unity school road, Sky high road, Good Shepherd road and Koinange road graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Lakeview | -0.758795, 36.458465 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | N/A | 12438486 | 12438486 | 12438486 | Equitable | N/A | 12438486 | 0 | 0 | 0 | 0 | 12438486 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Kayole.
1065 | Infrastructure, Development and Maintenance | Grading, murraming and installation of culverts in Manera banda road | To implement grading, murraming and installation of culverts in manera banda road for road connectivity and accessibility | Grading, murraming and installation of culverts in Manera banda road completed | 3110499 | Construction of Roads - Other | Naivasha | Lakeview | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 2024893 | 1752850 | 1752850 | Equitable | N/A | 1752850 | 0 | 1750645 | 99.9 | 1750645 | 2205 | 2205 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1066 | Rehabilitation of road Infrastructure in Lakeview ward through Boresha Barabara | Rehabilitation of road Infrastructure in Lakeview ward through Boresha Barabara | To rehabilitate road Infrastructure in Lakeview ward through Boresha Barabara to restore functionality | Road Infrastructure in Lakeview ward through Boresha Barabara rehabilitated | 3110499 | Construction of Roads - Other | Naivasha | Lakeview | -0.751001, 36.459783 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 5000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
1067 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Dispensary Road (4km) in Lake View Ward Naivasha Sub County | To maintain Spot Improvement of Dispensary Road (4km) in Lake View Ward Naivasha Sub County in serviceable condition | Spot Improvement of Dispensary Road (4km) in Lake View Ward Naivasha Sub County maintained | 3110499 | Construction of Roads - Other | Naivasha | Lakeview | -0.75025, 36.456875 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | N/A | 3498746 | 1737866 | 1737866 | Equitable | N/A | 1737866 | 0 | 1364334 | 78.5 | 1364334 | 1737866 | 373532 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In Good condition.
1068 | Infrastructure, Development & Maintenance | Upgrade of access roads in Lakeview using Boresha Barabara | To implement upgrade of access roads in lakeview using boresha barabara for road connectivity and accessibility | Upgrade of access roads in Lakeview using Boresha Barabara completed | 3110499 | Construction of Roads - Other | Naivasha | Lakeview | -0.726771, 36.43997 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 3850000 | 3850000 | 3850000 | Equitable | N/A | 3850000 | 0 | 3850000 | 100 | 3850000 | 3850000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
1069 | Infrastructure, Development and Maintenance | Grading and gravelling of modern and murunyu access roads in Lanet Umoja | To improve road infrastructure by grading and murraming modern and murunyu access roads in Lanet Umoja | Modern and murunyu access roads in Lanet Umoja graded and murramed | 3110499 | Construction of Roads - Other | Bahati | Lanet-Umoja | -0.235546, 36.162791 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2024/2025 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 0 | 0 | 0 | 1996186 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: On going.
1070 | Infrastructure, Development and Maintenance | Grading and murraming of Nyonjoro area | To improve road infrastructure by grading and murraming Nyonjoro area | Nyonjoro area graded and murramed | 3110499 | Construction of Roads - Other | Bahati | Lanet-Umoja | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2024/25 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 0 | 0 | 0 | 1600000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1071 | Infrastructure, Development and Maintenance | Grading, murraming and culvert installation at St. Monica Lanet Catholic Church road, Shell to Kangema road | To implement grading, murraming and culvert installation at st. monica lanet catholic church road, shell to kangema road for road connectivity and accessibility | Grading, murraming and culvert installation at St. Monica Lanet Catholic Church road, Shell to Kangema road completed | 3110499 | Construction of Roads - Other | Bahati | Lanet-Umoja | -0.276413, 36.154031 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2024/2025 | 4000000 | 0 | 4000000 | Equitable | N/A | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Completed.
1072 | Infrastructure, Development & Maintenance | Culverts and drainages at Kamfarm and Baraka | To implement culverts and drainages at kamfarm and baraka for road connectivity and accessibility | Culverts and drainages at Kamfarm and Baraka completed | 3110499 | Construction of Roads - Other | Bahati | Lanet/Umoja | -0.279464, 36.175312 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1488888 | 99.3 | 1488888 | 0 | 11112 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Need drainage unblocking.
1073 | Infrastructure, Development and Maintenance | Grading and murraming of Ndege ndimu area | To improve road infrastructure by grading and murraming Ndege ndimu area | Ndege ndimu area graded and murramed | 3110499 | Construction of Roads - Other | Bahati | Lanet/Umoja | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 4000000 | 0 | 1600000 | Equitable | N/A | 1600000 | 0 | 0 | 0 | 0 | 1600000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1074 | Infrastructure, Development & Maintenance | Hire of machinery for road works rehabilitation | To implement hire of machinery for road works rehabilitation for road connectivity and accessibility | Hire of machinery for road works rehabilitation completed | 3110499 | Construction of Roads - Other | Bahati | Lanet/Umoja | -0.279053, 36.174416 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 7000000 | 7000000 | 7000000 | Equitable | N/A | 7000000 | 0 | 7000000 | 100 | 7000000 | 3900000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
1075 | Infrastructure, Development and Maintenance | Purchase of murram and fuel for roads maintenance across the Ward | To procure murram and fuel for roads maintenance across the Ward | Murram and fuel for roads maintenance across the Ward procured | 3110499 | Construction of Roads - Other | Bahati | Lanet/Umoja | -0.278888, 36.180375 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/2024 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 2400000 | 60 | 2400000 | 1600000 | 1600000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
1076 | Infrastructure, Development and Maintenance | Bush Clearing, Grading and Murraming of Wagathwara - Wambua Road | To implement bush clearing, grading and murraming of wagathwara - wambua road for road connectivity and accessibility | Bush Clearing, Grading and Murraming of Wagathwara - Wambua Road completed | 3110499 | Construction of Roads - Other | Njoro | Lare | -0.452378, 36.033072 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2024 | 2000000 | 2100000 | 2100000 | Equitable | N/A | 2100000 | 0 | 1813632 | 86.4 | 1813632 | 286368 | 286368 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
1077 | Infrastructure, Development and Maintenance | Grading And Murraming Of Bagari A Road | To improve road infrastructure by grading and murraming Bagari A Road | Bagari A Road graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Lare | -0.385862, 35.974245 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2024 | 1900000 | 1853150 | 1853150 | Equitable | N/A | 1853150 | 0 | 1825825 | 98.5 | 1825825 | 1853150 | 27325 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
1078 | Infrastructure, Development and Maintenance | Grading And Murraming Of Block Three Road | To improve road infrastructure by grading and murraming Block Three Road | Block Three Road graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Lare | -0.385862, 35.974245 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2024 | 1900000 | 1867950 | 1867950 | Equitable | N/A | 1867950 | 0 | 1863883 | 99.8 | 1863883 | 1867950 | 4067 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
1079 | Infrastructure, Development and Maintenance | Grading and Murraming of Gichobo road | To improve road infrastructure by grading and murraming Gichobo road | Gichobo road graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Lare | -0.385862, 35.974245 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2024 | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 2296980 | 95.7 | 2296980 | 103020 | 103020 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
1080 | Infrastructure, Development and Maintenance | Grading and Murraming of Lare central road | To improve road infrastructure by grading and murraming Lare central road | Lare central road graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Lare | -0.467588 36.031073 2039.4 6.099999904632568 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 2300000 | 1800600 | 1800600 | Equitable | N/A | 1800600 | 0 | 1800600 | 100 | 1800600 | 1800600 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
1081 | Infrastructure, Development and Maintenance | Grading and Murraming of Lare juu road | To improve road infrastructure by grading and murraming Lare juu road | Lare juu road graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Lare | -0.385862, 35.974245 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2024 | 2300000 | 2300000 | 2300000 | Equitable | N/A | 2300000 | 0 | 2298815 | 99.9 | 2298815 | 1185 | 1185 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
1082 | Infrastructure, Development and Maintenance | Grading and Murraming of Lare lower zone road | To improve road infrastructure by grading and murraming Lare lower zone road | Lare lower zone road graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Lare | -0.495563 36.024872 2208.6 11.800000190734863 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 1900000 | 1600268 | 1600268 | Equitable | N/A | 1600268 | 0 | 1600268 | 100 | 1600268 | 1600268 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: In pathetic state.
1083 | Infrastructure, Development and Maintenance | Heavy Bush Clearing, Grading and Murraming Lare - Naishi Road | To implement heavy bush clearing, grading and murraming lare - naishi road for road connectivity and accessibility | Heavy Bush Clearing, Grading and Murraming Lare - Naishi Road completed | 3110499 | Construction of Roads - Other | Njoro | Lare | -0.444372, 36.012941 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2024 | 3200000 | 3300000 | 3300000 | Equitable | N/A | 3300000 | 0 | 2796891 | 84.8 | 2796891 | 503109 | 503109 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintence.
1084 | Infrastructure, Development and Maintenance | Heavy Bush Clearing, Grading and Murraming of Block 3 Road | To implement heavy bush clearing, grading and murraming of block 3 road for road connectivity and accessibility | Heavy Bush Clearing, Grading and Murraming of Block 3 Road completed | 3110499 | Construction of Roads - Other | Njoro | Lare | -0.444372, 36.012941 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2024 | 2600000 | 2800000 | 2800000 | Equitable | N/A | 2800000 | 0 | 2743221 | 98 | 2743221 | 56779 | 56779 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintence.
1085 | Infrastructure, Development and Maintenance | Heavy Bush Clearing, Grading and Murraming of Lare B Road | To implement heavy bush clearing, grading and murraming of lare b road for road connectivity and accessibility | Heavy Bush Clearing, Grading and Murraming of Lare B Road completed | 3110499 | Construction of Roads - Other | Njoro | Lare | -0.452378, 36.033072 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2024 | 1200000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 1300000 | 100 | 1300000 | 478900 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
1086 | Infrastructure, Development and Maintenance | Heavy Bush Clearing, Grading and Murraming of Lare G Road | To implement heavy bush clearing, grading and murraming of lare g road for road connectivity and accessibility | Heavy Bush Clearing, Grading and Murraming of Lare G Road completed | 3110499 | Construction of Roads - Other | Njoro | Lare | -0.452378, 36.033072 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2024 | 2800000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2521100 | 84 | 2521100 | 478900 | 478900 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
1087 | Infrastructure, Development and Maintenance | Heavy Bush Clearing, Grading and Murraming of Lare P Road | To implement heavy bush clearing, grading and murraming of lare p road for road connectivity and accessibility | Heavy Bush Clearing, Grading and Murraming of Lare P Road completed | 3110499 | Construction of Roads - Other | Njoro | Lare | -0.452378, 36.033072 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2024 | 1900000 | 1900000 | 1900000 | Equitable | N/A | 1900000 | 0 | 1900000 | 100 | 1900000 | 478900 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
1088 | Infrastructure, Development and Maintenance | Heavy Bush Clearing, Grading and Murraming of Lare Upper Road | To implement heavy bush clearing, grading and murraming of lare upper road for road connectivity and accessibility | Heavy Bush Clearing, Grading and Murraming of Lare Upper Road completed | 3110499 | Construction of Roads - Other | Njoro | Lare | -0.444372, 36.012941 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2024 | 2400000 | 2600000 | 2600000 | Equitable | N/A | 2600000 | 0 | 2600000 | 100 | 2600000 | 478900 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintence.
1089 | Hire Of Machinery And Murram For Lare Ward | Hire Of Machinery And Murram For Lare Ward | To implement hire of machinery and murram for lare ward for road connectivity and accessibility | Hire Of Machinery And Murram For Lare Ward completed | 3110499 | Construction of Roads - Other | Njoro | Lare | -0.455725, 36.016665 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1861152 | 1861152 | 1861152 | Equitable | N/A | 1861152 | 0 | 1860650 | 100 | 1860650 | 1861152 | 502 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: 2021. Assessor remarks: Need maintenance.
1090 | Infrastructure, Development and Maintenance | Road Rehabiltation -Hire of Machinery for Lare Road works | To implement road rehabiltation -hire of machinery for lare road works for road connectivity and accessibility | Road Rehabiltation -Hire of Machinery for Lare Road works completed | 3110499 | Construction of Roads - Other | Njoro | Lare | -0.419918 36.039327 2033.4 5.300000190734863 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 1900000 | 1604700 | 1604700 | Equitable | N/A | 1604700 | 0 | 1603865 | 99.9 | 1603865 | 835 | 835 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
1091 | Infrastructure, Development and Maintenance | Grading And Murraming Of Bagaria - Mwenyere Road. | To improve road infrastructure by grading and murraming Bagaria - Mwenyere Road | Bagaria - Mwenyere Road graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Lare | -0.495563 36.024872 2208.6 11.800000190734863 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2500000 | 2327800 | 2327800 | Equitable | N/A | 2327800 | 0 | 2327800 | 100 | 2327800 | 2327800 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: In pathetic state.
1092 | Infrastructure, Development and Maintenance | Grading and murraming of Bagaria Zone E road | To improve road infrastructure by grading and murraming Bagaria Zone E road | Bagaria Zone E road graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Lare | -0.495563 36.024872 2208.6 11.800000190734863 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1489923 | 99.3 | 1489923 | 2327800 | 10077 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: In pathetic state.
1093 | Infrastructure, Development and Maintenance | Grading and Murraming Of Block Two Road | To improve road infrastructure by grading and murraming Block Two Road | Block Two Road graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Lare | -0.385862, 35.974245 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2024 | 1000000 | 987937.2 | 987937.2 | Equitable | N/A | 987937.2 | 0 | 987937 | 100 | 987937 | 987937 | 0.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
1094 | Infrastructure, Development and Maintenance | Grading and murraming of Kapyamit - Kianugu road | To improve road infrastructure by grading and murraming Kapyamit - Kianugu road | Kapyamit - Kianugu road graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Lare | -0.495563 36.024872 2208.6 11.800000190734863 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 2500000 | 968848.81 | 968848.81 | Equitable | N/A | 968848.81 | 0 | 861474 | 88.9 | 861474 | 107374 | 107374.81 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: In pathetic state.
1095 | Infrastructure, Development and Maintenance | Grading and Murraming Of Lare Road | To improve road infrastructure by grading and murraming Lare Road | Lare Road graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Lare | -0.385862, 35.974245 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2024 | 2300000 | 2110573.6 | 2110573.6 | Equitable | N/A | 2110573.6 | 0 | 2110574 | 100 | 2110574 | 2110574 | -0.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
1096 | Infrastructure, Development & Maintenance | Grading And Murraming Of Mugumo - Kwale - Muthiga Road. | To improve road infrastructure by grading and murraming Mugumo - Kwale - Muthiga Road | Mugumo - Kwale - Muthiga Road graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Lare | -0.431365, 36.045213 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2020 | 2000000 | 40164.79 | 40164.79 | Equitable | N/A | 40164.79 | 0 | 40165 | 100 | 40165 | 40165 | -0.21 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Need murraming.
1097 | Infrastructure, Development and Maintenance | Grading And Murraming Of Mwenyere-Milimani Road. | To improve road infrastructure by grading and murraming Mwenyere-Milimani Road | Mwenyere-Milimani Road graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Lare | -0.495563 36.024872 2208.6 11.800000190734863 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 999999.92 | 999999.92 | Equitable | N/A | 999999.92 | 0 | 999450 | 99.9 | 999450 | 1000000 | 549.92 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: In pathetic state.
1098 | Infrastructure, Development and Maintenance | Grading and Murraming Of Naishi Game Road | To improve road infrastructure by grading and murraming Naishi Game Road | Naishi Game Road graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Lare | -0.385862, 35.974245 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2024 | 2300000 | 2200995.6 | 2200995.6 | Equitable | N/A | 2200995.6 | 0 | 2108858 | 95.8 | 2108858 | 2200996 | 92137.6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
1099 | Infrastructure, Development and Maintenance | Grading and murraming of Nduriri - Kahuho road | To improve road infrastructure by grading and murraming Nduriri - Kahuho road | Nduriri - Kahuho road graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Lare | -0.385862, 35.974245 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2024 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1985096 | 99.3 | 1985096 | 1853150 | 14904 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
1100 | Infrastructure, Development and Maintenance | Grading and Murraming Of Road G Lare Ward | To improve road infrastructure by grading and murraming Road G Lare Ward | Road G Lare Ward graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Lare | -0.495563 36.024872 2208.6 11.800000190734863 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1743206 | 96.8 | 1743206 | 2110574 | 56794 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: In pathetic state.
1101 | Infrastructure, Development & Maintenance | Grading And Murraming Of Wambia - Nduriri - Nduriri Juu Borehole Road. | To improve road infrastructure by grading and murraming Wambia - Nduriri - Nduriri Juu Borehole Road | Wambia - Nduriri - Nduriri Juu Borehole Road graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Lare | -0.467588 36.031073 2039.4 6.099999904632568 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2500000 | 1996550 | 1996550 | Equitable | N/A | 1996550 | 0 | 1996550 | 100 | 1996550 | 1996550 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
1102 | Infrastructure, Development and Maintenance | Grading and Murraming Of Wanginyo - Block 3 Road | To improve road infrastructure by grading and murraming Wanginyo - Block 3 Road | Wanginyo - Block 3 Road graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Lare | -0.385862, 35.974245 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2024 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1885770 | 94.3 | 1885770 | 987937 | 114230 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
1103 | Infrastructure, Development & Maintenance | Grading, murraming and installation of culverts of Road K in Lare ward | To implement grading, murraming and installation of culverts of road k in lare ward for road connectivity and accessibility | Grading, murraming and installation of culverts of Road K in Lare ward completed | 3110499 | Construction of Roads - Other | Njoro | Lare | -0.462187, 36.050997 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2022 | 2004039 | 2004039 | 2004039 | Equitable | N/A | 2004039 | 0 | 1800205 | 89.8 | 1800205 | 1808250 | 203834 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
1104 | Infrastructure, Development & Maintenance | Grading And Murraming And Installation Of Culverts Of Muthiga – Karogoe Road. | To improve road infrastructure by grading and murraming And Installation Of Culverts Of Muthiga – Karogoe Road | And Installation Of Culverts Of Muthiga – Karogoe Road graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Lare | -0.462187, 36.050997 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2022 | 2000000 | 1808250 | 1808250 | Equitable | N/A | 1808250 | 0 | 1800205 | 99.6 | 1800205 | 1808250 | 8045 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
1105 | Infrastructure, Development and Maintenance | Construction Of Boda-boda Sheds Across London Ward | To construct Boda-boda Sheds Across London Ward | Boda-boda Sheds Across London Ward constructed | 3110499 | Construction of Roads - Other | Nakuru West | London | -0.271836, 36.052853 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 1600000 | 1600000 | 1600000 | Equitable | N/A | 1600000 | 0 | 1546320 | 96.6 | 1546320 | 53680 | 53680 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good job.
1106 | Infrastructure, Development and Maintenance | Spot Improvement & Maintenance of Social Hall Access Roads | To improve the condition of & Maintenance of Social Hall Access Roads | & Maintenance of Social Hall Access Roads improved | 3110499 | Construction of Roads - Other | Nakuru West | London | -0.274966, 36.050484 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: The project has not yet started.
1107 | Spots Filling With Concreate At Guba Road | Spots Filling With Concreate At Guba Road | To implement spots filling with concreate at guba road for road connectivity and accessibility | Spots Filling With Concreate At Guba Road completed | 3110499 | Construction of Roads - Other | Nakuru West | London | -0.269757, 36.051053 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 2000000 | 1968114 | 1968114 | Equitable | N/A | 1968114 | 0 | 0 | 0 | 0 | 1968114 | 0 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: The project was done though it's currently in a bad shape.
1108 | Infrastructure, Development and Maintenance | Boresha barabara murram for road rehabilitation | To implement boresha barabara murram for road rehabilitation for road connectivity and accessibility | Boresha barabara murram for road rehabilitation completed | 3110499 | Construction of Roads - Other | Naivasha | Maai Mahiu | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2335000 | 93.4 | 2335000 | 1000000 | 165000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1109 | Infrastructure, Development and Maintenance | Construction, rehabilitation and maintenance of access roads | To implement construction, rehabilitation and maintenance of access roads for road connectivity and accessibility | Construction, rehabilitation and maintenance of access roads completed | 3110499 | Construction of Roads - Other | Naivasha | Maai Mahiu | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 5500000 | 5500000 | 5500000 | Equitable | N/A | 5500000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
1110 | Infrastructure, Development and Maintenance | Grading and gravelling and construction of a bridge in Githioro village- Maai Mahiu ward | To improve road infrastructure by grading and murraming and construction of a bridge in Githioro village- Maai Mahiu ward | And construction of a bridge in Githioro village- Maai Mahiu ward graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Maai Mahiu | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | N/A | 3000000 | 0 | 1475298.6 | Equitable | N/A | 1475298.6 | 0 | 6474701 | 100 | 6474701 | 1475299 | -6474701 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
1111 | Infrastructure, Development and Maintenance | Grading And Gravelling Longonot and Maai Mahiu Access Roads | To improve road infrastructure by grading and murraming Longonot and Maai Mahiu Access Roads | Longonot and Maai Mahiu Access Roads graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Maai Mahiu | -0.967163, 36.57326 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 5324111 | 0 | 5304111 | Equitable | N/A | 5304111 | 0 | 4817870 | 100 | 4817870 | 5304111 | -4817870 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Yes.
1112 | Infrastructure, Development and Maintenance | Grading and gravelling of Maai Mahiu and Longonot access roads | To improve road infrastructure by grading and murraming Maai Mahiu and Longonot access roads | Maai Mahiu and Longonot access roads graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Maai Mahiu | -0.992613, 36.593148 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 5324111 | 5324111 | 5324111 | Equitable | N/A | 5324111 | 0 | 4817870 | 90.5 | 4817870 | 5324111 | 506241 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good, but needs routine maintenance.
1113 | Infrastructure, Development and Maintenance | Grading and murraming of Maai Mahiu Town access roads | To improve road infrastructure by grading and murraming Maai Mahiu Town access roads | Maai Mahiu Town access roads graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Maai Mahiu | -0.992613, 36.593148 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 4817870 | 96.4 | 4817870 | 182130 | 182130 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good, but needs routine maintenance.
1114 | Infrastructure, Development and Maintenance | Grading and Murraming of Roads in Maai Mahiu | To improve road infrastructure by grading and murraming Roads in Maai Mahiu | Roads in Maai Mahiu graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Maai Mahiu | -0.980271, 36.584833 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 3494096 | 0 | 3414096 | Equitable | N/A | 3414096 | 0 | 4817870 | 100 | 4817870 | 3494096 | -4817870 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
1115 | Infrastructure, Development and Maintenance | Grading And Murraming of Roads Through Imarisha Barabara Programme | To improve road infrastructure by grading and murraming Roads Through Imarisha Barabara Programme | Roads Through Imarisha Barabara Programme graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Maai Mahiu | -0.984544, 36.587964 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 0 | 0 | 0 | 3494096 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
1116 | Infrastructure, Development & Maintenance | Grading, murraming and culverts installation in Maai Mahiu Town access roads | To implement grading, murraming and culverts installation in maai mahiu town access roads for road connectivity and accessibility | Grading, murraming and culverts installation in Maai Mahiu Town access roads completed | 3110499 | Construction of Roads - Other | Naivasha | Maai Mahiu | -0.979395, 36.583706 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1314200 | 1314200 | Equitable | N/A | 1314200 | 0 | 1314200 | 100 | 1314200 | 1314200 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good state.
1117 | Infrastructure, Development & Maintenance | Proposed Routine Maintenance and Drain Construction of Maai Mahiu Centre Road in Mai Mahiu Ward -Naivasha Sub County | To undertake the proposed Routine Maintenance and Drain Construction of Maai Mahiu Centre Road in Mai Mahiu Ward -Naivasha Sub County | Proposed Routine Maintenance and Drain Construction of Maai Mahiu Centre Road in Mai Mahiu Ward -Naivasha Sub County implemented | 3110499 | Construction of Roads - Other | Naivasha | Maai Mahiu | -0.983497, 36.58729 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 588924 | 588924 | 588924 | Equitable | N/A | 588924 | 0 | 588924 | 100 | 588924 | 588924 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs spot filling.
1118 | Infrastructure, Development and Maintenance | Rehabilitation of Roads and hire of equipments and machinery | To rehabilitate Roads and hire of equipments and machinery to restore functionality | Roads and hire of equipments and machinery rehabilitated | 3110499 | Construction of Roads - Other | Naivasha | Maai Mahiu | -0.991272, 36.571424 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 3000000 | 100 | 3000000 | 3000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: To be maintained.
1119 | Roadworks in Maai Mahiu, culverts and murraming | Roadworks in Maai Mahiu, culverts and murraming | To implement roadworks in maai mahiu, culverts and murraming for road connectivity and accessibility | Roadworks in Maai Mahiu, culverts and murraming completed | 3110499 | Construction of Roads - Other | Naivasha | Maai Mahiu | -0.977473, 36.584927 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2495800 | 99.8 | 2495800 | 2500000 | 4200 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need to revisit the road.
1120 | Infrastructure, Development and Maintenance | Routine Maintenance and Spot Improvement of Longonot - Kenton road in Mai Mahiu Ward Naivasha Sub County | To maintain Spot Improvement of Longonot - Kenton road in Mai Mahiu Ward Naivasha Sub County in serviceable condition | Spot Improvement of Longonot - Kenton road in Mai Mahiu Ward Naivasha Sub County maintained | 3110499 | Construction of Roads - Other | Naivasha | Maai Mahiu | -0.870717, 36.555893 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1904720 | 1523725 | 1523725 | Equitable | N/A | 1523725 | 0 | 588924 | 38.7 | 588924 | 1523725 | 934801 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs maintenance.
1121 | Infrastructure, Development and Maintenance | Routine Maintenance and Spot Improvement of Maai Mahiu Town Roads in Mai Mahiu Ward Naivasha Sub County | To maintain Spot Improvement of Maai Mahiu Town Roads in Mai Mahiu Ward Naivasha Sub County in serviceable condition | Spot Improvement of Maai Mahiu Town Roads in Mai Mahiu Ward Naivasha Sub County maintained | 3110499 | Construction of Roads - Other | Naivasha | Maai Mahiu | -0.870717, 36.555893 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 3000000 | 1934900 | 1934900 | Equitable | N/A | 1934900 | 0 | 588924 | 30.4 | 588924 | 1934900 | 1345976 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs maintenance.
1122 | Infrastructure, Development & Maintenance | Supply of murram and fuel for roadwork rehabilitation | To implement supply of murram and fuel for roadwork rehabilitation for road connectivity and accessibility | Supply of murram and fuel for roadwork rehabilitation completed | 3110499 | Construction of Roads - Other | Naivasha | Maai Mahiu | -0.942229, 36.560043 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | N/A | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 2335000 | 100 | 2335000 | 1000000 | -2335000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
1123 | Infrastructure, Development and Maintenance | Maiella road works | To implement maiella road works for road connectivity and accessibility | Maiella road works completed | 3110499 | Construction of Roads - Other | Naivasha | Maiella | -0.863935, 36.185365 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2025 | 4000000 | 4000000 | 7000000 | Equitable | N/A | 7000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational....
1124 | Infrastructure, Development and Maintenance | Road rehabiltation - hiring of machineries for Road rehabiltation | To implement road rehabiltation - hiring of machineries for road rehabiltation for road connectivity and accessibility | Road rehabiltation - hiring of machineries for Road rehabiltation completed | 3110499 | Construction of Roads - Other | Naivasha | Maiella | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1125 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Ndabibi Primary - Ndabibi Centre-Chief's Road in Maiella Ward Naivasha Sub County | To maintain Spot Improvement of Ndabibi Primary - Ndabibi Centre-Chief's Road in Maiella Ward Naivasha Sub County in serviceable condition | Spot Improvement of Ndabibi Primary - Ndabibi Centre-Chief's Road in Maiella Ward Naivasha Sub County maintained | 3110499 | Construction of Roads - Other | Naivasha | Maiella | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 3050800 | 6050800 | 6050800 | Equitable | N/A | 6050800 | 0 | 6050800 | 100 | 6050800 | 6050800 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1126 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Ngondi -Ngunyumu Road in Maiella Ward Naivasha Sub County | To maintain Spot Improvement of Ngondi -Ngunyumu Road in Maiella Ward Naivasha Sub County in serviceable condition | Spot Improvement of Ngondi -Ngunyumu Road in Maiella Ward Naivasha Sub County maintained | 3110499 | Construction of Roads - Other | Naivasha | Maiella | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2987232 | 2987232 | 2987232 | Equitable | N/A | 2987232 | 0 | 2950463 | 98.8 | 2950463 | 2987232 | 36769 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1127 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Ngondi to Ngondi primary in Maiella Ward Naivasha Sub County | To maintain Spot Improvement of Ngondi to Ngondi primary in Maiella Ward Naivasha Sub County in serviceable condition | Spot Improvement of Ngondi to Ngondi primary in Maiella Ward Naivasha Sub County maintained | 3110499 | Construction of Roads - Other | Naivasha | Maiella | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 3700000 | 3700000 | 3700000 | Equitable | N/A | 3700000 | 0 | 3373394 | 91.2 | 3373394 | 3700000 | 326606 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1128 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Ngunyumu Ngondi-Lager Road in Maiella Ward Naivasha Sub County | To maintain Spot Improvement of Ngunyumu Ngondi-Lager Road in Maiella Ward Naivasha Sub County in serviceable condition | Spot Improvement of Ngunyumu Ngondi-Lager Road in Maiella Ward Naivasha Sub County maintained | 3110499 | Construction of Roads - Other | Naivasha | Maiella | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1730720 | 1695820 | 1695820 | Equitable | N/A | 1695820 | 0 | 1695820 | 100 | 1695820 | 1695820 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1129 | Infrastructure, Development and Maintenance | Bush Clearing, Grading, Gravelling Compaction and Culverts Installation in SMK road | To implement bush clearing, grading, gravelling compaction and culverts installation in smk road for road connectivity and accessibility | Bush Clearing, Grading, Gravelling Compaction and Culverts Installation in SMK road completed | 3110499 | Construction of Roads - Other | Gilgil | Malewa West | -0.684685, 36.471073 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2882615 | 96.1 | 2882615 | 117385 | 117385 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/S RISA LTD. Assessor remarks: Continuous maintenance.
1130 | Infrastructure, Development and Maintenance | Grading & Murraming for the Imarisha barabara program in Malewa West | To improve road accessibility by grading & Murraming for the Imarisha barabara program in Malewa West | & Murraming for the Imarisha barabara program in Malewa West graded | 3110499 | Construction of Roads - Other | Gilgil | Malewa West | -0.684685, 36.471073 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2024/25 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
1131 | Infrastructure, Development and Maintenance | Improvement of Malewa West Ward Roads through grading, gravelling,Compaction and culverts installation | To implement improvement of malewa west ward roads through grading, gravelling,compaction and culverts installation for road connectivity and accessibility | Improvement of Malewa West Ward Roads through grading, gravelling,Compaction and culverts installation completed | 3110499 | Construction of Roads - Other | Gilgil | Malewa West | -0.684685, 36.489092 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 9000000 | 8000000 | 8000000 | Equitable | N/A | 8000000 | 0 | 7501329 | 93.8 | 7501329 | 117385 | 498671 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
1132 | Infrastructure, Development and Maintenance | Malewa West Roads rehabilitation (hire of machinery and equipments) | To implement malewa west roads rehabilitation (hire of machinery and equipments) for road connectivity and accessibility | Malewa West Roads rehabilitation (hire of machinery and equipments) completed | 3110499 | Construction of Roads - Other | Gilgil | Malewa West | -0.666667 36.39886 0 2000 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2999405 | 100 | 2999405 | 3000000 | 595 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
1133 | Infrastructure, Development & Maintenance | Rehabilitation of roads in Malewa West -Hire of machines for grading, gravelling and compacting | To rehabilitate roads in Malewa West -Hire of machines for grading, gravelling and compacting to restore functionality | Roads in Malewa West -Hire of machines for grading, gravelling and compacting rehabilitated | 3110499 | Construction of Roads - Other | Gilgil | Malewa West | -0.684685 36.471073 0 2000 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999100 | 100 | 1999100 | 0 | 900 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Has been maintained over years.
1134 | Infrastructure, Development & Maintenance | Grading and gravelling of Disital Kaliet road | To improve road infrastructure by grading and murraming Disital Kaliet road | Disital Kaliet road graded and murramed | 3110499 | Construction of Roads - Other | Molo | Mariashoni | -0.350431, 35.812051 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2138191 | 2136530 | 2136530 | Equitable | N/A | 2136530 | 0 | 2136530 | 100 | 2136530 | 2136530 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
1135 | Infrastructure, Development & Maintenance | Grading and levelling Kapchepokazi-Kalegu road | To improve road accessibility by grading and levelling Kapchepokazi-Kalegu road | And levelling Kapchepokazi-Kalegu road graded | 3110499 | Construction of Roads - Other | Molo | Mariashoni | -0.386159, 35.809073 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 996360 | 996360 | Equitable | N/A | 996360 | 0 | 996360 | 100 | 996360 | 996360 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Partly. Viable: Yes. Assessor remarks: Poor road.
1136 | Infrastructure, Development & Maintenance | Grading and levelling Ndoswa-Ndashatai Road | To improve road accessibility by grading and levelling Ndoswa-Ndashatai Road | And levelling Ndoswa-Ndashatai Road graded | 3110499 | Construction of Roads - Other | Molo | Mariashoni | -0.369206, 35.841966 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 1800000 | 1799000 | 1799000 | Equitable | N/A | 1799000 | 0 | 1799000 | 100 | 1799000 | 1799000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Access road good.
1137 | Infrastructure, Development & Maintenance | Grading and murraming Marioshoni-Taragonic road | To improve road infrastructure by grading and murraming Marioshoni-Taragonic road | Marioshoni-Taragonic road graded and murramed | 3110499 | Construction of Roads - Other | Molo | Mariashoni | -0.340543, 35.814798 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1813140 | 90.7 | 1813140 | 2000000 | 186860 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
1138 | Infrastructure, Development and Maintenance | Grading and murraming of Elburgon Mawe Mbili road | To improve road infrastructure by grading and murraming Elburgon Mawe Mbili road | Elburgon Mawe Mbili road graded and murramed | 3110499 | Construction of Roads - Other | Molo | Mariashoni | -0.343871, 35.791629 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 1975271 | 1975271 | Equitable | N/A | 1975271 | 0 | 1975271 | 100 | 1975271 | 1975271 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Access road to town good.
1139 | Infrastructure, Development and Maintenance | Grading and Murraming of Kaliet-Mauche Ndogo Road | To improve road infrastructure by grading and murraming Kaliet-Mauche Ndogo Road | Kaliet-Mauche Ndogo Road graded and murramed | 3110499 | Construction of Roads - Other | Molo | Mariashoni | -0.376959 35.790913 2793.112 0.71200001239771 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 6000000 | 0 | 403244.9 | Equitable | N/A | 403244.9 | 0 | 859885 | 100 | 859885 | 403245 | -859885 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Access road good.
1140 | Infrastructure, Development and Maintenance | Grading and murraming of Kapsinendet Kitango road | To improve road infrastructure by grading and murraming Kapsinendet Kitango road | Kapsinendet Kitango road graded and murramed | 3110499 | Construction of Roads - Other | Molo | Mariashoni | -0.378993, 35.796751 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 1931829 | 1931829 | Equitable | N/A | 1931829 | 0 | 1931829 | 100 | 1931829 | 1931829 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Routine maintenance needed.
1141 | Infrastructure, Development and Maintenance | Grading and Murraming of Kipchumus-Kapsita Road | To improve road infrastructure by grading and murraming Kipchumus-Kapsita Road | Kipchumus-Kapsita Road graded and murramed | 3110499 | Construction of Roads - Other | Molo | Mariashoni | -0.341913 35.790872 2619.225 1.9689999818801 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 2401774 | 2058524 | 2058524 | Equitable | N/A | 2058524 | 0 | 2058524 | 100 | 2058524 | 2058524 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Access road good. Viable: Yes. Assessor remarks: Good.
1142 | Infrastructure, Development and Maintenance | Grading and Murraming of Kiptunga- Tertit Road | To improve road infrastructure by grading and murraming Kiptunga- Tertit Road | Kiptunga- Tertit Road graded and murramed | 3110499 | Construction of Roads - Other | Molo | Mariashoni | -0.376959 35.790913 2793.112 0.71200001239771 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Access road good.
1143 | Infrastructure, Development and Maintenance | Grading and murraming of Mawe Mbili-Kalwet road | To improve road infrastructure by grading and murraming Mawe Mbili-Kalwet road | Mawe Mbili-Kalwet road graded and murramed | 3110499 | Construction of Roads - Other | Molo | Mariashoni | -0.343871, 35.791629 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1664905 | 444660 | 444660 | Equitable | N/A | 444660 | 0 | 444660 | 100 | 444660 | 444660 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Access road to town good.
1144 | Infrastructure, Development & Maintenance | Grading and murraming of Munyukwa-Marioshoni road | To improve road infrastructure by grading and murraming Munyukwa-Marioshoni road | Munyukwa-Marioshoni road graded and murramed | 3110499 | Construction of Roads - Other | Molo | Mariashoni | -0.370821, 35.82629 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1798140 | 89.9 | 1798140 | 2000000 | 201860 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
1145 | Infrastructure, Development and Maintenance | Grading and murraming of Oinoptich Kapgarang road | To improve road infrastructure by grading and murraming Oinoptich Kapgarang road | Oinoptich Kapgarang road graded and murramed | 3110499 | Construction of Roads - Other | Molo | Mariashoni | -0.341913 35.790872 2619.225 1.9689999818801 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 404155 | 404155 | Equitable | N/A | 404155 | 0 | 404155 | 100 | 404155 | 404155 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Access road good. Viable: Yes. Assessor remarks: Good.
1146 | Infrastructure, Development and Maintenance | Grading and murraming of Rombei-Kapsita road | To improve road infrastructure by grading and murraming Rombei-Kapsita road | Rombei-Kapsita road graded and murramed | 3110499 | Construction of Roads - Other | Molo | Mariashoni | -0.341913 35.790872 2619.225 1.9689999818801 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1600443 | 1600443 | 1600443 | Equitable | N/A | 1600443 | 0 | 1418690 | 88.6 | 1418690 | 1600443 | 181753 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Access road good. Viable: Yes. Assessor remarks: Good.
1147 | Infrastructure, Development and Maintenance | Grading & gravelling of Access roads through Imarisha barabara programme fuel within the ward | To improve road accessibility by grading & gravelling of Access roads through Imarisha barabara programme fuel within the ward | & gravelling of Access roads through Imarisha barabara programme fuel within the ward graded | 3110499 | Construction of Roads - Other | Molo | Mariashoni | -0.366949, 35.785199 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 3000000 | 2000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
1148 | Infrastructure, Development and Maintenance | Hire of machineries for roads rehabilitation across the Ward | To implement hire of machineries for roads rehabilitation across the ward for road connectivity and accessibility | Hire of machineries for roads rehabilitation across the Ward completed | 3110499 | Construction of Roads - Other | Molo | Mariashoni | -0.350329 35.870564 2396.2960449307725 16 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 6002719 | 6002719 | 6002719 | Equitable | N/A | 6002719 | 0 | 0 | 0 | 0 | 6900891 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Working.
1149 | Infrastructure, Development and Maintenance | Hiring of machineries for roads works rehabilitation | To implement hiring of machineries for roads works rehabilitation for road connectivity and accessibility | Hiring of machineries for roads works rehabilitation completed | 3110499 | Construction of Roads - Other | Molo | Mariashoni | -0.374407 35.789768 2791.467 2.1500000953674 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 7900891 | 0 | 6900891 | Equitable | N/A | 6900891 | 0 | 0 | 0 | 0 | 6900891 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Annual unblocking.
1150 | Infrastructure, Development & Maintenance | Opening of Ndoswa Bosnia road | To improve the condition of Ndoswa Bosnia road | Ndoswa Bosnia road improved | 3110499 | Construction of Roads - Other | Molo | Mariashoni | -0.34129, 35.88619 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 1000000 | 993099 | 993099 | Equitable | N/A | 993099 | 0 | 992900 | 100 | 992900 | 993099 | 199 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
1151 | Infrastructure, Development & Maintenance | Grading and gravelling of Likia-Dispensary, Bestland-Toplife road | To improve road infrastructure by grading and murraming Likia-Dispensary, Bestland-Toplife road | Likia-Dispensary, Bestland-Toplife road graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Mau Narok | -1.2841, 36.8155 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1797787 | 89.9 | 1797787 | 2000246 | 202213 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: viable. Assessor remarks: good state of repair.
1152 | Infrastructure, Development & Maintenance | Grading and gravelling of Mirangini-Obwaka farm road | To improve road infrastructure by grading and murraming Mirangini-Obwaka farm road | Mirangini-Obwaka farm road graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Mau Narok | -1.2841, 36.8155 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1886870 | 94.3 | 1886870 | 630 | 113130 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: viable. Assessor remarks: good state of repair.
1153 | Infrastructure, Development & Maintenance | Grading And Gravelling Of Tipis Center Access Road | To improve road infrastructure by grading and murraming Tipis Center Access Road | Tipis Center Access Road graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Mau Narok | -0.529072 35.968285 2526.1000000000004 10.699999809265137 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2161201 | 2000246 | 2000246 | Equitable | N/A | 2000246 | 0 | 1987883 | 99.4 | 1987883 | 2000246 | 12363 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Viable. Assessor remarks: In Procurement 2024/2025.
1154 | Infrastructure, Development and Maintenance | Grading And Murraming of Access Roads- Imarisha Barabara in Mau Narok Ward | To improve road infrastructure by grading and murraming Access Roads- Imarisha Barabara in Mau Narok Ward | Access Roads- Imarisha Barabara in Mau Narok Ward graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Mau Narok | -0.633057 35.995753 0 149 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 500000 | 0 | 200000 | Equitable | N/A | 200000 | 0 | 300000 | 100 | 300000 | 200000 | -300000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: needs repair.
1155 | Infrastructure, Development & Maintenance | Grading And Murraming Of Bondeni-Waweru Farm Road | To improve road infrastructure by grading and murraming Bondeni-Waweru Farm Road | Bondeni-Waweru Farm Road graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Mau Narok | -0.597775, 36.005282 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 3500000 | 630 | 630 | Equitable | N/A | 630 | 0 | 2499370 | 396725.4 | 2499370 | 630 | -2498740 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Assessor remarks: Good state of repair.
1156 | Infrastructure, Development and Maintenance | Grading And Murraming of downtown to catholic church Roads | To improve road infrastructure by grading and murraming downtown to catholic church Roads | Downtown to catholic church Roads graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Mau Narok | -0.529072 35.968285 2526.1000000000004 10.699999809265137 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3534774 | 88.4 | 3534774 | 465226 | 465226 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Viable. Assessor remarks: In Procurement 2024/2025.
1157 | Infrastructure, Development and Maintenance | Grading And Murraming of Thwariga-West, Gate-Kahuho Roads | To improve road infrastructure by grading and murraming Thwariga-West, Gate-Kahuho Roads | Thwariga-West, Gate-Kahuho Roads graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Mau Narok | -1.2841, 36.8155 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 3700000 | 3700000 | 3700000 | Equitable | N/A | 3700000 | 0 | 3249910 | 87.8 | 3249910 | 450090 | 450090 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: YES. Viable: YES. Assessor remarks: IN STATE OF REPAIR.
1158 | Infrastructure, Development and Maintenance | Grading and murraming through Imarisha barabara | To improve road infrastructure by grading and murraming through Imarisha barabara | Through Imarisha barabara graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Mau Narok | -0.598002 36.005328 2574.8999999999996 4.599999904632568 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 300000 | 100 | 300000 | 200000 | -300000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Assessor remarks: Good state of repair.
1159 | Infrastructure, Development and Maintenance | Grading, gravelling and compacting of roads in Mau Narok Ward | To implement grading, gravelling and compacting of roads in mau narok ward for road connectivity and accessibility | Grading, gravelling and compacting of roads in Mau Narok Ward completed | 3110499 | Construction of Roads - Other | Njoro | Mau Narok | -0.569682 36.06244 2354 6 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 6000000 | 6000000 | 5100000 | Equitable | N/A | 5100000 | 0 | 300000 | 5 | 300000 | 200000 | 5700000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Stalled project.
1160 | Infrastructure, Development and Maintenance | Grading, gravelling and compaction of Down-town PCEA Road, Mwisho wa Lami-Kahuho Road, Breweries-Lengetia scheme Road and Gatinga-Kiahiti road | To implement grading, gravelling and compaction of down-town pcea road, mwisho wa lami-kahuho road, breweries-lengetia scheme road and gatinga-kiahiti road for road connectivity and accessibility | Grading, gravelling and compaction of Down-town PCEA Road, Mwisho wa Lami-Kahuho Road, Breweries-Lengetia scheme Road and Gatinga-Kiahiti road completed | 3110499 | Construction of Roads - Other | Njoro | Mau Narok | -0.633018, 35.995964 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 10800000 | 0 | 1472137.2 | Equitable | N/A | 1472137.2 | 0 | 8525527 | 100 | 8525527 | 1472137 | -8525527 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: not in good condition.
1161 | Infrastructure, Development and Maintenance | Grading, murraming and compaction of Likia-Digital roads in Mau Narok | To implement grading, murraming and compaction of likia-digital roads in mau narok for road connectivity and accessibility | Grading, murraming and compaction of Likia-Digital roads in Mau Narok completed | 3110499 | Construction of Roads - Other | Njoro | Mau Narok | -0.529072 35.968285 2526.1000000000004 10.699999809265137 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 300000 | 6 | 300000 | 994845 | 4700000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Viable. Assessor remarks: In Procurement 2024/2025.
1162 | Infrastructure, Development and Maintenance | Hire of machinery for roads construction in Mau Narok Ward | To implement hire of machinery for roads construction in mau narok ward for road connectivity and accessibility | Hire of machinery for roads construction in Mau Narok Ward completed | 3110499 | Construction of Roads - Other | Njoro | Mau Narok | -0.599922 36.005513 2648.2001953125 4.800000190734863 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 6000000 | 6000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Assessor remarks: Good state of repair.
1163 | Infrastructure, Development and Maintenance | Installation of Streetlights in Mau narok ward | To improve lighting and safety through installation of solar streetlights at Mau narok ward | Solar streetlights installed at Mau narok ward | 3110499 | Construction of Roads - Other | Njoro | Mau Narok | -1.2841, 36.8155 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 900000 | 0 | 900000 | Equitable | N/A | 900000 | 0 | 1588500 | 100 | 1588500 | 11500 | -1588500 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: yes. Viable: yes. Assessor remarks: in good use.
1164 | Infrastructure, Development and Maintenance | Roads rehabilitation in Mau Narok Ward | To implement roads rehabilitation in mau narok ward for road connectivity and accessibility | Roads rehabilitation in Mau Narok Ward completed | 3110499 | Construction of Roads - Other | Njoro | Mau Narok | -1.2841, 36.8155 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 5200000 | 5200000 | 4000000 | Equitable | N/A | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Bad. Objective met: not yet. Viable: not viable. Assessor remarks: project on going.
1165 | Infrastructure, Development and Maintenance | Routine Maintenance And Spot Improvement Of Sugutiek -Kamungei Road In Mau Narok Ward Njoro Sub County | To maintain Spot Improvement Of Sugutiek -Kamungei Road In Mau Narok Ward Njoro Sub County in serviceable condition | Spot Improvement Of Sugutiek -Kamungei Road In Mau Narok Ward Njoro Sub County maintained | 3110499 | Construction of Roads - Other | Njoro | Mau Narok | -0.588187 36.013644 0 0 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2968440 | 1468430 | 1468430 | Equitable | N/A | 1468430 | 0 | 1468430 | 100 | 1468430 | 1468430 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: viable. Assessor remarks: good state of repair.
1166 | Infrastructure, Development and Maintenance | Streetlights maintenance in Mau narok ward | To implement streetlights maintenance in mau narok ward for road connectivity and accessibility | Streetlights maintenance in Mau narok ward completed | 3110499 | Construction of Roads - Other | Njoro | Mau Narok | -0.588187 36.013644 0 0 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 900000 | 0 | 900000 | Equitable | N/A | 900000 | 0 | 500000 | 100 | 500000 | 11500 | -500000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: viable. Assessor remarks: good state of repair.
1167 | Infrastructure, Development and Maintenance | Construction of bodaboda shed in Lulukwet | To construct bodaboda shed in Lulukwet | Bodaboda shed in Lulukwet constructed | 3110499 | Construction of Roads - Other | Njoro | Mauche | -0.438943 35.939703 2324.60009765625 10.100000381469727 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 450000 | 0 | 450000 | Equitable | N/A | 450000 | 0 | 2925371 | 100 | 2925371 | 450000 | -2925371 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Needs watering point and roofing repair.
1168 | Infrastructure, Development & Maintenance | Grading and murraming of Kap-Joseph-River road and Teret Secondary - Mosop Road | To improve road infrastructure by grading and murraming Kap-Joseph-River road and Teret Secondary - Mosop Road | Kap-Joseph-River road and Teret Secondary - Mosop Road graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Mauche | -0.455438, 35.945078 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2022 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3220250 | 92 | 3220250 | 2999760 | 279750 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Needs improvement.
1169 | Infrastructure, Development & Maintenance | Grading And Murraming Of Mauche Centre | To improve road infrastructure by grading and murraming Mauche Centre | Mauche Centre graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Mauche | -0.513187, 35.97513 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2022 | 2719822 | 2719822 | 2719822 | Equitable | N/A | 2719822 | 0 | 2719822 | 100 | 2719822 | 2719822 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Needs improvement.
1170 | Infrastructure, Development & Maintenance | Grading and murraming of Mosop road | To improve road infrastructure by grading and murraming Mosop road | Mosop road graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Mauche | -0.45465, 35.94461 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2022 | 3500000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2999790 | 100 | 2999790 | 3000000 | 210 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
1171 | Infrastructure, Development & Maintenance | Grading And Murraming Of Taita Health - Techasis Primary Road | To improve road infrastructure by grading and murraming Taita Health - Techasis Primary Road | Taita Health - Techasis Primary Road graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Mauche | -0.524523, 35.952498 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2023 | 3000000 | 2918606 | 2918606 | Equitable | N/A | 2918606 | 0 | 2918606 | 100 | 2918606 | 2918606 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Needs improvement.
1172 | Infrastructure, Development and Maintenance | Grading and murraming through Imarisha barabara | To improve road infrastructure by grading and murraming through Imarisha barabara | Through Imarisha barabara graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Mauche | -0.45557, 35.94505 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2022 | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 2719822 | 0 | 2719822 | 2719822 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Needs improvement.
1173 | Infrastructure, Development and Maintenance | Grading, gravelling and murraming of Mauche road works | To implement grading, gravelling and murraming of mauche road works for road connectivity and accessibility | Grading, gravelling and murraming of Mauche road works completed | 3110499 | Construction of Roads - Other | Njoro | Mauche | -0.4785, 35.943625 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2025 | 6548255 | 6548255 | 6548255 | Equitable | N/A | 6548255 | 0 | 2719822 | 41.5 | 2719822 | 2719822 | 3828433 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
1174 | Infrastructure, Development and Maintenance | Hire of machineries for road works | To implement hire of machineries for road works for road connectivity and accessibility | Hire of machineries for road works completed | 3110499 | Construction of Roads - Other | Njoro | Mauche | -0.450682, 35.936465 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2025 | 3700000 | 7400000 | 7400000 | Equitable | N/A | 7400000 | 0 | 0 | 0 | 0 | 3700000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Needs improvement.
1175 | Infrastructure, Development and Maintenance | Rehabilitation and maintenance of floodlights in mauche ward | To rehabilitate maintenance of floodlights in mauche ward to restore functionality | Maintenance of floodlights in mauche ward rehabilitated | 3110499 | Construction of Roads - Other | Njoro | Mauche | -0.513718 35.962478 2562.5 97.9000015258789 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 1550000 | 0 | 1550000 | Equitable | N/A | 1550000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Needs improvement.
1176 | Infrastructure, Development and Maintenance | Construction of drainage at Mwangaza estate | To construct drainage at Mwangaza estate | Drainage at Mwangaza estate constructed | 3110499 | Construction of Roads - Other | Nakuru East | Menengai | -0.273529, 36.105142 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2024/25 | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 2997950 | 100 | 2997950 | 2997950 | -2997950 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
1177 | Infrastructure, Development and Maintenance | Hire of machineries for grading and murraming of Menengai roads | To implement hire of machineries for grading and murraming of menengai roads for road connectivity and accessibility | Hire of machineries for grading and murraming of Menengai roads completed | 3110499 | Construction of Roads - Other | Nakuru East | Menengai | -0.268111, 36.104167 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 4551946 | 91 | 4551946 | 448054 | 448054 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
1178 | Infrastructure, Development and Maintenance | Hire of machinery for roads rehabilitation, maintenance, installation of culverts | To implement hire of machinery for roads rehabilitation, maintenance, installation of culverts for road connectivity and accessibility | Hire of machinery for roads rehabilitation, maintenance, installation of culverts completed | 3110499 | Construction of Roads - Other | Nakuru East | Menengai | -0.275779, 36.115331 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2024/25 | 7000000 | 7000000 | 7000000 | Equitable | N/A | 7000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
1179 | Infrastructure, Development and Maintenance | Grading And Murraming of Access Roads- Imarisha Barabara in Menengai West Ward | To improve road infrastructure by grading and murraming Access Roads- Imarisha Barabara in Menengai West Ward | Access Roads- Imarisha Barabara in Menengai West Ward graded and murramed | 3110499 | Construction of Roads - Other | Rongai | Menengai West | -0.270342, 36.03636 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2024/25 | 1000000 | 0 | 400000 | Equitable | N/A | 400000 | 0 | 600000 | 100 | 600000 | 400000 | -600000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
1180 | Infrastructure, Development and Maintenance | Hire of equipments for road maintenance in Menengai West Ward | To implement hire of equipments for road maintenance in menengai west ward for road connectivity and accessibility | Hire of equipments for road maintenance in Menengai West Ward completed | 3110499 | Construction of Roads - Other | Rongai | Menengai West | -0.167281, 36.011944 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2024/25 | 5500000 | 5500000 | 5500000 | Equitable | N/A | 5500000 | 0 | 5491153 | 99.8 | 5491153 | 8847 | 8847 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
1181 | Infrastructure, Development and Maintenance | Hire of roads equipment for roads maintenance in the Ward | To implement hire of roads equipment for roads maintenance in the ward for road connectivity and accessibility | Hire of roads equipment for roads maintenance in the Ward completed | 3110499 | Construction of Roads - Other | Rongai | Menengai West | -0.167281, 36.011944 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2024/25 | 5000000 | 5000000 | 7000000 | Equitable | N/A | 7000000 | 0 | 5491153 | 109.8 | 5491153 | 8847 | -491153 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
1182 | Infrastructure, Development and Maintenance | Road Maintenance in Ol-Rongai Rigogo-Cuba Road and Kagaki- Baraka Road | To implement road maintenance in ol-rongai rigogo-cuba road and kagaki- baraka road for road connectivity and accessibility | Road Maintenance in Ol-Rongai Rigogo-Cuba Road and Kagaki- Baraka Road completed | 3110499 | Construction of Roads - Other | Rongai | Menengai West | -0.167608, 36.01229 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 4550000 | 4550000 | 4550000 | Equitable | N/A | 4550000 | 0 | 3654732 | 80.3 | 3654732 | 0 | 895268 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need rehabilitation.
1183 | Infrastructure, Development and Maintenance | Grading And Murraming of Access Roads- Imarisha Barabara in Molo Central Ward | To improve road infrastructure by grading and murraming Access Roads- Imarisha Barabara in Molo Central Ward | Access Roads- Imarisha Barabara in Molo Central Ward graded and murramed | 3110499 | Construction of Roads - Other | Molo | Molo | -0.249143, 35.727862 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2024/25 | 2000000 | 0 | 800000 | Equitable | N/A | 800000 | 0 | 1200000 | 100 | 1200000 | 800000 | -1200000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need grading.
1184 | Infrastructure, Development and Maintenance | Grading and Murraming through hiring of machinery across Molo Ward | To improve road infrastructure by grading and murraming through hiring of machinery across Molo Ward | Through hiring of machinery across Molo Ward graded and murramed | 3110499 | Construction of Roads - Other | Molo | Molo | -0.240494, 35.729679 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2021/22 | 7073326 | 6493110 | 6493110 | Equitable | N/A | 6493110 | 0 | 6108905 | 94.1 | 6108905 | 384205 | 384205 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Fair.
1185 | Infrastructure, Development and Maintenance | Routine Maintenance and Spot Improvement of Tayari Road in Molo Central Ward Molo Sub County | To maintain Spot Improvement of Tayari Road in Molo Central Ward Molo Sub County in serviceable condition | Spot Improvement of Tayari Road in Molo Central Ward Molo Sub County maintained | 3110499 | Construction of Roads - Other | Molo | Molo | -0.236301, 35.712926 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2024/25 | 1817024 | 0 | 1817024 | Equitable | N/A | 1817024 | 0 | 3584253 | 100 | 3584253 | 1817024 | -3584253 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
1186 | Infrastructure, Development & Maintenance | Grading and gravelling of Tayari-Moto road | To improve road infrastructure by grading and murraming Tayari-Moto road | Tayari-Moto road graded and murramed | 3110499 | Construction of Roads - Other | Molo | Molo Central | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2019/20 | N/A | 3000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
1187 | Infrastructure, Development & Maintenance | Grading and murraming of Chepalungu road at Sachangwan | To improve road infrastructure by grading and murraming Chepalungu road at Sachangwan | Chepalungu road at Sachangwan graded and murramed | 3110499 | Construction of Roads - Other | Molo | Molo Central | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 1000000 | 965610 | 965610 | Equitable | N/A | 965610 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
1188 | Infrastructure, Development & Maintenance | Grading and murraming of Chesilogo road at Sachagwan | To improve road infrastructure by grading and murraming Chesilogo road at Sachagwan | Chesilogo road at Sachagwan graded and murramed | 3110499 | Construction of Roads - Other | Molo | Molo Central | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 1000000 | 971540 | 971540 | Equitable | N/A | 971540 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
1189 | Infrastructure, Development & Maintenance | Grading and murraming of Kalyet-Kurkong road at Sachangwan | To improve road infrastructure by grading and murraming Kalyet-Kurkong road at Sachangwan | Kalyet-Kurkong road at Sachangwan graded and murramed | 3110499 | Construction of Roads - Other | Molo | Molo Central | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 2000000 | 1922410 | 1922410 | Equitable | N/A | 1922410 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
1190 | Infrastructure, Development & Maintenance | Grading and murraming of Kiambogo bridge road | To improve road infrastructure by grading and murraming Kiambogo bridge road | Kiambogo bridge road graded and murramed | 3110499 | Construction of Roads - Other | Molo | Molo Central | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 1000000 | 1037600 | 1037600 | Equitable | N/A | 1037600 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
1191 | Infrastructure, Development & Maintenance | Grading and murraming of Molo Ward access roads | To improve road infrastructure by grading and murraming Molo Ward access roads | Molo Ward access roads graded and murramed | 3110499 | Construction of Roads - Other | Molo | Molo Central | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 4598331 | 4097128 | 4097128 | Equitable | N/A | 4097128 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
1192 | Infrastructure, Development & Maintenance | Grading and murraming of Polytechnic, Maishani - Michina, Kivulini Roads | To improve road infrastructure by grading and murraming Polytechnic, Maishani - Michina, Kivulini Roads | Polytechnic, Maishani - Michina, Kivulini Roads graded and murramed | 3110499 | Construction of Roads - Other | Molo | Molo Central | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | N/A | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
1193 | Infrastructure, Development & Maintenance | Grading and murraming of Roads in Molo Ward - Hiring of machinery | To improve road infrastructure by grading and murraming Roads in Molo Ward - Hiring of machinery | Roads in Molo Ward - Hiring of machinery graded and murramed | 3110499 | Construction of Roads - Other | Molo | Molo Central | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | N/A | 5493326 | 5993326 | 5993326 | Equitable | N/A | 5993326 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
1194 | Infrastructure, Development & Maintenance | Grading and murraming of Sagoo research road | To improve road infrastructure by grading and murraming Sagoo research road | Sagoo research road graded and murramed | 3110499 | Construction of Roads - Other | Molo | Molo Central | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 2500000 | 2357100 | 2357100 | Equitable | N/A | 2357100 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
1195 | Infrastructure, Development & Maintenance | Grading and murraming of Tayari Primary-Tombo road | To improve road infrastructure by grading and murraming Tayari Primary-Tombo road | Tayari Primary-Tombo road graded and murramed | 3110499 | Construction of Roads - Other | Molo | Molo Central | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 2800000 | 2731010 | 2731010 | Equitable | N/A | 2731010 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
1196 | Infrastructure, Development & Maintenance | Grading, murraming and gravelling of Tayari Primary school - Dam road | To implement grading, murraming and gravelling of tayari primary school - dam road for road connectivity and accessibility | Grading, murraming and gravelling of Tayari Primary school - Dam road completed | 3110499 | Construction of Roads - Other | Molo | Molo Central | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 2237797 | 2237797 | 2237797 | Equitable | N/A | 2237797 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
1197 | Infrastructure, Development and Maintenance | Hiring of machinery and supply of murram for Lower Molo Academy Primary School | To implement hiring of machinery and supply of murram for lower molo academy primary school for road connectivity and accessibility | Hiring of machinery and supply of murram for Lower Molo Academy Primary School completed | 3110499 | Construction of Roads - Other | Molo | Molo Central | -0.530098, 36.383684 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2023/24 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Imarisha barabara. Assessor remarks: Good.
1198 | Infrastructure, Development and Maintenance | Hiring of machinery for grading and murraming | To implement hiring of machinery for grading and murraming for road connectivity and accessibility | Hiring of machinery for grading and murraming completed | 3110499 | Construction of Roads - Other | Molo | Molo Central | -0.530098, 36.383684 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2023/24 | 4500000 | 4500000 | 6064672 | Equitable | N/A | 6064672 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Imarisha barabara. Assessor remarks: Good.
1199 | Infrastructure, Development and Maintenance | Imarisha barabara- fueling and floodlights maintenance equipment | To implement imarisha barabara- fueling and floodlights maintenance equipment for road connectivity and accessibility | Imarisha barabara- fueling and floodlights maintenance equipment completed | 3110499 | Construction of Roads - Other | Molo | Molo Central | -0.530098, 36.383684 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2023/24 | 5000000 | 5000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Imarisha barabara. Assessor remarks: Good.
1200 | Infrastructure, Development and Maintenance | Rehabilitation of Molo Central access roads | To rehabilitate Molo Central access roads to restore functionality | Molo Central access roads rehabilitated | 3110499 | Construction of Roads - Other | Molo | Molo Central | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1201 | Infrastructure, Development and Maintenance | Routine Maintenance and Spot Improvement of Tayari Road in Molo Central Ward Molo Sub County | To maintain Spot Improvement of Tayari Road in Molo Central Ward Molo Sub County in serviceable condition | Spot Improvement of Tayari Road in Molo Central Ward Molo Sub County maintained | 3110499 | Construction of Roads - Other | Molo | Molo Central | -0.530098, 36.383684 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2023/24 | 1817024 | 1817024 | 1817024 | Equitable | N/A | 1817024 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Imarisha barabara. Assessor remarks: Good.
1202 | Infrastructure, Development and Maintenance | Grading And Murraming Of Mimwaita Road | To improve road infrastructure by grading and murraming Mimwaita Road | Mimwaita Road graded and murramed | 3110499 | Construction of Roads - Other | Rongai | Mosop | -0.244286, 35.909447 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2020 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1495750 | 99.7 | 1495750 | 1500000 | 4250 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: It was viable. Contractor: DANJACQUE. Assessor remarks: In good condition.
1203 | Infrastructure, Development and Maintenance | Grading And Murraming Of Roret Aic Road | To improve road infrastructure by grading and murraming Roret Aic Road | Roret Aic Road graded and murramed | 3110499 | Construction of Roads - Other | Rongai | Mosop | -0.244286, 35.909447 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2020 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 3000000 | 100 | 3000000 | 3000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: It was viable. Contractor: DANJACQUE. Assessor remarks: In good condition.
1204 | Infrastructure, Development and Maintenance | Grading, Murraming, Gravelling, Compacting and Installation of Culverts of Mimwata-Exmargaret to Acacia Road, Gakwen to Dwale to Suumek Bridge Road, Boror Mutarakwa to DIP Road, Wakaguthi Road from Elburgon Main Road to Keriko, Keriko to Kihara Road to Nursery Road, AIC Roret To Kapkatet Road, RVIST To Tree Farm Road and Face 9 To Kwa Container Road through Imarisha barabara programme | To implement grading, murraming, gravelling, compacting and installation of culverts of mimwata-exmargaret to acacia road, gakwen to dwale to suumek bridge road, boror mutarakwa to dip road, wakaguthi road from elburgon main road to keriko, keriko to kihara road to nursery road, aic roret to kapkatet road, rvist to tree farm road and face 9 to kwa container road through imarisha barabara programme for road connectivity and accessibility | Grading, Murraming, Gravelling, Compacting and Installation of Culverts of Mimwata-Exmargaret to Acacia Road, Gakwen to Dwale to Suumek Bridge Road, Boror Mutarakwa to DIP Road, Wakaguthi Road from Elburgon Main Road to Keriko, Keriko to Kihara Road to Nursery Road, AIC Roret To Kapkatet Road, RVIST To Tree Farm Road and Face 9 To Kwa Container Road through Imarisha barabara programme completed | 3110499 | Construction of Roads - Other | Rongai | Mosop | -0.264631, 35.987186 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2025 | 11850000 | 0 | 10528172 | Equitable | N/A | 10528172 | 0 | 1321828 | 100 | 1321828 | 10528172 | -1321828 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Imarisha program. Assessor remarks: Good.
1205 | Infrastructure, Development & Maintenance | Hiring of machineries, fuel and supply of murram at Lower Mosop road networks construction of culverts | To implement hiring of machineries, fuel and supply of murram at lower mosop road networks construction of culverts for road connectivity and accessibility | Hiring of machineries, fuel and supply of murram at Lower Mosop road networks construction of culverts completed | 3110499 | Construction of Roads - Other | Rongai | Mosop | -0.250942, 35.838502 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 22 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1800000 | 100 | 1800000 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: Possible by pedestrians and motorbikes only.
1206 | Infrastructure, Development & Maintenance | Hiring of machineries, fuel and supply of murram at Sobea-Ngondu-Ngecha road and construction of culverts | To implement hiring of machineries, fuel and supply of murram at sobea-ngondu-ngecha road and construction of culverts for road connectivity and accessibility | Hiring of machineries, fuel and supply of murram at Sobea-Ngondu-Ngecha road and construction of culverts completed | 3110499 | Construction of Roads - Other | Rongai | Mosop | -0.250942, 35.838502 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 22 | 1700000 | 1700000 | 1700000 | Equitable | N/A | 1700000 | 0 | 1700000 | 100 | 1700000 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: Possible by pedestrians and motorbikes only.
1207 | Infrastructure, Development & Maintenance | Hiring of machineries, fuel and supply of murram at Upper Mosop road networks | To implement hiring of machineries, fuel and supply of murram at upper mosop road networks for road connectivity and accessibility | Hiring of machineries, fuel and supply of murram at Upper Mosop road networks completed | 3110499 | Construction of Roads - Other | Rongai | Mosop | -0.250942, 35.838502 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 22 | 1700433 | 1700433 | 1700433 | Equitable | N/A | 1700433 | 0 | 1700433 | 100 | 1700433 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: Possible by pedestrians and motorbikes only.
1208 | Infrastructure, Development & Maintenance | Hiring of machineries, fuel and supply of murram at Wakarimu Bomasan, Sumeek and Rigogo road construction of culverts | To implement hiring of machineries, fuel and supply of murram at wakarimu bomasan, sumeek and rigogo road construction of culverts for road connectivity and accessibility | Hiring of machineries, fuel and supply of murram at Wakarimu Bomasan, Sumeek and Rigogo road construction of culverts completed | 3110499 | Construction of Roads - Other | Rongai | Mosop | -0.250942, 35.838502 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 22 | 1700000 | 1700000 | 1700000 | Equitable | N/A | 1700000 | 0 | 1700000 | 100 | 1700000 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: Possible by pedestrians and motorbikes only.
1209 | Infrastructure, Development & Maintenance | Road Works Across Mosop Ward (Purchase Of Fuel And Murram,Culverts And Hire Of Machines) | To implement road works across mosop ward (purchase of fuel and murram,culverts and hire of machines) for road connectivity and accessibility | Road Works Across Mosop Ward (Purchase Of Fuel And Murram,Culverts And Hire Of Machines) completed | 3110499 | Construction of Roads - Other | Rongai | Mosop | -0.252383 35.840025 2064.6 3.700000047683716 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 3667621 | 3667621 | 3667621 | Equitable | N/A | 3667621 | 0 | 3667621 | 100 | 3667621 | 3667621 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: Good.
1210 | Infrastructure, Development and Maintenance | Completion of Gilgil Murindat bridge phase II | To complete Gilgil Murindat bridge phase II | Gilgil Murindat bridge phase II completed | 3110499 | Construction of Roads - Other | Gilgil | Murindat | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 2500000 | 0 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 1750000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
1211 | Infrastructure, Development and Maintenance | Grading and Murraming kiamburi nessuit road | To improve road infrastructure by grading and murraming kiamburi nessuit road | Kiamburi nessuit road graded and murramed | 3110499 | Construction of Roads - Other | Gilgil | Murindat | -0.454062, 36.226977 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 2000000 | 1961600 | 1961600 | Equitable | N/A | 1961600 | 0 | 1958798 | 99.9 | 1958798 | 2802 | 2802 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: It was a viable project but didn't meet the needs of the residents. Contractor: M/S STARLIGHT PRECISION LTD. Assessor remarks: Road in bad condition, impassible.
1212 | Infrastructure, Development and Maintenance | Grading and murraming of Maji moto-Kagumu Primary school | To improve road infrastructure by grading and murraming Maji moto-Kagumu Primary school | Maji moto-Kagumu Primary school graded and murramed | 3110499 | Construction of Roads - Other | Gilgil | Murindat | -0.403679, 36.302623 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2024/25 | 7000000 | 0 | 7000000 | Equitable | N/A | 7000000 | 0 | 812223 | 100 | 812223 | 191977 | -812223 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
1213 | Infrastructure, Development and Maintenance | Grading and Murraming of roads and installation of culverts in Gitare Location, Langalanga location and Karunga Location | To improve road infrastructure by grading and murraming roads and installation of culverts in Gitare Location, Langalanga location and Karunga Location | Roads and installation of culverts in Gitare Location, Langalanga location and Karunga Location graded and murramed | 3110499 | Construction of Roads - Other | Gilgil | Murindat | -0.514958, 36.378604 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 22000000 | 739736.9 | 739736.9 | Equitable | N/A | 739736.9 | 0 | 6438205 | 870.3 | 6438205 | 739737 | -5698468.1 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/S LUMISEAL ENTERPRISES LTD,M/S KEMEMO. Assessor remarks: Good.
1214 | Infrastructure, Development and Maintenance | Rehabilitation of feeder roads at Gitare and Karunga locations | To rehabilitate feeder roads at Gitare and Karunga locations to restore functionality | Feeder roads at Gitare and Karunga locations rehabilitated | 3110499 | Construction of Roads - Other | Gilgil | Murindat | -0.527136, 36.332032 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 5831620 | 97.2 | 5831620 | 168381 | 168380 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s/ Pekima Ltd. Assessor remarks: Road in good condition.
1215 | Infrastructure, Development and Maintenance | Rehabilitation of roads at Lang langa, Gitare and Karunga in murindat ward | To rehabilitate roads at Lang langa, Gitare and Karunga in murindat ward to restore functionality | Roads at Lang langa, Gitare and Karunga in murindat ward rehabilitated | 3110499 | Construction of Roads - Other | Gilgil | Murindat | -0.525474, 36.358679 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2024/25 | 15190000 | 0 | 15190000 | Equitable | N/A | 15190000 | 0 | 5831620 | 100 | 5831620 | 168381 | -5831620 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: NGEMI CORP LTD. Assessor remarks: In good condition.
1216 | Infrastructure, Development and Maintenance | Rehabilitation of roads at Langa langa sub locations | To rehabilitate roads at Langa langa sub locations to restore functionality | Roads at Langa langa sub locations rehabilitated | 3110499 | Construction of Roads - Other | Gilgil | Murindat | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 4810854 | 4810854 | 4810854 | Equitable | N/A | 4810854 | 0 | 4623949 | 96.1 | 4623949 | 186906 | 186905 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1217 | Infrastructure, Development and Maintenance | Rehabilitation of roads in Langa langa | To rehabilitate roads in Langa langa to restore functionality | Roads in Langa langa rehabilitated | 3110499 | Construction of Roads - Other | Gilgil | Murindat | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 4611590 | 92.2 | 4611590 | 2692328 | 388410 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1218 | Infrastructure, Development and Maintenance | Rehabilitation of selected roads in Langa Langa | To rehabilitate selected roads in Langa Langa to restore functionality | Selected roads in Langa Langa rehabilitated | 3110499 | Construction of Roads - Other | Gilgil | Murindat | -0.520737, 36.375889 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2022/23 | 2700000 | 2692328 | 2692328 | Equitable | N/A | 2692328 | 0 | 2685385 | 99.7 | 2685385 | 2692328 | 6943 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/S KEMEMO WORKS AND SUPPLIES. Assessor remarks: Good.
1219 | Infrastructure, Development and Maintenance | Roads rehabilitation through Hiring of equipments across the Ward | To implement roads rehabilitation through hiring of equipments across the ward for road connectivity and accessibility | Roads rehabilitation through Hiring of equipments across the Ward completed | 3110499 | Construction of Roads - Other | Gilgil | Murindat | -0.52502, 36.375843 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2024/25 | 4042786 | 2042786 | 4042786 | Equitable | N/A | 4042786 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
1220 | Infrastructure, Development and Maintenance | Street lighting at woodlands, gatundu, momani and langa langa center | To implement street lighting at woodlands, gatundu, momani and langa langa center for road connectivity and accessibility | Street lighting at woodlands, gatundu, momani and langa langa center completed | 3110499 | Construction of Roads - Other | Gilgil | Murindat | -0.502552, 36.367833 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 2000000 | 1995900 | 1995900 | Equitable | N/A | 1995900 | 0 | 1995900 | 100 | 1995900 | 1995900 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/S BIEMDI LIMITED. Assessor remarks: Operational.
1221 | Infrastructure, Development & Maintenance | Grading and gravelling at Ha Nderitu-Kagumu primary Road | To improve road infrastructure by grading and murraming at Ha Nderitu-Kagumu primary Road | At Ha Nderitu-Kagumu primary Road graded and murramed | 3110499 | Construction of Roads - Other | Gilgil | Murindat | -0.402038, 36.293648 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1100000 | 191976.55 | 191976.55 | Equitable | N/A | 191976.55 | 0 | 812223 | 423.1 | 812223 | 191977 | -620246.45 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ahnna Supplies Company Ltd. Assessor remarks: Good.
1222 | Grading and gravelling of Kangai- Chemichemi road | Grading and gravelling of Kangai- Chemichemi road | To improve road infrastructure by grading and murraming Kangai- Chemichemi road | Kangai- Chemichemi road graded and murramed | 3110499 | Construction of Roads - Other | Gilgil | Murindat | -0.50413, 36.381348 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 17357 | 17357 | Equitable | N/A | 17357 | 0 | 1981343 | 11415.2 | 1981343 | 17357 | -1963986 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Durhas Construction. Assessor remarks: Good.
1223 | Infrastructure, Development & Maintenance | Grading and gravelling Woodard cemetery road and Drainage Works at Ngumo Road | To improve road infrastructure by grading and murraming Woodard cemetery road and Drainage Works at Ngumo Road | Woodard cemetery road and Drainage Works at Ngumo Road graded and murramed | 3110499 | Construction of Roads - Other | Gilgil | Murindat | -0.511012, 36.368231 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2442336 | 97.7 | 2442336 | 57664 | 57664 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Cubango East Limited. Assessor remarks: In good condition.
1224 | Infrastructure, Development and Maintenance | Grading and gravelling of Nyakairo road | To improve road infrastructure by grading and murraming Nyakairo road | Nyakairo road graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Naivasha East | -0.792455, 36.534807 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 991637 | 99.2 | 991637 | 1000000 | 8363 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require addition of culverts.
1225 | Infrastructure, Development & Maintenance | Grading and Gravelling of roads at Naivasha (Hiring of Machinery and equipments) | To improve road infrastructure by grading and murraming roads at Naivasha (Hiring of Machinery and equipments) | Roads at Naivasha (Hiring of Machinery and equipments) graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Naivasha East | -0.826234 36.53653 2480 5.611999988555908 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3995600 | 99.9 | 3995600 | 3000000 | 4400 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require regular mainatance.
1226 | Infrastructure, Development and Maintenance | Grading and gravelling of roads in Naivasha East Ward- Imarisha barabara | To improve road infrastructure by grading and murraming roads in Naivasha East Ward- Imarisha barabara | Roads in Naivasha East Ward- Imarisha barabara graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Naivasha East | -0.745223 36.476318 2091.500244140625 3.75 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 661276 | 661276 | 661276 | Equitable | N/A | 661276 | 0 | 300000 | 45.4 | 300000 | 3000000 | 361276 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Ues. Assessor remarks: Require regular maintenance.
1227 | Grading and gravelling of Thome Wa Munyu road-GUCUGA AP Post, Sindano road, Run-together road and Kahuho road through boresha | Grading and gravelling of Thome Wa Munyu road-GUCUGA AP Post, Sindano road, Run-together road and Kahuho road through boresha | To improve road infrastructure by grading and murraming Thome Wa Munyu road-GUCUGA AP Post, Sindano road, Run-together road and Kahuho road through boresha | Thome Wa Munyu road-GUCUGA AP Post, Sindano road, Run-together road and Kahuho road through boresha graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Naivasha East | -0.842973 36.556068 2599 6.122000217437744 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 1872.5 | 1872.5 | Equitable | N/A | 1872.5 | 0 | 2993293 | 159855.4 | 2993293 | 1873 | -2991420.5 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Poor drainage requires caravat.
1228 | Infrastructure, Development and Maintenance | Grading And Murraming of Access Roads- Hire of machineries in Naivasha East Ward | To improve road infrastructure by grading and murraming Access Roads- Hire of machineries in Naivasha East Ward | Access Roads- Hire of machineries in Naivasha East Ward graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Naivasha East | -0.849131, 36.547446 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2024 | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 300000 | 100 | 300000 | 3000000 | -300000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Regular maintenance but gravelling should be be increased.
1229 | Infrastructure, Development and Maintenance | Grading and murraming of Acre Moja Road | To improve road infrastructure by grading and murraming Acre Moja Road | Acre Moja Road graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Naivasha East | -0.86648, 36.538122 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2025 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 768900 | 25.6 | 768900 | 768900 | 2231100 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require gravelling.
1230 | Infrastructure, Development and Maintenance | Grading and murraming of Acre Moja-Kiambogo road | To improve road infrastructure by grading and murraming Acre Moja-Kiambogo road | Acre Moja-Kiambogo road graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Naivasha East | -0.86648, 36.538122 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2025 | 1000000 | 768900 | 768900 | Equitable | N/A | 768900 | 0 | 768900 | 100 | 768900 | 768900 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require gravelling.
1231 | Infrastructure, Development & Maintenance | Grading and murraming of Kahuho road and installation of culverts | To improve road infrastructure by grading and murraming Kahuho road and installation of culverts | Kahuho road and installation of culverts graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Naivasha East | -0.881628, 36.55029 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2022 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1781750 | 89.1 | 1781750 | 718600 | 218250 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good workmanship.
1232 | Grading and murraming of Kenvash-Guchuga road and Kinungi-Nyandarua road | Grading and murraming of Kenvash-Guchuga road and Kinungi-Nyandarua road | To improve road infrastructure by grading and murraming Kenvash-Guchuga road and Kinungi-Nyandarua road | Kenvash-Guchuga road and Kinungi-Nyandarua road graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Naivasha East | -0.840637, 36.54841 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020-21 | 1000000 | 718600 | 718600 | Equitable | N/A | 718600 | 0 | 718600 | 100 | 718600 | 718600 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
1233 | Infrastructure, Development and Maintenance | Grading and murraming of roads in Naivasha East Ward- hire of machinery | To improve road infrastructure by grading and murraming roads in Naivasha East Ward- hire of machinery | Roads in Naivasha East Ward- hire of machinery graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Naivasha East | -0.813922, 36.544971 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 300000 | 5 | 300000 | 3000000 | 5700000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Granding and gravelling ongoing.
1234 | Infrastructure, Development and Maintenance | Grading, murraming of Nyakairo Road | To implement grading, murraming of nyakairo road for road connectivity and accessibility | Grading, murraming of Nyakairo Road completed | 3110499 | Construction of Roads - Other | Naivasha | Naivasha East | -0.792455, 36.534807 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 991637 | 100 | 991637 | 2000000 | -991637 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require addition of culverts.
1235 | Road rehabilitation and maintenance (hire of machinery for rehabiltation of Naivasha East access roads) | Road rehabilitation and maintenance (hire of machinery for rehabiltation of Naivasha East access roads) | To implement road rehabilitation and maintenance (hire of machinery for rehabiltation of naivasha east access roads) for road connectivity and accessibility | Road rehabilitation and maintenance (hire of machinery for rehabiltation of Naivasha East access roads) completed | 3110499 | Construction of Roads - Other | Naivasha | Naivasha East | -0.861268, 36.541282 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2022 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2500000 | 100 | 2500000 | 2500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require regular maintenance and gravelling.
1236 | Infrastructure, Development and Maintenance | Road Rehabilitation - Hire of equipment for roads Maintenance | To implement road rehabilitation - hire of equipment for roads maintenance for road connectivity and accessibility | Road Rehabilitation - Hire of equipment for roads Maintenance completed | 3110499 | Construction of Roads - Other | Naivasha | Naivasha East | -0.785525, 36.533707 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2023 | 4000000 | 0 | 686409 | Equitable | N/A | 686409 | 0 | 2699525 | 100 | 2699525 | 686409 | -2699525 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Consider increasing funding in future for wide coverage.
1237 | Infrastructure, Development and Maintenance | Routine Maintenance of Halian-Marari Road | To maintain Halian-Marari Road in serviceable condition | Halian-Marari Road maintained | 3110499 | Construction of Roads - Other | Naivasha | Naivasha East | -0.74819 36.470822 2071.60009765625 4.199999809265137 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1369400 | 91.3 | 1369400 | 787539 | 130600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require regular maintenance.
1238 | Infrastructure, Development & Maintenance | Routine maintenance of Kayole-Italian-Kinamba road | To maintain Kayole-Italian-Kinamba road in serviceable condition | Kayole-Italian-Kinamba road maintained | 3110499 | Construction of Roads - Other | Naivasha | Naivasha East | -0.74819 36.470822 2071.60009765625 4.199999809265137 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 787539 | 787539 | Equitable | N/A | 787539 | 0 | 787539 | 100 | 787539 | 787539 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require regular maintenance.
1239 | Infrastructure, Development & Maintenance | Routine maintenance of Maraigushu-Church road | To maintain Maraigushu-Church road in serviceable condition | Maraigushu-Church road maintained | 3110499 | Construction of Roads - Other | Naivasha | Naivasha East | -0.744489, 36.511607 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2022 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 959110 | 95.9 | 959110 | 787539 | 40890 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Usable.
1240 | Grading And Murraming Of California Estate | Grading And Murraming Of California Estate | To improve road infrastructure by grading and murraming California Estate | California Estate graded and murramed | 3110499 | Construction of Roads - Other | Nakuru East | Nakuru East | -0.378443, 36.151903 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/2021 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1353000 | 90.2 | 1353000 | 1500000 | 147000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Babuye investments limited. Assessor remarks: Complete.
1241 | Infrastructure, Development & Maintenance | Grading And Murraming Of Kamukunji And Shimo Mbili Estate | To improve road infrastructure by grading and murraming Kamukunji And Shimo Mbili Estate | Kamukunji And Shimo Mbili Estate graded and murramed | 3110499 | Construction of Roads - Other | Nakuru East | Nakuru East | -0.405603, 36.155024 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 20202021 | 1500000 | 1350000 | 1350000 | Equitable | N/A | 1350000 | 0 | 1349085 | 99.9 | 1349085 | 1350000 | 915 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Techfieod system limited. Assessor remarks: Project complete.
1242 | Grading And Murraming Of Mwangaza Estate | Grading And Murraming Of Mwangaza Estate | To improve road infrastructure by grading and murraming Mwangaza Estate | Mwangaza Estate graded and murramed | 3110499 | Construction of Roads - Other | Nakuru East | Nakuru East | -0.378443, 36.151903 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/2021 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2244300 | 89.8 | 2244300 | 2500000 | 255700 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Babuye investments limited. Assessor remarks: Complete.
1243 | Infrastructure, Development and Maintenance | Grading and Murraming of Mzee Wanyama access Roads | To improve road infrastructure by grading and murraming Mzee Wanyama access Roads | Mzee Wanyama access Roads graded and murramed | 3110499 | Construction of Roads - Other | Nakuru East | Nakuru East | -0.405637, 36.14086 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/2022 | 1400155 | 1246478 | 1246478 | Equitable | N/A | 1246478 | 0 | 1242320 | 99.7 | 1242320 | 4159 | 4158 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Kirgot enterprises. Assessor remarks: Grading needed.
1244 | Infrastructure, Development and Maintenance | Grading and Murraming of Mzee Wanyama Roads | To improve road infrastructure by grading and murraming Mzee Wanyama Roads | Mzee Wanyama Roads graded and murramed | 3110499 | Construction of Roads - Other | Nakuru East | Nakuru East | -0.405637, 36.14086 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/2022 | 3000000 | 152679.45 | 152679.45 | Equitable | N/A | 152679.45 | 0 | 152679 | 100 | 152679 | 152679 | 0.45 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Kirgot enterprises. Assessor remarks: Grading needed.
1245 | Infrastructure, Development and Maintenance | Grading And Punching Of JB-Mzee Wanyama Road | To improve road accessibility by grading And Punching Of JB-Mzee Wanyama Road | And Punching Of JB-Mzee Wanyama Road graded | 3110499 | Construction of Roads - Other | Nakuru East | Nakuru East | -0.360122 36.149943 1876.5 4.300000190734863 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1636482 | 1411250 | 1411250 | Equitable | N/A | 1411250 | 0 | 1411015 | 100 | 1411015 | 0 | 235 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Techfield system limited. Assessor remarks: Its in good condition.
1246 | Infrastructure, Development and Maintenance | Hire of machinery for roads maintenance and installation of culverts across the Ward | To implement hire of machinery for roads maintenance and installation of culverts across the ward for road connectivity and accessibility | Hire of machinery for roads maintenance and installation of culverts across the Ward completed | 3110499 | Construction of Roads - Other | Nakuru East | Nakuru East | -0.394692, 36.144847 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2024/2025 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1266477 | 63.3 | 1266477 | 733523 | 733523 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Project will serve residents.
1247 | Infrastructure, Development and Maintenance | Murraming And Grading of Roads and Installation of Culverts Across the Ward through Imarisha barabara programme | To implement murraming and grading of roads and installation of culverts across the ward through imarisha barabara programme for road connectivity and accessibility | Murraming And Grading of Roads and Installation of Culverts Across the Ward through Imarisha barabara programme completed | 3110499 | Construction of Roads - Other | Nakuru East | Nakuru East | -0.405448, 36.149433 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 2000000 | 0 | 733523 | Equitable | N/A | 733523 | 0 | 1266477 | 100 | 1266477 | 733523 | -1266477 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Project complete.
1248 | Infrastructure, Development and Maintenance | Bush clearing across the ward | To improve the condition of across the ward | Across the ward improved | 3110499 | Construction of Roads - Other | Njoro | Nessuit | -0.411305, 35.942585 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 500000 | 0 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The work was done and the road requires regular Bush clearing.
1249 | Infrastructure, Development and Maintenance | Completion of Kamugulet Bridge | To complete Kamugulet Bridge | Kamugulet Bridge completed | 3110499 | Construction of Roads - Other | Njoro | Nessuit | -0.424083, 35.907561 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 2296800 | 100 | 2296800 | 1000000 | -2296800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The bridge is in good condition and serving the residents well. However the road needs murram to cover the big stones making it difficult for motorists to pass.
1250 | Infrastructure, Development and Maintenance | Construction of a bridge at Kaplembika | To construct a bridge at Kaplembika | A bridge at Kaplembika constructed | 3110499 | Construction of Roads - Other | Njoro | Nessuit | -0.396605, 35.871823 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2024/25 | 1200000 | 0 | 1200000 | Equitable | N/A | 1200000 | 0 | 2296800 | 100 | 2296800 | 1200000 | -2296800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Money allocated was not enough to construct a bridge, therefore the money was reallocated..
1251 | Infrastructure, Development & Maintenance | Grading And Murraming And Culverts Of Amos Arap Kangongo Road | To improve road infrastructure by grading and murraming And Culverts Of Amos Arap Kangongo Road | And Culverts Of Amos Arap Kangongo Road graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Nessuit | -0.415259, 35.949121 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2019/20 | 2000000 | 1999400 | 1999400 | Equitable | N/A | 1999400 | 0 | 1999400 | 100 | 1999400 | 1999400 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is a continuous from Amos Kangogo road, it is Amos -Amani road..
1252 | Infrastructure, Development & Maintenance | Grading And Murraming And Culverts Of Cheptebes- Elkana Road | To improve road infrastructure by grading and murraming And Culverts Of Cheptebes- Elkana Road | And Culverts Of Cheptebes- Elkana Road graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Nessuit | -0.412079, 35.937341 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2019/20 | 2000000 | 619479.5 | 619479.5 | Equitable | N/A | 619479.5 | 0 | 619480 | 100 | 619480 | 619480 | -0.5 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is motorable and functional, it requires regular maintenance.
1253 | Infrastructure, Development and Maintenance | Grading And Murraming of Access Roads- Imarisha Barabara in Nessuit Ward | To improve road infrastructure by grading and murraming Access Roads- Imarisha Barabara in Nessuit Ward | Access Roads- Imarisha Barabara in Nessuit Ward graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Nessuit | -0.41331 35.93147 2402.864532420494 7.486000061035156 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 2500000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 1500000 | 100 | 1500000 | 1000000 | -1500000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road requires improvement.
1254 | Infrastructure, Development & Maintenance | Grading And Murraming Of Kamara-Kamasit Roads | To improve road infrastructure by grading and murraming Kamara-Kamasit Roads | Kamara-Kamasit Roads graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Nessuit | -0.419334, 35.932833 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 997604 | 997604 | Equitable | N/A | 997604 | 0 | 2333210 | 233.9 | 2333210 | 997604 | -1335606 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/S Beliot investment limited. Assessor remarks: The road requires regular maintenance.
1255 | Infrastructure, Development and Maintenance | Grading and murraming of Kapketiro-Sigaon road | To improve road infrastructure by grading and murraming Kapketiro-Sigaon road | Kapketiro-Sigaon road graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Nessuit | -0.429883, 35.887503 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 2379423 | 2379423 | 2379423 | Equitable | N/A | 2379423 | 0 | 2333210 | 98.1 | 2333210 | 46214 | 46213 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: Yes. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The road was halfway done.
1256 | Infrastructure, Development & Maintenance | Grading, Murraming And Culverting Of Cutline-Kamasut Road | To implement grading, murraming and culverting of cutline-kamasut road for road connectivity and accessibility | Grading, Murraming And Culverting Of Cutline-Kamasut Road completed | 3110499 | Construction of Roads - Other | Njoro | Nessuit | -0.428558, 35.933756 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 1999490.2 | 1999490.2 | Equitable | N/A | 1999490.2 | 0 | 1995518 | 99.8 | 1995518 | 1999490 | 3972.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is in good condition, it just needs regular maintenance.
1257 | Infrastructure, Development & Maintenance | Grading, Murraming And Culverting Of Junction-Kap Jona-Cheporgei | To implement grading, murraming and culverting of junction-kap jona-cheporgei for road connectivity and accessibility | Grading, Murraming And Culverting Of Junction-Kap Jona-Cheporgei completed | 3110499 | Construction of Roads - Other | Njoro | Nessuit | -0.417985, 35.882619 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 1840920 | 1840920 | Equitable | N/A | 1840920 | 0 | 1840920 | 100 | 1840920 | 1840920 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: The road is in poor condition and requires urgent improvement.
1258 | Infrastructure, Development and Maintenance | Grading & Murraming of KAP Councilor - Tuei borehole - Kap Koigeloo road | To improve road accessibility by grading & Murraming of KAP Councilor - Tuei borehole - Kap Koigeloo road | & Murraming of KAP Councilor - Tuei borehole - Kap Koigeloo road graded | 3110499 | Construction of Roads - Other | Njoro | Nessuit | -0.369016, 35.876727 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 2000000 | 2000000 | 4100000 | Equitable | N/A | 4100000 | 0 | 2333210 | 116.7 | 2333210 | 2495856 | -333210 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yet to start. Viable: Yet to start. Assessor remarks: Project yet to start.
1259 | Hire Of Machineries And Road Equipments | Hire Of Machineries And Road Equipments | To implement hire of machineries and road equipments for road connectivity and accessibility | Hire Of Machineries And Road Equipments completed | 3110499 | Construction of Roads - Other | Njoro | Nessuit | -0.429181, 35.914642 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2500000 | 100 | 2500000 | 2500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: Project yet to start. Viable: Project yet to start. Assessor remarks: Project stalled due to lack of fuel for the equipments.
1260 | Infrastructure, Development and Maintenance | Installation of culverts at Sigotik | To improve drainage and road access through culvert installation at Sigotik | Culverts installed at Sigotik | 3110499 | Construction of Roads - Other | Njoro | Nessuit | -0.429535 35.91303 2519.8181831532115 5.734000205993652 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 971755 | 97.2 | 971755 | 28246 | 28245 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Culverts require regular unclogging.
1261 | Infrastructure, Development and Maintenance | Murram and fuel for boresha barabara | To implement murram and fuel for boresha barabara for road connectivity and accessibility | Murram and fuel for boresha barabara completed | 3110499 | Construction of Roads - Other | Njoro | Nessuit | -0.359941 35.87825 2420.552922772206 4.163000106811523 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 1500000 | 0 | 1500000 | Equitable | N/A | 1500000 | 0 | 1000000 | 100 | 1000000 | 1500000 | -1000000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road needs improvement.
1262 | Infrastructure, Development and Maintenance | Opening of agricultural roads across the Ward | To improve the condition of agricultural roads across the Ward | Agricultural roads across the Ward improved | 3110499 | Construction of Roads - Other | Njoro | Nessuit | -0.409598, 35.932627 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2024/25 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1794420 | 119.6 | 1794420 | 1797420 | -294420 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The roads are in good condition.
1263 | Infrastructure, Development & Maintenance | Routine Maintenance And Spot Improvement Of Kasa Roho - Mathias - Kamara Road In Nessuit Ward Njoro Sub County | To maintain Spot Improvement Of Kasa Roho - Mathias - Kamara Road In Nessuit Ward Njoro Sub County in serviceable condition | Spot Improvement Of Kasa Roho - Mathias - Kamara Road In Nessuit Ward Njoro Sub County maintained | 3110499 | Construction of Roads - Other | Njoro | Nessuit | -0.416054, 35.949283 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2019/20 | 1000000 | 975212 | 975212 | Equitable | N/A | 975212 | 0 | 975149 | 100 | 975149 | 975212 | 63 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is motorable but requires regular maintenance.
1264 | Supply Of Murram Though Boresha Barabara | Supply Of Murram Though Boresha Barabara | To implement supply of murram though boresha barabara for road connectivity and accessibility | Supply Of Murram Though Boresha Barabara completed | 3110499 | Construction of Roads - Other | Njoro | Nessuit | -0.415382, 35.918672 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yet to start. Viable: Project yet to start. Assessor remarks: Project yet to start.
1265 | Infrastructure, Development and Maintenance | Grading and Murraming and installation of two 600 mm culverts at Mogas Industrial Area and Njoro Day | To improve road infrastructure by grading and murraming and installation of two 600 mm culverts at Mogas Industrial Area and Njoro Day | And installation of two 600 mm culverts at Mogas Industrial Area and Njoro Day graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Njoro | -0.385656 35.936259 2285.187744140625 6.638000011444092 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 2654864 | 100 | 2654864 | 2000000 | -2654864 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: In fair condition.
1266 | Infrastructure, Development and Maintenance | Grading And Murraming of Access Roads- Imarisha Barabara in Njoro Ward | To improve road infrastructure by grading and murraming Access Roads- Imarisha Barabara in Njoro Ward | Access Roads- Imarisha Barabara in Njoro Ward graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Njoro | -0.340559 35.951069 1044.5999755859375 7.118000030517578 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 4000000 | 0 | 1200000 | Equitable | N/A | 1200000 | 0 | 1800000 | 100 | 1800000 | 1200000 | -1800000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: Good work.
1267 | Infrastructure, Development and Maintenance | Grading And Murraming of Beeston-Rurii Village Roads and Installation of Three 600mm Culverts | To improve road infrastructure by grading and murraming Beeston-Rurii Village Roads and Installation of Three 600mm Culverts | Beeston-Rurii Village Roads and Installation of Three 600mm Culverts graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Njoro | -0.361805, 35.908936 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2024 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2654864 | 88.5 | 2654864 | 345136 | 345136 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yet to start. Viable: Yet to start. Contractor: Not available. Assessor remarks: Yet to start.
1268 | Infrastructure, Development and Maintenance | Grading And Murraming of Kenyatta Stage to Cheseton junction | To improve road infrastructure by grading and murraming Kenyatta Stage to Cheseton junction | Kenyatta Stage to Cheseton junction graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Njoro | -0.338096, 35.968071 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2024 | 3000000 | 0 | 973124.35 | Equitable | N/A | 973124.35 | 0 | 2026876 | 100 | 2026876 | 973124 | -2026876 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Amogracia contractor Ltd. Assessor remarks: In good state.
1269 | Infrastructure, Development and Maintenance | Grading and Murraming of Njoro Day Road | To improve road infrastructure by grading and murraming Njoro Day Road | Njoro Day Road graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Njoro | -0.332953, 35.946213 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2024 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1930021 | 96.5 | 1930021 | 69979 | 69979 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/S Amogracia Constructor. Assessor remarks: Good work.
1270 | Infrastructure, Development and Maintenance | Grading And Murraming of Njoro KCB - Konza Road | To improve road infrastructure by grading and murraming Njoro KCB - Konza Road | Njoro KCB - Konza Road graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Njoro | -0.340559 35.951069 1044.5999755859375 7.118000030517578 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 69979 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: Good work.
1271 | Infrastructure, Development and Maintenance | Grading And Murraming of Njoro Police-Jewathu-PCEA Road | To improve road infrastructure by grading and murraming Njoro Police-Jewathu-PCEA Road | Njoro Police-Jewathu-PCEA Road graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Njoro | -0.332953, 35.946213 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2024 | 3000000 | 0 | 682687.95 | Equitable | N/A | 682687.95 | 0 | 2317312 | 100 | 2317312 | 682688 | -2317312 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/S Amogracia Constructor. Assessor remarks: Good work.
1272 | Infrastructure, Development and Maintenance | Grading and murraming of Njoro ward roads - Hiring of boresha barabara equipments | To improve road infrastructure by grading and murraming Njoro ward roads - Hiring of boresha barabara equipments | Njoro ward roads - Hiring of boresha barabara equipments graded and murramed | 3110499 | Construction of Roads - Other | Njoro | Njoro | -0.340559 35.951069 1044.5999755859375 7.118000030517578 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 8500000 | 8500000 | 8500000 | Equitable | N/A | 8500000 | 0 | 8499685 | 100 | 8499685 | 8500000 | 315 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: Good work.
1273 | Infrastructure, Development and Maintenance | Grading, fueling & murraming - Imarisha barabara programme | To implement grading, fueling & murraming - imarisha barabara programme for road connectivity and accessibility | Grading, fueling & murraming - Imarisha barabara programme completed | 3110499 | Construction of Roads - Other | Njoro | Njoro | -0.340559 35.951069 1044.5999755859375 7.118000030517578 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2024/25 | 1311995 | 1311995 | 3311995 | Equitable | N/A | 3311995 | 0 | 1300000 | 99.1 | 1300000 | 1200000 | 11995 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: Good work.
1274 | Infrastructure, Development and Maintenance | Grading & Murraming Louis Centre - Piave - Jesus is Lord junction | To improve road accessibility by grading & Murraming Louis Centre - Piave - Jesus is Lord junction | & Murraming Louis Centre - Piave - Jesus is Lord junction graded | 3110499 | Construction of Roads - Other | Njoro | Njoro | -0.385656 35.936259 2285.187744140625 6.638000011444092 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2026876 | 67.6 | 2026876 | 973124 | 973124 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: In fair condition.
1275 | Infrastructure, Development and Maintenance | Grading & murraming - Night Gale to Kenana Gatabaki road | To improve road accessibility by grading & murraming - Night Gale to Kenana Gatabaki road | & murraming - Night Gale to Kenana Gatabaki road graded | 3110499 | Construction of Roads - Other | Njoro | Njoro | -0.302031 35.891603 2245.38916015625 10.288999557495117 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 1000000 | 33.3 | 1000000 | 69979 | 2000000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: Worn out due to rain.
1276 | Infrastructure, Development and Maintenance | Heavy Grading and Murraming of AIC Lochorai-Michorwe Sigotik Caves Roads | To implement heavy grading and murraming of aic lochorai-michorwe sigotik caves roads for road connectivity and accessibility | Heavy Grading and Murraming of AIC Lochorai-Michorwe Sigotik Caves Roads completed | 3110499 | Construction of Roads - Other | Njoro | Njoro | -0.385763, 35.936167 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2024 | 2500000 | 0 | 2500000 | Equitable | N/A | 2500000 | 0 | 3000000 | 100 | 3000000 | 2500000 | -3000000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: In good state.
1277 | Infrastructure, Development and Maintenance | Heavy Grading and Murraming of Midway Junction-Tarmac Road | To implement heavy grading and murraming of midway junction-tarmac road for road connectivity and accessibility | Heavy Grading and Murraming of Midway Junction-Tarmac Road completed | 3110499 | Construction of Roads - Other | Njoro | Njoro | -0.361731, 35.942382 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2024 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 3000000 | 100 | 3000000 | 69979 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: In good state.
1278 | Infrastructure, Development and Maintenance | Heavy grading & murraming, installation of 900mm culvert, two lanes in Upper Belbur - Musonic - Mutano road | To implement heavy grading & murraming, installation of 900mm culvert, two lanes in upper belbur - musonic - mutano road for road connectivity and accessibility | Heavy grading & murraming, installation of 900mm culvert, two lanes in Upper Belbur - Musonic - Mutano road completed | 3110499 | Construction of Roads - Other | Njoro | Njoro | -0.392658, 35.955744 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2025 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yet to start. Viable: Yet to start. Contractor: Not available. Assessor remarks: Needy.
1279 | Infrastructure, Development & Maintenance | Hiring Of Boresha Barabara Machineries | To implement hiring of boresha barabara machineries for road connectivity and accessibility | Hiring Of Boresha Barabara Machineries completed | 3110499 | Construction of Roads - Other | Njoro | Njoro | -0.302031 35.891603 2245.38916015625 10.288999557495117 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 8300000 | 8000000 | 8000000 | Equitable | N/A | 8000000 | 0 | 6997045 | 87.5 | 6997045 | 8000000 | 1002955 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: Worn out due to rain.
1280 | Infrastructure, Development & Maintenance | Purchase and Supply Of Murram | To procure and supply Murram | Murram procured and supplied | 3110499 | Construction of Roads - Other | Njoro | Njoro | -0.376968 35.942036 2214.500244140625 42.5 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 3792710 | 2000000 | 3792710 | Equitable | N/A | 3792710 | 0 | 3792710 | 189.6 | 3792710 | 2000000 | -1792710 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: In fair state.
1281 | Infrastructure, Development & Maintenance | Construction of Chesirikwa shed | To construct Chesirikwa shed | Chesirikwa shed constructed | 3110499 | Construction of Roads - Other | Kuresoi North | Nyota | -0.410803 35.655528 2673.7 13.800000190734863 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 400000 | 317534 | 317534 | Equitable | N/A | 317534 | 0 | 317534 | 100 | 317534 | 317534 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs urgent painting..
1282 | Infrastructure, Development & Maintenance | Construction of Roads in Nyota Ward -Hiring of machinery/equipment | To construct Roads in Nyota Ward -Hiring of machinery/equipment | Roads in Nyota Ward -Hiring of machinery/equipment constructed | 3110499 | Construction of Roads - Other | Kuresoi North | Nyota | -0.300447 35.59213 2720.8 11.699999809265137 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 4166584 | 4166584 | 4166584 | Equitable | N/A | 4166584 | 0 | 3998922 | 96 | 3998922 | 0 | 167662 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: YES. Viable: YES. Contractor: _. Assessor remarks: IT WILL BE BENEFICIAL TO COMMUNITY.
1283 | Infrastructure, Development & Maintenance | Grading and murraming Mkeu road | To improve road infrastructure by grading and murraming Mkeu road | Mkeu road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi North | Nyota | -0.301497 35.59234 2716 3.700000047683716 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1499575 | 1499575 | Equitable | N/A | 1499575 | 0 | 1499575 | 100 | 1499575 | 1499575 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: YES. Viable: YES. Contractor: _. Assessor remarks: NEED DRAINAGE AND SPOT BATCHING.
1284 | Infrastructure, Development and Maintenance | Grading and murraming of 3 PS road | To improve road infrastructure by grading and murraming 3 PS road | 3 PS road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi North | Nyota | -0.378012, 35.688995 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2024-2025 | 1500000 | 1499461 | 1499461 | Equitable | N/A | 1499461 | 0 | 1498217 | 99.9 | 1498217 | 1499461 | 1244 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: SHARPQUEEN ENTERPRISES. Assessor remarks: Well done.
1285 | Infrastructure, Development and Maintenance | Grading and murraming of ADC,chesirikwo and saboi road | To improve road infrastructure by grading and murraming ADC,chesirikwo and saboi road | ADC,chesirikwo and saboi road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi North | Nyota | -0.415393, 35.629297 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2024-2025 | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 1999849 | 0 | 1999849 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Some pots need refill- spot patches..
1286 | Infrastructure, Development & Maintenance | Grading and murraming of Baringo valley road | To improve road infrastructure by grading and murraming Baringo valley road | Baringo valley road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi North | Nyota | -0.301497 35.59234 2716 3.700000047683716 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1374920 | 1374920 | Equitable | N/A | 1374920 | 0 | 1374920 | 100 | 1374920 | 1374920 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: YES. Viable: YES. Contractor: _. Assessor remarks: NEED DRAINAGE AND SPOT BATCHING.
1287 | Infrastructure, Development and Maintenance | Grading And Murraming of Bridge Matunda Road | To improve road infrastructure by grading and murraming Bridge Matunda Road | Bridge Matunda Road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi North | Nyota | -0.388303, 35.628555 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2024-2025 | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 1836395 | 100 | 1836395 | 1000000 | -1836395 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Not yet. Viable: Yes. Assessor remarks: Side grills are missing, Refl.
1288 | Infrastructure, Development and Maintenance | Grading And Murraming of Chesaini Cheborbai Will Road | To improve road infrastructure by grading and murraming Chesaini Cheborbai Will Road | Chesaini Cheborbai Will Road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi North | Nyota | -0.301497 35.59234 2716 3.700000047683716 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 1374920 | 100 | 1374920 | 3000000 | -1374920 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: YES. Viable: YES. Contractor: _. Assessor remarks: NEED DRAINAGE AND SPOT BATCHING.
1289 | Infrastructure, Development and Maintenance | Grading and Murraming of Chesingele - Omari Road | To improve road infrastructure by grading and murraming Chesingele - Omari Road | Chesingele - Omari Road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi North | Nyota | -0.388303, 35.628555 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2024-2025 | 2500000 | 190721 | 190721 | Equitable | N/A | 190721 | 0 | 561629 | 294.5 | 561629 | 190721 | -370908 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Not yet. Viable: Yes. Assessor remarks: Side grills are missing, Refl.
1290 | Infrastructure, Development & Maintenance | Grading and murraming of Kamore road | To improve road infrastructure by grading and murraming Kamore road | Kamore road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi North | Nyota | -0.301497 35.59234 2716 3.700000047683716 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 1828545 | 1828545 | Equitable | N/A | 1828545 | 0 | 1828545 | 100 | 1828545 | 1828545 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: YES. Viable: YES. Contractor: _. Assessor remarks: NEED DRAINAGE AND SPOT BATCHING.
1291 | Infrastructure, Development and Maintenance | Grading and Murraming of Kondomet Soweto | To improve road infrastructure by grading and murraming Kondomet Soweto | Kondomet Soweto graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi North | Nyota | -0.361698 35.650313 2691.7 67.4000015258789 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 1066584 | 769090 | 769090 | Equitable | N/A | 769090 | 0 | 769090 | 100 | 769090 | 769090 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs urgent spot patches..
1292 | Infrastructure, Development and Maintenance | Grading and murraming of Masaita road | To improve road infrastructure by grading and murraming Masaita road | Masaita road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi North | Nyota | -0.378012, 35.688995 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2024-2025 | 1500000 | 1499715 | 1499715 | Equitable | N/A | 1499715 | 0 | 1499715 | 100 | 1499715 | 1499715 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: SHARPQUEEN ENTERPRISES. Assessor remarks: Well done.
1293 | Infrastructure, Development and Maintenance | Grading and murraming of Ng'arua-Silibonik Road | To improve road infrastructure by grading and murraming Ng'arua-Silibonik Road | Ng'arua-Silibonik Road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi North | Nyota | -0.338628 35.597783 2620.9 10.899999618530273 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1200000 | 100 | 1200000 | 1200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Fair- Needs routen Maintenance: Culverts, Graveling etc..
1294 | Infrastructure, Development and Maintenance | Grading And Murraming of Roads Through Imarisha Barabara Programme | To improve road infrastructure by grading and murraming Roads Through Imarisha Barabara Programme | Roads Through Imarisha Barabara Programme graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi North | Nyota | -0.301497 35.59234 2716 3.700000047683716 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 1998884 | 0 | 1998884 | 1499461 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: YES. Viable: YES. Contractor: _. Assessor remarks: NEED DRAINAGE AND SPOT BATCHING.
1295 | Infrastructure, Development and Maintenance | Grading and murraming of Sasimua road | To improve road infrastructure by grading and murraming Sasimua road | Sasimua road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi North | Nyota | -0.378012, 35.688995 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2024-2025 | 2000000 | 1836395 | 1836395 | Equitable | N/A | 1836395 | 0 | 1836395 | 100 | 1836395 | 1836395 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: SHARPQUEEN ENTERPRISES. Assessor remarks: Well done.
1296 | Infrastructure, Development and Maintenance | Grading and murraming of Seguton songo road | To improve road infrastructure by grading and murraming Seguton songo road | Seguton songo road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi North | Nyota | -0.378012, 35.688995 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2024-2025 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1966913 | 196.7 | 1966913 | 362100 | -966913 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: SHARPQUEEN ENTERPRISES. Assessor remarks: Well done.
1297 | Infrastructure, Development and Maintenance | Grading and Murraming of Songo Musola Road | To improve road infrastructure by grading and murraming Songo Musola Road | Songo Musola Road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi North | Nyota | -0.378012, 35.688995 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2024-2025 | 2400000 | 362100 | 362100 | Equitable | N/A | 362100 | 0 | 1966913 | 543.2 | 1966913 | 362100 | -1604813 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: SHARPQUEEN ENTERPRISES. Assessor remarks: Well done.
1298 | Infrastructure, Development & Maintenance | Grading, graveling and murraming of Lagweda, Bosire, Willa/Kagundu and Tonongoi Roads | To implement grading, graveling and murraming of lagweda, bosire, willa/kagundu and tonongoi roads for road connectivity and accessibility | Grading, graveling and murraming of Lagweda, Bosire, Willa/Kagundu and Tonongoi Roads completed | 3110499 | Construction of Roads - Other | Kuresoi North | Nyota | -0.301497 35.59234 2716 3.700000047683716 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 10500000 | 10500000 | 10500000 | Equitable | N/A | 10500000 | 0 | 9298740 | 88.6 | 9298740 | 2912958 | 1201260 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: YES. Viable: YES. Contractor: _. Assessor remarks: NEED DRAINAGE AND SPOT BATCHING.
1299 | Infrastructure, Development & Maintenance | Grading, Gravelling and compaction of Aremi Sitoito road | To implement grading, gravelling and compaction of aremi sitoito road for road connectivity and accessibility | Grading, Gravelling and compaction of Aremi Sitoito road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Nyota | -0.37899, 35.585875 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2017-2018 | 1412958 | 2912958 | 2912958 | Equitable | N/A | 2912958 | 0 | 2912958 | 100 | 2912958 | 2912958 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: Yes. Condition: Bad. Objective met: No. Viable: Yes if done. Assessor remarks: Bad state- Needs urgent attention..
1300 | Infrastructure, Development and Maintenance | Grading, Murraming and gravelling of Kamuri-Ndege Wairungi Road | To implement grading, murraming and gravelling of kamuri-ndege wairungi road for road connectivity and accessibility | Grading, Murraming and gravelling of Kamuri-Ndege Wairungi Road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Nyota | -0.308548, 35.645022 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | _ | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: YES. Viable: YES. Contractor: _. Assessor remarks: ACCESSIBLE.
1301 | Infrastructure, Development & Maintenance | Gravelling and murraming of 3km of Mawingu Centre to lami juu road | To implement gravelling and murraming of 3km of mawingu centre to lami juu road for road connectivity and accessibility | Gravelling and murraming of 3km of Mawingu Centre to lami juu road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Nyota | -0.301497 35.59234 2716 3.700000047683716 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 2962988 | 2962988 | Equitable | N/A | 2962988 | 0 | 2962988 | 100 | 2962988 | 2962988 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: YES. Viable: YES. Contractor: _. Assessor remarks: NEED DRAINAGE AND SPOT BATCHING.
1302 | Infrastructure, Development and Maintenance | Hiring of equipments for roads network | To implement hiring of equipments for roads network for road connectivity and accessibility | Hiring of equipments for roads network completed | 3110499 | Construction of Roads - Other | Kuresoi North | Nyota | -0.391423 35.716408 2718.2 14.399999618530273 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 10129723 | 0 | 10129723 | Equitable | N/A | 10129723 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: HOLSAN HOLDING LTD. Assessor remarks: Good.
1303 | Infrastructure, Development & Maintenance | Grading and gravelling of Muchorwe-Sasimua-Githiriga-Kamwaura road, Tegea access roads and Mwahe-Soimet-Masaita road | To improve road infrastructure by grading and murraming Muchorwe-Sasimua-Githiriga-Kamwaura road, Tegea access roads and Mwahe-Soimet-Masaita road | Muchorwe-Sasimua-Githiriga-Kamwaura road, Tegea access roads and Mwahe-Soimet-Masaita road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi North | Nyota | -0.350325 35.637462 2686.6 22.600000381469727 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 8500000 | 3349718 | 3349718 | Equitable | N/A | 3349718 | 0 | 3349718 | 100 | 3349718 | 3349718 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
1304 | Infrastructure, Development and Maintenance | Grading And Murraming of Roads Through Imarisha Barabara Programme | To improve road infrastructure by grading and murraming Roads Through Imarisha Barabara Programme | Roads Through Imarisha Barabara Programme graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Olkaria | -0.748908 36.530458 2294.7000000000003 4.400000095367432 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Require regular maintenance.
1305 | Infrastructure, Development and Maintenance | Grading, gravelling and stone pitching of Rapland-Suswa road | To implement grading, gravelling and stone pitching of rapland-suswa road for road connectivity and accessibility | Grading, gravelling and stone pitching of Rapland-Suswa road completed | 3110499 | Construction of Roads - Other | Naivasha | Olkaria | -0.942669, 36.365197 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 4900000 | 4900000 | 4900000 | Equitable | N/A | 4900000 | 0 | 4757075 | 97.1 | 4757075 | 142925 | 142925 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Njebwe enterprises limited. Assessor remarks: Completed.
1306 | Infrastructure, Development and Maintenance | Grading, murraming and stone pitching of Kamere Beach Road | To implement grading, murraming and stone pitching of kamere beach road for road connectivity and accessibility | Grading, murraming and stone pitching of Kamere Beach Road completed | 3110499 | Construction of Roads - Other | Naivasha | Olkaria | -0.816383 36.324117 1932.699951171875 7.5 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 4500000 | 4500000 | 4500000 | Equitable | N/A | 4500000 | 0 | 4757075 | 105.7 | 4757075 | 142925 | -257075 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Has been damaged by rain so requires maintenance.
1307 | Infrastructure, Development & Maintenance | Grading, stone pitching and culverts at Kamere Beach | To implement grading, stone pitching and culverts at kamere beach for road connectivity and accessibility | Grading, stone pitching and culverts at Kamere Beach completed | 3110499 | Construction of Roads - Other | Naivasha | Olkaria | -0.816383 36.324117 1932.699951171875 7.5 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 1408393 | 1232200 | 1232200 | Equitable | N/A | 1232200 | 0 | 1172979 | 95.2 | 1172979 | 1232200 | 59221 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Has been damaged by rain so requires maintenance.
1308 | Infrastructure, Development and Maintenance | Road rehabilitation - hire of machineries and purchase of murram for road works in Olkaria ward | To implement road rehabilitation - hire of machineries and purchase of murram for road works in olkaria ward for road connectivity and accessibility | Road rehabilitation - hire of machineries and purchase of murram for road works in Olkaria ward completed | 3110499 | Construction of Roads - Other | Naivasha | Olkaria | -0.936488, 36.369755 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Road passable.
1309 | Infrastructure, Development and Maintenance | Routine Maintenance and Spot Improvement of Cultural Centre - Nkorionito access road in Olkaria Ward Naivasha Sub County | To maintain Spot Improvement of Cultural Centre - Nkorionito access road in Olkaria Ward Naivasha Sub County in serviceable condition | Spot Improvement of Cultural Centre - Nkorionito access road in Olkaria Ward Naivasha Sub County maintained | 3110499 | Construction of Roads - Other | Naivasha | Olkaria | -0.838224 36.362161 1883.0999755859375 11.142999649047852 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2994784 | 287990.25 | 287990.25 | Equitable | N/A | 287990.25 | 0 | 1034800 | 359.3 | 1034800 | 287990 | -746809.75 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Solar light operational.
1310 | Infrastructure, Development & Maintenance | Completion of storm water drainage along sewage, PCEA-Ndarugu | To complete storm water drainage along sewage, PCEA-Ndarugu | Storm water drainage along sewage, PCEA-Ndarugu completed | 3110499 | Construction of Roads - Other | Nakuru West | Rhonda | -0.316318, 36.062007 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 21/22 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1871917 | 93.6 | 1871917 | 5000000 | 128083 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Ms Aimers construction ltd. Assessor remarks: Needs rehabilitation.
1311 | Infrastructure, Development and Maintenance | Murraming At Nakuru West Health Center | To implement murraming at nakuru west health center for road connectivity and accessibility | Murraming At Nakuru West Health Center completed | 3110499 | Construction of Roads - Other | Nakuru West | Shabab | -0.530098, 36.383684 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 1395456 | 0 | 1395456 | Equitable | N/A | 1395456 | 0 | 0 | 0 | 0 | 1395456 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Imarisha barabara. Assessor remarks: Good.
1312 | Infrastructure, Development & Maintenance | Construction of Gacharage roads | To construct Gacharage roads | Gacharage roads constructed | 3110499 | Construction of Roads - Other | Kuresoi North | Sirikwa | -0.289234 35.63603 2712.264136918813 13 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2643077 | 2643077 | 2643077 | Equitable | N/A | 2643077 | 0 | 2618608 | 99.1 | 2618608 | 2643077 | 24469 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is in use though it has no water supply.
1313 | Infrastructure, Development and Maintenance | Grading and gravelling - Imarisha barabara programme | To improve road infrastructure by grading and murraming - Imarisha barabara programme | - Imarisha barabara programme graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi North | Sirikwa | -0.311827, 35.683133 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 3000000 | 1000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2994583 | 299.5 | 2994583 | 942625 | -1994583 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Bush clearing, grading and gravelling of the entire road, culvert installation in some sections and unblocking existing culverts.
1314 | Grading and murraming of ADC- Cheptagum road | Grading and murraming of ADC- Cheptagum road | To improve road infrastructure by grading and murraming ADC- Cheptagum road | ADC- Cheptagum road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi North | Sirikwa | -0.27362, 35.661595 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 1881885 | 1881885 | Equitable | N/A | 1881885 | 0 | 1881885 | 100 | 1881885 | 1881885 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is still in use, however the road needs reshaping, and murraming afresh, bush clearing and culverting in some sections.
1315 | Infrastructure, Development and Maintenance | Grading And Murraming of Gacharage-Bonde Access roads | To improve road infrastructure by grading and murraming Gacharage-Bonde Access roads | Gacharage-Bonde Access roads graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi North | Sirikwa | -0.22384 35.688552 2591.8 15.699999809265137 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 2000000 | 0 | 942625 | Equitable | N/A | 942625 | 0 | 1057375 | 100 | 1057375 | 942625 | -1057375 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: At the moment project is in bad condition,. Viable: Yes. Assessor remarks: An old project that needs all road works afresh.
1316 | Infrastructure, Development & Maintenance | Grading and murraming of Kangawa-Upendo roads | To improve road infrastructure by grading and murraming Kangawa-Upendo roads | Kangawa-Upendo roads graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi North | Sirikwa | -0.209732, 35.702143 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 1810570 | 1810570 | Equitable | N/A | 1810570 | 0 | 1810570 | 100 | 1810570 | 1810570 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project has recently been repaired by county government.
1317 | Infrastructure, Development and Maintenance | Grading And Murraming of Nyakinyua-Kiletien Access Roads | To improve road infrastructure by grading and murraming Nyakinyua-Kiletien Access Roads | Nyakinyua-Kiletien Access Roads graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi North | Sirikwa | -0.238579, 35.66559 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1897640 | 94.9 | 1897640 | 102360 | 102360 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project needs rehabilitation to drain water and spot patching to improve some sections.
1318 | Infrastructure, Development & Maintenance | Grading and murraming of Sirikwa Secondary-Taachasis road | To improve road infrastructure by grading and murraming Sirikwa Secondary-Taachasis road | Sirikwa Secondary-Taachasis road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi North | Sirikwa | -0.256867, 35.66989 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 189430 | 189430 | Equitable | N/A | 189430 | 0 | 1617590 | 853.9 | 1617590 | 189430 | -1428160 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes, but at the moment it is challenging especially during raining days. Viable: Yes. Assessor remarks: The project is in poor state, needs to be worked on afresh.
1319 | Infrastructure, Development and Maintenance | Grading, murraming and culverting of Kangawa- Upendo- Highlands Road | To implement grading, murraming and culverting of kangawa- upendo- highlands road for road connectivity and accessibility | Grading, murraming and culverting of Kangawa- Upendo- Highlands Road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Sirikwa | -0.209773, 35.702068 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1810570 | 90.5 | 1810570 | 1810570 | 189430 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project has recently been repaired by the county government.
1320 | Infrastructure, Development and Maintenance | Grading, Murraming and culverting of Nyakinywa-Kagondo Road | To implement grading, murraming and culverting of nyakinywa-kagondo road for road connectivity and accessibility | Grading, Murraming and culverting of Nyakinywa-Kagondo Road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Sirikwa | -0.239888, 35.670125 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2237235 | 111.9 | 2237235 | 693970 | -237235 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is still under implementation.
1321 | Infrastructure, Development and Maintenance | Grading, murraming and culverting (spot improvement) of Gacharage-Kiptenden road | To implement grading, murraming and culverting (spot improvement) of gacharage-kiptenden road for road connectivity and accessibility | Grading, murraming and culverting (spot improvement) of Gacharage-Kiptenden road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Sirikwa | -0.288338, 35.633252 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1602345 | 80.1 | 1602345 | 3000000 | 397655 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is currently under implementation.
1322 | Infrastructure, Development and Maintenance | Grading, murraming and culverts installation in Kaptembwa access road | To implement grading, murraming and culverts installation in kaptembwa access road for road connectivity and accessibility | Grading, murraming and culverts installation in Kaptembwa access road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Sirikwa | -0.252485 35.680303 2662.7 14.300000190734863 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 1602345 | 53.4 | 1602345 | 3000000 | 1397655 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs reshaping, culvert unblocking and installation of new, bush clearing.
1323 | Infrastructure, Development and Maintenance | Grading, murraming and culverts installation in Sirikwa road networks | To implement grading, murraming and culverts installation in sirikwa road networks for road connectivity and accessibility | Grading, murraming and culverts installation in Sirikwa road networks completed | 3110499 | Construction of Roads - Other | Kuresoi North | Sirikwa | -0.252485 35.680303 2662.7 14.300000190734863 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 2237235 | 100 | 2237235 | 2000000 | -2237235 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs reshaping, culvert unblocking and installation of new, bush clearing.
1324 | Infrastructure, Development & Maintenance | Grading, murraming and drainage works of Motto access road | To implement grading, murraming and drainage works of motto access road for road connectivity and accessibility | Grading, murraming and drainage works of Motto access road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Sirikwa | -0.26333, 35.665958 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 1602345 | 1602345 | Equitable | N/A | 1602345 | 0 | 1602345 | 100 | 1602345 | 1602345 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Reshaping, drainage, culverting, and culvert unblocking and murraming works needed.
1325 | Infrastructure, Development & Maintenance | Grading, murraming and drainage works of Sirikwa roads | To implement grading, murraming and drainage works of sirikwa roads for road connectivity and accessibility | Grading, murraming and drainage works of Sirikwa roads completed | 3110499 | Construction of Roads - Other | Kuresoi North | Sirikwa | -0.26333, 35.665958 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 3190625 | 693970 | 693970 | Equitable | N/A | 693970 | 0 | 2237235 | 322.4 | 2237235 | 693970 | -1543265 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Reshaping, drainage, culverting, and culvert unblocking and murraming works needed.
1326 | Infrastructure, Development and Maintenance | Hiring of machineries for roads rehabilitation | To implement hiring of machineries for roads rehabilitation for road connectivity and accessibility | Hiring of machineries for roads rehabilitation completed | 3110499 | Construction of Roads - Other | Kuresoi North | Sirikwa | -0.292393, 35.64323 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2024/25 | 6000000 | 0 | 6000000 | Equitable | N/A | 6000000 | 0 | 4432000 | 100 | 4432000 | 68000 | -4432000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is currently under implementation, the project will rehabilitate 6kms of road network.
1327 | Infrastructure, Development and Maintenance | Installation of highmast lights in Sirikwa | To improve security lighting through high mast floodlight installation at lights in Sirikwa | High mast floodlight installed at lights in Sirikwa | 3110499 | Construction of Roads - Other | Kuresoi North | Sirikwa | -0.288318, 35.642182 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2100000 | 2975797 | 2975797 | Equitable | N/A | 2975797 | 0 | 2840000 | 95.4 | 2840000 | 2975797 | 135797 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: Yes, however the faulty ones need repairs while Kenya power needs to reconnect the rest. Assessor remarks: The mast at Baringo is faulty while the rest were disconnected by Kenya power.
1328 | Infrastructure, Development and Maintenance | Murraming & culverting of Bygum-Ngenia-Nyaruai Road | To implement murraming & culverting of bygum-ngenia-nyaruai road for road connectivity and accessibility | Murraming & culverting of Bygum-Ngenia-Nyaruai Road completed | 3110499 | Construction of Roads - Other | Kuresoi North | Sirikwa | -0.284393, 35.696747 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2500000 | 100 | 2500000 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yed. Viable: Yes. Assessor remarks: Bush clearing, drainage, culvert unblocking and installation of new ones in some sections.
1329 | Infrastructure, Development and Maintenance | Murraming & Culverting of Moto Estate | To implement murraming & culverting of moto estate for road connectivity and accessibility | Murraming & Culverting of Moto Estate completed | 3110499 | Construction of Roads - Other | Kuresoi North | Sirikwa | -0.257053, 35.71925 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 1600000 | 1600000 | 1600000 | Equitable | N/A | 1600000 | 0 | 1441100 | 90.1 | 1441100 | 1602345 | 158900 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: O. B. T. Assessor remarks: Drainage works, Culverting unblocking, bush clearing and road reshaping.
1330 | Infrastructure, Development and Maintenance | Murraming of Sirikwa Ward Roads - Hiring of Equipment at wet rates, purchasing of murram and installation of culverts | To implement murraming of sirikwa ward roads - hiring of equipment at wet rates, purchasing of murram and installation of culverts for road connectivity and accessibility | Murraming of Sirikwa Ward Roads - Hiring of Equipment at wet rates, purchasing of murram and installation of culverts completed | 3110499 | Construction of Roads - Other | Kuresoi North | Sirikwa | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3976297 | 99.4 | 3976297 | 4000000 | 23703 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1331 | Infrastructure, Development and Maintenance | Rehabilitation of Murgiyeny road networks | To rehabilitate Murgiyeny road networks to restore functionality | Murgiyeny road networks rehabilitated | 3110499 | Construction of Roads - Other | Kuresoi North | Sirikwa | -0.285022 35.665988 2776.2999999999997 20.600000381469727 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Biroks Company ltd. Assessor remarks: The project needs bush clearing, reshaping, culvert unblocking and installation of new box culvert in at least two sections of the road.
1332 | Infrastructure, Development & Maintenance | Sirikwa Ward Road Works | To implement sirikwa ward road works for road connectivity and accessibility | Sirikwa Ward Road Works completed | 3110499 | Construction of Roads - Other | Kuresoi North | Sirikwa | -0.266925, 35.663488 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 2013103 | 2013103 | 2013103 | Equitable | N/A | 2013103 | 0 | 2013103 | 100 | 2013103 | 2013103 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Reshaping, culverting, murraming, bush clearing works are needed.
1333 | Infrastructure, Development and Maintenance | Constructio of a boda boda sheds | To implement constructio of a boda boda sheds for road connectivity and accessibility | Constructio of a boda boda sheds completed | 3110499 | Construction of Roads - Other | Rongai | Soin | -0.086134 35.954893 1642 10 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 500000 | 0 | 500000 | Equitable | N/A | 500000 | 0 | 1398960 | 0 | 1398960 | 600000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Gabion construction.
1334 | Infrastructure, Development and Maintenance | Construction of drainage in soin ward | To construct drainage in soin ward | Drainage in soin ward constructed | 3110499 | Construction of Roads - Other | Rongai | Soin | -0.054612 35.86942 1837.6 11 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 1398960 | 100 | 1398960 | 1040 | -1398960 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The roads need regular maintenance and drainage.
1335 | Infrastructure, Development and Maintenance | Construction Of Sarambei - Mosonik Bridge road | To construct Sarambei - Mosonik Bridge road | Sarambei - Mosonik Bridge road constructed | 3110499 | Construction of Roads - Other | Rongai | Soin | -0.073306, 35.962459 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1348953 | 89.9 | 1348953 | 151047 | 151047 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Gabion construction urgently needed.
1336 | Infrastructure, Development and Maintenance | Grading And Gravelling of Access Roads in Sawaiti Road | To improve road infrastructure by grading and murraming Access Roads in Sawaiti Road | Access Roads in Sawaiti Road graded and murramed | 3110499 | Construction of Roads - Other | Rongai | Soin | -0.06147, 36.043575 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 1033152 | 1033152 | 1033152 | Equitable | N/A | 1033152 | 0 | 948478 | 91.8 | 948478 | 84675 | 84674 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The roads needs repair and drainage system.
1337 | Infrastructure, Development and Maintenance | Grading, fueling & murraming -Imarisha barabara programme | To implement grading, fueling & murraming -imarisha barabara programme for road connectivity and accessibility | Grading, fueling & murraming -Imarisha barabara programme completed | 3110499 | Construction of Roads - Other | Rongai | Soin | -0.054688 36.056855 1618.2 4.400000095367432 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 1000000 | 1000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: The roads needs repair.
1338 | Infrastructure, Development & Maintenance | Hire Of Machines To Repair Kapsetek Roads | To implement hire of machines to repair kapsetek roads for road connectivity and accessibility | Hire Of Machines To Repair Kapsetek Roads completed | 3110499 | Construction of Roads - Other | Rongai | Soin | -0.054612 35.86942 1837.6 11 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1600000 | 1600000 | 1600000 | Equitable | N/A | 1600000 | 0 | 1600000 | 100 | 1600000 | 1600000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The roads need regular maintenance and drainage.
1339 | Infrastructure, Development & Maintenance | Kamonde-Sawati Road Construction | To implement kamonde-sawati road construction for road connectivity and accessibility | Kamonde-Sawati Road Construction completed | 3110499 | Construction of Roads - Other | Rongai | Soin | -0.07098, 36.048205 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1199200 | 1199200 | Equitable | N/A | 1199200 | 0 | 1199200 | 100 | 1199200 | 1199200 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road needs repair.
1340 | Infrastructure, Development & Maintenance | Rafiki roadworks | To implement rafiki roadworks for road connectivity and accessibility | Rafiki roadworks completed | 3110499 | Construction of Roads - Other | Rongai | Soin | -0.100878, 35.935519 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | FY 2024 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1947505 | 97.4 | 1947505 | 0 | 52495 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: No. Assessor remarks: The shade needs repair the floor was not made in good condition,The roofing not done well the users are rained on.
1341 | Infrastructure, Development and Maintenance | Road rehabilitation - supply of murram in Mulwang | To implement road rehabilitation - supply of murram in mulwang for road connectivity and accessibility | Road rehabilitation - supply of murram in Mulwang completed | 3110499 | Construction of Roads - Other | Rongai | Soin | -0.027537 35.965817 1560.199951171875 6 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 600000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 6000000 | 100 | 6000000 | 6000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Traders are safe with their goods.
1342 | Soin Road Rehabilitation (Hire Of Machines / Fuels For Road Maintenance And Rehabilitation) | Soin Road Rehabilitation (Hire Of Machines / Fuels For Road Maintenance And Rehabilitation) | To implement soin road rehabilitation (hire of machines / fuels for road maintenance and rehabilitation) for road connectivity and accessibility | Soin Road Rehabilitation (Hire Of Machines / Fuels For Road Maintenance And Rehabilitation) completed | 3110499 | Construction of Roads - Other | Rongai | Soin | -0.080693, 35.871902 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2990500 | 99.7 | 2990500 | 3000000 | 9500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: RAHASA VENTURES LTD. Assessor remarks: Require repair.
1343 | Infrastructure, Development & Maintenance | Soin road works (hire of machineries) | To implement soin road works (hire of machineries) for road connectivity and accessibility | Soin road works (hire of machineries) completed | 3110499 | Construction of Roads - Other | Rongai | Soin | -0.075263, 36.076688 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 3602540 | 3602540 | 4602540 | Equitable | N/A | 4602540 | 0 | 0 | 0 | 0 | 4602540 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Tes. Assessor remarks: The roads in good condition but needs regular maintenance.
1344 | Infrastructure, Development and Maintenance | Grading and murraming of Stimaline road in Sawaiti | To improve road infrastructure by grading and murraming Stimaline road in Sawaiti | Stimaline road in Sawaiti graded and murramed | 3110499 | Construction of Roads - Other | Rongai | Soin | -0.058704, 36.021129 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 1300000 | 1140466 | 1140466 | Equitable | N/A | 1140466 | 0 | 1140347 | 100 | 1140347 | 119 | 119 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Routine maintenance to be considered.
1345 | Infrastructure, Development & Maintenance | Grading Of Peter Chotara-Sawaiti-Benita-Border Road | To improve road accessibility by grading Peter Chotara-Sawaiti-Benita-Border Road | Peter Chotara-Sawaiti-Benita-Border Road graded | 3110499 | Construction of Roads - Other | Rongai | Soin | -0.118689 35.950928 1739 7.5 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 759300 | 759300 | Equitable | N/A | 759300 | 0 | 759300 | 100 | 759300 | 759300 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require maintenance.
1346 | Infrastructure, Development and Maintenance | Road Rehabilitation -Hire of Equipment for Levelling of Mulwang Road | To implement road rehabilitation -hire of equipment for levelling of mulwang road for road connectivity and accessibility | Road Rehabilitation -Hire of Equipment for Levelling of Mulwang Road completed | 3110499 | Construction of Roads - Other | Rongai | Soin | -0.065388 36.063068 1640.9 6.099999904632568 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 1000000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 863300 | 66.4 | 863300 | 136700 | 436700 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Project in good condition.
1347 | Infrastructure, Development & Maintenance | Grading And Murraming Kiboronjo-Kithire-Mutitaithia Road | To improve road infrastructure by grading and murraming Kiboronjo-Kithire-Mutitaithia Road | Kiboronjo-Kithire-Mutitaithia Road graded and murramed | 3110499 | Construction of Roads - Other | Rongai | Solai | 0.015959 36.1597 1585.875 5.960999965667725 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 1999330 | 1999330 | Equitable | N/A | 1999330 | 0 | 1894512 | 94.8 | 1894512 | 1999330 | 104818 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
1348 | Infrastructure, Development and Maintenance | Grading And Murraming of Access Roads- Imarisha Barabara in Solai Ward | To improve road infrastructure by grading and murraming Access Roads- Imarisha Barabara in Solai Ward | Access Roads- Imarisha Barabara in Solai Ward graded and murramed | 3110499 | Construction of Roads - Other | Rongai | Solai | 0.00289, 36.127668 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2024 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1809600 | 90.5 | 1809600 | 190400 | 190400 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
1349 | Infrastructure, Development & Maintenance | Grading And Murraming/Culverts Kapkoros-Mahinga-Ngendaptich Road | To improve road accessibility by grading And Murraming/Culverts Kapkoros-Mahinga-Ngendaptich Road | And Murraming/Culverts Kapkoros-Mahinga-Ngendaptich Road graded | 3110499 | Construction of Roads - Other | Rongai | Solai | 0.015959 36.1597 1585.875 5.960999965667725 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 1999080 | 1999080 | Equitable | N/A | 1999080 | 0 | 1997920 | 99.9 | 1997920 | 1999080 | 1160 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
1350 | Infrastructure, Development & Maintenance | Grading And Murraming/Culverts Lower Solai-Machine-Koimogul Road | To improve road accessibility by grading And Murraming/Culverts Lower Solai-Machine-Koimogul Road | And Murraming/Culverts Lower Solai-Machine-Koimogul Road graded | 3110499 | Construction of Roads - Other | Rongai | Solai | 0.015959 36.1597 1585.875 5.960999965667725 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2650000 | 2650000 | 2650000 | Equitable | N/A | 2650000 | 0 | 2540215 | 95.9 | 2540215 | 2650000 | 109785 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
1351 | Infrastructure, Development & Maintenance | Grading And Murraming/Culverts Tegunot-Rocks Road | To improve road accessibility by grading And Murraming/Culverts Tegunot-Rocks Road | And Murraming/Culverts Tegunot-Rocks Road graded | 3110499 | Construction of Roads - Other | Rongai | Solai | 0.015959 36.1597 1585.875 5.960999965667725 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1300000 | 1299432 | 1299432 | Equitable | N/A | 1299432 | 0 | 1296254 | 99.8 | 1296254 | 1299432 | 3178 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
1352 | Infrastructure, Development and Maintenance | Grading, murraming and rehabilitation of roads through Imarisha barabara programme in Solai Ward | To implement grading, murraming and rehabilitation of roads through imarisha barabara programme in solai ward for road connectivity and accessibility | Grading, murraming and rehabilitation of roads through Imarisha barabara programme in Solai Ward completed | 3110499 | Construction of Roads - Other | Rongai | Solai | -0.001224, 36.152165 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | July 2025 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1809600 | 90.5 | 1809600 | 190400 | 190400 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Chekibor investment limited. Assessor remarks: Road done well.
1353 | Infrastructure, Development & Maintenance | Hire of equipments and machineries for rehabilitation of roads in Solai ward | To implement hire of equipments and machineries for rehabilitation of roads in solai ward for road connectivity and accessibility | Hire of equipments and machineries for rehabilitation of roads in Solai ward completed | 3110499 | Construction of Roads - Other | Rongai | Solai | 0.16787 36.159957 1580.02001953125 18.270000457763672 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 3800000 | 3800000 | 3800000 | Equitable | N/A | 3800000 | 0 | 3799880 | 100 | 3799880 | 0 | 120 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is complete.
1354 | Infrastructure, Development and Maintenance | Hiring of machinery for grading and murraming of roads | To implement hiring of machinery for grading and murraming of roads for road connectivity and accessibility | Hiring of machinery for grading and murraming of roads completed | 3110499 | Construction of Roads - Other | Rongai | Solai | 0.015959 36.1597 1585.875 5.960999965667725 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 7000000 | 0 | 7000000 | Equitable | N/A | 7000000 | 0 | 1000610 | 0 | 1000610 | 1000616 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
1355 | Infrastructure, Development & Maintenance | Grading And Murraming Of Tuiyomoi Road | To improve road infrastructure by grading and murraming Tuiyomoi Road | Tuiyomoi Road graded and murramed | 3110499 | Construction of Roads - Other | Rongai | Solai | 0.015959 36.1597 1585.875 5.960999965667725 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 1000616 | 1000616 | Equitable | N/A | 1000616 | 0 | 1000610 | 100 | 1000610 | 1000616 | 6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
1356 | Infrastructure, Development and Maintenance | Grading, Murraming And Construction Of Gabion At White Rock-Dip Road | To implement grading, murraming and construction of gabion at white rock-dip road for road connectivity and accessibility | Grading, Murraming And Construction Of Gabion At White Rock-Dip Road completed | 3110499 | Construction of Roads - Other | Rongai | Solai | 0.159874 36.164702 1611.9619140625 8.440999984741211 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 252511 | 252511 | Equitable | N/A | 252511 | 0 | 252511 | 100 | 252511 | 252511 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is well maintained.
1357 | Infrastructure, Development and Maintenance | Bush Clearing and Road Rehabilitation - Labour Based | To improve the condition of and Road Rehabilitation - Labour Based | And Road Rehabilitation - Labour Based improved | 3110499 | Construction of Roads - Other | Subukia | Subukia | -0.031723, 36.171952 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2023 | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Need to be done again.
1358 | Infrastructure, Development and Maintenance | Grading And Gravelling Of Kimoni Taribo Road | To improve road infrastructure by grading and murraming Kimoni Taribo Road | Kimoni Taribo Road graded and murramed | 3110499 | Construction of Roads - Other | Subukia | Subukia | -0.029452, 36.236129 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2023 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1482400 | 98.8 | 1482400 | 1500000 | 17600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes.. Viable: The road serves the community. Contractor: Information not available. Assessor remarks: Good work.
1359 | Infrastructure, Development & Maintenance | Grading And Murraming And Construction Of Bridge Of Grogon Kwa Maina Tetu Road | To improve road infrastructure by grading and murraming And Construction Of Bridge Of Grogon Kwa Maina Tetu Road | And Construction Of Bridge Of Grogon Kwa Maina Tetu Road graded and murramed | 3110499 | Construction of Roads - Other | Subukia | Subukia | -0.031797 36.1717 2081.5 2 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2500000 | 0 | 591245.65 | Equitable | N/A | 591245.65 | 0 | 1894176 | 100 | 1894176 | 591246 | -1894176 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need to be redo.
1360 | Infrastructure, Development & Maintenance | Grading And Murraming Of Arash Mande Road | To improve road infrastructure by grading and murraming Arash Mande Road | Arash Mande Road graded and murramed | 3110499 | Construction of Roads - Other | Subukia | Subukia | -0.020588, 36.22147 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 01/12/2021 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 1500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes.. Viable: Sure. Contractor: Information not available. Assessor remarks: Good work.
1361 | Grading And Murraming Of Kibe-Hyrax-Magomano Secondary Road At Gatongu | Grading And Murraming Of Kibe-Hyrax-Magomano Secondary Road At Gatongu | To improve road infrastructure by grading and murraming Kibe-Hyrax-Magomano Secondary Road At Gatongu | Kibe-Hyrax-Magomano Secondary Road At Gatongu graded and murramed | 3110499 | Construction of Roads - Other | Subukia | Subukia | -0.031748, 36.171823 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2021 | 2000000 | 1927800 | 1927800 | Equitable | N/A | 1927800 | 0 | 1927800 | 100 | 1927800 | 1927800 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Need to be redone.
1362 | Grading And Murraming Of Subukia Day-Soko Mjinga,Wainaina Muchori,-Paul Gakuha Road | Grading And Murraming Of Subukia Day-Soko Mjinga,Wainaina Muchori,-Paul Gakuha Road | To improve road infrastructure by grading and murraming Subukia Day-Soko Mjinga,Wainaina Muchori,-Paul Gakuha Road | Subukia Day-Soko Mjinga,Wainaina Muchori,-Paul Gakuha Road graded and murramed | 3110499 | Construction of Roads - Other | Subukia | Subukia | -0.019127, 36.215098 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/2021 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes road opened up and upgraded. Viable: Yes. Contractor: Details not ot available. Assessor remarks: Requires more murraming.
1363 | Infrastructure, Development and Maintenance | Grading And Murraming Of Thungura-Wakamau-Chiefs Office Road In Kijabe | To improve road infrastructure by grading and murraming Thungura-Wakamau-Chiefs Office Road In Kijabe | Thungura-Wakamau-Chiefs Office Road In Kijabe graded and murramed | 3110499 | Construction of Roads - Other | Subukia | Subukia | -0.0247, 36.239128 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/2021 | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 700000 | 100 | 700000 | 700000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes, access road opened up. Viable: Yes. Contractor: Details not availed. Assessor remarks: Requires more murraming and continuous grading.
1364 | Infrastructure, Development and Maintenance | Grading, Culverts and Murraming of Mugumoini-Gichu Road in Muthaiga Kianoe | To implement grading, culverts and murraming of mugumoini-gichu road in muthaiga kianoe for road connectivity and accessibility | Grading, Culverts and Murraming of Mugumoini-Gichu Road in Muthaiga Kianoe completed | 3110499 | Construction of Roads - Other | Subukia | Subukia | -0.980495, 36.581642 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1069856 | 692351 | 692351 | Equitable | N/A | 692351 | 0 | 377505 | 54.5 | 377505 | 692351 | 314846 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
1365 | Infrastructure, Development and Maintenance | Grading, murraming and fueling - Imarisha barabara programme | To implement grading, murraming and fueling - imarisha barabara programme for road connectivity and accessibility | Grading, murraming and fueling - Imarisha barabara programme completed | 3110499 | Construction of Roads - Other | Subukia | Subukia | -0.006035, 36.228805 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2024/2025 | 4500000 | 1000000 | 4500000 | Equitable | N/A | 4500000 | 0 | 2000000 | 200 | 2000000 | 2500000 | -1000000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Details unavailable. Assessor remarks: The road is serving the public linking estates to the town.
1366 | Infrastructure, Development & Maintenance | Grading ,Murraming And Installation Of Culverts At Rukuini-Grave Yard-Mosque-Jec Church And Kwa Michael Road In Subukia Center | To improve road accessibility by grading ,Murraming And Installation Of Culverts At Rukuini-Grave Yard-Mosque-Jec Church And Kwa Michael Road In Subukia Center | ,Murraming And Installation Of Culverts At Rukuini-Grave Yard-Mosque-Jec Church And Kwa Michael Road In Subukia Center graded | 3110499 | Construction of Roads - Other | Subukia | Subukia | 0.003171, 36.233178 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/2021 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Access to trading centre, homes and work places enhanced. Contractor: Details not availed. Assessor remarks: Road is in good state.
1367 | Infrastructure, Development and Maintenance | Grading,Culverts And Murraming Of Mugumoini-Gichu Road In Muthaiga Kianoe | To implement grading,culverts and murraming of mugumoini-gichu road in muthaiga kianoe for road connectivity and accessibility | Grading,Culverts And Murraming Of Mugumoini-Gichu Road In Muthaiga Kianoe completed | 3110499 | Construction of Roads - Other | Subukia | Subukia | -0.980495, 36.581642 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1069856 | 692351 | 692351 | Equitable | N/A | 692351 | 0 | 377505 | 54.5 | 377505 | 692351 | 314846 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
1368 | Infrastructure, Development and Maintenance | Grading,Murraming And Culverts Installation At Ngomongo Road In Tetu | To implement grading,murraming and culverts installation at ngomongo road in tetu for road connectivity and accessibility | Grading,Murraming And Culverts Installation At Ngomongo Road In Tetu completed | 3110499 | Construction of Roads - Other | Subukia | Subukia | -0.052713, 36.22759 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 10/04/2023 | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 700000 | 100 | 700000 | 700000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes.. Viable: Sure.. Contractor: Information not available. Assessor remarks: Good work.
1369 | Infrastructure, Development & Maintenance | Hire of equipments for improvement of Subukia Ward roads | To implement hire of equipments for improvement of subukia ward roads for road connectivity and accessibility | Hire of equipments for improvement of Subukia Ward roads completed | 3110499 | Construction of Roads - Other | Subukia | Subukia | -0.000397, 36.233982 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2022 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 5000000 | 100 | 5000000 | 3100000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Need to redone.
1370 | Infrastructure, Development & Maintenance | Hire Of Equipments For Road Maintenance,Grading And Gravelling At Arash Location And Subukia East Location In Subukia Ward | To implement hire of equipments for road maintenance,grading and gravelling at arash location and subukia east location in subukia ward for road connectivity and accessibility | Hire Of Equipments For Road Maintenance,Grading And Gravelling At Arash Location And Subukia East Location In Subukia Ward completed | 3110499 | Construction of Roads - Other | Subukia | Subukia | -0.018708, 36.195552 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/2021 | 3900000 | 3900000 | 3900000 | Equitable | N/A | 3900000 | 0 | 3900000 | 100 | 3900000 | 3900000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Access road to the village and farms opened up. Contractor: Details not availed. Assessor remarks: The road is well maintained.
1371 | Infrastructure, Development & Maintenance | Hire Of Equipments For Road Maintenance,Grading And Gravelling At Munanda Location In Subukia Ward | To implement hire of equipments for road maintenance,grading and gravelling at munanda location in subukia ward for road connectivity and accessibility | Hire Of Equipments For Road Maintenance,Grading And Gravelling At Munanda Location In Subukia Ward completed | 3110499 | Construction of Roads - Other | Subukia | Subukia | -0.018708, 36.195552 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/2021 | 3100000 | 3100000 | 3100000 | Equitable | N/A | 3100000 | 0 | 3100000 | 100 | 3100000 | 3100000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Access road to the village and farms opened up. Contractor: Details not availed. Assessor remarks: The road is well maintained.
1372 | Infrastructure, Development and Maintenance | Hire of Machineries for rehabilitation of roads | To implement hire of machineries for rehabilitation of roads for road connectivity and accessibility | Hire of Machineries for rehabilitation of roads completed | 3110499 | Construction of Roads - Other | Subukia | Subukia | -0.00961, 36.225472 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/2023 | 4000000 | 0 | 919185 | Equitable | N/A | 919185 | 0 | 3080815 | 100 | 3080815 | 919185 | -3080815 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Not availed. Assessor remarks: Machinery hired, roads upgraded.
1373 | Infrastructure, Development and Maintenance | Hire of machinery for road maintenance and repair | To implement hire of machinery for road maintenance and repair for road connectivity and accessibility | Hire of machinery for road maintenance and repair completed | 3110499 | Construction of Roads - Other | Subukia | Subukia | -0.009938, 36.225358 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2025 | 7000000 | 7000000 | 7000000 | Equitable | N/A | 7000000 | 0 | 3100000 | 44.3 | 3100000 | 3100000 | 3900000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good work.
1374 | Infrastructure, Development and Maintenance | Murraming of 1.25km Kahero Road in Subukia Ward | To implement murraming of 1.25km kahero road in subukia ward for road connectivity and accessibility | Murraming of 1.25km Kahero Road in Subukia Ward completed | 3110499 | Construction of Roads - Other | Subukia | Subukia | -0.00072 36.233087 1996.0999755859375 28.263999938964844 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 2000000 | 100 | 2000000 | 1000000 | -2000000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: Road improvement works completed.
1375 | Infrastructure, Development and Maintenance | Murraming Of Roads in Subukia Ward Under Imarisha Barabara | To implement murraming of roads in subukia ward under imarisha barabara for road connectivity and accessibility | Murraming Of Roads in Subukia Ward Under Imarisha Barabara completed | 3110499 | Construction of Roads - Other | Subukia | Subukia | -0.022867, 36.212809 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 12/03/2024 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes.. Viable: Yes, the local people use the road.. Contractor: Information not available. Assessor remarks: Ths road is in good condition.
1376 | Infrastructure, Development and Maintenance | Construction of Kipsirat Bridge | To construct Kipsirat Bridge | Kipsirat Bridge constructed | 3110499 | Construction of Roads - Other | Kuresoi South | Tinet | -0.547201, 35.674632 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999113 | 100 | 1999113 | 887 | 887 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational and in good.
1377 | Infrastructure, Development and Maintenance | Grading and murraming of aon-kimoron road | To improve road infrastructure by grading and murraming aon-kimoron road | Aon-kimoron road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Tinet | -0.522393, 35.610737 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 1668000 | 0 | 1668000 | Equitable | N/A | 1668000 | 0 | 2000000 | 100 | 2000000 | 2000000 | -2000000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Handed over.
1378 | Infrastructure, Development and Maintenance | Grading and murraming of Boron pri-Kipsilwet road | To improve road infrastructure by grading and murraming Boron pri-Kipsilwet road | Boron pri-Kipsilwet road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Tinet | -0.547201, 35.674632 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | N/A | 2000000 | 1969580 | 1969580 | Equitable | N/A | 1969580 | 0 | 1969580 | 100 | 1969580 | 1969580 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition few potholes.
1379 | Infrastructure, Development and Maintenance | Grading and murraming of Chepkosigen-kaber road | To improve road infrastructure by grading and murraming Chepkosigen-kaber road | Chepkosigen-kaber road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Tinet | -0.440734, 35.577584 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 2168000 | 0 | 2168000 | Equitable | N/A | 2168000 | 0 | 2000000 | 100 | 2000000 | 2000000 | -2000000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes viable but not meet the need. Assessor remarks: Bad state.
1380 | Infrastructure, Development and Maintenance | Grading and murraming of Chepkosigen-kiptendon road | To improve road infrastructure by grading and murraming Chepkosigen-kiptendon road | Chepkosigen-kiptendon road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Tinet | -0.522393, 35.610737 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 1584000 | 0 | 1584000 | Equitable | N/A | 1584000 | 0 | 2000000 | 100 | 2000000 | 2000000 | -2000000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Handed over.
1381 | Infrastructure, Development and Maintenance | Grading and murraming of Kabongoi-Busienkiruk road | To improve road infrastructure by grading and murraming Kabongoi-Busienkiruk road | Kabongoi-Busienkiruk road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Tinet | -0.522393, 35.610737 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 2000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Handed over.
1382 | Infrastructure, Development and Maintenance | Grading and murraming of kapcheserem-chepkosigen road | To improve road infrastructure by grading and murraming kapcheserem-chepkosigen road | Kapcheserem-chepkosigen road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Tinet | -0.440734, 35.577584 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 1500000 | 0 | 1500000 | Equitable | N/A | 1500000 | 0 | 2000000 | 100 | 2000000 | 2000000 | -2000000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes viable but not meet the need. Assessor remarks: Bad state.
1383 | Infrastructure, Development and Maintenance | Grading and murraming of kapsirat road | To improve road infrastructure by grading and murraming kapsirat road | Kapsirat road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Tinet | -0.522393, 35.610737 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 1584000 | 0 | 1584000 | Equitable | N/A | 1584000 | 0 | 2000000 | 100 | 2000000 | 2000000 | -2000000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Handed over.
1384 | Infrastructure, Development and Maintenance | Grading and murraming of Kapteleit road | To improve road infrastructure by grading and murraming Kapteleit road | Kapteleit road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Tinet | -0.522393, 35.610737 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 1584000 | 0 | 1584000 | Equitable | N/A | 1584000 | 0 | 2000000 | 100 | 2000000 | 2000000 | -2000000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Handed over.
1385 | Infrastructure, Development and Maintenance | Grading and murraming of Kaptembwa arap too road | To improve road infrastructure by grading and murraming Kaptembwa arap too road | Kaptembwa arap too road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Tinet | -0.547201, 35.674632 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 3168000 | 0 | 3168000 | Equitable | N/A | 3168000 | 0 | 2000000 | 100 | 2000000 | 2000000 | -2000000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition few potholes.
1386 | Infrastructure, Development and Maintenance | Grading and murraming of Kibugeto road | To improve road infrastructure by grading and murraming Kibugeto road | Kibugeto road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Tinet | -0.522393, 35.610737 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 2168000 | 0 | 2168000 | Equitable | N/A | 2168000 | 0 | 2000000 | 100 | 2000000 | 2000000 | -2000000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Handed over.
1387 | Infrastructure, Development and Maintenance | Grading and murraming of Kimugul argunet road | To improve road infrastructure by grading and murraming Kimugul argunet road | Kimugul argunet road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Tinet | -0.522393, 35.610737 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 1584000 | 0 | 1584000 | Equitable | N/A | 1584000 | 0 | 2000000 | 100 | 2000000 | 2000000 | -2000000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Handed over.
1388 | Infrastructure, Development and Maintenance | Grading and murraming of korao-kapnanda road | To improve road infrastructure by grading and murraming korao-kapnanda road | Korao-kapnanda road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Tinet | -0.522393, 35.610737 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 2168000 | 0 | 2168000 | Equitable | N/A | 2168000 | 0 | 1969580 | 100 | 1969580 | 1969580 | -1969580 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Handed over.
1389 | Infrastructure, Development and Maintenance | Grading and murraming of Sibor road | To improve road infrastructure by grading and murraming Sibor road | Sibor road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Tinet | -0.522393, 35.610737 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 1584000 | 0 | 1584000 | Equitable | N/A | 1584000 | 0 | 2000000 | 100 | 2000000 | 2000000 | -2000000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Handed over.
1390 | Infrastructure, Development and Maintenance | Grading and murraming of Timbwalo road | To improve road infrastructure by grading and murraming Timbwalo road | Timbwalo road graded and murramed | 3110499 | Construction of Roads - Other | Kuresoi South | Tinet | -0.522393, 35.610737 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 2000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Handed over.
1391 | Infrastructure, Development and Maintenance | Grading, Gravelling and Murraming of Chemaner-Mia Tatu Road | To implement grading, gravelling and murraming of chemaner-mia tatu road for road connectivity and accessibility | Grading, Gravelling and Murraming of Chemaner-Mia Tatu Road completed | 3110499 | Construction of Roads - Other | Kuresoi South | Tinet | -0.512645 35.645253 2492.6 7.300000190734863 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2500000 | 100 | 2500000 | 247800 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: Yes. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: Handed over.
1392 | Infrastructure, Development and Maintenance | Grading, Gravelling and Murraming of Chenugu Primary Road | To implement grading, gravelling and murraming of chenugu primary road for road connectivity and accessibility | Grading, Gravelling and Murraming of Chenugu Primary Road completed | 3110499 | Construction of Roads - Other | Kuresoi South | Tinet | -0.530856 35.597755 0 3599.9990234375 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2252200 | 90.1 | 2252200 | 247800 | 247800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: Handed over.
1393 | Infrastructure, Development and Maintenance | Grading, Gravelling and Murraming of Kabaon-Tilindi Road | To implement grading, gravelling and murraming of kabaon-tilindi road for road connectivity and accessibility | Grading, Gravelling and Murraming of Kabaon-Tilindi Road completed | 3110499 | Construction of Roads - Other | Kuresoi South | Tinet | -0.512645 35.645253 2492.6 7.300000190734863 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 974430 | 97.4 | 974430 | 25570 | 25570 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: Yes. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: Handed over.
1394 | Infrastructure, Development and Maintenance | Grading, Gravelling and Murraming of Kapket-Botkikor Road | To implement grading, gravelling and murraming of kapket-botkikor road for road connectivity and accessibility | Grading, Gravelling and Murraming of Kapket-Botkikor Road completed | 3110499 | Construction of Roads - Other | Kuresoi South | Tinet | -0.512645 35.645253 2492.6 7.300000190734863 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 132000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: Yes. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: Handed over.
1395 | Infrastructure, Development and Maintenance | Grading, Gravelling and Murraming of Kaprusei-Busienguru Road | To implement grading, gravelling and murraming of kaprusei-busienguru road for road connectivity and accessibility | Grading, Gravelling and Murraming of Kaprusei-Busienguru Road completed | 3110499 | Construction of Roads - Other | Kuresoi South | Tinet | -0.512645 35.645253 2492.6 7.300000190734863 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2868000 | 95.6 | 2868000 | 132000 | 132000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: Yes. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: Handed over.
1396 | Infrastructure, Development and Maintenance | Grading, Gravelling and Murraming of Lumumba Road | To implement grading, gravelling and murraming of lumumba road for road connectivity and accessibility | Grading, Gravelling and Murraming of Lumumba Road completed | 3110499 | Construction of Roads - Other | Kuresoi South | Tinet | -0.530856 35.597755 0 3599.9990234375 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 842598 | 70.2 | 842598 | 357402 | 357402 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: Handed over.
1397 | Infrastructure, Development and Maintenance | Grading, Gravelling and Murraming of Tirigoi-Wejeko Road | To implement grading, gravelling and murraming of tirigoi-wejeko road for road connectivity and accessibility | Grading, Gravelling and Murraming of Tirigoi-Wejeko Road completed | 3110499 | Construction of Roads - Other | Kuresoi South | Tinet | -0.530856 35.597755 0 3599.9990234375 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2429030 | 97.2 | 2429030 | 70970 | 70970 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: Handed over.
1398 | Infrastructure, Development and Maintenance | Grading, murraming and installation of culverts of kapongoil-bushienguruk road | To implement grading, murraming and installation of culverts of kapongoil-bushienguruk road for road connectivity and accessibility | Grading, murraming and installation of culverts of kapongoil-bushienguruk road completed | 3110499 | Construction of Roads - Other | Kuresoi South | Tinet | -0.512645 35.645253 2492.6 7.300000190734863 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 2000000 | -2000000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: Yes. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: Handed over.
1399 | Infrastructure, Development & Maintenance | Hiring of machines and Fueling for Tinet road networks and culverts installation | To implement hiring of machines and fueling for tinet road networks and culverts installation for road connectivity and accessibility | Hiring of machines and Fueling for Tinet road networks and culverts installation completed | 3110499 | Construction of Roads - Other | Kuresoi South | Tinet | -0.436869 35.625097 0 5199.9990234375 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 10019025 | 4816200 | 4816200 | Equitable | N/A | 4816200 | 0 | 4784648 | 99.3 | 4784648 | 4816200 | 31552 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Bad state.
1400 | Infrastructure, Development & Maintenance | Tinet Road Works -Rehabilitation/Maintainance of roads | To implement tinet road works -rehabilitation/maintainance of roads for road connectivity and accessibility | Tinet Road Works -Rehabilitation/Maintainance of roads completed | 3110499 | Construction of Roads - Other | Kuresoi South | Tinet | -0.52457 35.648055 2559.6 5.900000095367432 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 10000000 | 10000000 | 10000000 | Equitable | N/A | 10000000 | 0 | 9699305 | 97 | 9699305 | 0 | 300695 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: Yes. Condition: Bad. Objective met: Met. Viable: Yes. Assessor remarks: Graded but not murramed.
1401 | Infrastructure, Development and Maintenance | Completion Of Rafiki Kwa Muliro Hill To Mona Road | To complete Rafiki Kwa Muliro Hill To Mona Road | Rafiki Kwa Muliro Hill To Mona Road completed | 3110499 | Construction of Roads - Other | Molo | Turi | -0.300087, 35.723901 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 1875367 | 4573088 | 6370809 | Equitable | N/A | 6370809 | 0 | 0 | 0 | 0 | 1797721 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: A road does not have ownership documents.
1402 | Infrastructure, Development & Maintenance | Grading and gravelling of Inooro -Managu road | To improve road infrastructure by grading and murraming Inooro -Managu road | Inooro -Managu road graded and murramed | 3110499 | Construction of Roads - Other | Molo | Turi | -0.330458, 35.729053 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: A road does not have ownership documents.
1403 | Infrastructure, Development & Maintenance | Grading and Gravelling of Kayole- Milimani Road | To improve road infrastructure by grading and murraming Kayole- Milimani Road | Kayole- Milimani Road graded and murramed | 3110499 | Construction of Roads - Other | Molo | Turi | -0.330458, 35.729053 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 1500000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1200000 | 100 | 1200000 | 1200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: A road does not have ownership documents.
1404 | Grading and gravelling of Kiambiriria primary to Tarmac road | Grading and gravelling of Kiambiriria primary to Tarmac road | To improve road infrastructure by grading and murraming Kiambiriria primary to Tarmac road | Kiambiriria primary to Tarmac road graded and murramed | 3110499 | Construction of Roads - Other | Molo | Turi | -0.299992, 35.695237 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 1500000 | 0 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Rehabilitation has been done recently.
1405 | Grading and gravelling of Michatha eastleigh roads | Grading and gravelling of Michatha eastleigh roads | To improve road infrastructure by grading and murraming Michatha eastleigh roads | Michatha eastleigh roads graded and murramed | 3110499 | Construction of Roads - Other | Molo | Turi | -0.28505, 35.739501 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 1000000 | 225310 | 225310 | Equitable | N/A | 225310 | 0 | 225310 | 100 | 225310 | 225310 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
1406 | Infrastructure, Development & Maintenance | Grading and gravelling of Ngwataniro road (kirangi) | To improve road infrastructure by grading and murraming Ngwataniro road (kirangi) | Ngwataniro road (kirangi) graded and murramed | 3110499 | Construction of Roads - Other | Molo | Turi | -0.322798 35.738772 2674.6 8.199999809265137 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 701405 | 701405 | 701405 | Equitable | N/A | 701405 | 0 | 701405 | 100 | 701405 | 701405 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road has been redone last financial year.
1407 | Infrastructure, Development & Maintenance | Grading and gravelling of Turi center road | To improve road infrastructure by grading and murraming Turi center road | Turi center road graded and murramed | 3110499 | Construction of Roads - Other | Molo | Turi | -0.282736, 35.75818 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: It has been graded gravelled recently.
1408 | Infrastructure, Development and Maintenance | Grading And Murraming of Access Roads- Imarisha Barabara in Turi Ward | To improve road infrastructure by grading and murraming Access Roads- Imarisha Barabara in Turi Ward | Access Roads- Imarisha Barabara in Turi Ward graded and murramed | 3110499 | Construction of Roads - Other | Molo | Turi | -0.303507, 35.731743 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 1200000 | 0 | 1200000 | 800000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: It needs to be rehabilitated again.
1409 | Infrastructure, Development & Maintenance | Grading and murraming of Kapsita road | To improve road infrastructure by grading and murraming Kapsita road | Kapsita road graded and murramed | 3110499 | Construction of Roads - Other | Molo | Turi | -0.266688 35.739926 2554.4 13.600000381469727 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2890 | 2890 | Equitable | N/A | 2890 | 0 | 1996950 | 69098.6 | 1996950 | 2890 | -1994060 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Newly graded again but not good during rainy season.
1410 | Infrastructure, Development & Maintenance | Grading and murraming of Kiambu road | To improve road infrastructure by grading and murraming Kiambu road | Kiambu road graded and murramed | 3110499 | Construction of Roads - Other | Molo | Turi | -0.266688 35.739926 2554.4 13.600000381469727 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 979110 | 979110 | Equitable | N/A | 979110 | 0 | 979110 | 100 | 979110 | 979110 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Newly graded again but not good during rainy season.
1411 | Infrastructure, Development & Maintenance | Grading and Murraming of Milima Mitatu roads | To improve road infrastructure by grading and murraming Milima Mitatu roads | Milima Mitatu roads graded and murramed | 3110499 | Construction of Roads - Other | Molo | Turi | -0.266712 35.73983 2554.4 11.199999809265137 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1200000 | 208990 | 208990 | Equitable | N/A | 208990 | 0 | 208990 | 100 | 208990 | 208990 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: The road was graded but was not gravelled. It needs gravelling as it impassable during rainy season.
1412 | Grading and murraming of Muchorwe dispensary - Kayole road | Grading and murraming of Muchorwe dispensary - Kayole road | To improve road infrastructure by grading and murraming Muchorwe dispensary - Kayole road | Muchorwe dispensary - Kayole road graded and murramed | 3110499 | Construction of Roads - Other | Molo | Turi | -0.316518, 35.710677 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 2400000 | 1080503 | 1080503 | Equitable | N/A | 1080503 | 0 | 1155527 | 106.9 | 1155527 | 1080503 | -75024 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In need of rehabilitation.
1413 | Grading and murraming of St. Brenden Managu road | Grading and murraming of St. Brenden Managu road | To improve road infrastructure by grading and murraming St. Brenden Managu road | St. Brenden Managu road graded and murramed | 3110499 | Construction of Roads - Other | Molo | Turi | -0.32778, 35.741407 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 1500000 | 1448990 | 1448990 | Equitable | N/A | 1448990 | 0 | 1448990 | 100 | 1448990 | 1448990 | 0 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
1414 | Infrastructure, Development & Maintenance | Grading and Murraming Yatta Road | To improve road infrastructure by grading and murraming Yatta Road | Yatta Road graded and murramed | 3110499 | Construction of Roads - Other | Molo | Turi | -0.310717, 35.700182 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 1067329 | 1067329 | 1067329 | Equitable | N/A | 1067329 | 0 | 1067329 | 100 | 1067329 | 1067329 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: In bad state, in need of rehabilitation.
1415 | Infrastructure, Development & Maintenance | Grading, dozing and gravelling of roads Mona Center to Tarmac road | To implement grading, dozing and gravelling of roads mona center to tarmac road for road connectivity and accessibility | Grading, dozing and gravelling of roads Mona Center to Tarmac road completed | 3110499 | Construction of Roads - Other | Molo | Turi | -0.282278 35.758575 2480.10009765625 39.599998474121094 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1300000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 1300000 | 100 | 1300000 | 1300000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Road network has been adversely affected by the ongoing heavy rains.
1416 | Infrastructure, Development and Maintenance | Grading,murraming,installation of Culverts and gabions in turi ward | To implement grading,murraming,installation of culverts and gabions in turi ward for road connectivity and accessibility | Grading,murraming,installation of Culverts and gabions in turi ward completed | 3110499 | Construction of Roads - Other | Molo | Turi | -0.309382 35.7569 2571.8 10.300000190734863 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 8000000 | 0 | 8000000 | Equitable | N/A | 8000000 | 0 | 800000 | 0 | 800000 | 800000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good.
1417 | Infrastructure, Development & Maintenance | Hiring of equipments at wet rate and supply of murram for Turi Ward roads | To implement hiring of equipments at wet rate and supply of murram for turi ward roads for road connectivity and accessibility | Hiring of equipments at wet rate and supply of murram for Turi Ward roads completed | 3110499 | Construction of Roads - Other | Molo | Turi | -0.29544, 35.705655 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 5500000 | 5500000 | 5500000 | Equitable | N/A | 5500000 | 0 | 5489650 | 99.8 | 5489650 | 1000000 | 10350 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
1418 | Infrastructure, Development and Maintenance | Hiring of Machineries at wet rate for road rehabilitation | To implement hiring of machineries at wet rate for road rehabilitation for road connectivity and accessibility | Hiring of Machineries at wet rate for road rehabilitation completed | 3110499 | Construction of Roads - Other | Molo | Turi | -0.30742, 35.70122 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2024/25 | 9500000 | 6000000 | 5500000 | Equitable | N/A | 5500000 | 0 | 5699745 | 95 | 5699745 | 300255 | 300255 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: The road needs rehabilitation.
1419 | Infrastructure, Development and Maintenance | Hiring of machineries at wet rate for roads rehabilitation in Turi Ward | To implement hiring of machineries at wet rate for roads rehabilitation in turi ward for road connectivity and accessibility | Hiring of machineries at wet rate for roads rehabilitation in Turi Ward completed | 3110499 | Construction of Roads - Other | Molo | Turi | -0.30742, 35.70122 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 5699745 | 95 | 5699745 | 300255 | 300255 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: The road needs rehabilitation.
1420 | Infrastructure, Development & Maintenance | Hiring of machinery and supply of murrum for Ndenderu A and Turi farmers roads | To implement hiring of machinery and supply of murrum for ndenderu a and turi farmers roads for road connectivity and accessibility | Hiring of machinery and supply of murrum for Ndenderu A and Turi farmers roads completed | 3110499 | Construction of Roads - Other | Molo | Turi | -0.305733, 35.749693 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 798613 | 99.8 | 798613 | 800000 | 1387 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is in good condition.
1421 | Hiring of machinery at net rate and supply of murrum for Mkorombosi Kavido road | Hiring of machinery at net rate and supply of murrum for Mkorombosi Kavido road | To implement hiring of machinery at net rate and supply of murrum for mkorombosi kavido road for road connectivity and accessibility | Hiring of machinery at net rate and supply of murrum for Mkorombosi Kavido road completed | 3110499 | Construction of Roads - Other | Molo | Turi | -1.28019, 36.818118 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: YES. Viable: YES. Assessor remarks: COMPLETED AND OPERATIONAL.
1422 | Hiring of machinery at net rate and supply of murrum for Ndenderu B roads | Hiring of machinery at net rate and supply of murrum for Ndenderu B roads | To implement hiring of machinery at net rate and supply of murrum for ndenderu b roads for road connectivity and accessibility | Hiring of machinery at net rate and supply of murrum for Ndenderu B roads completed | 3110499 | Construction of Roads - Other | Molo | Turi | -1.28019, 36.818118 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: YES. Viable: YES. Assessor remarks: COMPLETED AND OPERATIONAL.
1423 | Infrastructure, Development & Maintenance | Hiring of machinery at wet rate and supply of murram for Mona, Ngerefu Kiambiriria and Kapsita road | To implement hiring of machinery at wet rate and supply of murram for mona, ngerefu kiambiriria and kapsita road for road connectivity and accessibility | Hiring of machinery at wet rate and supply of murram for Mona, Ngerefu Kiambiriria and Kapsita road completed | 3110499 | Construction of Roads - Other | Molo | Turi | -0.330763 35.72908 2767.2000000000003 12.300000190734863 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 800000 | 100 | 800000 | 800000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: A road does not have ownership documents.
1424 | Infrastructure, Development and Maintenance | Hiring of Machinery at Wet Rate for Turi Roads | To implement hiring of machinery at wet rate for turi roads for road connectivity and accessibility | Hiring of Machinery at Wet Rate for Turi Roads completed | 3110499 | Construction of Roads - Other | Molo | Turi | -0.291467, 35.722087 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1899457 | 95 | 1899457 | 100543 | 100543 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
1425 | Infrastructure, Development and Maintenance | Hiring of Machinery for roads rehabilitation in Turi Ward | To implement hiring of machinery for roads rehabilitation in turi ward for road connectivity and accessibility | Hiring of Machinery for roads rehabilitation in Turi Ward completed | 3110499 | Construction of Roads - Other | Molo | Turi | -0.30742, 35.70122 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 2000000 | 1680503 | 1680503 | Equitable | N/A | 1680503 | 0 | 1594545 | 94.9 | 1594545 | 85958 | 85958 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: The road needs rehabilitation.
1426 | Infrastructure, Development and Maintenance | Milima Mitatu road Works | To implement milima mitatu road works for road connectivity and accessibility | Milima Mitatu road Works completed | 3110499 | Construction of Roads - Other | Molo | Turi | -1.281229 36.821402 0 291468.7964650597 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 2199053 | 2099053 | 2099053 | Equitable | N/A | 2099053 | 0 | 1181783 | 56.3 | 1181783 | 208990 | 917270 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: YES. Viable: YES. Assessor remarks: the project is in use.
1427 | Infrastructure, Development & Maintenance | Routine Maintenance of Rafiki B Roads Turi Ward | To maintain Rafiki B Roads Turi Ward in serviceable condition | Rafiki B Roads Turi Ward maintained | 3110499 | Construction of Roads - Other | Molo | Turi | -0.300535 35.723508 2573.9 73.80000305175781 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 1500000 | 1450960 | 1450960 | Equitable | N/A | 1450960 | 0 | 1450960 | 100 | 1450960 | 1450960 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: A road does not have ownership documents.
1428 | Infrastructure, Development & Maintenance | Grading and gravelling of Mwangaza kwa Ndungu-Mona, Kiambu-Kiranga-Kapsita, Muchorwe, Sagaitim-Kapsita, Milima mitatu-Nderitu, Ngwataniro -ADC, Turi Centre, Turi farmers, and Kiangwaci roads | To improve road infrastructure by grading and murraming Mwangaza kwa Ndungu-Mona, Kiambu-Kiranga-Kapsita, Muchorwe, Sagaitim-Kapsita, Milima mitatu-Nderitu, Ngwataniro -ADC, Turi Centre, Turi farmers, and Kiangwaci roads | Mwangaza kwa Ndungu-Mona, Kiambu-Kiranga-Kapsita, Muchorwe, Sagaitim-Kapsita, Milima mitatu-Nderitu, Ngwataniro -ADC, Turi Centre, Turi farmers, and Kiangwaci roads graded and murramed | 3110499 | Construction of Roads - Other | Molo | Turi | -0.32764, 35.739845 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 5200000 | 975367 | 975367 | Equitable | N/A | 975367 | 0 | 2524633 | 258.8 | 2524633 | 975367 | -1549266 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Is good use.
1429 | Infrastructure, Development and Maintenance | Grading And Murraming of Ethirando Road, Kapklach-Kwale Road, Kandutura Oasis Road, St. Mary- Kasaon Road, Visoi Road and Burgei Road | To improve road infrastructure by grading and murraming Ethirando Road, Kapklach-Kwale Road, Kandutura Oasis Road, St. Mary- Kasaon Road, Visoi Road and Burgei Road | Ethirando Road, Kapklach-Kwale Road, Kandutura Oasis Road, St. Mary- Kasaon Road, Visoi Road and Burgei Road graded and murramed | 3110499 | Construction of Roads - Other | Rongai | Visoi | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 7000000 | 0 | 1458166 | Equitable | N/A | 1458166 | 0 | 5541834 | 100 | 5541834 | 1458166 | -5541834 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1430 | Infrastructure, Development and Maintenance | Grading and Murraming of Kimangu East Road, Moricho-Milimani road, Toyoitich-Polytechnic Road, Bongo Loiya Road, Chebii Thirandu primary road and Kilombe-Kagwa Road | To improve road infrastructure by grading and murraming Kimangu East Road, Moricho-Milimani road, Toyoitich-Polytechnic Road, Bongo Loiya Road, Chebii Thirandu primary road and Kilombe-Kagwa Road | Kimangu East Road, Moricho-Milimani road, Toyoitich-Polytechnic Road, Bongo Loiya Road, Chebii Thirandu primary road and Kilombe-Kagwa Road graded and murramed | 3110499 | Construction of Roads - Other | Rongai | Visoi | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 6000000 | 0 | 818163.75 | Equitable | N/A | 818163.75 | 0 | 4680536 | 100 | 4680536 | 818164 | -4680536 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1431 | Infrastructure, Development and Maintenance | Grading and murraming of legetio-mabatini,boito kayole,kimangu-arasa and chepseon-salgaa roads | To improve road infrastructure by grading and murraming legetio-mabatini,boito kayole,kimangu-arasa and chepseon-salgaa roads | Legetio-mabatini,boito kayole,kimangu-arasa and chepseon-salgaa roads graded and murramed | 3110499 | Construction of Roads - Other | Rongai | Visoi | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 5058905 | 0 | 5058905 | Equitable | N/A | 5058905 | 0 | 1054503 | 100 | 1054503 | 1500000 | -1054503 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
1432 | Infrastructure, Development and Maintenance | Grading And Murraming of Roads Through Imarisha Barabara Programme | To improve road infrastructure by grading and murraming Roads Through Imarisha Barabara Programme | Roads Through Imarisha Barabara Programme graded and murramed | 3110499 | Construction of Roads - Other | Rongai | Visoi | -0.205011 35.84867 1901.199951171875 29.555999755859375 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 2576410 | 100 | 2576410 | 2598960 | -2576410 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
1433 | Infrastructure, Development & Maintenance | Grading And Spot Murraming Of Bongoloia-Muricho Road | To improve road accessibility by grading And Spot Murraming Of Bongoloia-Muricho Road | And Spot Murraming Of Bongoloia-Muricho Road graded | 3110499 | Construction of Roads - Other | Rongai | Visoi | -0.205011 35.84867 1901.199951171875 29.555999755859375 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 2576410 | 171.8 | 2576410 | 1500000 | -1076410 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
1434 | Infrastructure, Development & Maintenance | Grading, spot murraming, dozing and culverts installation of Jamaica-Ex Batler road | To implement grading, spot murraming, dozing and culverts installation of jamaica-ex batler road for road connectivity and accessibility | Grading, spot murraming, dozing and culverts installation of Jamaica-Ex Batler road completed | 3110499 | Construction of Roads - Other | Rongai | Visoi | -0.137292 35.824637 1889.3 9.199999809265137 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Rynix investment. Assessor remarks: Good.
1435 | Infrastructure, Development & Maintenance | Hiring of equipments for road work rehabilitation in Nafaka-Arasha road, Mara Nne road, Burgei-Chesarina Mololine road, Salgaa-Chepseon road, Delorain road and Jirani Mwema | To implement hiring of equipments for road work rehabilitation in nafaka-arasha road, mara nne road, burgei-chesarina mololine road, salgaa-chepseon road, delorain road and jirani mwema for road connectivity and accessibility | Hiring of equipments for road work rehabilitation in Nafaka-Arasha road, Mara Nne road, Burgei-Chesarina Mololine road, Salgaa-Chepseon road, Delorain road and Jirani Mwema completed | 3110499 | Construction of Roads - Other | Rongai | Visoi | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 5969652 | 99.5 | 5969652 | 0 | 30348 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1436 | Infrastructure, Development and Maintenance | Construction of Viwandani access roads | To construct Viwandani access roads | Viwandani access roads constructed | 3110499 | Construction of Roads - Other | Naivasha | Viwandani | -0.701188, 36.426037 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 7000000 | 1561242.8 | 1561242.8 | Equitable | N/A | 1561242.8 | 0 | 1561259 | 100 | 1561259 | 1561243 | -16.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Assessor remarks: Operational.
1437 | Infrastructure, Development and Maintenance | Grading And Murraming of Access Roads Across the Ward | To improve road infrastructure by grading and murraming Access Roads Across the Ward | Access Roads Across the Ward graded and murramed | 3110499 | Construction of Roads - Other | Naivasha | Viwandani | -0.716704 36.443369 0 400 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 8721741 | 8721741 | 8721741 | Equitable | N/A | 8721741 | 0 | 8323995 | 95.4 | 8323995 | 397746 | 397746 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Assessor remarks: Complete.
1438 | Infrastructure, Development and Maintenance | Grading, Murraming, Compacting and installation of culverts in Viwandani Access roads | To implement grading, murraming, compacting and installation of culverts in viwandani access roads for road connectivity and accessibility | Grading, Murraming, Compacting and installation of culverts in Viwandani Access roads completed | 3110499 | Construction of Roads - Other | Naivasha | Viwandani | -0.701035, 36.426361 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 10000000 | 10000000 | 10000000 | Equitable | N/A | 10000000 | 0 | 9695183 | 97 | 9695183 | 304817 | 304817 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Assessor remarks: Operational.
1439 | Infrastructure, Development and Maintenance | Hire of machinery and equipment of Viwandani access roads | To implement hire of machinery and equipment of viwandani access roads for road connectivity and accessibility | Hire of machinery and equipment of Viwandani access roads completed | 3110499 | Construction of Roads - Other | Naivasha | Viwandani | -0.714893 36.434213 1900.199951171875 19.398000717163086 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 1561259 | 26 | 1561259 | 1561243 | 4438741 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Very viable. Assessor remarks: Operational.
1440 | Infrastructure, Development & Maintenance | Upgrade of roads to Bitumen Standard at Boma, Kabati | To implement upgrade of roads to bitumen standard at boma, kabati for road connectivity and accessibility | Upgrade of roads to Bitumen Standard at Boma, Kabati completed | 3110499 | Construction of Roads - Other | Naivasha | Viwandani | -0.715753, 36.439069 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 13305241 | 0 | 13305241 | Equitable | N/A | 13305241 | 0 | 0 | 0 | 0 | 13305241 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Assessor remarks: Complete.
1441 | Infrastructure, Development and Maintenance | Grading And Gravelling of Access Roads in Waseges (Imarisha Barabara) | To improve road infrastructure by grading and murraming Access Roads in Waseges (Imarisha Barabara) | Access Roads in Waseges (Imarisha Barabara) graded and murramed | 3110499 | Construction of Roads - Other | Subukia | Waseges | 0.19759, 36.22461 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 3000000 | 3000000 | 3275000 | Equitable | N/A | 3275000 | 0 | 525000 | 17.5 | 525000 | 375000 | 2475000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs Maintenance.
1442 | Infrastructure, Development & Maintenance | Grading And Gravelling Of Baharini-Kericho Road | To improve road infrastructure by grading and murraming Baharini-Kericho Road | Baharini-Kericho Road graded and murramed | 3110499 | Construction of Roads - Other | Subukia | Waseges | 0.14589 36.242263 1696.7 9.300000190734863 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 901112 | 901112 | Equitable | N/A | 901112 | 0 | 857463 | 95.2 | 857463 | 901112 | 43649 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs Maintenance.
1443 | Infrastructure, Development & Maintenance | Grading And Levelling Komu-Kaharagwe Road | To improve road accessibility by grading And Levelling Komu-Kaharagwe Road | And Levelling Komu-Kaharagwe Road graded | 3110499 | Construction of Roads - Other | Subukia | Waseges | 0.14589 36.242263 1696.7 9.300000190734863 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2160655 | 2160655 | Equitable | N/A | 2160655 | 0 | 2160655 | 100 | 2160655 | 2160655 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs Maintenance.
1444 | Infrastructure, Development & Maintenance | Grading And Murraming Kanyotu Baraka Road | To improve road infrastructure by grading and murraming Kanyotu Baraka Road | Kanyotu Baraka Road graded and murramed | 3110499 | Construction of Roads - Other | Subukia | Waseges | 0.145993, 36.251227 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 1998000 | 1998000 | Equitable | N/A | 1998000 | 0 | 1857447 | 93 | 1857447 | 1998000 | 140553 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
1445 | Infrastructure, Development & Maintenance | Grading Of Mwiteithia-Suswa Road (Kahuruko) | To improve road accessibility by grading Mwiteithia-Suswa Road (Kahuruko) | Mwiteithia-Suswa Road (Kahuruko) graded | 3110499 | Construction of Roads - Other | Subukia | Waseges | 0.16629, 36.249878 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1300000 | 193044 | 193044 | Equitable | N/A | 193044 | 0 | 193044 | 100 | 193044 | 193044 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs Maintenance.
1446 | Infrastructure, Development & Maintenance | Hire Of Machinery And Supply Of Murram | To implement hire of machinery and supply of murram for road connectivity and accessibility | Hire Of Machinery And Supply Of Murram completed | 3110499 | Construction of Roads - Other | Subukia | Waseges | 0.021193 36.258142 2118.1 8.399999618530273 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 4000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 5999700 | 100 | 5999700 | 6000000 | 300 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Passable road.
1447 | Infrastructure, Development and Maintenance | Road Rehabilitation of Waseges Ward through Imarisha Barabara | To implement road rehabilitation of waseges ward through imarisha barabara for road connectivity and accessibility | Road Rehabilitation of Waseges Ward through Imarisha Barabara completed | 3110499 | Construction of Roads - Other | Subukia | Waseges | 0.166398, 36.249798 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 1100000 | 0 | 203972.52 | Equitable | N/A | 203972.52 | 0 | 896027 | 100 | 896027 | 203973 | -896027 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs Maintenance.
1448 | Infrastructure, Development and Maintenance | Road Rehabiltation -Hire of Machinery and Purchase of fuel and murram for access roads across Waseges Ward | To implement road rehabiltation -hire of machinery and purchase of fuel and murram for access roads across waseges ward for road connectivity and accessibility | Road Rehabiltation -Hire of Machinery and Purchase of fuel and murram for access roads across Waseges Ward completed | 3110499 | Construction of Roads - Other | Subukia | Waseges | 0.099095, 36.237527 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | N/A | 5200000 | 222498.95 | 222498.95 | Equitable | N/A | 222498.95 | 0 | 4483231 | 2014.9 | 4483231 | 222499 | -4260732.05 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
1449 | Infrastructure, Development and Maintenance | Routine Maintenance and Spot Improvement of Waseges Solai Road (Mbogoini Kavilila Phase II) | To maintain Spot Improvement of Waseges Solai Road (Mbogoini Kavilila Phase II) in serviceable condition | Spot Improvement of Waseges Solai Road (Mbogoini Kavilila Phase II) maintained | 3110499 | Construction of Roads - Other | Subukia | Waseges | 0.19475, 36.213015 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 2198074 | 0 | 4396148 | Equitable | N/A | 4396148 | 0 | 1697776 | 100 | 1697776 | 2198074 | -1697776 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good state.
1450 | Infrastructure, Development & Maintenance | Waseges Road Works - Hire of Equipment and purchase of murram | To implement waseges road works - hire of equipment and purchase of murram for road connectivity and accessibility | Waseges Road Works - Hire of Equipment and purchase of murram completed | 3110499 | Construction of Roads - Other | Subukia | Waseges | 0.079875, 36.242145 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 9872876 | 9872876 | 9872876 | Equitable | N/A | 9872876 | 0 | 9872065 | 100 | 9872065 | 0 | 811 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
1451 | Infrastructure, Development and Maintenance | Construction of Kapwinner Bridge | To construct Kapwinner Bridge | Kapwinner Bridge constructed | 3110501 | Bridges | Kuresoi South | Amalo | -0.707425 35.640247 2268.5 7.800000190734863 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 2800000 | 2800000 | 2800000 | Equitable | N/A | 2800000 | 0 | 1997200 | 71.3 | 1997200 | 67380 | 802800 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: bridge operational.
1452 | Infrastructure, Development and Maintenance | Construction of Mzalendo - Kiptenden bridge in Amalo Ward | To construct Mzalendo - Kiptenden bridge in Amalo Ward | Mzalendo - Kiptenden bridge in Amalo Ward constructed | 3110501 | Bridges | Kuresoi South | Amalo | -0.574555, 35.69361 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2024 | 2100000 | 2064580 | 2064580 | Equitable | N/A | 2064580 | 0 | 1997200 | 96.7 | 1997200 | 67380 | 67380 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: project completed.
1453 | Infrastructure, Development & Maintenance | Construction of Sausa-Kaplamboi, Nukiat-Kimugul and Barargeiyet-Gorofa Foot Bridges | To construct Sausa-Kaplamboi, Nukiat-Kimugul and Barargeiyet-Gorofa Foot Bridges | Sausa-Kaplamboi, Nukiat-Kimugul and Barargeiyet-Gorofa Foot Bridges constructed | 3110501 | Bridges | Kuresoi South | Amalo | -0.570205 35.691767 2584.2 6.599999904632568 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 0 | 0 | 0 | 1200000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: no. Viable: not yet. Assessor remarks: footbridge not started.
1454 | Infrastructure, Development & Maintenance | Construction Of Sausa-Kaplamboi, Nukiat-Kimugul And Barargeiyet-Gorofa Footbridges | To construct Sausa-Kaplamboi, Nukiat-Kimugul And Barargeiyet-Gorofa Footbridges | Sausa-Kaplamboi, Nukiat-Kimugul And Barargeiyet-Gorofa Footbridges constructed | 3110501 | Bridges | Kuresoi South | Amalo | -0.570205 35.691767 2584.2 6.599999904632568 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 0 | 0 | 0 | 1200000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: no. Viable: not yet. Assessor remarks: footbridge not started.
1455 | Infrastructure, Development and Maintenance | Construction of Bridge at High-Kiambaria Road | To construct Bridge at High-Kiambaria Road | Bridge at High-Kiambaria Road constructed | 3110501 | Bridges | Naivasha | Biashara-Naivasha | -0.719067, 36.505095 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2023 | 4500000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3945642 | 98.6 | 3945642 | 54358 | 54358 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: DAKUKI. Assessor remarks: Well done.
1456 | Infrastructure, Development and Maintenance | Construction of Hotel Eel Kahuruko road Bridge (box Culvert) | To construct Hotel Eel Kahuruko road Bridge (box Culvert) | Hotel Eel Kahuruko road Bridge (box Culvert) constructed | 3110501 | Bridges | Molo | Elburgon | -0.303299, 35.813848 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | - | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1200000 | 100 | 1200000 | 700000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete and operational.
1457 | Infrastructure, Development and Maintenance | Construction of Mugumo road Bridge (Box Culvert) | To construct Mugumo road Bridge (Box Culvert) | Mugumo road Bridge (Box Culvert) constructed | 3110501 | Bridges | Molo | Elburgon | -0.303299, 35.813848 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | - | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 1200000 | 171.4 | 1200000 | 700000 | -500000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete and operational.
1458 | Infrastructure, Development and Maintenance | Construction of Njeru bridge | To construct Njeru bridge | Njeru bridge constructed | 3110501 | Bridges | Gilgil | Elementaita | -0.581721 36.082011 2049.59 0.9729999899864197 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 3400000 | 3394694 | 3394694 | Equitable | N/A | 3394694 | 0 | 3392375 | 99.9 | 3392375 | 3394694 | 2319 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
1459 | Infrastructure, Development and Maintenance | Completion of Murindat-Gilgil bridge | To complete Murindat-Gilgil bridge | Murindat-Gilgil bridge completed | 3110501 | Bridges | Gilgil | Gilgil | -0.536367, 36.344742 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 500000 | 0 | 500000 | Equitable | N/A | 500000 | 0 | 2495600 | 100 | 2495600 | 500000 | -2495600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Good. Objective met: No. Viable: No. Contractor: M/s Durhas construction. Assessor remarks: Project not started.
1460 | Construction of Gilgil Murindat Mbeggi Bridge | Construction of Gilgil Murindat Mbeggi Bridge | To construct Gilgil Murindat Mbeggi Bridge | Gilgil Murindat Mbeggi Bridge constructed | 3110501 | Bridges | Gilgil | Gilgil | -0.538348, 36.359 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2024/25 | 2023/2024 | 1000000 | 7000000 | 8000000 | Equitable | N/A | 8000000 | 0 | 828680 | 11.8 | 828680 | 1750000 | 6171320 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Cubango. Assessor remarks: Okay.
1461 | Infrastructure, Development and Maintenance | Construction Of Mbegi Bridge-Additional Funds | To construct Mbegi Bridge-Additional Funds | Mbegi Bridge-Additional Funds constructed | 3110501 | Bridges | Gilgil | Gilgil | -0.536367, 36.344742 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 600000 | 0 | 600000 | Equitable | N/A | 600000 | 0 | 0 | 0 | 0 | 600000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Good. Objective met: No. Viable: No. Contractor: M/s Durhas construction. Assessor remarks: Project not started.
1462 | Infrastructure, Development and Maintenance | Construction of Baraka Bridge | To construct Baraka Bridge | Baraka Bridge constructed | 3110501 | Bridges | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | N/A | 1000000 | 5944021.9 | 5944021.9 | Equitable | N/A | 5944021.9 | 0 | 30510811 | 513.3 | 30510811 | 4000000 | -24566789.1 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
1463 | Infrastructure, Development and Maintenance | Construction of Bridges | To construct Bridges | Bridges constructed | 3110501 | Bridges | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | N/A | 20000000 | 0 | 4000000 | Equitable | N/A | 4000000 | 0 | 6978545 | 100 | 6978545 | 4000000 | -6978545 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
1464 | Infrastructure, Development and Maintenance | Proposed Construction of Bridges at Rare Maai Mahiu Road Ereri Road Concreting of Kamore Longonot Road in Maai Mahiu Ward and Moi Ndabi Bridge in Maiella Ward Naivasha Sub-County | To undertake the proposed Construction of Bridges at Rare Maai Mahiu Road Ereri Road Concreting of Kamore Longonot Road in Maai Mahiu Ward and Moi Ndabi Bridge in Maiella Ward Naivasha Sub-County | Proposed Construction of Bridges at Rare Maai Mahiu Road Ereri Road Concreting of Kamore Longonot Road in Maai Mahiu Ward and Moi Ndabi Bridge in Maiella Ward Naivasha Sub-County implemented | 3110501 | Bridges | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | N/A | 16643870 | 16643870 | 16643870 | Equitable | N/A | 16643870 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
1465 | Infrastructure, Development and Maintenance | Construction of a footbridge at Mwiciringiri | To construct a footbridge at Mwiciringiri | A footbridge at Mwiciringiri constructed | 3110501 | Bridges | Naivasha | Hells Gate | -0.783694, 36.507606 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 983500 | 65.6 | 983500 | 983500 | 516500 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Not yet. Assessor remarks: The project has not started.
1466 | Infrastructure, Development and Maintenance | Construction of Keriopa bridge along Endao-Mitimingi Road | To construct Keriopa bridge along Endao-Mitimingi Road | Keriopa bridge along Endao-Mitimingi Road constructed | 3110501 | Bridges | Subukia | Kabazi | -0.12904 36.15429 0 220 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 3000000 | 3000000 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 2006603 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Requires renovations, additional classroom and furniture.
1467 | Infrastructure, Development and Maintenance | Construction Of Maombi and Maringu Bridges and Installation of Culverts at Kabazi Centre and Road Works Around Kabazi Ward | To construct Maombi and Maringu Bridges and Installation of Culverts at Kabazi Centre and Road Works Around Kabazi Ward | Maombi and Maringu Bridges and Installation of Culverts at Kabazi Centre and Road Works Around Kabazi Ward constructed | 3110501 | Bridges | Subukia | Kabazi | -0.23853 35.86724 2237 0 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 5000000 | 1244627.2 | 1209627.2 | Equitable | N/A | 1209627.2 | 0 | 1757447 | 141.2 | 1757447 | 1209627 | -512819.8 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: No details available. Assessor remarks: Requires additional ecd classroom, toilets and kitchen.
1468 | Infrastructure, Development & Maintenance | Construction bridges & drainages and installation of Culverts | To construct bridges & drainages and installation of Culverts | Bridges & drainages and installation of Culverts constructed | 3110501 | Bridges | Kuresoi North | Kamara | -0.172682 35.679654 2519.9 36.900001525878906 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2500000 | 499283.5 | 499283.5 | Equitable | N/A | 499283.5 | 0 | 499284 | 100 | 499284 | 499284 | -0.5 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Yes. Contractor: Not indicated. Assessor remarks: Needs renovation.
1469 | Infrastructure, Development & Maintenance | Construction of Kapkwen Mombasa foot bridge | To construct Kapkwen Mombasa foot bridge | Kapkwen Mombasa foot bridge constructed | 3110501 | Bridges | Kuresoi South | Keringet | -0.46613, 35.717493 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2022 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Roads passable.
1470 | Installation of a foot bridge and culvert along river Munyaka | Installation of a foot bridge and culvert along river Munyaka | To install a foot bridge and culvert along river Munyaka | A foot bridge and culvert along river Munyaka installed | 3110501 | Bridges | Bahati | Kiamaina | -0.240843, 36.133888 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1319488 | 1319488 | 1319488 | Equitable | N/A | 1319488 | 0 | 1299393 | 98.5 | 1299393 | 20095 | 20095 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Culverts are well maintained.
1471 | Infrastructure, Development & Maintenance | Construction Of Footbridge At Mutito B | To construct Footbridge At Mutito B | Footbridge At Mutito B constructed | 3110501 | Bridges | Njoro | Kihingo | -0.440014 35.974624 2303.300048828125 98.4000015258789 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 1500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires Renovation.
1472 | Infrastructure, Development & Maintenance | Construction Of Footbridge At Subuku-Munanda | To construct Footbridge At Subuku-Munanda | Footbridge At Subuku-Munanda constructed | 3110501 | Bridges | Njoro | Kihingo | -0.426452 35.9737 2257.5 14.600000381469727 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 1500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires Renovation.
1473 | Infrastructure, Development & Maintenance | Construction Of Kwa Ford Foot Bridge | To construct Kwa Ford Foot Bridge | Kwa Ford Foot Bridge constructed | 3110501 | Bridges | Njoro | Kihingo | -0.475127 35.988002 2285.2 4.199999809265137 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 922621 | 92.3 | 922621 | 1000000 | 77379 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Fencing and staff house construction.
1474 | Infrastructure, Development and Maintenance | Construction of Araret-Kiptororo Bridge | To construct Araret-Kiptororo Bridge | Araret-Kiptororo Bridge constructed | 3110501 | Bridges | Kuresoi North | Kiptororo | -0.377203 35.505747 0 800 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 1500000 | 1409000 | 1409000 | Equitable | N/A | 1409000 | 0 | 1272998 | 90.3 | 1272998 | 136002 | 136002 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The bridge was constructed but no gurd rails.
1475 | Infrastructure, Development and Maintenance | Construction of Chebonde bridge | To construct Chebonde bridge | Chebonde bridge constructed | 3110501 | Bridges | Kuresoi North | Kiptororo | -0.389489, 35.568792 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | N/A | 1500000 | 0 | 1500000 | Equitable | N/A | 1500000 | 0 | 1272998 | 100 | 1272998 | 1500000 | -1272998 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
1476 | Infrastructure, Development & Maintenance | Design and Construction of Bridge of Chepkosa bridge | To design and construct Bridge of Chepkosa bridge | Bridge of Chepkosa bridge designed and constructed | 3110501 | Bridges | Kuresoi North | Kiptororo | -0.339452 35.480974 2456.8 4.300000190734863 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | N/A | 2000000 | 1987830 | 1950830 | Equitable | N/A | 1950830 | 0 | 1272998 | 64 | 1272998 | 1950830 | 714832 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: They need additional classroom.the existing classroomm is partitioned,PP1 and pp2 share one classroom.
1477 | Infrastructure, Development & Maintenance | Design and Construction of Bridge of Kiplongony bridge | To design and construct Bridge of Kiplongony bridge | Bridge of Kiplongony bridge designed and constructed | 3110501 | Bridges | Kuresoi North | Kiptororo | -0.377203 35.505747 0 800 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | N/A | 2500000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 1272998 | 100 | 1272998 | 2000000 | -1272998 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The bridge was constructed but no gurd rails.
1478 | Infrastructure, Development & Maintenance | Construction of bridge at Ngaci-Mireroni | To construct bridge at Ngaci-Mireroni | Bridge at Ngaci-Mireroni constructed | 3110501 | Bridges | Bahati | Lanet/Umoja | -0.2962, 36.179403 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 999200 | 999200 | Equitable | N/A | 999200 | 0 | 995888 | 99.7 | 995888 | 999200 | 3312 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
1479 | Infrastructure, Development & Maintenance | Construction of bridge at Nyonjoro river | To construct bridge at Nyonjoro river | Bridge at Nyonjoro river constructed | 3110501 | Bridges | Bahati | Lanet/Umoja | -0.279715, 36.174596 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/2021 | 776672 | 738000 | 738000 | Equitable | N/A | 738000 | 0 | 737225 | 99.9 | 737225 | 775 | 775 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
1480 | Infrastructure, Development and Maintenance | Construction of Jerusalem Bridge-Mireroni | To construct Jerusalem Bridge-Mireroni | Jerusalem Bridge-Mireroni constructed | 3110501 | Bridges | Bahati | Lanet/Umoja | -0.303562, 36.179645 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 0 | 622450 | Equitable | N/A | 622450 | 0 | 339500 | 100 | 339500 | 622450 | -339500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional but needs upgrading.
1481 | Infrastructure, Development and Maintenance | Construction of a bridge in Lare Ward | To construct a bridge in Lare Ward | A bridge in Lare Ward constructed | 3110501 | Bridges | Njoro | Lare | -0.44825, 36.025733 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2025 | 3851752 | 3851752 | 3851752 | Equitable | N/A | 3851752 | 0 | 2741870 | 71.2 | 2741870 | 258000 | 1109882 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: Need to be undertaken.
1482 | Infrastructure, Development & Maintenance | Completion of Governor bridge | To complete Governor bridge | Governor bridge completed | 3110501 | Bridges | Naivasha | Maai Mahiu | -0.966875, 36.546208 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1498569 | 99.9 | 1498569 | 1500000 | 1431 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
1483 | Infrastructure, Development and Maintenance | Completion of Jikaze Muniu bridge and road works at Maai Mahiu and Longonot Roads | To complete Jikaze Muniu bridge and road works at Maai Mahiu and Longonot Roads | Jikaze Muniu bridge and road works at Maai Mahiu and Longonot Roads completed | 3110501 | Bridges | Naivasha | Maai Mahiu | -0.932119, 36.536306 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 5500000 | 1623890 | 1623890 | Equitable | N/A | 1623890 | 0 | 1306328 | 80.4 | 1306328 | 317562 | 317562 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. The bridge has ensure connectivity in an area that would have otherwise been cut off due to erosion.. Viable: Yes.. Assessor remarks: Bridge guard rails vandalised, needs repair..
1484 | Infrastructure, Development & Maintenance | Completion of Wagachunga bridge | To complete Wagachunga bridge | Wagachunga bridge completed | 3110501 | Bridges | Naivasha | Maai Mahiu | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 3665650 | 244.4 | 3665650 | 1500000 | -2165650 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1485 | Infrastructure, Development & Maintenance | Construction of Governor village footbridge | To construct Governor village footbridge | Governor village footbridge constructed | 3110501 | Bridges | Naivasha | Maai Mahiu | -0.966875, 36.546208 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999638 | 100 | 1999638 | 2000000 | 362 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
1486 | Infrastructure, Development and Maintenance | Construction of Kwa Gedion bridge | To construct Kwa Gedion bridge | Kwa Gedion bridge constructed | 3110501 | Bridges | Naivasha | Maai Mahiu | -0.946486, 36.541664 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 2450000 | 61.3 | 2450000 | 1500000 | 1550000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Project yet to start. There is a proposal for the bridge to be merged with construction of a bridge in Maai Mahiu in the FY2024/25.
1487 | Infrastructure, Development and Maintenance | Construction Of Kwanjuiri Bridge | To construct Kwanjuiri Bridge | Kwanjuiri Bridge constructed | 3110501 | Bridges | Naivasha | Maai Mahiu | -0.946486, 36.541664 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 1500000 | 0 | 1500000 | Equitable | N/A | 1500000 | 0 | 2450000 | 100 | 2450000 | 1500000 | -2450000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Project yet to start. There is a proposal for the bridge to be merged with construction of a bridge in Maai Mahiu in the FY2024/25.
1488 | Infrastructure, Development and Maintenance | Construction of Maai Mahiu bridge | To construct Maai Mahiu bridge | Maai Mahiu bridge constructed | 3110501 | Bridges | Naivasha | Maai Mahiu | -0.947318, 36.594714 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2024/25 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2450000 | 81.7 | 2450000 | 3494096 | 550000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes.. Viable: Yes. Assessor remarks: This project was implemented at Governor - Weru after being changed, hence the Kwanjuiri Bridge wasn't done..
1489 | Infrastructure, Development and Maintenance | Construction of Texas-Ndonga village bridge | To construct Texas-Ndonga village bridge | Texas-Ndonga village bridge constructed | 3110501 | Bridges | Naivasha | Maai Mahiu | -0.990632, 36.578457 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 3000000 | 0 | 840589.8 | Equitable | N/A | 840589.8 | 0 | 2065647 | 100 | 2065647 | 840590 | -2065647 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Backfilling and gabion installation.
1490 | Infrastructure, Development and Maintenance | Construction of Tumaini Bridge | To construct Tumaini Bridge | Tumaini Bridge constructed | 3110501 | Bridges | Naivasha | Maai Mahiu | -0.946486, 36.541664 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | N/A | 3500000 | 3494096 | 3494096 | Equitable | N/A | 3494096 | 0 | 2450000 | 70.1 | 2450000 | 3494096 | 1044096 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Project yet to start. There is a proposal for the bridge to be merged with construction of a bridge in Maai Mahiu in the FY2024/25.
1491 | Infrastructure, Development & Maintenance | Construction of Vumilia Governor -AP Foot Bridge | To construct Vumilia Governor -AP Foot Bridge | Vumilia Governor -AP Foot Bridge constructed | 3110501 | Bridges | Naivasha | Maai Mahiu | -0.966875, 36.546208 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1954020 | 97.7 | 1954020 | 2000000 | 45980 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
1492 | Infrastructure, Development and Maintenance | Construction of Wagacunga bridge | To construct Wagacunga bridge | Wagacunga bridge constructed | 3110501 | Bridges | Naivasha | Maai Mahiu | -0.946486, 36.541664 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 2450000 | 2450000 | 2450000 | Equitable | N/A | 2450000 | 0 | 2450000 | 100 | 2450000 | 2450000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Project yet to start. There is a proposal for the bridge to be merged with construction of a bridge in Maai Mahiu in the FY2024/25.
1493 | Infrastructure, Development & Maintenance | Completion of Nyondia bridge | To complete Nyondia bridge | Nyondia bridge completed | 3110501 | Bridges | Gilgil | Malewa West | -0.702703, 36.489231 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 149052 | 149052 | 149052 | Equitable | N/A | 149052 | 0 | 0 | 0 | 0 | 149052 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Assessor remarks: Survey done.
1494 | Infrastructure, Development & Maintenance | Construction of Kamungei bridge | To construct Kamungei bridge | Kamungei bridge constructed | 3110501 | Bridges | Molo | Mariashoni | -0.346125, 35.818593 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 780855 | 780855 | Equitable | N/A | 780855 | 0 | 780855 | 100 | 780855 | 780855 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Working.
1495 | Infrastructure, Development & Maintenance | Construction of Kapcherutich Bridge | To construct Kapcherutich Bridge | Kapcherutich Bridge constructed | 3110501 | Bridges | Molo | Mariashoni | -0.346125, 35.818593 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1933808 | 96.7 | 1933808 | 780855 | 66192 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Working.
1496 | Infrastructure, Development & Maintenance | Construction of Kapsimotwo Bridge | To construct Kapsimotwo Bridge | Kapsimotwo Bridge constructed | 3110501 | Bridges | Molo | Mariashoni | -0.346125, 35.818593 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1944520 | 97.2 | 1944520 | 780855 | 55480 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Working.
1497 | Infrastructure, Development & Maintenance | Construction Of Bridge At Kap Arusei | To construct Bridge At Kap Arusei | Bridge At Kap Arusei constructed | 3110501 | Bridges | Njoro | Mauche | -0.48123, 35.963507 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019 | 3000000 | 74596.65 | 74596.65 | Equitable | N/A | 74596.65 | 0 | 2925371 | 3921.6 | 2925371 | 74597 | -2850774.35 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
1498 | Construction Of Kapsawe Bridge | Construction Of Kapsawe Bridge | To construct Kapsawe Bridge | Kapsawe Bridge constructed | 3110501 | Bridges | Njoro | Mauche | -0.496008, 35.952415 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2022 | 3000000 | 836662.25 | 836662.25 | Equitable | N/A | 836662.25 | 0 | 836662 | 100 | 836662 | 836662 | 0.25 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
1499 | Construction Of Kwa Rono Bridge | Construction Of Kwa Rono Bridge | To construct Kwa Rono Bridge | Kwa Rono Bridge constructed | 3110501 | Bridges | Njoro | Mauche | -0.496008, 35.952415 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2022 | 3000000 | 2832500 | 2832500 | Equitable | N/A | 2832500 | 0 | 2780640 | 98.2 | 2780640 | 2832500 | 51860 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
1500 | Infrastructure, Development and Maintenance | Construction Of Bridge at Huruma/Upendo | To construct Bridge at Huruma/Upendo | Bridge at Huruma/Upendo constructed | 3110501 | Bridges | Molo | Molo | -0.380641 35.796196 2793.679531111378 6 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 3994693 | 100 | 3994693 | 2000000 | -3994693 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Partially. Viable: Partially. Assessor remarks: The toilet is non existent.
1501 | Infrastructure, Development and Maintenance | Construction Of Bridge at Mtaa wa Saba | To construct Bridge at Mtaa wa Saba | Bridge at Mtaa wa Saba constructed | 3110501 | Bridges | Molo | Molo | -0.801138, 36.513198 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 3994693 | 100 | 3994693 | 1000000 | -3994693 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: It is very useful.
1502 | Infrastructure, Development and Maintenance | Construction of bridge at Tayari- Molo | To construct bridge at Tayari- Molo | Bridge at Tayari- Molo constructed | 3110501 | Bridges | Molo | Molo Central | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 4000000 | 5286.55 | 5286.55 | Equitable | N/A | 5286.55 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
1503 | Infrastructure, Development and Maintenance | Construction of Kivulini Bridge | To construct Kivulini Bridge | Kivulini Bridge constructed | 3110501 | Bridges | Molo | Molo Central | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 3700000 | 3694344 | 4694344 | Equitable | N/A | 4694344 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
1504 | Infrastructure, Development and Maintenance | Molo Central Bridge in Molo Cental Ward Molo Sub County: 1200mm ID - 2lines | To implement molo central bridge in molo cental ward molo sub county: 1200mm id - 2lines for road connectivity and accessibility | Molo Central Bridge in Molo Cental Ward Molo Sub County: 1200mm ID - 2lines completed | 3110501 | Bridges | Molo | Molo Central | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | N/A | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
1505 | Infrastructure, Development and Maintenance | Repair of Foot Bridge and Installation of Culverts in Kiambogo (Munju) - Miti Mirefu - Green Garden Areas in Molo Central Ward - Molo Sub County | To rehabilitate Foot Bridge and Installation of Culverts in Kiambogo (Munju) - Miti Mirefu - Green Garden Areas in Molo Central Ward - Molo Sub County to restore functionality | Foot Bridge and Installation of Culverts in Kiambogo (Munju) - Miti Mirefu - Green Garden Areas in Molo Central Ward - Molo Sub County rehabilitated | 3110501 | Bridges | Molo | Molo Central | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | N/A | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
1506 | Infrastructure, Development and Maintenance | Construction of Gilgil-Murindat Mbegi bridge | To construct Gilgil-Murindat Mbegi bridge | Gilgil-Murindat Mbegi bridge constructed | 3110501 | Bridges | Gilgil | Murindat | -0.479849, 36.379091 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1750000 | 0 | 1750000 | Equitable | N/A | 1750000 | 0 | 3426808 | 100 | 3426808 | 1750000 | -3426808 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not done. Viable: Not done. Assessor remarks: Not done.
1507 | Infrastructure, Development & Maintenance | Construction of Kahuho bridge in Murindat | To construct Kahuho bridge in Murindat | Kahuho bridge in Murindat constructed | 3110501 | Bridges | Gilgil | Murindat | -0.420368, 36.330678 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 4000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2743027 | 91.4 | 2743027 | 3000000 | 256973 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Benline Limited. Assessor remarks: Operational.
1508 | Infrastructure, Development & Maintenance | Construction of Nicesuit bridge | To construct Nicesuit bridge | Nicesuit bridge constructed | 3110501 | Bridges | Gilgil | Murindat | -0.425456, 36.314081 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 3700000 | 3700000 | 3700000 | Equitable | N/A | 3700000 | 0 | 3426808 | 92.6 | 3426808 | 3700000 | 273192 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Amogracia Contractors Ltd. Assessor remarks: Operational.
1509 | Infrastructure, Development and Maintenance | Construction of a bridge (donkey factory) | To construct a bridge (donkey factory) | A bridge (donkey factory) constructed | 3110501 | Bridges | Naivasha | Naivasha East | -0.749061 36.530254 2084.900146484375 5.611999988555908 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1394868 | 93 | 1394868 | 1500000 | 105132 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Usable.
1510 | Infrastructure, Development & Maintenance | Construction of Kiambogo bridge | To construct Kiambogo bridge | Kiambogo bridge constructed | 3110501 | Bridges | Naivasha | Naivasha East | -0.851778, 36.515645 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019-20 | 1599910 | 1589910 | 1589910 | Equitable | N/A | 1589910 | 0 | 1589910 | 100 | 1589910 | 1589910 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
1511 | Infrastructure, Development & Maintenance | Construction Of A Bridge And Culverting At Kap Gorogoro | To construct A Bridge And Culverting At Kap Gorogoro | A Bridge And Culverting At Kap Gorogoro constructed | 3110501 | Bridges | Njoro | Nessuit | -0.361119 35.873546 2413.553466796875 4.578999996185303 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 1999640 | 1999640 | Equitable | N/A | 1999640 | 0 | 1936850 | 96.9 | 1936850 | 1999640 | 62790 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Babuye investments limited. Assessor remarks: Functional and operational.
1512 | Infrastructure, Development and Maintenance | Construction of Kap Ketiro bridge | To construct Kap Ketiro bridge | Kap Ketiro bridge constructed | 3110501 | Bridges | Njoro | Nessuit | -0.430448, 35.905942 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 3800000 | 3800000 | 3800000 | Equitable | N/A | 3800000 | 0 | 2296800 | 60.4 | 2296800 | 2296800 | 1503200 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yet to start. Viable: Yet to start. Assessor remarks: The bridge serves a big population especially school going children that use it to access school..
1513 | Infrastructure, Development and Maintenance | Design & Construction of Kap Lembigas bridge | To implement design & construction of kap lembigas bridge for road connectivity and accessibility | Design & Construction of Kap Lembigas bridge completed | 3110501 | Bridges | Njoro | Nessuit | -0.387383, 35.907231 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 2347243 | 2347243 | 2347243 | Equitable | N/A | 2347243 | 0 | 2296800 | 97.9 | 2296800 | 2296800 | 50443 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not yet started. Viable: The project is viable. Assessor remarks: It will be beneficial to the residents especially the school going kids who use a makeshift wooden bridge.The makeshift is very dangerous to the residents especially during the heavy downpour and lives have been lost.bridge is.
1514 | Infrastructure, Development and Maintenance | Construction Of Kamugulet Bridge | To construct Kamugulet Bridge | Kamugulet Bridge constructed | 3110501 | Bridges | Njoro | Nessuit | -0.430448, 35.905942 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 2000000 | 2296800 | 2296800 | Equitable | N/A | 2296800 | 0 | 2296800 | 100 | 2296800 | 2296800 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yet to start. Viable: Yet to start. Assessor remarks: The bridge serves a big population especially school going children that use it to access school..
1515 | Infrastructure, Development and Maintenance | Construction of a Footbridge at Utafiti Primary | To construct a Footbridge at Utafiti Primary | A Footbridge at Utafiti Primary constructed | 3110501 | Bridges | Njoro | Njoro | -0.323139, 35.938565 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2024 | 2500000 | 0 | 2500000 | Equitable | N/A | 2500000 | 0 | 1199768 | 100 | 1199768 | 2500000 | -1199768 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: In good state.
1516 | Infrastructure, Development & Maintenance | Construction of soliat masaita bridge | To construct soliat masaita bridge | Soliat masaita bridge constructed | 3110501 | Bridges | Kuresoi North | Nyota | -0.30826, 35.604622 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | - | 2000000 | 0 | 1993645 | Equitable | N/A | 1993645 | 0 | 317534 | 100 | 317534 | 1993645 | -317534 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: YES. Viable: YES. Assessor remarks: Good.
1517 | Construction Of A Bridge/Culverts Along Lomolo A-Lomolo B Road | Construction Of A Bridge/Culverts Along Lomolo A-Lomolo B Road | To construct A Bridge/Culverts Along Lomolo A-Lomolo B Road | A Bridge/Culverts Along Lomolo A-Lomolo B Road constructed | 3110501 | Bridges | Rongai | Soin | 0.00414, 36.036628 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | FY 2020 | 800000 | 748000 | 748000 | Equitable | N/A | 748000 | 0 | 748000 | 100 | 748000 | 748000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
1518 | Infrastructure, Development and Maintenance | Construction Of Sawaiti Bridge | To construct Sawaiti Bridge | Sawaiti Bridge constructed | 3110501 | Bridges | Rongai | Soin | -0.061284, 36.043651 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1438624 | 95.9 | 1438624 | 61376 | 61376 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Vandalized.
1519 | Infrastructure, Development and Maintenance | Construction Of Bokibor Bridge | To construct Bokibor Bridge | Bokibor Bridge constructed | 3110501 | Bridges | Kuresoi South | Tinet | -0.52716, 35.651287 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 1999113 | 100 | 1999113 | 3000000 | -1999113 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Ongoing.
1520 | Infrastructure, Development and Maintenance | Construction of Chepsoet bridge | To construct Chepsoet bridge | Chepsoet bridge constructed | 3110501 | Bridges | Kuresoi South | Tinet | -0.445126 35.609035 0 2200 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 3000000 | 2741140 | 2711140 | Equitable | N/A | 2711140 | 0 | 1999113 | 72.9 | 1999113 | 2741140 | 742027 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: Yes but not meet the need. Assessor remarks: Converted to staff quarters.
1521 | Infrastructure, Development and Maintenance | Construction of Kapkembu River Bridge 3M High Single Lane in Tinet Ward - Kuresoi South Sub County | To construct Kapkembu River Bridge 3M High Single Lane in Tinet Ward - Kuresoi South Sub County | Kapkembu River Bridge 3M High Single Lane in Tinet Ward - Kuresoi South Sub County constructed | 3110501 | Bridges | Kuresoi South | Tinet | -0.47504 35.631932 0 2400 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 1951320 | 1926890 | 1926890 | Equitable | N/A | 1926890 | 0 | 1926890 | 100 | 1926890 | 1926890 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Bad. Objective met: No. Viable: Yes but it was never started. Assessor remarks: Never started/established.
1522 | Infrastructure, Development and Maintenance | Construction of Kapkembu-Kapaon Bridge | To construct Kapkembu-Kapaon Bridge | Kapkembu-Kapaon Bridge constructed | 3110501 | Bridges | Kuresoi South | Tinet | -0.520868 35.620393 2526.8999999999996 4 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | N/A | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 2634354 | 100 | 2634354 | 3000000 | -2634354 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
1523 | Infrastructure, Development & Maintenance | Construction of Kereswa-Kapket Bridge and road | To construct Kereswa-Kapket Bridge and road | Kereswa-Kapket Bridge and road constructed | 3110501 | Bridges | Kuresoi South | Tinet | -0.529565, 35.610744 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 4000000 | 3817640 | 3817640 | Equitable | N/A | 3817640 | 0 | 3817640 | 100 | 3817640 | 3817640 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Murrum washed away by rain.
1524 | Infrastructure, Development and Maintenance | Construction Of Kimaech Bridge | To construct Kimaech Bridge | Kimaech Bridge constructed | 3110501 | Bridges | Kuresoi South | Tinet | -0.445126 35.609035 0 2200 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 2952722 | 2952722 | Equitable | N/A | 2952722 | 0 | 2634354 | 89.2 | 2634354 | 318368 | 318368 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: Yes but not meet the need. Assessor remarks: Converted to staff quarters.
1525 | Infrastructure, Development and Maintenance | Construction Of Taita Bridge | To construct Taita Bridge | Taita Bridge constructed | 3110501 | Bridges | Kuresoi South | Tinet | -0.445126 35.609035 0 2200 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1900195 | 95 | 1900195 | 99805 | 99805 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: Yes but not meet the need. Assessor remarks: Converted to staff quarters.
1526 | Infrastructure, Development and Maintenance | Construction Of Tinet Dispensary Bridge | To construct Tinet Dispensary Bridge | Tinet Dispensary Bridge constructed | 3110501 | Bridges | Kuresoi South | Tinet | -0.47504 35.631932 0 2400 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2998415 | 99.9 | 2998415 | 3000000 | 1585 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: Yes. Assessor remarks: Complete not equipped.
1527 | Infrastructure, Development and Maintenance | Construction Of Tinet- Kaprengero Bridge | To construct Tinet- Kaprengero Bridge | Tinet- Kaprengero Bridge constructed | 3110501 | Bridges | Kuresoi South | Tinet | -0.511222 35.692048 0 1200 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2998415 | 99.9 | 2998415 | 3000000 | 1585 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
1528 | Infrastructure, Development and Maintenance | Construction of Tinet-Kaprengero Bridge | To construct Tinet-Kaprengero Bridge | Tinet-Kaprengero Bridge constructed | 3110501 | Bridges | Kuresoi South | Tinet | -0.511222 35.692048 0 1200 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2998415 | 99.9 | 2998415 | 3000000 | 1585 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
1529 | Infrastructure, Development & Maintenance | Design and Construction of Kipsotet-Chepkesigen bridge | To design and construct Kipsotet-Chepkesigen bridge | Kipsotet-Chepkesigen bridge designed and constructed | 3110501 | Bridges | Kuresoi South | Tinet | -0.509848, 35.664498 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 3000000 | 2998930 | 2998930 | Equitable | N/A | 2998930 | 0 | 2981947 | 99.4 | 2981947 | 2998930 | 16983 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good state.
1530 | Infrastructure, Development & Maintenance | Construction of bridge and culverts across Turi ward | To construct bridge and culverts across Turi ward | Bridge and culverts across Turi ward constructed | 3110501 | Bridges | Molo | Turi | -0.288588, 35.693317 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1805852 | 90.3 | 1805852 | 2000000 | 194148 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The bridge was well constructed but there is no road ahead since it requires heavy dozing for the road to be operational. No backfilling was done to the bridge.
1531 | Infrastructure, Development and Maintenance | Construction of Milima Mitatu Footbridge | To construct Milima Mitatu Footbridge | Milima Mitatu Footbridge constructed | 3110501 | Bridges | Molo | Turi | -0.297121 35.713899 2654.8 72.9000015258789 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 500000 | 0 | 499658.4 | Equitable | N/A | 499658.4 | 0 | 208990 | 100 | 208990 | 499658 | -208990 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
1532 | Infrastructure, Development & Maintenance | Construction Of Kayole-Boito Bridge | To construct Kayole-Boito Bridge | Kayole-Boito Bridge constructed | 3110501 | Bridges | Rongai | Visoi | -0.160137, 35.871107 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1400000 | 1400000 | 1400000 | Equitable | N/A | 1400000 | 0 | 1400000 | 100 | 1400000 | 1400000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
1533 | Infrastructure, Development and Maintenance | Construction Of Magare Bridge | To construct Magare Bridge | Magare Bridge constructed | 3110501 | Bridges | Rongai | Visoi | -0.102878 35.914592 1711.9 6.099999904632568 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1400000 | 1400000 | 1400000 | Equitable | N/A | 1400000 | 0 | 1360750 | 97.2 | 1360750 | 1400000 | 39250 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
1534 | Infrastructure, Development & Maintenance | Construction of Makanisa Mingi Bridge (Kwa Mbari) | To construct Makanisa Mingi Bridge (Kwa Mbari) | Makanisa Mingi Bridge (Kwa Mbari) constructed | 3110501 | Bridges | Rongai | Visoi | -0.102878 35.914592 1711.9 6.099999904632568 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | N/A | 400000 | 0 | 400000 | Equitable | N/A | 400000 | 0 | 1360750 | 0 | 1360750 | 400000 | 0 | Stalled | 90 | N/A | Awaiting for more allocation of fund in the next FY. Documentation | 2021 | N/A | N/A | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
1535 | Infrastructure, Development and Maintenance | Construction of Mawe and Mogiiwet footbridge | To construct Mawe and Mogiiwet footbridge | Mawe and Mogiiwet footbridge constructed | 3110501 | Bridges | Rongai | Visoi | -0.102878 35.914592 1711.9 6.099999904632568 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 1360750 | 34 | 1360750 | 2000000 | 2639250 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
1536 | Infrastructure, Development & Maintenance | Construction of Mawe -Birir bridge | To construct Mawe -Birir bridge | Mawe -Birir bridge constructed | 3110501 | Bridges | Rongai | Visoi | -0.160137, 35.871107 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1360750 | 68 | 1360750 | 2000000 | 639250 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
1537 | Infrastructure, Development and Maintenance | Construction Of Thirandu Bridge | To construct Thirandu Bridge | Thirandu Bridge constructed | 3110501 | Bridges | Rongai | Visoi | -0.102878 35.914592 1711.9 6.099999904632568 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1009490 | 100.9 | 1009490 | 1000000 | -9490 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
1538 | Infrastructure, Development and Maintenance | Repair Of Bridges At Kware, Thirandu And Kanga | To rehabilitate Bridges At Kware, Thirandu And Kanga to restore functionality | Bridges At Kware, Thirandu And Kanga rehabilitated | 3110501 | Bridges | Rongai | Visoi | -0.139406 35.905676 1808.19482421875 5.670000076293945 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1400000 | 1400000 | 1400000 | Equitable | N/A | 1400000 | 0 | 1237905 | 88.4 | 1237905 | 1400000 | 162095 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
1539 | Construction Of Wei Cross Bridge | Construction Of Wei Cross Bridge | To construct Wei Cross Bridge | Wei Cross Bridge constructed | 3110501 | Bridges | Subukia | Waseges | 0.005697 36.25448 2085.5 13.5 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2019/20 | 2019/20 | 3500000 | 1096.2 | 1096.2 | Equitable | N/A | 1096.2 | 0 | 941839 | 85918.5 | 941839 | 1096 | -940742.8 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The is in use.
1540 | Infrastructure, Development and Maintenance | Construction of two boda boda shed across the ward | To construct two boda boda shed across the ward | Two boda boda shed across the ward constructed | 3110504 | Other Infrastructure and Civil Works | Bahati | Bahati | -0.151909, 36.144662 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 900000 | 900000 | 900000 | Equitable | N/A | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
1541 | Infrastructure, Development and Maintenance | Highmast maintenance | To implement highmast maintenance for road connectivity and accessibility | Highmast maintenance completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Bahati | -0.158327, 36.166215 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 1600000 | 1600000 | 1600000 | Equitable | N/A | 1600000 | 0 | 1600000 | 100 | 1600000 | 300000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: The project is not working at the moment.
1542 | Infrastructure, Development and Maintenance | Installation Of Culverts In 5 Locations In Dundori Access Roads | To improve drainage and road access through culvert installation at In 5 Locations In Dundori Access Roads | Culverts installed at In 5 Locations In Dundori Access Roads | 3110504 | Other Infrastructure and Civil Works | Bahati | Bahati | -0.154558 36.146584 2048.5 68.4000015258789 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 1790001 | 1790001 | Equitable | N/A | 1790001 | 0 | 1789870 | 100 | 1789870 | 131 | 131 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Piping of water is required.
1543 | Infrastructure, Development and Maintenance | Installation of High Mast flood lights at Corner Baraka | To improve security lighting through high mast floodlight installation at flood lights at Corner Baraka | High mast floodlight installed at flood lights at Corner Baraka | 3110504 | Other Infrastructure and Civil Works | Bahati | Bahati | -0.125317, 36.159568 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 328400 | 82.1 | 328400 | 1500000 | 71600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes it is. Assessor remarks: The floodlight is in use.
1544 | Infrastructure, Development and Maintenance | Installation of High mast solar lighting | To improve security lighting through high mast floodlight installation at solar lighting | High mast floodlight installed at solar lighting | 3110504 | Other Infrastructure and Civil Works | Bahati | Bahati | -0.17352, 36.13302 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 3072327 | 3072327 | 3072327 | Equitable | N/A | 3072327 | 0 | 328400 | 10.7 | 328400 | 1500000 | 2743927 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The projects is in use.
1545 | Infrastructure, Development and Maintenance | Installation of highmast streetlights (mulika mwizi) in Bahati ward | To improve security lighting through high mast floodlight installation at streetlights (mulika mwizi) in Bahati ward | High mast floodlight installed at streetlights (mulika mwizi) in Bahati ward | 3110504 | Other Infrastructure and Civil Works | Bahati | Bahati | -0.194242, 36.133374 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 1500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not yet done.
1546 | Infrastructure, Development and Maintenance | Installation of streetlights across the ward (Bahati Ward) | To improve lighting and safety through installation of solar streetlights at across the ward (Bahati Ward) | Solar streetlights installed at across the ward (Bahati Ward) | 3110504 | Other Infrastructure and Civil Works | Bahati | Bahati | -0.154694 36.099038 0 39.599998474121094 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 646391 | 80.8 | 646391 | 153609 | 153609 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Working very well.
1547 | Infrastructure, Development and Maintenance | Maintenance Of Street Lights | To implement maintenance of street lights for road connectivity and accessibility | Maintenance Of Street Lights completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Bahati | -0.161814, 36.109552 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 675000 | 96.4 | 675000 | 25000 | 25000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: LEDs light required.
1548 | Infrastructure, Development & Maintenance | Streetlights maintenance | To implement streetlights maintenance for road connectivity and accessibility | Streetlights maintenance completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Bahati | -0.154969 36.097733 1856.6309972650731 4.501999855041504 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | N/A | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 1600000 | 533.3 | 1600000 | 300000 | -1300000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Assessor remarks: The road needs to be redone.
1549 | Infrastructure, Development and Maintenance | Construction of boda boda sheds | To construct boda boda sheds | Boda boda sheds constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Barut | -0.342405, 36.0423 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2024 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/S Raindrops Contractors P.O Box 6232-00100 Nakuru.. Assessor remarks: It's on going.
1550 | Infrastructure, Development and Maintenance | High mast lights installation at Mwariki and Kaptich | To implement high mast lights installation at mwariki and kaptich for road connectivity and accessibility | High mast lights installation at Mwariki and Kaptich completed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Barut | -0.3424 36.042 0 2000 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 3000000 | 2988700 | 2988700 | Equitable | N/A | 2988700 | 0 | 2988700 | 100 | 2988700 | 2988700 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Some are functional.
1551 | Infrastructure, Development and Maintenance | Installation Of Four High Mast In Barut | To install Four High Mast In Barut | Four High Mast In Barut installed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Barut | -0.32524 36.0458 0 2000 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2040992 | 1991750 | 1991750 | Equitable | N/A | 1991750 | 0 | 1991750 | 100 | 1991750 | 1991750 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: They are functional.
1552 | Infrastructure, Development and Maintenance | Installation Of High Mast Street Lights at Barut Ward | To improve security lighting through high mast floodlight installation at Street Lights at Barut Ward | High mast floodlight installed at Street Lights at Barut Ward | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Barut | -1.2841, 36.8155 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 3000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3574125 | 89.4 | 3574125 | 425875 | 425875 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Bad. Objective met: no. Viable: no. Assessor remarks: site handed over.
1553 | Infrastructure, Development and Maintenance | Installation of high mast streetlights in Barut Ward | To improve security lighting through high mast floodlight installation at streetlights in Barut Ward | High mast floodlight installed at streetlights in Barut Ward | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Barut | -1.2841, 36.8155 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 3574125 | 59.6 | 3574125 | 425875 | 2425875 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Bad. Objective met: no. Viable: no. Assessor remarks: site handed over.
1554 | Infrastructure, Development and Maintenance | Installation Of Streetlights at Barut Ward | To improve lighting and safety through installation of solar streetlights at Barut Ward | Solar streetlights installed at Barut Ward | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Barut | -1.2841, 36.8155 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 2996466 | 0 | 2996466 | Equitable | N/A | 2996466 | 0 | 3574125 | 100 | 3574125 | 2996466 | -3574125 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Bad. Objective met: no. Viable: no. Assessor remarks: site handed over.
1555 | Infrastructure, Development and Maintenance | Maintenance Of Security Lights at Barut Ward | To implement maintenance of security lights at barut ward for road connectivity and accessibility | Maintenance Of Security Lights at Barut Ward completed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Barut | 0.3624 36.042 0 2000 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 500000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 914200 | 91.4 | 914200 | 85800 | 85800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good state of repair.
1556 | Infrastructure, Development and Maintenance | Maintenance of streetlights at barut ward | To implement maintenance of streetlights at barut ward for road connectivity and accessibility | Maintenance of streetlights at barut ward completed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Barut | -0.3242, 36.042 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2024 | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 914200 | 100 | 914200 | 85800 | -914200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Completed.
1557 | Infrastructure, Development and Maintenance | Drainage Works and Culverts in Kinamba Town | To implement drainage works and culverts in kinamba town for road connectivity and accessibility | Drainage Works and Culverts in Kinamba Town completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Biashara-Naivasha | -0.722032, 36.474828 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2024 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3422579 | 97.8 | 3422579 | 77421 | 77421 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Fairly. Viable: Fairly. Contractor: Ndakuki. Assessor remarks: 50m line drain needs to extension to upper end of town.,routine maintaince of the road..
1558 | Infrastructure, Development & Maintenance | Installation of Gituru streetlights | To install Gituru streetlights | Gituru streetlights installed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Biashara-Naivasha | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999970 | 100 | 1999970 | 2000000 | 30 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1559 | Infrastructure, Development & Maintenance | Installation of Kinamba streetlights | To install Kinamba streetlights | Kinamba streetlights installed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Biashara-Naivasha | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 7000000 | 5100000 | 7000000 | Equitable | N/A | 7000000 | 0 | 2999986 | 58.8 | 2999986 | 3000000 | 2100014 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1560 | Infrastructure, Development and Maintenance | Installation Of Streetlights Across the Ward | To improve lighting and safety through installation of solar streetlights at Across the Ward | Solar streetlights installed at Across the Ward | 3110504 | Other Infrastructure and Civil Works | Naivasha | Biashara-Naivasha | -0.722022, 36.474813 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2024 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3981000 | 99.5 | 3981000 | 19000 | 19000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Not known.. Assessor remarks: In good condition but need frequent servicing.
1561 | Infrastructure, Development and Maintenance | Construction of four bodaboda sheds at Freehold, Section 58, Kisulisuli and Kichinjio | To construct four bodaboda sheds at Freehold, Section 58, Kisulisuli and Kichinjio | Four bodaboda sheds at Freehold, Section 58, Kisulisuli and Kichinjio constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | -0.284002, 36.093736 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2024/25 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
1562 | Infrastructure, Development and Maintenance | Construction of motorbike sheds at Mt. Kenya University, Christ the King, Nyamira Flats and Nakuru Day Secondary | To construct motorbike sheds at Mt. Kenya University, Christ the King, Nyamira Flats and Nakuru Day Secondary | Motorbike sheds at Mt. Kenya University, Christ the King, Nyamira Flats and Nakuru Day Secondary constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1052600 | 87.7 | 1052600 | 147400 | 147400 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1563 | Infrastructure, Development and Maintenance | Installation of four 13-meter-high streetlights at Pyrethrum Estate, Christ the King Junction, Rangies road-YMCA, and Stadium Road near Friends Church | To install four 13-meter-high streetlights at Pyrethrum Estate, Christ the King Junction, Rangies road-YMCA, and Stadium Road near Friends Church | Four 13-meter-high streetlights at Pyrethrum Estate, Christ the King Junction, Rangies road-YMCA, and Stadium Road near Friends Church installed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | -0.292444, 36.06988 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2024/25 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Its operational.
1564 | Infrastructure, Development and Maintenance | Installation of high mast streetlighting | To improve security lighting through high mast floodlight installation at streetlighting | High mast floodlight installed at streetlighting | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1500000 | 150 | 1500000 | 1000000 | -500000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1565 | Infrastructure, Development & Maintenance | Maintenance of streetlighting | To implement maintenance of streetlighting for road connectivity and accessibility | Maintenance of streetlighting completed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | N/A | 1600000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
1566 | Infrastructure, Development & Maintenance | Maintenance of streetlights across the ward | To implement maintenance of streetlights across the ward for road connectivity and accessibility | Maintenance of streetlights across the ward completed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 1606500 | 100 | 1606500 | 1000000 | -1606500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1567 | Infrastructure, Development and Maintenance | Rehabilitation of streetlights across Biashara Ward | To rehabilitate streetlights across Biashara Ward to restore functionality | Streetlights across Biashara Ward rehabilitated | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 599500 | 30 | 599500 | 599500 | 1400500 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
1568 | Infrastructure, Development and Maintenance | Rehabilitation of streetlights in Biashara ward | To rehabilitate streetlights in Biashara ward to restore functionality | Streetlights in Biashara ward rehabilitated | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 600000 | 599500 | 599500 | Equitable | N/A | 599500 | 0 | 599500 | 100 | 599500 | 599500 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
1569 | Infrastructure, Development and Maintenance | Security Lights Maintenance across the Ward | To implement security lights maintenance across the ward for road connectivity and accessibility | Security Lights Maintenance across the Ward completed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 1700000 | 1700000 | 1700000 | Equitable | N/A | 1700000 | 0 | 1606500 | 94.5 | 1606500 | 93500 | 93500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1570 | Infrastructure, Development and Maintenance | Installation of 10 no highmast floodlights | To install 10 no highmast floodlights | 10 no highmast floodlights installed | 3110504 | Other Infrastructure and Civil Works | Bahati | Dundori | -0.263586, 36.188365 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/2022 | 3200000 | 0 | 1802800 | Equitable | N/A | 1802800 | 0 | 1397200 | 100 | 1397200 | 1802800 | -1397200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s sincere electrical. Assessor remarks: 10 number installed in ward currently require being serviced.
1571 | Infrastructure, Development and Maintenance | Installation of high mast lights at Wanguhu borehole and Tabiga Mbaruk lane | To improve security lighting through high mast floodlight installation at lights at Wanguhu borehole and Tabiga Mbaruk lane | High mast floodlight installed at lights at Wanguhu borehole and Tabiga Mbaruk lane | 3110504 | Other Infrastructure and Civil Works | Bahati | Dundori | -0.259738, 36.189711 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2024/2025 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 2103400 | 210.3 | 2103400 | 2103400 | -1103400 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
1572 | Infrastructure, Development and Maintenance | Installation of high mast security lights at Upper Dundori and Githioro Sub Location | To improve security lighting through high mast floodlight installation at security lights at Upper Dundori and Githioro Sub Location | High mast floodlight installed at security lights at Upper Dundori and Githioro Sub Location | 3110504 | Other Infrastructure and Civil Works | Bahati | Dundori | -0.2633, 36.187225 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/203 | 2300000 | 2103400 | 2103400 | Equitable | N/A | 2103400 | 0 | 2103400 | 100 | 2103400 | 2103400 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Wellbuck. Assessor remarks: They are six in nimber.
1573 | Infrastructure, Development & Maintenance | Installation of High Mast Street Lighting floodlights in Dundori ward | To improve security lighting through high mast floodlight installation at Street Lighting floodlights in Dundori ward | High mast floodlight installed at Street Lighting floodlights in Dundori ward | 3110504 | Other Infrastructure and Civil Works | Bahati | Dundori | -0.262936, 36.190874 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/2021 | 2800000 | 2800000 | 2800000 | Equitable | N/A | 2800000 | 0 | 2791150 | 99.7 | 2791150 | 2800000 | 8850 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Holy son. Assessor remarks: Good.
1574 | Infrastructure, Development & Maintenance | Installation of high mast streetlights | To improve security lighting through high mast floodlight installation at streetlights | High mast floodlight installed at streetlights | 3110504 | Other Infrastructure and Civil Works | Bahati | Dundori | -0.254746, 36.233905 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/2019 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 871400 | 87.1 | 871400 | 1000000 | 128600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ms Holy sons. Assessor remarks: Good require maintenance.
1575 | Installation of highmast floodlights meter at Kiwamu Dispensary and Dundori Health Center and other repairs | Installation of highmast floodlights meter at Kiwamu Dispensary and Dundori Health Center and other repairs | To improve security lighting through high mast floodlight installation at s meter at Kiwamu Dispensary and Dundori Health Center and other repairs | High mast floodlight installed at s meter at Kiwamu Dispensary and Dundori Health Center and other repairs | 3110504 | Other Infrastructure and Civil Works | Bahati | Dundori | -0.237126, 36.167582 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/2021 | 100000 | 100000 | 100000 | Equitable | N/A | 100000 | 0 | 2103400 | 2103.4 | 2103400 | 100000 | -2003400 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
1576 | Infrastructure, Development & Maintenance | Purchase and installation of culverts in Githioro / Mugwathi access roads | To procure and install culverts in Githioro / Mugwathi access roads | Culverts in Githioro / Mugwathi access roads procured and installed | 3110504 | Other Infrastructure and Civil Works | Bahati | Dundori | -0.237125, 36.167581 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/2016 | 106553.03 | 106553.03 | 106553.03 | Equitable | N/A | 106553.03 | 0 | 106553 | 100 | 106553 | 106553 | 0.03 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition, require maintenance.
1577 | Infrastructure, Development & Maintenance | Rehabilitation of streetlights - Purchase and supply of floodlights accessories for maintenance and repairing | To rehabilitate streetlights - Purchase and supply of floodlights accessories for maintenance and repairing to restore functionality | Streetlights - Purchase and supply of floodlights accessories for maintenance and repairing rehabilitated | 3110504 | Other Infrastructure and Civil Works | Bahati | Dundori | -0.263236, 36.187524 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/2022 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 983500 | 98.4 | 983500 | 0 | 16500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ms sincere electrical sales and services. Assessor remarks: Good.
1578 | Infrastructure, Development and Maintenance | Installation of street lights in Eburru/Mbaruk | To install street lights in Eburru/Mbaruk | Street lights in Eburru/Mbaruk installed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Eburru-Mbaruk | -0.353544, 36.211277 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 24/25 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 2423520 | 48.5 | 2423520 | 376480 | 2576480 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes , it's viable. Contractor: Not specified. Assessor remarks: Works well.
1579 | Infrastructure, Development and Maintenance | Rehabilitation of street lights | To rehabilitate street lights to restore functionality | Street lights rehabilitated | 3110504 | Other Infrastructure and Civil Works | Gilgil | Eburru-Mbaruk | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 495500 | 99.1 | 495500 | 4500 | 4500 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
1580 | Infrastructure, Development and Maintenance | Installation of five highmast lighting within the ward | To install five highmast lighting within the ward | Five highmast lighting within the ward installed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Eburru/Mbaruk | -0.361044, 36.19708 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 22/23 | 1300000 | 412900 | 412900 | Equitable | N/A | 412900 | 0 | 887100 | 214.8 | 887100 | 412900 | -474200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Unspecified. Assessor remarks: Works welk.
1581 | Infrastructure, Development & Maintenance | Installation of flood lights across the ward | To install flood lights across the ward | Flood lights across the ward installed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Eburru/Mbaruk | -0.6478203, 36.6266263 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 21-22 | 5000000 | 4765250 | 4765250 | Equitable | N/A | 4765250 | 0 | 4765250 | 100 | 4765250 | 4765250 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not specified. Assessor remarks: More needed.
1582 | Infrastructure, Development and Maintenance | Installation Of Street Lights in Eburru Mbaruk | To install Street Lights in Eburru Mbaruk | Street Lights in Eburru Mbaruk installed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Eburru/Mbaruk | -0.353544, 36.211277 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 24/25 | 2800000 | 2800000 | 2800000 | Equitable | N/A | 2800000 | 0 | 2423520 | 86.6 | 2423520 | 376480 | 376480 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes , it's viable. Contractor: Not specified. Assessor remarks: Works well.
1583 | Infrastructure, Development and Maintenance | Installation of Street Lights in Eburru/Mbaruk Ward | To install Street Lights in Eburru/Mbaruk Ward | Street Lights in Eburru/Mbaruk Ward installed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Eburru/Mbaruk | -0.353544, 36.211277 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 24/25 | 1500000 | 1347720 | 1347720 | Equitable | N/A | 1347720 | 0 | 1347720 | 100 | 1347720 | 1347720 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes , it's viable. Contractor: Not specified. Assessor remarks: Works well.
1584 | Infrastructure, Development and Maintenance | Maintenance of streetlights | To implement maintenance of streetlights for road connectivity and accessibility | Maintenance of streetlights completed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Eburru/Mbaruk | -0.348433, 36.22162 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 23/24 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 495500 | 99.1 | 495500 | 4500 | 4500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Maintenance is key. Viable: Yes. Contractor: Not indcated. Assessor remarks: It's in good working condition.
1585 | Infrastructure, Development and Maintenance | Completion Of Box Culvert at Mugumo Road | To complete Box Culvert at Mugumo Road | Box Culvert at Mugumo Road completed | 3110504 | Other Infrastructure and Civil Works | Molo | Elburgon | -0.294954 35.766447 0 2799.9990234375 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 1300000 | 1300000 | 3500000 | Equitable | N/A | 3500000 | 0 | 920145 | 70.8 | 920145 | 1300000 | 379855 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
1586 | Infrastructure, Development and Maintenance | Construction of Car wash shed at Kahuruko Road | To construct Car wash shed at Kahuruko Road | Car wash shed at Kahuruko Road constructed | 3110504 | Other Infrastructure and Civil Works | Molo | Elburgon | -0.288188 35.816137 2443.8 11.800000190734863 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | N/A | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 965294 | 241.3 | 965294 | 400000 | -565294 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
1587 | Construction of Mwatu A drainage | Construction of Mwatu A drainage | To construct Mwatu A drainage | Mwatu A drainage constructed | 3110504 | Other Infrastructure and Civil Works | Molo | Elburgon | -0.292988, 35.799262 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | -- | 3000000 | 12135.38 | 12135.38 | Equitable | N/A | 12135.38 | 0 | 2948335 | 24295.4 | 2948335 | 12135 | -2936199.62 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Well done.
1588 | Construction of Mwatu B Kasarani drainage | Construction of Mwatu B Kasarani drainage | To construct Mwatu B Kasarani drainage | Mwatu B Kasarani drainage constructed | 3110504 | Other Infrastructure and Civil Works | Molo | Elburgon | -0.292975, 35.799212 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | - | 3043892 | 15713.31 | 15713.31 | Equitable | N/A | 15713.31 | 0 | 3004757 | 19122.4 | 3004757 | 15713 | -2989043.69 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
1589 | Infrastructure, Development and Maintenance | Installation of Culverts at Nyakiambi Access roads | To improve drainage and road access through culvert installation at Nyakiambi Access roads | Culverts installed at Nyakiambi Access roads | 3110504 | Other Infrastructure and Civil Works | Molo | Elburgon | -0.284884, 35.845889 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | - | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 920145 | 92 | 920145 | 1186660 | 79855 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
1590 | Infrastructure, Development & Maintenance | Installation of Elburgon ward culverts | To install Elburgon ward culverts | Elburgon ward culverts installed | 3110504 | Other Infrastructure and Civil Works | Molo | Elburgon | -0.303366, 35.81419 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | - | 700000 | 1857.5 | 1857.5 | Equitable | N/A | 1857.5 | 0 | 662173 | 35648.6 | 662173 | 1858 | -660315.5 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
1591 | Infrastructure, Development and Maintenance | Installation Of Seven (7) Streetlights Across Elburgon Ward | To install Seven (7) Streetlights Across Elburgon Ward | Seven (7) Streetlights Across Elburgon Ward installed | 3110504 | Other Infrastructure and Civil Works | Molo | Elburgon | -0.303366, 35.81419 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | - | 2800000 | 0 | 2800000 | Equitable | N/A | 2800000 | 0 | 1161000 | 100 | 1161000 | 2800000 | -1161000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
1592 | Infrastructure, Development and Maintenance | Installation of Street Lights at Mathuke, AIC, DO's Office | To install Street Lights at Mathuke, AIC, DO's Office | Street Lights at Mathuke, AIC, DO's Office installed | 3110504 | Other Infrastructure and Civil Works | Molo | Elburgon | -0.303366, 35.81419 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | - | 900000 | 892764 | 892764 | Equitable | N/A | 892764 | 0 | 892764 | 100 | 892764 | 892764 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
1593 | Infrastructure, Development and Maintenance | Installation of streetlights in Elburgon Ward | To improve lighting and safety through installation of solar streetlights at Elburgon Ward | Solar streetlights installed at Elburgon Ward | 3110504 | Other Infrastructure and Civil Works | Molo | Elburgon | -0.303366, 35.81419 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | - | 1350000 | 1350000 | 2300000 | Equitable | N/A | 2300000 | 0 | 1161000 | 86 | 1161000 | 2800000 | 189000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
1594 | Streetlight maintenance across the ward | Streetlight maintenance across the ward | To implement streetlight maintenance across the ward for road connectivity and accessibility | Streetlight maintenance across the ward completed | 3110504 | Other Infrastructure and Civil Works | Molo | Elburgon | -0.303366 35.81419 0 2000 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 385789 | 385789 | 385789 | Equitable | N/A | 385789 | 0 | 0 | 0 | 0 | 385789 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
1595 | Infrastructure, Development and Maintenance | Construction of Kiptangwanyi drainages | To construct Kiptangwanyi drainages | Kiptangwanyi drainages constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Elementaita | -0.563416 36.116992 1960.699951171875 0.6940000057220459 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | N/A | 8000000 | 689016.2 | 689016.2 | Equitable | N/A | 689016.2 | 0 | 6424879 | 932.5 | 6424879 | 689016 | -5735862.8 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
1596 | Infrastructure, Development and Maintenance | Culverts installation across the ward | To implement culverts installation across the ward for road connectivity and accessibility | Culverts installation across the ward completed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Elementaita | -0.505133, 36.078115 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
1597 | Maintenance of highmast streetlights in Elementaita ward | Maintenance of highmast streetlights in Elementaita ward | To implement maintenance of highmast streetlights in elementaita ward for road connectivity and accessibility | Maintenance of highmast streetlights in Elementaita ward completed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Elementaita | -0.489651, 36.156922 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 22308736 | 1487.2 | 22308736 | 1500000 | -20808736 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need routine Maintenance.
1598 | Infrastructure, Development and Maintenance | Construction of drainage at Lakeview Estate (Kipsigis road) | To construct drainage at Lakeview Estate (Kipsigis road) | Drainage at Lakeview Estate (Kipsigis road) constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Flamingo | -0.308058, 36.079119 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2024/2025 | 1730000 | 1000000 | 1730000 | Equitable | N/A | 1730000 | 0 | 3999680 | 400 | 3999680 | 3999680 | -2999680 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Functional and in operation.
1599 | Infrastructure, Development and Maintenance | Construction of six bodaboda sheds across the Ward | To construct six bodaboda sheds across the Ward | Six bodaboda sheds across the Ward constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Flamingo | -0.299279, 36.073882 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2024/25 | 2700000 | 2700000 | 2700000 | Equitable | N/A | 2700000 | 0 | 1957540 | 72.5 | 1957540 | 42460 | 742460 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Not yet. Assessor remarks: Yet to start.
1600 | Infrastructure, Development and Maintenance | Drainage Maintenance Across the Ward | To implement drainage maintenance across the ward for road connectivity and accessibility | Drainage Maintenance Across the Ward completed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Flamingo | -0.307851, 36.079105 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/2024 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Lumiseal enterprises Ltd. Assessor remarks: In good state.
1601 | Infrastructure, Development & Maintenance | Installation Of 5 No (13M) High Mast Street Lights At Lake View And Race Course Estates | To install 5 No (13M) High Mast Street Lights At Lake View And Race Course Estates | 5 No (13M) High Mast Street Lights At Lake View And Race Course Estates installed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Flamingo | -0.310232, 36.073934 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2018/2019 | 1500000 | 1420750 | 1420750 | Equitable | N/A | 1420750 | 0 | 1420750 | 100 | 1420750 | 1420750 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Leogeo general agencies. Assessor remarks: Functional.
1602 | Infrastructure, Development and Maintenance | Proposed rehabilitation,cleaning and installation of culverts acrosss the ward | To undertake the proposed rehabilitation,cleaning and installation of culverts acrosss the ward | Proposed rehabilitation,cleaning and installation of culverts acrosss the ward implemented | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Flamingo | -0.301183, 36.073542 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2024/25 | 1500000 | 0 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Good. Objective met: Yes it will. Viable: It will. Contractor: Ardent Logistics. Assessor remarks: Ongoing.
1603 | Infrastructure, Development and Maintenance | Rehabilitation and construction of drainage at Pangani estate | To rehabilitate construction of drainage at Pangani estate to restore functionality | Construction of drainage at Pangani estate rehabilitated | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Flamingo | -0.299279, 36.073882 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2024/25 | 2100000 | 1000000 | 2100000 | Equitable | N/A | 2100000 | 0 | 1892100 | 189.2 | 1892100 | 107900 | -892100 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Lumiseal enterprises. Assessor remarks: Ongoing.
1604 | Infrastructure, Development and Maintenance | Rehabilitation Of Drainage System at Flamingo & Kimathi Estate | To rehabilitate Drainage System at Flamingo & Kimathi Estate to restore functionality | Drainage System at Flamingo & Kimathi Estate rehabilitated | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Flamingo | -0.30376, 36.078488 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1892100 | 94.6 | 1892100 | 107900 | 107900 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Complete.
1605 | Infrastructure, Development and Maintenance | Rehabilitation of streetlights | To rehabilitate streetlights to restore functionality | Streetlights rehabilitated | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Flamingo | -0.308245, 36.079225 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2024/2025 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: In operation.
1606 | Infrastructure, Development and Maintenance | Security Lights Installation in Flamingo Ward | To implement security lights installation in flamingo ward for road connectivity and accessibility | Security Lights Installation in Flamingo Ward completed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Flamingo | -0.308173, 36.079237 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/2024 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1710585 | 85.5 | 1710585 | 289415 | 289415 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Njonturi company ltd. Assessor remarks: It's in operation/Functional.
1607 | Infrastructure, Development and Maintenance | Security Lights Maintenance in Flamingo Ward | To implement security lights maintenance in flamingo ward for road connectivity and accessibility | Security Lights Maintenance in Flamingo Ward completed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Flamingo | -0.308173, 36.079237 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/2024 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 949100 | 94.9 | 949100 | 50900 | 50900 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Njonturi company ltd. Assessor remarks: It's in operation/Functional.
1608 | Infrastructure, Development and Maintenance | Street Maintenance Across Flamingo Ward | To implement street maintenance across flamingo ward for road connectivity and accessibility | Street Maintenance Across Flamingo Ward completed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Flamingo | -0.30825, 36.079272 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2023/2024 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 949100 | 189.8 | 949100 | 500000 | -449100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Well done. Functional.
1609 | Infrastructure, Development and Maintenance | Streetlight Maintanance In Flamingo Ward | To implement streetlight maintanance in flamingo ward for road connectivity and accessibility | Streetlight Maintanance In Flamingo Ward completed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Flamingo | -0.30825, 36.079272 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2023/2024 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 949100 | 189.8 | 949100 | 500000 | -449100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Well done. Functional.
1610 | Infrastructure, Development & Maintenance | Installation Of 10 (13M) Highmast Streetlights At Lakeview Estate (Kipsigis Road), Langalanga Estate And Racecourse Estate | To install 10 (13M) Highmast Streetlights At Lakeview Estate (Kipsigis Road), Langalanga Estate And Racecourse Estate | 10 (13M) Highmast Streetlights At Lakeview Estate (Kipsigis Road), Langalanga Estate And Racecourse Estate installed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Flamingo | -0.302653, 36.072775 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2021/22 | 2000000 | 0 | 1998500 | Equitable | N/A | 1998500 | 0 | 1420750 | 100 | 1420750 | 1998500 | -1420750 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Complete.
1611 | Infrastructure, Development and Maintenance | Installation And Maintenance of Gilgil sub location Security Lights (Mulika Mwizi) | To install And Maintenance of Gilgil sub location Security Lights (Mulika Mwizi) | And Maintenance of Gilgil sub location Security Lights (Mulika Mwizi) installed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Gilgil | -0.474518 36.290929 1884.699951171875 64.0999984741211 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 2200000 | 0 | 608852 | Equitable | N/A | 608852 | 0 | 1591148 | 100 | 1591148 | 608852 | -1591148 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yed. Viable: Yes. Contractor: M/s wellbucks construction. Assessor remarks: Functional.
1612 | Infrastructure, Development and Maintenance | Installation And Maintenance of Kikopey Sub Location Security Lights (Mulika Mwizi) | To install And Maintenance of Kikopey Sub Location Security Lights (Mulika Mwizi) | And Maintenance of Kikopey Sub Location Security Lights (Mulika Mwizi) installed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Gilgil | -0.474518 36.290929 1884.699951171875 64.0999984741211 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 1750000 | 1750000 | 1750000 | Equitable | N/A | 1750000 | 0 | 1750000 | 100 | 1750000 | 608852 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yed. Viable: Yes. Contractor: M/s wellbucks construction. Assessor remarks: Functional.
1613 | Infrastructure, Development and Maintenance | Installation of flood lights across Gilgil ward | To install flood lights across Gilgil ward | Flood lights across Gilgil ward installed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Gilgil | -0.500033 36.322175 1978.9000244140625 20.899999618530273 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3857000 | 96.4 | 3857000 | 2938906 | 143000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
1614 | Infrastructure, Development and Maintenance | Installation of high mast flood lights in Gilgil Ward | To improve security lighting through high mast floodlight installation at flood lights in Gilgil Ward | High mast floodlight installed at flood lights in Gilgil Ward | 3110504 | Other Infrastructure and Civil Works | Gilgil | Gilgil | -0.500033 36.322175 1978.9000244140625 20.899999618530273 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 3000000 | 2938906 | 2938906 | Equitable | N/A | 2938906 | 0 | 2938906 | 100 | 2938906 | 2938906 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
1615 | Infrastructure, Development and Maintenance | Cabro paving at Blankets, Free area | To implement cabro paving at blankets, free area for road connectivity and accessibility | Cabro paving at Blankets, Free area completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1616 | Infrastructure, Development and Maintenance | Construction and purchase of building materials | To construct and purchase of building materials | And purchase of building materials constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 8000000 | 8000000 | 8000000 | Equitable | N/A | 8000000 | 0 | 30510811 | 381.4 | 30510811 | 4537500 | -22510811 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1617 | Infrastructure, Development and Maintenance | Construction of Bus Park/Matatu terminus | To construct Bus Park/Matatu terminus | Bus Park/Matatu terminus constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 40000000 | 1082852.95 | 282852.95 | Equitable | N/A | 282852.95 | 0 | 30510811 | 2817.6 | 30510811 | 1082853 | -29427958.05 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1618 | Infrastructure, Development and Maintenance | Construction of Storm water Drains | To construct Storm water Drains | Storm water Drains constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2018/19 | 2018/19 | 40000000 | 30521455 | 33542910 | Equitable | N/A | 33542910 | 0 | 6978545 | 22.9 | 6978545 | 3021455 | 23542910 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1619 | Infrastructure, Development and Maintenance | Counterpart funding acquisition of Fire Engines from UK Government | To implement counterpart funding acquisition of fire engines from uk government for road connectivity and accessibility | Counterpart funding acquisition of Fire Engines from UK Government completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 11602898 | 11602898 | 11602898 | Equitable | N/A | 11602898 | 0 | 0 | 0 | 0 | 11602898 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1620 | Installation, Rehabilitation & Maintenance of Lighting Infrastructure | Installation of Segut river culvert | To install Segut river culvert | Segut river culvert installed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.408907, 36.360101 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2024/25 | 800000 | 0 | 800000 | Equitable | N/A | 800000 | 0 | 9793000 | 0 | 9793000 | 9793000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Enhanced security.
1621 | Infrastructure, Development and Maintenance | Installation of solar streetlights in the County | To improve lighting and safety through installation of solar streetlights at the County | Solar streetlights installed at the County | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 50000000 | 10900700 | 11515780 | Equitable | N/A | 11515780 | 0 | 9084220 | 83.3 | 9084220 | 11515780 | 1816480 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
1622 | Infrastructure, Development and Maintenance | Installation of streetlights along the highway in the County | To improve lighting and safety through installation of solar streetlights at the highway in the County | Solar streetlights installed at the highway in the County | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 40000000 | 40000000 | 5811000 | Equitable | N/A | 5811000 | 0 | 34189000 | 85.5 | 34189000 | 5811000 | 5811000 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
1623 | Infrastructure, Development and Maintenance | Installation of streetlights in Royal Estate area in Eburru Mbaruk Ward | To improve lighting and safety through installation of solar streetlights at Royal Estate area in Eburru Mbaruk Ward | Solar streetlights installed at Royal Estate area in Eburru Mbaruk Ward | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 1590100 | 1590100 | 1590100 | Equitable | N/A | 1590100 | 0 | 34189000 | 2150.1 | 34189000 | 5811000 | -32598900 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
1624 | Installation, Rehabilitation & Maintenance of Lighting Infrastructure | Installation of streetlights | To improve lighting and safety through installation of solar streetlights at s | Solar streetlights installed at s | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.408907, 36.360101 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2024/25 | 18000000 | 33000000 | 3043031 | Equitable | N/A | 3043031 | 0 | 1755670 | 5.3 | 1755670 | 1755670 | 31244330 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Enhanced security.
1625 | Installation, Rehabilitation & Maintenance of Lighting Infrastructure | Maintenance of streetlights | To implement maintenance of streetlights for road connectivity and accessibility | Maintenance of streetlights completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.350801, 36.219177 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 24/25 | 40000000 | 50000000 | 20000000 | Equitable | N/A | 20000000 | 0 | 1755670 | 3.5 | 1755670 | 5000000 | 48244330 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes, value. Contractor: Not indcated. Assessor remarks: Works welk.
1626 | Infrastructure, Development and Maintenance | Proposed construction and installation of Steel Pipes Culverts (AMCO) in different areas in Nakuru County:- | To undertake the proposed construction and installation of Steel Pipes Culverts (AMCO) in different areas in Nakuru County:- | Proposed construction and installation of Steel Pipes Culverts (AMCO) in different areas in Nakuru County:- implemented | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 750000 | 18204565.4 | 18204565.4 | Equitable | N/A | 18204565.4 | 0 | 18204565 | 100 | 18204565 | 0 | 0.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1627 | Infrastructure, Development and Maintenance | Proposed Construction of Drainage System at Jewatho (Phase II) and Njoro Girls Access Road in Njoro Ward Njoro Sub-County | To undertake the proposed Construction of Drainage System at Jewatho (Phase II) and Njoro Girls Access Road in Njoro Ward Njoro Sub-County | Proposed Construction of Drainage System at Jewatho (Phase II) and Njoro Girls Access Road in Njoro Ward Njoro Sub-County implemented | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 13123400 | 13123400 | 13123400 | Equitable | N/A | 13123400 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1628 | Infrastructure, Development and Maintenance | Proposed faultline fill at Kapkures access roads in Kapkures ward, Nakuru west sub-county | To undertake the proposed faultline fill at Kapkures access roads in Kapkures ward, Nakuru west sub-county | Proposed faultline fill at Kapkures access roads in Kapkures ward, Nakuru west sub-county implemented | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 11602900 | 11602900 | 11602900 | Equitable | N/A | 11602900 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1629 | Infrastructure, Development and Maintenance | Proposed Rehabilitation of Molo Bus Park and Rehabilitation of Molo Town Access Road in Molo Ward and Routine Maintenance and Spot Improvement of Comfort Feeds Saptet Centre St Joseph Primary School Road in Elburgon Ward Molo Sub County | To undertake the proposed Rehabilitation of Molo Bus Park and Rehabilitation of Molo Town Access Road in Molo Ward and Routine Maintenance and Spot Improvement of Comfort Feeds Saptet Centre St Joseph Primary School Road in Elburgon Ward Molo Sub County | Proposed Rehabilitation of Molo Bus Park and Rehabilitation of Molo Town Access Road in Molo Ward and Routine Maintenance and Spot Improvement of Comfort Feeds Saptet Centre St Joseph Primary School Road in Elburgon Ward Molo Sub County implemented | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 22872750 | 22872750 | 22872750 | Equitable | N/A | 22872750 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1630 | Infrastructure, Development and Maintenance | Proposed Rehabilitation of Shabab Stage and Main Stage in Biashara Ward Nakuru East Sub County | To undertake the proposed Rehabilitation of Shabab Stage and Main Stage in Biashara Ward Nakuru East Sub County | Proposed Rehabilitation of Shabab Stage and Main Stage in Biashara Ward Nakuru East Sub County implemented | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 9675500 | 9675500 | 9675500 | Equitable | N/A | 9675500 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1631 | Infrastructure, Development and Maintenance | Proposed Road and Culvert Works in Selected Roads in the Catchment Area of Malewa West Ward Gilgil Sub County | To undertake the proposed Road and Culvert Works in Selected Roads in the Catchment Area of Malewa West Ward Gilgil Sub County | Proposed Road and Culvert Works in Selected Roads in the Catchment Area of Malewa West Ward Gilgil Sub County implemented | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 3600623.76 | 3600623.76 | 3600623.76 | Equitable | N/A | 3600623.76 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1632 | Infrastructure, Development and Maintenance | Proposed sectional construction and completion of Fire Brigade station Lakeview ward in Naivasha Sub county | To undertake the proposed sectional construction and completion of Fire Brigade station Lakeview ward in Naivasha Sub county | Proposed sectional construction and completion of Fire Brigade station Lakeview ward in Naivasha Sub county implemented | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 6029900 | 492788.4 | 492788.4 | Equitable | N/A | 492788.4 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1633 | Infrastructure, Development and Maintenance | Purchase of building materials | To procure building materials | Building materials procured | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 15000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1634 | Infrastructure, Development and Maintenance | Rehabilitation of drainages | To rehabilitate drainages to restore functionality | Drainages rehabilitated | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | N/A | 15000000 | 12224715 | 12224715 | Equitable | N/A | 12224715 | 0 | 4414833 | 36.1 | 4414833 | 85167 | 7809882 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
1635 | Infrastructure, Development & Maintenance | Rehabilitation of streetlights across the County | To rehabilitate streetlights across the County to restore functionality | Streetlights across the County rehabilitated | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 6083300 | 6083300 | 5583300 | Equitable | N/A | 5583300 | 0 | 5568840 | 91.5 | 5568840 | 6083300 | 514460 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1636 | Infrastructure, Development and Maintenance | Rehabilitation of streetlights | To rehabilitate streetlights to restore functionality | Streetlights rehabilitated | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 20000000 | 1755670 | 1755670 | Equitable | N/A | 1755670 | 0 | 1755670 | 100 | 1755670 | 1755670 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1637 | Infrastructure, Development and Maintenance | Replacement of conventional light with LED Lights/Solar Lights | To implement replacement of conventional light with led lights/solar lights for road connectivity and accessibility | Replacement of conventional light with LED Lights/Solar Lights completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 15000000 | 852509.2 | 852509.2 | Equitable | N/A | 852509.2 | 0 | 1643700 | 192.8 | 1643700 | 1643700 | -791190.8 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1638 | Infrastructure, Development and Maintenance | Road safety Programme (Road Marking and Construction of NMT facilities) | To implement road safety programme (road marking and construction of nmt facilities) for road connectivity and accessibility | Road safety Programme (Road Marking and Construction of NMT facilities) completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 10000000 | 0 | 1328552.75 | Equitable | N/A | 1328552.75 | 0 | 3671447 | 100 | 3671447 | 1328553 | -3671447 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
1639 | Infrastructure, Development and Maintenance | Construction of drainage system at Memorial Road at Mt. View | To construct drainage system at Memorial Road at Mt. View | Drainage system at Memorial Road at Mt. View constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Hells Gate | -0.778197, 36.453312 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 1815785 | 60.5 | 1815785 | 139627 | 1184215 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road was being swipped away by floods but since the construction the problem is no longer seen. Few meters needs the drainage on the same road.
1640 | Infrastructure, Development and Maintenance | Construction of drainage system at Sanctuary roads | To construct drainage system at Sanctuary roads | Drainage system at Sanctuary roads constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Hells Gate | -0.795647, 36.425499 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The drainage is helping the area road not to be carried away by flood's.
1641 | Infrastructure, Development and Maintenance | Construction Of Motorbike Sheds Within Hells Gate Ward | To construct Motorbike Sheds Within Hells Gate Ward | Motorbike Sheds Within Hells Gate Ward constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Hells Gate | -0.776517, 36.428084 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999150 | 100 | 1999150 | 850 | 850 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project meet the needs of our motorbike riders and community.
1642 | Infrastructure, Development and Maintenance | Installation of 10 Highmast streetlights at Hells Gate Ward | To install 10 Highmast streetlights at Hells Gate Ward | 10 Highmast streetlights at Hells Gate Ward installed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Hells Gate | -0.784627, 36.439987 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3402845 | 85.1 | 3402845 | 258190 | 597155 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The light is efficient in the installed areas.
1643 | Infrastructure, Development & Maintenance | Installation of culverts in Hellsgate ward | To improve drainage and road access through culvert installation at in Hellsgate ward | Culverts installed at in Hellsgate ward | 3110504 | Other Infrastructure and Civil Works | Naivasha | Hells Gate | -0.788605, 36.439233 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1238453 | 82.6 | 1238453 | 1800000 | 261547 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project costed 1,500,000.
1644 | Infrastructure, Development and Maintenance | Installation Of seven (7) High mast Street Lights at Hells Gate Ward | To install seven (7) High mast Street Lights at Hells Gate Ward | Seven (7) High mast Street Lights at Hells Gate Ward installed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Hells Gate | -0.784627, 36.439987 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 3000000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2241810 | 89.7 | 2241810 | 258190 | 258190 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The light is efficient in the installed areas.
1645 | Infrastructure, Development & Maintenance | Installation of solar street lights at Mirera railway, Mirera air strip, Nyamathi and Mwiciringiri | To install solar street lights at Mirera railway, Mirera air strip, Nyamathi and Mwiciringiri | Solar street lights at Mirera railway, Mirera air strip, Nyamathi and Mwiciringiri installed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Hells Gate | -0.794645, 36.425905 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1997750 | 99.9 | 1997750 | 2000000 | 2250 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The security light has really reduced insecurity cases in This areas.
1646 | Infrastructure, Development & Maintenance | Installation Of Solar Streetlights At Mirera Railways, Mirera Airstrip, Nyamathi And Mwiciringiri | To improve lighting and safety through installation of solar streetlights at Mirera Railways, Mirera Airstrip, Nyamathi And Mwiciringiri | Solar streetlights installed at Mirera Railways, Mirera Airstrip, Nyamathi And Mwiciringiri | 3110504 | Other Infrastructure and Civil Works | Naivasha | Hells Gate | -0.794645, 36.425905 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1997750 | 99.9 | 1997750 | 2000000 | 2250 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The security light has really reduced insecurity cases in This areas.
1647 | Infrastructure, Development and Maintenance | Installation Of Twenty (20) Culverts and Drainage Opening Within Hells Gate Ward | To install Twenty (20) Culverts and Drainage Opening Within Hells Gate Ward | Twenty (20) Culverts and Drainage Opening Within Hells Gate Ward installed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Hells Gate | -0.778446, 36.427112 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 1800000 | 0 | 1800000 | Equitable | N/A | 1800000 | 0 | 1238453 | 100 | 1238453 | 1800000 | -1238453 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project was done at a cost of 1,800,000.
1648 | Infrastructure, Development and Maintenance | Maintenance of floodlights across the Ward | To implement maintenance of floodlights across the ward for road connectivity and accessibility | Maintenance of floodlights across the Ward completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Hells Gate | -0.779978, 36.437974 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 991800 | 141.7 | 991800 | 97990 | -291800 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The floodlights are functioning well improving the area's security.
1649 | Infrastructure, Development and Maintenance | Maintenance Of Streetlights Within Hells Gate Ward | To implement maintenance of streetlights within hells gate ward for road connectivity and accessibility | Maintenance Of Streetlights Within Hells Gate Ward completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Hells Gate | -0.798693, 36.422858 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 589790 | 1089790 | 1089790 | Equitable | N/A | 1089790 | 0 | 991800 | 91 | 991800 | 97990 | 97990 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project was done at a cost of 1,089,790.
1650 | Infrastructure, Development and Maintenance | Installation of floodlights across the Ward | To install floodlights across the Ward | Floodlights across the Ward installed | 3110504 | Other Infrastructure and Civil Works | Bahati | Kabatini | -0.232106, 36.156236 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2024 | 753853 | 750000 | 750000 | Equitable | N/A | 750000 | 0 | 742900 | 99.1 | 742900 | 750000 | 7100 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ceanmi merchants limited. Assessor remarks: Only one head light is working.
1651 | Infrastructure, Development and Maintenance | Installation Of Street Lights at Mwaki Mugi | To install Street Lights at Mwaki Mugi | Street Lights at Mwaki Mugi installed | 3110504 | Other Infrastructure and Civil Works | Bahati | Kabatini | -0.227422 36.114824 1950 52.400001525878906 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1976400 | 98.8 | 1976400 | 23600 | 23600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
1652 | Infrastructure, Development and Maintenance | Installation Of Street Lights at Wendo Sub-Location | To install Street Lights at Wendo Sub-Location | Street Lights at Wendo Sub-Location installed | 3110504 | Other Infrastructure and Civil Works | Bahati | Kabatini | -0.188571, 36.170602 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1200000 | 100 | 1200000 | 23600 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: M/s similion ventures limited. Assessor remarks: It needs adjustable /setting of the lights there all facing downwards.
1653 | Infrastructure, Development and Maintenance | Installation of streetlighting at Wendo, Mwaki Mugi and Kabatini | To improve lighting and safety through installation of solar streetlights at ing at Wendo, Mwaki Mugi and Kabatini | Solar streetlights installed at ing at Wendo, Mwaki Mugi and Kabatini | 3110504 | Other Infrastructure and Civil Works | Bahati | Kabatini | -0.227422 36.114824 1950 52.400001525878906 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 1976400 | 65.9 | 1976400 | 23600 | 1023600 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
1654 | Infrastructure, Development and Maintenance | Installation Of Streetlights Across Kabatini Ward | To improve lighting and safety through installation of solar streetlights at Across Kabatini Ward | Solar streetlights installed at Across Kabatini Ward | 3110504 | Other Infrastructure and Civil Works | Bahati | Kabatini | -0.230574, 36.163072 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2024 | 1500000 | 0 | 1500000 | Equitable | N/A | 1500000 | 0 | 742900 | 100 | 742900 | 1500000 | -742900 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational, sensor should be checked.
1655 | Infrastructure, Development and Maintenance | Maintenance and repair of Streetlights in Kabatini ward | To implement maintenance and repair of streetlights in kabatini ward for road connectivity and accessibility | Maintenance and repair of Streetlights in Kabatini ward completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Kabatini | -0.244935, 36.143518 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2024 | 1000000 | 997200 | 997200 | Equitable | N/A | 997200 | 0 | 997200 | 100 | 997200 | 997200 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ms/ similion ventures ltd. Assessor remarks: Operational.
1656 | Infrastructure, Development and Maintenance | Rehabilitation and maintenance of streetlights within the ward | To rehabilitate maintenance of streetlights within the ward to restore functionality | Maintenance of streetlights within the ward rehabilitated | 3110504 | Other Infrastructure and Civil Works | Bahati | Kabatini | -0.22345 36.15032 1945.0999755859375 10.427000045776367 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 997200 | 99.7 | 997200 | 997200 | 2800 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Vannetta contractors limited. Assessor remarks: Operational but requires alignment.
1657 | Infrastructure, Development and Maintenance | Additional Fund To Installation Of Streetlights In Kabazi Ward | To implement additional fund to installation of streetlights in kabazi ward for road connectivity and accessibility | Additional Fund To Installation Of Streetlights In Kabazi Ward completed | 3110504 | Other Infrastructure and Civil Works | Subukia | Kabazi | -0.077859, 36.171008 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2024/25 | 100000 | 100000 | 100000 | Equitable | N/A | 100000 | 0 | 1497715 | 1497.7 | 1497715 | 100000 | -1397715 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Requires maintenance.
1658 | Additional Fund To Streetlights Maintenance In Kabazi Ward | Additional Fund To Streetlights Maintenance In Kabazi Ward | To implement additional fund to streetlights maintenance in kabazi ward for road connectivity and accessibility | Additional Fund To Streetlights Maintenance In Kabazi Ward completed | 3110504 | Other Infrastructure and Civil Works | Subukia | Kabazi | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 82646 | 82646 | 82646 | Equitable | N/A | 82646 | 0 | 117354 | 142 | 117354 | 82646 | -34708 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
1659 | Infrastructure, Development and Maintenance | Construction Of Boda-Boda Shed and Installation of High Mast Light at Endao Trading Centre | To construct Boda-Boda Shed and Installation of High Mast Light at Endao Trading Centre | Boda-Boda Shed and Installation of High Mast Light at Endao Trading Centre constructed | 3110504 | Other Infrastructure and Civil Works | Subukia | Kabazi | -0.06491, 36.13243 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1494000 | 99.6 | 1494000 | 6000 | 6000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not identified. Assessor remarks: Bodaboda shed floor to be upgraded.
1660 | Infrastructure, Development and Maintenance | Installation of highmast streelights | To improve security lighting through high mast floodlight installation at streelights | High mast floodlight installed at streelights | 3110504 | Other Infrastructure and Civil Works | Subukia | Kabazi | -0.077942 36.170989 0 12.281660079956055 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1073520 | 89.5 | 1073520 | 126480 | 126480 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Requires renovation.
1661 | Infrastructure, Development and Maintenance | Installation Of Streetlights In Kabazi Ward | To improve lighting and safety through installation of solar streetlights at Kabazi Ward | Solar streetlights installed at Kabazi Ward | 3110504 | Other Infrastructure and Civil Works | Subukia | Kabazi | -0.077859, 36.171008 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2024/25 | 100000 | 0 | 100000 | Equitable | N/A | 100000 | 0 | 1073520 | 100 | 1073520 | 100000 | -1073520 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Requires maintenance.
1662 | Infrastructure, Development and Maintenance | Streetlight Maintenance In Kabazi Ward | To implement streetlight maintenance in kabazi ward for road connectivity and accessibility | Streetlight Maintenance In Kabazi Ward completed | 3110504 | Other Infrastructure and Civil Works | Subukia | Kabazi | -0.077907 36.170967 2259.4 8.800000190734863 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 117354 | 117354 | 117354 | Equitable | N/A | 117354 | 0 | 117354 | 100 | 117354 | 117354 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Requires floor renovation.
1663 | Construction of boda boda shades | Construction of boda boda shades | To construct boda boda shades | Boda boda shades constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Kamara | -0.169028, 35.703205 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | U2019/20 | 1000000 | 981402 | 981402 | Equitable | N/A | 981402 | 0 | 998600 | 101.8 | 998600 | 981402 | -17198 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Unknown. Assessor remarks: Seats vandalised, needs re-painting.
1664 | Infrastructure, Development and Maintenance | Installation of High mast street lights in Kamara Ward | To improve security lighting through high mast floodlight installation at street lights in Kamara Ward | High mast floodlight installed at street lights in Kamara Ward | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Kamara | -0.170525, 35.704932 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1995000 | 133 | 1995000 | 1500000 | -495000 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: Yes if it was repaired and maintained. Contractor: Unknown. Assessor remarks: The street lights needs to repaired and maintained.
1665 | Infrastructure, Development and Maintenance | Installation of street lights and high mast | To install street lights and high mast | Street lights and high mast installed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Kamara | -0.092542, 35.684012 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2021/22 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1995000 | 199.5 | 1995000 | 1500000 | -995000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Partially. Viable: Yes if implemented. Contractor: Not indicated. Assessor remarks: 3 bulbs are not operational.
1666 | Infrastructure, Development and Maintenance | Construction of drainage at Ingobor Sub location | To construct drainage at Ingobor Sub location | Drainage at Ingobor Sub location constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kapkures | -0.306306, 36.018533 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2024/25 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 550895 | 27.5 | 550895 | 550895 | 1449105 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and draining water well. Assessor remarks: Well done and functional.
1667 | Infrastructure, Development and Maintenance | Installation Of High Mast Lights across Kapkures Ward | To improve security lighting through high mast floodlight installation at Lights across Kapkures Ward | High mast floodlight installed at Lights across Kapkures Ward | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kapkures | -0.288288, 36.000456 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 2800000 | 5600000 | 8161670 | Equitable | N/A | 8161670 | 0 | 2234025 | 39.9 | 2234025 | 2680835 | 3365975 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Security has improved. Assessor remarks: Done and working.
1668 | Infrastructure, Development and Maintenance | Installation of high mast security lights at Mogoon Sub location, Ingobor Sub location and Lalwet Sub location | To improve security lighting through high mast floodlight installation at security lights at Mogoon Sub location, Ingobor Sub location and Lalwet Sub location | High mast floodlight installed at security lights at Mogoon Sub location, Ingobor Sub location and Lalwet Sub location | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kapkures | -0.288288 36.000456 0 2000 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 4400000 | 4400000 | 4400000 | Equitable | N/A | 4400000 | 0 | 2340800 | 53.2 | 2340800 | 2340800 | 2059200 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Improved security. Assessor remarks: Well implemented and functional.
1669 | Infrastructure, Development & Maintenance | Installation Of Mulika Mwizi At Ingobor Upper | To install Mulika Mwizi At Ingobor Upper | Mulika Mwizi At Ingobor Upper installed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kapkures | -0.313727, 36.014906 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 880000 | 880000 | Equitable | N/A | 880000 | 0 | 880000 | 100 | 880000 | 880000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: well installed and in use.
1670 | Infrastructure, Development & Maintenance | Installation Of Streetlights 180 Watts At Ingobor And Laluet | To improve lighting and safety through installation of solar streetlights at 180 Watts At Ingobor And Laluet | Solar streetlights installed at 180 Watts At Ingobor And Laluet | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kapkures | -0.306306, 36.000514 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 2340800 | 2340800 | Equitable | N/A | 2340800 | 0 | 2340800 | 100 | 2340800 | 2340800 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: No. Viable: Viable but vandalism has stalled it. Assessor remarks: Well done, but solar panels stolen.
1671 | Infrastructure, Development and Maintenance | Rehabilitation and Maintenance of security lights at Kapkures Ward | To rehabilitate Maintenance of security lights at Kapkures Ward to restore functionality | Maintenance of security lights at Kapkures Ward rehabilitated | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kapkures | -0.288288 36.000456 0 2000 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 612844 | 612844 | 612844 | Equitable | N/A | 612844 | 0 | 2400000 | 391.6 | 2400000 | 2680835 | -1787156 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Improved security. Assessor remarks: Well implemented and functional.
1672 | Infrastructure, Development and Maintenance | Construction of Boda Boda sheds across the Ward | To construct Boda Boda sheds across the Ward | Boda Boda sheds across the Ward constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kaptembwo | -0.302048, 36.061657 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1346531 | 89.8 | 1346531 | 153470 | 153469 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes,it has helped the bodaboda riders. Contractor: M/SGAJAS DEVELOPMENT SOLUTIONS. Assessor remarks: Complete but need renovation.
1673 | Infrastructure, Development and Maintenance | Construction of Drainage System in Jasho-Kwa mrembo roads, Jubilee Academy, Hony cup-Eastern estate, Rhonda hospital-Rad 6, Chiefs Office-weavers | To construct Drainage System in Jasho-Kwa mrembo roads, Jubilee Academy, Hony cup-Eastern estate, Rhonda hospital-Rad 6, Chiefs Office-weavers | Drainage System in Jasho-Kwa mrembo roads, Jubilee Academy, Hony cup-Eastern estate, Rhonda hospital-Rad 6, Chiefs Office-weavers constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kaptembwo | -0.302357, 36.059036 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 9000000 | 8588750 | 8588750 | Equitable | N/A | 8588750 | 0 | 8585942 | 100 | 8585942 | 2808 | 2808 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes,it was met. Viable: It's a viable project, it met the needs of the residents. Contractor: M/S NAKULINK SERVICES. Assessor remarks: Complete.
1674 | Infrastructure, Development and Maintenance | Installation of Street Lights at Kaptembwo Ward (Lukamba, Kwa Chief, Pistis, Kwa Semweno, Pondamali, Bangi road, Kipanga, Senere, Blescourse, Check Point, Plot 10-Betheli, Kishimo, Uthabete, Church of God, Osieko) | To install Street Lights at Kaptembwo Ward (Lukamba, Kwa Chief, Pistis, Kwa Semweno, Pondamali, Bangi road, Kipanga, Senere, Blescourse, Check Point, Plot 10-Betheli, Kishimo, Uthabete, Church of God, Osieko) | Street Lights at Kaptembwo Ward (Lukamba, Kwa Chief, Pistis, Kwa Semweno, Pondamali, Bangi road, Kipanga, Senere, Blescourse, Check Point, Plot 10-Betheli, Kishimo, Uthabete, Church of God, Osieko) installed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kaptembwo | -0.305432, 36.059714 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2023/24 | 5000000 | 4850395 | 4850395 | Equitable | N/A | 4850395 | 0 | 4850395 | 100 | 4850395 | 4850395 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes, it met the needs of the residents. Contractor: U115. Assessor remarks: Not working, needs maintenance.
1675 | Infrastructure, Development and Maintenance | Installation of Street lights in Kaptembwo Ward | To install Street lights in Kaptembwo Ward | Street lights in Kaptembwo Ward installed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kaptembwo | -0.307582 36.04956 1787.0712703487839 48.900001525878906 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | N/A | 4629240 | 4629240 | 4629240 | Equitable | N/A | 4629240 | 0 | 4629240 | 100 | 4629240 | 4629240 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/S TERIBELK TRADING LIMITED. Assessor remarks: In good condition.
1676 | Infrastructure, Development and Maintenance | Installation of streetlights across Kaptembwo Ward | To improve lighting and safety through installation of solar streetlights at across Kaptembwo Ward | Solar streetlights installed at across Kaptembwo Ward | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kaptembwo | -0.307582 36.04956 1787.0712703487839 48.900001525878906 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 2778520 | 100 | 2778520 | 2778520 | -2778520 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/S TERIBELK TRADING LIMITED. Assessor remarks: In good condition.
1677 | Infrastructure, Development and Maintenance | Installation Of Streetlights In Kaptembwo Ward | To improve lighting and safety through installation of solar streetlights at Kaptembwo Ward | Solar streetlights installed at Kaptembwo Ward | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kaptembwo | -0.307582 36.04956 1787.0712703487839 48.900001525878906 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2019/20 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 2778520 | 277.9 | 2778520 | 2778520 | -1778520 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/S TERIBELK TRADING LIMITED. Assessor remarks: In good condition.
1678 | Infrastructure, Development and Maintenance | Maintanance Of Streetlights In Kaptembwo Ward | To implement maintanance of streetlights in kaptembwo ward for road connectivity and accessibility | Maintanance Of Streetlights In Kaptembwo Ward completed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kaptembwo | -0.302372, 36.06287 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2024/25 | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 1787300 | 100 | 1787300 | 1000000 | -1787300 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes,it has curbed insecurity issues. Contractor: U115. Assessor remarks: In good condition.
1679 | Infrastructure, Development and Maintenance | Maintenance Of Street Lights Across Kaptembwo Ward | To implement maintenance of street lights across kaptembwo ward for road connectivity and accessibility | Maintenance Of Street Lights Across Kaptembwo Ward completed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kaptembwo | -0.302648 36.04481 1806.8267321810167 3.9230000972747803 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1787300 | 89.4 | 1787300 | 212700 | 212700 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Nakuru County. Assessor remarks: Viable.
1680 | Infrastructure, Development and Maintenance | Maintenance of Street lights in Kaptembwo Ward | To implement maintenance of street lights in kaptembwo ward for road connectivity and accessibility | Maintenance of Street lights in Kaptembwo Ward completed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kaptembwo | -0.302372, 36.06287 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2024/25 | 3000000 | 0 | 2998700 | Equitable | N/A | 2998700 | 0 | 1787300 | 100 | 1787300 | 2998700 | -1787300 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes,it has curbed insecurity issues. Contractor: U115. Assessor remarks: In good condition.
1681 | Infrastructure, Development and Maintenance | Rehabilitation of drainages across Kaptembwo Ward | To rehabilitate drainages across Kaptembwo Ward to restore functionality | Drainages across Kaptembwo Ward rehabilitated | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kaptembwo | -0.298518 36.046052 1808.800048828125 64.54000091552734 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 1572762 | 1572762 | 1572762 | Equitable | N/A | 1572762 | 0 | 922599 | 58.7 | 922599 | 32451 | 650163 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: PICVERD SUPPLIES. Assessor remarks: Defective,has debris and thrush,clogged,.
1682 | Infrastructure, Development and Maintenance | Rehabilitation of streetlights across Kaptembwo Ward | To rehabilitate streetlights across Kaptembwo Ward to restore functionality | Streetlights across Kaptembwo Ward rehabilitated | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kaptembwo | -0.307582 36.04956 1787.0712703487839 48.900001525878906 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1787300 | 119.2 | 1787300 | 212700 | -287300 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/S TERIBELK TRADING LIMITED. Assessor remarks: In good condition.
1683 | Infrastructure, Development & Maintenance | Streetlighting Maintenance | To implement streetlighting maintenance for road connectivity and accessibility | Streetlighting Maintenance completed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kaptembwo | -0.302265, 36.058547 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2021/22 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: It's a viable project, it's has met the needs of the residents. Contractor: Y72. Assessor remarks: It functional.
1684 | Infrastructure, Development and Maintenance | Construction of Boda Boda sheds at Keringet, Sachangwan, Seplet,Lendwet and Soitaran | To construct Boda Boda sheds at Keringet, Sachangwan, Seplet,Lendwet and Soitaran | Boda Boda sheds at Keringet, Sachangwan, Seplet,Lendwet and Soitaran constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Keringet | -0.501285, 35.700935 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2023 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1054360 | 70.3 | 1054360 | 1500000 | 445640 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
1685 | Infrastructure, Development and Maintenance | Construction Of Bodaboda Shed At Keringet, Sachangwan, Seplet, Lendwet And Soitaran | To construct Bodaboda Shed At Keringet, Sachangwan, Seplet, Lendwet And Soitaran | Bodaboda Shed At Keringet, Sachangwan, Seplet, Lendwet And Soitaran constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Keringet | -0.501285, 35.700935 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2023 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1054360 | 70.3 | 1054360 | 1500000 | 445640 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
1686 | Infrastructure, Development & Maintenance | Construction of Sheds at Keringet Bus Park | To construct Sheds at Keringet Bus Park | Sheds at Keringet Bus Park constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Keringet | -0.427113 35.692842 2683.500244140625 57.48400115966797 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | N/A | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 1054360 | 351.5 | 1054360 | 300000 | -754360 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Not constructed.
1687 | Infrastructure, Development & Maintenance | Construction of Toilets, pit latrines at Keringet Bus Park | To construct Toilets, pit latrines at Keringet Bus Park | Toilets, pit latrines at Keringet Bus Park constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Keringet | -0.427113 35.692842 2683.500244140625 57.48400115966797 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | N/A | 551799 | 551799 | 551799 | Equitable | N/A | 551799 | 0 | 422214 | 76.5 | 422214 | 551799 | 129585 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Not constructed.
1688 | Infrastructure, Development and Maintenance | Culverting of Milimet sub location | To implement culverting of milimet sub location for road connectivity and accessibility | Culverting of Milimet sub location completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Keringet | -0.44031, 35.713578 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2025 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Ongoing.
1689 | Infrastructure, Development and Maintenance | Installation Of Culverts And Construction Of Kapkwen Mombasa Foot Bridge, Construction Of Bodaboda Shed At Keringet,Sachangwan, | To improve drainage and road access through culvert installation at And Construction Of Kapkwen Mombasa Foot Bridge, Construction Of Bodaboda Shed At Keringet,Sachangwan, | Culverts installed at And Construction Of Kapkwen Mombasa Foot Bridge, Construction Of Bodaboda Shed At Keringet,Sachangwan, | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Keringet | -0.424835 35.690778 2699.500244140625 92.9000015258789 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1229981 | 82 | 1229981 | 0 | 270019 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In use.
1690 | Infrastructure, Development and Maintenance | Installation of floodlights at Keringet-Bararget road and Mwangate Junction | To install floodlights at Keringet-Bararget road and Mwangate Junction | Floodlights at Keringet-Bararget road and Mwangate Junction installed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Keringet | -0.425627, 35.694027 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2025 | 900000 | 0 | 900000 | Equitable | N/A | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not conected.
1691 | Infrastructure, Development and Maintenance | Rehabilitation Of Culverts Kamanyoa Milimet Road | To rehabilitate Culverts Kamanyoa Milimet Road to restore functionality | Culverts Kamanyoa Milimet Road rehabilitated | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Keringet | -0.46407, 35.697232 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 300000 | 0 | 300000 | Equitable | N/A | 300000 | 0 | 0 | 0 | 0 | 300000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not yet started. Viable: Not yes started. Assessor remarks: Yet to start.
1692 | Infrastructure, Development and Maintenance | Construction Of Drainage System at Kiamaina Sub-location | To construct Drainage System at Kiamaina Sub-location | Drainage System at Kiamaina Sub-location constructed | 3110504 | Other Infrastructure and Civil Works | Bahati | Kiamaina | -0.268282 36.11517 1863.800048828125 4.699999809265137 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 9453802 | 100 | 9453802 | 1000000 | -9453802 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires routine maintenance.
1693 | Infrastructure, Development and Maintenance | Construction Of Drainage System at Rurii Sub-Location | To construct Drainage System at Rurii Sub-Location | Drainage System at Rurii Sub-Location constructed | 3110504 | Other Infrastructure and Civil Works | Bahati | Kiamaina | -0.268282 36.11517 1863.800048828125 4.699999809265137 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 2700000 | 0 | 2700000 | Equitable | N/A | 2700000 | 0 | 9453802 | 100 | 9453802 | 2700000 | -9453802 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires routine maintenance.
1694 | Infrastructure, Development and Maintenance | Construction Of Drainage System at Workers Sub-Location | To construct Drainage System at Workers Sub-Location | Drainage System at Workers Sub-Location constructed | 3110504 | Other Infrastructure and Civil Works | Bahati | Kiamaina | -0.268282 36.11517 1863.800048828125 4.699999809265137 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 2600000 | 0 | 2600000 | Equitable | N/A | 2600000 | 0 | 9453802 | 100 | 9453802 | 2600000 | -9453802 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires routine maintenance.
1695 | Infrastructure, Development and Maintenance | Construction Of Drainages In Kiamaina Ward | To construct Drainages In Kiamaina Ward | Drainages In Kiamaina Ward constructed | 3110504 | Other Infrastructure and Civil Works | Bahati | Kiamaina | -0.2675, 36.114467 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 10465732 | 9899630 | 9899630 | Equitable | N/A | 9899630 | 0 | 9453802 | 95.5 | 9453802 | 445828 | 445828 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: It's needs clean up.
1696 | Infrastructure, Development and Maintenance | Installation Of Culverts at Munyaka Stream, Good Shepherd and Haigwa Area Gituamba Location | To improve drainage and road access through culvert installation at Munyaka Stream, Good Shepherd and Haigwa Area Gituamba Location | Culverts installed at Munyaka Stream, Good Shepherd and Haigwa Area Gituamba Location | 3110504 | Other Infrastructure and Civil Works | Bahati | Kiamaina | -0.231536 36.116876 1940.9000244140625 19.493999481201172 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 816793 | 816793 | 816793 | Equitable | N/A | 816793 | 0 | 783905 | 96 | 783905 | 32888 | 32888 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Not yet done. Assessor remarks: The contractor is yet to begin the works.
1697 | Infrastructure, Development & Maintenance | Installation of flood lights at Workers | To install flood lights at Workers | Flood lights at Workers installed | 3110504 | Other Infrastructure and Civil Works | Bahati | Kiamaina | -0.265858, 36.10787 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 1999950 | 1999950 | Equitable | N/A | 1999950 | 0 | 1999950 | 100 | 1999950 | 1999950 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires maintenance.
1698 | Infrastructure, Development and Maintenance | Installation of Highmast Streetlights In Kiamaina Ward | To improve security lighting through high mast floodlight installation at Streetlights In Kiamaina Ward | High mast floodlight installed at Streetlights In Kiamaina Ward | 3110504 | Other Infrastructure and Civil Works | Bahati | Kiamaina | -0.231536 36.116876 1940.9000244140625 19.493999481201172 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 5000000 | 3613850 | 3613850 | Equitable | N/A | 3613850 | 0 | 3613850 | 100 | 3613850 | 3613850 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Not yet done. Assessor remarks: The contractor is yet to begin the works.
1699 | Infrastructure, Development & Maintenance | Installation of Solar flood lights in Gituamba | To install Solar flood lights in Gituamba | Solar flood lights in Gituamba installed | 3110504 | Other Infrastructure and Civil Works | Bahati | Kiamaina | -0.237962 36.119598 1921.699951171875 20.100000381469727 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2500000 | 2499950 | 2499950 | Equitable | N/A | 2499950 | 0 | 2499950 | 100 | 2499950 | 2499950 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires maintenance.
1700 | Infrastructure, Development and Maintenance | Installation Of Streetlight at Gituamba Sub-Location | To improve lighting and safety through installation of solar streetlights at Gituamba Sub-Location | Solar streetlights installed at Gituamba Sub-Location | 3110504 | Other Infrastructure and Civil Works | Bahati | Kiamaina | -0.259021 36.134371 1892.800048828125 92.9000015258789 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1149621 | 95.8 | 1149621 | 50379 | 50379 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes for security purposes. Assessor remarks: Some lights are off requires replacement.
1701 | Infrastructure, Development and Maintenance | Installation Of Streetlight at Kiamaina Sub-Location | To improve lighting and safety through installation of solar streetlights at Kiamaina Sub-Location | Solar streetlights installed at Kiamaina Sub-Location | 3110504 | Other Infrastructure and Civil Works | Bahati | Kiamaina | -0.259021 36.134371 1892.800048828125 92.9000015258789 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1170025 | 97.5 | 1170025 | 29975 | 29975 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes for security purposes. Assessor remarks: Some lights are off requires replacement.
1702 | Infrastructure, Development and Maintenance | Installation Of Streetlight at Rurii Sub-Location | To improve lighting and safety through installation of solar streetlights at Rurii Sub-Location | Solar streetlights installed at Rurii Sub-Location | 3110504 | Other Infrastructure and Civil Works | Bahati | Kiamaina | -0.231698 36.116888 1940.699951171875 26.440000534057617 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 2400000 | 0 | 2400000 | Equitable | N/A | 2400000 | 0 | 1170025 | 100 | 1170025 | 2400000 | -1170025 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Not yet done. Assessor remarks: The project is yet to start.
1703 | Infrastructure, Development and Maintenance | Installation Of Streetlight at Workers Sub-Location | To improve lighting and safety through installation of solar streetlights at Workers Sub-Location | Solar streetlights installed at Workers Sub-Location | 3110504 | Other Infrastructure and Civil Works | Bahati | Kiamaina | -0.265068 36.120542 1870.699951171875 45.599998474121094 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 2400000 | 0 | 2400000 | Equitable | N/A | 2400000 | 0 | 1170025 | 100 | 1170025 | 2400000 | -1170025 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires maintenance.
1704 | Infrastructure, Development and Maintenance | Installation of Streetlights at VOK, Kiriko and Crater Villages | To improve lighting and safety through installation of solar streetlights at VOK, Kiriko and Crater Villages | Solar streetlights installed at VOK, Kiriko and Crater Villages | 3110504 | Other Infrastructure and Civil Works | Bahati | Kiamaina | -0.259021 36.134371 1892.800048828125 92.9000015258789 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 1200000 | 0 | 1200000 | Equitable | N/A | 1200000 | 0 | 1170025 | 100 | 1170025 | 1200000 | -1170025 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes for security purposes. Assessor remarks: Some lights are off requires replacement.
1705 | Infrastructure, Development and Maintenance | Labour based drainage works of Menengai Crater Dispensary access road | To implement labour based drainage works of menengai crater dispensary access road for road connectivity and accessibility | Labour based drainage works of Menengai Crater Dispensary access road completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Kiamaina | -0.246042 36.117933 1898.300048828125 7 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1899024 | 345134.65 | 345134.65 | Equitable | N/A | 345134.65 | 0 | 345135 | 100 | 345135 | 345135 | -0.35 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Routine maintenance.
1706 | Labour based drainage works of poshomill - Bee Valley access road | Labour based drainage works of poshomill - Bee Valley access road | To implement labour based drainage works of poshomill - bee valley access road for road connectivity and accessibility | Labour based drainage works of poshomill - Bee Valley access road completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Kiamaina | -0.242746, 36.113191 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1919341 | 96 | 1919341 | 2000000 | 80659 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Project requires routine maintenance.
1707 | Infrastructure, Development and Maintenance | Maintenance of streetlights across the ward | To implement maintenance of streetlights across the ward for road connectivity and accessibility | Maintenance of streetlights across the ward completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Kiamaina | -0.265068 36.120542 1870.699951171875 45.599998474121094 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 700000 | 0 | 700000 | Equitable | N/A | 700000 | 0 | 643250 | 100 | 643250 | 700000 | -643250 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires maintenance.
1708 | Infrastructure, Development and Maintenance | Maintenance Of Streetlights at Kiamaina Ward | To implement maintenance of streetlights at kiamaina ward for road connectivity and accessibility | Maintenance Of Streetlights at Kiamaina Ward completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Kiamaina | -0.259021 36.134371 1892.800048828125 92.9000015258789 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 2000000 | 0 | 1356750 | Equitable | N/A | 1356750 | 0 | 643250 | 100 | 643250 | 1356750 | -643250 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes for security purposes. Assessor remarks: Some lights are off requires replacement.
1709 | Infrastructure, Development and Maintenance | Purchase of culverts for emergency drainage mitigations in the Ward | To procure culverts for emergency drainage mitigations in the Ward | Culverts for emergency drainage mitigations in the Ward procured | 3110504 | Other Infrastructure and Civil Works | Bahati | Kiamaina | -0.231627 36.116888 1940.699951171875 39.599998474121094 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 752037 | 752037 | 752037 | Equitable | N/A | 752037 | 0 | 750000 | 99.7 | 750000 | 752037 | 2037 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Not yet done. Assessor remarks: The project is yet to start.
1710 | Infrastructure, Development and Maintenance | Rehabilitation of streetlights across Kiamaina Ward | To rehabilitate streetlights across Kiamaina Ward to restore functionality | Streetlights across Kiamaina Ward rehabilitated | 3110504 | Other Infrastructure and Civil Works | Bahati | Kiamaina | -0.231696, 36.116885 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 643250 | 32.2 | 643250 | 1356750 | 1356750 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes after completion. Viable: Yes after completion. Assessor remarks: The contractor is on site.
1711 | Infrastructure, Development and Maintenance | Construction Of 3 Boda-boda Shed in Ndeffo, Store Mbili and Kihingo | To construct 3 Boda-boda Shed in Ndeffo, Store Mbili and Kihingo | 3 Boda-boda Shed in Ndeffo, Store Mbili and Kihingo constructed | 3110504 | Other Infrastructure and Civil Works | Njoro | Kihingo | -0.433992, 35.972122 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2024 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 990780 | 99.1 | 990780 | 9220 | 9220 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: It's in good state.
1712 | Infrastructure, Development & Maintenance | Floodlight mlika mwizi installation | To implement floodlight mlika mwizi installation for road connectivity and accessibility | Floodlight mlika mwizi installation completed | 3110504 | Other Infrastructure and Civil Works | Njoro | Kihingo | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 922700 | 92.3 | 922700 | 0 | 77300 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1713 | Infrastructure, Development and Maintenance | Installation of two high mast security lights at Muhumoini Centre and Lusiru Centre | To install two high mast security lights at Muhumoini Centre and Lusiru Centre | Two high mast security lights at Muhumoini Centre and Lusiru Centre installed | 3110504 | Other Infrastructure and Civil Works | Njoro | Kihingo | -0.458447, 35.980643 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2023 | 1400000 | 1400000 | 1400000 | Equitable | N/A | 1400000 | 0 | 1198767 | 85.6 | 1198767 | 0 | 201233 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
1714 | Infrastructure, Development and Maintenance | Construction of Kipsogon-Kombich box culvert | To construct Kipsogon-Kombich box culvert | Kipsogon-Kombich box culvert constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.600282, 35.637542 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 1600000 | 1600000 | 1600000 | Equitable | N/A | 1600000 | 0 | 0 | 0 | 0 | 500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and needs met. Assessor remarks: Functional.
1715 | Infrastructure, Development and Maintenance | Installation of a highmast streetlights at Kuresoi center | To install a highmast streetlights at Kuresoi center | A highmast streetlights at Kuresoi center installed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Kiptororo | -0.302677, 35.529363 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 900000 | 0 | 888200 | Equitable | N/A | 888200 | 0 | 0 | 0 | 0 | 888200 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
1716 | Infrastructure, Development and Maintenance | Construction of 5 no. Motorbike sheds | To construct 5 no. Motorbike sheds | 5 no. Motorbike sheds constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Kivumbini | -0.297893, 36.08279 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 2250000 | 2250000 | 2250000 | Equitable | N/A | 2250000 | 0 | 0 | 0 | 0 | 1200376 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Protect riders from harsh weather conditions.
1717 | Infrastructure, Development and Maintenance | Construction of drainage along Kalewa road (Calvary Church-Bondeni Police Station - Burma) | To construct drainage along Kalewa road (Calvary Church-Bondeni Police Station - Burma) | Drainage along Kalewa road (Calvary Church-Bondeni Police Station - Burma) constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Kivumbini | -0.297973, 36.082795 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2025 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes..helps in managing storm and waste water. Assessor remarks: functional but not maintained.
1718 | Infrastructure, Development and Maintenance | Drainage Maintenance in Kivumbini Ward | To implement drainage maintenance in kivumbini ward for road connectivity and accessibility | Drainage Maintenance in Kivumbini Ward completed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Kivumbini | -0.299248, 36.082036 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 976737 | 97.7 | 976737 | 23263 | 23263 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Improved sanitation.
1719 | Infrastructure, Development and Maintenance | Installation of New Street Lights at Kivumbini Ward | To install New Street Lights at Kivumbini Ward | New Street Lights at Kivumbini Ward installed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Kivumbini | -0.296244, 36.084835 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 1900000 | 1900000 | 1900000 | Equitable | N/A | 1900000 | 0 | 1852500 | 97.5 | 1852500 | 47500 | 47500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Enhanced security.
1720 | Infrastructure, Development and Maintenance | Installation Of Security Lights, Kivumbini Ward | To install Security Lights, Kivumbini Ward | Security Lights, Kivumbini Ward installed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Kivumbini | -0.296244, 36.084835 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 1000000 | 0 | 880200 | Equitable | N/A | 880200 | 0 | 1852500 | 100 | 1852500 | 880200 | -1852500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Enhanced security.
1721 | Infrastructure, Development and Maintenance | Installation Of Streetlights at Kivumbini | To improve lighting and safety through installation of solar streetlights at Kivumbini | Solar streetlights installed at Kivumbini | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Kivumbini | -0.296395, 36.085107 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 766000 | 766000 | 766000 | Equitable | N/A | 766000 | 0 | 1852500 | 241.8 | 1852500 | 766000 | -1086500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Enhanced security.
1722 | Infrastructure, Development and Maintenance | Installation of three streetlights and maintenance of streetlights across Kivumbini Ward | To install three streetlights and maintenance of streetlights across Kivumbini Ward | Three streetlights and maintenance of streetlights across Kivumbini Ward installed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Kivumbini | -0.294656, 36.090036 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | June 2025 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1852500 | 92.6 | 1852500 | 47500 | 147500 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Enhanced security within the area.
1723 | Infrastructure, Development and Maintenance | Maintanance Of Street Lights At Kivumbini | To implement maintanance of street lights at kivumbini for road connectivity and accessibility | Maintanance Of Street Lights At Kivumbini completed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Kivumbini | -0.296395, 36.085107 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 597638 | 597638 | 597638 | Equitable | N/A | 597638 | 0 | 576500 | 96.5 | 576500 | 597638 | 21138 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Enhanced security.
1724 | Infrastructure, Development & Maintenance | Maintenance Of Street Lights Across The Ward | To implement maintenance of street lights across the ward for road connectivity and accessibility | Maintenance Of Street Lights Across The Ward completed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Kivumbini | -0.30403, 36.082783 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 481800 | 96.4 | 481800 | 500000 | 18200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Enhanced security.
1725 | Infrastructure, Development & Maintenance | Maintenance Of Streetlights In Kivumbini Ward | To implement maintenance of streetlights in kivumbini ward for road connectivity and accessibility | Maintenance Of Streetlights In Kivumbini Ward completed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Kivumbini | -0.298543, 36.086344 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | july2022 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 481800 | 96.4 | 481800 | 500000 | 18200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: project helped improve security.
1726 | Infrastructure, Development and Maintenance | Rehabilitation and cleaning of drainages across Kivumbini ward | To rehabilitate cleaning of drainages across Kivumbini ward to restore functionality | Cleaning of drainages across Kivumbini ward rehabilitated | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Kivumbini | -0.298938, 36.082631 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2025 | 1300000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 2100500 | 161.6 | 2100500 | 1000000 | -800500 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes,managed storm water. Assessor remarks: functional but not cleaned.
1727 | Infrastructure, Development and Maintenance | Street Light Maintenance in Kivumbini Ward | To implement street light maintenance in kivumbini ward for road connectivity and accessibility | Street Light Maintenance in Kivumbini Ward completed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Kivumbini | -0.299248, 36.082036 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 23263 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Improved sanitation.
1728 | Infrastructure, Development and Maintenance | Construction of concrete fence at Unity ECDE compound | To construct concrete fence at Unity ECDE compound | Concrete fence at Unity ECDE compound constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Lake View | -0.763086, 36.459064 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Yes partially. Assessor remarks: Good but need more funding for completion.
1729 | Infrastructure, Development and Maintenance | Drainage works and uncloggingand cleaning at Kihoto estate | To implement drainage works and uncloggingand cleaning at kihoto estate for road connectivity and accessibility | Drainage works and uncloggingand cleaning at Kihoto estate completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Lake View | -0.727947, 36.432638 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 4490610 | 89.8 | 4490610 | 509390 | 509390 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: No. Viable: At that time. Assessor remarks: Needs routine maintenance.
1730 | Infrastructure, Development and Maintenance | Installation Of 5 Floodlights at Lake View, Kihoto, Banda Area and Kayole A | To install 5 Floodlights at Lake View, Kihoto, Banda Area and Kayole A | 5 Floodlights at Lake View, Kihoto, Banda Area and Kayole A installed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Lake View | -0.754371, 36.465124 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 2000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2691940 | 89.7 | 2691940 | 308060 | 308060 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
1731 | Infrastructure, Development and Maintenance | Installation of flood lights across the Ward | To install flood lights across the Ward | Flood lights across the Ward installed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Lake View | -0.765206, 36.451327 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 2000000 | 2000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 934800 | 46.7 | 934800 | 65200 | 1065200 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
1732 | Infrastructure, Development and Maintenance | Maintenance of Streetlights across the Ward | To implement maintenance of streetlights across the ward for road connectivity and accessibility | Maintenance of Streetlights across the Ward completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Lake View | -0.729662, 36.431714 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 934800 | 93.5 | 934800 | 65200 | 65200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
1733 | Infrastructure, Development and Maintenance | Maintenance of streetligts | To implement maintenance of streetligts for road connectivity and accessibility | Maintenance of streetligts completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Lake View | -0.733737, 36.433052 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 934800 | 0 | 934800 | 65200 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project was done to completion.
1734 | Infrastructure, Development and Maintenance | Rehabilitation of Drainages in Lakeview Ward | To rehabilitate Drainages in Lakeview Ward to restore functionality | Drainages in Lakeview Ward rehabilitated | 3110504 | Other Infrastructure and Civil Works | Naivasha | Lake View | -0.74909, 36.443446 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 5000000 | 5000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 1105480 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Complete. Viable: Yes. Assessor remarks: Complete.
1735 | Infrastructure, Development & Maintenance | Installation of 20 Highmasts streetlights in Lakeview ward | To install 20 Highmasts streetlights in Lakeview ward | 20 Highmasts streetlights in Lakeview ward installed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Lakeview | -0.727709, 36.443981 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 5000000 | 1998000 | 1998000 | Equitable | N/A | 1998000 | 0 | 1998000 | 100 | 1998000 | 1998000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
1736 | Infrastructure, Development & Maintenance | Installation of culverts in Lakeview | To improve drainage and road access through culvert installation at in Lakeview | Culverts installed at in Lakeview | 3110504 | Other Infrastructure and Civil Works | Naivasha | Lakeview | -0.732486, 36.443473 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 997000 | 99.7 | 997000 | 1000000 | 3000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
1737 | Infrastructure, Development and Maintenance | Installation of high mast lights twenty (20) in various places in Lakeview Ward | To improve security lighting through high mast floodlight installation at lights twenty (20) in various places in Lakeview Ward | High mast floodlight installed at lights twenty (20) in various places in Lakeview Ward | 3110504 | Other Infrastructure and Civil Works | Naivasha | Lakeview | -0.756141, 36.445047 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 5000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 3000000 | 100 | 3000000 | 1998000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete and functional.
1738 | Infrastructure, Development and Maintenance | Maintenance of Drainages in Lakeview ward (Desilting and Unblocking) | To implement maintenance of drainages in lakeview ward (desilting and unblocking) for road connectivity and accessibility | Maintenance of Drainages in Lakeview ward (Desilting and Unblocking) completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Lakeview | -0.72715, 36.433157 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | N/A | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Stalled | 25 | N/A | TO RETENDERED | 2022 | N/A | N/A | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: Was a viable project then. Assessor remarks: Kihoto area has been submerged in water all drainages and not functioning.
1739 | Infrastructure, Development and Maintenance | Maintenance of high mast streetlights | To implement maintenance of high mast streetlights for road connectivity and accessibility | Maintenance of high mast streetlights completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Lakeview | -0.733737, 36.433052 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | N/A | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 556400 | 69.5 | 556400 | 3795650 | 243600 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project was done to completion.
1740 | Infrastructure, Development & Maintenance | Installation of high mast lighting | To improve security lighting through high mast floodlight installation at lighting | High mast floodlight installed at lighting | 3110504 | Other Infrastructure and Civil Works | Naivasha | Lakeview | -0.73156, 36.446771 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 3797814 | 3795650 | 3795650 | Equitable | N/A | 3795650 | 0 | 3795650 | 100 | 3795650 | 3795650 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
1741 | Infrastructure, Development and Maintenance | Installation of streetlights | To improve lighting and safety through installation of solar streetlights at s | Solar streetlights installed at s | 3110504 | Other Infrastructure and Civil Works | Bahati | Lanet Umoja | -0.289997, 36.15359 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | N/A | 3410000 | 3410000 | 3410000 | Equitable | N/A | 3410000 | 0 | 436000 | 12.8 | 436000 | 3410000 | 2974000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Not done.
1742 | Infrastructure, Development and Maintenance | Construction of culverts across the Ward | To construct culverts across the Ward | Culverts across the Ward constructed | 3110504 | Other Infrastructure and Civil Works | Bahati | Lanet-Umoja | -0.269018, 36.157453 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2025/2025 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1095757 | 91.3 | 1095757 | 104243 | 104243 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
1743 | Infrastructure, Development and Maintenance | Installation of Streetlights | To improve lighting and safety through installation of solar streetlights at s | Solar streetlights installed at s | 3110504 | Other Infrastructure and Civil Works | Bahati | Lanet-Umoja | -0.289997, 36.15359 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 436000 | 21.8 | 436000 | 3410000 | 1564000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Not done.
1744 | Infrastructure, Development and Maintenance | Construction Of Culverts across Lanet Ward | To construct Culverts across Lanet Ward | Culverts across Lanet Ward constructed | 3110504 | Other Infrastructure and Civil Works | Bahati | Lanet/Umoja | -0.269018, 36.157453 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2025/2025 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1095757 | 91.3 | 1095757 | 104243 | 104243 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
1745 | Infrastructure, Development and Maintenance | Grading and murraming of murunyu and munyeki roads | To improve road infrastructure by grading and murraming murunyu and munyeki roads | Murunyu and munyeki roads graded and murramed | 3110504 | Other Infrastructure and Civil Works | Bahati | Lanet/Umoja | -0.27868, 36.155335 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 3900000 | 0 | 3900000 | Equitable | N/A | 3900000 | 0 | 0 | 0 | 0 | 1600000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Work in progress.
1746 | Infrastructure, Development and Maintenance | Hire of Machinery for roads rehabilitation | To implement hire of machinery for roads rehabilitation for road connectivity and accessibility | Hire of Machinery for roads rehabilitation completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Lanet/Umoja | -0.276882, 36.141068 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/2024 | 3900000 | 3900000 | 3900000 | Equitable | N/A | 3900000 | 0 | 7000000 | 179.5 | 7000000 | 3900000 | -3100000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Completed.
1747 | Infrastructure, Development and Maintenance | Installation & Maintenance of New Street Lights | To install & Maintenance of New Street Lights | & Maintenance of New Street Lights installed | 3110504 | Other Infrastructure and Civil Works | Bahati | Lanet/Umoja | -0.272331, 36.154652 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/2024 | 2900000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes, very viable. Assessor remarks: Good working condition.
1748 | Infrastructure, Development & Maintenance | Installation of High mast streetlights in Kiamunyeki, Makutano, Moi Forces, Tiger road, Kichinjio road, Remdic Stop, Mtaa B and Ndege Ndimu | To improve security lighting through high mast floodlight installation at streetlights in Kiamunyeki, Makutano, Moi Forces, Tiger road, Kichinjio road, Remdic Stop, Mtaa B and Ndege Ndimu | High mast floodlight installed at streetlights in Kiamunyeki, Makutano, Moi Forces, Tiger road, Kichinjio road, Remdic Stop, Mtaa B and Ndege Ndimu | 3110504 | Other Infrastructure and Civil Works | Bahati | Lanet/Umoja | -0.275097, 36.174683 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/2019 | 3200000 | 0 | 3198500 | Equitable | N/A | 3198500 | 0 | 762100 | 100 | 762100 | 3198500 | -762100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs maintainance.
1749 | Infrastructure, Development and Maintenance | Installation of highmast streetlights at PCEA Kiamunyeki, Junction Mukuru road, Umoja III and Kiratu area | To improve security lighting through high mast floodlight installation at streetlights at PCEA Kiamunyeki, Junction Mukuru road, Umoja III and Kiratu area | High mast floodlight installed at streetlights at PCEA Kiamunyeki, Junction Mukuru road, Umoja III and Kiratu area | 3110504 | Other Infrastructure and Civil Works | Bahati | Lanet/Umoja | -0.277113, 36.152872 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 950613 | 762100 | 762100 | Equitable | N/A | 762100 | 0 | 762100 | 100 | 762100 | 762100 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes very viable. Assessor remarks: Needs mantainance.
1750 | Infrastructure, Development & Maintenance | Installation Of Streetlights At Huruma-Kamfarm Junction, Mafije Area, Potters, Tuinuane, Ndimu Chiefs Road And Down Town | To improve lighting and safety through installation of solar streetlights at Huruma-Kamfarm Junction, Mafije Area, Potters, Tuinuane, Ndimu Chiefs Road And Down Town | Solar streetlights installed at Huruma-Kamfarm Junction, Mafije Area, Potters, Tuinuane, Ndimu Chiefs Road And Down Town | 3110504 | Other Infrastructure and Civil Works | Bahati | Lanet/Umoja | -0.27379, 36.138817 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2022/23 | 2500000 | 2037600.1 | 2037600.1 | Equitable | N/A | 2037600.1 | 0 | 2037600 | 100 | 2037600 | 2037600 | 0.1 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes ,some not functional though. Assessor remarks: Most of them needs mantainance.
1751 | Infrastructure, Development and Maintenance | Installation of streetlights | To improve lighting and safety through installation of solar streetlights at s | Solar streetlights installed at s | 3110504 | Other Infrastructure and Civil Works | Bahati | Lanet/Umoja | -0.289997, 36.15359 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | N/A | 3410000 | 0 | 3410000 | Equitable | N/A | 3410000 | 0 | 436000 | 100 | 436000 | 3410000 | -436000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Not done.
1752 | Infrastructure, Development and Maintenance | Labour based Road maintenance and rehabilitation (purchase of murram and casuals) | To implement labour based road maintenance and rehabilitation (purchase of murram and casuals) for road connectivity and accessibility | Labour based Road maintenance and rehabilitation (purchase of murram and casuals) completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Lanet/Umoja | -0.278138, 36.176558 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
1753 | Infrastructure, Development and Maintenance | Repair Of Street Lights at Umoja, Kiamunyeki, Murunyu, Nyonjoro & Ndege-Ndimu | To rehabilitate Street Lights at Umoja, Kiamunyeki, Murunyu, Nyonjoro & Ndege-Ndimu to restore functionality | Street Lights at Umoja, Kiamunyeki, Murunyu, Nyonjoro & Ndege-Ndimu rehabilitated | 3110504 | Other Infrastructure and Civil Works | Bahati | Lanet/Umoja | -0.272266, 36.154728 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2013/2024 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1447300 | 96.5 | 1447300 | 52700 | 52700 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Completed.
1754 | Infrastructure, Development and Maintenance | Repair of streetlights | To rehabilitate streetlights to restore functionality | Streetlights rehabilitated | 3110504 | Other Infrastructure and Civil Works | Bahati | Lanet/Umoja | -0.275461, 36.15471 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/2022 | 506689 | 436000 | 436000 | Equitable | N/A | 436000 | 0 | 436000 | 100 | 436000 | 436000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Some bulbs needs replacement.
1755 | Infrastructure, Development and Maintenance | Supply of murram | To implement supply of murram for road connectivity and accessibility | Supply of murram completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Lanet/Umoja | -0.283788, 36.174979 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/2021 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999565 | 100 | 999565 | 1000000 | 435 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
1756 | Infrastructure, Development and Maintenance | Bush clearing, grading & murraming of Road K in Lare Ward | To implement bush clearing, grading & murraming of road k in lare ward for road connectivity and accessibility | Bush clearing, grading & murraming of Road K in Lare Ward completed | 3110504 | Other Infrastructure and Civil Works | Njoro | Lare | -0.45063, 36.052547 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2025 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2521100 | 84 | 2521100 | 478900 | 478900 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Okay.
1757 | Infrastructure, Development and Maintenance | Bush clearing, grading & murraming of Road M in Lare Ward | To implement bush clearing, grading & murraming of road m in lare ward for road connectivity and accessibility | Bush clearing, grading & murraming of Road M in Lare Ward completed | 3110504 | Other Infrastructure and Civil Works | Njoro | Lare | -0.45063, 36.052547 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2025 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2521100 | 84 | 2521100 | 478900 | 478900 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Okay.
1758 | Infrastructure, Development and Maintenance | Bush clearing, grading & murraming of Road P in Lare Ward | To implement bush clearing, grading & murraming of road p in lare ward for road connectivity and accessibility | Bush clearing, grading & murraming of Road P in Lare Ward completed | 3110504 | Other Infrastructure and Civil Works | Njoro | Lare | -0.45063, 36.052547 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2025 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2521100 | 84 | 2521100 | 478900 | 478900 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Okay.
1759 | Infrastructure, Development and Maintenance | Bush clearing, grading & murraming of Road S in Lare Ward | To implement bush clearing, grading & murraming of road s in lare ward for road connectivity and accessibility | Bush clearing, grading & murraming of Road S in Lare Ward completed | 3110504 | Other Infrastructure and Civil Works | Njoro | Lare | -0.45063, 36.052547 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2025 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 2521100 | 140.1 | 2521100 | 478900 | -721100 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Okay.
1760 | Infrastructure, Development and Maintenance | Construction of two (2) motorbikes sheds in Lare Ward | To construct two (2) motorbikes sheds in Lare Ward | Two (2) motorbikes sheds in Lare Ward constructed | 3110504 | Other Infrastructure and Civil Works | Njoro | Lare | -0.442734, 36.011476 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2025 | 900000 | 900000 | 900000 | Equitable | N/A | 900000 | 0 | 1700000 | 188.9 | 1700000 | 335593 | -800000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Okay.
1761 | Infrastructure, Development and Maintenance | Grading and murraming through Imarisha barabara(fuel and murram) | To improve road infrastructure by grading and murraming through Imarisha barabara(fuel and murram) | Through Imarisha barabara(fuel and murram) graded and murramed | 3110504 | Other Infrastructure and Civil Works | Njoro | Lare | -0.467588 36.031073 2039.4 6.099999904632568 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 600000 | 0 | 600000 | Equitable | N/A | 600000 | 0 | 1743206 | 100 | 1743206 | 1853150 | -1743206 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
1762 | Infrastructure, Development and Maintenance | Hire of machinery to work on Lare roads - Grading & gravelling | To implement hire of machinery to work on lare roads - grading & gravelling for road connectivity and accessibility | Hire of machinery to work on Lare roads - Grading & gravelling completed | 3110504 | Other Infrastructure and Civil Works | Njoro | Lare | -0.482217 36.04014 1898.6 11.199999809265137 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1860650 | 93 | 1860650 | 1861152 | 139350 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
1763 | Installation Of Mulika Mwizi Across Lare Ward | Installation Of Mulika Mwizi Across Lare Ward | To install Mulika Mwizi Across Lare Ward | Mulika Mwizi Across Lare Ward installed | 3110504 | Other Infrastructure and Civil Works | Njoro | Lare | -0.444369, 36.012939 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2021 | 350000 | 350000 | 350000 | Equitable | N/A | 350000 | 0 | 1700000 | 485.7 | 1700000 | 350000 | -1350000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
1764 | Infrastructure, Development and Maintenance | Construction of a Motorcycle Shed at Lare Ward | To construct a Motorcycle Shed at Lare Ward | A Motorcycle Shed at Lare Ward constructed | 3110504 | Other Infrastructure and Civil Works | Njoro | Lare | -0.442734, 36.011476 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2025 | 335593 | 335593 | 335593 | Equitable | N/A | 335593 | 0 | 699670 | 208.5 | 699670 | 335593 | -364077 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Okay.
1765 | Installation Of 5 Mulika Mwizi In Lare Ward. | Installation Of 5 Mulika Mwizi In Lare Ward. | To install 5 Mulika Mwizi In Lare Ward | 5 Mulika Mwizi In Lare Ward installed | 3110504 | Other Infrastructure and Civil Works | Njoro | Lare | -0.386115, 35.969257 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2021 | 1700000 | 1700000 | 1700000 | Equitable | N/A | 1700000 | 0 | 1700000 | 100 | 1700000 | 1700000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
1766 | Infrastructure, Development and Maintenance | Construction of bodaboda sheds in the Ward | To construct bodaboda sheds in the Ward | Bodaboda sheds in the Ward constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | London | -0.281348, 36.057845 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2025 | 2301371 | 2301371 | 2301371 | Equitable | N/A | 2301371 | 0 | 1546320 | 67.2 | 1546320 | 53680 | 755051 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Bad. Objective met: Not yet. Viable: Not yet. Assessor remarks: The project is currently ongoing.
1767 | Infrastructure, Development and Maintenance | Construction of drainage at Golf Estate | To construct drainage at Golf Estate | Drainage at Golf Estate constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | London | -0.279913 36.055837 1858.5999755859375 8.5 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 3268114 | 1300000 | 6536228 | Equitable | N/A | 6536228 | 0 | 2425821 | 186.6 | 2425821 | 3268114 | -1125821 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Still under construction.
1768 | Infrastructure, Development & Maintenance | Erection And Installation Of Streetlights In Bangladesh | To implement erection and installation of streetlights in bangladesh for road connectivity and accessibility | Erection And Installation Of Streetlights In Bangladesh completed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | London | -0.288092, 36.054717 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 3000000 | 2968460 | 2968460 | Equitable | N/A | 2968460 | 0 | 2968460 | 100 | 2968460 | 2968460 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yea. Assessor remarks: Regularly maintained.
1769 | Infrastructure, Development and Maintenance | Highridge Estate Road drainage construction | To implement highridge estate road drainage construction for road connectivity and accessibility | Highridge Estate Road drainage construction completed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | London | -0.261096, 36.041396 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3356528 | 95.9 | 3356528 | 143472 | 143472 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: DERMERC VENTURES LIMITED. Assessor remarks: Job well done.
1770 | Infrastructure, Development and Maintenance | Installation and Maintenance of High mast lights within the Ward | To install and Maintenance of High mast lights within the Ward | And Maintenance of High mast lights within the Ward installed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | London | -0.271426 36.051788 1907.699951171875 30.98200035095215 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2880600 | 144 | 2880600 | 3500000 | -880600 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good job.
1771 | Infrastructure, Development & Maintenance | Installation of electric power in London Ward | To install electric power in London Ward | Electric power in London Ward installed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | London | -0.274103 36.054114 1880.728105673961 24 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | N/A | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 2880600 | 0 | 2880600 | 2000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
1772 | Infrastructure, Development and Maintenance | Installation of Street Lighting and High Mast Flood Lights at London Ward | To install Street Lighting and High Mast Flood Lights at London Ward | Street Lighting and High Mast Flood Lights at London Ward installed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | London | -0.274075, 36.058162 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2024 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3372950 | 96.4 | 3372950 | 127050 | 127050 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functioning.
1773 | Installation/Laying of Cabro Blocks in London Ward Road Works | Installation/Laying of Cabro Blocks in London Ward Road Works | To implement installation/laying of cabro blocks in london ward road works for road connectivity and accessibility | Installation/Laying of Cabro Blocks in London Ward Road Works completed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | London | -0.273027, 36.05145 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 20000000 | 1165540 | 1165540 | Equitable | N/A | 1165540 | 0 | 7084874 | 607.9 | 7084874 | 1165540 | -5919334 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good job.
1774 | Infrastructure, Development and Maintenance | Maintenance of streetlights across the Ward | To implement maintenance of streetlights across the ward for road connectivity and accessibility | Maintenance of streetlights across the Ward completed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | London | -0.288764 36.055242 1837.800048828125 37.31700134277344 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
1775 | Infrastructure, Development & Maintenance | Rehabilitation of streetlights - Purchase of Streetlight maintenance equipments for London ward | To rehabilitate streetlights - Purchase of Streetlight maintenance equipments for London ward to restore functionality | Streetlights - Purchase of Streetlight maintenance equipments for London ward rehabilitated | 3110504 | Other Infrastructure and Civil Works | Nakuru West | London | -0.276285 36.057374 1873.7531102884197 20.25200080871582 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 499600 | 99.9 | 499600 | 500000 | 400 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Regularly maintentained.
1776 | Infrastructure, Development and Maintenance | Storm Water Drainage along Hospital – KMTC Road in Milimani & FITC Dispensary & Argwings Kodhek Roads | To implement storm water drainage along hospital – kmtc road in milimani & fitc dispensary & argwings kodhek roads for road connectivity and accessibility | Storm Water Drainage along Hospital – KMTC Road in Milimani & FITC Dispensary & Argwings Kodhek Roads completed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | London | -0.276823, 36.073576 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2024 | 2000000 | 1844780 | 1844780 | Equitable | N/A | 1844780 | 0 | 1838380 | 99.7 | 1838380 | 6400 | 6400 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functioning.
1777 | Infrastructure, Development and Maintenance | Street Light Installation in London Ward | To implement street light installation in london ward for road connectivity and accessibility | Street Light Installation in London Ward completed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | London | -0.274169, 36.063824 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1305000 | 87 | 1305000 | 195000 | 195000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Lights working.
1778 | Infrastructure, Development and Maintenance | Street Light maintenance in London Ward | To implement street light maintenance in london ward for road connectivity and accessibility | Street Light maintenance in London Ward completed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | London | -0.274169, 36.063824 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 950000 | 0 | 950000 | Equitable | N/A | 950000 | 0 | 1305000 | 100 | 1305000 | 950000 | -1305000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Lights working.
1779 | Infrastructure, Development and Maintenance | Installation Of High Mast Flood Lights In London Ward | To improve security lighting through high mast floodlight installation at Flood Lights In London Ward | High mast floodlight installed at Flood Lights In London Ward | 3110504 | Other Infrastructure and Civil Works | Nakuru West | London | -0.274075, 36.058162 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2024 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 2880600 | 82.3 | 2880600 | 3500000 | 619400 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functioning.
1780 | Infrastructure, Development and Maintenance | Construction of motorbike sheds in Maai Mahiu and Longonot Towns | To construct motorbike sheds in Maai Mahiu and Longonot Towns | Motorbike sheds in Maai Mahiu and Longonot Towns constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maai Mahiu | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 1400000 | 1400000 | 1400000 | Equitable | N/A | 1400000 | 0 | 3000000 | 214.3 | 3000000 | 500000 | -1600000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
1781 | Infrastructure, Development and Maintenance | Installation of 3 floodights across the Ward | To install 3 floodights across the Ward | 3 floodights across the Ward installed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maai Mahiu | -0.990634, 36.578457 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 1200000 | 0 | 1200000 | Equitable | N/A | 1200000 | 0 | 4000000 | 0 | 4000000 | 1200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
1782 | Infrastructure, Development and Maintenance | Installation of culverts across Maai Mahiu Ward | To improve drainage and road access through culvert installation at across Maai Mahiu Ward | Culverts installed at across Maai Mahiu Ward | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maai Mahiu | -1.00767, 36.523364 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 980876 | 0 | 980876 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Done.
1783 | Infrastructure, Development and Maintenance | Installation of culverts and drainage system on roads | To improve drainage and road access through culvert installation at and drainage system on roads | Culverts installed at and drainage system on roads | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maai Mahiu | -0.982495, 36.586401 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | N/A | 3500000 | 0 | 1261307.4 | Equitable | N/A | 1261307.4 | 0 | 2238693 | 100 | 2238693 | 1261307 | -2238693 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Unclogging needs to be done.
1784 | Infrastructure, Development and Maintenance | Installation Of Culverts In Maai Mahiu | To improve drainage and road access through culvert installation at In Maai Mahiu | Culverts installed at In Maai Mahiu | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maai Mahiu | -1.00767, 36.523364 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 980876 | 98.1 | 980876 | 1000000 | 19124 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Done.
1785 | Infrastructure, Development and Maintenance | Installation of floodlights / street lights across the Ward | To install floodlights / street lights across the Ward | Floodlights / street lights across the Ward installed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maai Mahiu | -0.990634, 36.578457 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 4972300 | 99.4 | 4972300 | 4000000 | 27700 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
1786 | Infrastructure, Development and Maintenance | Installation of the street lights across the Ward | To install the street lights across the Ward | The street lights across the Ward installed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maai Mahiu | -0.990634, 36.578457 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 4000000 | 100 | 4000000 | 4000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
1787 | Infrastructure, Development & Maintenance | Maintenance and installation of 2 floodlights across the Ward | To implement maintenance and installation of 2 floodlights across the ward for road connectivity and accessibility | Maintenance and installation of 2 floodlights across the Ward completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maai Mahiu | -0.952736, 36.54566 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | N/A | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 1152500 | 0 | 1152500 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
1788 | Infrastructure, Development and Maintenance | Repair and maintenance of streetlights across the Ward | To rehabilitate maintenance of streetlights across the Ward to restore functionality | Maintenance of streetlights across the Ward rehabilitated | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maai Mahiu | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 1342063 | 1342063 | 1342063 | Equitable | N/A | 1342063 | 0 | 4000000 | 298 | 4000000 | 4000000 | -2657937 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
1789 | Infrastructure, Development & Maintenance | Streetlights maintenance | To implement streetlights maintenance for road connectivity and accessibility | Streetlights maintenance completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maai Mahiu | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 499500 | 99.9 | 499500 | 500000 | 500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1790 | Installation of high mast streetlights | Installation of high mast streetlights | To improve security lighting through high mast floodlight installation at streetlights | High mast floodlight installed at streetlights | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maai Mahiu | -0.979929, 36.578177 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 1933030 | 1933030 | Equitable | N/A | 1933030 | 0 | 1933030 | 100 | 1933030 | 1933030 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Destroyed by flash floods.
1791 | Infrastructure, Development and Maintenance | Construction of 10 motorbike sheds at Ndabibi | To construct 10 motorbike sheds at Ndabibi | 10 motorbike sheds at Ndabibi constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maiella | -0.804803 36.246244 0 22.5 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2533435 | 84.4 | 2533435 | 0 | 466565 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Eruc Africa Ltd. Assessor remarks: In use.
1792 | Infrastructure, Development and Maintenance | Construction of four motorbike sheds | To construct four motorbike sheds | Four motorbike sheds constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maiella | -0.874886, 36.19251 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2025 | 1600000 | 1600000 | 1600000 | Equitable | N/A | 1600000 | 0 | 2533435 | 158.3 | 2533435 | 0 | -933435 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Work in Progress..Branding Remaining.
1793 | Infrastructure, Development and Maintenance | Installation of Culverts across the Ward | To improve drainage and road access through culvert installation at across the Ward | Culverts installed at across the Ward | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maiella | -0.796872 36.250812 1882.2 6.900000095367432 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 1320001 | 1320001 | Equitable | N/A | 1320001 | 0 | 1238460 | 93.8 | 1238460 | 81541 | 81541 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Bad. Objective met: Not at all. Viable: Not at all. Contractor: Em Hech investment ltd.. Assessor remarks: Poorly done.
1794 | Infrastructure, Development and Maintenance | Installation of solar security light at Moi Ndabi | To install solar security light at Moi Ndabi | Solar security light at Moi Ndabi installed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maiella | -0.804803 36.246244 0 22.5 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 1082480 | 1082480 | 1082480 | Equitable | N/A | 1082480 | 0 | 989526 | 91.4 | 989526 | 92954 | 92954 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Eruc Africa Ltd. Assessor remarks: In use.
1795 | Infrastructure, Development and Maintenance | Maintenance of Streetlights across the ward | To implement maintenance of streetlights across the ward for road connectivity and accessibility | Maintenance of Streetlights across the ward completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maiella | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 460400 | 92.1 | 460400 | 39600 | 39600 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
1796 | Infrastructure, Development and Maintenance | Repairs of streetlights across the ward | To implement repairs of streetlights across the ward for road connectivity and accessibility | Repairs of streetlights across the ward completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maiella | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 582515 | 582515 | 582515 | Equitable | N/A | 582515 | 0 | 460400 | 79 | 460400 | 39600 | 122115 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
1797 | Infrastructure, Development and Maintenance | Bush Clearing and Drainage Cleaning Malewa | To improve the condition of and Drainage Cleaning Malewa | And Drainage Cleaning Malewa improved | 3110504 | Other Infrastructure and Civil Works | Gilgil | Malewa West | -0.702703, 36.471211 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | Yet to start | 1649973 | 0 | 1649973 | Equitable | N/A | 1649973 | 0 | 0 | 0 | 0 | 1649973 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes on completion. Viable: Yes, on completion. Assessor remarks: Yet to start.
1798 | Infrastructure, Development and Maintenance | Construction of Boda Boda Shed in Malewa west | To construct Boda Boda Shed in Malewa west | Boda Boda Shed in Malewa west constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Malewa West | -0.684685, 36.471073 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1491750 | 99.5 | 1491750 | 8250 | 8250 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Done well.
1799 | Infrastructure, Development and Maintenance | Construction of one motorbike shade at high junction to Kasarani | To construct one motorbike shade at high junction to Kasarani | One motorbike shade at high junction to Kasarani constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Malewa West | -0.684685, 36.471073 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2023/24 | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 300000 | 100 | 300000 | 300000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Done well.
1800 | Infrastructure, Development & Maintenance | Installation of High mast Solar floodlights at Nyondia Corner, Karate at Chotara building near North Karate Primary school and Gatamaiyu | To improve security lighting through high mast floodlight installation at Solar floodlights at Nyondia Corner, Karate at Chotara building near North Karate Primary school and Gatamaiyu | High mast floodlight installed at Solar floodlights at Nyondia Corner, Karate at Chotara building near North Karate Primary school and Gatamaiyu | 3110504 | Other Infrastructure and Civil Works | Gilgil | Malewa West | -0.702703, 36.489231 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2019/20 | 1000000 | 999100 | 999100 | Equitable | N/A | 999100 | 0 | 999100 | 100 | 999100 | 999100 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: 2019/20. Assessor remarks: Good work.
1801 | Infrastructure, Development and Maintenance | Installation of street lights in Malewa West ward | To install street lights in Malewa West ward | Street lights in Malewa West ward installed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Malewa West | -0.702703, 36.471211 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | Yet to start | 2000000 | 2000000 | 1350000 | Equitable | N/A | 1350000 | 0 | 1491750 | 74.6 | 1491750 | 600000 | 508250 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: It will once delivered. Viable: It will once delivered. Assessor remarks: Good work.
1802 | Infrastructure, Development and Maintenance | Malewa West culverts Installation | To implement malewa west culverts installation for road connectivity and accessibility | Malewa West culverts Installation completed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Malewa West | -0.702703 36.471211 0 2000 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1935000 | 96.8 | 1935000 | 2000000 | 65000 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: It will. Viable: It will once delivered. Assessor remarks: Yet to start.
1803 | Infrastructure, Development and Maintenance | Malewa West High Mast Flooding Lights Installation | To implement malewa west high mast flooding lights installation for road connectivity and accessibility | Malewa West High Mast Flooding Lights Installation completed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Malewa West | -0.540541 36.34396 0 2000 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1935000 | 96.8 | 1935000 | 65000 | 65000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good project.
1804 | Infrastructure, Development and Maintenance | Construction of Boda Boda shed across the Ward | To construct Boda Boda shed across the Ward | Boda Boda shed across the Ward constructed | 3110504 | Other Infrastructure and Civil Works | Molo | Mariashoni | -0.34614, 35.818449 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 826250 | 82.6 | 826250 | 1000000 | 173750 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Not yet. Assessor remarks: Good.
1805 | Infrastructure, Development and Maintenance | Construction of Boda-Boda Sheds at Mariashoni, Ndoswa, Lawina Centres | To construct Boda-Boda Sheds at Mariashoni, Ndoswa, Lawina Centres | Boda-Boda Sheds at Mariashoni, Ndoswa, Lawina Centres constructed | 3110504 | Other Infrastructure and Civil Works | Molo | Mariashoni | -0.325176, 35.867511 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 826250 | 82.6 | 826250 | 1000000 | 173750 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
1806 | Infrastructure, Development & Maintenance | Installation of culverts at Nduswa - Biston junction road | To improve drainage and road access through culvert installation at Nduswa - Biston junction road | Culverts installed at Nduswa - Biston junction road | 3110504 | Other Infrastructure and Civil Works | Molo | Mariashoni | -0.363089, 35.866439 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 500000 | 100 | 500000 | 500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Working.
1807 | Infrastructure, Development and Maintenance | Installation of floodlights at Oinoptich, Rombei and Segut centers | To install floodlights at Oinoptich, Rombei and Segut centers | Floodlights at Oinoptich, Rombei and Segut centers installed | 3110504 | Other Infrastructure and Civil Works | Molo | Mariashoni | -0.342994, 35.845929 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 900000 | 900000 | 900000 | Equitable | N/A | 900000 | 0 | 735000 | 81.7 | 735000 | 900000 | 165000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
1808 | Infrastructure, Development and Maintenance | Installation of streetlights across the Ward | To improve lighting and safety through installation of solar streetlights at across the Ward | Solar streetlights installed at across the Ward | 3110504 | Other Infrastructure and Civil Works | Molo | Mariashoni | -0.341264, 35.88625 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2024/25 | N/A | 1950000 | 3200000 | 3950000 | Equitable | N/A | 3950000 | 0 | 1958500 | 61.2 | 1958500 | 41500 | 1241500 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Ok.
1809 | Infrastructure, Development and Maintenance | Installation Of Mulika Mwizi/Streetlights in Mau Narok Ward | To install Mulika Mwizi/Streetlights in Mau Narok Ward | Mulika Mwizi/Streetlights in Mau Narok Ward installed | 3110504 | Other Infrastructure and Civil Works | Njoro | Mau Narok | -1.2841 36.8155 0 83800 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 1600000 | 1600000 | 1600000 | Equitable | N/A | 1600000 | 0 | 1588500 | 99.3 | 1588500 | 11500 | 11500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: needs repair.
1810 | Infrastructure, Development and Maintenance | Maintenance Of Street Lights Within Mau Narok Ward | To implement maintenance of street lights within mau narok ward for road connectivity and accessibility | Maintenance Of Street Lights Within Mau Narok Ward completed | 3110504 | Other Infrastructure and Civil Works | Njoro | Mau Narok | -0.29623, 35.958597 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2025 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 500000 | 100 | 500000 | 11500 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Not yet. Viable: Viable. Contractor: Not indicated. Assessor remarks: good condition.
1811 | Infrastructure, Development and Maintenance | Purchase and supply of culverts in Mau Narok Ward | To procure and supply culverts in Mau Narok Ward | Culverts in Mau Narok Ward procured and supplied | 3110504 | Other Infrastructure and Civil Works | Njoro | Mau Narok | -0.630114, 35.992588 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 1332527 | 1332527 | 1332527 | Equitable | N/A | 1332527 | 0 | 500000 | 37.5 | 500000 | 11500 | 832527 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: in good condition.
1812 | Infrastructure, Development and Maintenance | Construction Of Boda-boda Sheds in Mauche | To construct Boda-boda Sheds in Mauche | Boda-boda Sheds in Mauche constructed | 3110504 | Other Infrastructure and Civil Works | Njoro | Mauche | -0.524205 35.952245 2615.7000000000003 6 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 450000 | 0 | 450000 | Equitable | N/A | 450000 | 0 | 2925371 | 100 | 2925371 | 450000 | -2925371 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
1813 | Infrastructure, Development & Maintenance | Culverts installation at Bunei footbridge (Mauche) and Mwolomet (Kapkembu) | To implement culverts installation at bunei footbridge (mauche) and mwolomet (kapkembu) for road connectivity and accessibility | Culverts installation at Bunei footbridge (Mauche) and Mwolomet (Kapkembu) completed | 3110504 | Other Infrastructure and Civil Works | Njoro | Mauche | -0.546022 36.025983 2370.2 12 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1919850 | 96 | 1919850 | 0 | 80150 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Needs improvement.
1814 | Infrastructure, Development & Maintenance | Installation of eight (8) High masts at Mauche Centre | To install eight (8) High masts at Mauche Centre | Eight (8) High masts at Mauche Centre installed | 3110504 | Other Infrastructure and Civil Works | Njoro | Mauche | -0.511313, 35.976385 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2022 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1975000 | 98.8 | 1975000 | 825200 | 25000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
1815 | Installation Of Highmast Streetlights At Mauche, Kamasai And Teret Centres | Installation Of Highmast Streetlights At Mauche, Kamasai And Teret Centres | To improve security lighting through high mast floodlight installation at Streetlights At Mauche, Kamasai And Teret Centres | High mast floodlight installed at Streetlights At Mauche, Kamasai And Teret Centres | 3110504 | Other Infrastructure and Civil Works | Njoro | Mauche | -0.495153, 35.957838 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2023 | 1000000 | 825200 | 825200 | Equitable | N/A | 825200 | 0 | 825200 | 100 | 825200 | 825200 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Tes. Contractor: Not known. Assessor remarks: Good.
1816 | Infrastructure, Development and Maintenance | Construction of Bodaboda sheds at Kiratina | To construct Bodaboda sheds at Kiratina | Bodaboda sheds at Kiratina constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Menengai | -0.289183, 36.115024 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
1817 | Infrastructure, Development and Maintenance | Construction Of Drainage at St. Francis-Deliverance Road | To construct Drainage at St. Francis-Deliverance Road | Drainage at St. Francis-Deliverance Road constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Menengai | -0.275364, 36.113039 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 2800000 | 2800000 | 2800000 | Equitable | N/A | 2800000 | 0 | 2982800 | 106.5 | 2982800 | 2800000 | -182800 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
1818 | Infrastructure, Development and Maintenance | Construction of Kiratina Drainage and installation of culverts | To construct Kiratina Drainage and installation of culverts | Kiratina Drainage and installation of culverts constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Menengai | -0.273086 36.114536 1888.52392578125 44.000999450683594 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | N/A | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3513548 | 87.8 | 3513548 | 2800000 | 486452 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional but needs clearing.
1819 | Infrastructure, Development and Maintenance | Construction of Motorbike sheds for Menengai Ward | To construct Motorbike sheds for Menengai Ward | Motorbike sheds for Menengai Ward constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Menengai | -0.276943, 36.099331 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2024/25 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 3792390 | 379.2 | 3792390 | 207610 | -2792390 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete and functional.
1820 | Infrastructure, Development and Maintenance | Construction of Mwangaza Estate Eastmore drainage works | To construct Mwangaza Estate Eastmore drainage works | Mwangaza Estate Eastmore drainage works constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Menengai | -0.276136, 36.105896 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2285304 | 91.4 | 2285304 | 214696 | 214696 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
1821 | Infrastructure, Development & Maintenance | Construction of Nyamarutu Storm Water Drainage, Police Post/Delivarance Teachers Drainage System, Emboita Drainage System , St Mary's Mountain View Drainage System,Construction of Ranges Vies Storm Water Drainage, Kiratina Drainage System, Whitehouse/Mwangaza/Eastmore Drainage System | To construct Nyamarutu Storm Water Drainage, Police Post/Delivarance Teachers Drainage System, Emboita Drainage System , St Mary's Mountain View Drainage System,Construction of Ranges Vies Storm Water Drainage, Kiratina Drainage System, Whitehouse/Mwangaza/Eastmore Drainage System | Nyamarutu Storm Water Drainage, Police Post/Delivarance Teachers Drainage System, Emboita Drainage System , St Mary's Mountain View Drainage System,Construction of Ranges Vies Storm Water Drainage, Kiratina Drainage System, Whitehouse/Mwangaza/Eastmore Drainage System constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Menengai | -0.274852, 36.113256 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 8000000 | 8000000 | 8000000 | Equitable | N/A | 8000000 | 0 | 7959059 | 99.5 | 7959059 | 0 | 40941 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
1822 | Infrastructure, Development and Maintenance | Construction of Nyamarutu-Kiti Drainage at Menengai Ward | To construct Nyamarutu-Kiti Drainage at Menengai Ward | Nyamarutu-Kiti Drainage at Menengai Ward constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Menengai | -0.267059, 36.101539 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3792390 | 94.8 | 3792390 | 207610 | 207610 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The drainage is blocked and in bad state.
1823 | Infrastructure, Development and Maintenance | Construction of Upper Teachers drainage | To construct Upper Teachers drainage | Upper Teachers drainage constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Menengai | -0.279564, 36.122442 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3988754 | 99.7 | 3988754 | 11246 | 11246 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
1824 | Infrastructure, Development and Maintenance | Installation and maintenance of streetlights across the Ward | To install and maintenance of streetlights across the Ward | And maintenance of streetlights across the Ward installed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Menengai | -0.272378, 36.096995 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2024/25 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 1441416 | 48 | 1441416 | 58584 | 1558584 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
1825 | Installation Of 13 Highmast Streetlighting In Raviella, Pemways, Nguta, Mireri Estate In Menengai Ward | Installation Of 13 Highmast Streetlighting In Raviella, Pemways, Nguta, Mireri Estate In Menengai Ward | To install 13 Highmast Streetlighting In Raviella, Pemways, Nguta, Mireri Estate In Menengai Ward | 13 Highmast Streetlighting In Raviella, Pemways, Nguta, Mireri Estate In Menengai Ward installed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Menengai | -0.279546 36.122457 1856.4000244140625 13.560999870300293 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 3972851.2 | 3760840 | 3760840 | Equitable | N/A | 3760840 | 0 | 3760840 | 100 | 3760840 | 3760840 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: 2017/18.
1826 | Infrastructure, Development & Maintenance | Installation Of Highmast Streetlighting At Kiratina In Menengai Ward | To improve security lighting through high mast floodlight installation at Streetlighting At Kiratina In Menengai Ward | High mast floodlight installed at Streetlighting At Kiratina In Menengai Ward | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Menengai | -0.277469, 36.115343 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2021/22 | 7000001 | 22800 | 22800 | Equitable | N/A | 22800 | 0 | 3499400 | 15348.2 | 3499400 | 22800 | -3476600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
1827 | Infrastructure, Development & Maintenance | Installation Of Highmast Streetlighting At Teachers In Menengai Ward | To improve security lighting through high mast floodlight installation at Streetlighting At Teachers In Menengai Ward | High mast floodlight installed at Streetlighting At Teachers In Menengai Ward | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Menengai | -0.277469, 36.115343 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2021/22 | 7000002 | 600 | 600 | Equitable | N/A | 600 | 0 | 3499400 | 583233.3 | 3499400 | 600 | -3498800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
1828 | Infrastructure, Development and Maintenance | Installation of street lights and maintenance in Menengai Ward | To install street lights and maintenance in Menengai Ward | Street lights and maintenance in Menengai Ward installed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Menengai | -0.279546 36.122457 1856.4000244140625 13.560999870300293 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 4717024 | 94.3 | 4717024 | 600 | 282976 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: 2017/18.
1829 | Infrastructure, Development and Maintenance | Installation of Streetlighting in Menengai Ward | To improve lighting and safety through installation of solar streetlights at ing in Menengai Ward | Solar streetlights installed at ing in Menengai Ward | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Menengai | -0.268181 36.103946 1895.199951171875 12.791999816894531 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2900000 | 96.7 | 2900000 | 22800 | 100000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
1830 | Infrastructure, Development and Maintenance | Maintenance And Cleaning of Drainage in The Ward | To implement maintenance and cleaning of drainage in the ward for road connectivity and accessibility | Maintenance And Cleaning of Drainage in The Ward completed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Menengai | -0.271411 36.111322 1863.5 14.951000213623047 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 1444249 | 1444249 | 1444249 | Equitable | N/A | 1444249 | 0 | 1295960 | 89.7 | 1295960 | 148289 | 148289 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
1831 | Infrastructure, Development and Maintenance | Maintenance Of Streetlights in The Ward | To implement maintenance of streetlights in the ward for road connectivity and accessibility | Maintenance Of Streetlights in The Ward completed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Menengai | -0.274416, 36.10005 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1441416 | 96.1 | 1441416 | 58584 | 58584 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
1832 | Streetlight Maintenanace In Menengai Ward | Streetlight Maintenanace In Menengai Ward | To implement streetlight maintenanace in menengai ward for road connectivity and accessibility | Streetlight Maintenanace In Menengai Ward completed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Menengai | -0.266246, 36.100626 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1325500 | 88.4 | 1325500 | 1500000 | 174500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: Partially. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Only done at one area, ( teachers).
1833 | Infrastructure, Development and Maintenance | Construction Of 10 Boda Boda Shed In Menengai West | To construct 10 Boda Boda Shed In Menengai West | 10 Boda Boda Shed In Menengai West constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Menengai West | -0.225937, 35.975482 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2023 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3482055 | 99.5 | 3482055 | 3500000 | 17945 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
1834 | Infrastructure, Development & Maintenance | Design And Installation Of Highmast Streetlights In Menengai West Ward | To implement design and installation of highmast streetlights in menengai west ward for road connectivity and accessibility | Design And Installation Of Highmast Streetlights In Menengai West Ward completed | 3110504 | Other Infrastructure and Civil Works | Rongai | Menengai West | -0.150263 36.010846 1900.199951171875 123.6719970703125 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2825750 | 94.2 | 2825750 | 3000000 | 174250 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
1835 | Infrastructure, Development and Maintenance | Installation Of Highmast Security Lights At Eden And Mercy Njeri | To improve security lighting through high mast floodlight installation at Security Lights At Eden And Mercy Njeri | High mast floodlight installed at Security Lights At Eden And Mercy Njeri | 3110504 | Other Infrastructure and Civil Works | Rongai | Menengai West | -0.26736, 36.028102 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2023/24 | 6500000 | 0 | 2825750 | Equitable | N/A | 2825750 | 0 | 5475750 | 100 | 5475750 | 2825750 | -5475750 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
1836 | Infrastructure, Development and Maintenance | Installation of Security Lights in Menengai West | To install Security Lights in Menengai West | Security Lights in Menengai West installed | 3110504 | Other Infrastructure and Civil Works | Rongai | Menengai West | -0.25909, 36.016752 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2023/24 | 6000000 | 0 | 524250 | Equitable | N/A | 524250 | 0 | 5475750 | 100 | 5475750 | 524250 | -5475750 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
1837 | Infrastructure, Development and Maintenance | Installation of security lights | To install security lights | Security lights installed | 3110504 | Other Infrastructure and Civil Works | Rongai | Menengai West | -0.267203, 36.037605 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2024/25 | 5700000 | 5700000 | 5700000 | Equitable | N/A | 5700000 | 0 | 5475750 | 96.1 | 5475750 | 524250 | 224250 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs installation of KPLC meters.
1838 | Infrastructure, Development and Maintenance | Rehabilitation Of Streetlights In Menengai West | To rehabilitate Streetlights In Menengai West to restore functionality | Streetlights In Menengai West rehabilitated | 3110504 | Other Infrastructure and Civil Works | Rongai | Menengai West | -0.150347, 36.010852 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2023/24 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 937000 | 187.4 | 937000 | 500000 | -437000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
1839 | Infrastructure, Development and Maintenance | Repair Of Street Lights in Menengai West Ward | To rehabilitate Street Lights in Menengai West Ward to restore functionality | Street Lights in Menengai West Ward rehabilitated | 3110504 | Other Infrastructure and Civil Works | Rongai | Menengai West | -0.150347, 36.010852 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 937000 | 93.7 | 937000 | 63000 | 63000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
1840 | Infrastructure, Development and Maintenance | Construction of concrete line drainage system at Casino area | To construct concrete line drainage system at Casino area | Concrete line drainage system at Casino area constructed | 3110504 | Other Infrastructure and Civil Works | Molo | Molo | -0.249881 35.733187 2442.2001953125 40.98400115966797 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 2000000 | 1799948 | 1799948 | Equitable | N/A | 1799948 | 0 | 1799511 | 100 | 1799511 | 437 | 437 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not yet done.
1841 | Infrastructure, Development and Maintenance | Installation of 10 High mast floodlights across the Ward | To install 10 High mast floodlights across the Ward | 10 High mast floodlights across the Ward installed | 3110504 | Other Infrastructure and Civil Works | Molo | Molo | -0.205407 35.786054 2137.500244140625 16.350000381469727 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3887000 | 97.2 | 3887000 | 900000 | 113000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
1842 | Infrastructure, Development and Maintenance | Installation of 3 floodlights mulika mwizi across the ward | To install 3 floodlights mulika mwizi across the ward | 3 floodlights mulika mwizi across the ward installed | 3110504 | Other Infrastructure and Civil Works | Molo | Molo | -0.240583, 35.726424 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2024/25 | 900000 | 0 | 900000 | Equitable | N/A | 900000 | 0 | 3887000 | 100 | 3887000 | 900000 | -3887000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yed. Viable: Yes. Assessor remarks: Fair.
1843 | Infrastructure, Development and Maintenance | Installation of floodlight at Tayari | To install floodlight at Tayari | Floodlight at Tayari installed | 3110504 | Other Infrastructure and Civil Works | Molo | Molo | -0.241711, 35.724926 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2024/25 | 1500000 | 0 | 1500000 | Equitable | N/A | 1500000 | 0 | 3887000 | 100 | 3887000 | 1500000 | -3887000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Faulty.
1844 | Infrastructure, Development and Maintenance | Installation of mulika mwizi at Kisii Ndogo, Opposite BP station Kwa Chang'aa, Kwa Baba Kamau shopping center, Kwa Ndung'u shopping center, Kwa Sagoo Forest Road, Kwa Kibunja Highway Primary School, Kiambogo shopping center, Matumaini shopping center and Millenium posho mill road | To install mulika mwizi at Kisii Ndogo, Opposite BP station Kwa Chang'aa, Kwa Baba Kamau shopping center, Kwa Ndung'u shopping center, Kwa Sagoo Forest Road, Kwa Kibunja Highway Primary School, Kiambogo shopping center, Matumaini shopping center and Millenium posho mill road | Mulika mwizi at Kisii Ndogo, Opposite BP station Kwa Chang'aa, Kwa Baba Kamau shopping center, Kwa Ndung'u shopping center, Kwa Sagoo Forest Road, Kwa Kibunja Highway Primary School, Kiambogo shopping center, Matumaini shopping center and Millenium posho mill road installed | 3110504 | Other Infrastructure and Civil Works | Molo | Molo | -0.240536, 35.734792 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2024/25 | 2700000 | 2498750 | 2498750 | Equitable | N/A | 2498750 | 0 | 0 | 0 | 0 | 2498750 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Fair.
1845 | Infrastructure, Development and Maintenance | Installation of streetlights at Chazon and Gateiguru | To improve lighting and safety through installation of solar streetlights at Chazon and Gateiguru | Solar streetlights installed at Chazon and Gateiguru | 3110504 | Other Infrastructure and Civil Works | Molo | Molo | -0.232085, 35.705662 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2024/25 | 600000 | 0 | 600000 | Equitable | N/A | 600000 | 0 | 1320450 | 100 | 1320450 | 600000 | -1320450 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Fair.
1846 | Infrastructure, Development and Maintenance | Maintenance of Street Lights Across the Ward | To implement maintenance of street lights across the ward for road connectivity and accessibility | Maintenance of Street Lights Across the Ward completed | 3110504 | Other Infrastructure and Civil Works | Molo | Molo | -0.270663 35.747343 2446.60009765625 4.550000190734863 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 937000 | 93.7 | 937000 | 63000 | 63000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Needs routine maintenance.
1847 | Infrastructure, Development and Maintenance | Meintenance of streetlights across the ward | To implement meintenance of streetlights across the ward for road connectivity and accessibility | Meintenance of streetlights across the ward completed | 3110504 | Other Infrastructure and Civil Works | Molo | Molo | -0.270663 35.747343 2446.60009765625 4.550000190734863 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 1500000 | 0 | 1447082 | Equitable | N/A | 1447082 | 0 | 937000 | 100 | 937000 | 1447082 | -937000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Needs routine maintenance.
1848 | Infrastructure, Development and Maintenance | Installating of culverts at Michina Bridge/ Kwa Ndungu areas | To implement installating of culverts at michina bridge/ kwa ndungu areas for road connectivity and accessibility | Installating of culverts at Michina Bridge/ Kwa Ndungu areas completed | 3110504 | Other Infrastructure and Civil Works | Molo | Molo Central | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | N/A | 2100000 | 2100000 | 2100000 | Equitable | N/A | 2100000 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
1849 | Infrastructure, Development and Maintenance | Installation of 10 Mulika mwizi (High mast security lights) across the ward | To install 10 Mulika mwizi (High mast security lights) across the ward | 10 Mulika mwizi (High mast security lights) across the ward installed | 3110504 | Other Infrastructure and Civil Works | Molo | Molo Central | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
1850 | Infrastructure, Development and Maintenance | Installation of 3 floodlights mulika mwizi across the ward | To install 3 floodlights mulika mwizi across the ward | 3 floodlights mulika mwizi across the ward installed | 3110504 | Other Infrastructure and Civil Works | Molo | Molo Central | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | N/A | 900000 | 900000 | 900000 | Equitable | N/A | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
1851 | Installation, Rehabilitation & Maintenance of Lighting Infrastructure | Installation of 4no. Highmast streetlights | To install 4no. Highmast streetlights | 4no. Highmast streetlights installed | 3110504 | Other Infrastructure and Civil Works | Molo | Molo Central | -0.408907, 36.360101 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2024/25 | 1373871 | 1373871 | 1373871 | Equitable | N/A | 1373871 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Enhanced security.
1852 | Infrastructure, Development and Maintenance | Installation of 8 mulika mwizi across Molo ward at Sachangwan Dispensary, Gitingi Sachangwan, Kwa Ndung'u, behind Molo Academy Primary School, Munju bridge-Kwa Muriu, Kenyatta Estate Phase 2, Lower Kaloleni-Kwa Munyoris and Kampi Mpya Sokoni | To install 8 mulika mwizi across Molo ward at Sachangwan Dispensary, Gitingi Sachangwan, Kwa Ndung'u, behind Molo Academy Primary School, Munju bridge-Kwa Muriu, Kenyatta Estate Phase 2, Lower Kaloleni-Kwa Munyoris and Kampi Mpya Sokoni | 8 mulika mwizi across Molo ward at Sachangwan Dispensary, Gitingi Sachangwan, Kwa Ndung'u, behind Molo Academy Primary School, Munju bridge-Kwa Muriu, Kenyatta Estate Phase 2, Lower Kaloleni-Kwa Munyoris and Kampi Mpya Sokoni installed | 3110504 | Other Infrastructure and Civil Works | Molo | Molo Central | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2400000 | 2240800 | 2240800 | Equitable | N/A | 2240800 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1853 | Installation, Rehabilitation & Maintenance of Lighting Infrastructure | Installation of floodlight at Tayari | To install floodlight at Tayari | Floodlight at Tayari installed | 3110504 | Other Infrastructure and Civil Works | Molo | Molo Central | -0.408907, 36.360101 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2024/25 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Enhanced security.
1854 | Installation, Rehabilitation & Maintenance of Lighting Infrastructure | Installation of floodlights in Molo ward | To install floodlights in Molo ward | Floodlights in Molo ward installed | 3110504 | Other Infrastructure and Civil Works | Molo | Molo Central | -0.408907, 36.360101 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2024/25 | 4200000 | 4200000 | 4200000 | Equitable | N/A | 4200000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Enhanced security.
1855 | Infrastructure, Development and Maintenance | Installation of mulika mwizi at Kisii Ndogo, Opposite BP station Kwa Chang'aa, Kwa Baba Kamau shopping center, Kwa Ndung'u shopping center, Kwa Sagoo forest road, Kwa Kibunja Highway Primary School, Kiambogo shopping center, Matumaini shopping center and Millenium posho mill road | To install mulika mwizi at Kisii Ndogo, Opposite BP station Kwa Chang'aa, Kwa Baba Kamau shopping center, Kwa Ndung'u shopping center, Kwa Sagoo forest road, Kwa Kibunja Highway Primary School, Kiambogo shopping center, Matumaini shopping center and Millenium posho mill road | Mulika mwizi at Kisii Ndogo, Opposite BP station Kwa Chang'aa, Kwa Baba Kamau shopping center, Kwa Ndung'u shopping center, Kwa Sagoo forest road, Kwa Kibunja Highway Primary School, Kiambogo shopping center, Matumaini shopping center and Millenium posho mill road installed | 3110504 | Other Infrastructure and Civil Works | Molo | Molo Central | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2700000 | 2498750 | 2498750 | Equitable | N/A | 2498750 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1856 | Installation, Rehabilitation & Maintenance of Lighting Infrastructure | Installation of streetlights at Chazon and Gateiguru | To improve lighting and safety through installation of solar streetlights at Chazon and Gateiguru | Solar streetlights installed at Chazon and Gateiguru | 3110504 | Other Infrastructure and Civil Works | Molo | Molo Central | -0.408907, 36.360101 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2024/25 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Enhanced security.
1857 | Installation, Rehabilitation & Maintenance of Lighting Infrastructure | Maintenance of floodlights | To implement maintenance of floodlights for road connectivity and accessibility | Maintenance of floodlights completed | 3110504 | Other Infrastructure and Civil Works | Molo | Molo Central | -0.350801, 36.219177 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 24/25 | 2300000 | 2300000 | 2300000 | Equitable | N/A | 2300000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes, value. Contractor: Not indcated. Assessor remarks: Works welk.
1858 | Installation, Rehabilitation & Maintenance of Lighting Infrastructure | Maintenance of streetlights across the ward | To implement maintenance of streetlights across the ward for road connectivity and accessibility | Maintenance of streetlights across the ward completed | 3110504 | Other Infrastructure and Civil Works | Molo | Molo Central | -0.350801, 36.219177 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 24/25 | 312596 | 312596 | 312596 | Equitable | N/A | 312596 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes, value. Contractor: Not indcated. Assessor remarks: Works welk.
1859 | Infrastructure, Development and Maintenance | Mulika Mwizi at Munju/Kanyoni/Tayari | To implement mulika mwizi at munju/kanyoni/tayari for road connectivity and accessibility | Mulika Mwizi at Munju/Kanyoni/Tayari completed | 3110504 | Other Infrastructure and Civil Works | Molo | Molo Central | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 900000 | 78112.95 | 78112.95 | Equitable | N/A | 78112.95 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1860 | Infrastructure, Development and Maintenance | Rehabillitation of streetlights and maintainance in Molo Ward, Molo Sub County, Mologreen garden area @ Tayari, Mutirithia kwa daktari, behind Molo Academy | To implement rehabillitation of streetlights and maintainance in molo ward, molo sub county, mologreen garden area @ tayari, mutirithia kwa daktari, behind molo academy for road connectivity and accessibility | Rehabillitation of streetlights and maintainance in Molo Ward, Molo Sub County, Mologreen garden area @ Tayari, Mutirithia kwa daktari, behind Molo Academy completed | 3110504 | Other Infrastructure and Civil Works | Molo | Molo Central | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 789728 | 3789728 | 3789728 | Equitable | N/A | 3789728 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1861 | Infrastructure, Development and Maintenance | Construction of Drainage at Mimwaita Road | To construct Drainage at Mimwaita Road | Drainage at Mimwaita Road constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Mosop | -0.285402 35.892338 2173.4 20.5 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 1140433 | 1140433 | 1140433 | Equitable | N/A | 1140433 | 0 | 928900 | 81.5 | 928900 | 211533 | 211533 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Kefalice. Assessor remarks: Good.
1862 | Infrastructure, Development and Maintenance | Drainage Construction Kapkatet - Ndarugu road | To implement drainage construction kapkatet - ndarugu road for road connectivity and accessibility | Drainage Construction Kapkatet - Ndarugu road completed | 3110504 | Other Infrastructure and Civil Works | Rongai | Mosop | -0.29878, 35.981102 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2025 | 900000 | 900000 | 900000 | Equitable | N/A | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Viable. Contractor: Andent ltd. Assessor remarks: Yet to start but already handled over.
1863 | Infrastructure, Development and Maintenance | Installation of Flood Lights at Kware ( Mast), at Phase 9 (2 Mast), Near Ronet Dispensary 1 mast | To install Flood Lights at Kware ( Mast), at Phase 9 (2 Mast), Near Ronet Dispensary 1 mast | Flood Lights at Kware ( Mast), at Phase 9 (2 Mast), Near Ronet Dispensary 1 mast installed | 3110504 | Other Infrastructure and Civil Works | Rongai | Mosop | -0.258958, 35.986323 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2023 | 1200000 | 1190596 | 1190596 | Equitable | N/A | 1190596 | 0 | 1190596 | 100 | 1190596 | 1190596 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Kosisit. Assessor remarks: Working.
1864 | Infrastructure, Development & Maintenance | Installation Of High Mast Lights In Mosop Ward | To improve security lighting through high mast floodlight installation at Lights In Mosop Ward | High mast floodlight installed at Lights In Mosop Ward | 3110504 | Other Infrastructure and Civil Works | Rongai | Mosop | -0.213155 35.844007 1903.300048828125 16.100000381469727 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1600000 | 1599200 | 1599200 | Equitable | N/A | 1599200 | 0 | 1599200 | 100 | 1599200 | 1599200 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated q. Assessor remarks: Good.
1865 | Infrastructure, Development & Maintenance | Installation Of Streetlights Across Mosop Ward | To improve lighting and safety through installation of solar streetlights at Across Mosop Ward | Solar streetlights installed at Across Mosop Ward | 3110504 | Other Infrastructure and Civil Works | Rongai | Mosop | -0.27141, 36.006577 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2022 | 1400000 | 1453100 | 1453100 | Equitable | N/A | 1453100 | 0 | 1453100 | 100 | 1453100 | 1453100 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: Complete.
1866 | Infrastructure, Development and Maintenance | Installation Of Streetlights at Ex-Margaret Centre, Dispensary, Ligogo, Sareto, Saiga Market Area, Lee Resort, Kwa Muti, Nda Estate, Kwatwele Junction, Sancity, Phase 9&10 And Sobea Centre | To improve lighting and safety through installation of solar streetlights at Ex-Margaret Centre, Dispensary, Ligogo, Sareto, Saiga Market Area, Lee Resort, Kwa Muti, Nda Estate, Kwatwele Junction, Sancity, Phase 9&10 And Sobea Centre | Solar streetlights installed at Ex-Margaret Centre, Dispensary, Ligogo, Sareto, Saiga Market Area, Lee Resort, Kwa Muti, Nda Estate, Kwatwele Junction, Sancity, Phase 9&10 And Sobea Centre | 3110504 | Other Infrastructure and Civil Works | Rongai | Mosop | -0.269586, 36.005245 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2024 | 4680000 | 0 | 688995 | Equitable | N/A | 688995 | 0 | 3991005 | 100 | 3991005 | 688995 | -3991005 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Imarisha program. Assessor remarks: In good condition.
1867 | Infrastructure, Development & Maintenance | Installation of streetlights | To improve lighting and safety through installation of solar streetlights at s | Solar streetlights installed at s | 3110504 | Other Infrastructure and Civil Works | Rongai | Mosop | -0.259014 35.985669 2075.10009765625 8.100000381469727 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | N/A | 900000 | 900000 | 900000 | Equitable | N/A | 900000 | 0 | 1453100 | 161.5 | 1453100 | 900000 | -553100 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: Working.
1868 | Infrastructure, Development and Maintenance | Maintenance of floodlights across Mosop Ward | To implement maintenance of floodlights across mosop ward for road connectivity and accessibility | Maintenance of floodlights across Mosop Ward completed | 3110504 | Other Infrastructure and Civil Works | Rongai | Mosop | -0.304482 35.987673 2032.800048828125 48.900001525878906 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 450000 | 450000 | 450000 | Equitable | N/A | 450000 | 0 | 1453100 | 322.9 | 1453100 | 1453100 | -1003100 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: Working partially.
1869 | Infrastructure, Development and Maintenance | Maintenance of Salgaa Drainage | To implement maintenance of salgaa drainage for road connectivity and accessibility | Maintenance of Salgaa Drainage completed | 3110504 | Other Infrastructure and Civil Works | Rongai | Mosop | -0.209382, 35.846532 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2024 | 900000 | 900000 | 900000 | Equitable | N/A | 900000 | 0 | 900000 | 100 | 900000 | 900000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: Good.
1870 | Infrastructure, Development and Maintenance | Security lights installation nine (9no.) in number at Ngundu Dispensary, Ndongu ECDE, Westgate, Bethsaida (Ngata), Afya Sacco Phase 1, Westland (Ngata), Pyrethrum (Kirobon), Quarry Area (Kirobon), Roret/ RVIST Junction | To implement security lights installation nine (9no.) in number at ngundu dispensary, ndongu ecde, westgate, bethsaida (ngata), afya sacco phase 1, westland (ngata), pyrethrum (kirobon), quarry area (kirobon), roret/ rvist junction for road connectivity and accessibility | Security lights installation nine (9no.) in number at Ngundu Dispensary, Ndongu ECDE, Westgate, Bethsaida (Ngata), Afya Sacco Phase 1, Westland (Ngata), Pyrethrum (Kirobon), Quarry Area (Kirobon), Roret/ RVIST Junction completed | 3110504 | Other Infrastructure and Civil Works | Rongai | Mosop | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 4050000 | 4050000 | 4050000 | Equitable | N/A | 4050000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
1871 | Infrastructure, Development and Maintenance | Installation of five hybrid solar streetlights at Naivasha East ward | To install five hybrid solar streetlights at Naivasha East ward | Five hybrid solar streetlights at Naivasha East ward installed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Naivasha East | -0.771788 36.506501 2176.800048828125 5.050000190734863 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 1400000 | 1400000 | 1400000 | Equitable | N/A | 1400000 | 0 | 2179377 | 155.7 | 2179377 | 320623 | -779377 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: Not yet done.
1872 | Infrastructure, Development and Maintenance | Installation Of High Mast streetlights Across the Ward | To improve security lighting through high mast floodlight installation at streetlights Across the Ward | High mast floodlight installed at streetlights Across the Ward | 3110504 | Other Infrastructure and Civil Works | Naivasha | Naivasha East | -0.86725 36.535237 2467 6.122000217437744 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2179377 | 87.2 | 2179377 | 320623 | 320623 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
1873 | Infrastructure, Development and Maintenance | Installation of street lighting at Kayole, Kinungi, Ihindu and Kiambogo | To install street lighting at Kayole, Kinungi, Ihindu and Kiambogo | Street lighting at Kayole, Kinungi, Ihindu and Kiambogo installed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Naivasha East | -0.867617 36.522882 2311.6000000000004 6 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 500000 | 480000 | 480000 | Equitable | N/A | 480000 | 0 | 496100 | 103.4 | 496100 | 480000 | -16100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
1874 | Infrastructure, Development and Maintenance | Construction Of Drainage Across the Ward | To construct Drainage Across the Ward | Drainage Across the Ward constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Nakuru East | -0.394532, 36.150395 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 20232024 | 4000000 | 0 | 4000000 | Equitable | N/A | 4000000 | 0 | 6500000 | 100 | 6500000 | 4000000 | -6500000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Manasse class logistics (E) limited. Assessor remarks: Project complete.
1875 | Infrastructure, Development and Maintenance | Construction of two bodaboda sheds in Nakuru East Ward | To construct two bodaboda sheds in Nakuru East Ward | Two bodaboda sheds in Nakuru East Ward constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Nakuru East | -0.351076, 36.150884 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 20242025 | 900000 | 900000 | 900000 | Equitable | N/A | 900000 | 0 | 3988358 | 443.2 | 3988358 | 0 | -3088358 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Project ok.
1876 | Infrastructure, Development & Maintenance | Design And Installation Of Highmast Streetlighting At Wanyama, Muguga, Free Area And Naka | To implement design and installation of highmast streetlighting at wanyama, muguga, free area and naka for road connectivity and accessibility | Design And Installation Of Highmast Streetlighting At Wanyama, Muguga, Free Area And Naka completed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Nakuru East | -0.292381, 36.119131 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/2018 | 11000000 | 10690650 | 10690650 | Equitable | N/A | 10690650 | 0 | 10690650 | 100 | 10690650 | 10690650 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Kilewe electrohard and electronics. Assessor remarks: Require maintainance.
1877 | Infrastructure, Development and Maintenance | Drainage clearing across the ward through Kazi kwa vijana | To implement drainage clearing across the ward through kazi kwa vijana for road connectivity and accessibility | Drainage clearing across the ward through Kazi kwa vijana completed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Nakuru East | -0.394532, 36.150395 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 20232024 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Manasse class logistics (E) limited. Assessor remarks: Project complete.
1878 | Infrastructure, Development and Maintenance | Installation And Maintenance of Street Lights Across the Wards | To install And Maintenance of Street Lights Across the Wards | And Maintenance of Street Lights Across the Wards installed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Nakuru East | -0.333833, 36.142962 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2024/2025 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2743645 | 91.5 | 2743645 | 256355 | 256355 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes. Assessor remarks: Project has been handed over but contractor not in site.
1879 | Infrastructure, Development and Maintenance | Installation and maintenance of streetlights across Nakuru East Ward | To install and maintenance of streetlights across Nakuru East Ward | And maintenance of streetlights across Nakuru East Ward installed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Nakuru East | -0.333833, 36.142962 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2024/2025 | 8500000 | 1649992 | 1609992 | Equitable | N/A | 1609992 | 0 | 6850008 | 415.2 | 6850008 | 1609992 | -5200016 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes. Assessor remarks: Project has been handed over but contractor not in site.
1880 | Infrastructure, Development and Maintenance | Installation and maintenance of streetlights across the Ward | To install and maintenance of streetlights across the Ward | And maintenance of streetlights across the Ward installed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Nakuru East | -0.333833, 36.142962 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2024/2025 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 2743645 | 54.9 | 2743645 | 256355 | 2256355 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes. Assessor remarks: Project has been handed over but contractor not in site.
1881 | Infrastructure, Development and Maintenance | Installation of Street Lights Across the Ward | To install Street Lights Across the Ward | Street Lights Across the Ward installed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Nakuru East | -0.333833, 36.142962 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2024/2025 | 7000000 | 6500000 | 6500000 | Equitable | N/A | 6500000 | 0 | 6500000 | 100 | 6500000 | 6500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes. Assessor remarks: Project has been handed over but contractor not in site.
1882 | Infrastructure, Development and Maintenance | Construction of Box culverts at Tuei Stream | To construct Box culverts at Tuei Stream | Box culverts at Tuei Stream constructed | 3110504 | Other Infrastructure and Civil Works | Njoro | Nessuit | -0.365381 35.872394 2429.5649980855856 5.835000038146973 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 971755 | 81 | 971755 | 1200000 | 228245 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Project yet to start. Viable: Project yet to start. Assessor remarks: Project yet to start.
1883 | Infrastructure, Development and Maintenance | Installation of Culverts at Centre Juu- Ndashatait | To improve drainage and road access through culvert installation at Centre Juu- Ndashatait | Culverts installed at Centre Juu- Ndashatait | 3110504 | Other Infrastructure and Civil Works | Njoro | Nessuit | -0.392578, 35.870721 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | N/A | 1889835 | 0 | 1789835 | Equitable | N/A | 1789835 | 0 | 971755 | 100 | 971755 | 1889835 | -971755 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: The project has not started yet.
1884 | Infrastructure, Development & Maintenance | Installation of floodlights | To install floodlights | Floodlights installed | 3110504 | Other Infrastructure and Civil Works | Njoro | Nessuit | -0.429535 35.91303 2519.8181831532115 5.734000205993652 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1077800 | 89.8 | 1077800 | 28246 | 122200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Culverts require regular unclogging.
1885 | Infrastructure, Development & Maintenance | Installation of High Mast security light at Nessuit Health centre | To improve security lighting through high mast floodlight installation at security light at Nessuit Health centre | High mast floodlight installed at security light at Nessuit Health centre | 3110504 | Other Infrastructure and Civil Works | Njoro | Nessuit | -0.392896 35.898763 2388.13560622558 27.98659896850586 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 350000 | 350000 | 350000 | Equitable | N/A | 350000 | 0 | 310600 | 88.7 | 310600 | 1797420 | 39400 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: No. Viable: No. Contractor: PETMAK INVESTMENTS COMPANY LTD. Assessor remarks: The wall was constructed and it covered part of the intended distance, during construction a section of the wall fell due to heavy rainfall which led to the wall not being complete as earlier intended, a section of the wall was also not painted as expected..
1886 | Infrastructure, Development & Maintenance | Construction Of Boda Boda Sheds At Njoro | To construct Boda Boda Sheds At Njoro | Boda Boda Sheds At Njoro constructed | 3110504 | Other Infrastructure and Civil Works | Njoro | Njoro | -0.332853, 35.943837 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2019 | 1296168 | 1296168 | 1296168 | Equitable | N/A | 1296168 | 0 | 1199768 | 92.6 | 1199768 | 1 | 96400 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: Solid Floor not provided.
1887 | Infrastructure, Development and Maintenance | Construction of open drainage - Beaston Rurii | To construct open drainage - Beaston Rurii | Open drainage - Beaston Rurii constructed | 3110504 | Other Infrastructure and Civil Works | Njoro | Njoro | -0.328842 35.941633 2160.3193359375 8.416999816894531 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 1199768 | 34.3 | 1199768 | 1296168 | 2300232 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: In good start.
1888 | Infrastructure, Development and Maintenance | Installation of 4no. Highmast streetlights | To install 4no. Highmast streetlights | 4no. Highmast streetlights installed | 3110504 | Other Infrastructure and Civil Works | Njoro | Njoro | -0.372267, 35.944313 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2022 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1200000 | 100 | 1200000 | 1200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Mammery Solutions. Assessor remarks: In good state.
1889 | Infrastructure, Development and Maintenance | Installation of floodlights across the ward | To install floodlights across the ward | Floodlights across the ward installed | 3110504 | Other Infrastructure and Civil Works | Njoro | Njoro | -0.289314, 35.896755 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2022 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 1500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/S Mamenyi solutions. Assessor remarks: Good work.
1890 | Infrastructure, Development and Maintenance | Installation Of floodlights through solarization in Njoro Hospital | To install floodlights through solarization in Njoro Hospital | Floodlights through solarization in Njoro Hospital installed | 3110504 | Other Infrastructure and Civil Works | Njoro | Njoro | -0.334448, 35.939609 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2024 | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 765700 | 100 | 765700 | 1000000 | -765700 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: M/S Denken building. Assessor remarks: In good working condition.
1891 | Infrastructure, Development and Maintenance | Maintenance of Streetlights at Njoro Ward | To implement maintenance of streetlights at njoro ward for road connectivity and accessibility | Maintenance of Streetlights at Njoro Ward completed | 3110504 | Other Infrastructure and Civil Works | Njoro | Njoro | -0.329135 35.95168 2146.10009765625 72.9000015258789 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 1000000 | 992900 | 992900 | Equitable | N/A | 992900 | 0 | 765700 | 77.1 | 765700 | 992900 | 227200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: M/S Sincere Electricals Ltd. Assessor remarks: Well done work.
1892 | Infrastructure, Development and Maintenance | Purchase & installation of flood lights | To procure & installation of flood lights | & installation of flood lights procured | 3110504 | Other Infrastructure and Civil Works | Njoro | Njoro | -0.36779 35.903571 2354.041259765625 10.54800033569336 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 1500000 | 50 | 1500000 | 1500000 | 1500000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: In fair state.
1893 | Purchase Of ELD Bulbs | Purchase Of ELD Bulbs | To procure ELD Bulbs | ELD Bulbs procured | 3110504 | Other Infrastructure and Civil Works | Njoro | Njoro | -0.384685 35.935928 2293.6 10.100000381469727 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Contractor: na. Assessor remarks: good.
1894 | Infrastructure, Development and Maintenance | Rehabilitation of streetlights (purchase of maintenance equipments) | To rehabilitate streetlights (purchase of maintenance equipments) to restore functionality | Streetlights (purchase of maintenance equipments) rehabilitated | 3110504 | Other Infrastructure and Civil Works | Njoro | Njoro | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 183797 | 183797 | 183797 | Equitable | N/A | 183797 | 0 | 183797 | 100 | 183797 | 183797 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1895 | Infrastructure, Development & Maintenance | Relocation of electricity poles in Mwigito farm | To implement relocation of electricity poles in mwigito farm for road connectivity and accessibility | Relocation of electricity poles in Mwigito farm completed | 3110504 | Other Infrastructure and Civil Works | Njoro | Njoro | -0.376627, 35.927453 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2022 | 2500000 | 2500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3500000 | 140 | 3500000 | 0 | -1000000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: yes. Viable: yes. Contractor: na. Assessor remarks: good.
1896 | Infrastructure, Development and Maintenance | Construction and installation of culverts at Karumba Bridge | To construct and installation of culverts at Karumba Bridge | And installation of culverts at Karumba Bridge constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Nyota | -0.302322 35.563305 2642.3 19.899999618530273 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 1500000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete: Needs urgent care: General Repairs..
1897 | Infrastructure, Development and Maintenance | Construction of Muchorwe shade | To construct Muchorwe shade | Muchorwe shade constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Nyota | -0.377837 35.709362 2720.8 5.199999809265137 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 400000 | 399950 | 399950 | Equitable | N/A | 399950 | 0 | 317534 | 79.4 | 317534 | 399950 | 82416 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No- Was constructed far from other classes. Viable: No. Contractor: M/S WAMKONG CONSTRUCTION & SuPPLIES LTD. Assessor remarks: Needs renovation.
1898 | Infrastructure, Development and Maintenance | Installation of highmast streetlights across Nyota ward | To improve security lighting through high mast floodlight installation at streetlights across Nyota ward | High mast floodlight installed at streetlights across Nyota ward | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Nyota | -0.30928 35.576045 0 45.599998474121094 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 3400000 | 3400000 | 3400000 | Equitable | N/A | 3400000 | 0 | 3336200 | 98.1 | 3336200 | 63800 | 63800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
1899 | Infrastructure, Development and Maintenance | Construction of bicycle shed at Kamere | To construct bicycle shed at Kamere | Bicycle shed at Kamere constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Olkaria | -0.81864, 36.320703 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 447225 | 29.8 | 447225 | 28500 | 1052775 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes atleast 50 boa boda drivers use the shed. Assessor remarks: The shed Is un operational state.
1900 | Infrastructure, Development and Maintenance | Construction of high mast electrical security light at Kasarani, Shermoi and Mayflower | To construct high mast electrical security light at Kasarani, Shermoi and Mayflower | High mast electrical security light at Kasarani, Shermoi and Mayflower constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Olkaria | -0.837308, 36.357587 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 3000000 | 2990600 | 2990600 | Equitable | N/A | 2990600 | 0 | 2990600 | 100 | 2990600 | 2990600 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Good. Viable: Good. Assessor remarks: Good.
1901 | Infrastructure, Development and Maintenance | Construction of Motor Bike Sheds at Olemayana Kubwa | To construct Motor Bike Sheds at Olemayana Kubwa | Motor Bike Sheds at Olemayana Kubwa constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Olkaria | -0.914569, 36.304266 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 500000 | 0 | 500000 | Equitable | N/A | 500000 | 0 | 447225 | 0 | 447225 | 500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Completed stated twice in the list.
1902 | Infrastructure, Development and Maintenance | Construction Of Motorbike Shed At kwa muhia DCK and Rift Camp | To construct Motorbike Shed At kwa muhia DCK and Rift Camp | Motorbike Shed At kwa muhia DCK and Rift Camp constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Olkaria | 0.834811, 36.365806 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1585070 | 79.3 | 1585070 | 414930 | 414930 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Completed and in order.
1903 | Infrastructure, Development and Maintenance | Construction Of Motorbike Shed At Olemayana Kubwa | To construct Motorbike Shed At Olemayana Kubwa | Motorbike Shed At Olemayana Kubwa constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Olkaria | -0.914569, 36.304266 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 500000 | 475725 | 475725 | Equitable | N/A | 475725 | 0 | 447225 | 94 | 447225 | 28500 | 28500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Completed stated twice in the list.
1904 | Infrastructure, Development and Maintenance | Maintenance Of High Mast Security Lights at Rift and White Gate | To implement maintenance of high mast security lights at rift and white gate for road connectivity and accessibility | Maintenance Of High Mast Security Lights at Rift and White Gate completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Olkaria | -0.836001, 36.3662 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1485900 | 99.1 | 1485900 | 14100 | 14100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The mast is okey but the lights are not working.
1905 | Infrastructure, Development and Maintenance | Power connection to ECDE Classroom in Olemayana Kubwa ECDE | To implement power connection to ecde classroom in olemayana kubwa ecde for road connectivity and accessibility | Power connection to ECDE Classroom in Olemayana Kubwa ECDE completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Olkaria | -0.914572, 36.304319 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 447225 | 44.7 | 447225 | 1000000 | 552775 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Viable but us not started. Assessor remarks: Power connection not yet.
1906 | Infrastructure, Development & Maintenance | Provision of security lights-high mast at May Flowers, Sher Moi, Kasarani and YMCA | To implement provision of security lights-high mast at may flowers, sher moi, kasarani and ymca for road connectivity and accessibility | Provision of security lights-high mast at May Flowers, Sher Moi, Kasarani and YMCA completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Olkaria | -0.835328, 36.353169 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 4000000 | 5999330 | 5999330 | Equitable | N/A | 5999330 | 0 | 5999330 | 100 | 5999330 | 5999330 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
1907 | Infrastructure, Development and Maintenance | Unblocking of drainages and maintenance works at Kamere and Kwa Muhia | To implement unblocking of drainages and maintenance works at kamere and kwa muhia for road connectivity and accessibility | Unblocking of drainages and maintenance works at Kamere and Kwa Muhia completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Olkaria | -0.832278, 36.337006 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project serves well since the vast amount of water us been drained well.
1908 | Infrastructure, Development and Maintenance | Construction of Boda Boda sheds at Rhonda Ward | To construct Boda Boda sheds at Rhonda Ward | Boda Boda sheds at Rhonda Ward constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Rhonda | -0.312705, 36.061213 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 24/25 | 1350000 | 1350000 | 1350000 | Equitable | N/A | 1350000 | 0 | 4991500 | 369.7 | 4991500 | 5000000 | -3641500 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Yet to start.
1909 | Infrastructure, Development & Maintenance | Construction of storm water drainages at Sewage road | To construct storm water drainages at Sewage road | Storm water drainages at Sewage road constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Rhonda | -0.315907, 36.060471 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 19/20 | 5000000 | 0 | 5000000 | Equitable | N/A | 5000000 | 0 | 1534800 | 0 | 1534800 | 5000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Completed.
1910 | Infrastructure, Development and Maintenance | Installation and repair of streetlights at Kanja Square | To install and repair of streetlights at Kanja Square | And repair of streetlights at Kanja Square installed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Rhonda | -0.306994, 36.065157 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 24/25 | 2000000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 5018500 | 334.6 | 5018500 | 481500 | -3518500 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: Not indicated. Assessor remarks: Needs replacement of all lights.
1911 | Infrastructure, Development and Maintenance | Installation Of Security Lights In Mwariki Rhoda Ward | To install Security Lights In Mwariki Rhoda Ward | Security Lights In Mwariki Rhoda Ward installed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Rhonda | -0.306934, 36.065085 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 23/24 | 2100000 | 2100000 | 2100000 | Equitable | N/A | 2100000 | 0 | 2068000 | 98.5 | 2068000 | 2100000 | 32000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Most need repairs.
1912 | Infrastructure, Development and Maintenance | Installation of Street Lights in Rhonda Ward | To install Street Lights in Rhonda Ward | Street Lights in Rhonda Ward installed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Rhonda | -0.306934, 36.065085 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 23/24 | 5500000 | 5500000 | 5500000 | Equitable | N/A | 5500000 | 0 | 5018500 | 91.2 | 5018500 | 481500 | 481500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Most need repairs.
1913 | Infrastructure, Development and Maintenance | Maintenance of streetlights across the Ward | To implement maintenance of streetlights across the ward for road connectivity and accessibility | Maintenance of streetlights across the Ward completed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Rhonda | -0.307373, 36.065665 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 23/24 | 950000 | 950000 | 950000 | Equitable | N/A | 950000 | 0 | 905200 | 95.3 | 905200 | 44800 | 44800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Needs rehabilitation.
1914 | Infrastructure, Development & Maintenance | Rehabilitation and maintenance of streetlights in Rhonda ward | To rehabilitate maintenance of streetlights in Rhonda ward to restore functionality | Maintenance of streetlights in Rhonda ward rehabilitated | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Rhonda | -0.307381, 36.065725 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 21/22 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 5018500 | 1003.7 | 5018500 | 500000 | -4518500 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Needs rehabilitation.
1915 | Infrastructure, Development and Maintenance | Construction of bodaboda sheds | To construct bodaboda sheds | Bodaboda sheds constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Shabab | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 1936394 | 64.5 | 1936394 | 63606 | 1063606 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
1916 | Infrastructure, Development and Maintenance | Construction of drainage along tanners Access road | To construct drainage along tanners Access road | Drainage along tanners Access road constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Shabab | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 2500000 | 0 | 586736.8 | Equitable | N/A | 586736.8 | 0 | 1913263 | 100 | 1913263 | 586737 | -1913263 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1917 | Construction of drainage system at Githima Estate | Construction of drainage system at Githima Estate | To construct drainage system at Githima Estate | Drainage system at Githima Estate constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Shabab | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 4400000 | 4297750 | 4297750 | Equitable | N/A | 4297750 | 0 | 4291953 | 99.9 | 4291953 | 5797 | 5797 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1918 | Infrastructure, Development and Maintenance | Construction of drainages along Lokicha road | To construct drainages along Lokicha road | Drainages along Lokicha road constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Shabab | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 2500000 | 0 | 593206 | Equitable | N/A | 593206 | 0 | 1906794 | 100 | 1906794 | 593206 | -1906794 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1919 | Infrastructure, Development and Maintenance | Construction of drainages at Bamba road | To construct drainages at Bamba road | Drainages at Bamba road constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Shabab | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1936394 | 96.8 | 1936394 | 63606 | 63606 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1920 | Infrastructure, Development and Maintenance | Installation of street lights across Shabab Ward (Ngei Estate; Keyatta spotlight; Watende road; Pyrethrum, Gilani & Githima; Solai Mariakani; Coca cola depot up to Kwa Chief junction | To install street lights across Shabab Ward (Ngei Estate; Keyatta spotlight; Watende road; Pyrethrum, Gilani & Githima; Solai Mariakani; Coca cola depot up to Kwa Chief junction | Street lights across Shabab Ward (Ngei Estate; Keyatta spotlight; Watende road; Pyrethrum, Gilani & Githima; Solai Mariakani; Coca cola depot up to Kwa Chief junction installed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Shabab | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 4500000 | 4500000 | 4500000 | Equitable | N/A | 4500000 | 0 | 4199950 | 93.3 | 4199950 | 300050 | 300050 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1921 | Infrastructure, Development and Maintenance | Installation of street lights at Ngei and Gilanis Estates | To install street lights at Ngei and Gilanis Estates | Street lights at Ngei and Gilanis Estates installed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Shabab | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 3497000 | 174.8 | 3497000 | 2000000 | -1497000 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
1922 | Installation, Rehabilitation & Maintenance of Lighting Infrastructure | Maintenance Of Street Lights in Shabab Ward | To implement maintenance of street lights in shabab ward for road connectivity and accessibility | Maintenance Of Street Lights in Shabab Ward completed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Shabab | -0.350801, 36.219177 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 24/25 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1920015 | 96 | 1920015 | 79985 | 79985 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes, value. Contractor: Not indcated. Assessor remarks: Works welk.
1923 | Installation, Rehabilitation & Maintenance of Lighting Infrastructure | Maintenance Of Streetlights At Shabab | To implement maintenance of streetlights at shabab for road connectivity and accessibility | Maintenance Of Streetlights At Shabab completed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Shabab | -0.350801, 36.219177 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 24/25 | 2043960 | 2043960 | 2043960 | Equitable | N/A | 2043960 | 0 | 1920015 | 93.9 | 1920015 | 2043960 | 123945 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes, value. Contractor: Not indcated. Assessor remarks: Works welk.
1924 | Infrastructure, Development and Maintenance | Rehabilitation and Maintenance of streetlights in Shabab Ward | To rehabilitate Maintenance of streetlights in Shabab Ward to restore functionality | Maintenance of streetlights in Shabab Ward rehabilitated | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Shabab | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 891031 | 891031 | 891031 | Equitable | N/A | 891031 | 0 | 1920015 | 215.5 | 1920015 | 891031 | -1028984 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1925 | Infrastructure, Development and Maintenance | Rehabilitation and unclogging of Drainages within the Ward | To rehabilitate unclogging of Drainages within the Ward to restore functionality | Unclogging of Drainages within the Ward rehabilitated | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Shabab | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2024/25 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 4078946 | 203.9 | 4078946 | 1934 | -2078946 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1926 | Infrastructure, Development and Maintenance | Rehabilitation of Streetlights | To rehabilitate Streetlights to restore functionality | Streetlights rehabilitated | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Shabab | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2024/25 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 3497000 | 174.8 | 3497000 | 891031 | -1497000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1927 | Infrastructure, Development and Maintenance | Hire of Machineries for roads rehabilitation | To implement hire of machineries for roads rehabilitation for road connectivity and accessibility | Hire of Machineries for roads rehabilitation completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Sirikwa | -0.286702, 35.6714 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 4500000 | 4500000 | 4500000 | Equitable | N/A | 4500000 | 0 | 4432000 | 98.5 | 4432000 | 68000 | 68000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is good, however, some sections of the road haa been washed off and needs murraming afresh, bush clearing, culvert installation in some sections as well as unblocking existing culverts.
1928 | Infrastructure, Development and Maintenance | Construction Of 4 Boda-Boda Sheds in Soin Ward | To construct 4 Boda-Boda Sheds in Soin Ward | 4 Boda-Boda Sheds in Soin Ward constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.057727, 36.024252 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 1400000 | 1400000 | 1400000 | Equitable | N/A | 1400000 | 0 | 1398960 | 99.9 | 1398960 | 1040 | 1040 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Sheds in use.
1929 | Infrastructure, Development & Maintenance | Installation of 10 highmast streetlights | To install 10 highmast streetlights | 10 highmast streetlights installed | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.07089, 35.862112 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2947260 | 98.2 | 2947260 | 300000 | 52740 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The lights are not working for six months.
1930 | Infrastructure, Development & Maintenance | Installation Of Highmast Light At Kapsetek Center | To improve security lighting through high mast floodlight installation at Light At Kapsetek Center | High mast floodlight installed at Light At Kapsetek Center | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.081677, 35.872422 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 234000 | 78 | 234000 | 300000 | 66000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Community are grateful.
1931 | Installation Of Highmast Lights At Kiroyo(4),Morop Stage(1),Athinai(1) And Lesibil (1) | Installation Of Highmast Lights At Kiroyo(4),Morop Stage(1),Athinai(1) And Lesibil (1) | To improve security lighting through high mast floodlight installation at Lights At Kiroyo(4),Morop Stage(1),Athinai(1) And Lesibil (1) | High mast floodlight installed at Lights At Kiroyo(4),Morop Stage(1),Athinai(1) And Lesibil (1) | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.124768, 35.943304 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2100000 | 1985750 | 1985750 | Equitable | N/A | 1985750 | 0 | 1985750 | 100 | 1985750 | 1985750 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require routine maintenance.
1932 | Infrastructure, Development and Maintenance | Installation of streetlight at Mauande and Rfiki center - Soin | To improve lighting and safety through installation of solar streetlights at Mauande and Rfiki center - Soin | Solar streetlights installed at Mauande and Rfiki center - Soin | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.146152, 35.967412 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | FY 2025 | 900000 | 400000 | 900000 | Equitable | N/A | 900000 | 0 | 234000 | 58.5 | 234000 | 300000 | 166000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Street lights are operational.
1933 | Infrastructure, Development and Maintenance | Installation Of Streetlights in Soin Ward | To improve lighting and safety through installation of solar streetlights at Soin Ward | Solar streetlights installed at Soin Ward | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.036478, 36.070788 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 496674 | 82.8 | 496674 | 103326 | 103326 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Work done.
1934 | Infrastructure, Development and Maintenance | Rehabilitation of streetlights in Soin Ward | To rehabilitate streetlights in Soin Ward to restore functionality | Streetlights in Soin Ward rehabilitated | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.036478, 36.070788 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 496674 | 49.7 | 496674 | 103326 | 503326 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Work done.
1935 | Infrastructure, Development & Maintenance | Installation Of 4 Floodlights At Rafiki Area | To install 4 Floodlights At Rafiki Area | 4 Floodlights At Rafiki Area installed | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.150125, 35.958591 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1800000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1164900 | 97.1 | 1164900 | 1200000 | 35100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require repair and additional streetlight at the end of the street.
1936 | Infrastructure, Development & Maintenance | Installation Of Floodlights At Kamundu Centre | To install Floodlights At Kamundu Centre | Floodlights At Kamundu Centre installed | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.082257 35.872951 1817 10 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 280000 | 93.3 | 280000 | 300000 | 20000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Two lights not working.
1937 | Infrastructure, Development and Maintenance | Maintenance of streetlight within Soin Ward | To implement maintenance of streetlight within soin ward for road connectivity and accessibility | Maintenance of streetlight within Soin Ward completed | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.027585 35.965793 1571.4000244140625 5.300000190734863 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 298500 | 99.5 | 298500 | 1500 | 1500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: The stalls should start for the.
1938 | Infrastructure, Development and Maintenance | Installation Of Culverts on Various Roads Across the Ward | To improve drainage and road access through culvert installation at Various Roads Across the Ward | Culverts installed at Various Roads Across the Ward | 3110504 | Other Infrastructure and Civil Works | Rongai | Solai | 0.0941 36.186492 1602.3 11.600000381469727 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1619140 | 81 | 1619140 | 380861 | 380860 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: Yes. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The classroom was never completed by the contractor.
1939 | Infrastructure, Development and Maintenance | Installation Of High Mast Floodlights Across the Ward | To improve security lighting through high mast floodlight installation at s Across the Ward | High mast floodlight installed at s Across the Ward | 3110504 | Other Infrastructure and Civil Works | Rongai | Solai | -0.02673, 36.136053 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2024 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1732050 | 86.6 | 1732050 | 267950 | 267950 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functioning.
1940 | Infrastructure, Development & Maintenance | Installation of streetlights at Solai ward | To improve lighting and safety through installation of solar streetlights at Solai ward | Solar streetlights installed at Solai ward | 3110504 | Other Infrastructure and Civil Works | Rongai | Solai | -0.033952 36.107965 1617.32373046875 6.8520002365112305 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 267950 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
1941 | Infrastructure, Development and Maintenance | Repair and Maintenance of Flood Lights | To rehabilitate Maintenance of Flood Lights to restore functionality | Maintenance of Flood Lights rehabilitated | 3110504 | Other Infrastructure and Civil Works | Rongai | Solai | 0.046714, 36.128962 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/23 | 2023/24 | 2024 | 200000 | 0 | 200000 | Equitable | N/A | 200000 | 0 | 0 | 0 | 0 | 200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
1942 | Infrastructure, Development and Maintenance | Repair and maintenance of High mast flood lights in Solai Ward | To rehabilitate maintenance of High mast flood lights in Solai Ward to restore functionality | Maintenance of High mast flood lights in Solai Ward rehabilitated | 3110504 | Other Infrastructure and Civil Works | Rongai | Solai | -0.033952 36.107965 1617.32373046875 6.8520002365112305 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 200000 | 200000 | 200000 | Equitable | N/A | 200000 | 0 | 1732050 | 866 | 1732050 | 200000 | -1532050 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
1943 | Supply And Installation Of 6 Solar Flood Lights (1 Lower Solai,1 Murram,1 Masitamu,1 Kfa And 2 Kiboronjo) | Supply And Installation Of 6 Solar Flood Lights (1 Lower Solai,1 Murram,1 Masitamu,1 Kfa And 2 Kiboronjo) | To procure and install 6 Solar Flood Lights (1 Lower Solai,1 Murram,1 Masitamu,1 Kfa And 2 Kiboronjo) | 6 Solar Flood Lights (1 Lower Solai,1 Murram,1 Masitamu,1 Kfa And 2 Kiboronjo) procured and installed | 3110504 | Other Infrastructure and Civil Works | Rongai | Solai | 0.001971, 36.155 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2022 | 1200000 | 1193300 | 1193300 | Equitable | N/A | 1193300 | 0 | 1193300 | 100 | 1193300 | 1193300 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functioning.
1944 | Infrastructure, Development & Maintenance | Construction of boda boda shed at Subukia center (PCEA) | To construct boda boda shed at Subukia center (PCEA) | Boda boda shed at Subukia center (PCEA) constructed | 3110504 | Other Infrastructure and Civil Works | Subukia | Subukia | 0.000856, 36.229906 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | April 2023 | 579422 | 0 | 577780 | Equitable | N/A | 577780 | 0 | 1394100 | 100 | 1394100 | 577780 | -1394100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes, the site well located to take care of the transport sector in boda boda service.. Contractor: Details not on site. Assessor remarks: Boda boda sector community using the facility.
1945 | Infrastructure, Development and Maintenance | Installation Of Culverts in Subukia Ward | To improve drainage and road access through culvert installation at in Subukia Ward | Culverts installed at in Subukia Ward | 3110504 | Other Infrastructure and Civil Works | Subukia | Subukia | -0.005993, 36.22894 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2024 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 988034 | 98.8 | 988034 | 11966 | 11966 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Working.
1946 | Infrastructure, Development and Maintenance | Installation of high mast solar lights | To improve security lighting through high mast floodlight installation at solar lights | High mast floodlight installed at solar lights | 3110504 | Other Infrastructure and Civil Works | Subukia | Subukia | -0.000202, 36.232353 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2025 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 897300 | 89.7 | 897300 | 0 | 102700 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Working condition.
1947 | Infrastructure, Development and Maintenance | Rehabilitation of Streetlights in Subukia Ward | To rehabilitate Streetlights in Subukia Ward to restore functionality | Streetlights in Subukia Ward rehabilitated | 3110504 | Other Infrastructure and Civil Works | Subukia | Subukia | -0.009177, 36.224835 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/2023 | 1000000 | 0 | 955400 | Equitable | N/A | 955400 | 0 | 988034 | 100 | 988034 | 955400 | -988034 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Not availed. Assessor remarks: Working condition.
1948 | Infrastructure, Development and Maintenance | Installation Of High Mask streetlights in Turi ward | To install High Mask streetlights in Turi ward | High Mask streetlights in Turi ward installed | 3110504 | Other Infrastructure and Civil Works | Molo | Turi | -0.31161, 35.733832 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 1750000 | 1750000 | 1750000 | Equitable | N/A | 1750000 | 0 | 1455420 | 83.2 | 1455420 | 294580 | 294580 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: No documentation, it's on road reserve.
1949 | Infrastructure, Development and Maintenance | Installation of High Mast Lights in Turi Ward | To improve security lighting through high mast floodlight installation at Lights in Turi Ward | High mast floodlight installed at Lights in Turi Ward | 3110504 | Other Infrastructure and Civil Works | Molo | Turi | -0.31161, 35.733832 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 2000000 | 1752750 | 1752750 | Equitable | N/A | 1752750 | 0 | 1752750 | 100 | 1752750 | 1752750 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: No documentation, it's on road reserve.
1950 | Infrastructure, Development and Maintenance | Installation of highmast streetlights | To improve security lighting through high mast floodlight installation at streetlights | High mast floodlight installed at streetlights | 3110504 | Other Infrastructure and Civil Works | Molo | Turi | -0.31161, 35.733832 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 1200000 | 0 | 1200000 | Equitable | N/A | 1200000 | 0 | 1455420 | 100 | 1455420 | 1200000 | -1455420 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: No documentation, it's on road reserve.
1951 | Infrastructure, Development and Maintenance | Installation of highmasts (Mulika mwizi) in Turi ward | To improve security lighting through high mast floodlight installation at s (Mulika mwizi) in Turi ward | High mast floodlight installed at s (Mulika mwizi) in Turi ward | 3110504 | Other Infrastructure and Civil Works | Molo | Turi | -0.268737, 35.745236 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 600000 | 0 | 600000 | Equitable | N/A | 600000 | 0 | 1752750 | 100 | 1752750 | 600000 | -1752750 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
1952 | Infrastructure, Development and Maintenance | Construction of a boda boda shade at Rongai stage F and Molo river | To construct a boda boda shade at Rongai stage F and Molo river | A boda boda shade at Rongai stage F and Molo river constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Visoi | -0.119997 35.933422 1746.5999755859375 6.900000095367432 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 594240 | 99 | 594240 | 600000 | 5760 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Merlins keys enterprises. Assessor remarks: Good.
1953 | Infrastructure, Development and Maintenance | Installation of highmast streetlight at Kanga Tinga and Salgaa center | To improve security lighting through high mast floodlight installation at streetlight at Kanga Tinga and Salgaa center | High mast floodlight installed at streetlight at Kanga Tinga and Salgaa center | 3110504 | Other Infrastructure and Civil Works | Rongai | Visoi | -0.174145 35.861612 1863.5 19.7450008392334 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 600000 | 599800 | 599800 | Equitable | N/A | 599800 | 0 | 599800 | 100 | 599800 | 599800 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Not working,need repair.
1954 | Infrastructure, Development and Maintenance | Installation Of Streetlights at Ranjuera Market, Stima House, Chepseon, Nathuiti and Rongai Centre | To improve lighting and safety through installation of solar streetlights at Ranjuera Market, Stima House, Chepseon, Nathuiti and Rongai Centre | Solar streetlights installed at Ranjuera Market, Stima House, Chepseon, Nathuiti and Rongai Centre | 3110504 | Other Infrastructure and Civil Works | Rongai | Visoi | -0.123247, 35.93443 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2024-25 | 2050000 | 2050000 | 2050000 | Equitable | N/A | 2050000 | 0 | 1949500 | 95.1 | 1949500 | 100500 | 100500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
1955 | Infrastructure, Development and Maintenance | Installatiuon Of Floodlights (Mulika Mwizi ) At Lenginet , Visoi And Muricho Center | To implement installatiuon of floodlights (mulika mwizi ) at lenginet , visoi and muricho center for road connectivity and accessibility | Installatiuon Of Floodlights (Mulika Mwizi ) At Lenginet , Visoi And Muricho Center completed | 3110504 | Other Infrastructure and Civil Works | Rongai | Visoi | -0.148545 35.873142 1880.4 14.699999809265137 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
1956 | Infrastructure, Development and Maintenance | Maintenance Of Streetlights in Vision Ward | To implement maintenance of streetlights in vision ward for road connectivity and accessibility | Maintenance Of Streetlights in Vision Ward completed | 3110504 | Other Infrastructure and Civil Works | Rongai | Visoi | -0.174145 35.861612 1863.5 19.7450008392334 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 500000 | 0 | 500000 | Equitable | N/A | 500000 | 0 | 1096290 | 100 | 1096290 | 500000 | -1096290 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Not working,need repair.
1957 | Infrastructure, Development and Maintenance | Construction of drainage channells at Kanju area | To construct drainage channells at Kanju area | Drainage channells at Kanju area constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Viwandani | -0.710119, 36.433267 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 10000000 | 10000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 1016424 | 10.2 | 1016424 | 333576 | 8983576 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Assessor remarks: Complete.
1958 | Infrastructure, Development and Maintenance | Construction of motorbike shades across the wards | To construct motorbike shades across the wards | Motorbike shades across the wards constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Viwandani | -0.700684, 36.427596 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 1350000 | 0 | 333576 | Equitable | N/A | 333576 | 0 | 1016424 | 100 | 1016424 | 333576 | -1016424 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Assessor remarks: Operational.
1959 | Infrastructure, Development and Maintenance | Installation of high mast streetlights | To improve security lighting through high mast floodlight installation at streetlights | High mast floodlight installed at streetlights | 3110504 | Other Infrastructure and Civil Works | Naivasha | Viwandani | -0.728025, 36.448459 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 6599810 | 110 | 6599810 | 6000000 | -599810 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Assessor remarks: Complete.
1960 | Infrastructure, Development and Maintenance | Repair and maintenance of High Mast Lights | To rehabilitate maintenance of High Mast Lights to restore functionality | Maintenance of High Mast Lights rehabilitated | 3110504 | Other Infrastructure and Civil Works | Naivasha | Viwandani | -0.710361 36.433995 1907.199951171875 10.710000038146973 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2881500 | 96 | 2881500 | 6000000 | 118500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Assessor remarks: Working.
1961 | Infrastructure, Development and Maintenance | Installation of culverts at Kianoe-Kirima Road | To improve drainage and road access through culvert installation at Kianoe-Kirima Road | Culverts installed at Kianoe-Kirima Road | 3110504 | Other Infrastructure and Civil Works | Subukia | Waseges | 0.023015 36.204362 2021.3 4.099999904632568 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 776725 | 129.5 | 776725 | 1000000 | -176725 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
1962 | Infrastructure, Development and Maintenance | Installation Of Culverts in Waseges Ward | To improve drainage and road access through culvert installation at in Waseges Ward | Culverts installed at in Waseges Ward | 3110504 | Other Infrastructure and Civil Works | Subukia | Waseges | 0.023015 36.204362 2021.3 4.099999904632568 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 984798 | 100 | 984798 | 1000000 | -984798 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
1963 | Infrastructure, Development and Maintenance | Installation of Streetlights in Waseges Ward | To improve lighting and safety through installation of solar streetlights at Waseges Ward | Solar streetlights installed at Waseges Ward | 3110504 | Other Infrastructure and Civil Works | Subukia | Waseges | 0.187977 36.235932 1657.3999999999999 6.300000190734863 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 1149770 | 0 | 1149770 | Equitable | N/A | 1149770 | 0 | 984798 | 100 | 984798 | 164972 | -984798 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs Maintenance.
1964 | Installation of culverts in Bahati ward | Installation of culverts in Bahati ward | To improve drainage and road access through culvert installation at in Bahati ward | Culverts installed at in Bahati ward | 3110599 | Other Infrastructure and Civil Works | Bahati | Bahati | -0.179883, 36.127924 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1320611 | 1173023.41 | 1173023.41 | Equitable | N/A | 1173023.41 | 0 | 1172922 | 100 | 1172922 | 1173023 | 101.41 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Working condition.
1965 | Infrastructure, Development and Maintenance | Installation Of Culverts And Gabions At Barut Ward | To improve drainage and road access through culvert installation at And Gabions At Barut Ward | Culverts installed at And Gabions At Barut Ward | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Barut | -0.3424, 36.0423 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2023 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1870183 | 93.5 | 1870183 | 2000000 | 129817 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/S TOPAL ENTERPRISES. Assessor remarks: Completed.
1966 | Infrastructure, Development & Maintenance | Installation of culverts and digging of trenches for Gituamba | To improve drainage and road access through culvert installation at and digging of trenches for Gituamba | Culverts installed at and digging of trenches for Gituamba | 3110599 | Other Infrastructure and Civil Works | Naivasha | Biashara-Naivasha | -0.73672, 36.480287 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2022 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1912000 | 95.6 | 1912000 | 0 | 88000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need for construction of trenches,enlargement and stone pitching of gituamba trench ..and proper drainages.
1967 | Installation of Ndoroto culverts | Installation of Ndoroto culverts | To install Ndoroto culverts | Ndoroto culverts installed | 3110599 | Other Infrastructure and Civil Works | Naivasha | Biashara-Naivasha | -0.688732, 36.526562 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2022 | 2400000 | 2229056 | 2229056 | Equitable | N/A | 2229056 | 0 | 2229056 | 100 | 2229056 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Drainage enhancement and unclogging.
1968 | Installation of Nyonjoro culverts | Installation of Nyonjoro culverts | To install Nyonjoro culverts | Nyonjoro culverts installed | 3110599 | Other Infrastructure and Civil Works | Naivasha | Biashara-Naivasha | -0.676312, 36.486825 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2021 | 1500000 | 1407944 | 1407944 | Equitable | N/A | 1407944 | 0 | 1407944 | 100 | 1407944 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Dakuki contractors. Assessor remarks: Need for stone pitching in quarry location,unblocking and unclogging..
1969 | Infrastructure, Development & Maintenance | Construction and Installation of Culverts in Bondeni Number One | To construct and Installation of Culverts in Bondeni Number One | And Installation of Culverts in Bondeni Number One constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | N/A | 323313 | 323313 | 323313 | Equitable | N/A | 323313 | 0 | 0 | 0 | 0 | 323313 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
1970 | Infrastructure, Development & Maintenance | Construction of cabro and bollards along Gussii road and drainage works | To construct cabro and bollards along Gussii road and drainage works | Cabro and bollards along Gussii road and drainage works constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | -0.285386, 36.075142 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2021/22 | 3500000 | 3074125 | 3074125 | Equitable | N/A | 3074125 | 0 | 3074125 | 100 | 3074125 | 3074125 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Very functional.
1971 | Infrastructure, Development & Maintenance | Construction of cabro and drainage works at East road | To construct cabro and drainage works at East road | Cabro and drainage works at East road constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 3000000 | 2640025 | 2640025 | Equitable | N/A | 2640025 | 0 | 2618760 | 99.2 | 2618760 | 2640025 | 21265 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1972 | Infrastructure, Development & Maintenance | Construction of club lane drainage | To construct club lane drainage | Club lane drainage constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 400000 | 17954.5 | 17954.5 | Equitable | N/A | 17954.5 | 0 | 782046 | 4355.7 | 782046 | 17955 | -764091.5 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1973 | Infrastructure, Development and Maintenance | Installation of fluorescent lighting at nasher market | To install fluorescent lighting at nasher market | Fluorescent lighting at nasher market installed | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | -0.28682, 36.075562 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2023/24 | 1500000 | 0 | 500000 | Equitable | N/A | 500000 | 0 | 1500000 | 100 | 1500000 | 500000 | -1500000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Very functional.
1974 | Infrastructure, Development & Maintenance | Installation of culverts in 5 locations in dundori access roads | To improve drainage and road access through culvert installation at in 5 locations in dundori access roads | Culverts installed at in 5 locations in dundori access roads | 3110599 | Other Infrastructure and Civil Works | Bahati | Dundori | -0.247407, 36.182378 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2018/2019 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 943870 | 47.2 | 943870 | 2000000 | 1056130 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Chartin construction ltd. Assessor remarks: Good three in number.
1975 | Infrastructure, Development & Maintenance | Construction of culverts on Elburgon roads | To construct culverts on Elburgon roads | Culverts on Elburgon roads constructed | 3110599 | Other Infrastructure and Civil Works | Molo | Elburgon | -0.303366 35.81419 0 2000 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 965294 | 96.5 | 965294 | 1186660 | 34706 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: Yet to start.
1976 | Infrastructure, Development and Maintenance | Installation of culverts at Kapsita roads | To improve drainage and road access through culvert installation at Kapsita roads | Culverts installed at Kapsita roads | 3110599 | Other Infrastructure and Civil Works | Molo | Elburgon | -0.289915, 35.773951 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | - | 1200000 | 0 | 1186660 | Equitable | N/A | 1186660 | 0 | 920145 | 100 | 920145 | 1186660 | -920145 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Ye. Viable: Ye. Assessor remarks: Shed need some repair and maintainance.
1977 | Infrastructure, Development and Maintenance | Completion and back filling of Munanda depression culverts | To complete and back filling of Munanda depression culverts | And back filling of Munanda depression culverts completed | 3110599 | Other Infrastructure and Civil Works | Gilgil | Elementaita | -0.584147, 36.114305 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 1998100 | 1998100 | Equitable | N/A | 1998100 | 0 | 1996948 | 99.9 | 1996948 | 1998100 | 1152 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
1978 | Infrastructure, Development & Maintenance | Construction of Wakajane-Meli culverts | To construct Wakajane-Meli culverts | Wakajane-Meli culverts constructed | 3110599 | Other Infrastructure and Civil Works | Gilgil | Elementaita | -0.640033, 36.115242 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1248109 | 1246020 | 1246020 | Equitable | N/A | 1246020 | 0 | 1246020 | 100 | 1246020 | 1246020 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Useful since the area is hilly has rendered the adjacent road impassable..
1979 | Installation of culverts at Kiambogo area | Installation of culverts at Kiambogo area | To improve drainage and road access through culvert installation at Kiambogo area | Culverts installed at Kiambogo area | 3110599 | Other Infrastructure and Civil Works | Gilgil | Elementaita | -0.599097, 36.131986 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1765992 | 1764592 | 1764592 | Equitable | N/A | 1764592 | 0 | 1763921 | 100 | 1763921 | 1764592 | 671 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Some culverts have been removed to pave way for construction of Elementaita Kiambogo road.
1980 | Infrastructure, Development and Maintenance | Maintenance and Installation of Streetlights | To implement maintenance and installation of streetlights for road connectivity and accessibility | Maintenance and Installation of Streetlights completed | 3110599 | Other Infrastructure and Civil Works | Gilgil | Elementaita | -0.594173, 36.11679 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 1500000 | 0 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 1500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
1981 | Infrastructure, Development and Maintenance | Construction Of Boda-boda Sheds | To construct Boda-boda Sheds | Boda-boda Sheds constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Flamingo | -0.306914, 36.078148 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/2024 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1957540 | 97.9 | 1957540 | 42460 | 42460 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Avram Africa ltd. Assessor remarks: In operation/good status.
1982 | Infrastructure, Development & Maintenance | Labour based drainage and culverts cleaning, bush clearing in Gilgil ward | To implement labour based drainage and culverts cleaning, bush clearing in gilgil ward for road connectivity and accessibility | Labour based drainage and culverts cleaning, bush clearing in Gilgil ward completed | 3110599 | Other Infrastructure and Civil Works | Gilgil | Gilgil | -0.471135 36.286586 1885.699951171875 87.5999984741211 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 997500 | 99.8 | 997500 | 1000000 | 2500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Partially. Viable: Partially. Assessor remarks: Needs maintainance and culverts.
1983 | Infrastructure, Development and Maintenance | Installation of highmast streetlights (mulika mwizi) in Bahati ward | To improve security lighting through high mast floodlight installation at streetlights (mulika mwizi) in Bahati ward | High mast floodlight installed at streetlights (mulika mwizi) in Bahati ward | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 1500000 | 0 | 1500000 | Equitable | N/A | 1500000 | 0 | 9793000 | 0 | 9793000 | 9793000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
1984 | Infrastructure, Development & Maintenance | Rehabilitation of bus park and other Parking bays | To rehabilitate bus park and other Parking bays to restore functionality | Bus park and other Parking bays rehabilitated | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 10000000 | 1537405.3 | 37405.3 | Equitable | N/A | 37405.3 | 0 | 1537405 | 100 | 1537405 | 1537405 | 0.3 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
1985 | Infrastructure, Development and Maintenance | Rehabilitation of drainages | To rehabilitate drainages to restore functionality | Drainages rehabilitated | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 8000000 | 7000000 | 7000000 | Equitable | N/A | 7000000 | 0 | 4414833 | 63.1 | 4414833 | 85167 | 2585167 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
1986 | Infrastructure, Development and Maintenance | Road safety Programme | To implement road safety programme for road connectivity and accessibility | Road safety Programme completed | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 9000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
1987 | Infrastructure, Development & Maintenance | Installation Of Culverts And Road Works Across Kabazi Ward | To improve drainage and road access through culvert installation at And Road Works Across Kabazi Ward | Culverts installed at And Road Works Across Kabazi Ward | 3110599 | Other Infrastructure and Civil Works | Subukia | Kabazi | -0.07176 36.1704 0 783.315673828125 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2020/21 | 2020/21 | 1500000 | 1441100 | 1441100 | Equitable | N/A | 1441100 | 0 | 4828453 | 335.1 | 4828453 | 1441100 | -3387353 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: To be operationalized.
1988 | Infrastructure, Development & Maintenance | Renovation Of Boda Boda Sheds | To rehabilitate Boda Boda Sheds to restore functionality | Boda Boda Sheds rehabilitated | 3110599 | Other Infrastructure and Civil Works | Subukia | Kabazi | -0.14564 36.042843 1893.8 3.799999952316284 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 398010 | 99.5 | 398010 | 400000 | 1990 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Well maintained.
1989 | Infrastructure, Development & Maintenance | Renovation Of Boda Boda Shed | To rehabilitate Boda Boda Shed to restore functionality | Boda Boda Shed rehabilitated | 3110599 | Other Infrastructure and Civil Works | Subukia | Kabazi | -0.14564 36.042843 1893.8 3.799999952316284 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 200000 | 200000 | 200000 | Equitable | N/A | 200000 | 0 | 200000 | 100 | 200000 | 200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Well maintained.
1990 | Infrastructure, Development and Maintenance | Grading and Gravelling of Kamara Sarambei and Mau Roads | To improve road infrastructure by grading and murraming Kamara Sarambei and Mau Roads | Kamara Sarambei and Mau Roads graded and murramed | 3110599 | Other Infrastructure and Civil Works | Kuresoi North | Kamara | -0.08666 35.685103 2506.4 3.700000047683716 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 2463632 | 2463632 | 2463632 | Equitable | N/A | 2463632 | 0 | 2451233 | 99.5 | 2451233 | 2463632 | 12399 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Unknown. Assessor remarks: Needs maintenance.
1991 | Infrastructure, Development & Maintenance | Construction Of Boda Boda Sheds Alongside Ingobor-Mombasa Road | To construct Boda Boda Sheds Alongside Ingobor-Mombasa Road | Boda Boda Sheds Alongside Ingobor-Mombasa Road constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Kapkures | -0.288288, 36.000456 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 550895 | 550895 | 550895 | Equitable | N/A | 550895 | 0 | 550895 | 100 | 550895 | 550895 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Has better work environment. Assessor remarks: Done but is in bad state.
1992 | Construction Of Boda Boda Sheds At Kb Area | Construction Of Boda Boda Sheds At Kb Area | To construct Boda Boda Sheds At Kb Area | Boda Boda Sheds At Kb Area constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Kapkures | -0.324324, 36.036613 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 700000 | 100 | 700000 | 700000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Viable. Improved transport services. Assessor remarks: Done and in use.
1993 | Infrastructure, Development and Maintenance | High Mast Street lights at Kipsimal | To implement high mast street lights at kipsimal for road connectivity and accessibility | High Mast Street lights at Kipsimal completed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Kapkures | -0.306306, 36.036551 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 103200 | 34.4 | 103200 | 0 | 196800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Has improved security in the area. Assessor remarks: Done and complete. But currently the bulbs need replacement.
1994 | Infrastructure, Development and Maintenance | Installation and maintenance of high mast lights at Kapkures center | To install and maintenance of high mast lights at Kapkures center | And maintenance of high mast lights at Kapkures center installed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Kapkures | -0.288288 36.000456 0 2000 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 2400000 | 100 | 2400000 | 2680835 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Improved security. Assessor remarks: Well implemented and functional.
1995 | Infrastructure, Development & Maintenance | Construction Of Drainage System | To construct Drainage System | Drainage System constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Kaptembwo | -0.299728 36.045548 1803.800048828125 21.075000762939453 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2497522 | 83.3 | 2497522 | 3000000 | 502478 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/S MIDRIFT GENERAL MERCHANTS. Assessor remarks: Overgrown vegetation has debris and thrush,needs unclogging.
1996 | Infrastructure, Development & Maintenance | Drainage construction along Gikomba market in Rhonda Estate (Kaptembwo Ward) | To implement drainage construction along gikomba market in rhonda estate (kaptembwo ward) for road connectivity and accessibility | Drainage construction along Gikomba market in Rhonda Estate (Kaptembwo Ward) completed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Kaptembwo | -0.301671, 36.055381 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: It's viable. Contractor: M/S TERIBELL TRADING COMPANY. Assessor remarks: It needs rehabilitation, since it's clogged and structural damage.
1997 | Rehabilitation Of Drainage System In Kaptembwo | Rehabilitation Of Drainage System In Kaptembwo | To rehabilitate Drainage System In Kaptembwo to restore functionality | Drainage System In Kaptembwo rehabilitated | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Kaptembwo | -0.302338, 36.049139 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2021/22 | 1000000 | 955050 | 955050 | Equitable | N/A | 955050 | 0 | 922599 | 96.6 | 922599 | 32451 | 32451 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes,it has helped reduce flooding. Contractor: M/S EXPERTS MERCHANTS. Assessor remarks: Needs rehabilitation.
1998 | Infrastructure, Development & Maintenance | Installation of culvert across Keringet ward | To improve drainage and road access through culvert installation at across Keringet ward | Culverts installed at across Keringet ward | 3110599 | Other Infrastructure and Civil Works | Kuresoi South | Keringet | -0.424285, 35.69566 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2022 | 500000 | 480480 | 480480 | Equitable | N/A | 480480 | 0 | 422214 | 87.9 | 422214 | 480480 | 58266 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Done.
1999 | Infrastructure, Development & Maintenance | Installation of culverts | To install culverts | Culverts installed | 3110599 | Other Infrastructure and Civil Works | Kuresoi South | Keringet | -0.431138, 35.708027 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 422214 | 42.2 | 422214 | 1000000 | 577786 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
2000 | Infrastructure, Development and Maintenance | Purchase of solar streetlights(400watts) for boosting security across the ward | To procure solar streetlights(400watts) for boosting security across the ward | Solar streetlights(400watts) for boosting security across the ward procured | 3110599 | Other Infrastructure and Civil Works | Bahati | Kiamaina | -0.236625 36.133717 1909.5 3.200000047683716 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 500000 | 628400 | 628400 | Equitable | N/A | 628400 | 0 | 628400 | 100 | 628400 | 628400 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: It's viable if can be purchased. Assessor remarks: No land purchased.
2001 | Infrastructure, Development & Maintenance | Construction And Installation Of Davishon Culverts | To construct And Installation Of Davishon Culverts | And Installation Of Davishon Culverts constructed | 3110599 | Other Infrastructure and Civil Works | Njoro | Kihingo | -0.491807 35.995308 2269.3999999999996 13.800000190734863 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2999999 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 971718 | 97.2 | 971718 | 1000000 | 28282 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
2002 | Infrastructure, Development & Maintenance | Installation Of Culverts In Kihingo Ward | To improve drainage and road access through culvert installation at In Kihingo Ward | Culverts installed at In Kihingo Ward | 3110599 | Other Infrastructure and Civil Works | Njoro | Kihingo | -0.397138 35.959772 2227.2000000000003 4.599999904632568 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1266636 | 1266636 | Equitable | N/A | 1266636 | 0 | 1266636 | 100 | 1266636 | 1266636 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires maintenance.
2003 | Infrastructure, Development and Maintenance | Culverting of roads within Kiptororo Ward | To implement culverting of roads within kiptororo ward for road connectivity and accessibility | Culverting of roads within Kiptororo Ward completed | 3110599 | Other Infrastructure and Civil Works | Kuresoi North | Kiptororo | -0.300889 35.533228 0 20.100000381469727 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 4800000 | 2000000 | 4800000 | Equitable | N/A | 4800000 | 0 | 1272998 | 63.6 | 1272998 | 136002 | 727002 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Request for construction of toilet.
2004 | Infrastructure, Development and Maintenance | Construction Of Boda Boda Shed In Kivumbini Ward | To construct Boda Boda Shed In Kivumbini Ward | Boda Boda Shed In Kivumbini Ward constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Kivumbini | -0.296226, 36.084967 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 999900 | 999900 | Equitable | N/A | 999900 | 0 | 999130 | 99.9 | 999130 | 999900 | 770 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Offer shelter for boda boda riders.
2005 | Infrastructure, Development and Maintenance | Construction Of Motorcycle Sheds | To construct Motorcycle Sheds | Motorcycle Sheds constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Kivumbini | -0.295417, 36.09162 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | July 2025 | 1200376 | 0 | 1200376 | Equitable | N/A | 1200376 | 0 | 999130 | 100 | 999130 | 1200376 | -999130 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Useful to boda boda operators.
2006 | Infrastructure, Development & Maintenance | Construction of motorbike sheds | To construct motorbike sheds | Motorbike sheds constructed | 3110599 | Other Infrastructure and Civil Works | Bahati | Lanet/Umoja | -0.275795, 36.135705 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 995888 | 142.3 | 995888 | 700000 | -295888 | Stalled | 75 | 100 | RECOMMENDED FOR TERMINATION | 2021 | N/A | -295888 | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
2007 | Infrastructure, Development and Maintenance | Installation Of Two Mulika Mwizi in Lare Ward | To install Two Mulika Mwizi in Lare Ward | Two Mulika Mwizi in Lare Ward installed | 3110599 | Other Infrastructure and Civil Works | Njoro | Lare | -0.442926, 36.011497 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2025 | 700000 | 0 | 700000 | Equitable | N/A | 700000 | 0 | 1700000 | 100 | 1700000 | 700000 | -1700000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
2008 | Infrastructure, Development and Maintenance | Construction Of Drainage System At Guba Road | To construct Drainage System At Guba Road | Drainage System At Guba Road constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | London | -0.272576, 36.054039 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 3000000 | 2433916 | 2433916 | Equitable | N/A | 2433916 | 0 | 2425821 | 99.7 | 2425821 | 2433916 | 8095 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes. Assessor remarks: Conatructor declined to begin the work ,needs more funds.
2009 | Infrastructure, Development and Maintenance | Construction of drainage system at Kwa Mama Wanjiku | To construct drainage system at Kwa Mama Wanjiku | Drainage system at Kwa Mama Wanjiku constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | London | -0.272576, 36.054039 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 2600000 | 2600000 | 2600000 | Equitable | N/A | 2600000 | 0 | 2425821 | 93.3 | 2425821 | 2433916 | 174179 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes. Assessor remarks: Conatructor declined to begin the work ,needs more funds.
2010 | Construction Of Drainage System At St. Michael Catholic Church | Construction Of Drainage System At St. Michael Catholic Church | To construct Drainage System At St. Michael Catholic Church | Drainage System At St. Michael Catholic Church constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | London | -0.271517, 36.05234 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 1994430 | 1994430 | Equitable | N/A | 1994430 | 0 | 1736413 | 87.1 | 1736413 | 1994430 | 258017 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: It needs cleaning.
2011 | Infrastructure, Development and Maintenance | Construction of drainage system in Bangladesh | To construct drainage system in Bangladesh | Drainage system in Bangladesh constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | London | -0.272973 36.050772 1903.1053267583588 100 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 3455390 | 172.8 | 3455390 | 4716 | -1455390 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The drianga drinage has since been improved by KISSIP PROJECT.
2012 | Infrastructure, Development and Maintenance | Construction of drainage system in High ridge estate | To construct drainage system in High ridge estate | Drainage system in High ridge estate constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | London | -0.269363 36.041384 1938.5 8.5 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 3455390 | 172.8 | 3455390 | 2500000 | -1455390 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: It has not sarted.
2013 | Infrastructure, Development and Maintenance | Construction Of Drainage System In London | To construct Drainage System In London | Drainage System In London constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | London | -0.272973 36.050772 1903.1053267583588 100 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 3500000 | 4716 | 4716 | Equitable | N/A | 4716 | 0 | 3455390 | 73269.5 | 3455390 | 4716 | -3450674 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The drianga drinage has since been improved by KISSIP PROJECT.
2014 | Infrastructure, Development and Maintenance | Construction of drainage system in Riva Estate | To construct drainage system in Riva Estate | Drainage system in Riva Estate constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | London | -0.279913 36.055837 1858.5999755859375 8.5 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 3455390 | 230.4 | 3455390 | 2500000 | -1955390 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Still under construction.
2015 | Construction Of Drainage System On 300M Hilton Road | Construction Of Drainage System On 300M Hilton Road | To construct Drainage System On 300M Hilton Road | Drainage System On 300M Hilton Road constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | London | -0.270625, 36.050993 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1239675 | 1239675 | 1239675 | Equitable | N/A | 1239675 | 0 | 1239675 | 100 | 1239675 | 1239675 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: The drainage was put but when tarmac was put they did awy with it.
2016 | Infrastructure, Development & Maintenance | Construction Of Motorcycle Sheds In Chomabase | To construct Motorcycle Sheds In Chomabase | Motorcycle Sheds In Chomabase constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | London | -0.27722 36.052943 1866.199951171875 29.358999252319336 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1499950 | 1499950 | Equitable | N/A | 1499950 | 0 | 1496325 | 99.8 | 1496325 | 1499950 | 3625 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good job.
2017 | Infrastructure, Development and Maintenance | Construction Of Longonot Parking | To construct Longonot Parking | Longonot Parking constructed | 3110599 | Other Infrastructure and Civil Works | Naivasha | Maai Mahiu | -0.883247, 36.496224 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3931173 | 98.3 | 3931173 | 68827 | 68827 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Partially. Viable: The project was very viable, but implemented in a limited way. Assessor remarks: Needs to be redone and extension to cover the entire parking..
2018 | Culverts installation across Maai Mahiu ward | Culverts installation across Maai Mahiu ward | To implement culverts installation across maai mahiu ward for road connectivity and accessibility | Culverts installation across Maai Mahiu ward completed | 3110599 | Other Infrastructure and Civil Works | Naivasha | Maai Mahiu | -0.957908, 36.557244 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1930176 | 96.5 | 1930176 | 2000000 | 69824 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
2019 | Infrastructure, Development & Maintenance | Drainage works (unclogging) | To implement drainage works (unclogging) for road connectivity and accessibility | Drainage works (unclogging) completed | 3110599 | Other Infrastructure and Civil Works | Naivasha | Maai Mahiu | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2020 | Infrastructure, Development and Maintenance | Erection of gabions and murraming at Ereri road | To implement erection of gabions and murraming at ereri road for road connectivity and accessibility | Erection of gabions and murraming at Ereri road completed | 3110599 | Other Infrastructure and Civil Works | Naivasha | Maai Mahiu | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1844100 | 1640275 | 1640275 | Equitable | N/A | 1640275 | 0 | 1640275 | 100 | 1640275 | 1640275 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2021 | Infrastructure, Development and Maintenance | Erection of gabions and murraming at Lari road | To implement erection of gabions and murraming at lari road for road connectivity and accessibility | Erection of gabions and murraming at Lari road completed | 3110599 | Other Infrastructure and Civil Works | Naivasha | Maai Mahiu | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 898120 | 898120 | Equitable | N/A | 898120 | 0 | 898120 | 100 | 898120 | 898120 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2022 | Infrastructure, Development and Maintenance | Erection of gabions at Karatu road | To implement erection of gabions at karatu road for road connectivity and accessibility | Erection of gabions at Karatu road completed | 3110599 | Other Infrastructure and Civil Works | Naivasha | Maai Mahiu | -1.007981, 36.522231 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 857033 | 857033 | Equitable | N/A | 857033 | 0 | 857034 | 100 | 857034 | 857033 | -1 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs bush clearing and maintenance.
2023 | Infrastructure, Development and Maintenance | Erection of gabions at Longonot Kiambogo road | To implement erection of gabions at longonot kiambogo road for road connectivity and accessibility | Erection of gabions at Longonot Kiambogo road completed | 3110599 | Other Infrastructure and Civil Works | Naivasha | Maai Mahiu | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 856672 | 856672 | Equitable | N/A | 856672 | 0 | 856672 | 100 | 856672 | 856672 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2024 | Infrastructure, Development and Maintenance | Rock filling and gabions on Munengi road landslide at Longonot | To implement rock filling and gabions on munengi road landslide at longonot for road connectivity and accessibility | Rock filling and gabions on Munengi road landslide at Longonot completed | 3110599 | Other Infrastructure and Civil Works | Naivasha | Maai Mahiu | -0.91047, 36.525415 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1305680 | 1305680 | Equitable | N/A | 1305680 | 0 | 1305680 | 100 | 1305680 | 1305680 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Project yet to start.
2025 | Infrastructure, Development & Maintenance | Drainage and culverts for Maai Mahiu Roads | To implement drainage and culverts for maai mahiu roads for road connectivity and accessibility | Drainage and culverts for Maai Mahiu Roads completed | 3110599 | Other Infrastructure and Civil Works | Naivasha | Maai Mahiu | -0.980223, 36.587151 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 1932328 | 1932328 | Equitable | N/A | 1932328 | 0 | 4817870 | 249.3 | 4817870 | 1932328 | -2885542 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Needs unclogging and maintenance.
2026 | Infrastructure, Development and Maintenance | Drainage cleaning and bush clearing in Malewa West Ward | To implement drainage cleaning and bush clearing in malewa west ward for road connectivity and accessibility | Drainage cleaning and bush clearing in Malewa West Ward completed | 3110599 | Other Infrastructure and Civil Works | Gilgil | Malewa West | -0.648649 36.488825 0 2000 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
2027 | Infrastructure, Development and Maintenance | Installation of culverts, drifts, footpaths & gabions in Malewa West ward | To install culverts, drifts, footpaths & gabions in Malewa West ward | Culverts, drifts, footpaths & gabions in Malewa West ward installed | 3110599 | Other Infrastructure and Civil Works | Gilgil | Malewa West | -0.684685, 36.471073 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | Yet to start | 3200000 | 2500000 | 3200000 | Equitable | N/A | 3200000 | 0 | 0 | 0 | 0 | 500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Will once delivered. Viable: Will once delivered. Assessor remarks: Yet to start.
2028 | Installation of culverts at Tummo quarry and Osama area | Installation of culverts at Tummo quarry and Osama area | To improve drainage and road access through culvert installation at Tummo quarry and Osama area | Culverts installed at Tummo quarry and Osama area | 3110599 | Other Infrastructure and Civil Works | Molo | Mariashoni | -0.336442, 35.883617 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 800000 | 5255 | 5255 | Equitable | N/A | 5255 | 0 | 5255 | 100 | 5255 | 5255 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Very good.
2029 | Infrastructure, Development and Maintenance | Installation of Segut river culvert | To install Segut river culvert | Segut river culvert installed | 3110599 | Other Infrastructure and Civil Works | Molo | Mariashoni | -0.350329 35.870564 2396.2960449307725 16 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 800000 | 100 | 800000 | 800000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Working.
2030 | Infrastructure, Development & Maintenance | Installation Of Culvert Across The Ward | To improve drainage and road access through culvert installation at Across The Ward | Culverts installed at Across The Ward | 3110599 | Other Infrastructure and Civil Works | Njoro | Mauche | -0.516872, 35.961768 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2022 | 1000000 | 938904 | 938904 | Equitable | N/A | 938904 | 0 | 938904 | 100 | 938904 | 938904 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Needs improvement.
2031 | Infrastructure, Development and Maintenance | Installation Of High mast Lights Within Mauche Ward and maintenance | To improve security lighting through high mast floodlight installation at Lights Within Mauche Ward and maintenance | High mast floodlight installed at Lights Within Mauche Ward and maintenance | 3110599 | Other Infrastructure and Civil Works | Njoro | Mauche | -0.512883, 35.99425 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023 | 1300000 | 0 | 568000 | Equitable | N/A | 568000 | 0 | 882000 | 100 | 882000 | 568000 | -882000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Needs repair.
2032 | Construction Of Bodaboda Sheds At Teacher And Kiratina | Construction Of Bodaboda Sheds At Teacher And Kiratina | To construct Bodaboda Sheds At Teacher And Kiratina | Bodaboda Sheds At Teacher And Kiratina constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Menengai | -0.266251, 36.100626 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 945221 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 642390 | 64.2 | 642390 | 1000000 | 357610 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Nop. Viable: No. Assessor remarks: Teachers shed is not there.
2033 | Infrastructure, Development & Maintenance | Construction Of Mariakani Teachers Stormwater Drainage Works | To construct Mariakani Teachers Stormwater Drainage Works | Mariakani Teachers Stormwater Drainage Works constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Menengai | -0.271371, 36.111308 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 5000000 | 4239.91 | 4239.91 | Equitable | N/A | 4239.91 | 0 | 4303910 | 101509.5 | 4303910 | 4240 | -4299670.09 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
2034 | Infrastructure, Development & Maintenance | Drainage And Bush Clearing In Menengai Ward | To implement drainage and bush clearing in menengai ward for road connectivity and accessibility | Drainage And Bush Clearing In Menengai Ward completed | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Menengai | -0.269616, 36.103414 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 882400 | 882400 | Equitable | N/A | 882400 | 0 | 787096 | 89.2 | 787096 | 95304 | 95304 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need to be done another bush clearing.
2035 | Infrastructure, Development and Maintenance | Routine Maintenance - Drainage cleaning and culverts opening in Menengai Ward | To maintain - Drainage cleaning and culverts opening in Menengai Ward in serviceable condition | - Drainage cleaning and culverts opening in Menengai Ward maintained | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Menengai | -0.279515, 36.122436 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 800000 | 560530 | 560530 | Equitable | N/A | 560530 | 0 | 560530 | 100 | 560530 | 560530 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
2036 | Infrastructure, Development and Maintenance | Clearing Of Culverts/drainages and Bush Clearing-labour based (Community Based Organizations) | To implement clearing of culverts/drainages and bush clearing-labour based (community based organizations) for road connectivity and accessibility | Clearing Of Culverts/drainages and Bush Clearing-labour based (Community Based Organizations) completed | 3110599 | Other Infrastructure and Civil Works | Rongai | Menengai West | -0.156467 36.000582 1898.9 26 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: EMHECH. Assessor remarks: Awaiting lab testing.
2037 | Infrastructure, Development and Maintenance | Construction of drainage and culverts at Kenyatta Estate | To construct drainage and culverts at Kenyatta Estate | Drainage and culverts at Kenyatta Estate constructed | 3110599 | Other Infrastructure and Civil Works | Molo | Molo Central | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
2038 | Infrastructure, Development and Maintenance | Installation of Tayari West culverts | To install Tayari West culverts | Tayari West culverts installed | 3110599 | Other Infrastructure and Civil Works | Molo | Molo Central | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 1500000 | 1390300 | 1390300 | Equitable | N/A | 1390300 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
2039 | Infrastructure, Development and Maintenance | Construction and repairing of Salgaa drainages | To construct and repairing of Salgaa drainages | And repairing of Salgaa drainages constructed | 3110599 | Other Infrastructure and Civil Works | Rongai | Mosop | -0.206401, 35.848247 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2023 | 1240000 | 1239800 | 1239800 | Equitable | N/A | 1239800 | 0 | 3727314 | 300.6 | 3727314 | 1239800 | -2487514 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: M/s vesta. Assessor remarks: Good work.
2040 | Infrastructure, Development & Maintenance | Gravelling, dozing and back filling of Kahuho Bridge | To implement gravelling, dozing and back filling of kahuho bridge for road connectivity and accessibility | Gravelling, dozing and back filling of Kahuho Bridge completed | 3110599 | Other Infrastructure and Civil Works | Gilgil | Murindat | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 2453350 | 245.3 | 2453350 | 1000000 | -1453350 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
2041 | Rehabilitation Of Drainage At Free Area Market | Rehabilitation Of Drainage At Free Area Market | To rehabilitate Drainage At Free Area Market to restore functionality | Drainage At Free Area Market rehabilitated | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Nakuru East | -0.293118, 36.120055 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/2020 | 2000000 | 1715073 | 1715073 | Equitable | N/A | 1715073 | 0 | 1711252 | 99.8 | 1711252 | 1715073 | 3821 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Jomikoka construction limited. Assessor remarks: Extension needed.
2042 | Installation Of Culverts Across Nessuit Ward | Installation Of Culverts Across Nessuit Ward | To improve drainage and road access through culvert installation at Across Nessuit Ward | Culverts installed at Across Nessuit Ward | 3110599 | Other Infrastructure and Civil Works | Njoro | Nessuit | -0.369043, 35.898225 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 1797420 | 1797420 | Equitable | N/A | 1797420 | 0 | 1794420 | 99.8 | 1794420 | 1797420 | 3000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: The culverts need unclogging.
2043 | Infrastructure, Development & Maintenance | Labourer For Bush Clearing And Drainage Works | To implement labourer for bush clearing and drainage works for road connectivity and accessibility | Labourer For Bush Clearing And Drainage Works completed | 3110599 | Other Infrastructure and Civil Works | Njoro | Nessuit | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2044 | Infrastructure, Development & Maintenance | Installation Of Culverts At Beeston Feeder Roads | To improve drainage and road access through culvert installation at Beeston Feeder Roads | Culverts installed at Beeston Feeder Roads | 3110599 | Other Infrastructure and Civil Works | Njoro | Njoro | -0.366398, 35.907184 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2022 | 1300000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 0 | 0 | 0 | 1300000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: In good state.
2045 | Infrastructure, Development and Maintenance | Construction Of A Drainage At Matunguru In Mwariki | To construct A Drainage At Matunguru In Mwariki | A Drainage At Matunguru In Mwariki constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Rhonda | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1930720 | 96.5 | 1930720 | 2000000 | 69280 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2046 | Infrastructure, Development and Maintenance | Construction Of Drainage In Top Ten-Ponda Mali | To construct Drainage In Top Ten-Ponda Mali | Drainage In Top Ten-Ponda Mali constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Rhonda | -0.306746, 36.064687 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 22/23 | 2670451 | 2670451 | 2670451 | Equitable | N/A | 2670451 | 0 | 2200258 | 82.4 | 2200258 | 2670451 | 470193 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: M/s Aimers. Assessor remarks: Needs rehabilitation.
2047 | Infrastructure, Development & Maintenance | Construction Of Drainage System Along Kwa Kahato Road | To construct Drainage System Along Kwa Kahato Road | Drainage System Along Kwa Kahato Road constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Rhonda | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 1597200 | 1597200 | Equitable | N/A | 1597200 | 0 | 1597200 | 100 | 1597200 | 1597200 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2048 | Infrastructure, Development & Maintenance | Construction Of Drainages Along Sewerage-Pcea Road | To construct Drainages Along Sewerage-Pcea Road | Drainages Along Sewerage-Pcea Road constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Rhonda | -0.316155, 36.062155 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 21/22 | 2000000 | 1534800 | 1534800 | Equitable | N/A | 1534800 | 0 | 1534800 | 100 | 1534800 | 1534800 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ms Aimers construction ltd. Assessor remarks: Complete.
2049 | Infrastructure, Development and Maintenance | Construction of storm water drainage along Bulldog, KK to Kwa Munene Area, along Takataka to Kwazi Area near Mwariki Secondary School and along Kipanga Way -Top Ten road | To construct storm water drainage along Bulldog, KK to Kwa Munene Area, along Takataka to Kwazi Area near Mwariki Secondary School and along Kipanga Way -Top Ten road | Storm water drainage along Bulldog, KK to Kwa Munene Area, along Takataka to Kwazi Area near Mwariki Secondary School and along Kipanga Way -Top Ten road constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Rhonda | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 12050000 | 4629828.7 | 4629828.7 | Equitable | N/A | 4629828.7 | 0 | 4626345 | 99.9 | 4626345 | 3484 | 3483.7 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2050 | Infrastructure, Development and Maintenance | Drainages At Mwariki, Lake Area | To implement drainages at mwariki, lake area for road connectivity and accessibility | Drainages At Mwariki, Lake Area completed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Rhonda | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 1700328 | 1700328 | Equitable | N/A | 1700328 | 0 | 1700328 | 100 | 1700328 | 1700328 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2051 | Infrastructure, Development and Maintenance | Cabro Paving At Shaabab Market | To implement cabro paving at shaabab market for road connectivity and accessibility | Cabro Paving At Shaabab Market completed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Shabab | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 2774426 | 2614300 | 2614300 | Equitable | N/A | 2614300 | 0 | 2614300 | 100 | 2614300 | 2614300 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
2052 | Construction Of A Drainage System At Githima | Construction Of A Drainage System At Githima | To construct A Drainage System At Githima | A Drainage System At Githima constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Shabab | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 1991450 | 1991450 | Equitable | N/A | 1991450 | 0 | 1988303 | 99.8 | 1988303 | 1991450 | 3147 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2053 | Construction Of Drainage Systems At Gilanis Estate | Construction Of Drainage Systems At Gilanis Estate | To construct Drainage Systems At Gilanis Estate | Drainage Systems At Gilanis Estate constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Shabab | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 1967.1 | 1967.1 | Equitable | N/A | 1967.1 | 0 | 1996713 | 101505.4 | 1996713 | 1967 | -1994745.9 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2054 | Infrastructure, Development and Maintenance | Covering Of Drainages from Empolos Hotel to Happy Church | To implement covering of drainages from empolos hotel to happy church for road connectivity and accessibility | Covering Of Drainages from Empolos Hotel to Happy Church completed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Shabab | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1895460 | 94.8 | 1895460 | 104540 | 104540 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
2055 | Infrastructure, Development and Maintenance | Drainage Construction & Murraming at Gilani Estate | To implement drainage construction & murraming at gilani estate for road connectivity and accessibility | Drainage Construction & Murraming at Gilani Estate completed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Shabab | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 2500000 | 0 | 2500000 | Equitable | N/A | 2500000 | 0 | 1996713 | 100 | 1996713 | 2500000 | -1996713 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
2056 | Infrastructure, Development and Maintenance | Drainage System At Mariakani Road | To implement drainage system at mariakani road for road connectivity and accessibility | Drainage System At Mariakani Road completed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Shabab | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 3022758 | 2839600 | 2839600 | Equitable | N/A | 2839600 | 0 | 2839444 | 100 | 2839444 | 2839600 | 156 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
2057 | Infrastructure, Development and Maintenance | Drainage Works At Lokichar Road | To implement drainage works at lokichar road for road connectivity and accessibility | Drainage Works At Lokichar Road completed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Shabab | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 2500000 | 2265900 | 2265900 | Equitable | N/A | 2265900 | 0 | 2265900 | 100 | 2265900 | 2265900 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
2058 | Infrastructure, Development and Maintenance | Drainage Works At Sondu Drive | To implement drainage works at sondu drive for road connectivity and accessibility | Drainage Works At Sondu Drive completed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Shabab | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | N/A | 2600000 | 2315000 | 2315000 | Equitable | N/A | 2315000 | 0 | 2315000 | 100 | 2315000 | 2315000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
2059 | Infrastructure, Development and Maintenance | Maintenance Of Drainage Systems in Shabab Ward | To implement maintenance of drainage systems in shabab ward for road connectivity and accessibility | Maintenance Of Drainage Systems in Shabab Ward completed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Shabab | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1987956 | 99.4 | 1987956 | 12044 | 12044 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
2060 | Infrastructure, Development and Maintenance | Rehabilitation Of Drainage Along John Momanyi Road | To rehabilitate Drainage Along John Momanyi Road to restore functionality | Drainage Along John Momanyi Road rehabilitated | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Shabab | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | N/A | 2460785 | 2459954 | 2459954 | Equitable | N/A | 2459954 | 0 | 2459954 | 100 | 2459954 | 2459954 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
2061 | Infrastructure, Development and Maintenance | Unblocking Of Drainage System In Shabab Ward | To implement unblocking of drainage system in shabab ward for road connectivity and accessibility | Unblocking Of Drainage System In Shabab Ward completed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Shabab | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1987956 | 198.8 | 1987956 | 1000000 | -987956 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
2062 | Infrastructure, Development & Maintenance | Construction of 2 boda boda sheds | To construct 2 boda boda sheds | 2 boda boda sheds constructed | 3110599 | Other Infrastructure and Civil Works | Rongai | Soin | -0.027512, 35.965663 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | FY 2024 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 1398960 | 233.2 | 1398960 | 600000 | -798960 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The area needs more boda boda sheds.
2063 | Infrastructure, Development and Maintenance | Construction Of Boda-Boda Sheds at Magomano, Kamothai and Kahatia | To construct Boda-Boda Sheds at Magomano, Kamothai and Kahatia | Boda-Boda Sheds at Magomano, Kamothai and Kahatia constructed | 3110599 | Other Infrastructure and Civil Works | Subukia | Subukia | -0.028661, 36.20545 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/2024 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1394100 | 92.9 | 1394100 | 105900 | 105900 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: Requires routine maintenance works.
2064 | Construction Of Culverts At Morro, Arash And Munanda | Construction Of Culverts At Morro, Arash And Munanda | To construct Culverts At Morro, Arash And Munanda | Culverts At Morro, Arash And Munanda constructed | 3110599 | Other Infrastructure and Civil Works | Subukia | Subukia | -0.00903, 36.209893 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2017/2018 | 500000 | 498650 | 498650 | Equitable | N/A | 498650 | 0 | 497035 | 99.7 | 497035 | 498650 | 1615 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: Requires Continuous maintenance works.
2065 | Infrastructure, Development & Maintenance | Culverts installation across the ward | To implement culverts installation across the ward for road connectivity and accessibility | Culverts installation across the ward completed | 3110599 | Other Infrastructure and Civil Works | Subukia | Subukia | -0.017646, 36.205878 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2022 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 988034 | 164.7 | 988034 | 600000 | -388034 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes.. Viable: Yes. The culvert drains water along the road.. Contractor: Information not known. Assessor remarks: The culvert is good..
2066 | Infrastructure, Development and Maintenance | Installation of culverts | To install culverts | Culverts installed | 3110599 | Other Infrastructure and Civil Works | Subukia | Subukia | -0.030927 36.197108 2206.2999999999997 20 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 897300 | 89.7 | 897300 | 11966 | 102700 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: 1 classroom constructed.
2067 | Infrastructure, Development and Maintenance | Installation of culverts across the ward | To improve drainage and road access through culvert installation at across the ward | Culverts installed at across the ward | 3110599 | Other Infrastructure and Civil Works | Molo | Turi | -0.258725, 35.735055 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 0 | 1999909.6 | Equitable | N/A | 1999909.6 | 0 | 800000 | 100 | 800000 | 1999910 | -800000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The culverts are blocked, they require drain cleaning and installation of large ones due to the large volume of water that flows downstream.
2068 | Infrastructure, Development & Maintenance | Installation of culverts and construction of drainage system at Kiambu | To improve drainage and road access through culvert installation at and construction of drainage system at Kiambu | Culverts installed at and construction of drainage system at Kiambu | 3110599 | Other Infrastructure and Civil Works | Molo | Turi | -0.309382 35.7569 2571.8 10.300000190734863 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 0 | 0 | 0 | 600000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good.
2069 | Infrastructure, Development and Maintenance | Installation of culverts across Turi ward | To improve drainage and road access through culvert installation at across Turi ward | Culverts installed at across Turi ward | 3110599 | Other Infrastructure and Civil Works | Molo | Turi | -0.258725, 35.735055 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 800000 | 100 | 800000 | 800000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The culverts are blocked, they require drain cleaning and installation of large ones due to the large volume of water that flows downstream.
2070 | Infrastructure, Development and Maintenance | Construction Of Drainage at Rongai Centre | To construct Drainage at Rongai Centre | Drainage at Rongai Centre constructed | 3110599 | Other Infrastructure and Civil Works | Rongai | Visoi | -0.174653 35.862943 1864.9000244140625 43.0989990234375 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 859617 | 86 | 859617 | 140383 | 140383 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need rehabilitation.
2071 | Infrastructure, Development and Maintenance | Installation of streetlights at Shalom B | To improve lighting and safety through installation of solar streetlights at Shalom B | Solar streetlights installed at Shalom B | 3110599 | Other Infrastructure and Civil Works | Rongai | Visoi | -0.174145 35.861612 1863.5 19.7450008392334 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | N/A | 950000 | 0 | 950000 | Equitable | N/A | 950000 | 0 | 599800 | 100 | 599800 | 599800 | -599800 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Not working,need repair.
2072 | Infrastructure, Development and Maintenance | Purchase and installation of culverts in Visoi ward | To procure and install culverts in Visoi ward | Culverts in Visoi ward procured and installed | 3110599 | Other Infrastructure and Civil Works | Rongai | Visoi | -0.148545 35.873142 1880.4 14.699999809265137 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 1800000 | 1794000 | 1794000 | Equitable | N/A | 1794000 | 0 | 1793970 | 100 | 1793970 | 1794000 | 30 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
2073 | Infrastructure, Development & Maintenance | Concrete paving works at Ogilgei-Bata Moja road 4 KM | To implement concrete paving works at ogilgei-bata moja road 4 km for road connectivity and accessibility | Concrete paving works at Ogilgei-Bata Moja road 4 KM completed | 3110599 | Other Infrastructure and Civil Works | Subukia | Waseges | 0.156432 36.259922 1711 20.299999237060547 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3998360 | 100 | 3998360 | 0 | 1640 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs Maintenance.
2074 | Infrastructure, Development & Maintenance | Concrete paving works at Wei center 600 M, Kahuti police 100 M, Nyama choma 100M and Gwa Gakombo 200 M | To implement concrete paving works at wei center 600 m, kahuti police 100 m, nyama choma 100m and gwa gakombo 200 m for road connectivity and accessibility | Concrete paving works at Wei center 600 M, Kahuti police 100 M, Nyama choma 100M and Gwa Gakombo 200 M completed | 3110599 | Other Infrastructure and Civil Works | Subukia | Waseges | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 1271100 | 1271100 | 1271100 | Equitable | N/A | 1271100 | 0 | 1271100 | 100 | 1271100 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2075 | Infrastructure, Development & Maintenance | Installation of Culvert and back filling at Kwa Soi, Kwa Wamartin, Gathima, Chania primary school, Kwa Kahindi area, AIC area Ngamini and Kwa Wa Muchori area, Mwireri primary and Wei shopping centre in Waseges Ward | To improve drainage and road access through culvert installation at and back filling at Kwa Soi, Kwa Wamartin, Gathima, Chania primary school, Kwa Kahindi area, AIC area Ngamini and Kwa Wa Muchori area, Mwireri primary and Wei shopping centre in Waseges Ward | Culverts installed at and back filling at Kwa Soi, Kwa Wamartin, Gathima, Chania primary school, Kwa Kahindi area, AIC area Ngamini and Kwa Wa Muchori area, Mwireri primary and Wei shopping centre in Waseges Ward | 3110599 | Other Infrastructure and Civil Works | Subukia | Waseges | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2076 | Infrastructure, Development & Maintenance | Laying Of Culverts At Academy ,Kwa Ngori Road | To implement laying of culverts at academy ,kwa ngori road for road connectivity and accessibility | Laying Of Culverts At Academy ,Kwa Ngori Road completed | 3110599 | Other Infrastructure and Civil Works | Subukia | Waseges | 0.08815 36.229812 1777.6 13.199999809265137 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 861835 | 776725 | 776725 | Equitable | N/A | 776725 | 0 | 776725 | 100 | 776725 | 776725 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The toilets is in use.
2077 | Infrastructure, Development and Maintenance | Rehabilitation and repair of County machinery | To rehabilitate repair of County machinery to restore functionality | Repair of County machinery rehabilitated | 3111201 | Overhaul of Plant, Machinery and Equipment | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | N/A | 10479203 | 3294203.1 | 3294203.1 | Equitable | N/A | 3294203.1 | 0 | 4414833 | 134 | 4414833 | 85167 | -1120629.9 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
2078 | Infrastructure, Development and Maintenance | Rehabilitation of hydraulic lift maintenance vehicle | To rehabilitate hydraulic lift maintenance vehicle to restore functionality | Hydraulic lift maintenance vehicle rehabilitated | 3111299 | Rehabilitation & Renovation - | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2024/25 | 2024/25 | 2024/25 | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 4414833 | 0 | 4414833 | 85167 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2079 | Infrastructure, Development and Maintenance | Rehabilitation of plants and equipment | To rehabilitate plants and equipment to restore functionality | Plants and equipment rehabilitated | 3111299 | Rehabilitation & Renovation - | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2024/25 | 2024/25 | 15000000 | 54424000 | 59695862.05 | Equitable | N/A | 59695862.05 | 0 | 4000000 | 7.3 | 4000000 | 5271862 | 50424000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2080 | Infrastructure, Development and Maintenance | Rehabilitation of Street Lights - Purchase of Street Lights Maintenance equipment for London Ward | To rehabilitate Street Lights - Purchase of Street Lights Maintenance equipment for London Ward to restore functionality | Street Lights - Purchase of Street Lights Maintenance equipment for London Ward rehabilitated | 3111299 | Rehabilitation & Renovation - | Nakuru West | London | -0.280902 36.05904 1852.5 7.5 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 500000 | 100 | 500000 | 500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functioning.
2081 | Infrastructure, Development and Maintenance | Maintenance And Installation Of 5 Floodlights | To implement maintenance and installation of 5 floodlights for road connectivity and accessibility | Maintenance And Installation Of 5 Floodlights completed | 3111299 | Rehabilitation & Renovation - | Naivasha | Maai Mahiu | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 2200000 | 0 | 1047500 | Equitable | N/A | 1047500 | 0 | 1152500 | 100 | 1152500 | 1047500 | -1152500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2082 | Infrastructure, Development and Maintenance | Highmast for Mbaruk | To implement highmast for mbaruk for road connectivity and accessibility | Highmast for Mbaruk completed | 3111504 | N/A | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2083 | Infrastructure, Development & Maintenance | Installation of highmast streetlights across the County | To improve security lighting through high mast floodlight installation at streetlights across the County | High mast floodlight installed at streetlights across the County | 3111504 | N/A | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 20000000 | 9793000 | 9793000 | Equitable | N/A | 9793000 | 0 | 9793000 | 100 | 9793000 | 9793000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2084 | Infrastructure, Development and Maintenance | Replacement of conventional light with LED Lights/Solar Lights | To implement replacement of conventional light with led lights/solar lights for road connectivity and accessibility | Replacement of conventional light with LED Lights/Solar Lights completed | 3111504 | N/A | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 6000000 | 1643700 | 1643700 | Equitable | N/A | 1643700 | 0 | 1643700 | 100 | 1643700 | 1643700 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2085 | Infrastructure, Development & Maintenance | Gravelling and murraming and culvert installation of Maai Mahiu / longonot access roads | To implement gravelling and murraming and culvert installation of maai mahiu / longonot access roads for road connectivity and accessibility | Gravelling and murraming and culvert installation of Maai Mahiu / longonot access roads completed | 3111504 | N/A | Naivasha | Maai Mahiu | -1.016438, 36.622719 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | N/A | 5000000 | 1014928 | 1014928 | Equitable | N/A | 1014928 | 0 | 985072 | 97.1 | 985072 | 1014928 | 29856 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yea. Viable: Yea. Assessor remarks: Complete.
2086 | Infrastructure, Development & Maintenance | Installation Of Barut Centre Highmast Streetlights | To install Barut Centre Highmast Streetlights | Barut Centre Highmast Streetlights installed | 4130299 | N/A | Nakuru West | Barut | -0.32425 36.4568 0 2000 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 1933050 | 1933050 | Equitable | N/A | 1933050 | 0 | 1933050 | 100 | 1933050 | 1933050 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M.s Topal Enterprises. Assessor remarks: In good state of repair.
2087 | Infrastructure, Development & Maintenance | Installation Of Mwariki Muungano Streetlights | To install Mwariki Muungano Streetlights | Mwariki Muungano Streetlights installed | 4130299 | N/A | Nakuru West | Barut | -0.3424 36.042 0 2000 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 1600000 | 1599000 | 1599000 | Equitable | N/A | 1599000 | 0 | 1599000 | 100 | 1599000 | 1599000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Some are functional.
2088 | Infrastructure, Development and Maintenance | Installation of high mast streetlighting | To improve security lighting through high mast floodlight installation at streetlighting | High mast floodlight installed at streetlighting | 4130299 | N/A | Nakuru East | Biashara-Nakuru | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1500000 | 150 | 1500000 | 1000000 | -500000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2089 | Infrastructure, Development & Maintenance | Purchase and installation of culverts in Githioro / Mugwathi access roads | To procure and install culverts in Githioro / Mugwathi access roads | Culverts in Githioro / Mugwathi access roads procured and installed | 4130299 | N/A | Bahati | Dundori | -0.237125, 36.167581 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/2016 | 106553.03 | 106553.03 | 106553.03 | Equitable | N/A | 106553.03 | 0 | 106553 | 100 | 106553 | 106553 | 0.03 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition, require maintenance.
2090 | Infrastructure, Development & Maintenance | Grading and Murraming of Gema Kamathatha - Nagum road-Eburru/Mbaruk Ward in Gilgil Sub County | To improve road infrastructure by grading and murraming Gema Kamathatha - Nagum road-Eburru/Mbaruk Ward in Gilgil Sub County | Gema Kamathatha - Nagum road-Eburru/Mbaruk Ward in Gilgil Sub County graded and murramed | 4130299 | N/A | Gilgil | Eburru/Mbaruk | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 1999950 | 1283694.85 | 1283694.85 | Equitable | N/A | 1283694.85 | 0 | 1168647 | 91 | 1168647 | 1283695 | 115047.85 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2091 | Grading and Murraming of Highway - Mbaruk Road | Grading and Murraming of Highway - Mbaruk Road | To improve road infrastructure by grading and murraming Highway - Mbaruk Road | Highway - Mbaruk Road graded and murramed | 4130299 | N/A | Gilgil | Eburru/Mbaruk | -0.267019, 36.193393 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 20/21 | 1400000 | 1400000 | 1400000 | Equitable | N/A | 1400000 | 0 | 1351440 | 96.5 | 1351440 | 1400000 | 48560 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Unspecified. Assessor remarks: Need rehabilitation.
2092 | Infrastructure, Development & Maintenance | Grading and Murraming of Morgen to Muraimo Road | To improve road infrastructure by grading and murraming Morgen to Muraimo Road | Morgen to Muraimo Road graded and murramed | 4130299 | N/A | Gilgil | Eburru/Mbaruk | -0.616511, 36.2546 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2019/20 | 2019/20 | 21-22 | 1998220 | 1893450 | 1893450 | Equitable | N/A | 1893450 | 0 | 1893424 | 100 | 1893424 | 1893450 | 26 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Partially. Viable: Yes. Contractor: Unspecified. Assessor remarks: Bad state of road.
2093 | Routine Maintenance and Spot Improvement of Matuiku Estate Roads in Elburgon Ward Molo Sub County | Routine Maintenance and Spot Improvement of Matuiku Estate Roads in Elburgon Ward Molo Sub County | To maintain Spot Improvement of Matuiku Estate Roads in Elburgon Ward Molo Sub County in serviceable condition | Spot Improvement of Matuiku Estate Roads in Elburgon Ward Molo Sub County maintained | 4130299 | N/A | Molo | Elburgon | -0.302023, 35.813376 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | - | 1500000 | 1499000 | 1499000 | Equitable | N/A | 1499000 | 0 | 1298411 | 86.6 | 1298411 | 200589 | 200589 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
2094 | Grading and sport gravelling of Tee - Munyaka -Meli- hakajane (2015/2016) | Grading and sport gravelling of Tee - Munyaka -Meli- hakajane (2015/2016) | To improve road accessibility by grading and sport gravelling of Tee - Munyaka -Meli- hakajane (2015/2016) | And sport gravelling of Tee - Munyaka -Meli- hakajane (2015/2016) graded | 4130299 | N/A | Gilgil | Elementaita | -0.658063, 36.11461 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2997152 | 99.9 | 2997152 | 3000000 | 2848 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes but maintanance needed. Viable: Yes. Assessor remarks: Needs renovation.
2095 | Infrastructure, Development & Maintenance | Grading and spot improvement of Makongo - Kifanya / Njunge and Munanda depression culverts (2015/16) | To improve road accessibility by grading and spot improvement of Makongo - Kifanya / Njunge and Munanda depression culverts (2015/16) | And spot improvement of Makongo - Kifanya / Njunge and Munanda depression culverts (2015/16) graded | 4130299 | N/A | Gilgil | Elementaita | -0.583917 36.112665 2077.4 5 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 3600000 | 2847.8 | 2847.8 | Equitable | N/A | 2847.8 | 0 | 3596052 | 126274.7 | 3596052 | 2848 | -3593204.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
2096 | Infrastructure, Development & Maintenance | Construction of Appropriate Technology Bridges and Prevention of Soil Erosion in Maai - Mahiu in Naivasha Sub County | To construct Appropriate Technology Bridges and Prevention of Soil Erosion in Maai - Mahiu in Naivasha Sub County | Appropriate Technology Bridges and Prevention of Soil Erosion in Maai - Mahiu in Naivasha Sub County constructed | 4130299 | N/A | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | N/A | 2547151.2 | 2547151.2 | 2547151.2 | Equitable | N/A | 2547151.2 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
2097 | Construction of Kio bridge in Kihingo ward | Construction of Kio bridge in Kihingo ward | To construct Kio bridge in Kihingo ward | Kio bridge in Kihingo ward constructed | 4130299 | N/A | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 6978545 | 697.9 | 6978545 | 4000000 | -5978545 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
2098 | Infrastructure, Development & Maintenance | Improvement of Mashambani Matatu Stage in Biashara Ward in Nakuru East Sub county | To implement improvement of mashambani matatu stage in biashara ward in nakuru east sub county for road connectivity and accessibility | Improvement of Mashambani Matatu Stage in Biashara Ward in Nakuru East Sub county completed | 4130299 | N/A | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | N/A | 4706955 | 4706955 | 4706955 | Equitable | N/A | 4706955 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
2099 | Infrastructure, Development & Maintenance | Installation of highmast streetlighting at Greenstead and Barnabas | To improve security lighting through high mast floodlight installation at streetlighting at Greenstead and Barnabas | High mast floodlight installed at streetlighting at Greenstead and Barnabas | 4130299 | N/A | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | N/A | 4000000 | 3808600 | 3808600 | Equitable | N/A | 3808600 | 0 | 9793000 | 257.1 | 9793000 | 9793000 | -5984400 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
2100 | Infrastructure, Development and Maintenance | Proposed construction and installation of Steel Pipes Culverts (AMCO) in different areas in Nakuru County:- | To undertake the proposed construction and installation of Steel Pipes Culverts (AMCO) in different areas in Nakuru County:- | Proposed construction and installation of Steel Pipes Culverts (AMCO) in different areas in Nakuru County:- implemented | 4130299 | N/A | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 750000 | 21560921 | 21560921 | Equitable | N/A | 21560921 | 0 | 18204565 | 84.4 | 18204565 | 0 | 3356356 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2101 | Infrastructure, Development & Maintenance | Proposed Construction of approach to Amalo River Bridge & Bridge Siera Leone (4.3m Single Span) in Amalo Ward Kuresoi South Sub County | To undertake the proposed Construction of approach to Amalo River Bridge & Bridge Siera Leone (4.3m Single Span) in Amalo Ward Kuresoi South Sub County | Proposed Construction of approach to Amalo River Bridge & Bridge Siera Leone (4.3m Single Span) in Amalo Ward Kuresoi South Sub County implemented | 4130299 | N/A | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | N/A | 4619070 | 1316020 | 1316020 | Equitable | N/A | 1316020 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
2102 | Infrastructure, Development & Maintenance | Proposed Routine Maintenance and Spot Improvement of Nyathuna - Quarry Road in Bahati Sub County | To undertake the proposed Routine Maintenance and Spot Improvement of Nyathuna - Quarry Road in Bahati Sub County | Proposed Routine Maintenance and Spot Improvement of Nyathuna - Quarry Road in Bahati Sub County implemented | 4130299 | N/A | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 4027926 | 860526 | 860526 | Equitable | N/A | 860526 | 0 | 5237600 | 608.7 | 5237600 | 5237600 | -4377074 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2103 | Infrastructure, Development & Maintenance | Proposed sectional constrution and completion of Fire Brigade station Lakeview ward in Naivasha Sub county | To undertake the proposed sectional constrution and completion of Fire Brigade station Lakeview ward in Naivasha Sub county | Proposed sectional constrution and completion of Fire Brigade station Lakeview ward in Naivasha Sub county implemented | 4130299 | N/A | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | N/A | 6029900 | 492788.4 | 492788.4 | Equitable | N/A | 492788.4 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
2104 | Infrastructure, Development and Maintenance | Replacement of conventional light with LED Lights/Solar Lights | To implement replacement of conventional light with led lights/solar lights for road connectivity and accessibility | Replacement of conventional light with LED Lights/Solar Lights completed | 4130299 | N/A | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 15000000 | 852509.2 | 852509.2 | Equitable | N/A | 852509.2 | 0 | 1643700 | 192.8 | 1643700 | 1643700 | -791190.8 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2105 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of:- Moi Road, Bus Park Frontage, Sera Centre, Karagita Bus Park and GWS Frontage in Naivasha Sub County | To maintain Spot Improvement of:- Moi Road, Bus Park Frontage, Sera Centre, Karagita Bus Park and GWS Frontage in Naivasha Sub County in serviceable condition | Spot Improvement of:- Moi Road, Bus Park Frontage, Sera Centre, Karagita Bus Park and GWS Frontage in Naivasha Sub County maintained | 4130299 | N/A | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 12169900 | 5237600 | 5237600 | Equitable | N/A | 5237600 | 0 | 5237600 | 100 | 5237600 | 5237600 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2106 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement :Tarmacking and Extension of Menengai Climb Road to Capital Hill Hotel (0.5km )in Nakuru East Sub County | To maintain Spot Improvement :Tarmacking and Extension of Menengai Climb Road to Capital Hill Hotel (0.5km )in Nakuru East Sub County in serviceable condition | Spot Improvement :Tarmacking and Extension of Menengai Climb Road to Capital Hill Hotel (0.5km )in Nakuru East Sub County maintained | 4130299 | N/A | HQ | HQ | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 10504000 | 10504000 | 10504000 | Equitable | N/A | 10504000 | 0 | 5237600 | 49.9 | 5237600 | 5237600 | 5266400 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2107 | Infrastructure, Development & Maintenance | Construction of motorbike sheds at Dispensary, BN Riders, Villa, Mwichiringiri and Karai | To construct motorbike sheds at Dispensary, BN Riders, Villa, Mwichiringiri and Karai | Motorbike sheds at Dispensary, BN Riders, Villa, Mwichiringiri and Karai constructed | 4130299 | N/A | Naivasha | Hells Gate | -0.796999, 36.434324 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2020/21 | 2020/21 | 2020/21 | 1800000 | 1141720 | 1141720 | Equitable | N/A | 1141720 | 0 | 1115760 | 97.7 | 1115760 | 1800000 | 25960 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project costed 1,141,720.
2108 | Installation of floodlights in Thayu, Mugetho, St John, Ngecha, Nyathuma primary,mirugi, junction, limuko corner, limuko centre, Mwaki Mugi sub location | Installation of floodlights in Thayu, Mugetho, St John, Ngecha, Nyathuma primary,mirugi, junction, limuko corner, limuko centre, Mwaki Mugi sub location | To install floodlights in Thayu, Mugetho, St John, Ngecha, Nyathuma primary,mirugi, junction, limuko corner, limuko centre, Mwaki Mugi sub location | Floodlights in Thayu, Mugetho, St John, Ngecha, Nyathuma primary,mirugi, junction, limuko corner, limuko centre, Mwaki Mugi sub location installed | 4130299 | N/A | Bahati | Kabatini | -0.222876, 36.1213 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2021 | 2520000 | 2404800 | 2404800 | Equitable | N/A | 2404800 | 0 | 2404500 | 100 | 2404500 | 2404800 | 300 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
2109 | Infrastructure, Development and Maintenance | Construction Of Maombi And Maringu Bridges And Installation Of Culverts At Kabazi Centre And Road Works Around Kabazi Ward | To construct Maombi And Maringu Bridges And Installation Of Culverts At Kabazi Centre And Road Works Around Kabazi Ward | Maombi And Maringu Bridges And Installation Of Culverts At Kabazi Centre And Road Works Around Kabazi Ward constructed | 4130299 | N/A | Subukia | Kabazi | -0.23853 35.86724 2237 0 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 5000000 | 3002074 | 3002074 | Equitable | N/A | 3002074 | 0 | 1757447 | 58.5 | 1757447 | 1209627 | 1244627 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: No details available. Assessor remarks: Requires additional ecd classroom, toilets and kitchen.
2110 | Infrastructure, Development & Maintenance | Design And Installation Highmast Streetlights At Kabazi, Solai And Kipngochoch | To implement design and installation highmast streetlights at kabazi, solai and kipngochoch for road connectivity and accessibility | Design And Installation Highmast Streetlights At Kabazi, Solai And Kipngochoch completed | 4130299 | N/A | Subukia | Kabazi | -0.152618, 36.074977 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2019/20 | 1500000 | 1497715 | 1497715 | Equitable | N/A | 1497715 | 0 | 1497715 | 100 | 1497715 | 1497715 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Well maintained.
2111 | Grading and levelling of Twinpik - Jogoo road | Grading and levelling of Twinpik - Jogoo road | To improve road accessibility by grading and levelling of Twinpik - Jogoo road | And levelling of Twinpik - Jogoo road graded | 4130299 | N/A | Kuresoi North | Kamara | -0.17825 35.711258 2501.3 4.5 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 1500000 | 8463.65 | 8463.65 | Equitable | N/A | 8463.65 | 0 | 1491536 | 17622.8 | 1491536 | 8464 | -1483072.35 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Unknown. Assessor remarks: Needs maintenance.
2112 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Maraba / Chesuvena /Sinedit Roads in Kamara Ward Kuresoi North Sub County | To maintain Spot Improvement of Maraba / Chesuvena /Sinedit Roads in Kamara Ward Kuresoi North Sub County in serviceable condition | Spot Improvement of Maraba / Chesuvena /Sinedit Roads in Kamara Ward Kuresoi North Sub County maintained | 4130299 | N/A | Kuresoi North | Kamara | -0.1583 35.693597 2533.000244140625 63.867000579833984 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2997672 | 2997672 | 2997672 | Equitable | N/A | 2997672 | 0 | 2997672 | 100 | 2997672 | 2997672 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Not indicated. Assessor remarks: Needs maintenance.
2113 | Infrastructure, Development and Maintenance | Grading and murraming of Cutline to Kibangui pri school road, Saptet polytechnic road to Daraja Mawe road, Kapsimbeiywo-Bondet road, Mosiat-Quarry-Bandiat road, Keringet-Bararget road, Tembwo-Tachasis road | To improve road infrastructure by grading and murraming Cutline to Kibangui pri school road, Saptet polytechnic road to Daraja Mawe road, Kapsimbeiywo-Bondet road, Mosiat-Quarry-Bandiat road, Keringet-Bararget road, Tembwo-Tachasis road | Cutline to Kibangui pri school road, Saptet polytechnic road to Daraja Mawe road, Kapsimbeiywo-Bondet road, Mosiat-Quarry-Bandiat road, Keringet-Bararget road, Tembwo-Tachasis road graded and murramed | 4130299 | N/A | Kuresoi South | Keringet | -0.303966, 36.082876 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 11600000 | 10802091 | 10802091 | Equitable | N/A | 10802091 | 0 | 10530782 | 97.5 | 10530782 | 10530782 | 271309 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Passable.
2114 | Infrastructure, Development & Maintenance | Routine Maintenance and Spot Improvement of Keringet - Kapkures - Tegat Road in Keringet Ward Kuresoi South Sub County | To maintain Spot Improvement of Keringet - Kapkures - Tegat Road in Keringet Ward Kuresoi South Sub County in serviceable condition | Spot Improvement of Keringet - Kapkures - Tegat Road in Keringet Ward Kuresoi South Sub County maintained | 4130299 | N/A | Kuresoi South | Keringet | -0.460018 35.694096 0 899.9990234375 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2993600 | 46349 | 46349 | Equitable | N/A | 46349 | 0 | 2947251 | 6358.8 | 2947251 | 46349 | -2900902 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
2115 | Infrastructure, Development & Maintenance | Murraming, Culverts Installation, Grading Heshima to Menengai Road (Kiamaina Roads) | To implement murraming, culverts installation, grading heshima to menengai road (kiamaina roads) for road connectivity and accessibility | Murraming, Culverts Installation, Grading Heshima to Menengai Road (Kiamaina Roads) completed | 4130299 | N/A | Bahati | Kiamaina | -0.242741 36.113229 1940.9000244140625 21.8700008392334 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2014/15 | 2014/15 | 2014/15 | 1237275 | 1237275 | 1237275 | Equitable | N/A | 1237275 | 0 | 1236769 | 100 | 1236769 | 1237275 | 506 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires marking.
2116 | Grading, Culverts and Murraming of Tiriyta Roads | Grading, Culverts and Murraming of Tiriyta Roads | To implement grading, culverts and murraming of tiriyta roads for road connectivity and accessibility | Grading, Culverts and Murraming of Tiriyta Roads completed | 4130299 | N/A | Kuresoi North | Kiptororo | -0.377203, 35.505747 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2490077 | 83 | 2490077 | 3000000 | 509923 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is passable.
2117 | Infrastructure, Development & Maintenance | Grading, Murraming and Culverts for Korongo - Motogir Road in Kiptororo Ward Kuresoi North Sub County | To implement grading, murraming and culverts for korongo - motogir road in kiptororo ward kuresoi north sub county for road connectivity and accessibility | Grading, Murraming and Culverts for Korongo - Motogir Road in Kiptororo Ward Kuresoi North Sub County completed | 4130299 | N/A | Kuresoi North | Kiptororo | -0.332747 35.570807 2661.2 16.100000381469727 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2497065.6 | 2480265 | 2480265 | Equitable | N/A | 2480265 | 0 | 2480265 | 100 | 2480265 | 2480265 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Regular maintenance is required.
2118 | Infrastructure, Development & Maintenance | Routine Maintenance , Spot Improvement and Culverts Installation for Araret / Tiriyta Road in Kiptororo Ward Kuresoi North Sub County | To maintain , Spot Improvement and Culverts Installation for Araret / Tiriyta Road in Kiptororo Ward Kuresoi North Sub County in serviceable condition | , Spot Improvement and Culverts Installation for Araret / Tiriyta Road in Kiptororo Ward Kuresoi North Sub County maintained | 4130299 | N/A | Kuresoi North | Kiptororo | -0.407175, 35.526648 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 3999854 | 3971350 | 3971350 | Equitable | N/A | 3971350 | 0 | 3971350 | 100 | 3971350 | 3971350 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Regular maintenance is required.
2119 | Infrastructure, Development & Maintenance | Routine Maintenance , Spot Improvement and Culverts Installation for Tulwet Road in Kiptororo Ward Kuresoi North Sub County | To maintain , Spot Improvement and Culverts Installation for Tulwet Road in Kiptororo Ward Kuresoi North Sub County in serviceable condition | , Spot Improvement and Culverts Installation for Tulwet Road in Kiptororo Ward Kuresoi North Sub County maintained | 4130299 | N/A | Kuresoi North | Kiptororo | -0.407175, 35.526648 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2998841.25 | 2970080 | 2970080 | Equitable | N/A | 2970080 | 0 | 2970080 | 100 | 2970080 | 2970080 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Regular maintenance is required.
2120 | Infrastructure, Development & Maintenance | Grading And Murraming Of Lare Zone D Road | To improve road infrastructure by grading and murraming Lare Zone D Road | Lare Zone D Road graded and murramed | 4130299 | N/A | Njoro | Lare | -0.476343, 36.033237 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2022 | 2400000 | 2389250 | 2389250 | Equitable | N/A | 2389250 | 0 | 2389250 | 100 | 2389250 | 2389250 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
2121 | Installation/Laying Of Cabro Blocks In London Ward Road Works | Installation/Laying Of Cabro Blocks In London Ward Road Works | To implement installation/laying of cabro blocks in london ward road works for road connectivity and accessibility | Installation/Laying Of Cabro Blocks In London Ward Road Works completed | 4130299 | N/A | Nakuru West | London | -0.273027, 36.05145 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 20000000 | 8250414 | 8250414 | Equitable | N/A | 8250414 | 0 | 7084874 | 85.9 | 7084874 | 1165540 | 1165540 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good job.
2122 | Infrastructure, Development and Maintenance | Routine Maintenance and Spot Improvement of Maai Mahiu Town Roads in Mai Mahiu Ward Naivasha Sub County | To maintain Spot Improvement of Maai Mahiu Town Roads in Mai Mahiu Ward Naivasha Sub County in serviceable condition | Spot Improvement of Maai Mahiu Town Roads in Mai Mahiu Ward Naivasha Sub County maintained | 4130299 | N/A | Naivasha | Maai Mahiu | -0.979368, 36.583679 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 3000000 | 1934900 | 1934900 | Equitable | N/A | 1934900 | 0 | 588924 | 30.4 | 588924 | 1934900 | 1345976 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good state, storm drains to be rennovated.
2123 | Grading and Murraming of Kaplabos - Kwa Jack Road | Grading and Murraming of Kaplabos - Kwa Jack Road | To improve road infrastructure by grading and murraming Kaplabos - Kwa Jack Road | Kaplabos - Kwa Jack Road graded and murramed | 4130299 | N/A | Molo | Mariashoni | -0.376959 35.790913 2793.112 0.71200001239771 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 979 | 979 | Equitable | N/A | 979 | 0 | 1997010 | 203984.7 | 1997010 | 979 | -1996031 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Access road good.
2124 | Infrastructure, Development and Maintenance | Routine Maintenance And Spot Improvement Of Sugutiek -Kamungei Road In Mau Narok Ward Njoro Sub County | To maintain Spot Improvement Of Sugutiek -Kamungei Road In Mau Narok Ward Njoro Sub County in serviceable condition | Spot Improvement Of Sugutiek -Kamungei Road In Mau Narok Ward Njoro Sub County maintained | 4130299 | N/A | Njoro | Mau Narok | -0.588187 36.013644 0 0 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2968440 | 1468430 | 1468430 | Equitable | N/A | 1468430 | 0 | 1468430 | 100 | 1468430 | 1468430 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: viable. Assessor remarks: good state of repair.
2125 | Infrastructure, Development & Maintenance | Gravelling , Compacting And Drainage And Murraming Of Olive Stage - Eden Road | To implement gravelling , compacting and drainage and murraming of olive stage - eden road for road connectivity and accessibility | Gravelling , Compacting And Drainage And Murraming Of Olive Stage - Eden Road completed | 4130299 | N/A | Rongai | Menengai West | -0.144707 36.007533 1806.5 56.099998474121094 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 2800000 | 2896590 | 2896590 | Equitable | N/A | 2896590 | 0 | 2674548 | 92.3 | 2674548 | 2896590 | 222042 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs improvement.
2126 | Infrastructure, Development and Maintenance | Installation Of Highmast Security Lights At Eden And Mercy Njeri | To improve security lighting through high mast floodlight installation at Security Lights At Eden And Mercy Njeri | High mast floodlight installed at Security Lights At Eden And Mercy Njeri | 4130299 | N/A | Rongai | Menengai West | -0.26736, 36.028102 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2023/24 | 6500000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 5475750 | 182.5 | 5475750 | 2825750 | -2475750 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
2127 | Infrastructure, Development & Maintenance | Design and construction of Kiarumbwa bridge | To design and construct Kiarumbwa bridge | Kiarumbwa bridge designed and constructed | 4130299 | N/A | Gilgil | Murindat | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | N/A | 2000000 | 11 | 11 | Equitable | N/A | 11 | 0 | 1999989 | 18181718.2 | 1999989 | 11 | -1999978 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
2128 | Infrastructure, Development & Maintenance | Roads Maintenance Within The Ward | To implement roads maintenance within the ward for road connectivity and accessibility | Roads Maintenance Within The Ward completed | 4130299 | N/A | Nakuru East | Nakuru East | -0.291608, 36.114337 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2018/19 | 2018/19 | 2018/2019 | 4000000 | 946472.6 | 946472.6 | Equitable | N/A | 946472.6 | 0 | 3058340 | 323.1 | 3058340 | 946473 | -2111867.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Glenwood construction limited. Assessor remarks: Project ok.
2129 | Infrastructure, Development & Maintenance | Grading And Murraming And Culverts Of Amos Arap Kangongo Road | To improve road infrastructure by grading and murraming And Culverts Of Amos Arap Kangongo Road | And Culverts Of Amos Arap Kangongo Road graded and murramed | 4130299 | N/A | Njoro | Nessuit | -0.415259, 35.949121 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2019/20 | 2000000 | 1999400 | 1999400 | Equitable | N/A | 1999400 | 0 | 1999400 | 100 | 1999400 | 1999400 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is a continuous from Amos Kangogo road, it is Amos -Amani road..
2130 | Infrastructure, Development & Maintenance | Routine Maintenance And Spot Improvement Of Kasa Roho - Mathias - Kamara Road In Nessuit Ward Njoro Sub County | To maintain Spot Improvement Of Kasa Roho - Mathias - Kamara Road In Nessuit Ward Njoro Sub County in serviceable condition | Spot Improvement Of Kasa Roho - Mathias - Kamara Road In Nessuit Ward Njoro Sub County maintained | 4130299 | N/A | Njoro | Nessuit | -0.416054, 35.949283 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2019/20 | 1000000 | 975212 | 975212 | Equitable | N/A | 975212 | 0 | 975149 | 100 | 975149 | 975212 | 63 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is motorable but requires regular maintenance.
2131 | Infrastructure, Development and Maintenance | Routine Maintenance and Spot Improvement of Cultural Centre - Nkorionito access road in Olkaria Ward Naivasha Sub County | To maintain Spot Improvement of Cultural Centre - Nkorionito access road in Olkaria Ward Naivasha Sub County in serviceable condition | Spot Improvement of Cultural Centre - Nkorionito access road in Olkaria Ward Naivasha Sub County maintained | 4130299 | N/A | Naivasha | Olkaria | -0.838224 36.362161 1883.0999755859375 11.142999649047852 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2994784 | 1322790 | 1322790 | Equitable | N/A | 1322790 | 0 | 1034800 | 78.2 | 1034800 | 287990 | 287990 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Solar light operational.
2132 | Infrastructure, Development & Maintenance | Installation Of Floodlights | To install Floodlights | Floodlights installed | 4130299 | N/A | Nakuru West | Rhonda | -0.30749, 36.065682 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 21/22 | 2000000 | 1649414 | 1649414 | Equitable | N/A | 1649414 | 0 | 5018500 | 304.3 | 5018500 | 1649414 | -3369086 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Needs rehabilitation.
2133 | Infrastructure, Development & Maintenance | Installation Of Highmast 20M At Gilanis, Pyrethrum And Ngei Estate | To improve security lighting through high mast floodlight installation at 20M At Gilanis, Pyrethrum And Ngei Estate | High mast floodlight installed at 20M At Gilanis, Pyrethrum And Ngei Estate | 4130299 | N/A | Nakuru West | Shabab | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | N/A | 4500000 | 4500000 | 4500000 | Equitable | N/A | 4500000 | 0 | 1996713 | 44.4 | 1996713 | 4500000 | 2503287 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
2134 | Infrastructure, Development & Maintenance | Design And Construction Of Bridge Connecting Arash And Kijabe And Murraming Of Lucia Moraa Connection Road | To design and construct Bridge Connecting Arash And Kijabe And Murraming Of Lucia Moraa Connection Road | Bridge Connecting Arash And Kijabe And Murraming Of Lucia Moraa Connection Road designed and constructed | 4130299 | N/A | Subukia | Subukia | 0.002262 36.227867 1993.800048828125 20.100000381469727 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2500000 | 100 | 2500000 | 2500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: The project has benefitted many learners. Viable: Yes. The project has been a learning facility to many learners. Contractor: Information not available. Assessor remarks: The classroom is in use, as well as latrines.
2135 | Infrastructure, Development & Maintenance | Routine Maintenance And Spot Improvement Of Lower Kimangu / Ex Butler Road Network In Visoi Ward Rongai Sub County | To maintain Spot Improvement Of Lower Kimangu / Ex Butler Road Network In Visoi Ward Rongai Sub County in serviceable condition | Spot Improvement Of Lower Kimangu / Ex Butler Road Network In Visoi Ward Rongai Sub County maintained | 4130299 | N/A | Rongai | Visoi | N/A | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2016/17 | 2016/17 | 2016/17 | 2800240 | 2800240 | 2800240 | Equitable | N/A | 2800240 | 0 | 2500000 | 89.3 | 2500000 | 2800240 | 300240 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2136 | Construction Of Ndatho Bridge Box Culvert 3.0Mx2.5X500 Long | Construction Of Ndatho Bridge Box Culvert 3.0Mx2.5X500 Long | To construct Ndatho Bridge Box Culvert 3.0Mx2.5X500 Long | Ndatho Bridge Box Culvert 3.0Mx2.5X500 Long constructed | 4130299 | N/A | Subukia | Waseges | 0.058923, 36.236265 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2014/15 | 2014/15 | 2014/15 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2494797 | 99.8 | 2494797 | 2500000 | 5203 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The bridge is in use and in good condition.
2137 | Infrastructure, Development & Maintenance | Grading And Murraming Of Limuru - St. Ulrich Road | To improve road infrastructure by grading and murraming Limuru - St. Ulrich Road | Limuru - St. Ulrich Road graded and murramed | 4130299 | N/A | Subukia | Waseges | 0.14589 36.242263 1696.7 9.300000190734863 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 1200000 | 1052100 | 1052100 | Equitable | N/A | 1052100 | 0 | 1051700 | 100 | 1051700 | 1052100 | 400 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs Maintenance.
2138 | Installation Of Waseges Ward Highmast Streetlighting | Installation Of Waseges Ward Highmast Streetlighting | To install Waseges Ward Highmast Streetlighting | Waseges Ward Highmast Streetlighting installed | 4130299 | N/A | Subukia | Waseges | 0.166308, 36.249808 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2015/16 | 2015/16 | 2015/16 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 900400 | 90 | 900400 | 1000000 | 99600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs maintenance.
2139 | Installation Of Waseges Highmast Streetlights | Installation Of Waseges Highmast Streetlights | To install Waseges Highmast Streetlights | Waseges Highmast Streetlights installed | 4130299 | N/A | Subukia | Waseges | 0.166308, 36.249808 | 4567 | INFRASTRUCTURE | INFRASTRUCTURE | N/A | 2017/18 | 2017/18 | 2017/18 | 1416745 | 1416744 | 1416744 | Equitable | N/A | 1416744 | 0 | 1404200 | 99.1 | 1404200 | 1416744 | 12544 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs maintenance.
2140 | Crop Development and Management | Agriculture Outstanding Contract Retention - development | To implement agriculture outstanding contract retention - development for agricultural development and food production | Agriculture Outstanding Contract Retention - development completed | 2211314 | Write Offs/ Bad Debt Expenses from Previous Years (Pending Bills) | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2022/23 | 2022/23 | 2022/23 | 3209833.36 | 3209833.36 | 3209833.36 | Equitable | Equitable | 3209833.36 | 0 | 1067000 | 33.2 | 1067000 | 0 | 2142833.36 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2141 | Crop Development and Management | Agricultural Sector Development Support Projects (ASDSP II) | To implement agricultural sector development support projects (asdsp ii) for agricultural development and food production | Agricultural Sector Development Support Projects (ASDSP II) completed | 2640503 | N/A | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 26343334 | 47743049.8 | 0 | ASDSP II | ASDSP II | 0 | 37168213.8 | 1083629 | 2.3 | 1083629 | 5252658 | 46659420.8 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2142 | Crop Development and Management | Agricultural Sector Development Support Projects (ASDSP) | To implement agricultural sector development support projects (asdsp) for agricultural development and food production | Agricultural Sector Development Support Projects (ASDSP) completed | 2640503 | N/A | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 14171667 | 893811 | 0 | ASDSP II | ASDSP II | 0 | 893811 | 197358 | 22.1 | 197358 | 696453 | 696453 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2143 | Crop Development and Management | Counterpart funding- Agricultural Sector Development Support Projects (ASDSP) | To implement counterpart funding- agricultural sector development support projects (asdsp) for agricultural development and food production | Counterpart funding- Agricultural Sector Development Support Projects (ASDSP) completed | 2640503 | N/A | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2022/23 | 2022/23 | 5500000 | 5500000 | 5500000 | ASDSP II | ASDSP II | 5500000 | 0 | 1500000 | 27.3 | 1500000 | 4500000 | 4000000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2144 | Crop Development and Management | Counterpart funding for Nakuru County Dairy Processing Plant: World Bank Co-Funded Community Driven project. | To implement counterpart funding for nakuru county dairy processing plant: world bank co-funded community driven project. for agricultural development and food production | Counterpart funding for Nakuru County Dairy Processing Plant: World Bank Co-Funded Community Driven project. completed | 2640503 | N/A | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2022/23 | 2022/23 | N/A | 120160115 | 15160115 | 15160115 | Equitable | Equitable | 15160115 | 0 | 0 | 0 | 0 | 17000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
2145 | Crop Development and Management | Counterpart funding- Nakuru Potato cold store: World Bank Funded Community Driven project | To implement counterpart funding- nakuru potato cold store: world bank funded community driven project for agricultural development and food production | Counterpart funding- Nakuru Potato cold store: World Bank Funded Community Driven project completed | 2640503 | N/A | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | N/A | 17000000 | 0 | 17000000 | Equitable | EQUITABLE | 17000000 | 0 | 0 | 0 | 0 | 17000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
2146 | Crop Development and Management | Counterpart funding- National Agricultural and Rural Inclusive Growth Projects (NARIGP) | To implement counterpart funding- national agricultural and rural inclusive growth projects (narigp) for agricultural development and food production | Counterpart funding- National Agricultural and Rural Inclusive Growth Projects (NARIGP) completed | 2640503 | N/A | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2022/23 | 2022/23 | 6500000 | 6500000 | 6500000 | NARIGP | NARIGP | 6500000 | 0 | 6500000 | 100 | 6500000 | 3910461 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2147 | Crop Development and Management | National Agricultural and Rural inclusive growth Projects (NARIGP) | To implement national agricultural and rural inclusive growth projects (narigp) for agricultural development and food production | National Agricultural and Rural inclusive growth Projects (NARIGP) completed | 2640503 | N/A | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2022/23 | 2022/23 | 187911173 | 393238283.6 | 0 | NARIGP | NARIGP | 0 | 489004796.6 | 351365 | 0.1 | 351365 | 3910461 | 392886918.6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2148 | Crop Development and Management | National Agricultural Value Chain Development Project (NAVCDP) | To implement national agricultural value chain development project (navcdp) for agricultural development and food production | National Agricultural Value Chain Development Project (NAVCDP) completed | 2640503 | N/A | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2022/23 | 2022/23 | 2022/23 | 70000000 | 0 | 0 | Equitable | N/A | 0 | 70000000 | 66492404 | 0 | 66492404 | 66492404 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2149 | Administration, Planning and Support Services | Construction of Offices for Saptet Dairy Farmers | To construct Offices for Saptet Dairy Farmers | Offices for Saptet Dairy Farmers constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Keringet | -0.488183, 35.706568 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2022/23 | 2022/23 | 2023 | 1800000 | 1800000 | 1800000 | Equitable | Equitable | 1800000 | 0 | 1758000 | 97.7 | 1758000 | 1758000 | 42000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: No electric ity.
2150 | Administration, Planning and Support Services | Completion of Tebeswet, Saptet Kapkwen, Taachasis Nukiat, Baragewet Tea buying centres | To complete Tebeswet, Saptet Kapkwen, Taachasis Nukiat, Baragewet Tea buying centres | Tebeswet, Saptet Kapkwen, Taachasis Nukiat, Baragewet Tea buying centres completed | 3110299 | Construction of Buildings - Ot | Kuresoi South | Amalo | -0.682723, 35.627042 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2022/23 | 2022/23 | 2023 | 4277890 | 4277890 | 4277890 | Equitable | Equitable | 4277890 | 0 | 1947508 | 45.5 | 1947508 | 2222993 | 2330382 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: project completed.
2151 | Administration, Planning and Support Services | Construction of Chorwet & Kapkures Tea Buying Centres | To construct Chorwet & Kapkures Tea Buying Centres | Chorwet & Kapkures Tea Buying Centres constructed | 3110299 | Construction of Buildings - Ot | Kuresoi South | Amalo | -0.671477, 35.61856 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2022/23 | 2022/23 | 2024 | 2700000 | 2700000 | 2700000 | Equitable | EQUITABLE | 2700000 | 0 | 2685300 | 99.5 | 2685300 | 2685300 | 14700 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: no. Viable: no. Assessor remarks: project stalled due to allocation of inadequate funds.
2152 | Administration, Planning and Support Services | Construction Of Tea Buying Centres At Ambusket, Chelalang, Saosa And Tuiyobei | To construct Tea Buying Centres At Ambusket, Chelalang, Saosa And Tuiyobei | Tea Buying Centres At Ambusket, Chelalang, Saosa And Tuiyobei constructed | 3110299 | Construction of Buildings - Ot | Kuresoi South | Amalo | -0.664247, 35.635138 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2025 | 2761228.5 | 1576228.5 | 1576228.5 | Equitable | equitable | 1576228.5 | 0 | 891679 | 56.6 | 891679 | 279520 | 684549.5 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: not yet. Viable: not yet. Assessor remarks: project not complete.
2153 | Administration, Planning and Support Services | Expansion of Mutamuiyu Milk Cooler House | To expand Mutamuiyu Milk Cooler House to increase capacity | Mutamuiyu Milk Cooler House expanded | 3110299 | Construction of Buildings - Ot | Molo | Elburgon | -0.284884 35.845889 0 1399.9990234375 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2022/23 | 2022/23 | N/A | 800000 | 800000 | 800000 | Equitable | EQUITABLE | 800000 | 0 | 1371380 | 171.4 | 1371380 | 1200000 | -571380 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: No Maternity wing-externsion of opd block.
2154 | Administration, Planning and Support Services | Construction Of Slaughter House And Fencing | To construct Slaughter House And Fencing | Slaughter House And Fencing constructed | 3110299 | Construction of Buildings - Ot | Gilgil | Gilgil | -0.460048, 36.296729 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 4000000 | 3894270 | 3894270 | Equitable | equitable | 3894270 | 0 | 3894270 | 100 | 3894270 | 3894270 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yet to start. Contractor: M/s Gactor enterprises ltd. Assessor remarks: In good state.
2155 | Livestock Resource Management and Development | Completion of ATC Kitchen and Dining | To complete ATC Kitchen and Dining | ATC Kitchen and Dining completed | 3110299 | Construction of Buildings - Ot | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2022/23 | 2022/23 | 2022/23 | 5891064 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 2386000 | 47.7 | 2386000 | 0 | 2614000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2156 | Administration, Planning and Support Services | Completion of Bondet, Sukutek, Kapchorwa, Chigamba, Banana, Kondamet Kiptagich Tea buying centres | To complete Bondet, Sukutek, Kapchorwa, Chigamba, Banana, Kondamet Kiptagich Tea buying centres | Bondet, Sukutek, Kapchorwa, Chigamba, Banana, Kondamet Kiptagich Tea buying centres completed | 3110299 | Construction of Buildings - Ot | Kuresoi South | Kiptagich | -0.63122 35.606292 2395.7000000000003 10.899999618530273 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2022/23 | 2022/23 | 2022/23 | 3500000 | 3500000 | 3500000 | Equitable | EQUITABLE | 3500000 | 0 | 3427272 | 97.9 | 3427272 | 60528 | 72728 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: No. Viable: Viable and needs met. Assessor remarks: The project is still under construction. No table tops, no painting, and no toilets..
2157 | Administration, Planning and Support Services | Completion of Irongo, Tilalwo, Kwenet, Kondomet Cheptuech, Lelechwet, Tuyobei Ketit, Ketitui, Kapungunot, Kokwet, Seger Kapmuge tea buying centre | To complete Irongo, Tilalwo, Kwenet, Kondomet Cheptuech, Lelechwet, Tuyobei Ketit, Ketitui, Kapungunot, Kokwet, Seger Kapmuge tea buying centre | Irongo, Tilalwo, Kwenet, Kondomet Cheptuech, Lelechwet, Tuyobei Ketit, Ketitui, Kapungunot, Kokwet, Seger Kapmuge tea buying centre completed | 3110299 | Construction of Buildings - Ot | Kuresoi South | Kiptagich | -0.596, 35.640372 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2022/23 | 2022/23 | 2022/23 | 8800000 | 8800000 | 8800000 | Equitable | Equitable | 8800000 | 0 | 8772162 | 99.7 | 8772162 | 0 | 27838 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and needs met. Assessor remarks: The project is complete but there is no toilets.
2158 | Administration, Planning and Support Services | Construction Of Tuyobei Ketit Tea Buying Centre | To construct Tuyobei Ketit Tea Buying Centre | Tuyobei Ketit Tea Buying Centre constructed | 3110299 | Construction of Buildings - Ot | Kuresoi South | Kiptagich | -0.599537 35.609858 2621.7000000000003 7.800000190734863 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2018/19 | 800000 | 726010 | 726010 | Equitable | Equitable | 726010 | 0 | 726010 | 100 | 726010 | 726010 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes, expected to meet the needs of the residents. Assessor remarks: Ongoing.
2159 | Administration, Planning and Support Services | Completion of Kio, Githima, Mwarangia, Arorwet, Korabariet, Chebitok, Tumoiyot and Chebkoburot Tea buying centres | To complete Kio, Githima, Mwarangia, Arorwet, Korabariet, Chebitok, Tumoiyot and Chebkoburot Tea buying centres | Kio, Githima, Mwarangia, Arorwet, Korabariet, Chebitok, Tumoiyot and Chebkoburot Tea buying centres completed | 3110299 | Construction of Buildings - Ot | Kuresoi North | Kiptororo | -0.301145, 35.52038 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2022/23 | 2022/23 | 2022/23 | 6000000 | 6000000 | 6000000 | Equitable | EQUITABLE | 6000000 | 0 | 3625000 | 60.4 | 3625000 | 2175000 | 2375000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Accessibility to the tea buying center is a challenge.the roads should be maintained.
2160 | Administration, Planning and Support Services | Completion of Sigowet Tea Buying Center | To complete Sigowet Tea Buying Center | Sigowet Tea Buying Center completed | 3110299 | Construction of Buildings - Ot | Kuresoi South | Tinet | -0.520868 35.620393 2526.8999999999996 4 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2022/23 | 2022/23 | 2022/23 | 1000000 | 1000000 | 1000000 | Equitable | Equitable | 1000000 | 0 | 970000 | 97 | 970000 | 100 | 30000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
2161 | Administration, Planning and Support Services | Completion Kandutura Cereal Store | To complete Kandutura Cereal Store | Kandutura Cereal Store completed | 3110299 | Construction of Buildings - Ot | Rongai | Visoi | -0.125295 35.935638 1744.699951171875 6 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1500000 | 1500000 | Equitable | equitable | 1500000 | 0 | 1500000 | 100 | 1500000 | 1500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: M/s AfelaLimited. Assessor remarks: Good.
2162 | Administration, Planning and Support Services | Purchase And Supply Of One Month Improved Kienyeji Old Chicks From Authorised Hatcheries | To procure and supply One Month Improved Kienyeji Old Chicks From Authorised Hatcheries | One Month Improved Kienyeji Old Chicks From Authorised Hatcheries procured and supplied | 3110302 | Refurbishment of Non-Residential Buildings | Bahati | Kiamaina | -0.231557, 36.116878 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 1000000 | 1000000 | 1000000 | Equitable | equitable | 1000000 | 0 | 977258 | 97.7 | 977258 | 0 | 22742 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: No. Assessor remarks: Some of the chicks died, others were sold at maturity and others untraceable.
2163 | Administration, Planning and Support Services | Purchase And Supply Of One Month Improved Kienyeji Old Chicks From Authorised Hatcheries | To procure and supply One Month Improved Kienyeji Old Chicks From Authorised Hatcheries | One Month Improved Kienyeji Old Chicks From Authorised Hatcheries procured and supplied | 3110302 | Refurbishment of Non-Residential Buildings | Nakuru West | London | -0.281352 36.0759 1837.5 10 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 3500000 | 0 | 3500000 | Equitable | equitable | 3500000 | 0 | 3467680 | 0 | 3467680 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
2164 | Administration, Planning and Support Services | Purchase And Supply Of One Month Old Kienyeji Chicks | To procure and supply One Month Old Kienyeji Chicks | One Month Old Kienyeji Chicks procured and supplied | 3110302 | Refurbishment of Non-Residential Buildings | Naivasha | Naivasha East | -0.80301, 36.532897 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2022 | 1500000 | 1500000 | 1500000 | Equitable | equitable | 1500000 | 0 | 1435600 | 95.7 | 1435600 | 0 | 64400 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Chick were very week majority did not survive.
2165 | Administration, Planning and Support Services | Completion Of Bondet Tea Buying Center | To complete Bondet Tea Buying Center | Bondet Tea Buying Center completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Amalo | -0.635302, 35.657887 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2024 | 300000 | 300000 | 300000 | Equitable | EQUITABLE | 300000 | 0 | 1000000 | 333.3 | 1000000 | 300000 | -700000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: project completed.
2166 | Administration, Planning and Support Services | Completion Of Kaptaragon Tea Buying Centre | To complete Kaptaragon Tea Buying Centre | Kaptaragon Tea Buying Centre completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Amalo | -0.635302, 35.657887 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2024 | 700000 | 680540 | 680540 | Equitable | EQUITABLE | 680540 | 0 | 680540 | 100 | 680540 | 680540 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: project completed.
2167 | Administration, Planning and Support Services | Completion Of Kaptembwa Tea Buying Center | To complete Kaptembwa Tea Buying Center | Kaptembwa Tea Buying Center completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Amalo | -0.635302, 35.657887 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2024 | 1000000 | 530015 | 530015 | Equitable | EQUITABLE | 530015 | 0 | 530015 | 100 | 530015 | 530015 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: project completed.
2168 | Administration, Planning and Support Services | Completion Of Nukiat Tea Buying Center | To complete Nukiat Tea Buying Center | Nukiat Tea Buying Center completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Amalo | -0.635302, 35.657887 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2024 | 300000 | 300000 | 300000 | Equitable | EQUITABLE | 300000 | 0 | 530015 | 176.7 | 530015 | 300000 | -230015 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: project completed.
2169 | Administration, Planning and Support Services | Completion Of Tea Buying Centre At Bondet | To complete Tea Buying Centre At Bondet | Tea Buying Centre At Bondet completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Amalo | -0.667318, 35.61563 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2023 | 699886 | 699886 | 699886 | Equitable | Equitable | 699886 | 0 | 699950 | 100 | 699950 | 699886 | -64 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: project completed.
2170 | Administration, Planning and Support Services | Completion Of Tea Buying Centre At Cornerstone | To complete Tea Buying Centre At Cornerstone | Tea Buying Centre At Cornerstone completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Amalo | -0.667318, 35.61563 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2023 | 700000 | 680660 | 680660 | Equitable | Equitable | 680660 | 0 | 680660 | 100 | 680660 | 680660 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: project completed.
2171 | Administration, Planning and Support Services | Completion Of Tea Buying Centre At Kaplamboi | To complete Tea Buying Centre At Kaplamboi | Tea Buying Centre At Kaplamboi completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Amalo | -0.667318, 35.61563 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2023 | 500000 | 480030 | 480030 | Equitable | Equitable | 480030 | 0 | 480030 | 100 | 480030 | 480030 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: project completed.
2172 | Administration, Planning and Support Services | Completion Of Tebeswet Tea Buying Center | To complete Tebeswet Tea Buying Center | Tebeswet Tea Buying Center completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Amalo | -0.635302, 35.657887 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2024 | 300000 | 300000 | 300000 | Equitable | EQUITABLE | 300000 | 0 | 530015 | 176.7 | 530015 | 300000 | -230015 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: project completed.
2173 | Administration, Planning and Support Services | Completion Of Tuyobei Tea Buying Center | To complete Tuyobei Tea Buying Center | Tuyobei Tea Buying Center completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Amalo | -0.635302, 35.657887 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2024 | 1000000 | 1000000 | 1000000 | Equitable | EQUITABLE | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: project completed.
2174 | Administration, Planning and Support Services | Construction Of Baregewet, Lelaitich, Ngorofa, Chumyot And Kaplamai Tea Buying Centres | To construct Baregewet, Lelaitich, Ngorofa, Chumyot And Kaplamai Tea Buying Centres | Baregewet, Lelaitich, Ngorofa, Chumyot And Kaplamai Tea Buying Centres constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Amalo | -0.677875, 35.639198 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2019 | 7500000 | 7500000 | 7500000 | Equitable | equitable | 7500000 | 0 | 7390650 | 98.5 | 7390650 | 1450000 | 109350 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: project incomplete.
2175 | Administration, Planning and Support Services | Construction Of Cheptangule Tea Buying Center | To construct Cheptangule Tea Buying Center | Cheptangule Tea Buying Center constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Amalo | -0.6786 35.654126 2470.228759765625 8.189000129699707 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | N/A | 1500000 | 1500000 | 1500000 | Equitable | Equitable | 1500000 | 0 | 1451750 | 96.8 | 1451750 | 1500000 | 48250 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Very Good. Objective met: yes. Viable: yes. Assessor remarks: done.
2176 | Administration, Planning and Support Services | Construction Of Greenhouses For Women Empowerment | To construct Greenhouses For Women Empowerment | Greenhouses For Women Empowerment constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Amalo | -0.588846 35.685603 2539.000244140625 72.9000015258789 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | N/A | 500000 | 499795 | 499795 | Equitable | equitable | 499795 | 0 | 2685300 | 537.3 | 2685300 | 499795 | -2185505 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: yes. Viable: yes. Assessor remarks: project completed.
2177 | Administration, Planning and Support Services | Construction Of Kiptenden Tea Buying Center | To construct Kiptenden Tea Buying Center | Kiptenden Tea Buying Center constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Amalo | -0.6348 35.657803 2448.7 12 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | N/A | 1500000 | 1500000 | 1500000 | Equitable | Equitable | 1500000 | 0 | 1479580 | 98.6 | 1479580 | 1500000 | 20420 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
2178 | Administration, Planning and Support Services | Construction Of Koilenget Tea Buying Center | To construct Koilenget Tea Buying Center | Koilenget Tea Buying Center constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Amalo | -0.653745 35.620132 2430.7999999999997 13.800000190734863 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | N/A | 1500000 | 1500000 | 1500000 | Equitable | Equitable | 1500000 | 0 | 1479580 | 98.6 | 1479580 | 1500000 | 20420 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: no. Viable: no. Assessor remarks: project stalled.
2179 | Administration, Planning and Support Services | Construction Of Tendwet Tea Buying Centre | To construct Tendwet Tea Buying Centre | Tendwet Tea Buying Centre constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Amalo | -0.653745 35.620132 2430.7999999999997 13.800000190734863 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | N/A | 1000000 | 1000000 | 1000000 | Equitable | Equitable | 1000000 | 0 | 978270 | 97.8 | 978270 | 1199469 | 21730 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: no. Viable: no. Assessor remarks: project stalled.
2180 | Crop Development and Management | Construction Of Umoja Tea Buying Center At Ambiska | To construct Umoja Tea Buying Center At Ambiska | Umoja Tea Buying Center At Ambiska constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Amalo | -0.615322, 35.65657 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2022 | 1500000 | 1500000 | 1500000 | Equitable | EQUITABLE | 1500000 | 0 | 1215610 | 81 | 1215610 | 1500000 | 284390 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: yes. Viable: yes. Assessor remarks: project completed.
2181 | Administration, Planning and Support Services | Erecting Of A Fence Around Olenguruone Dairies Society | To implement erecting of a fence around olenguruone dairies society for agricultural development and food production | Erecting Of A Fence Around Olenguruone Dairies Society completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Amalo | -0.592109, 35.684406 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2017/18 | 2017/18 | 2023 | 2000000 | 1999608 | 1999608 | Equitable | Equitable | 1999608 | 0 | 0 | 0 | 0 | 1999608 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: yes. Assessor remarks: project on progress.
2182 | Administration, Planning and Support Services | Construction Of Kasambara Milk Cooling Plant (Phase 1) | To construct Kasambara Milk Cooling Plant (Phase 1) | Kasambara Milk Cooling Plant (Phase 1) constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Eburru/Mbaruk | -0.365659, 36.237175 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | No details | 3000000 | 2990950 | 2990950 | Equitable | equitable | 2990950 | 0 | 2990950 | 100 | 2990950 | 2990950 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No, because it not operational. Viable: Yes. Contractor: No details. Assessor remarks: Fairly done.
2183 | Administration, Planning and Support Services | Supply Of Solar Panel For Itura Farm Incubators | To implement supply of solar panel for itura farm incubators for agricultural development and food production | Supply Of Solar Panel For Itura Farm Incubators completed | 3110504 | Other Infrastructure and Civil Works | Molo | Elburgon | -0.260228 35.795537 2376.5 9.5 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | N/A | 300000 | 300000 | 300000 | Equitable | equitable | 300000 | 0 | 0 | 0 | 0 | 300000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete project.
2184 | Crop Development and Management | Construction of Chicken empowerment houses at Kiambogo, Kahuho and Muthaiti. | To construct Chicken empowerment houses at Kiambogo, Kahuho and Muthaiti | Chicken empowerment houses at Kiambogo, Kahuho and Muthaiti constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Elementaita | -0.567127, 36.114877 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2022/23 | 2022/23 | 2022/23 | 3000000 | 3000000 | 3000000 | Equitable | EQUITABLE | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
2185 | Crop Development and Management | Construction of Chicken empowerment houses at Miti Mingi, Mugaa Olesultan and Ndibai. | To construct Chicken empowerment houses at Miti Mingi, Mugaa Olesultan and Ndibai | Chicken empowerment houses at Miti Mingi, Mugaa Olesultan and Ndibai constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Elementaita | -0.567127, 36.114877 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2022/23 | 2022/23 | 2022/23 | 3000000 | 3000000 | 3000000 | Equitable | EQUITABLE | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
2186 | Administration, Planning and Support Services | Completion and equipping of slaughter House in Naivasha, Hells Gate ward | To complete and equip slaughter House in Naivasha, Hells Gate ward | Slaughter House in Naivasha, Hells Gate ward completed and equipped | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2022/23 | 2022/23 | 2022/23 | 15000000 | 3000000 | 3000000 | Equitable | EQUITABLE | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2187 | Administration, Planning and Support Services | Completion of Eburru/Mbaruk Slaughter House | To complete Eburru/Mbaruk Slaughter House | Eburru/Mbaruk Slaughter House completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2022/23 | 2022/23 | 2022/23 | 38396882 | 6000000 | 6000000 | Equitable | EQUITABLE | 6000000 | 0 | 5668369 | 94.5 | 5668369 | 0 | 331631 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2188 | Fisheries Development | Completion of fish processing and market in Naivasha | To complete fish processing and market in Naivasha | Fish processing and market in Naivasha completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 2000000 | 2400000 | Equitable | equitable | 2400000 | 0 | 2386000 | 119.3 | 2386000 | 5459432 | -386000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2189 | Administration, Planning and Support Services | Completion of security wall and machinery shed at AMS for securing procured machinery and implements | To complete security wall and machinery shed at AMS for securing procured machinery and implements | Security wall and machinery shed at AMS for securing procured machinery and implements completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2022/23 | 2022/23 | 2022/23 | 22000000 | 6113590 | 6113590 | Equitable | EQUITABLE | 6113590 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2190 | Fisheries Development | Completion of slaughter House in Naivasha, Hells Gate ward | To complete slaughter House in Naivasha, Hells Gate ward | Slaughter House in Naivasha, Hells Gate ward completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 18500000 | 6200000 | 6200000 | Equitable | equitable | 6200000 | 0 | 2980492 | 48.1 | 2980492 | 0 | 3219508 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2191 | Administration, Planning and Support Services | Construction of a Kitchen and Dinning Hall at the ATC | To construct a Kitchen and Dinning Hall at the ATC | A Kitchen and Dinning Hall at the ATC constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 10000000 | 5000000 | 5000000 | Equitable | EQUITABLE | 5000000 | 0 | 2299932 | 46 | 2299932 | 0 | 2700068 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2192 | Administration, Planning and Support Services | Construction of Eburru/Mbaruk slaughter House and Auction Yard | To construct Eburru/Mbaruk slaughter House and Auction Yard | Eburru/Mbaruk slaughter House and Auction Yard constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 50000000 | 10309855 | 10309855 | Equitable | EQUITABLE | 10309855 | 0 | 2980492 | 28.9 | 2980492 | 0 | 7329363 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2193 | Fisheries Development | Construction of livestock Auction yard in Naivasha East | To construct livestock Auction yard in Naivasha East | Livestock Auction yard in Naivasha East constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 1500000 | 1500000 | 1500000 | Equitable | equitable | 1500000 | 0 | 2386000 | 159.1 | 2386000 | 0 | -886000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2194 | Construction of Makongeni cattle dip at Soin Ward | Construction of Makongeni cattle dip at Soin Ward | To construct Makongeni cattle dip at Soin Ward | Makongeni cattle dip at Soin Ward constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
2195 | Administration, Planning and Support Services | Construction of security wall and machinery shed at AMS for securing procured machinery and implements | To construct security wall and machinery shed at AMS for securing procured machinery and implements | Security wall and machinery shed at AMS for securing procured machinery and implements constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 25000000 | 3000000 | 3000000 | Equitable | EQUITABLE | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2196 | Administration, Planning and Support Services | Construction of slaughter slab in Sirikwa ward | To construct slaughter slab in Sirikwa ward | Slaughter slab in Sirikwa ward constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 2500000 | 2500000 | 2500000 | Equitable | EQUITABLE | 2500000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2197 | Administration, Planning and Support Services | Development, Demarcation, Provision Of Tap Water And Fencing And Kamere Beach Area, Naivasha | To implement development, demarcation, provision of tap water and fencing and kamere beach area, naivasha for agricultural development and food production | Development, Demarcation, Provision Of Tap Water And Fencing And Kamere Beach Area, Naivasha completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2018/19 | 1497908 | 1497908 | 1497908 | Equitable | EQUITABLE | 1497908 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2198 | Administration, Planning and Support Services | Extension Fence at ATC | To expand Fence at ATC to increase capacity | Fence at ATC expanded | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 20000000 | 2000000 | 2000000 | Equitable | EQUITABLE | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2199 | Administration, Planning and Support Services | Extra Works For Proposed Construction Of Slaughter Slab At Malewa West Naivasha Sub County | To implement extra works for proposed construction of slaughter slab at malewa west naivasha sub county for agricultural development and food production | Extra Works For Proposed Construction Of Slaughter Slab At Malewa West Naivasha Sub County completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2018/19 | 450000 | 450000 | 450000 | Equitable | EQUITABLE | 450000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2200 | Fisheries Development | Fishing and safety Gears in Lake Naivasha | To implement fishing and safety gears in lake naivasha for agricultural development and food production | Fishing and safety Gears in Lake Naivasha completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2022/23 | 2022/23 | 2022/23 | 10000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 3994966 | 399.5 | 3994966 | 4533338 | -2994966 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2201 | Administration, Planning and Support Services | Gilgil slaughter house gates and fencing | To implement gilgil slaughter house gates and fencing for agricultural development and food production | Gilgil slaughter house gates and fencing completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 0 | 2000000 | Equitable | EQUITABLE | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2202 | Administration, Planning and Support Services | Potato Stores In Kuresoi South And Njoro | To implement potato stores in kuresoi south and njoro for agricultural development and food production | Potato Stores In Kuresoi South And Njoro completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2018/19 | 2998855.2 | 2998855 | 2998855 | Equitable | EQUITABLE | 2998855 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2203 | Livestock Resource Management and Development | Purchase and supply of standby generator for Inua Hustlers Cooperative | To procure and supply standby generator for Inua Hustlers Cooperative | Standby generator for Inua Hustlers Cooperative procured and supplied | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 2000000 | 2000000 | Equitable | EQUITABLE | 2000000 | 0 | 1900540 | 95 | 1900540 | 0 | 99460 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2204 | Administration, Planning and Support Services | Purchase of livestock support equipments | To procure livestock support equipments | Livestock support equipments procured | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 20000000 | 13846768 | 13846768 | Equitable | EQUITABLE | 13846768 | 0 | 3749520 | 27.1 | 3749520 | 13846768 | 10097248 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2205 | Administration, Planning and Support Services | Construction Of Underground Tank At Kibowen Komen For Urban Agriculture | To construct Underground Tank At Kibowen Komen For Urban Agriculture | Underground Tank At Kibowen Komen For Urban Agriculture constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kaptembwo | -0.312177, 36.052969 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | N/A | 1000000 | 999700 | 999700 | Equitable | Equitable | 999700 | 0 | 499290 | 49.9 | 499290 | 699700 | 500410 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not yet started. Viable: No. Contractor: Carofa enterprises. Assessor remarks: Yet to be started.
2206 | Administration, Planning and Support Services | Promotion Of Youth And Women Urban Agriculture | To implement promotion of youth and women urban agriculture for agricultural development and food production | Promotion Of Youth And Women Urban Agriculture completed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kaptembwo | -0.312069, 36.053022 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 501200 | 501200 | 501200 | Equitable | equitable | 501200 | 0 | 499290 | 99.6 | 499290 | 501200 | 1910 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No since it was vandalized after two years of completion. Viable: Yes it was a very viable project if not for vandalism. Contractor: Arthritis enterprises. Assessor remarks: The project was vandalized hence it's not working.
2207 | Administration, Planning and Support Services | Construction Of Cut Off Drains In Agricultural Farm Lands | To construct Cut Off Drains In Agricultural Farm Lands | Cut Off Drains In Agricultural Farm Lands constructed | 3110504 | Other Infrastructure and Civil Works | Njoro | Kihingo | -0.451828, 35.976993 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2022 | 2500000 | 1175000 | 1175000 | Equitable | equitable | 1175000 | 0 | 1160000 | 98.7 | 1160000 | 15000 | 15000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yea. Viable: Yes. Assessor remarks: Requires maintenance.
2208 | Administration, Planning and Support Services | Completion Of Aonet Tea Buying Center | To complete Aonet Tea Buying Center | Aonet Tea Buying Center completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.592825, 35.636085 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | N/A | 400000 | 400000 | 400000 | Equitable | EQUITABLE | 400000 | 0 | 400000 | 100 | 400000 | 400000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and needs met. Assessor remarks: Functional.
2209 | Administration, Planning and Support Services | Completion Of Ararwet Marisim Tea Buying Center | To complete Ararwet Marisim Tea Buying Center | Ararwet Marisim Tea Buying Center completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.592825, 35.636085 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | N/A | 400000 | 400000 | 400000 | Equitable | EQUITABLE | 400000 | 0 | 396390 | 99.1 | 396390 | 400000 | 3610 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and needs met. Assessor remarks: Functional.
2210 | Administration, Planning and Support Services | Completion Of Banana Tea Buying Center | To complete Banana Tea Buying Center | Banana Tea Buying Center completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.592825, 35.636085 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | N/A | 400000 | 399310 | 399310 | Equitable | EQUITABLE | 399310 | 0 | 400000 | 100.2 | 400000 | 399310 | -690 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and needs met. Assessor remarks: Functional.
2211 | Administration, Planning and Support Services | Completion Of Chepkiswet Tea Buying Center | To complete Chepkiswet Tea Buying Center | Chepkiswet Tea Buying Center completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.592825, 35.636085 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | N/A | 600000 | 600000 | 600000 | Equitable | EQUITABLE | 600000 | 0 | 600000 | 100 | 600000 | 600000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and needs met. Assessor remarks: Functional.
2212 | Administration, Planning and Support Services | Completion Of Kapkwen-Kabungunot Tea Buying Center | To complete Kapkwen-Kabungunot Tea Buying Center | Kapkwen-Kabungunot Tea Buying Center completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.592825, 35.636085 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | N/A | 600000 | 600000 | 600000 | Equitable | EQUITABLE | 600000 | 0 | 600000 | 100 | 600000 | 600000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and needs met. Assessor remarks: Functional.
2213 | Administration, Planning and Support Services | Completion Of Kapugunot Tea Buying Centre | To complete Kapugunot Tea Buying Centre | Kapugunot Tea Buying Centre completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.592825, 35.636085 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | N/A | 700000 | 693262 | 693262 | Equitable | EQUITABLE | 693262 | 0 | 693262 | 100 | 693262 | 693262 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and needs met. Assessor remarks: Functional.
2214 | Administration, Planning and Support Services | Completion Of Ketitui Tea Buying Centre | To complete Ketitui Tea Buying Centre | Ketitui Tea Buying Centre completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.592825, 35.636085 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | N/A | 300000 | 300000 | 300000 | Equitable | EQUITABLE | 300000 | 0 | 399272 | 133.1 | 399272 | 300000 | -99272 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and needs met. Assessor remarks: Functional.
2215 | Administration, Planning and Support Services | Completion Of Kibirech Tea Buying Center | To complete Kibirech Tea Buying Center | Kibirech Tea Buying Center completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.592825, 35.636085 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | N/A | 200000 | 199189 | 199189 | Equitable | EQUITABLE | 199189 | 0 | 199189 | 100 | 199189 | 199189 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and needs met. Assessor remarks: Functional.
2216 | Administration, Planning and Support Services | Completion Of Kiborowa Tea Buying Center | To complete Kiborowa Tea Buying Center | Kiborowa Tea Buying Center completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.592825, 35.636085 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | N/A | 800000 | 800000 | 800000 | Equitable | EQUITABLE | 800000 | 0 | 800000 | 100 | 800000 | 800000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and needs met. Assessor remarks: Functional.
2217 | Administration, Planning and Support Services | Completion Of Kipsunyam-Table Tops Tea Buying Center | To complete Kipsunyam-Table Tops Tea Buying Center | Kipsunyam-Table Tops Tea Buying Center completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.638423, 35.60739 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2023 | 300000 | 300000 | 300000 | Equitable | Equitable | 300000 | 0 | 300000 | 100 | 300000 | 300000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable and it meets the needs of the residents. Contractor: Don't know. Assessor remarks: The project is complete.
2218 | Administration, Planning and Support Services | Completion Of Kondamet Tea Buying Centre | To complete Kondamet Tea Buying Centre | Kondamet Tea Buying Centre completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.592825, 35.636085 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | N/A | 400000 | 399272 | 399272 | Equitable | EQUITABLE | 399272 | 0 | 399272 | 100 | 399272 | 399272 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and needs met. Assessor remarks: Functional.
2219 | Administration, Planning and Support Services | Completion Of Saptonok Tea Buying Centre | To complete Saptonok Tea Buying Centre | Saptonok Tea Buying Centre completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.592825, 35.636085 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | N/A | 400000 | 393820 | 393820 | Equitable | EQUITABLE | 393820 | 0 | 393820 | 100 | 393820 | 393820 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and needs met. Assessor remarks: Functional.
2220 | Administration, Planning and Support Services | Completion Of Seger Tea Buying Center | To complete Seger Tea Buying Center | Seger Tea Buying Center completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.592825, 35.636085 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | N/A | 400000 | 400000 | 400000 | Equitable | EQUITABLE | 400000 | 0 | 349980 | 87.5 | 349980 | 400000 | 50020 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and needs met. Assessor remarks: Functional.
2221 | Administration, Planning and Support Services | Completion Of Tea Buying Center At Chepkiswet | To complete Tea Buying Center At Chepkiswet | Tea Buying Center At Chepkiswet completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.582347 35.64907 2515.7999999999997 7.400000095367432 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | N/A | 400000 | 400000 | 400000 | Equitable | equitable | 400000 | 0 | 400000 | 100 | 400000 | 400000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes and met the needs. Assessor remarks: Functional.
2222 | Administration, Planning and Support Services | Completion Of Tea Buying Center At Chepnyalilo | To complete Tea Buying Center At Chepnyalilo | Tea Buying Center At Chepnyalilo completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.582347 35.64907 2515.7999999999997 7.400000095367432 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | N/A | 400000 | 400000 | 400000 | Equitable | equitable | 400000 | 0 | 400000 | 100 | 400000 | 400000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes and met the needs. Assessor remarks: Functional.
2223 | Administration, Planning and Support Services | Completion Of Tuiyobei-Tebeswet Tea Buying Center | To complete Tuiyobei-Tebeswet Tea Buying Center | Tuiyobei-Tebeswet Tea Buying Center completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.582347 35.64907 2515.7999999999997 7.400000095367432 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 600000 | 600000 | 600000 | Equitable | Equitable | 600000 | 0 | 600000 | 100 | 600000 | 600000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes and met the needs. Assessor remarks: Functional.
2224 | Administration, Planning and Support Services | Construction Of Ararwet Mbaley Tea Buying Center | To construct Ararwet Mbaley Tea Buying Center | Ararwet Mbaley Tea Buying Center constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.562995, 35.589517 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | Not yet started | 1000000 | 927290 | 927290 | Equitable | EQUITABLE | 927290 | 0 | 396390 | 42.7 | 396390 | 927290 | 530900 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: The project was viable but it never met the objectives of the residents.. Contractor: Don't know. Assessor remarks: The project has not started.
2225 | Administration, Planning and Support Services | Construction Of Chepkiswet Tea Buying Centre | To construct Chepkiswet Tea Buying Centre | Chepkiswet Tea Buying Centre constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.599537 35.609858 2621.7000000000003 7.800000190734863 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2018/19 | 1198687 | 1198687 | 1198687 | Equitable | EQUITABLE | 1198687 | 0 | 600000 | 50.1 | 600000 | 698687 | 598687 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes, expected to meet the needs of the residents. Assessor remarks: Ongoing.
2226 | Administration, Planning and Support Services | Construction Of Kanoin Tea Buying Center | To construct Kanoin Tea Buying Center | Kanoin Tea Buying Center constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.579408 35.574193 2412.1 4.199999809265137 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 800000 | 800000 | 800000 | Equitable | EQUITABLE | 800000 | 0 | 730923 | 91.4 | 730923 | 69077 | 69077 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: The project is viable but it doesn't meet the needs of the residents. Contractor: Don't know. Assessor remarks: The project is at lintel level and has stalled..
2227 | Administration, Planning and Support Services | Construction Of Kapsilibwo Tea Buying Centre | To construct Kapsilibwo Tea Buying Centre | Kapsilibwo Tea Buying Centre constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.631022 35.606107 2398.9 14.100000381469727 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 1199109.4 | 1199109.4 | 1199109.4 | Equitable | EQUITABLE | 1199109.4 | 0 | 1199109 | 100 | 1199109 | 1199109 | 0.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Viable but it is still under construction.. Contractor: Don't. Assessor remarks: The project is still under construction. No table tops, no painting, and no toilets..
2228 | Administration, Planning and Support Services | Construction Of Kiborowo Tea Buying Centre | To construct Kiborowo Tea Buying Centre | Kiborowo Tea Buying Centre constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.599537 35.609858 2621.7000000000003 7.800000190734863 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 1199600 | 1299600 | 1299600 | Equitable | EQUITABLE | 1299600 | 0 | 1299580 | 100 | 1299580 | 1299600 | 20 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes, expected to meet the needs of the residents. Assessor remarks: Ongoing.
2229 | Administration, Planning and Support Services | Construction Of Tea Buying Center At Ararwet | To construct Tea Buying Center At Ararwet | Tea Buying Center At Ararwet constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.599537 35.609858 2621.7000000000003 7.800000190734863 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 800000 | 726010 | 726010 | Equitable | Equitable | 726010 | 0 | 726010 | 100 | 726010 | 726010 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes, expected to meet the needs of the residents. Assessor remarks: Ongoing.
2230 | Administration, Planning and Support Services | Construction Of Tea Buying Center At Lelechwet | To construct Tea Buying Center At Lelechwet | Tea Buying Center At Lelechwet constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.599537 35.609858 2621.7000000000003 7.800000190734863 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 800000 | 726010 | 726010 | Equitable | Equitable | 726010 | 0 | 726010 | 100 | 726010 | 726010 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes, expected to meet the needs of the residents. Assessor remarks: Ongoing.
2231 | Administration, Planning and Support Services | Construction Of Tea Buying Center At Tilalwo Irongo | To construct Tea Buying Center At Tilalwo Irongo | Tea Buying Center At Tilalwo Irongo constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.599537 35.609858 2621.7000000000003 7.800000190734863 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 800000 | 726010 | 726010 | Equitable | Equitable | 726010 | 0 | 726010 | 100 | 726010 | 726010 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes, expected to meet the needs of the residents. Assessor remarks: Ongoing.
2232 | Administration, Planning and Support Services | Construction Of Tea Buying Center Kokwet | To construct Tea Buying Center Kokwet | Tea Buying Center Kokwet constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.579623, 35.574247 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 400000 | 399504 | 399504 | Equitable | EQUITABLE | 399504 | 0 | 399504 | 100 | 399504 | 399504 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: Yes. Assessor remarks: Constructed UpTo lental.
2233 | Administration, Planning and Support Services | Completion And Refurbishment Of Kipkewa Tea Buying Centre | To complete And Refurbishment Of Kipkewa Tea Buying Centre | And Refurbishment Of Kipkewa Tea Buying Centre completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Kiptororo | -0.32762, 35.498182 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 800000 | 800000 | 800000 | Equitable | equitable | 800000 | 0 | 800000 | 100 | 800000 | 800000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need for a latrine.
2234 | Administration, Planning and Support Services | Completion Of Chorwa Tea Buying Center | To complete Chorwa Tea Buying Center | Chorwa Tea Buying Center completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Kiptororo | -0.335513, 35.484805 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 200000 | 200000 | 200000 | Equitable | equitable | 200000 | 0 | 197800 | 98.9 | 197800 | 200000 | 2200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
2235 | Administration, Planning and Support Services | Construction Of A Tea Buying Center At Arorwet | To construct A Tea Buying Center At Arorwet | A Tea Buying Center At Arorwet constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Kiptororo | -0.302533 35.5297 0 800 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 1400000 | 1400000 | 1400000 | Equitable | Equitable | 1400000 | 0 | 1378824 | 98.5 | 1378824 | 1400000 | 21176 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yess but without toilet it will be closed by pho. Assessor remarks: The banda is complete without paint and the area pho has issued notice for construction of a toilet.
2236 | Administration, Planning and Support Services | Construction Of A Tea Buying Center At Chematich | To construct A Tea Buying Center At Chematich | A Tea Buying Center At Chematich constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Kiptororo | -0.302533 35.5297 0 800 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | Equitable | 1200000 | 0 | 1175350 | 97.9 | 1175350 | 1200000 | 24650 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yess but without toilet it will be closed by pho. Assessor remarks: The banda is complete without paint and the area pho has issued notice for construction of a toilet.
2237 | Administration, Planning and Support Services | Construction Of A Tea Buying Center At Karabariet | To construct A Tea Buying Center At Karabariet | A Tea Buying Center At Karabariet constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Kiptororo | -0.302533 35.5297 0 800 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 1399920 | 1399920 | 1399920 | Equitable | Equitable | 1399920 | 0 | 1399920 | 100 | 1399920 | 1399920 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yess but without toilet it will be closed by pho. Assessor remarks: The banda is complete without paint and the area pho has issued notice for construction of a toilet.
2238 | Administration, Planning and Support Services | Construction Of A Tea Buying Center At Mwaragania | To construct A Tea Buying Center At Mwaragania | A Tea Buying Center At Mwaragania constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Kiptororo | -0.302533 35.5297 0 800 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 1400000 | 666950 | 666950 | Equitable | Equitable | 666950 | 0 | 666950 | 100 | 666950 | 666950 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yess but without toilet it will be closed by pho. Assessor remarks: The banda is complete without paint and the area pho has issued notice for construction of a toilet.
2239 | Administration, Planning and Support Services | Construction Of A Tea Buying Centre At Kio | To construct A Tea Buying Centre At Kio | A Tea Buying Centre At Kio constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Kiptororo | -0.302533 35.5297 0 800 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 1400000 | 1400000 | 1400000 | Equitable | Equitable | 1400000 | 0 | 1378824 | 98.5 | 1378824 | 1400000 | 21176 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yess but without toilet it will be closed by pho. Assessor remarks: The banda is complete without paint and the area pho has issued notice for construction of a toilet.
2240 | Administration, Planning and Support Services | Construction Of Chebitoik,Burgei Ogilgei, Tumoiyot And Completion Of Chematichtea Buying Centre | To construct Chebitoik,Burgei Ogilgei, Tumoiyot And Completion Of Chematichtea Buying Centre | Chebitoik,Burgei Ogilgei, Tumoiyot And Completion Of Chematichtea Buying Centre constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Kiptororo | -0.309289, 35.516698 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | N/A | 4400000 | 4250000 | 4250000 | Equitable | N/A | 4250000 | 0 | 2106760 | 49.6 | 2106760 | 2143240 | 2143240 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: The is in complete,without roof and all other finishings.
2241 | Administration, Planning and Support Services | Construction Of Githima Tea Buying Center | To construct Githima Tea Buying Center | Githima Tea Buying Center constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Kiptororo | -0.313788, 35.483612 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 1097450 | 1097450 | Equitable | Equitable | 1097450 | 0 | 1046650 | 95.4 | 1046650 | 1097450 | 50800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is funtional.
2242 | Administration, Planning and Support Services | Purchase And Supply Of Dam Liners | To procure and supply Dam Liners | Dam Liners procured and supplied | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maai Mahiu | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 1500000 | 1500000 | 1500000 | Equitable | equitable | 1500000 | 0 | 1491600 | 99.4 | 1491600 | 0 | 8400 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2243 | Administration, Planning and Support Services | Electricity (3 phase) and water connection to Maiella and Ndabibi milk cooling plants | To implement electricity (3 phase) and water connection to maiella and ndabibi milk cooling plants for agricultural development and food production | Electricity (3 phase) and water connection to Maiella and Ndabibi milk cooling plants completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maiella | -0.891966, 36.197259 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2025 | 1000000 | 0 | 1000000 | Equitable | equitable | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Yet to start/New | 0 | N/A | Insufficient Funds | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: NO. Viable: YES. Assessor remarks: Awarded..Yet to start.
2244 | Administration, Planning and Support Services | Completion of Kasarani Slaughter house | To complete Kasarani Slaughter house | Kasarani Slaughter house completed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Malewa West | -0.702703, 36.309037 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 1000000 | 1000000 | 1000000 | Equitable | Equitable | 1000000 | 0 | 1499999 | 150 | 1499999 | 1000000 | -499999 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Land has been encroached.
2245 | Administration, Planning and Support Services | Purchase And Supply Of Nets, Fishing Hooks And Life Savers At Talambeta Landing Beach | To procure and supply Nets, Fishing Hooks And Life Savers At Talambeta Landing Beach | Nets, Fishing Hooks And Life Savers At Talambeta Landing Beach procured and supplied | 3110504 | Other Infrastructure and Civil Works | Gilgil | Malewa West | -0.774775 36.291606 0 4300 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 1200000 | 1200000 | 1200000 | Equitable | equitable | 1200000 | 0 | 1197800 | 99.8 | 1197800 | 1200000 | 2200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good initiative.
2246 | Administration, Planning and Support Services | Purchase And Supply Of Nyondia Farmers Bee Hives | To procure and supply Nyondia Farmers Bee Hives | Nyondia Farmers Bee Hives procured and supplied | 3110504 | Other Infrastructure and Civil Works | Gilgil | Malewa West | -0.702703, 36.471211 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2022/23 | 337416 | 337416 | 337416 | Equitable | Equitable | 337416 | 0 | 333469 | 98.8 | 333469 | 337416 | 3947 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Partly. Viable: Partly. Assessor remarks: Need more training.
2247 | Administration, Planning and Support Services | Construction of Potatoes Cold storage facility | To construct Potatoes Cold storage facility | Potatoes Cold storage facility constructed | 3110504 | Other Infrastructure and Civil Works | Njoro | Mau Narok | -0.542218 36.05591 1837.300048828125 12.699999809265137 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2022/23 | 2022/23 | N/A | 4400000 | 4400000 | 4400000 | Equitable | Equitable | 4400000 | 0 | 0 | 0 | 0 | 4400000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Not yet. Viable: Somehow. Assessor remarks: Needs repair and new class.
2248 | Crop Development and Management | Fencing Of Mauka Cereal Store | To secure Mauka Cereal Store through fencing | Mauka Cereal Store fenced and secured | 3110504 | Other Infrastructure and Civil Works | Njoro | Mauche | -0.508777, 35.971722 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2021 | 3000000 | 2850000 | 2850000 | Equitable | EQUITABLE | 2850000 | 0 | 2850000 | 100 | 2850000 | 2850000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
2249 | Administration, Planning and Support Services | Construction of Kamunei milk cooler and installation of electricity | To construct Kamunei milk cooler and installation of electricity | Kamunei milk cooler and installation of electricity constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Menengai West | -0.2466 36.013657 2010.9 9.5 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | N/A | 2000000 | 0 | 2000000 | Equitable | equitable | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
2250 | Administration, Planning and Support Services | Construction Of Perimeter Wall In Kenyatta Slaughter House | To construct Perimeter Wall In Kenyatta Slaughter House | Perimeter Wall In Kenyatta Slaughter House constructed | 3110504 | Other Infrastructure and Civil Works | Molo | Molo Central | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | EQUITABLE | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2251 | Administration, Planning and Support Services | Construction of a Vegetable Value addition Plant at Munyu | To construct a Vegetable Value addition Plant at Munyu | A Vegetable Value addition Plant at Munyu constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Naivasha East | -0.738739, 36.435461 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2022/23 | 2022/23 | 2022 | 3137509 | 3137509 | 3137509 | Equitable | Equitable | 3137509 | 0 | 1285567 | 41 | 1285567 | 1512663 | 1851942 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Funds used to buy land instead ofbuilding.
2252 | Administration, Planning and Support Services | Construction of Value Addition Factory Phase I | To construct Value Addition Factory Phase I | Value Addition Factory Phase I constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Naivasha East | -0.825465, 36.532288 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2023/24 | 3000000 | 3000000 | 3000000 | Equitable | EQUITABLE | 3000000 | 0 | 1285567 | 42.9 | 1285567 | 2000000 | 1714433 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Not yet. Assessor remarks: Not yet complete.
2253 | Administration, Planning and Support Services | Purchase Of Bee Hives The Youth At Nessuit Ward | To procure Bee Hives The Youth At Nessuit Ward | Bee Hives The Youth At Nessuit Ward procured | 3110504 | Other Infrastructure and Civil Works | Njoro | Nessuit | -0.409336, 35.871119 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2022/23 | 100000 | 100000 | 100000 | Equitable | Equitable | 100000 | 0 | 99999 | 100 | 99999 | 100000 | 1 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is doing very well. Continuous capacity building is requested by the farmers. Safety gears also a necessity for the farmers.
2254 | Administration, Planning and Support Services | Construction of Kamere Beach kiosk phase II | To construct Kamere Beach kiosk phase II | Kamere Beach kiosk phase II constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Olkaria | -0.817132 36.32586 1922.199951171875 24.67099952697754 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | N/A | 5000000 | 5000000 | 5000000 | Equitable | Equitable | 5000000 | 0 | 1499994 | 30 | 1499994 | 4000000 | 3500006 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Viable when completed it will serve the purpose. Contractor: Willpo solutions. Assessor remarks: Ground handed over.
2255 | Administration, Planning and Support Services | Construction Of Kamere Beach Kiosks (Phase Two) | To construct Kamere Beach Kiosks (Phase Two) | Kamere Beach Kiosks (Phase Two) constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Olkaria | -0.817132 36.32586 1922.199951171875 24.67099952697754 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | N/A | 5000000 | 5000000 | 5000000 | Equitable | Equitable | 5000000 | 0 | 1499994 | 30 | 1499994 | 5000000 | 3500006 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Viable when completed it will serve the purpose. Contractor: Willpo solutions. Assessor remarks: Ground handed over.
2256 | Administration, Planning and Support Services | Installation of power to Kamere Beach kiosk and fish freezer | To install power to Kamere Beach kiosk and fish freezer | Power to Kamere Beach kiosk and fish freezer installed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Olkaria | -0.817274, 36.326042 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | N/A | 1500000 | 1500000 | 1500000 | Equitable | EQUITABLE | 1500000 | 0 | 1998705 | 133.2 | 1998705 | 1500000 | -498705 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes.not yet since installation us not been done. Assessor remarks: Installation of power not done.
2257 | Administration, Planning and Support Services | Installation Of Power To Kamere Beach Kiosks And Fish Freezer | To install Power To Kamere Beach Kiosks And Fish Freezer | Power To Kamere Beach Kiosks And Fish Freezer installed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Olkaria | -0.817274, 36.326042 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | N/A | 1500000 | 1500000 | 1500000 | Equitable | EQUITABLE | 1500000 | 0 | 0 | 0 | 0 | 1500000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes.not yet since installation us not been done. Assessor remarks: Installation of power not done.
2258 | Administration, Planning and Support Services | Purchase And Supply Of Bee Hives In Sirikwa Ward | To procure and supply Bee Hives In Sirikwa Ward | Bee Hives In Sirikwa Ward procured and supplied | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Sirikwa | -0.288365, 35.67337 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 2000000 | 2000000 | Equitable | equitable | 2000000 | 0 | 1915586 | 95.8 | 1915586 | 2000000 | 84414 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is good, more beehives needed.
2259 | Administration, Planning and Support Services | Additional Fund To Construction Of Barina Cattle Dip | To implement additional fund to construction of barina cattle dip for agricultural development and food production | Additional Fund To Construction Of Barina Cattle Dip completed | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.065365 36.063149 1637 9.5 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 117304 | 107304 | 107304 | Equitable | equitable | 107304 | 0 | 107304 | 100 | 107304 | 107304 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require renovation.
2260 | Administration, Planning and Support Services | Construction Of Barina Sub Location Cattle Dip | To construct Barina Sub Location Cattle Dip | Barina Sub Location Cattle Dip constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.083409 35.873848 1801 9.5 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 1882696 | 1882696 | 1882696 | Equitable | equitable | 1882696 | 0 | 1882696 | 100 | 1882696 | 1882696 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require water supply.
2261 | Administration, Planning and Support Services | Construction Of Soin Cattle Dip | To construct Soin Cattle Dip | Soin Cattle Dip constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.08633, 35.937677 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2024/2025 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1986750 | 99.3 | 1986750 | 1882696 | 13250 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require fencing and construction of a public toilet.
2262 | Administration, Planning and Support Services | Construction Of Water Tank At Sawaiti Cattledip | To construct Water Tank At Sawaiti Cattledip | Water Tank At Sawaiti Cattledip constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.070984, 36.044943 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 270000 | 268000 | 268000 | Equitable | equitable | 268000 | 0 | 268000 | 100 | 268000 | 268000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
2263 | Administration, Planning and Support Services | Purchase And Supply Of Bee Hives In Soin Ward | To procure and supply Bee Hives In Soin Ward | Bee Hives In Soin Ward procured and supplied | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.055935 36.076458 1641.2 3.200000047683716 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 519433 | 519433 | 519433 | Equitable | Equitable | 519433 | 0 | 510751 | 98.3 | 510751 | 519433 | 8682 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Luki Contractors. Assessor remarks: Work done but needs regular maintenance.
2264 | Administration, Planning and Support Services | Purchase Of Bee Hives To Soin Groups | To procure Bee Hives To Soin Groups | Bee Hives To Soin Groups procured | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.055935 36.076458 1641.2 3.200000047683716 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 848331 | 848331 | 848331 | Equitable | equitable | 848331 | 0 | 848331 | 100 | 848331 | 848331 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Luki Contractors. Assessor remarks: Work done but needs regular maintenance.
2265 | Administration, Planning and Support Services | Renovation Of Banita Cattle Dip | To rehabilitate Banita Cattle Dip to restore functionality | Banita Cattle Dip rehabilitated | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.06361, 35.941616 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2024-2025 | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 672000 | 96 | 672000 | 1882696 | 28000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Cyntak Ventures ltd. Assessor remarks: A toilet required and a shade.
2266 | Administration, Planning and Support Services | Construction Of Kamosop Cattle Dip | To construct Kamosop Cattle Dip | Kamosop Cattle Dip constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Solai | 0.01178, 36.144923 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2023 | 2000000 | 1990000 | 1990000 | Equitable | Equitable | 1990000 | 0 | 1990000 | 100 | 1990000 | 1990000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
2267 | Administration, Planning and Support Services | Construction Of Koimugul, Machine And Chelitit Cattle Dips | To construct Koimugul, Machine And Chelitit Cattle Dips | Koimugul, Machine And Chelitit Cattle Dips constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Solai | 0.151219, 36.19544 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2022 | 4000000 | 3999100 | 3999100 | Equitable | equitable | 3999100 | 0 | 3999100 | 100 | 3999100 | 3999100 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
2268 | Administration, Planning and Support Services | Construction Of Kwa Carry Cattle Dip | To construct Kwa Carry Cattle Dip | Kwa Carry Cattle Dip constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Solai | 0.01178, 36.144923 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2023 | 2000000 | 1800000 | 1800000 | Equitable | Equitable | 1800000 | 0 | 1800000 | 100 | 1800000 | 1800000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
2269 | Administration, Planning and Support Services | Construction of Limuru Cattle Dip and Renovation of Tuiyomoi cattle dip | To construct Limuru Cattle Dip and Renovation of Tuiyomoi cattle dip | Limuru Cattle Dip and Renovation of Tuiyomoi cattle dip constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Solai | 0.124977, 36.224388 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2022/23 | 2022/23 | 2025 | 2500000 | 2500000 | 2500000 | Equitable | EQUITABLE | 2500000 | 0 | 1957950 | 78.3 | 1957950 | 402050 | 542050 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The cattle dip is broken down all the posts have been eaten by termites.
2270 | Administration, Planning and Support Services | Construction Of Sachangwan Cattle Dip | To construct Sachangwan Cattle Dip | Sachangwan Cattle Dip constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Solai | 0.003207, 36.123313 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2022 | 2000000 | 2000000 | 2000000 | Equitable | equitable | 2000000 | 0 | 1960500 | 98 | 1960500 | 1800000 | 39500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Not functional.
2271 | Administration, Planning and Support Services | Construction Of Kapket Tea Buying Centre | To construct Kapket Tea Buying Centre | Kapket Tea Buying Centre constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Tinet | -0.520868 35.620393 2526.8999999999996 4 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 1500000 | 1499440 | 1499440 | Equitable | EQUITABLE | 1499440 | 0 | 852725 | 56.9 | 852725 | 100 | 646715 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
2272 | Administration, Planning and Support Services | Construction Of Tea Buying Centre At Chorwet Kiptenden | To construct Tea Buying Centre At Chorwet Kiptenden | Tea Buying Centre At Chorwet Kiptenden constructed | 3110599 | Other Infrastructure and Civil Works | Kuresoi South | Amalo | -0.584763 35.680692 2496 12 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 1300000 | 1300000 | 1300000 | Equitable | EQUITABLE | 1300000 | 0 | 1300000 | 100 | 1300000 | 1300000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Ongoing.
2273 | Administration, Planning and Support Services | Construction Of Tea Buying Centre At Saptet Kapkwen | To construct Tea Buying Centre At Saptet Kapkwen | Tea Buying Centre At Saptet Kapkwen constructed | 3110599 | Other Infrastructure and Civil Works | Kuresoi South | Amalo | -0.584673 35.680673 2593.1 4.800000190734863 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 1299170 | 1299170 | 1299170 | Equitable | EQUITABLE | 1299170 | 0 | 1215610 | 93.6 | 1215610 | 83560 | 83560 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: not yet. Viable: not yet. Assessor remarks: project ongoing.
2274 | Administration, Planning and Support Services | Construction Of Tebeswet Tea Buying Center | To construct Tebeswet Tea Buying Center | Tebeswet Tea Buying Center constructed | 3110599 | Other Infrastructure and Civil Works | Kuresoi South | Amalo | -0.653843, 35.62003 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2022 | 1199469 | 1199469 | 1199469 | Equitable | equitable | 1199469 | 0 | 1199469 | 100 | 1199469 | 1199469 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: no. Viable: no. Assessor remarks: project stalled.
2275 | Administration, Planning and Support Services | Fencing and installation of two gates at Gilgil slaughterhouse | To secure and installation of two gates at Gilgil slaughterhouse through fencing | And installation of two gates at Gilgil slaughterhouse fenced and secured | 3110599 | Other Infrastructure and Civil Works | Gilgil | Gilgil | -0.459991, 36.296639 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2022/23 | 2022/23 | 2022/23 | 2000000 | 2000000 | 2000000 | Equitable | EQUITABLE | 2000000 | 0 | 1974364 | 98.7 | 1974364 | 1974364 | 25636 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Macknox contractors. Assessor remarks: In good state.
2276 | Proposed Renovation Of Kibagenge Cattle Dip In Amalo Ward Kuresoi South Sub County | Proposed Renovation Of Kibagenge Cattle Dip In Amalo Ward Kuresoi South Sub County | To undertake the proposed Renovation Of Kibagenge Cattle Dip In Amalo Ward Kuresoi South Sub County | Proposed Renovation Of Kibagenge Cattle Dip In Amalo Ward Kuresoi South Sub County implemented | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 500000 | 499032 | 499032 | N/A | N/A | 499032 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
2277 | Administration, Planning and Support Services | Connection of electricity at Saptet farmers cooperative | To implement connection of electricity at saptet farmers cooperative for agricultural development and food production | Connection of electricity at Saptet farmers cooperative completed | 3110599 | Other Infrastructure and Civil Works | Kuresoi South | Keringet | -0.488112, 35.706482 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2022/23 | 2022/23 | 2024 | 300000 | 300000 | 300000 | Equitable | Equitable | 300000 | 0 | 1758000 | 586 | 1758000 | 300000 | -1458000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Underfunded.
2278 | Administration, Planning and Support Services | Connection of electricity at Teta Cooperative Society Milk Coolant | To implement connection of electricity at teta cooperative society milk coolant for agricultural development and food production | Connection of electricity at Teta Cooperative Society Milk Coolant completed | 3110599 | Other Infrastructure and Civil Works | Kuresoi South | Keringet | -0.465005, 35.623853 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2022/23 | 2022/23 | N/A | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 0 | 0 | 0 | 800000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Ongoing.
2279 | Crop Development and Management | Construction And Installation Of Potato Cold Store | To construct And Installation Of Potato Cold Store | And Installation Of Potato Cold Store constructed | 3110599 | Other Infrastructure and Civil Works | Kuresoi South | Keringet | -0.427544, 35.68904 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 5290000 | 5290000 | 5290000 | Equitable | EQUITABLE | 5290000 | 0 | 0 | 0 | 0 | 5290000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Vandalized and demolished.
2280 | Administration, Planning and Support Services | Completion Of Kasarani Slaughter House | To complete Kasarani Slaughter House | Kasarani Slaughter House completed | 3110599 | Other Infrastructure and Civil Works | Gilgil | Malewa West | -0.702703, 36.309037 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 1000000 | 1000000 | 1000000 | Equitable | Equitable | 1000000 | 0 | 1499999 | 150 | 1499999 | 1000000 | -499999 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Land has been encroached.
2281 | Administration, Planning and Support Services | Construction And Expansion Of Gatamaiyu Fish Pond | To construct And Expansion Of Gatamaiyu Fish Pond | And Expansion Of Gatamaiyu Fish Pond constructed | 3110599 | Other Infrastructure and Civil Works | Gilgil | Malewa West | -0.612613, 36.380458 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 500000 | 499800 | 499800 | Equitable | equitable | 499800 | 0 | 499800 | 100 | 499800 | 499800 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Partly. Viable: Partly. Assessor remarks: Need close monitoring of groups management.
2282 | Administration, Planning and Support Services | Completion Of Cereal Store At Msingi Mwema | To complete Cereal Store At Msingi Mwema | Cereal Store At Msingi Mwema completed | 3110599 | Other Infrastructure and Civil Works | Molo | Mariashoni | -0.340229, 35.808263 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 1000000 | 1000000 | Equitable | equitable | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Masonry walls do not exist.
2283 | Administration, Planning and Support Services | Construction Of Taita Slaughter Slab | To construct Taita Slaughter Slab | Taita Slaughter Slab constructed | 3110599 | Other Infrastructure and Civil Works | Kuresoi South | Tinet | -0.570268 35.61587 0 500 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | N/A | 1999838.44 | 1999838 | 1999838 | Equitable | N/A | 1999838 | 0 | 852725 | 42.6 | 852725 | 1699838 | 1147113 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Ongoing almost complete.
2284 | Fisheries Development | Acquisition of a Patrol/Rescue boat for Lake Solai | To procure a Patrol/Rescue boat for Lake Solai | A Patrol/Rescue boat for Lake Solai procured | 3110702 | N/A | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
2285 | Administration, Planning and Support Services | Purchase of 2 motorboats at Karagita Beach | To procure 2 motorboats at Karagita Beach | 2 motorboats at Karagita Beach procured | 3110702 | N/A | Naivasha | Hells Gate | -0.76238, 36.427085 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2022/23 | 2022/23 | 2022/23 | 3000000 | 3000000 | 3000000 | Equitable | EQUITABLE | 3000000 | 0 | 2939000 | 98 | 2939000 | 2939000 | 61000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The boats are really helping the BMU to cater for major needs in the lake.
2286 | Administration, Planning and Support Services | Buying Of Motor Boat For Kamere Beach Youth Groups And Beach Hustler Group | To procure Motor Boat For Kamere Beach Youth Groups And Beach Hustler Group | Motor Boat For Kamere Beach Youth Groups And Beach Hustler Group procured | 3110702 | N/A | Naivasha | Olkaria | -0.819698 36.322931 1932.699951171875 35.104000091552734 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 4000000 | 3965000 | 3965000 | Equitable | equitable | 3965000 | 0 | 3965000 | 100 | 3965000 | 3965000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Viable. Once the project is finished since there is no other hospital. Assessor remarks: The containers are being refurbished but handing over done.
2287 | Administration, Planning and Support Services | Purchase of Motorboat engine | To procure Motorboat engine | Motorboat engine procured | 3110702 | N/A | Naivasha | Olkaria | 0.830138 36.338593 1895.69951171875 27.18400001525879 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 1500000 | 1299800 | 1299800 | Equitable | Equitable | 1299800 | 0 | 1299800 | 100 | 1299800 | 1299800 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Sports equipment supplied and delivered to olkaria teams.
2288 | Equipping of ATC Soilo - acquisition of ICT equipment | Equipping of ATC Soilo - acquisition of ICT equipment | To equip ATC Soilo - acquisition of ICT equipment with necessary facilities and equipment | ATC Soilo - acquisition of ICT equipment equipped | 3111002 | Purchase of Computers, Printers and other IT Equipment | HQ | HQ | -0.173672, 35.862823 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2022/23 | 2022/23 | 2022/23 | 3000000 | 3000000 | 3000000 | N/A | N/A | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
2289 | Administration, Planning and Support Services | Purchase Of Livestock Support Equipments | To procure Livestock Support Equipments | Livestock Support Equipments procured | 3111103 | Purchase of Agricultural Machinery and Equipment | Gilgil | Elementaita | -0.596434 36.111478 2107.10009765625 68.11900329589844 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 4000000 | 4000000 | 4000000 | Equitable | equitable | 4000000 | 0 | 3940950 | 98.5 | 3940950 | 0 | 59050 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Basic equipments needed.
2290 | Fisheries Development | Procure and deliver of water Multi parameter Kits | To implement procure and deliver of water multi parameter kits for agricultural development and food production | Procure and deliver of water Multi parameter Kits completed | 3111104 | N/A | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 1000000 | 1000000 | 1000000 | Equitable | equitable | 1000000 | 0 | 999999 | 100 | 999999 | 0 | 1 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2291 | Administration, Planning and Support Services | Purchase And Supply Of Potato Value Addition Machine | To procure and supply Potato Value Addition Machine | Potato Value Addition Machine procured and supplied | 3111120 | Purchase of Specialized Plant. - | Kuresoi South | Amalo | -0.59184 35.68619 2549.500244140625 533.1409912109375 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | N/A | 600000 | 600000 | 600000 | Equitable | equitable | 600000 | 0 | 471340 | 78.6 | 471340 | 600000 | 128660 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: yes. Viable: Yes. Assessor remarks: facility fully operational.
2292 | Administration, Planning and Support Services | Purchase And Supply Of Incubators For Groups | To procure and supply Incubators For Groups | Incubators For Groups procured and supplied | 3111120 | Purchase of Specialized Plant. - | Nakuru West | Barut | 0.0353373 36.049 1834 2000 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 1500000 | 1500000 | 1500000 | Equitable | equitable | 1500000 | 0 | 1429200 | 95.3 | 1429200 | 0 | 70800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: No. Viable: No. Assessor remarks: It's yet to start.
2293 | Administration, Planning and Support Services | Kirima Milk Cooler - Installation Of Milk Cooler And Accessories | To implement kirima milk cooler - installation of milk cooler and accessories for agricultural development and food production | Kirima Milk Cooler - Installation Of Milk Cooler And Accessories completed | 3111120 | Purchase of Specialized Plant. - | Naivasha | Biashara-Naivasha | -0.632517, 36.488908 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2022 | 9000000 | 9000000 | 9000000 | Equitable | equitable | 9000000 | 0 | 8100000 | 90 | 8100000 | 5000000 | 900000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Working perfectly.
2294 | Administration, Planning and Support Services | Kirima Milk Cooler - Installation Of Three Phase Electricity Power And Highmast Lights | To implement kirima milk cooler - installation of three phase electricity power and highmast lights for agricultural development and food production | Kirima Milk Cooler - Installation Of Three Phase Electricity Power And Highmast Lights completed | 3111120 | Purchase of Specialized Plant. - | Naivasha | Biashara-Naivasha | -0.632653, 36.48875 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2022 | 1000000 | 1000000 | 1000000 | Equitable | equitable | 1000000 | 0 | 980084 | 98 | 980084 | 1000000 | 19916 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Working well.
2295 | Administration, Planning and Support Services | Purchase Of Egg Incubators | To procure Egg Incubators | Egg Incubators procured | 3111120 | Purchase of Specialized Plant. - | Nakuru East | Biashara-Nakuru | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 500000 | 500000 | 500000 | Equitable | equitable | 500000 | 0 | 497200 | 99.4 | 497200 | 0 | 2800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2296 | Administration, Planning and Support Services | Purchase And Supply Of Incubators | To procure and supply Incubators | Incubators procured and supplied | 3111120 | Purchase of Specialized Plant. - | Bahati | Dundori | -0.251659, 36.234072 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/2022 | 250000 | 250000 | 250000 | Equitable | equitable | 250000 | 0 | 244840 | 97.9 | 244840 | 0 | 5160 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: Yes. Contractor: Natasha ltd. Assessor remarks: No in good condition.
2297 | Administration, Planning and Support Services | Purchase Of Portable Deep Freezer For Daily Goat Farmers | To procure Portable Deep Freezer For Daily Goat Farmers | Portable Deep Freezer For Daily Goat Farmers procured | 3111120 | Purchase of Specialized Plant. - | Gilgil | Eburru/Mbaruk | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | N/A | 235000 | 226200 | 226200 | Equitable | equitable | 226200 | 0 | 0 | 0 | 0 | 226200 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
2298 | Administration, Planning and Support Services | Purchase Of Incubators And Fertilised Eggs For Youth And Women Empowerment | To procure Incubators And Fertilised Eggs For Youth And Women Empowerment | Incubators And Fertilised Eggs For Youth And Women Empowerment procured | 3111120 | Purchase of Specialized Plant. - | Gilgil | Gilgil | -0.507431 36.327348 1989.199951171875 12.510000228881836 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 1500000 | 1500000 | 1500000 | Equitable | equitable | 1500000 | 0 | 1458720 | 97.2 | 1458720 | 0 | 41280 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: The project description does not match whats on the ground.
2299 | Administration, Planning and Support Services | Procure, Deliver and Installation of Pyrethrum solar dryers | To implement procure, deliver and installation of pyrethrum solar dryers for agricultural development and food production | Procure, Deliver and Installation of Pyrethrum solar dryers completed | 3111120 | Purchase of Specialized Plant. - | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | N/A | 10000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1997000 | 99.9 | 1997000 | 2700003 | 3000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
2300 | Administration, Planning and Support Services | Purchase and installation of 3,000 litres Burgei Milk Cooler, Visoi Ward | To procure and install 3,000 litres Burgei Milk Cooler, Visoi Ward | 3,000 litres Burgei Milk Cooler, Visoi Ward procured and installed | 3111120 | Purchase of Specialized Plant. - | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | N/A | 4500000 | 4500000 | 4500000 | Equitable | N/A | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
2301 | Administration, Planning and Support Services | Purchase and installation of 3,000 litres Giachonge Milk cooler, Dundori ward | To procure and install 3,000 litres Giachonge Milk cooler, Dundori ward | 3,000 litres Giachonge Milk cooler, Dundori ward procured and installed | 3111120 | Purchase of Specialized Plant. - | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | N/A | 4500000 | 4500000 | 4500000 | Equitable | N/A | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
2302 | Administration, Planning and Support Services | Purchase and installation of 3,000 litres Kiribon Milk cooler, Menengai west Ward | To procure and install 3,000 litres Kiribon Milk cooler, Menengai west Ward | 3,000 litres Kiribon Milk cooler, Menengai west Ward procured and installed | 3111120 | Purchase of Specialized Plant. - | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | N/A | 4500000 | 4500000 | 4500000 | Equitable | N/A | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
2303 | Administration, Planning and Support Services | Purchase and installation of 3,000 litres Maiella milk cooler, Maiella Ward | To procure and install 3,000 litres Maiella milk cooler, Maiella Ward | 3,000 litres Maiella milk cooler, Maiella Ward procured and installed | 3111120 | Purchase of Specialized Plant. - | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | N/A | 4500000 | 4500000 | 4500000 | Equitable | N/A | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
2304 | Administration, Planning and Support Services | Purchase and installation of 3,000 litres Mutamaiyo milk Cooler, Elburgon ward | To procure and install 3,000 litres Mutamaiyo milk Cooler, Elburgon ward | 3,000 litres Mutamaiyo milk Cooler, Elburgon ward procured and installed | 3111120 | Purchase of Specialized Plant. - | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | N/A | 4500000 | 4500000 | 4500000 | Equitable | N/A | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
2305 | Administration, Planning and Support Services | Purchase and installation of 3,000 litres Ndabibi Milk Cooler, Maiella ward | To procure and install 3,000 litres Ndabibi Milk Cooler, Maiella ward | 3,000 litres Ndabibi Milk Cooler, Maiella ward procured and installed | 3111120 | Purchase of Specialized Plant. - | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | N/A | 4500000 | 4500000 | 4500000 | Equitable | N/A | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
2306 | Administration, Planning and Support Services | Purchase and installation of 3,000 litres Teta Milk Cooler, Kiptagich ward | To procure and install 3,000 litres Teta Milk Cooler, Kiptagich ward | 3,000 litres Teta Milk Cooler, Kiptagich ward procured and installed | 3111120 | Purchase of Specialized Plant. - | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | N/A | 4500000 | 4500000 | 4500000 | Equitable | N/A | 4500000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
2307 | Administration, Planning and Support Services | Purchase And Supply Of Chicken Incubators To Vulnerables | To procure and supply Chicken Incubators To Vulnerables | Chicken Incubators To Vulnerables procured and supplied | 3111120 | Purchase of Specialized Plant. - | Bahati | Kabatini | -0.215458, 36.16447 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2022 | 1000000 | 1000000 | 1000000 | Equitable | equitable | 1000000 | 0 | 992480 | 99.2 | 992480 | 0 | 7520 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Natash limited. Assessor remarks: Partially operational but consumes alot of electricity.
2308 | Administration, Planning and Support Services | Purchase And Installation Of Pulping Machine For Jumatato Sacco Cooperative | To procure and install Pulping Machine For Jumatato Sacco Cooperative | Pulping Machine For Jumatato Sacco Cooperative procured and installed | 3111120 | Purchase of Specialized Plant. - | Subukia | Kabazi | -0.13503 36.1535 0 2218 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | N/A | 2000000 | 2000000 | 2000000 | Equitable | equitable | 2000000 | 0 | 1000000 | 50 | 1000000 | 2000000 | 1000000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Delight pro ltd. Assessor remarks: Requires drying beds.
2309 | Administration, Planning and Support Services | Purchase Of Pulping Machine For Jumatatu Society | To procure Pulping Machine For Jumatatu Society | Pulping Machine For Jumatatu Society procured | 3111120 | Purchase of Specialized Plant. - | Subukia | Kabazi | -0.08223 36.16987 0 1381 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | N/A | 1900000 | 1900000 | 1900000 | Equitable | equitable | 1900000 | 0 | 0 | 0 | 0 | 1900000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: Not indicated. Assessor remarks: Machine was brought but transferred to subukia Valley coffee factory.
2310 | Administration, Planning and Support Services | Youth Empowerment (Purchase Of 10 Incubators) | To implement youth empowerment (purchase of 10 incubators) for agricultural development and food production | Youth Empowerment (Purchase Of 10 Incubators) completed | 3111120 | Purchase of Specialized Plant. - | Nakuru West | Kapkures | -0.324324 36.036613 0 2000 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | equitable | 1000000 | 0 | 991000 | 99.1 | 991000 | 1000000 | 9000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Has enhanced access to clean water. Assessor remarks: Done and in operation.
2311 | Administration, Planning and Support Services | Construction Of Milk Cooler At Saptet Center | To construct Milk Cooler At Saptet Center | Milk Cooler At Saptet Center constructed | 3111120 | Purchase of Specialized Plant. - | Kuresoi South | Keringet | -0.488075, 35.706518 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2022 | 1200000 | 1200000 | 1200000 | Equitable | equitable | 1200000 | 0 | 1758000 | 146.5 | 1758000 | 1758000 | -558000 | Yet to start/New | 0 | N/A | Insufficient Funds | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
2312 | Administration, Planning and Support Services | Purchase And Supply Of Eggs Incubators | To procure and supply Eggs Incubators | Eggs Incubators procured and supplied | 3111120 | Purchase of Specialized Plant. - | Kuresoi South | Keringet | -0.431263, 35.6896 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2022 | 1000000 | 998200 | 998200 | Equitable | equitable | 998200 | 0 | 666960 | 66.8 | 666960 | 998200 | 331240 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In use.
2313 | Administration, Planning and Support Services | Purchase And Supply Of Four 500 Eggs Capacity Incubators For Rurii Sub Location Nyumba Kumi Elders Empowerment,Heshima And Bethania Welfare Groups Empowerment | To procure and supply Four 500 Eggs Capacity Incubators For Rurii Sub Location Nyumba Kumi Elders Empowerment,Heshima And Bethania Welfare Groups Empowerment | Four 500 Eggs Capacity Incubators For Rurii Sub Location Nyumba Kumi Elders Empowerment,Heshima And Bethania Welfare Groups Empowerment procured and supplied | 3111120 | Purchase of Specialized Plant. - | Bahati | Kiamaina | -0.263544, 36.116767 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 300000 | 300000 | 300000 | Equitable | equitable | 300000 | 0 | 296400 | 98.8 | 296400 | 0 | 3600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Some are operational and others not.
2314 | Administration, Planning and Support Services | Purchase And Supply Of One Milk Atm Machine And One Cooking Oil Atm Machine For Kiamaina Sub Location Nyumba Kumi Leaders Empowerment | To procure and supply One Milk Atm Machine And One Cooking Oil Atm Machine For Kiamaina Sub Location Nyumba Kumi Leaders Empowerment | One Milk Atm Machine And One Cooking Oil Atm Machine For Kiamaina Sub Location Nyumba Kumi Leaders Empowerment procured and supplied | 3111120 | Purchase of Specialized Plant. - | Bahati | Kiamaina | -0.231627 36.116888 1940.699951171875 39.599998474121094 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | N/A | 200000 | 200000 | 200000 | Equitable | equitable | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | Insufficient Funds | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Not yet done. Assessor remarks: The project is yet to start.
2315 | Administration, Planning and Support Services | Purchase Of Incubators | To procure Incubators | Incubators procured | 3111120 | Purchase of Specialized Plant. - | Njoro | Kihingo | -0.433932 35.972208 2278.2001953125 27.77400016784668 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 500000 | 500000 | 500000 | Equitable | equitable | 500000 | 0 | 477000 | 95.4 | 477000 | 0 | 23000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Market construction ongoing.
2316 | Administration, Planning and Support Services | Construction of Kiptagich milk cooling plant | To construct Kiptagich milk cooling plant | Kiptagich milk cooling plant constructed | 3111120 | Purchase of Specialized Plant. - | Kuresoi South | Kiptagich | -0.574248, 35.617453 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2022/23 | 2022/23 | 15 June 2025 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1974700 | 98.7 | 1974700 | 1974700 | 25300 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Not yet. Viable: Viable. Assessor remarks: Need electricity for cooling plant to be operational.
2317 | Administration, Planning and Support Services | Youths/Women Empowerment(Incubators) | To implement youths/women empowerment(incubators) for agricultural development and food production | Youths/Women Empowerment(Incubators) completed | 3111120 | Purchase of Specialized Plant. - | Kuresoi South | Kiptagich | -0.59902 35.61123 2497.2000000000003 7.800000190734863 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 1300000 | 1297600 | 1297600 | Equitable | equitable | 1297600 | 0 | 1297600 | 100 | 1297600 | 1297600 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: No. Viable: Yes but needs not met. Assessor remarks: In bad condition.
2318 | Administration, Planning and Support Services | Purchase And Supply Of Incubators | To procure and supply Incubators | Incubators procured and supplied | 3111120 | Purchase of Specialized Plant. - | Kuresoi North | Kiptororo | -0.356669 35.481787 0 2099.9990234375 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | equitable | 1000000 | 0 | 991000 | 99.1 | 991000 | 1000000 | 9000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete and equiped requires paint.
2319 | Crop Development and Management | Purchase Of Hutcheries | To procure Hutcheries | Hutcheries procured | 3111120 | Purchase of Specialized Plant. - | Naivasha | Maai Mahiu | -0.881478, 36.489213 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 500000 | 488600 | 488600 | Equitable | EQUITABLE | 488600 | 0 | 488600 | 100 | 488600 | 488600 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functioning normally ,big challenge electricity.
2320 | Administration, Planning and Support Services | Completion, Purchase And Installation Of Milk Coolers In Central | To implement completion, purchase and installation of milk coolers in central for agricultural development and food production | Completion, Purchase And Installation Of Milk Coolers In Central completed | 3111120 | Purchase of Specialized Plant. - | Naivasha | Maiella | -0.729928, 36.230427 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2020 | 3500000 | 2168567 | 2168567 | Equitable | equitable | 2168567 | 0 | 2168567 | 100 | 2168567 | 2168567 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Prisconet system. Assessor remarks: Yes.
2321 | Administration, Planning and Support Services | Completion, Purchase And Installation Of Milk Coolers In Maiella | To implement completion, purchase and installation of milk coolers in maiella for agricultural development and food production | Completion, Purchase And Installation Of Milk Coolers In Maiella completed | 3111120 | Purchase of Specialized Plant. - | Naivasha | Maiella | -0.729928, 36.230427 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2020 | 3500000 | 2168567 | 2168567 | Equitable | equitable | 2168567 | 0 | 2168567 | 100 | 2168567 | 2168567 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Prisconet system. Assessor remarks: Yes.
2322 | Administration, Planning and Support Services | Purchase And Supply Of Incubators | To procure and supply Incubators | Incubators procured and supplied | 3111120 | Purchase of Specialized Plant. - | Naivasha | Maiella | -0.816635 36.262152 1868 19.700000762939453 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 1802000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Willpo Solutions Ltd. Assessor remarks: In Use.
2323 | Administration, Planning and Support Services | Malewa Youth And Women Group Incubator | To implement malewa youth and women group incubator for agricultural development and food production | Malewa Youth And Women Group Incubator completed | 3111120 | Purchase of Specialized Plant. - | Gilgil | Malewa West | -0.684685, 36.453053 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2021/22 | 998200 | 985100 | 985100 | Equitable | equitable | 985100 | 0 | 985100 | 100 | 985100 | 985100 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good project.
2324 | Administration, Planning and Support Services | Purchase And Supply Of Incubators (64 Eggs Incubators) | To procure and supply Incubators (64 Eggs Incubators) | Incubators (64 Eggs Incubators) procured and supplied | 3111120 | Purchase of Specialized Plant. - | Gilgil | Malewa West | -0.774775 36.291606 0 4300 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | N/A | 1000000 | 950000 | 950000 | Equitable | equitable | 950000 | 0 | 333469 | 35.1 | 333469 | 950000 | 616531 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good initiative.
2325 | Administration, Planning and Support Services | Construction Of A Potato Cooling Plant In Masai Centre In Mauche Ward | To construct A Potato Cooling Plant In Masai Centre In Mauche Ward | A Potato Cooling Plant In Masai Centre In Mauche Ward constructed | 3111120 | Purchase of Specialized Plant. - | Njoro | Mauche | -0.50456, 35.958508 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2021 | 5299999.48 | 5299999.48 | 5299999.48 | Equitable | equitable | 5299999.48 | 0 | 5299999 | 100 | 5299999 | 5299999 | 0.48 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: Not known. Assessor remarks: Solar panels vandalized and stolen.
2326 | Administration, Planning and Support Services | Purchase Of Incubators For Women Groups At Mauche Ward | To procure Incubators For Women Groups At Mauche Ward | Incubators For Women Groups At Mauche Ward procured | 3111120 | Purchase of Specialized Plant. - | Njoro | Mauche | -0.501888 35.980393 2406.1000000000004 12.199999809265137 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 1200000 | 1200000 | 1200000 | Equitable | equitable | 1200000 | 0 | 1143360 | 95.3 | 1143360 | 1924100 | 56640 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
2327 | Administration, Planning and Support Services | Purchase And Supply Of Eggs Incubators | To procure and supply Eggs Incubators | Eggs Incubators procured and supplied | 3111120 | Purchase of Specialized Plant. - | Rongai | Menengai West | -0.153605, 35.997195 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 500000 | 500000 | 500000 | Equitable | equitable | 500000 | 0 | 477000 | 95.4 | 477000 | 0 | 23000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
2328 | Administration, Planning and Support Services | Purchase And Supply Of Incubators And Purchase Of Eggs For Hatching | To procure and supply Incubators And Purchase Of Eggs For Hatching | Incubators And Purchase Of Eggs For Hatching procured and supplied | 3111120 | Purchase of Specialized Plant. - | Rongai | Mosop | -0.304303, 35.977943 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2022 | 1400000 | 1400000 | 1400000 | Equitable | equitable | 1400000 | 0 | 1285400 | 91.8 | 1285400 | 0 | 114600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: Good.
2329 | Administration, Planning and Support Services | Purchase of Incubators for Youth poultry Project at Mosop Ward | To procure Incubators for Youth poultry Project at Mosop Ward | Incubators for Youth poultry Project at Mosop Ward procured | 3111120 | Purchase of Specialized Plant. - | Rongai | Mosop | -0.299893 35.954843 2191.6000000000004 5 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2022/23 | 2022/23 | 2022/23 | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 0 | 0 | 0 | 700000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: Viable. Contractor: Not indicated. Assessor remarks: Not functioning.
2330 | Crop Development and Management | Purchase And Supply Of Incubators, Solar Panel Generators And Hatching Trays | To procure and supply Incubators, Solar Panel Generators And Hatching Trays | Incubators, Solar Panel Generators And Hatching Trays procured and supplied | 3111120 | Purchase of Specialized Plant. - | Naivasha | Olkaria | -0.938607 36.369038 1912.6000000000001 4.900000095367432 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 978500 | 978500 | Equitable | EQUITABLE | 978500 | 0 | 2969200 | 303.4 | 2969200 | 578500 | -1990700 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Understand construction still. Assessor remarks: Supply of modern jikos and 110litres sufuria not yet.
2331 | Administration, Planning and Support Services | Purchase And Supply Of Solar Powered Incubators | To procure and supply Solar Powered Incubators | Solar Powered Incubators procured and supplied | 3111120 | Purchase of Specialized Plant. - | Naivasha | Olkaria | 0.830138 36.338593 1895.69951171875 27.18400001525879 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 1000000 | 918000 | 918000 | Equitable | equitable | 918000 | 0 | 1996616 | 217.5 | 1996616 | 518000 | -1078616 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Sports equipment supplied and delivered to olkaria teams.
2332 | Administration, Planning and Support Services | Purchase And Supply Of Fishing Equipments For Kenyatta Dam | To procure and supply Fishing Equipments For Kenyatta Dam | Fishing Equipments For Kenyatta Dam procured and supplied | 3111120 | Purchase of Specialized Plant. - | Kuresoi North | Sirikwa | -0.29891, 35.63593 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2021/22 | 200000 | 200000 | 200000 | Equitable | equitable | 200000 | 0 | 199050 | 99.5 | 199050 | 200000 | 950 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes,,but proper documentation is needed when supplying the equipments. Assessor remarks: No fishing at the site,and no known individuals owning the equipments.
2333 | Administration, Planning and Support Services | Purchase And Supply Of Incubators | To procure and supply Incubators | Incubators procured and supplied | 3111120 | Purchase of Specialized Plant. - | Rongai | Soin | -0.055935 36.076458 1641.2 3.200000047683716 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 2000000 | 2000000 | Equitable | equitable | 2000000 | 0 | 1905600 | 95.3 | 1905600 | 1924100 | 94400 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Luki Contractors. Assessor remarks: Work done but needs regular maintenance.
2334 | Administration, Planning and Support Services | Purchase And Supply Of Milk Gallons | To procure and supply Milk Gallons | Milk Gallons procured and supplied | 3111120 | Purchase of Specialized Plant. - | Rongai | Soin | -0.055935 36.076458 1641.2 3.200000047683716 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | N/A | 1000000 | 1000000 | 1000000 | Equitable | Equitable | 1000000 | 0 | 1924100 | 192.4 | 1924100 | 500000 | -924100 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Luki Contractors. Assessor remarks: Work done but needs regular maintenance.
2335 | Administration, Planning and Support Services | Purchase Of 4 Manual Honey Extractor To Different Groups | To procure 4 Manual Honey Extractor To Different Groups | 4 Manual Honey Extractor To Different Groups procured | 3111120 | Purchase of Specialized Plant. - | Rongai | Soin | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 450000 | 370869 | 370869 | Equitable | equitable | 370869 | 0 | 370869 | 100 | 370869 | 370869 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2336 | Administration, Planning and Support Services | Purchase And Supply Of Taita Milk Cooler | To procure and supply Taita Milk Cooler | Taita Milk Cooler procured and supplied | 3111120 | Purchase of Specialized Plant. - | Kuresoi South | Tinet | -0.502635 35.680779 0 1600 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | N/A | 1500000 | 1500000 | 1500000 | Equitable | equitable | 1500000 | 0 | 0 | 0 | 0 | 1500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Land purchased.
2337 | Administration, Planning and Support Services | Purchase Of Egg Incubators For Farmers In Tinet Ward | To procure Egg Incubators For Farmers In Tinet Ward | Egg Incubators For Farmers In Tinet Ward procured | 3111120 | Purchase of Specialized Plant. - | Kuresoi South | Tinet | -0.502635 35.680779 0 1600 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 1000000 | 1000000 | 1000000 | Equitable | equitable | 1000000 | 0 | 952800 | 95.3 | 952800 | 0 | 47200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Land purchased.
2338 | Crop Development and Management | Purchase Of 174 Hatchery Capacity Incubators And Back Up Generators | To procure 174 Hatchery Capacity Incubators And Back Up Generators | 174 Hatchery Capacity Incubators And Back Up Generators procured | 3111120 | Purchase of Specialized Plant. - | Molo | Turi | -0.279395 35.753738 2477.9 9.800000190734863 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 650000 | 650000 | 650000 | Equitable | EQUITABLE | 650000 | 0 | 644000 | 99.1 | 644000 | 650000 | 6000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The land was bought by the county, the title of the land to be confirmed by the department.
2339 | Administration, Planning and Support Services | Purchase And Supply Of Incubators | To procure and supply Incubators | Incubators procured and supplied | 3111120 | Purchase of Specialized Plant. - | Rongai | Visoi | -0.119957 35.933578 1710.7 7 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 500000 | 500000 | 500000 | Equitable | equitable | 500000 | 0 | 477000 | 95.4 | 477000 | 0 | 23000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
2340 | Administration, Planning and Support Services | Rehabilitation Of Ambosket Dip | To rehabilitate Ambosket Dip to restore functionality | Ambosket Dip rehabilitated | 3111299 | Rehabilitation & Renovation - | Kuresoi South | Amalo | -0.588523 35.684659 2531.300048828125 77.5999984741211 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | N/A | 500000 | 500000 | 500000 | Equitable | equitable | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: works done well.
2341 | Administration, Planning and Support Services | Rehabilitation Of Kitoben Dip | To rehabilitate Kitoben Dip to restore functionality | Kitoben Dip rehabilitated | 3111299 | Rehabilitation & Renovation - | Kuresoi South | Amalo | -0.588523 35.684659 2531.300048828125 77.5999984741211 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | N/A | 406972 | 406972 | 406972 | Equitable | equitable | 406972 | 0 | 0 | 0 | 0 | 406972 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: works done well.
2342 | Administration, Planning and Support Services | Renovation Of Mulango Tea Buying Centre | To rehabilitate Mulango Tea Buying Centre to restore functionality | Mulango Tea Buying Centre rehabilitated | 3111299 | Rehabilitation & Renovation - | Kuresoi South | Kiptagich | -0.59592, 35.589018 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 800000 | 800000 | 800000 | Equitable | EQUITABLE | 800000 | 0 | 800000 | 100 | 800000 | 800000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Assessor remarks: Need table and electrification.
2343 | Administration, Planning and Support Services | Renovation Of Kandutura Cereal Store | To rehabilitate Kandutura Cereal Store to restore functionality | Kandutura Cereal Store rehabilitated | 3111299 | Rehabilitation & Renovation - | Rongai | Visoi | -0.13549 35.794188 2186.6000000000004 22 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 600000 | 600000 | 600000 | Equitable | equitable | 600000 | 0 | 524100 | 87.4 | 524100 | 600000 | 75900 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Poor because no county project.
2344 | Administration, Planning and Support Services | Purchase and supply of pyrethrum seedlings | To procure and supply pyrethrum seedlings | Pyrethrum seedlings procured and supplied | 3111301 | Purchase of Certified Crop Seed | Gilgil | Elementaita | -0.59591, 36.11219 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2022/23 | 2022/23 | 2022/23 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1600000 | 80 | 1600000 | 4000000 | 400000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Well done.
2345 | Administration, Planning and Support Services | Purchase and distribution of pyrethrum seedlings to farmers in Nakuru county | To procure and distribution of pyrethrum seedlings to farmers in Nakuru county | And distribution of pyrethrum seedlings to farmers in Nakuru county procured | 3111301 | Purchase of Certified Crop Seed | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2022/23 | 2022/23 | 2022/23 | 50000000 | 5839885 | 18339885 | Equitable | N/A | 18339885 | 0 | 37299997 | 638.7 | 37299997 | 2700003 | -31460112 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2346 | Crop Development and Management | Supply and Delivery of potato seedlings to farmers in Nakuru County | To implement supply and delivery of potato seedlings to farmers in nakuru county for agricultural development and food production | Supply and Delivery of potato seedlings to farmers in Nakuru County completed | 3111301 | Purchase of Certified Crop Seed | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2022/23 | 2022/23 | N/A | 20000000 | 0 | 17500000 | Equitable | Equitable | 17500000 | 0 | 32480684 | 0 | 32480684 | 2519316 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
2347 | Crop Development and Management | Purchase And Supply Of Dwaf Pawpaws To Nyondia Farmers | To procure and supply Dwaf Pawpaws To Nyondia Farmers | Dwaf Pawpaws To Nyondia Farmers procured and supplied | 3111301 | Purchase of Certified Crop Seed | Gilgil | Malewa West | -0.702703 36.471211 0 2000 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 2793371 | 2690800 | 2690800 | Equitable | EQUITABLE | 2690800 | 0 | 2690080 | 100 | 2690080 | 2690800 | 720 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
2348 | Administration, Planning and Support Services | Input support - purchase and supply of Kenya Seed Maize to vulnerable in Visoi Ward | To implement input support - purchase and supply of kenya seed maize to vulnerable in visoi ward for agricultural development and food production | Input support - purchase and supply of Kenya Seed Maize to vulnerable in Visoi Ward completed | 3111301 | Purchase of Certified Crop Seed | Rongai | Visoi | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | N/A | 1350000 | 0 | 1350000 | Equitable | equitable | 1350000 | 0 | 0 | 0 | 0 | 1350000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
2349 | Administration, Planning and Support Services | Purchase And Supply Of One Month Old Chicks | To procure and supply One Month Old Chicks | One Month Old Chicks procured and supplied | 3111302 | Purchase of Animals and Breeding Stock | Kuresoi South | Amalo | -0.59184 35.68619 2549.500244140625 533.1409912109375 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 500000 | 500000 | 500000 | Equitable | equitable | 500000 | 0 | 471340 | 94.3 | 471340 | 600000 | 28660 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: yes. Viable: Yes. Assessor remarks: facility fully operational.
2350 | Administration, Planning and Support Services | Purchase And Supply Of 1 Month Old Chicks For Barut Farmers | To procure and supply 1 Month Old Chicks For Barut Farmers | 1 Month Old Chicks For Barut Farmers procured and supplied | 3111302 | Purchase of Animals and Breeding Stock | Nakuru West | Barut | -0.324324, 36.054632 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2022 | 1500000 | 1500000 | 1500000 | Equitable | equitable | 1500000 | 0 | 1442800 | 96.2 | 1442800 | 0 | 57200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Frausand Limited. Assessor remarks: Most of the chicks matures and were sold,others died as well.
2351 | Administration, Planning and Support Services | Purchase And Supply Of Daily Goats To Groups | To procure and supply Daily Goats To Groups | Daily Goats To Groups procured and supplied | 3111302 | Purchase of Animals and Breeding Stock | Nakuru West | Barut | -0.32032, 36.05254 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 1637133 | 1637133 | 1637133 | Equitable | equitable | 1637133 | 0 | 1603390 | 97.9 | 1603390 | 0 | 33743 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Some were sold,some dies.
2352 | Administration, Planning and Support Services | Purchase And Supply Of One(1) Month Old Improved Kienyeji Chicks | To procure and supply One(1) Month Old Improved Kienyeji Chicks | One(1) Month Old Improved Kienyeji Chicks procured and supplied | 3111302 | Purchase of Animals and Breeding Stock | Bahati | Dundori | -0.263156, 36.187378 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/2022 | 1000318 | 1000318 | 1000318 | Equitable | equitable | 1000318 | 0 | 888155 | 88.8 | 888155 | 0 | 112163 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Can not be traced no record available.
2353 | Administration, Planning and Support Services | Supply Of Improved Kienyeji Chicken To Elburgon Farmers. | To implement supply of improved kienyeji chicken to elburgon farmers. for agricultural development and food production | Supply Of Improved Kienyeji Chicken To Elburgon Farmers. completed | 3111302 | Purchase of Animals and Breeding Stock | Molo | Elburgon | -0.294731 35.799338 0 838.1790161132812 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 1000289 | 183 | 183 | Equitable | equitable | 183 | 0 | 1000289 | 546606 | 1000289 | 183 | -1000106 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
2354 | Administration, Planning and Support Services | Purchase And Supply Of 1 Month Month Old Improved Kienyeji Chicks | To procure and supply 1 Month Month Old Improved Kienyeji Chicks | 1 Month Month Old Improved Kienyeji Chicks procured and supplied | 3111302 | Purchase of Animals and Breeding Stock | Gilgil | Elementaita | -0.566456, 36.117463 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 2997000 | 2997000 | Equitable | equitable | 2997000 | 0 | 2997000 | 100 | 2997000 | 2997000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Supplied to farmers.
2355 | Administration, Planning and Support Services | Purchase and supply of one month old chicks | To procure and supply one month old chicks | One month old chicks procured and supplied | 3111302 | Purchase of Animals and Breeding Stock | Gilgil | Elementaita | -0.566368, 36.116833 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2022/23 | 2022/23 | 2022/23 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3716290 | 92.9 | 3716290 | 10 | 283710 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
2356 | Administration, Planning and Support Services | Purchase And Supply Of One(1) Month Old Improved Kienyeji Chicks | To procure and supply One(1) Month Old Improved Kienyeji Chicks | One(1) Month Old Improved Kienyeji Chicks procured and supplied | 3111302 | Purchase of Animals and Breeding Stock | Gilgil | Elementaita | -0.566368, 36.116833 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2794200 | 93.1 | 2794200 | 2997000 | 205800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
2357 | Livestock Resource Management and Development | Acquisition and Delivery of Dairy Goats in Nakuru County | To procure and Delivery of Dairy Goats in Nakuru County | And Delivery of Dairy Goats in Nakuru County procured | 3111302 | Purchase of Animals and Breeding Stock | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 20000000 | 10000000 | 10000000 | Equitable | EQUITABLE | 10000000 | 0 | 9004900 | 90 | 9004900 | 0 | 995100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2358 | Livestock Resource Management and Development | Livestock Improvement project through acquisition of one(1) month old improved kienyeji chicks | To implement livestock improvement project through acquisition of one(1) month old improved kienyeji chicks for agricultural development and food production | Livestock Improvement project through acquisition of one(1) month old improved kienyeji chicks completed | 3111302 | Purchase of Animals and Breeding Stock | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 28000000 | 11500000 | 11500000 | Equitable | EQUITABLE | 11500000 | 0 | 11132287 | 96.8 | 11132287 | 0 | 367713 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2359 | Livestock Resource Management and Development | Livestock Improvement project through wool sheep breeding in Kiptagich | To implement livestock improvement project through wool sheep breeding in kiptagich for agricultural development and food production | Livestock Improvement project through wool sheep breeding in Kiptagich completed | 3111302 | Purchase of Animals and Breeding Stock | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 11500000 | 1500000 | 1500000 | Equitable | EQUITABLE | 1500000 | 0 | 11132287 | 742.2 | 11132287 | 0 | -9632287 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2360 | Fisheries Development | Procure and restock fingerlings in dams and ponds | To implement procure and restock fingerlings in dams and ponds for agricultural development and food production | Procure and restock fingerlings in dams and ponds completed | 3111302 | Purchase of Animals and Breeding Stock | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 5000000 | 1500000 | 1500000 | Equitable | equitable | 1500000 | 0 | 1414000 | 94.3 | 1414000 | 0 | 86000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2361 | Fisheries Development | Restocking of fingerlings to Lake Naivasha | To implement restocking of fingerlings to lake naivasha for agricultural development and food production | Restocking of fingerlings to Lake Naivasha completed | 3111302 | Purchase of Animals and Breeding Stock | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2022/23 | 2022/23 | 2022/23 | 10000000 | 0 | 5000000 | Equitable | equitable | 5000000 | 0 | 2386000 | 100 | 2386000 | 4533338 | -2386000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2362 | Administration, Planning and Support Services | Purchase Of Daily Goats For Youths And Women Groups In Hellsgate Ward | To procure Daily Goats For Youths And Women Groups In Hellsgate Ward | Daily Goats For Youths And Women Groups In Hellsgate Ward procured | 3111302 | Purchase of Animals and Breeding Stock | Naivasha | Hells Gate | -0.792492 36.442714 1955.699951171875 9.182999610900879 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 3000000 | 3000000 | 3000000 | Equitable | equitable | 3000000 | 0 | 2983100 | 99.4 | 2983100 | 0 | 16900 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is complete but not in use.
2363 | Administration, Planning and Support Services | Purchase Of Poultry Chicks For Women And Youth Groups In Hellsgate Wa | To procure Poultry Chicks For Women And Youth Groups In Hellsgate Wa | Poultry Chicks For Women And Youth Groups In Hellsgate Wa procured | 3111302 | Purchase of Animals and Breeding Stock | Naivasha | Hells Gate | -0.810806, 36.467528 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 3500000 | 3500000 | 3500000 | Equitable | equitable | 3500000 | 0 | 3349656 | 95.7 | 3349656 | 0 | 150344 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The empowerment project was good done at a cost of 2,750,551.
2364 | Administration, Planning and Support Services | Purchase And Supply Of Eggs Incubators | To procure and supply Eggs Incubators | Eggs Incubators procured and supplied | 3111302 | Purchase of Animals and Breeding Stock | Kuresoi South | Keringet | -0.431263, 35.6896 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2022 | 700000 | 700000 | 700000 | Equitable | equitable | 700000 | 0 | 666960 | 95.3 | 666960 | 998200 | 33040 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In use.
2365 | Administration, Planning and Support Services | Purchase And Supply of approved One Month Improved Kienyeji Old Chicks | To procure and supply approved One Month Improved Kienyeji Old Chicks | Approved One Month Improved Kienyeji Old Chicks procured and supplied | 3111302 | Purchase of Animals and Breeding Stock | Bahati | Kiamaina | -0.231542, 36.116878 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 3400000 | 0 | 3400000 | Equitable | equitable | 3400000 | 0 | 3393828 | 0 | 3393828 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: No. Assessor remarks: The chicks are untraceable, some died and others were sold.
2366 | Administration, Planning and Support Services | Purchase And Supply of One Month Improved Kienyeji Old Chicks | To procure and supply One Month Improved Kienyeji Old Chicks | One Month Improved Kienyeji Old Chicks procured and supplied | 3111302 | Purchase of Animals and Breeding Stock | Naivasha | Lakeview | -0.727934, 36.432601 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 3000000 | 0 | 3000000 | Equitable | equitable | 3000000 | 0 | 2994400 | 0 | 2994400 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The chicks were distributed.
2367 | Administration, Planning and Support Services | Purchase And Supply Of Piglets For Youth And Women Groups | To procure and supply Piglets For Youth And Women Groups | Piglets For Youth And Women Groups procured and supplied | 3111302 | Purchase of Animals and Breeding Stock | Nakuru West | London | -0.281352 36.0759 1837.5 10 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 800000 | 800000 | 800000 | Equitable | equitable | 800000 | 0 | 781910 | 97.7 | 781910 | 0 | 18090 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
2368 | Administration, Planning and Support Services | Purchase And Supply of pigs (pregnant sow) - large white pure breed | To procure and supply pigs (pregnant sow) - large white pure breed | Pigs (pregnant sow) - large white pure breed procured and supplied | 3111302 | Purchase of Animals and Breeding Stock | Nakuru West | London | -0.281352 36.0759 1837.5 10 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 1000000 | 0 | 1000000 | Equitable | equitable | 1000000 | 0 | 998050 | 0 | 998050 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
2369 | Administration, Planning and Support Services | Purchase of dairy goats across the Ward | To procure dairy goats across the Ward | Dairy goats across the Ward procured | 3111302 | Purchase of Animals and Breeding Stock | Naivasha | Maai Mahiu | -0.885078, 36.499483 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2022/23 | 2022/23 | 2022/23 | 5000000 | 5000000 | 5000000 | Equitable | Equitable | 5000000 | 0 | 4805000 | 96.1 | 4805000 | 488600 | 195000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: If need be avail vaccination for goats.
2370 | Administration, Planning and Support Services | Purchase Of Chick And Eggs For Farmers In Maiella Ward | To procure Chick And Eggs For Farmers In Maiella Ward | Chick And Eggs For Farmers In Maiella Ward procured | 3111302 | Purchase of Animals and Breeding Stock | Naivasha | Maiella | -0.816635 36.262152 1868 19.700000762939453 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 3000000 | 3000000 | 3000000 | Equitable | equitable | 3000000 | 0 | 2999272 | 100 | 2999272 | 300000 | 728 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Willpo Solutions Ltd. Assessor remarks: In Use.
2371 | Administration, Planning and Support Services | Purchase And Supply Fingerlings And (Fish Feeds) For Youth And Women Groups In Malewa West Ward | To procure and supply Fingerlings And (Fish Feeds) For Youth And Women Groups In Malewa West Ward | Fingerlings And (Fish Feeds) For Youth And Women Groups In Malewa West Ward procured and supplied | 3111302 | Purchase of Animals and Breeding Stock | Gilgil | Malewa West | -0.702703 36.471211 0 2000 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 1000000 | 1000000 | 1000000 | Equitable | equitable | 1000000 | 0 | 956800 | 95.7 | 956800 | 0 | 43200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
2372 | Administration, Planning and Support Services | Purchase Of Milk Goats For Women Empowerment | To procure Milk Goats For Women Empowerment | Milk Goats For Women Empowerment procured | 3111302 | Purchase of Animals and Breeding Stock | Gilgil | Malewa West | -0.702703 36.291018 0 2000 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 1000000 | 1000000 | 1000000 | Equitable | equitable | 1000000 | 0 | 993000 | 99.3 | 993000 | 0 | 7000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need continuous improvement.
2373 | Administration, Planning and Support Services | Purchase Of Improved Kienyeji Chicken For Farmers Group | To procure Improved Kienyeji Chicken For Farmers Group | Improved Kienyeji Chicken For Farmers Group procured | 3111302 | Purchase of Animals and Breeding Stock | Molo | Mariashoni | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 1901773 | 1901773 | 1901773 | Equitable | equitable | 1901773 | 0 | 1859150 | 97.8 | 1859150 | 0 | 42623 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2374 | Administration, Planning and Support Services | Purchase Of Dairy Goats For Women Groups In Mauche Ward | To procure Dairy Goats For Women Groups In Mauche Ward | Dairy Goats For Women Groups In Mauche Ward procured | 3111302 | Purchase of Animals and Breeding Stock | Njoro | Mauche | -0.528462 36.006998 2358.2 5.800000190734863 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 1924100 | 1924100 | Equitable | Equitable | 1924100 | 0 | 1924100 | 100 | 1924100 | 1924100 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Needs improvement.
2375 | Administration, Planning and Support Services | Purchase Of One Month Old Chicks For Farmers At Mauche Ward | To procure One Month Old Chicks For Farmers At Mauche Ward | One Month Old Chicks For Farmers At Mauche Ward procured | 3111302 | Purchase of Animals and Breeding Stock | Njoro | Mauche | -0.501888 35.980393 2406.1000000000004 12.199999809265137 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 3000000 | 3000000 | 3000000 | Equitable | equitable | 3000000 | 0 | 3000000 | 100 | 3000000 | 1924100 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
2376 | Crop Development and Management | Kiratina Great Women Co-Op Society Supply Of 1 Day Old Chicks | To implement kiratina great women co-op society supply of 1 day old chicks for agricultural development and food production | Kiratina Great Women Co-Op Society Supply Of 1 Day Old Chicks completed | 3111302 | Purchase of Animals and Breeding Stock | Nakuru East | Menengai | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | EQUITABLE | 2000000 | 0 | 2000000 | 100 | 2000000 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2377 | Administration, Planning and Support Services | Menengai Ward Supply Of 1 Day Old Chicks To Plwd | To implement menengai ward supply of 1 day old chicks to plwd for agricultural development and food production | Menengai Ward Supply Of 1 Day Old Chicks To Plwd completed | 3111302 | Purchase of Animals and Breeding Stock | Nakuru East | Menengai | -0.275696 36.115354 1856.300048828125 19.395999908447266 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | equitable | 1000000 | 0 | 980441 | 98 | 980441 | 1000000 | 19559 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional but needs renovation.
2378 | Administration, Planning and Support Services | Purchase And Supply Of Goats For Kiratina Youths | To procure and supply Goats For Kiratina Youths | Goats For Kiratina Youths procured and supplied | 3111302 | Purchase of Animals and Breeding Stock | Nakuru East | Menengai | -0.269251 36.099069 1908.0999755859375 57.066001892089844 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 500000 | 500000 | 500000 | Equitable | equitable | 500000 | 0 | 490000 | 98 | 490000 | 0 | 10000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not functional.
2379 | Administration, Planning and Support Services | Supple of one month old chicks | To implement supple of one month old chicks for agricultural development and food production | Supple of one month old chicks completed | 3111302 | Purchase of Animals and Breeding Stock | Nakuru East | Menengai | -0.266298 36.100687 1913.5 100 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2022/23 | 2022/23 | 2022/23 | 1000000 | 1000000 | 1000000 | Equitable | EQUITABLE | 1000000 | 0 | 947850 | 94.8 | 947850 | 947850 | 52150 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: Lumiseal enterprise. Assessor remarks: Complete.
2380 | Administration, Planning and Support Services | Supply of one month old chicks for Menengai Ward PLWD Group | To implement supply of one month old chicks for menengai ward plwd group for agricultural development and food production | Supply of one month old chicks for Menengai Ward PLWD Group completed | 3111302 | Purchase of Animals and Breeding Stock | Nakuru East | Menengai | -0.266245 36.100625 1913.5 20 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2022/23 | 2022/23 | 2022/23 | 1000000 | 4000000 | 4000000 | Equitable | EQUITABLE | 4000000 | 0 | 3715250 | 92.9 | 3715250 | 80000 | 284750 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Lewamu construction. Assessor remarks: Completed.
2381 | Administration, Planning and Support Services | Purchase And Supply Of One Month Old Chicks | To procure and supply One Month Old Chicks | One Month Old Chicks procured and supplied | 3111302 | Purchase of Animals and Breeding Stock | Rongai | Menengai West | -0.140932, 35.960531 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 7000000 | 4000000 | 7000000 | Equitable | equitable | 7000000 | 0 | 6658561 | 166.5 | 6658561 | 0 | -2658561 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Partially. Viable: Yes. Assessor remarks: Needs review.
2382 | Livestock Resource Management and Development | Supply Of Pourtry Chicks To Welfare Groups | To implement supply of pourtry chicks to welfare groups for agricultural development and food production | Supply Of Pourtry Chicks To Welfare Groups completed | 3111302 | Purchase of Animals and Breeding Stock | Molo | Molo Central | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | N/A | 1700000 | 1700000 | 1700000 | Equitable | N/A | 1700000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
2383 | Administration, Planning and Support Services | Purchase Of One Month Old Improved Kienyeji Chicks For Women Group In Nessuit Ward | To procure One Month Old Improved Kienyeji Chicks For Women Group In Nessuit Ward | One Month Old Improved Kienyeji Chicks For Women Group In Nessuit Ward procured | 3111302 | Purchase of Animals and Breeding Stock | Njoro | Nessuit | -0.370185 35.906144 2335.897705078125 5.4710001945495605 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 4038195 | 4038195 | 4038195 | Equitable | equitable | 4038195 | 0 | 3925130 | 97.2 | 3925130 | 0 | 113065 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road requires improvement.
2384 | Administration, Planning and Support Services | Supply Of One Month Old Chicks | To implement supply of one month old chicks for agricultural development and food production | Supply Of One Month Old Chicks completed | 3111302 | Purchase of Animals and Breeding Stock | Njoro | Njoro | -0.326792 35.940977 2151.900146484375 9.845999717712402 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 3000000 | 3000000 | 3000000 | Equitable | equitable | 3000000 | 0 | 2995880 | 99.9 | 2995880 | 0 | 4120 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Samues merchants. Assessor remarks: Well done project.
2385 | Administration, Planning and Support Services | Purchase And Supply of One Month Improved Kienyeji Old Chicks | To procure and supply One Month Improved Kienyeji Old Chicks | One Month Improved Kienyeji Old Chicks procured and supplied | 3111302 | Purchase of Animals and Breeding Stock | Naivasha | Olkaria | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | N/A | 2000000 | 0 | 2000000 | Equitable | EQUITABLE | 2000000 | 0 | 1996616 | 0 | 1996616 | 1896500 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
2386 | Administration, Planning and Support Services | Purchase And Supply Of One Month Old Kienyeji Chicks | To procure and supply One Month Old Kienyeji Chicks | One Month Old Kienyeji Chicks procured and supplied | 3111302 | Purchase of Animals and Breeding Stock | Kuresoi North | Sirikwa | -0.235177 35.662557 2740.7999999999997 13.399999618530273 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 3000000 | 3000000 | 3000000 | Equitable | equitable | 3000000 | 0 | 2970600 | 99 | 2970600 | 200000 | 29400 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Signs of leaking roof noted, peeling of Wall paint, gutters need fixing.
2387 | Administration, Planning and Support Services | Purchase And Supply Of Dairy Goats | To procure and supply Dairy Goats | Dairy Goats procured and supplied | 3111302 | Purchase of Animals and Breeding Stock | Rongai | Soin | -0.055935 36.076458 1641.2 3.200000047683716 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 1924100 | 1924100 | Equitable | Equitable | 1924100 | 0 | 1924100 | 100 | 1924100 | 1924100 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Luki Contractors. Assessor remarks: Work done but needs regular maintenance.
2388 | Administration, Planning and Support Services | Purchase And Supply Of One Month Old Improved Kienyeji Chicks | To procure and supply One Month Old Improved Kienyeji Chicks | One Month Old Improved Kienyeji Chicks procured and supplied | 3111302 | Purchase of Animals and Breeding Stock | Subukia | Subukia | 0.002518 36.230234 1991.4000244140625 33.17599868774414 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 1200000 | 1200000 | 1200000 | Equitable | equitable | 1200000 | 0 | 1173120 | 97.8 | 1173120 | 997800 | 26880 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Residents, patients and staff now have interrupted power supply.. Viable: Yes. Power outages have since been resolved.. Assessor remarks: The power generator was a donation from Gilgil Sub county hospital. The funds initially allocated to the purchase of a new power generator were reallocated via public participation to other uses within the same facility, particularly the renovation works for Subukia sub County hospital old wing..
2389 | Administration, Planning and Support Services | Purchase Of Poultry Chicks For Farmer Groups In Tinet Ward | To procure Poultry Chicks For Farmer Groups In Tinet Ward | Poultry Chicks For Farmer Groups In Tinet Ward procured | 3111302 | Purchase of Animals and Breeding Stock | Kuresoi South | Tinet | -0.502635 35.680779 0 1600 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 2000000 | 2000000 | Equitable | equitable | 2000000 | 0 | 1962495 | 98.1 | 1962495 | 0 | 37505 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Land purchased.
2390 | Administration, Planning and Support Services | Supply Of Poultry Chicks To Welfare Groups In Turi Ward | To implement supply of poultry chicks to welfare groups in turi ward for agricultural development and food production | Supply Of Poultry Chicks To Welfare Groups In Turi Ward completed | 3111302 | Purchase of Animals and Breeding Stock | Molo | Turi | -0.285788 35.742842 2682.1 9.300000190734863 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 1000000 | 1000000 | 1000000 | Equitable | equitable | 1000000 | 0 | 977258 | 97.7 | 977258 | 0 | 22742 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: This is a road hence no documentation.
2391 | Administration, Planning and Support Services | Avocado promotion in the County | To implement avocado promotion in the county for agricultural development and food production | Avocado promotion in the County completed | 3111305 | Beautification and Tree Planting | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2022/23 | N/A | 45000000 | 25000000 | 40000000 | Equitable | N/A | 40000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
2392 | Administration, Planning and Support Services | Purchase of avocado seedlings | To procure avocado seedlings | Avocado seedlings procured | 3111305 | Beautification and Tree Planting | Subukia | Subukia | -0.025302, 36.216638 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2022/23 | 2022/23 | 2022/2023 | 4500000 | 3840551.06 | 3840551.06 | Equitable | Equitable | 3840551.06 | 0 | 3840551 | 100 | 3840551 | 0 | 0.06 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: Avocado trees doing well in the farms.
2393 | Farm Input Support - Purchase and Supply of Bio Fertilizer Mycorrhizal | Farm Input Support - Purchase and Supply of Bio Fertilizer Mycorrhizal | To implement farm input support - purchase and supply of bio fertilizer mycorrhizal for agricultural development and food production | Farm Input Support - Purchase and Supply of Bio Fertilizer Mycorrhizal completed | 3111399 | Purchase. of Certified Seeds - Ot | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | N/A | 25000000 | 0 | 25000000 | Equitable | N/A | 25000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
2394 | Pyrethrum promotion in the County | Pyrethrum promotion in the County | To implement pyrethrum promotion in the county for agricultural development and food production | Pyrethrum promotion in the County completed | 3111399 | Purchase. of Certified Seeds - Ot | HQ | HQ | -0.173672, 35.862823 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 50000000 | 20000000 | 20000000 | N/A | N/A | 20000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
2395 | Administration, Planning and Support Services | Farm Input Support - Purchase and Supply of Bio Fertilizer to Farmers | To implement farm input support - purchase and supply of bio fertilizer to farmers for agricultural development and food production | Farm Input Support - Purchase and Supply of Bio Fertilizer to Farmers completed | 3111399 | Purchase. of Certified Seeds - Ot | Kuresoi North | Kamara | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 3000000 | 0 | 2991655 | Equitable | equitable | 2991655 | 0 | 2991500 | 0 | 2991500 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2396 | Administration, Planning and Support Services | Farm Input Support - Purchase and Supply of Bio Fertilizer to Farmers | To implement farm input support - purchase and supply of bio fertilizer to farmers for agricultural development and food production | Farm Input Support - Purchase and Supply of Bio Fertilizer to Farmers completed | 3111399 | Purchase. of Certified Seeds - Ot | Kuresoi North | Kiptororo | -0.302533 35.5297 0 800 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 2300000 | 0 | 2300000 | Equitable | equitable | 2300000 | 0 | 2299580 | 0 | 2299580 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yess. Viable: Yess. Assessor remarks: In a better state of repair.
2397 | Administration, Planning and Support Services | Farm Input Support - Purchase and Supply of Bio Fertilizer to Farmers | To implement farm input support - purchase and supply of bio fertilizer to farmers for agricultural development and food production | Farm Input Support - Purchase and Supply of Bio Fertilizer to Farmers completed | 3111399 | Purchase. of Certified Seeds - Ot | Bahati | Lanet/Umoja | -0.248637, 36.168119 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 1300000 | 0 | 1200000 | Equitable | equitable | 1200000 | 0 | 1199700 | 0 | 1199700 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
2398 | Administration, Planning and Support Services | Farm Input Support - Purchase and Supply of Bio Fertilizer to Farmers | To implement farm input support - purchase and supply of bio fertilizer to farmers for agricultural development and food production | Farm Input Support - Purchase and Supply of Bio Fertilizer to Farmers completed | 3111399 | Purchase. of Certified Seeds - Ot | Molo | Mariashoni | -0.366176, 35.819734 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 1300000 | 0 | 1300000 | Equitable | equitable | 1300000 | 0 | 1299520 | 0 | 1299520 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Parltly. Viable: Yes. Assessor remarks: It was implemented but the food produce was below expected.
2399 | Administration, Planning and Support Services | Farm Input Support - Purchase and Supply of Bio Fertilizer to Farmers | To implement farm input support - purchase and supply of bio fertilizer to farmers for agricultural development and food production | Farm Input Support - Purchase and Supply of Bio Fertilizer to Farmers completed | 3111399 | Purchase. of Certified Seeds - Ot | Njoro | Mauche | -0.497747 35.960893 2477.6000000000004 12.399999618530273 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 4800000 | 0 | 4800000 | Equitable | equitable | 4800000 | 0 | 4799420 | 0 | 4799420 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
2400 | Administration, Planning and Support Services | Input support -Purchase and supply of Bio fertilizer to farmer | To implement input support -purchase and supply of bio fertilizer to farmer for agricultural development and food production | Input support -Purchase and supply of Bio fertilizer to farmer completed | 3111399 | Purchase. of Certified Seeds - Ot | Njoro | Nessuit | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 4980000 | 0 | 4980000 | Equitable | equitable | 4980000 | 0 | 4979840 | 0 | 4979840 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2401 | Administration, Planning and Support Services | Farm Input Support - Purchase and Supply of Bio Fertilizer to Farmers | To implement farm input support - purchase and supply of bio fertilizer to farmers for agricultural development and food production | Farm Input Support - Purchase and Supply of Bio Fertilizer to Farmers completed | 3111399 | Purchase. of Certified Seeds - Ot | Kuresoi North | Nyota | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 800200 | 0 | 800200 | Equitable | equitable | 800200 | 0 | 799800 | 0 | 799800 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2402 | Administration, Planning and Support Services | Farm Input Support - Purchase and Supply of Bio Fertilizer to Farmers | To implement farm input support - purchase and supply of bio fertilizer to farmers for agricultural development and food production | Farm Input Support - Purchase and Supply of Bio Fertilizer to Farmers completed | 3111399 | Purchase. of Certified Seeds - Ot | Kuresoi North | Sirikwa | -0.257498 35.721115 2517.2001953125 24 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 3400000 | 0 | 3400000 | Equitable | equitable | 3400000 | 0 | 3399460 | 0 | 3399460 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Drainage works, grading and murraming,.
2403 | Administration, Planning and Support Services | Farm Input Support - Purchase and Supply of Bio Fertilizer to Farmers | To implement farm input support - purchase and supply of bio fertilizer to farmers for agricultural development and food production | Farm Input Support - Purchase and Supply of Bio Fertilizer to Farmers completed | 3111399 | Purchase. of Certified Seeds - Ot | Subukia | Waseges | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 0 | 2000000 | Equitable | Equitable | 2000000 | 0 | 1955029 | 0 | 1955029 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2404 | Administration, Planning and Support Services | Erecting Of A Fence Around Olenguruone Dairies Society | To implement erecting of a fence around olenguruone dairies society for agricultural development and food production | Erecting Of A Fence Around Olenguruone Dairies Society completed | 4130299 | N/A | Kuresoi South | Amalo | -0.592109, 35.684406 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2017/18 | 2017/18 | 2023 | 2000000 | 1999608 | 1999608 | Equitable | Equitable | 1999608 | 0 | 0 | 0 | 0 | 1999608 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: yes. Assessor remarks: project on progress.
2405 | Construction Of Tea Buying Centres At Ambusket, Chelalang, Saosa And Tuiyobei | Construction Of Tea Buying Centres At Ambusket, Chelalang, Saosa And Tuiyobei | To construct Tea Buying Centres At Ambusket, Chelalang, Saosa And Tuiyobei | Tea Buying Centres At Ambusket, Chelalang, Saosa And Tuiyobei constructed | 4130299 | N/A | Kuresoi South | Amalo | -0.615343 35.656623 2472.1 55.29999923706055 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | N/A | 2761228.5 | 2761228.5 | 2761228.5 | Equitable | equitable | 2761228.5 | 0 | 891679 | 32.3 | 891679 | 279520 | 1869549.5 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
2406 | Administration, Planning and Support Services | ATC (8 Km) Farm Perimeter / Concrete Pillar Posts / Chain Link | To implement atc (8 km) farm perimeter / concrete pillar posts / chain link for agricultural development and food production | ATC (8 Km) Farm Perimeter / Concrete Pillar Posts / Chain Link completed | 4130299 | N/A | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | N/A | 622823.8 | 48.2 | 48.2 | Equitable | equitable | 48.2 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
2407 | Administration, Planning and Support Services | Construction Of Data Collection Shades At Fish Landing Beaches.. | To construct Data Collection Shades At Fish Landing Beaches | Data Collection Shades At Fish Landing Beaches constructed | 4130299 | N/A | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | N/A | 999800 | 999800 | 999800 | Equitable | equitable | 999800 | 0 | 0 | 0 | 0 | 999800 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
2408 | Administration, Planning and Support Services | Counterpart Funding - Purchase Of Pulping Machine For Jumatatu Society In Kabazi | To implement counterpart funding - purchase of pulping machine for jumatatu society in kabazi for agricultural development and food production | Counterpart Funding - Purchase Of Pulping Machine For Jumatatu Society In Kabazi completed | 4130299 | N/A | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | N/A | 591600 | 591600 | 591600 | Equitable | equitable | 591600 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
2409 | Administration, Planning and Support Services | Development, Demarcation, Provision Of Tap Water And Fencing And Kamere Beach Area, Naivasha | To implement development, demarcation, provision of tap water and fencing and kamere beach area, naivasha for agricultural development and food production | Development, Demarcation, Provision Of Tap Water And Fencing And Kamere Beach Area, Naivasha completed | 4130299 | N/A | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | N/A | 1497908 | 1497908 | 1497908 | Equitable | equitable | 1497908 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
2410 | Administration, Planning and Support Services | Potato Stores In Kuresoi South And Njoro | To implement potato stores in kuresoi south and njoro for agricultural development and food production | Potato Stores In Kuresoi South And Njoro completed | 4130299 | N/A | HQ | HQ | N/A | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | N/A | 2998855.2 | 2998855 | 2998855 | Equitable | equitable | 2998855 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
2411 | Administration, Planning and Support Services | Construction Of Seger Kap Mugei Tea Buying Centre | To construct Seger Kap Mugei Tea Buying Centre | Seger Kap Mugei Tea Buying Centre constructed | 4130299 | N/A | Kuresoi South | Kiptagich | -0.631137, 35.606343 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2022 | 400000 | 400000 | 400000 | Equitable | equitable | 400000 | 0 | 349980 | 87.5 | 349980 | 400000 | 50020 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Viable but still under construction. Contractor: Don't know. Assessor remarks: The project is ongoing. No painting, no table tops and no toilets..
2412 | Administration, Planning and Support Services | Construction Of Tuyobei Ketit Tea Buying Centre | To construct Tuyobei Ketit Tea Buying Centre | Tuyobei Ketit Tea Buying Centre constructed | 4130299 | N/A | Kuresoi South | Kiptagich | -0.599537 35.609858 2621.7000000000003 7.800000190734863 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | 2018/19 | 800000 | 726010 | 726010 | Equitable | Equitable | 726010 | 0 | 726010 | 100 | 726010 | 726010 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes, expected to meet the needs of the residents. Assessor remarks: Ongoing.
2413 | Administration, Planning and Support Services | Purchase And Supply Of Goats | To procure and supply Goats | Goats procured and supplied | 4130299 | N/A | Subukia | Subukia | 0.002518 36.230234 1991.4000244140625 33.17599868774414 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 997800 | 997800 | Equitable | equitable | 997800 | 0 | 997800 | 100 | 997800 | 997800 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Residents, patients and staff now have interrupted power supply.. Viable: Yes. Power outages have since been resolved.. Assessor remarks: The power generator was a donation from Gilgil Sub county hospital. The funds initially allocated to the purchase of a new power generator were reallocated via public participation to other uses within the same facility, particularly the renovation works for Subukia sub County hospital old wing..
2414 | Construction Of Olmanyatta Cattle Dip | Construction Of Olmanyatta Cattle Dip | To construct Olmanyatta Cattle Dip | Olmanyatta Cattle Dip constructed | 4130299 | N/A | Subukia | Waseges | 0.166288, 36.231724 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2016/17 | 2016/17 | N/A | 499066 | 499066 | 499066 | Equitable | N/A | 499066 | 0 | 498950 | 100 | 498950 | 499066 | 116 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Ye. Assessor remarks: Needs to be operationalize.
2415 | Administration, Planning and Support Services | Purchase Of Land For Milk Coolers, Water And Electricity At Wei Centre | To acquire land for Milk Coolers, Water And Electricity At Wei Centre | Land for Milk Coolers, Water And Electricity At Wei Centre acquired | 4130299 | N/A | Subukia | Waseges | 0.02338 36.262172 1995.300048828125 5.199999809265137 | 4569 | AGRICULTURE, LIVESTOCK AND FISHERIES | AGRICULTURE, LIVESTOCK AND FISHERIES | N/A | 2018/19 | 2018/19 | N/A | 2000000 | 800000 | 800000 | Equitable | equitable | 800000 | 0 | 1200000 | 150 | 1200000 | 800000 | -400000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The land has already been purchased.
2416 | Supervision of Naivasha market in Naivasha Municipality (Naivasha UDG) | Supervision of Naivasha market in Naivasha Municipality (Naivasha UDG) | To provide professional services for of Naivasha market in Naivasha Municipality (Naivasha UDG) | Professional services for of Naivasha market in Naivasha Municipality (Naivasha UDG) delivered | 2211310 | Contracted Professional Services | HQ | HQ | N/A | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2018/19 | N/A | 3500000 | 3500000 | 0 | Equitable | N/A | 0 | 3500000 | 0 | 0 | 0 | 0 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
2417 | Consultancy services to carry out environmental and social impact for KUSP (Nakuru UDG) | Consultancy services to carry out environmental and social impact for KUSP (Nakuru UDG) | To provide professional services for carry out environmental and social impact for KUSP (Nakuru UDG) | Professional services for carry out environmental and social impact for KUSP (Nakuru UDG) delivered | 2211311 | N/A | HQ | HQ | N/A | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2018/19 | N/A | 1823114 | 241052 | 0 | Equitable | N/A | 0 | 241052 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
2418 | Supervision of of Nakuru CBD Fire station (Nakuru UDG) | Supervision of of Nakuru CBD Fire station (Nakuru UDG) | To provide professional services for of of Nakuru CBD Fire station (Nakuru UDG) | Professional services for of of Nakuru CBD Fire station (Nakuru UDG) delivered | 2211311 | N/A | HQ | HQ | N/A | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2018/19 | N/A | 5983815 | 341410 | 0 | Equitable | N/A | 0 | 341410 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
2419 | Supervision of roads and drainage works in Naivasha Municipality (Naivasha UDG) | Supervision of roads and drainage works in Naivasha Municipality (Naivasha UDG) | To provide professional services for of roads and drainage works in Naivasha Municipality (Naivasha UDG) | Professional services for of roads and drainage works in Naivasha Municipality (Naivasha UDG) delivered | 2211311 | N/A | HQ | HQ | N/A | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2018/19 | N/A | 2248202 | 1500000 | 0 | Equitable | N/A | 0 | 1500000 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
2420 | Supervision of roads and drainage works in Nakuru Municipality (Nakuru UDG) | Supervision of roads and drainage works in Nakuru Municipality (Nakuru UDG) | To provide professional services for of roads and drainage works in Nakuru Municipality (Nakuru UDG) | Professional services for of roads and drainage works in Nakuru Municipality (Nakuru UDG) delivered | 2211311 | N/A | HQ | HQ | N/A | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2018/19 | N/A | 4246521.4 | 496521.4 | 0 | Equitable | N/A | 0 | 496521.4 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
2421 | Lands Outstanding Contract Retention - development | Lands Outstanding Contract Retention - development | To implement lands outstanding contract retention - development for orderly land use and housing provision | Lands Outstanding Contract Retention - development completed | 2211314 | Write Offs/ Bad Debt Expenses from Previous Years (Pending Bills) | HQ | HQ | -0.173672, 35.862823 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2022/23 | 2022/23 | 2022/23 | 408455.7 | 408455.7 | 408455.7 | N/A | N/A | 408455.7 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
2422 | Conditional Fund - World Bank—Kenya Informal Settlement Improvement Project II (KISIP II) | Conditional Fund - World Bank—Kenya Informal Settlement Improvement Project II (KISIP II) | To implement conditional fund - world bank—kenya informal settlement improvement project ii (kisip ii) for orderly land use and housing provision | Conditional Fund - World Bank—Kenya Informal Settlement Improvement Project II (KISIP II) completed | 2630203 | N/A | HQ | HQ | -0.173672, 35.862823 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2021/22 | 2022/23 | 2022/23 | 200000000 | 600000000 | 0 | N/A | N/A | 0 | 500000000 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
2423 | Construction Of Alternative Building Materials And Training Centre At Kware Polytechnic | Construction Of Alternative Building Materials And Training Centre At Kware Polytechnic | To construct Alternative Building Materials And Training Centre At Kware Polytechnic | Alternative Building Materials And Training Centre At Kware Polytechnic constructed | 3110299 | Construction of Buildings - Ot | HQ | HQ | -0.173672, 35.862823 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2020/21 | 2020/21 | 2020/21 | 2460322 | 2429480.8 | 2429480.8 | N/A | N/A | 2429480.8 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
2424 | Construction Of Alternative Building Materials And Training Centre At Lare Polytechnic | Construction Of Alternative Building Materials And Training Centre At Lare Polytechnic | To construct Alternative Building Materials And Training Centre At Lare Polytechnic | Alternative Building Materials And Training Centre At Lare Polytechnic constructed | 3110299 | Construction of Buildings - Ot | HQ | HQ | -0.173672, 35.862823 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2020/21 | 2020/21 | 2020/21 | 2533677.8 | 2533677.8 | 2533677.8 | N/A | N/A | 2533677.8 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
2425 | Reroofing of Flamingo Estate County Houses | Reroofing of Flamingo Estate County Houses | To implement reroofing of flamingo estate county houses for orderly land use and housing provision | Reroofing of Flamingo Estate County Houses completed | 3110301 | Refurbishment of Residential Buildings | Nakuru East | Flamingo | -0.302183, 36.079475 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2022/23 | 2022/23 | 2024/25 | 2696440 | 2696440 | 2696440 | Equitable | N/A | 2696440 | 0 | 2996976 | 111.1 | 2996976 | 2696440 | -300536 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: ECRAT merchants ltd.
2426 | Proposed reroofing of Kaloleni A and Baharini 2 Estates | Proposed reroofing of Kaloleni A and Baharini 2 Estates | To undertake the proposed reroofing of Kaloleni A and Baharini 2 Estates | Proposed reroofing of Kaloleni A and Baharini 2 Estates implemented | 3110301 | Refurbishment of Residential Buildings | Nakuru East | Kivumbini | -0.300694, 36.086594 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2022/23 | 2022/23 | 2022/23 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3261159 | 93.2 | 3261159 | 161701 | 238841 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
2427 | Construction of Roads in Industrial Area, Site & Service and Kabati (Naivasha UDG) | Construction of Roads in Industrial Area, Site & Service and Kabati (Naivasha UDG) | To construct Roads in Industrial Area, Site & Service and Kabati (Naivasha UDG) | Roads in Industrial Area, Site & Service and Kabati (Naivasha UDG) constructed | 3110401 | Major Roads | HQ | HQ | -0.173672, 35.862823 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2018/19 | 2018/19 | 100067851.9 | 419.9 | 0 | N/A | N/A | 0 | 419.9 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
2428 | Survey, Valuation, Mapping And Conveyancing Cost | Survey, Valuation, Mapping And Conveyancing Cost | To implement survey, valuation, mapping and conveyancing cost for orderly land use and housing provision | Survey, Valuation, Mapping And Conveyancing Cost completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Bahati | -0.176836 36.132331 1982.8623046875 15.597999572753906 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | N/A | 1580000 | 1580000 | 1580000 | Equitable | N/A | 1580000 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The road is good.
2429 | Construction and equipping of ABMT Demonstration Centre in Cheptuech VTC in Kuresoi South | Construction and equipping of ABMT Demonstration Centre in Cheptuech VTC in Kuresoi South | To construct and equip ABMT Demonstration Centre in Cheptuech VTC in Kuresoi South | ABMT Demonstration Centre in Cheptuech VTC in Kuresoi South constructed and equipped | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2022/23 | 2022/23 | 2022/23 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2430 | Construction of 3.6km storm water drainage in Kiamurogia and Mombasa & Kipkelion roads (Nakuru UDG) | Construction of 3.6km storm water drainage in Kiamurogia and Mombasa & Kipkelion roads (Nakuru UDG) | To construct 3.6km storm water drainage in Kiamurogia and Mombasa & Kipkelion roads (Nakuru UDG) | 3.6km storm water drainage in Kiamurogia and Mombasa & Kipkelion roads (Nakuru UDG) constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2018/19 | 2018/19 | 63974869.5 | 102422.05 | 0 | Equitable | N/A | 0 | 102422.05 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2431 | Construction of a new stadium at the existing Afraha Stadium -Phase 1 (Nakuru UDG) | Construction of a new stadium at the existing Afraha Stadium -Phase 1 (Nakuru UDG) | To construct a new stadium at the existing Afraha Stadium -Phase 1 (Nakuru UDG) | A new stadium at the existing Afraha Stadium -Phase 1 (Nakuru UDG) constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2018/19 | 2018/19 | 303924500 | 227782302 | 0 | Equitable | N/A | 0 | 227782302 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | Yes | Done | Yes | Done | Yes | Done | Status: Complete. Recommendation: Retain and archive.
2432 | Construction of ABMT Centres in Begi Polytechnic, Kamara Polytechnic, Barut Polytechnic and Subukia Polytechnic | Construction of ABMT Centres in Begi Polytechnic, Kamara Polytechnic, Barut Polytechnic and Subukia Polytechnic | To construct ABMT Centres in Begi Polytechnic, Kamara Polytechnic, Barut Polytechnic and Subukia Polytechnic | ABMT Centres in Begi Polytechnic, Kamara Polytechnic, Barut Polytechnic and Subukia Polytechnic constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2021/22 | 2021/22 | 2021/22 | 12580089.6 | 12500000 | 12500000 | Equitable | N/A | 12500000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2433 | Construction of ABMT Centres in Begi Polytechnic | Construction of ABMT Centres in Begi Polytechnic | To construct ABMT Centres in Begi Polytechnic | ABMT Centres in Begi Polytechnic constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2021/22 | 2021/22 | 2021/22 | 3122430 | 3122430 | 3122430 | Equitable | N/A | 3122430 | 0 | 0 | 0 | 0 | 5300000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2434 | Construction of ABMT Centres in Kamara Polytechnic | Construction of ABMT Centres in Kamara Polytechnic | To construct ABMT Centres in Kamara Polytechnic | ABMT Centres in Kamara Polytechnic constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2021/22 | 2021/22 | 2021/22 | 2999900 | 2999900 | 2999900 | Equitable | N/A | 2999900 | 0 | 0 | 0 | 0 | 5300000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2435 | Construction of ABMT Centres in Subukia Polytechnic | Construction of ABMT Centres in Subukia Polytechnic | To construct ABMT Centres in Subukia Polytechnic | ABMT Centres in Subukia Polytechnic constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2021/22 | 2021/22 | 2021/22 | 3122430 | 3122430 | 3122430 | Equitable | N/A | 3122430 | 0 | 0 | 0 | 0 | 5300000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2436 | Construction of fire station at Nakuru Old Town Hall (Nakuru UDG) | Construction of fire station at Nakuru Old Town Hall (Nakuru UDG) | To construct fire station at Nakuru Old Town Hall (Nakuru UDG) | Fire station at Nakuru Old Town Hall (Nakuru UDG) constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2018/19 | 2018/19 | 118036109 | 19256778 | 0 | Equitable | N/A | 0 | 19256778 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2437 | Development Of Housing Infrastructure | Development Of Housing Infrastructure | To develop Housing Infrastructure | Housing Infrastructure developed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2018/19 | 2018/19 | 8009185.75 | 1982368 | 1982368 | Equitable | N/A | 1982368 | 0 | 19500000 | 983.7 | 19500000 | 23103900 | -17517632 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2438 | Establishment Of G.I.S Laboratory (Land Information Management (LIMS)) | Establishment Of G.I.S Laboratory (Land Information Management (LIMS)) | To implement establishment of g.i.s laboratory (land information management (lims)) for orderly land use and housing provision | Establishment Of G.I.S Laboratory (Land Information Management (LIMS)) completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2014/15 | 2014/15 | 2014/15 | 4244494.5 | 4244495 | 4244495 | Equitable | N/A | 4244495 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2439 | Fencing Of Pipeline County Land | Fencing Of Pipeline County Land | To secure Pipeline County Land through fencing | Pipeline County Land fenced and secured | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2020/21 | 2020/21 | 2020/21 | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2440 | Partial construction of Naivasha market (Naivasha UDG) | Partial construction of Naivasha market (Naivasha UDG) | To implement partial construction of naivasha market (naivasha udg) for orderly land use and housing provision | Partial construction of Naivasha market (Naivasha UDG) completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2018/19 | 2018/19 | 123620348.7 | 10414556.6 | 0 | Equitable | N/A | 0 | 10414556.6 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2441 | Planning Of Urban Centres | Planning Of Urban Centres | To develop Of Urban Centres | Of Urban Centres developed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2018/19 | N/A | 20428585 | 1688125 | 1688125 | Equitable | N/A | 1688125 | 0 | 1688125 | 100 | 1688125 | 2156959 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
2442 | Survey And Mapping (Titling Of Land) | Survey And Mapping (Titling Of Land) | To survey And Mapping (Titling Of Land) for planning and development | And Mapping (Titling Of Land) surveyed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2018/19 | N/A | 12991330 | 10740580 | 10740580 | Equitable | N/A | 10740580 | 0 | 2250750 | 21 | 2250750 | 10740580 | 8489830 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
2443 | Upgrading of sewer line at Naivasha Sub County Estate | Upgrading of sewer line at Naivasha Sub County Estate | To upgrade sewer line at Naivasha Sub County Estate through tarmacking for improved road connectivity | Sewer line at Naivasha Sub County Estate tarmacked and upgraded | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2022/23 | 2022/23 | 2022/23 | 20500000 | 5979073 | 5979073 | Equitable | N/A | 5979073 | 0 | 4879891 | 81.6 | 4879891 | 842585 | 1099182 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2444 | Construction of 5 sanitation blocks at Kivumbini 1 and 2 Estates | Construction of 5 sanitation blocks at Kivumbini 1 and 2 Estates | To construct 5 sanitation blocks at Kivumbini 1 and 2 Estates | 5 sanitation blocks at Kivumbini 1 and 2 Estates constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Kivumbini | -0.299264, 36.082708 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2022/23 | 2022/23 | 2022/23 | 10000000 | 10000000 | 10000000 | Equitable | N/A | 10000000 | 0 | 8958027 | 89.6 | 8958027 | 494173 | 1041973 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
2445 | Survey And Conveyancing Of Gicheha Land | Survey And Conveyancing Of Gicheha Land | To survey And Conveyancing Of Gicheha Land for planning and development | And Conveyancing Of Gicheha Land surveyed | 3110599 | Other Infrastructure and Civil Works | Naivasha | Biashara-Naivasha | N/A | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2021/22 | 2021/22 | N/A | 167810 | 167810 | 167810 | Equitable | N/A | 167810 | 0 | 0 | 0 | 0 | 167810 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
2446 | Survey For New Game Mutukanio In Elementaita Ward | Survey For New Game Mutukanio In Elementaita Ward | To survey For New Game Mutukanio In Elementaita Ward for planning and development | For New Game Mutukanio In Elementaita Ward surveyed | 3110599 | Other Infrastructure and Civil Works | Gilgil | Elementaita | -0.559358 36.111862 1961.0999755859375 19.200000762939453 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2021/22 | 2021/22 | N/A | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 0 | 0 | 0 | 7000000 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Most of it has been carried away by Rain.
2447 | Surveying Of Trading Centres | Surveying Of Trading Centres | To survey Trading Centres for planning and development | Trading Centres surveyed | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | N/A | 18895710 | 16185695.75 | 16185695.75 | Equitable | N/A | 16185695.75 | 0 | 2710014 | 16.7 | 2710014 | 16185696 | 13475681.75 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
2448 | Purchase of Fire Engines for Disaster Management | Purchase of Fire Engines for Disaster Management | To procure Fire Engines for Disaster Management | Fire Engines for Disaster Management procured | 3110705 | N/A | HQ | HQ | -0.173672, 35.862823 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2018/19 | 2018/19 | 113500000 | 624000 | 0 | N/A | N/A | 0 | 624000 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
2449 | Acquisition Of A Server For Land Information Management System (Lims) | Acquisition Of A Server For Land Information Management System (Lims) | To procure A Server For Land Information Management System (Lims) | A Server For Land Information Management System (Lims) procured | 3111111 | Purchase of ICT networking and Communications Equipment | HQ | HQ | -0.173672, 35.862823 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 2000000 | 2000000 | N/A | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
2450 | Acquisition of survey equipments RTK (GPS) | Acquisition of survey equipments RTK (GPS) | To procure survey equipments RTK (GPS) | Survey equipments RTK (GPS) procured | 3111114 | N/A | HQ | HQ | -0.173672, 35.862823 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2021/22 | 2021/22 | 2021/22 | 10000000 | 4337748 | 4337748 | N/A | N/A | 4337748 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
2451 | Re-Roofing Of Flamingo Estate County Houses (Section 3) | Re-Roofing Of Flamingo Estate County Houses (Section 3) | To implement re-roofing of flamingo estate county houses (section 3) for orderly land use and housing provision | Re-Roofing Of Flamingo Estate County Houses (Section 3) completed | 3111299 | Rehabilitation & Renovation - | Nakuru East | Flamingo | -0.302277, 36.079525 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2020/21 | 2020/21 | 2022/23 | 1000000 | 850000 | 850000 | Equitable | N/A | 850000 | 0 | 850000 | 100 | 850000 | 2696440 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Mammeny.
2452 | Reroofing Of Flamingo Estate | Reroofing Of Flamingo Estate | To implement reroofing of flamingo estate for orderly land use and housing provision | Reroofing Of Flamingo Estate completed | 3111299 | Rehabilitation & Renovation - | Nakuru East | Flamingo | -0.302283, 36.079495 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2020/21 | 2020/21 | 2022/23 | 1500000 | 1410000 | 1410000 | Equitable | N/A | 1410000 | 0 | 959740 | 68.1 | 959740 | 2696440 | 450260 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Kempy.
2453 | Re-Roofing Of Kimathi Estate County Houses | Re-Roofing Of Kimathi Estate County Houses | To implement re-roofing of kimathi estate county houses for orderly land use and housing provision | Re-Roofing Of Kimathi Estate County Houses completed | 3111299 | Rehabilitation & Renovation - | Nakuru East | Flamingo | -0.302237, 36.072567 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2020/21 | 2020/21 | 2022/23 | 1000000 | 950000 | 950000 | Equitable | N/A | 950000 | 0 | 950000 | 100 | 950000 | 2696440 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated.
2454 | Renovation Of County Houses | Renovation Of County Houses | To rehabilitate County Houses to restore functionality | County Houses rehabilitated | 3111299 | Rehabilitation & Renovation - | HQ | HQ | -0.173672, 35.862823 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2020/21 | 2020/21 | 2020/21 | 3596155 | 3596155 | 3596155 | N/A | N/A | 3596155 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
2455 | Baharaini 1 And 2 Estate Re-Roofing | Baharaini 1 And 2 Estate Re-Roofing | To implement baharaini 1 and 2 estate re-roofing for orderly land use and housing provision | Baharaini 1 And 2 Estate Re-Roofing completed | 3111299 | Rehabilitation & Renovation - | Nakuru East | Kivumbini | -0.299289 36.08272 1786.4000244140625 18.538000106811523 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2021/22 | 2021/22 | 2021/22 | 4000000 | 3875000 | 3875000 | Equitable | N/A | 3875000 | 0 | 3315591 | 85.6 | 3315591 | 106286 | 559409 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Protect residents from effects of asbestos.
2456 | Baharini 1 Estate Re-Roofing | Baharini 1 Estate Re-Roofing | To implement baharini 1 estate re-roofing for orderly land use and housing provision | Baharini 1 Estate Re-Roofing completed | 3111299 | Rehabilitation & Renovation - | Nakuru East | Kivumbini | -0.299289 36.08272 1786.4000244140625 18.538000106811523 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 106286 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Protect residents from effects of asbestos.
2457 | Kaloleni A Reroofing | Kaloleni A Reroofing | To implement kaloleni a reroofing for orderly land use and housing provision | Kaloleni A Reroofing completed | 3111299 | Rehabilitation & Renovation - | Nakuru East | Kivumbini | -0.300544, 36.086574 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 1884550 | 1884550 | Equitable | N/A | 1884550 | 0 | 1884550 | 100 | 1884550 | 106286 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
2458 | Ojuka Reroofing | Ojuka Reroofing | To implement ojuka reroofing for orderly land use and housing provision | Ojuka Reroofing completed | 3111299 | Rehabilitation & Renovation - | Nakuru East | Kivumbini | -0.298793, 36.082064 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 1980044 | 1980044 | Equitable | N/A | 1980044 | 0 | 1949806 | 98.5 | 1949806 | 0 | 30238 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
2459 | Reroofing Of Baharini 1 Estate | Reroofing Of Baharini 1 Estate | To implement reroofing of baharini 1 estate for orderly land use and housing provision | Reroofing Of Baharini 1 Estate completed | 3111299 | Rehabilitation & Renovation - | Nakuru East | Kivumbini | -0.300255, 36.087205 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1200000 | 100 | 1200000 | 3000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
2460 | Reroofing Of Baharini 2 Estate | Reroofing Of Baharini 2 Estate | To implement reroofing of baharini 2 estate for orderly land use and housing provision | Reroofing Of Baharini 2 Estate completed | 3111299 | Rehabilitation & Renovation - | Nakuru East | Kivumbini | -0.300255, 36.087205 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1100000 | 1100000 | Equitable | N/A | 1100000 | 0 | 1200000 | 109.1 | 1200000 | 3000000 | -100000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
2461 | Reroofing Of Baharini I & II Estate | Reroofing Of Baharini I & II Estate | To implement reroofing of baharini i & ii estate for orderly land use and housing provision | Reroofing Of Baharini I & II Estate completed | 3111299 | Rehabilitation & Renovation - | Nakuru East | Kivumbini | -0.300255, 36.087205 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2020/21 | 2020/21 | 2020/21 | 3793570 | 3688500 | 3688500 | Equitable | N/A | 3688500 | 0 | 3688258 | 100 | 3688258 | 3000000 | 242 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
2462 | Reroofing Of Kaloleni A Estate | Reroofing Of Kaloleni A Estate | To implement reroofing of kaloleni a estate for orderly land use and housing provision | Reroofing Of Kaloleni A Estate completed | 3111299 | Rehabilitation & Renovation - | Nakuru East | Kivumbini | -0.300577, 36.0869 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 1925746 | 1925746 | Equitable | N/A | 1925746 | 0 | 1925746 | 100 | 1925746 | 50000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
2463 | Survey For New Game, Mutukanio for Elementaita | Survey For New Game, Mutukanio for Elementaita | To survey For New Game, Mutukanio for Elementaita for planning and development | For New Game, Mutukanio for Elementaita surveyed | 3111402 | N/A | Gilgil | Elementaita | -0.594149 36.116792 2063.298 1.2970000505447388 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2021/22 | 2021/22 | N/A | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 0 | 0 | 0 | 7000000 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs renovation.
2464 | Conveyancing Fees For Kiambogo Settlement Scheme Elementaita Ward | Conveyancing Fees For Kiambogo Settlement Scheme Elementaita Ward | To implement conveyancing fees for kiambogo settlement scheme elementaita ward for orderly land use and housing provision | Conveyancing Fees For Kiambogo Settlement Scheme Elementaita Ward completed | 3111403 | Research | HQ | HQ | -0.173672, 35.862823 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2021/22 | 2021/22 | 2021/22 | 9000000 | 9000000 | 9000000 | N/A | N/A | 9000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
2465 | Preparation Of Physical Development Plans For Trading Centres In Rongai Town, Lare, Piave, Njoro Township, Bagaria, Kiambogo -Elementaita Ward, Mbaruk, Wanyororo, Maraigishu, Karati, Elementaita And Site And Service In Gilgil, Kirima And Banita Centres | Preparation Of Physical Development Plans For Trading Centres In Rongai Town, Lare, Piave, Njoro Township, Bagaria, Kiambogo -Elementaita Ward, Mbaruk, Wanyororo, Maraigishu, Karati, Elementaita And Site And Service In Gilgil, Kirima And Banita Centres | To implement preparation of physical development plans for trading centres in rongai town, lare, piave, njoro township, bagaria, kiambogo -elementaita ward, mbaruk, wanyororo, maraigishu, karati, elementaita and site and service in gilgil, kirima and banita centres for orderly land use and housing provision | Preparation Of Physical Development Plans For Trading Centres In Rongai Town, Lare, Piave, Njoro Township, Bagaria, Kiambogo -Elementaita Ward, Mbaruk, Wanyororo, Maraigishu, Karati, Elementaita And Site And Service In Gilgil, Kirima And Banita Centres completed | 3111403 | Research | HQ | HQ | -0.173672, 35.862823 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2021/22 | 2021/22 | 2021/22 | 45159756 | 40000000 | 20000000 | N/A | N/A | 20000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
2466 | Survey Of Trading Centres In Rongai Town, Lare, Piave, Njoro Township, Bagaria, Kiambogo -Elementaita Ward, Mbaruk, Wanyororo, Maraigishu, Karati, Elementaita And Site And Service In Gilgil, Kirima And Banita Centres | Survey Of Trading Centres In Rongai Town, Lare, Piave, Njoro Township, Bagaria, Kiambogo -Elementaita Ward, Mbaruk, Wanyororo, Maraigishu, Karati, Elementaita And Site And Service In Gilgil, Kirima And Banita Centres | To survey Trading Centres In Rongai Town, Lare, Piave, Njoro Township, Bagaria, Kiambogo -Elementaita Ward, Mbaruk, Wanyororo, Maraigishu, Karati, Elementaita And Site And Service In Gilgil, Kirima And Banita Centres for planning and development | Trading Centres In Rongai Town, Lare, Piave, Njoro Township, Bagaria, Kiambogo -Elementaita Ward, Mbaruk, Wanyororo, Maraigishu, Karati, Elementaita And Site And Service In Gilgil, Kirima And Banita Centres surveyed | 3111403 | Research | HQ | HQ | -0.173672, 35.862823 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2021/22 | 2021/22 | 2021/22 | 45159756 | 40000000 | 5000000 | N/A | N/A | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
2467 | Preparation of Integrated Strategic Plan for Gilgil Town | Preparation of Integrated Strategic Plan for Gilgil Town | To implement preparation of integrated strategic plan for gilgil town for orderly land use and housing provision | Preparation of Integrated Strategic Plan for Gilgil Town completed | 3111499 | Research & Feasibility Studies | HQ | HQ | N/A | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2022/23 | 2022/23 | N/A | 23000000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
2468 | Preparation of Integrated Strategic Plan for Molo Town | Preparation of Integrated Strategic Plan for Molo Town | To implement preparation of integrated strategic plan for molo town for orderly land use and housing provision | Preparation of Integrated Strategic Plan for Molo Town completed | 3111499 | Research & Feasibility Studies | HQ | HQ | N/A | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2022/23 | 2022/23 | N/A | 20000000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
2469 | Preparation Of Physical Development Plans For Trading Centres In Rongai Town, Lare, Piave, Njoro Township, Bagaria, Kiambogo -Elementaita Ward, Mbaruk, Wanyororo, Maraigishu, Karati, Elementaita And Site And Service In Gilgil, Kirima And Banita Centres | Preparation Of Physical Development Plans For Trading Centres In Rongai Town, Lare, Piave, Njoro Township, Bagaria, Kiambogo -Elementaita Ward, Mbaruk, Wanyororo, Maraigishu, Karati, Elementaita And Site And Service In Gilgil, Kirima And Banita Centres | To implement preparation of physical development plans for trading centres in rongai town, lare, piave, njoro township, bagaria, kiambogo -elementaita ward, mbaruk, wanyororo, maraigishu, karati, elementaita and site and service in gilgil, kirima and banita centres for orderly land use and housing provision | Preparation Of Physical Development Plans For Trading Centres In Rongai Town, Lare, Piave, Njoro Township, Bagaria, Kiambogo -Elementaita Ward, Mbaruk, Wanyororo, Maraigishu, Karati, Elementaita And Site And Service In Gilgil, Kirima And Banita Centres completed | 3111499 | Research & Feasibility Studies | HQ | HQ | N/A | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2021/22 | 2021/22 | N/A | 45159756 | 18316980 | 18316980 | Equitable | N/A | 18316980 | 0 | 0 | 0 | 0 | 0 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
2470 | Purchase Of Land For Kapsoyo ECDE | Purchase Of Land For Kapsoyo ECDE | To acquire land for Kapsoyo ECDE | Land for Kapsoyo ECDE acquired | 3130101 | Acquisition of Land | Kuresoi South | Amalo | -0.641135 35.623433 2440 6.199999809265137 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
2471 | Purchase Of Land For Water Project At Pangani Network | Purchase Of Land For Water Project At Pangani Network | To acquire land for Water Project At Pangani Network | Land for Water Project At Pangani Network acquired | 3130101 | Acquisition of Land | Kuresoi South | Amalo | -0.641135 35.623433 2440 6.199999809265137 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | N/A | 578966 | 578966 | 578966 | Equitable | N/A | 578966 | 0 | 0 | 0 | 0 | 578966 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
2472 | Purchase Of Land For Ahero Market | Purchase Of Land For Ahero Market | To acquire land for Ahero Market | Land for Ahero Market acquired | 3130101 | Acquisition of Land | Bahati | Bahati | -0.187336, 36.124786 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | 2019/20 | 5200000 | 5200000 | 5200000 | Equitable | N/A | 5200000 | 0 | 5200000 | 100 | 5200000 | 3440461 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Not really. Viable: No. Assessor remarks: The land isn't well situated for a market.
2473 | Purchase Of Land For Maili Kumi Trade Market | Purchase Of Land For Maili Kumi Trade Market | To acquire land for Maili Kumi Trade Market | Land for Maili Kumi Trade Market acquired | 3130101 | Acquisition of Land | Bahati | Bahati | -0.16885, 36.123548 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2020/21 | 2020/21 | 2020/21 | 5400000 | 5400000 | 5400000 | Equitable | N/A | 5400000 | 0 | 5400000 | 100 | 5400000 | 3440461 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
2474 | Purchase Of Land For Wanyororo Market | Purchase Of Land For Wanyororo Market | To acquire land for Wanyororo Market | Land for Wanyororo Market acquired | 3130101 | Acquisition of Land | Bahati | Bahati | -0.187336, 36.124786 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | 2019/20 | 5200000 | 5200000 | 5200000 | Equitable | N/A | 5200000 | 0 | 5200000 | 100 | 5200000 | 3440461 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Not really. Viable: No. Assessor remarks: The land isn't well situated for a market.
2475 | Purchase Of Land For Kelelwet Borehole Land | Purchase Of Land For Kelelwet Borehole Land | To acquire land for Kelelwet Borehole Land | Land for Kelelwet Borehole Land acquired | 3130101 | Acquisition of Land | Nakuru West | Barut | -0.3425 36.042 0 2000 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2020/21 | 2020/21 | 2020/21 | 600000 | 600000 | 750000 | Equitable | N/A | 750000 | 0 | 750000 | 125 | 750000 | 3000000 | -150000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: No. Assessor remarks: No land has been purchased for soimet ecd.
2476 | Additional Funding For Purchase Of Land In Kahuruko Borehole | Additional Funding For Purchase Of Land In Kahuruko Borehole | To implement additional funding for purchase of land in kahuruko borehole for orderly land use and housing provision | Additional Funding For Purchase Of Land In Kahuruko Borehole completed | 3130101 | Acquisition of Land | Naivasha | Biashara-Naivasha | N/A | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2021/22 | 2021/22 | 2021/22 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 400000 | 80 | 400000 | 0 | 100000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2477 | Purchase Of Land For Kahuruko Community Borehole | Purchase Of Land For Kahuruko Community Borehole | To acquire land for Kahuruko Community Borehole | Land for Kahuruko Community Borehole acquired | 3130101 | Acquisition of Land | Naivasha | Biashara-Naivasha | -0.728632, 36.50234 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | 2022 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 600000 | 100 | 600000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Fastracking of title deed by county government..
2478 | Purchase Of A Plot For Mugwathi Sub Location Water Borehole In Munyeki | Purchase Of A Plot For Mugwathi Sub Location Water Borehole In Munyeki | To procure A Plot For Mugwathi Sub Location Water Borehole In Munyeki | A Plot For Mugwathi Sub Location Water Borehole In Munyeki procured | 3130101 | Acquisition of Land | Bahati | Dundori | -0.225233, 36.184632 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2021/22 | 2021/22 | 2021/2022 | 1950000 | 1950000 | 1950000 | Equitable | N/A | 1950000 | 0 | 1850000 | 94.9 | 1850000 | 0 | 100000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Samuel Gichuki. Assessor remarks: Good.
2479 | Purchasing of land at Witemere area for Construction of ECDE and waterpoint | Purchasing of land at Witemere area for Construction of ECDE and waterpoint | To implement purchasing of land at witemere area for construction of ecde and waterpoint for orderly land use and housing provision | Purchasing of land at Witemere area for Construction of ECDE and waterpoint completed | 3130101 | Acquisition of Land | Gilgil | Eburru/Mbaruk | -0.393269, 36.141933 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2022/23 | 2022/23 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 1300000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Good. Objective met: Yes. Viable: It's viable. Contractor: Not known. Assessor remarks: Fairly in Good place.
2480 | Purchase Land For Karunga ECDE | Purchase Land For Karunga ECDE | To procure Land For Karunga ECDE | Land For Karunga ECDE procured | 3130101 | Acquisition of Land | Molo | Elburgon | -0.26052 35.863608 0 6199.9990234375 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 4000000 | 400 | 4000000 | 1000000 | -3000000 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
2481 | Purchase Land For Saptet Tagat Road | Purchase Land For Saptet Tagat Road | To procure Land For Saptet Tagat Road | Land For Saptet Tagat Road procured | 3130101 | Acquisition of Land | Molo | Elburgon | -0.293257 35.80205 2488.1 15.399999618530273 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Ownership documents are not ready.
2482 | Purchase Of Land for Karunga EDC | Purchase Of Land for Karunga EDC | To acquire land for Karunga EDC | Land for Karunga EDC acquired | 3130101 | Acquisition of Land | Molo | Elburgon | -0.293257 35.80205 2488.1 15.399999618530273 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 4000000 | 400 | 4000000 | 1000000 | -3000000 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Ownership documents are not ready.
2483 | Purchase of land for Kasarani dispensary - additional allocation | Purchase of land for Kasarani dispensary - additional allocation | To acquire land for Kasarani dispensary - additional allocation | Land for Kasarani dispensary - additional allocation acquired | 3130101 | Acquisition of Land | Molo | Elburgon | -0.284884 35.845889 0 1399.9990234375 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2022/23 | 2022/23 | 2022/23 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Construction of 2.no consultation rooms.
2484 | Purchase Of Land for Ndimu Dispensary | Purchase Of Land for Ndimu Dispensary | To acquire land for Ndimu Dispensary | Land for Ndimu Dispensary acquired | 3130101 | Acquisition of Land | Molo | Elburgon | -0.279925 35.765083 0 2299.9990234375 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2021/22 | 2021/22 | 2021/22 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: Pikverd supplies. Assessor remarks: Ongoing well.
2485 | Purchase Of Land For Proposed Kasarani Health Centre | Purchase Of Land For Proposed Kasarani Health Centre | To acquire land for Proposed Kasarani Health Centre | Land for Proposed Kasarani Health Centre acquired | 3130101 | Acquisition of Land | Molo | Elburgon | -0.297869 35.806554 0 1711.865966796875 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2021/22 | 2021/22 | 2021/22 | 4500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 4000000 | 800 | 4000000 | 500000 | -3500000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
2486 | Purchase Of Land for Sabtet- Tagat Road | Purchase Of Land for Sabtet- Tagat Road | To acquire land for Sabtet- Tagat Road | Land for Sabtet- Tagat Road acquired | 3130101 | Acquisition of Land | Molo | Elburgon | -0.293257 35.80205 2488.1 15.399999618530273 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 4000000 | 400 | 4000000 | 1000000 | -3000000 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Ownership documents are not ready.
2487 | Purchase Of Land For Mbombo ECDE | Purchase Of Land For Mbombo ECDE | To acquire land for Mbombo ECDE | Land for Mbombo ECDE acquired | 3130101 | Acquisition of Land | Gilgil | Elementaita | -0.556018 36.104887 1961.0999755859375 18.899999618530273 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | N/A | 5500000 | 6490000 | 6490000 | Equitable | N/A | 6490000 | 0 | 4490000 | 69.2 | 4490000 | 4200000 | 2000000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Owners are yet to be paid..
2488 | Kihingo Market - Purchase Of Market Land For Kihingo Community | Kihingo Market - Purchase Of Market Land For Kihingo Community | To implement kihingo market - purchase of market land for kihingo community for orderly land use and housing provision | Kihingo Market - Purchase Of Market Land For Kihingo Community completed | 3130101 | Acquisition of Land | HQ | HQ | -0.173672, 35.862823 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2015/16 | 2015/16 | 2015/16 | 5500000 | 5500000 | 5500000 | N/A | N/A | 5500000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
2489 | Purchase of land at St. John and Kwa Makala (Green Valley) | Purchase of land at St. John and Kwa Makala (Green Valley) | To acquire land for St. John and Kwa Makala (Green Valley) | Land for St. John and Kwa Makala (Green Valley) acquired | 3130101 | Acquisition of Land | HQ | HQ | -0.173672, 35.862823 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2021/22 | 2021/22 | 2021/22 | 6000000 | 1500000 | 1500000 | N/A | N/A | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
2490 | Purchase Of Land For A Market In Kamara | Purchase Of Land For A Market In Kamara | To acquire land for A Market In Kamara | Land for A Market In Kamara acquired | 3130101 | Acquisition of Land | HQ | HQ | -0.173672, 35.862823 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | 2019/20 | 12500000 | 12500000 | 12500000 | N/A | N/A | 12500000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
2491 | Purchase Of Land For Construction of Kihingo Market | Purchase Of Land For Construction of Kihingo Market | To acquire land for Construction of Kihingo Market | Land for Construction of Kihingo Market acquired | 3130101 | Acquisition of Land | HQ | HQ | -0.173672, 35.862823 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2021/22 | 2021/22 | 2021/22 | 9000000 | 0 | 9000000 | N/A | N/A | 9000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
2492 | Purchase Of Land For Kirathimo Market In Kiamaina | Purchase Of Land For Kirathimo Market In Kiamaina | To acquire land for Kirathimo Market In Kiamaina | Land for Kirathimo Market In Kiamaina acquired | 3130101 | Acquisition of Land | HQ | HQ | -0.173672, 35.862823 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2021/22 | 2021/22 | 2021/22 | 20000000 | 20000000 | 20000000 | N/A | N/A | 20000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
2493 | Purchase Of Land For Lanet Umoja Health Centre | Purchase Of Land For Lanet Umoja Health Centre | To acquire land for Lanet Umoja Health Centre | Land for Lanet Umoja Health Centre acquired | 3130101 | Acquisition of Land | HQ | HQ | -0.173672, 35.862823 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2021/22 | 2021/22 | 2021/22 | 95000000 | 30000000 | 30000000 | N/A | N/A | 30000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
2494 | Purchase of land for a Playfield in Arahuka | Purchase of land for a Playfield in Arahuka | To acquire land for a Playfield in Arahuka | Land for a Playfield in Arahuka acquired | 3130101 | Acquisition of Land | Subukia | Kabazi | -0.08223 36.16987 0 1381 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2022/23 | 2022/23 | N/A | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 0 | 0 | 0 | 2500000 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: Not indicated. Assessor remarks: Machine was brought but transferred to subukia Valley coffee factory.
2495 | Purchase of land for access road between Kiangari and Lasit | Purchase of land for access road between Kiangari and Lasit | To acquire land for access road between Kiangari and Lasit | Land for access road between Kiangari and Lasit acquired | 3130101 | Acquisition of Land | Subukia | Kabazi | -0.07176 36.1704 0 783.315673828125 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2022/23 | 2022/23 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 1500000 | 0 | Vired | 25 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: To be operationalized.
2496 | Purchase of land for access road to KAG/Kabazi Hospital | Purchase of land for access road to KAG/Kabazi Hospital | To acquire land for access road to KAG/Kabazi Hospital | Land for access road to KAG/Kabazi Hospital acquired | 3130101 | Acquisition of Land | Subukia | Kabazi | -0.232911, 36.00584 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2022/23 | 2022/23 | 2023/24 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 0 | 0 | 0 | 1200000 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes but was not purchased. Contractor: Not indicated.
2497 | Purchase of land for construction of storage tank at Kamuohi Water Project | Purchase of land for construction of storage tank at Kamuohi Water Project | To acquire land for construction of storage tank at Kamuohi Water Project | Land for construction of storage tank at Kamuohi Water Project acquired | 3130101 | Acquisition of Land | Subukia | Kabazi | -0.09011, 36.16711 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2022/23 | 2022/23 | 2024/25 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Mr. Njoroge.
2498 | Purchase Of Land For Ndungiri Hospital | Purchase Of Land For Ndungiri Hospital | To acquire land for Ndungiri Hospital | Land for Ndungiri Hospital acquired | 3130101 | Acquisition of Land | Subukia | Kabazi | -0.08223 36.16987 0 1381 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2020/21 | 2020/21 | N/A | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 0 | 0 | 0 | 5000000 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: Not indicated. Assessor remarks: Machine was brought but transferred to subukia Valley coffee factory.
2499 | Purchase Of Land Near Kabazi Main Stage To Connect Kabazi Centre And Kabazi Secondary And Purchase Of Land For Kabazi Primary Access Road | Purchase Of Land Near Kabazi Main Stage To Connect Kabazi Centre And Kabazi Secondary And Purchase Of Land For Kabazi Primary Access Road | To acquire land for Near Kabazi Main Stage To Connect Kabazi Centre And Kabazi Secondary And Purchase Of Land For Kabazi Primary Access Road | Land for Near Kabazi Main Stage To Connect Kabazi Centre And Kabazi Secondary And Purchase Of Land For Kabazi Primary Access Road acquired | 3130101 | Acquisition of Land | Subukia | Kabazi | N/A | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2021/22 | 2021/22 | N/A | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 0 | 0 | 0 | 2400000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
2500 | Purchase Of Muthaiga Plot For Construction Of Tank For Kware Water Project | Purchase Of Muthaiga Plot For Construction Of Tank For Kware Water Project | To procure Muthaiga Plot For Construction Of Tank For Kware Water Project | Muthaiga Plot For Construction Of Tank For Kware Water Project procured | 3130101 | Acquisition of Land | Subukia | Kabazi | -0.09011, 36.16711 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2021/22 | 2021/22 | 2024/25 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Mr. Njoroge.
2501 | Purchase Of Ndungiri Market Land | Purchase Of Ndungiri Market Land | To procure Ndungiri Market Land | Ndungiri Market Land procured | 3130101 | Acquisition of Land | Subukia | Kabazi | -0.118145, 36.052432 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2020/21 | 2020/21 | 2021/22 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: Not indicated.
2502 | Purchase Of Land For Road Connecting Mausammit-Masaideni-Kwa Aron | Purchase Of Land For Road Connecting Mausammit-Masaideni-Kwa Aron | To acquire land for Road Connecting Mausammit-Masaideni-Kwa Aron | Land for Road Connecting Mausammit-Masaideni-Kwa Aron acquired | 3130101 | Acquisition of Land | Kuresoi North | Kamara | -0.18302 35.714287 2502.800048828125 5.699999809265137 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2021/22 | 2021/22 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 9800000 | 653.3 | 9800000 | 1500000 | -8300000 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes if it was implemented. Assessor remarks: Land was not purchased hence construction was not done.
2503 | Purchase of land at Kapkures Center for construction of market stalls and public toilet | Purchase of land at Kapkures Center for construction of market stalls and public toilet | To acquire land for Kapkures Center for construction of market stalls and public toilet | Land for Kapkures Center for construction of market stalls and public toilet acquired | 3130101 | Acquisition of Land | Nakuru West | Kapkures | -0.306306, 36.036551 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2022/23 | 2022/23 | 2022/23 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 0 | 0 | 0 | 2500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Viable. But land has not been found.
2504 | Purchase Of Land For Kapkures ECD | Purchase Of Land For Kapkures ECD | To acquire land for Kapkures ECD | Land for Kapkures ECD acquired | 3130101 | Acquisition of Land | Nakuru West | Kapkures | -0.306306 36.036551 0 2000 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | 2016/17 | 6000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 5000000 | 500 | 5000000 | 1000000 | -4000000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Class was never done. No land available.
2505 | Purchase of land for Lawlet water tanks reservoir | Purchase of land for Lawlet water tanks reservoir | To acquire land for Lawlet water tanks reservoir | Land for Lawlet water tanks reservoir acquired | 3130101 | Acquisition of Land | Nakuru West | Kapkures | -0.288288, 36.000456 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2022/23 | 2022/23 | 2022/23 | 2788025 | 2788025 | 2788025 | Equitable | N/A | 2788025 | 0 | 5000000 | 179.3 | 5000000 | 2500000 | -2211975 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Very viable. It will improve access to clean water.
2506 | Purchase Of Additional Land For Construction Of Vocational Training Centre | Purchase Of Additional Land For Construction Of Vocational Training Centre | To procure Additional Land For Construction Of Vocational Training Centre | Additional Land For Construction Of Vocational Training Centre procured | 3130101 | Acquisition of Land | Nakuru West | Kaptembwo | -0.30479 36.055153 1791.5 14.612000465393066 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2020/21 | 2020/21 | 2020/21 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 4000000 | 100 | 4000000 | 10000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Very viable, it has helped the youths Very much,but defective toilets and urinals. Contractor: ZIBO COMPANY. Assessor remarks: Complete.
2507 | Purchase Of Land For Public Use In Upper Kaptembwo | Purchase Of Land For Public Use In Upper Kaptembwo | To acquire land for Public Use In Upper Kaptembwo | Land for Public Use In Upper Kaptembwo acquired | 3130101 | Acquisition of Land | Nakuru West | Kaptembwo | -0.315776 36.052811 0 0 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | 2019/20 | 8000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not yet levelled.
2508 | Purchase Of Land For Public Utility - Resource Centre - At Sewage Village (Additional) | Purchase Of Land For Public Utility - Resource Centre - At Sewage Village (Additional) | To acquire land for Public Utility - Resource Centre - At Sewage Village (Additional) | Land for Public Utility - Resource Centre - At Sewage Village (Additional) acquired | 3130101 | Acquisition of Land | Nakuru West | Kaptembwo | -0.315776 36.052811 0 0 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | 2016/17 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not yet levelled.
2509 | Purchase 3 Parcel Of Land (0.25Ha) (Higher Point ) For Construction Of Water Tanks At Saptet, Sotaran And Tulwet | Purchase 3 Parcel Of Land (0.25Ha) (Higher Point ) For Construction Of Water Tanks At Saptet, Sotaran And Tulwet | To procure 3 Parcel Of Land (0.25Ha) (Higher Point ) For Construction Of Water Tanks At Saptet, Sotaran And Tulwet | 3 Parcel Of Land (0.25Ha) (Higher Point ) For Construction Of Water Tanks At Saptet, Sotaran And Tulwet procured | 3130101 | Acquisition of Land | Kuresoi South | Keringet | -0.499312, 35.72438 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2021/22 | 2021/23 | 2033 | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 0 | 0 | 0 | 400000 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yed.
2510 | Purchase of land for Construction of Burugo water tank | Purchase of land for Construction of Burugo water tank | To acquire land for Construction of Burugo water tank | Land for Construction of Burugo water tank acquired | 3130101 | Acquisition of Land | Bahati | Kiamaina | -0.240665, 36.110522 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2022/23 | 2022/23 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 19250000 | 962.5 | 19250000 | 2000000 | -17250000 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
2511 | Purchase Of Land For Installation Of Water Tank | Purchase Of Land For Installation Of Water Tank | To acquire land for Installation Of Water Tank | Land for Installation Of Water Tank acquired | 3130101 | Acquisition of Land | Njoro | Kihingo | -0.48105, 35.990172 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | 2022 | 500000 | 485000 | 485000 | Equitable | N/A | 485000 | 0 | 485000 | 100 | 485000 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
2512 | Purchase Of Land For Lanet Umoja Health Centre | Purchase Of Land For Lanet Umoja Health Centre | To acquire land for Lanet Umoja Health Centre | Land for Lanet Umoja Health Centre acquired | 3130101 | Acquisition of Land | Bahati | Lanet/Umoja | -0.267792, 36.171793 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | 2021/22 | 23015405 | 219120 | 219120 | Equitable | N/A | 219120 | 0 | 30000000 | 13691.1 | 30000000 | 1000000 | -29780880 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No.
2513 | Purchase Of Land For Longonot Water Project | Purchase Of Land For Longonot Water Project | To acquire land for Longonot Water Project | Land for Longonot Water Project acquired | 3130101 | Acquisition of Land | Naivasha | Maai Mahiu | N/A | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | N/A | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 0 | 0 | 0 | 800000 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
2514 | Purchase Of Land For Tarembeta Borehole | Purchase Of Land For Tarembeta Borehole | To acquire land for Tarembeta Borehole | Land for Tarembeta Borehole acquired | 3130101 | Acquisition of Land | Gilgil | Malewa West | -0.702703, 36.291018 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2020/21 | 2020/21 | 2020/21 | 3000000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2500000 | 100 | 2500000 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
2515 | Acquisition Of Land For ECD Centre-Kahuho Mwisho | Acquisition Of Land For ECD Centre-Kahuho Mwisho | To acquire land for ECD Centre-Kahuho Mwisho | Land for ECD Centre-Kahuho Mwisho acquired | 3130101 | Acquisition of Land | Njoro | Mau Narok | -0.597728 35.995954 0 20 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | 2019/20 | 2520000 | 2520000 | 2520000 | Equitable | N/A | 2520000 | 0 | 2520000 | 100 | 2520000 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Viable. Assessor remarks: Need repair for door and windows.
2516 | Kamungei Land Purchase | Kamungei Land Purchase | To implement kamungei land purchase for orderly land use and housing provision | Kamungei Land Purchase completed | 3130101 | Acquisition of Land | Rongai | Menengai West | -0.12535 36.008185 1778.4 2.5 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2021/22 | 2021/22 | N/A | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 0 | 0 | 0 | 4000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
2517 | Purchase Of Market Land At Mang'u | Purchase Of Market Land At Mang'u | To procure Market Land At Mang'u | Market Land At Mang'u procured | 3130101 | Acquisition of Land | Rongai | Menengai West | -0.144718 36.010936 0 92.9000015258789 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | N/A | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 0 | 0 | 0 | 5000000 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: No. Viable: No. Assessor remarks: Not operational.
2518 | Purchase of land at Chepseon | Purchase of land at Chepseon | To acquire land for Chepseon | Land for Chepseon acquired | 3130101 | Acquisition of Land | Rongai | Mosop | -0.220708 35.825988 1901.9000244140625 45.16899871826172 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2021/22 | 2021/22 | 2021/22 | 499999 | 0 | 6000000 | Equitable | N/A | 6000000 | 0 | 5800000 | 0 | 5800000 | 1800000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: M/Ssam. Assessor remarks: Complete and in good condition.
2519 | Buying Of Land For Naivasha East Value Additional Factory | Buying Of Land For Naivasha East Value Additional Factory | To procure Land For Naivasha East Value Additional Factory | Land For Naivasha East Value Additional Factory procured | 3130101 | Acquisition of Land | Naivasha | Naivasha East | -0.82546, 36.532327 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2020/21 | 2020/21 | 2023 | 3500000 | 3200000 | 3200000 | Equitable | N/A | 3200000 | 0 | 3200000 | 100 | 3200000 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
2520 | Purchase Of Land (1 Acre) For Sossion ECD | Purchase Of Land (1 Acre) For Sossion ECD | To acquire land for (1 Acre) For Sossion ECD | Land for (1 Acre) For Sossion ECD acquired | 3130101 | Acquisition of Land | Naivasha | Naivasha East | -0.87416 36.540758 2116.800048828125 3.299999952316284 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2020/21 | 2020/21 | N/A | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require fencing to mark boundary.
2521 | Purchase of land (I acre ) for Sossion ECD | Purchase of land (I acre ) for Sossion ECD | To acquire land for (I acre ) for Sossion ECD | Land for (I acre ) for Sossion ECD acquired | 3130101 | Acquisition of Land | Naivasha | Naivasha East | -0.87416 36.540758 2116.800048828125 3.299999952316284 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2020/21 | 2020/21 | N/A | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require fencing to mark boundary.
2522 | Purchase Of Land For Establishment Of A Dispensary In Rhonda | Purchase Of Land For Establishment Of A Dispensary In Rhonda | To acquire land for Establishment Of A Dispensary In Rhonda | Land for Establishment Of A Dispensary In Rhonda acquired | 3130101 | Acquisition of Land | Nakuru West | Rhonda | N/A | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2019/20 | N/A | 10000000 | 10000000 | 10000000 | Equitable | N/A | 10000000 | 0 | 0 | 0 | 0 | 10000000 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
2523 | Purchase Of Land At Chemasis Cattle Dip | Purchase Of Land At Chemasis Cattle Dip | To acquire land for Chemasis Cattle Dip | Land for Chemasis Cattle Dip acquired | 3130101 | Acquisition of Land | Rongai | Solai | 0.151221 36.195465 1713.139404296875 7.593999862670898 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2021/22 | 2021/22 | 2021/22 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 900000 | 90 | 900000 | 3000000 | 100000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
2524 | Purchase Of Land For Arus Dispensary | Purchase Of Land For Arus Dispensary | To acquire land for Arus Dispensary | Land for Arus Dispensary acquired | 3130101 | Acquisition of Land | Rongai | Solai | 0.013051 36.159552 1574.0458984375 4.935999870300293 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 900000 | 112.5 | 900000 | 800000 | -100000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Purchased.
2525 | Kirengero Water Borehole - Plot Compensation | Kirengero Water Borehole - Plot Compensation | To implement kirengero water borehole - plot compensation for orderly land use and housing provision | Kirengero Water Borehole - Plot Compensation completed | 3130101 | Acquisition of Land | Subukia | Subukia | -0.041156 36.220377 2150.7001953125 56.099998474121094 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | N/A | 1200000 | 1200000 | 1600000 | Equitable | N/A | 1600000 | 0 | 0 | 0 | 0 | 3600000 | 0 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes.. Viable: Sure. The community now uses the water. Contractor: Information not available. Assessor remarks: Good work..
2526 | Kirengoro Water Borehole - Plot Compensation | Kirengoro Water Borehole - Plot Compensation | To implement kirengoro water borehole - plot compensation for orderly land use and housing provision | Kirengoro Water Borehole - Plot Compensation completed | 3130101 | Acquisition of Land | Subukia | Subukia | -0.041156 36.220377 2150.7001953125 56.099998474121094 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2022/23 | 2022/23 | N/A | 1600000 | 0 | 1600000 | Equitable | N/A | 1600000 | 0 | 0 | 0 | 0 | 3600000 | 0 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes.. Viable: Sure. The community now uses the water. Contractor: Information not available. Assessor remarks: Good work..
2527 | Purchase Of Land For Public Use In Lucia Moraa Arash | Purchase Of Land For Public Use In Lucia Moraa Arash | To acquire land for Public Use In Lucia Moraa Arash | Land for Public Use In Lucia Moraa Arash acquired | 3130101 | Acquisition of Land | Subukia | Subukia | 0.002545 36.22944 2004.1999999999998 1 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | 2016/17 | 1400000 | 1400000 | 1400000 | Equitable | N/A | 1400000 | 0 | 1200000 | 85.7 | 1200000 | 2400000 | 200000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: Not known. Assessor remarks: Further interventions.
2528 | Purchase Of Muthaiga Plot For Construction Of Tank For Kware Water Project | Purchase Of Muthaiga Plot For Construction Of Tank For Kware Water Project | To procure Muthaiga Plot For Construction Of Tank For Kware Water Project | Muthaiga Plot For Construction Of Tank For Kware Water Project procured | 3130101 | Acquisition of Land | Subukia | Subukia | -0.006188, 36.235553 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2021/22 | 2021/22 | 2021/2022 | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 500000 | 100 | 500000 | 1600000 | -500000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: No. Community blocked accessing the water till the matter of payment for the landis resolved. Viable: Yes. Contractor: Details not availed.
2529 | Purchase of Muya's Land To Connect Kamigutha and Kirengero | Purchase of Muya's Land To Connect Kamigutha and Kirengero | To procure Muya's Land To Connect Kamigutha and Kirengero | Muya's Land To Connect Kamigutha and Kirengero procured | 3130101 | Acquisition of Land | Subukia | Subukia | 0.002545 36.22944 2004.1999999999998 1 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2021/22 | 2022/23 | N/A | 750000 | 500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 900000 | 180 | 900000 | 750000 | -400000 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: Not known. Assessor remarks: Further interventions.
2530 | Purchase Of Land For Road Network At Kiagwaci | Purchase Of Land For Road Network At Kiagwaci | To acquire land for Road Network At Kiagwaci | Land for Road Network At Kiagwaci acquired | 3130101 | Acquisition of Land | Molo | Turi | -0.279395 35.753738 2477.9 9.800000190734863 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 2900000 | 580 | 2900000 | 500000 | -2400000 | Vired | 90 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The land was bought by the county, the title of the land to be confirmed by the department.
2531 | Purchase Of Land for Road Network At Kiangwaci | Purchase Of Land for Road Network At Kiangwaci | To acquire land for Road Network At Kiangwaci | Land for Road Network At Kiangwaci acquired | 3130101 | Acquisition of Land | Molo | Turi | -0.279395 35.753738 2477.9 9.800000190734863 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2019/20 | 2019/20 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 2900000 | 580 | 2900000 | 500000 | -2400000 | Vired | 90 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The land was bought by the county, the title of the land to be confirmed by the department.
2532 | Purchase Of Land For Turi Health Center (Land Buying) | Purchase Of Land For Turi Health Center (Land Buying) | To acquire land for Turi Health Center (Land Buying) | Land for Turi Health Center (Land Buying) acquired | 3130101 | Acquisition of Land | Molo | Turi | -0.279395 35.753738 2477.9 9.800000190734863 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | 2016/17 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2900000 | 96.7 | 2900000 | 3000000 | 100000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The land was bought by the county, the title of the land to be confirmed by the department.
2533 | Purchase Of Land For Kware Kapkwen Borehole | Purchase Of Land For Kware Kapkwen Borehole | To acquire land for Kware Kapkwen Borehole | Land for Kware Kapkwen Borehole acquired | 3130101 | Acquisition of Land | Rongai | Visoi | -0.119957 35.933578 1710.7 7 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2017/18 | 2017/18 | N/A | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 0 | 0 | 0 | 700000 | 0 | Vired | 90 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
2534 | Purchase of land at kianoe borehole | Purchase of land at kianoe borehole | To acquire land for kianoe borehole | Land for kianoe borehole acquired | 3130101 | Acquisition of Land | Subukia | Waseges | 0.02338 36.262172 1995.300048828125 5.199999809265137 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2022/23 | 2022/23 | N/A | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 0 | 0 | 0 | 400000 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The land has already been purchased.
2535 | Purchase Of Land For Igwamiti ECD | Purchase Of Land For Igwamiti ECD | To acquire land for Igwamiti ECD | Land for Igwamiti ECD acquired | 3130101 | Acquisition of Land | Subukia | Waseges | 0.02338 36.262172 1995.300048828125 5.199999809265137 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The land has already been purchased.
2536 | Development Of Housing Infrastructure | Development Of Housing Infrastructure | To develop Housing Infrastructure | Housing Infrastructure developed | 4130299 | N/A | HQ | HQ | N/A | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2018/19 | 2018/19 | 8009185.75 | 1982368 | 1982368 | Equitable | N/A | 1982368 | 0 | 19500000 | 983.7 | 19500000 | 23103900 | -17517632 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2537 | Establishment Of G.I.S Laboratory (Land Information Management (LIMS)) | Establishment Of G.I.S Laboratory (Land Information Management (LIMS)) | To implement establishment of g.i.s laboratory (land information management (lims)) for orderly land use and housing provision | Establishment Of G.I.S Laboratory (Land Information Management (LIMS)) completed | 4130299 | N/A | HQ | HQ | N/A | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2014/15 | 2014/15 | N/A | 4244494.5 | 4244495 | 4244495 | Equitable | N/A | 4244495 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
2538 | Planning Of Urban Centres | Planning Of Urban Centres | To develop Of Urban Centres | Of Urban Centres developed | 4130299 | N/A | HQ | HQ | N/A | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2018/19 | N/A | 20428585 | 1688125 | 1688125 | Equitable | N/A | 1688125 | 0 | 1688125 | 100 | 1688125 | 2156959 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
2539 | Survey And Mapping (Titling Of Land) | Survey And Mapping (Titling Of Land) | To survey And Mapping (Titling Of Land) for planning and development | And Mapping (Titling Of Land) surveyed | 4130299 | N/A | HQ | HQ | N/A | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2018/19 | 2018/19 | N/A | 12991330 | 12991330 | 12991330 | Equitable | N/A | 12991330 | 0 | 2250750 | 17.3 | 2250750 | 10740580 | 10740580 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
2540 | Purchase Of Land For Kapkures ECD | Purchase Of Land For Kapkures ECD | To acquire land for Kapkures ECD | Land for Kapkures ECD acquired | 4130299 | N/A | Nakuru West | Kapkures | -0.306306 36.036551 0 2000 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | 2016/17 | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 5000000 | 83.3 | 5000000 | 1000000 | 1000000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Class was never done. No land available.
2541 | Purchase Of Land For Tachasis Market | Purchase Of Land For Tachasis Market | To acquire land for Tachasis Market | Land for Tachasis Market acquired | 4130299 | N/A | Nakuru West | Kapkures | -0.306306, 36.036551 | 4570 | LAND, HOUSING AND PHYSICAL PLANNING | LAND, HOUSING AND PHYSICAL PLANNING | N/A | 2016/17 | 2016/17 | 2016/17 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 3000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Not viable. The place is not ideal for market due to poor accessibility and low population.
2542 | Water and Sewerage Management | Water Outstanding Contract Retention - development | To implement water outstanding contract retention - development for access to clean water and environmental sustainability | Water Outstanding Contract Retention - development completed | 2211314 | Write Offs/ Bad Debt Expenses from Previous Years (Pending Bills) | HQ | HQ | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | N/A | 4679515.56 | 4679515.56 | 4679515.56 | Equitable | N/A | 4679515.56 | 0 | 2858049 | 61.1 | 2858049 | 0 | 1821466.56 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
2543 | Climate Change Resilience and County Energy Development | Climate Change Mitigation Programme (1% Of Equitable Development) | To implement climate change mitigation programme (1% of equitable development) for access to clean water and environmental sustainability | Climate Change Mitigation Programme (1% Of Equitable Development) completed | 2630203 | N/A | HQ | HQ | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | N/A | 33312923.13 | 33312923.13 | 33312923.13 | Equitable | N/A | 33312923.13 | 0 | 0 | 0 | 0 | 33312923 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
2544 | Water and Sewerage Management | Salgaa Area Programme (World Vision) Counterpart funding | To implement salgaa area programme (world vision) counterpart funding for access to clean water and environmental sustainability | Salgaa Area Programme (World Vision) Counterpart funding completed | 2630203 | N/A | HQ | HQ | -0.391082, 35.742475 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | N/A | 23000000 | 15000000 | 15000000 | N/A | N/A | 15000000 | 0 | 0 | 0 | 0 | 16970338 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Project moved from baraget to baseline.
2545 | Water and Sewerage Management | Completion Of Lelaitich Water Project | To complete Lelaitich Water Project | Lelaitich Water Project completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Amalo | -0.63578 35.67659 2498.5 10.300000190734863 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 300000 | 100 | 300000 | 300000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: partially. Viable: partially. Assessor remarks: requires completion of piping.
2546 | Water and Sewerage Management | Construction Of A Water Tank And Piping At Ambusket And Singorwet | To construct A Water Tank And Piping At Ambusket And Singorwet | A Water Tank And Piping At Ambusket And Singorwet constructed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Amalo | -0.576578 35.700243 2542.400146484375 11.399999618530273 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 5327890 | 5167823 | 5167823 | Equitable | N/A | 5167823 | 0 | 2159970 | 41.8 | 2159970 | 101703 | 3007853 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: yes. Viable: yes. Assessor remarks: project completed.
2547 | Water and Sewerage Management | Construction Of A Water Tank At Olenguruone | To construct A Water Tank At Olenguruone | A Water Tank At Olenguruone constructed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Amalo | -0.67954 35.639677 2420.475341796875 5.486999988555908 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 1000000 | 996028 | 996028 | Equitable | N/A | 996028 | 0 | 980775 | 98.5 | 980775 | 980775 | 15253 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: not yet done. Viable: yes. Assessor remarks: not done.
2548 | Water and Sewerage Management | Construction of Bondet water tank project | To construct Bondet water tank project | Bondet water tank project constructed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Amalo | -0.590476 35.686102 2581.1123046875 9.741999626159668 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 599824 | 60 | 599824 | 1000000 | 400176 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: yes. Viable: yes. Contractor: m/s koros. Assessor remarks: works going on well.
2549 | Water and Sewerage Management | Construction Of Community Water Tank At Kitoben Primary School | To construct Community Water Tank At Kitoben Primary School | Community Water Tank At Kitoben Primary School constructed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Amalo | -0.635722, 35.67651 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2022 | 1000000 | 119.4 | 119.4 | Equitable | N/A | 119.4 | 0 | 999881 | 837421.3 | 999881 | 119 | -999761.6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: complete.
2550 | Water and Sewerage Management | Construction Of Community Water Tank At Pangani Network | To construct Community Water Tank At Pangani Network | Community Water Tank At Pangani Network constructed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Amalo | -0.493175, 35.716723 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2020 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999881 | 100 | 999881 | 1000000 | 119 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Not working due to pump failure.
2551 | Water and Sewerage Management | Construction Of Lelaitich Water Project | To construct Lelaitich Water Project | Lelaitich Water Project constructed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Amalo | -0.615343 35.656623 2472.1 55.29999923706055 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 400000 | 100 | 400000 | 400000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
2552 | Water and Sewerage Management | Construction Of Water Tank At Sinerindet | To construct Water Tank At Sinerindet | Water Tank At Sinerindet constructed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Amalo | -0.632512 35.664773 2513.7 10.5 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 960712 | 96.1 | 960712 | 39288 | 39288 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: not yet in use. Viable: yet to start. Assessor remarks: project ongoing.
2553 | Water and Sewerage Management | Drilling Of Borehole At Network | To provide access to clean water through borehole drilling at Network | Borehole drilled at Network | 3110502 | Water Supplies and Sewerage | Kuresoi South | Amalo | -0.638882 35.658625 2494.7 11.300000190734863 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 363370.4 | 363370.4 | Equitable | N/A | 363370.4 | 0 | 2636630 | 725.6 | 2636630 | 363370 | -2273259.6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yesllà. Assessor remarks: Complete.
2554 | Water and Sewerage Management | Drilling Of Kitoben Borehole | To implement drilling of kitoben borehole for access to clean water and environmental sustainability | Drilling Of Kitoben Borehole completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Amalo | -0.633461, 35.677897 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2023 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2619477 | 87.3 | 2619477 | 3000000 | 380523 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: yes. Viable: yes. Assessor remarks: operational.
2555 | Water and Sewerage Management | Kiptaragon water project -piping | To implement kiptaragon water project -piping for access to clean water and environmental sustainability | Kiptaragon water project -piping completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Amalo | -0.603628, 35.675373 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2025 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 0 | 0 | 0 | 1200000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: not yet. Viable: not yet. Assessor remarks: project not started.
2556 | Water and Sewerage Management | Laying Of Pipes At Kabigeriet From Ndasiata | To implement laying of pipes at kabigeriet from ndasiata for access to clean water and environmental sustainability | Laying Of Pipes At Kabigeriet From Ndasiata completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Amalo | -0.639938, 35.658435 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2025 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 1500000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: completed.
2557 | Water and Sewerage Management | Laying of waterpipes at Kabigeriet from Ndasiata | To implement laying of waterpipes at kabigeriet from ndasiata for access to clean water and environmental sustainability | Laying of waterpipes at Kabigeriet from Ndasiata completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Amalo | -0.639938, 35.658435 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2025 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 1500000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: completed.
2558 | Water and Sewerage Management | Piping And Distribution At Ndashata Water Project | To provide water distribution infrastructure at Ndashata Water Project | Water piping at Ndashata Water Project completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Amalo | -0.639807 35.658602 2502.2 9.199999809265137 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 1500000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: completed.
2559 | Water and Sewerage Management | Piping of Kitoben water project | To provide water distribution infrastructure at Kitoben water project | Water piping at Kitoben water project completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Amalo | -0.603628, 35.675373 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2025 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 300000 | 30 | 300000 | 847082 | 700000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: not yet. Viable: not yet. Assessor remarks: project not started.
2560 | Water and Sewerage Management | Sinendet water project & piping | To implement sinendet water project & piping for access to clean water and environmental sustainability | Sinendet water project & piping completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Amalo | -0.603628, 35.675373 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2025 | 4200000 | 4200000 | 4200000 | Equitable | N/A | 4200000 | 0 | 400000 | 9.5 | 400000 | 4200000 | 3800000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: not yet. Viable: not yet. Assessor remarks: project not started.
2561 | Water and Sewerage Management | Bahati Ward Water Works | To implement bahati ward water works for access to clean water and environmental sustainability | Bahati Ward Water Works completed | 3110502 | Water Supplies and Sewerage | Bahati | Bahati | -0.174075, 36.135411 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 16500000 | 16500000 | 16500000 | Equitable | N/A | 16500000 | 0 | 3157845 | 19.1 | 3157845 | 3042155 | 13342155 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Well done.
2562 | Water and Sewerage Management | Bahati Water Works Project | To implement bahati water works project for access to clean water and environmental sustainability | Bahati Water Works Project completed | 3110502 | Water Supplies and Sewerage | Bahati | Bahati | -0.174193, 36.135371 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 14124449 | 1259690 | 1259690 | Equitable | N/A | 1259690 | 0 | 1197584 | 95.1 | 1197584 | 1197584 | 62106 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes it is viable. Viable: Yes it did. Assessor remarks: Nicely done.
2563 | Water and Sewerage Management | Bahati Water Works | To implement bahati water works for access to clean water and environmental sustainability | Bahati Water Works completed | 3110502 | Water Supplies and Sewerage | Bahati | Bahati | -0.174075, 36.135411 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 5000000 | 2008348.4 | 2008348.4 | Equitable | N/A | 2008348.4 | 0 | 2991652 | 149 | 2991652 | 2008348 | -983303.6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Well done.
2564 | Water and Sewerage Management | Equipping and piping of Bahati Ward water works | To equip and piping of Bahati Ward water works with necessary facilities and equipment | And piping of Bahati Ward water works equipped | 3110502 | Water Supplies and Sewerage | Bahati | Bahati | -0.174075, 36.135411 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/23 | 8000000 | 8000000 | 8000000 | Equitable | N/A | 8000000 | 0 | 7659858 | 95.7 | 7659858 | 340142 | 340142 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Well done.
2565 | Water And Sewerage Management | Piping At Rumathi Water Project | To provide water distribution infrastructure at Rumathi Water Project | Water piping at Rumathi Water Project completed | 3110502 | Water Supplies and Sewerage | Bahati | Bahati | -0.127386, 36.178531 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 999589.25 | 621.25 | 621.25 | Equitable | N/A | 621.25 | 0 | 998968 | 160799.7 | 998968 | 621 | -998346.75 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The water is in use.
2566 | Water and Sewerage Management | Purchase And Supply Of 10,000 Litres Water Tanks At Osembo Primary School And St. John Secondary School | To procure and supply 10,000 Litres Water Tanks At Osembo Primary School And St. John Secondary School | 10,000 Litres Water Tanks At Osembo Primary School And St. John Secondary School procured and supplied | 3110502 | Water Supplies and Sewerage | Bahati | Bahati | -0.173854 36.132917 0 87.5999984741211 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 200000 | 200000 | 200000 | Equitable | N/A | 200000 | 0 | 200000 | 100 | 200000 | 200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: It is well in use.
2567 | Water and Sewerage Management | Purchase And Supply Of 10,000 Litres Water Tanks For Public Toilet At Maili Kumi Level 4 Hospital | To procure and supply 10,000 Litres Water Tanks For Public Toilet At Maili Kumi Level 4 Hospital | 10,000 Litres Water Tanks For Public Toilet At Maili Kumi Level 4 Hospital procured and supplied | 3110502 | Water Supplies and Sewerage | Bahati | Bahati | -0.170023 36.123607 1924.5 53.448001861572266 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 150000 | 150000 | 150000 | Equitable | N/A | 150000 | 0 | 89377 | 59.6 | 89377 | 150000 | 60623 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
2568 | Water and Sewerage Management | Purchase And Supply Of 10,000L Water Tank At Muringa Primary,St Joseph Kirima Secondary, Jm Secondary School ,Bahati Wanyororo B Polytechnic And Bahati PCEA Primary School | To procure and supply 10,000L Water Tank At Muringa Primary,St Joseph Kirima Secondary, Jm Secondary School ,Bahati Wanyororo B Polytechnic And Bahati PCEA Primary School | 10,000L Water Tank At Muringa Primary,St Joseph Kirima Secondary, Jm Secondary School ,Bahati Wanyororo B Polytechnic And Bahati PCEA Primary School procured and supplied | 3110502 | Water Supplies and Sewerage | Bahati | Bahati | -0.14783, 36.121778 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 200000 | 33.3 | 200000 | 600000 | 400000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yesb. Assessor remarks: Good.
2569 | Water and Sewerage Management | Purchase And Supply Of 500L Water Tanks To Vulnerables | To procure and supply 500L Water Tanks To Vulnerables | 500L Water Tanks To Vulnerables procured and supplied | 3110502 | Water Supplies and Sewerage | Bahati | Bahati | -0.631697, 36.497917 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2023 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1041042 | 52.1 | 1041042 | 2000000 | 958958 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Essymumbi contractors. Assessor remarks: Poor management,manhole vandalism.
2570 | Water and Sewerage Management | Purchase and supply of water pipes in Bahati ward | To procure and supply water pipes in Bahati ward | Water pipes in Bahati ward procured and supplied | 3110502 | Water Supplies and Sewerage | Bahati | Bahati | -0.150455 36.146665 2036.32080078125 5.013999938964844 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/23 | 1800000 | 0 | 1800000 | Equitable | N/A | 1800000 | 0 | 788916 | 100 | 788916 | 11084 | -788916 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: It is in use.
2571 | Water and Sewerage Management | Purchase Of 5 Water Tank For Our Lady Of Fatuma Secondary School, St. Lwanga, St. Francis Secondary School | To procure 5 Water Tank For Our Lady Of Fatuma Secondary School, St. Lwanga, St. Francis Secondary School | 5 Water Tank For Our Lady Of Fatuma Secondary School, St. Lwanga, St. Francis Secondary School procured | 3110502 | Water Supplies and Sewerage | Bahati | Bahati | -0.14783, 36.121778 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 500000 | 27 | 27 | Equitable | N/A | 27 | 0 | 499973 | 1851751.9 | 499973 | 27 | -499946 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yesb. Assessor remarks: Good.
2572 | Water and Sewerage Management | Purchase Of Water Tank At Jakaranda Primary School | To procure Water Tank At Jakaranda Primary School | Water Tank At Jakaranda Primary School procured | 3110502 | Water Supplies and Sewerage | Bahati | Bahati | -0.150455 36.146665 2036.32080078125 5.013999938964844 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 100000 | 100000 | 100000 | Equitable | N/A | 100000 | 0 | 100000 | 100 | 100000 | 100000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: It is in use.
2573 | Water and Sewerage Management | Supply Of Pipes(1,2 And 3.5 Inches) In Bahati Ward | To implement supply of pipes(1,2 and 3.5 inches) in bahati ward for access to clean water and environmental sustainability | Supply Of Pipes(1,2 And 3.5 Inches) In Bahati Ward completed | 3110502 | Water Supplies and Sewerage | Bahati | Bahati | -0.154613 36.157595 2094.000244140625 6.599999904632568 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 496000 | 99.2 | 496000 | 500000 | 4000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is good.
2574 | Water and Sewerage Management | Water Piping For Bahati Farmer Water, Bahati Trading Centre, Jomokenyatta Area Maili Kumi And Wanyororo Gatangi To Ngoti | To implement water piping for bahati farmer water, bahati trading centre, jomokenyatta area maili kumi and wanyororo gatangi to ngoti for access to clean water and environmental sustainability | Water Piping For Bahati Farmer Water, Bahati Trading Centre, Jomokenyatta Area Maili Kumi And Wanyororo Gatangi To Ngoti completed | 3110502 | Water Supplies and Sewerage | Bahati | Bahati | -0.160193, 36.102193 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 499926 | 100 | 499926 | 500000 | 74 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes it is viable. Viable: Yes. Assessor remarks: The projects is on use.
2575 | Water and Sewerage Management | Drilling Of A Borehole And Installation Of Piping And Electricity At Mlima Ugali | To implement drilling of a borehole and installation of piping and electricity at mlima ugali for access to clean water and environmental sustainability | Drilling Of A Borehole And Installation Of Piping And Electricity At Mlima Ugali completed | 3110502 | Water Supplies and Sewerage | Nakuru West | Barut | -0.353373, 36.049497 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2020 | 3800000 | 1934441.6 | 1934441.6 | Equitable | N/A | 1934441.6 | 0 | 1865558 | 96.4 | 1865558 | 1934442 | 68883.6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: GREAT RIFT GENERAL MERCHANTS. Assessor remarks: The project is complete and operational.
2576 | Water and Sewerage Management | Drilling Of Borehole For Kelelwet Water Project | To provide access to clean water through borehole drilling at For Kelelwet Water Project | Borehole drilled at For Kelelwet Water Project | 3110502 | Water Supplies and Sewerage | Nakuru West | Barut | 0.3533, 36.049 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 12224 | 12224 | Equitable | N/A | 12224 | 0 | 1987776 | 16261.3 | 1987776 | 12224 | -1975552 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: Yes. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: There is no drilling which has been done.
2577 | Water and Sewerage Management | Soimet Water Borehole - Piping To Kapkwen Village,Soimet Village And Kiptenden Village And Kipsimbol | To implement soimet water borehole - piping to kapkwen village,soimet village and kiptenden village and kipsimbol for access to clean water and environmental sustainability | Soimet Water Borehole - Piping To Kapkwen Village,Soimet Village And Kiptenden Village And Kipsimbol completed | 3110502 | Water Supplies and Sewerage | Nakuru West | Barut | -0.342342, 36.036679 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2018 | 1800000 | 2078.55 | 2078.55 | Equitable | N/A | 2078.55 | 0 | 1797921 | 86498.8 | 1797921 | 2079 | -1795842.45 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: CIDER COLLECTIONS. Assessor remarks: There was no project done.
2578 | Water and Sewerage Management | Supply Of Water Pipes To Barut Community Borehole | To implement supply of water pipes to barut community borehole for access to clean water and environmental sustainability | Supply Of Water Pipes To Barut Community Borehole completed | 3110502 | Water Supplies and Sewerage | Nakuru West | Barut | -0.324324, 36.054632 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2020 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1422856 | 94.9 | 1422856 | 1500000 | 77144 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: NDIRANCHI GROUP LTD. Assessor remarks: The pipes were bought.
2579 | Water and Sewerage Management | Water Works At Barut | To implement water works at barut for access to clean water and environmental sustainability | Water Works At Barut completed | 3110502 | Water Supplies and Sewerage | Nakuru West | Barut | -0.342342, 36.054698 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2022 | 1500000 | 3004245 | 3004245 | Equitable | N/A | 3004245 | 0 | 1455000 | 48.4 | 1455000 | 1500000 | 1549245 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Good. Objective met: Not yet. Viable: Not yet. Assessor remarks: The project are still ongoing.
2580 | Water and Sewerage Management | Water Works In Mwariki Health | To implement water works in mwariki health for access to clean water and environmental sustainability | Water Works In Mwariki Health completed | 3110502 | Water Supplies and Sewerage | Nakuru West | Barut | 0.353373, 36.049497 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2021 | 1000000 | 803 | 803 | Equitable | N/A | 803 | 0 | 999197 | 124433 | 999197 | 803 | -998394 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: No water works which has been done.
2581 | Water and Sewerage Management | Drilling Borehole In Mwariki Area And Piping | To implement drilling borehole in mwariki area and piping for access to clean water and environmental sustainability | Drilling Borehole In Mwariki Area And Piping completed | 3110502 | Water Supplies and Sewerage | Nakuru West | Barut | 0.324324, 36.054632 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 1921 | 1473237 | 1473237 | 1473237 | Equitable | N/A | 1473237 | 0 | 1463150 | 99.3 | 1463150 | 1473237 | 10087 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
2582 | Water and Sewerage Management | Drilling Of Gituamba Borehole | To implement drilling of gituamba borehole for access to clean water and environmental sustainability | Drilling Of Gituamba Borehole completed | 3110502 | Water Supplies and Sewerage | Naivasha | Biashara-Naivasha | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 2588981.6 | 2558.6 | 2558.6 | Equitable | N/A | 2558.6 | 0 | 2586423 | 101087.4 | 2586423 | 2559 | -2583864.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2583 | Water and Sewerage Management | Muteithia Borehole - Drilling Of Muteithia Borehole | To implement muteithia borehole - drilling of muteithia borehole for access to clean water and environmental sustainability | Muteithia Borehole - Drilling Of Muteithia Borehole completed | 3110502 | Water Supplies and Sewerage | Naivasha | Biashara-Naivasha | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 2800000 | 1918 | 1918 | Equitable | N/A | 1918 | 0 | 2798082 | 145885.4 | 2798082 | 1918 | -2796164 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2584 | Water and Sewerage Management | Piping at Gicheha Borehole | To provide water distribution infrastructure at Gicheha Borehole | Water piping at Gicheha Borehole completed | 3110502 | Water Supplies and Sewerage | Naivasha | Biashara-Naivasha | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | N/A | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 2857880 | 71.4 | 2857880 | 4000000 | 1142120 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
2585 | Water and Sewerage Management | Piping at Kambi Ndoro borehole | To provide water distribution infrastructure at Kambi Ndoro borehole | Water piping at Kambi Ndoro borehole completed | 3110502 | Water Supplies and Sewerage | Naivasha | Biashara-Naivasha | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/23 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2780822 | 92.7 | 2780822 | 1255440 | 219178 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2586 | Water and Sewerage Management | Piping at Kirima water project | To provide water distribution infrastructure at Kirima water project | Water piping at Kirima water project completed | 3110502 | Water Supplies and Sewerage | Naivasha | Biashara-Naivasha | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/23 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1780720 | 98.9 | 1780720 | 800 | 19280 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2587 | Water and Sewerage Management | Piping at Muteithia borehole | To provide water distribution infrastructure at Muteithia borehole | Water piping at Muteithia borehole completed | 3110502 | Water Supplies and Sewerage | Naivasha | Biashara-Naivasha | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2857880 | 95.3 | 2857880 | 132896 | 142120 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
2588 | Water and Sewerage Management | Piping In Mununga Water Project | To provide water distribution infrastructure at In Mununga Water Project | Water piping at In Mununga Water Project completed | 3110502 | Water Supplies and Sewerage | Naivasha | Biashara-Naivasha | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 800 | 800 | Equitable | N/A | 800 | 0 | 1999200 | 249900 | 1999200 | 800 | -1998400 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2589 | Water and Sewerage Management | Upper Kinamba Water Piping | To implement upper kinamba water piping for access to clean water and environmental sustainability | Upper Kinamba Water Piping completed | 3110502 | Water Supplies and Sewerage | Naivasha | Biashara-Naivasha | -0.71484, 36.486358 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2023 | 2600000 | 188360 | 188360 | Equitable | N/A | 188360 | 0 | 2411640 | 1280.3 | 2411640 | 188360 | -2223280 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Lumiseal. Assessor remarks: In a good working conditions.
2590 | Water and Sewerage Management | Purchase And Supply Of 5,000 Litres Water Tank For Bondeni Mithonge And Other Two (2) Groups | To procure and supply 5,000 Litres Water Tank For Bondeni Mithonge And Other Two (2) Groups | 5,000 Litres Water Tank For Bondeni Mithonge And Other Two (2) Groups procured and supplied | 3110502 | Water Supplies and Sewerage | Nakuru East | Biashara-Nakuru | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 200000 | 200000 | 200000 | Equitable | N/A | 200000 | 0 | 0 | 0 | 0 | 200000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
2591 | Water and Sewerage Management | Construction of a water tank at upper Dundori | To construct a water tank at upper Dundori | A water tank at upper Dundori constructed | 3110502 | Water Supplies and Sewerage | Bahati | Dundori | -0.246032 36.239455 2322.7001953125 23.299999237060547 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/23 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1467220 | 97.8 | 1467220 | 1467220 | 32780 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Sodys general. Assessor remarks: In good state.
2592 | Water and Sewerage Management | Construction of an underground water tank 100cm3 at Chiefs Office ground in Giachonge | To construct an underground water tank 100cm3 at Chiefs Office ground in Giachonge | An underground water tank 100cm3 at Chiefs Office ground in Giachonge constructed | 3110502 | Water Supplies and Sewerage | Bahati | Dundori | -0.246032 36.239455 2322.7001953125 23.299999237060547 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1467220 | 97.8 | 1467220 | 1500000 | 32780 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Sodys general. Assessor remarks: In good state.
2593 | Water and Sewerage Management | Construction Of Dundori Water Tank | To construct Dundori Water Tank | Dundori Water Tank constructed | 3110502 | Water Supplies and Sewerage | Bahati | Dundori | -0.236015 36.182315 2054.3999999999996 8.5 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1417143 | 94.5 | 1417143 | 1500000 | 82857 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Kewaska company. Assessor remarks: Good.
2594 | Water and Sewerage Management | Drilling And Purchase Of Water Pump For Wanyororo Water Project | To implement drilling and purchase of water pump for wanyororo water project for access to clean water and environmental sustainability | Drilling And Purchase Of Water Pump For Wanyororo Water Project completed | 3110502 | Water Supplies and Sewerage | Bahati | Dundori | -0.252388, 36.187673 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/2019 | 1526377.2 | 1369684.8 | 1369684.8 | Equitable | N/A | 1369684.8 | 0 | 1369685 | 100 | 1369685 | 1369685 | -0.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Naxxy limited. Assessor remarks: Ongoing project.
2595 | Water and Sewerage Management | Drilling, Equipping And Water Works At Dundori Water Projects | To implement drilling, equipping and water works at dundori water projects for access to clean water and environmental sustainability | Drilling, Equipping And Water Works At Dundori Water Projects completed | 3110502 | Water Supplies and Sewerage | Bahati | Dundori | -0.24679, 36.2379 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/2020 | 3500000 | 655673.1 | 655673.1 | Equitable | N/A | 655673.1 | 0 | 621700 | 94.8 | 621700 | 621700 | 33973.1 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Nemoca enterprise. Assessor remarks: In good state.
2596 | Water and Sewerage Management | Dundori Water Works | To implement dundori water works for access to clean water and environmental sustainability | Dundori Water Works completed | 3110502 | Water Supplies and Sewerage | Bahati | Dundori | -0.239802 36.241437 2324.000244140625 5.599999904632568 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 3333 | 3333 | Equitable | N/A | 3333 | 0 | 1559761 | 46797.5 | 1559761 | 140239 | -1556428 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
2597 | Water and Sewerage Management | Mugwathi Dundori Water Project - Drilling Of Mugwathi Dundori Borehole And Purchase Of Pump | To implement mugwathi dundori water project - drilling of mugwathi dundori borehole and purchase of pump for access to clean water and environmental sustainability | Mugwathi Dundori Water Project - Drilling Of Mugwathi Dundori Borehole And Purchase Of Pump completed | 3110502 | Water Supplies and Sewerage | Bahati | Dundori | -0.235918, 36.182103 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/2018 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 4000000 | 100 | 4000000 | 4000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
2598 | Water and Sewerage Management | Supply Of Pipes To Water Projects | To implement supply of pipes to water projects for access to clean water and environmental sustainability | Supply Of Pipes To Water Projects completed | 3110502 | Water Supplies and Sewerage | Bahati | Dundori | -0.246448, 36.238052 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/2020 | 700000 | 49795 | 49795 | Equitable | N/A | 49795 | 0 | 650205 | 1305.8 | 650205 | 49795 | -600410 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Endorse ventures. Assessor remarks: Good.
2599 | Water and Sewerage Management | Supply of water pipes for Bavuni Mugwathi and Upper Dundori water projects | To implement supply of water pipes for bavuni mugwathi and upper dundori water projects for access to clean water and environmental sustainability | Supply of water pipes for Bavuni Mugwathi and Upper Dundori water projects completed | 3110502 | Water Supplies and Sewerage | Bahati | Dundori | -0.240442, 36.172773 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/2023 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2916959 | 97.2 | 2916959 | 1000000 | 83041 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Kirwan limited. Assessor remarks: Good.
2600 | Water and Sewerage Management | Supply Of Water Pipes To Community Water Projects | To implement supply of water pipes to community water projects for access to clean water and environmental sustainability | Supply Of Water Pipes To Community Water Projects completed | 3110502 | Water Supplies and Sewerage | Bahati | Dundori | -0.25254, 36.239842 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/2022 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 899500 | 90 | 899500 | 1000000 | 100500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Purim logistics. Assessor remarks: Good.
2601 | Water and Sewerage Management | Supply of water pipes to community water project | To implement supply of water pipes to community water project for access to clean water and environmental sustainability | Supply of water pipes to community water project completed | 3110502 | Water Supplies and Sewerage | Bahati | Dundori | -0.25254, 36.239842 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/2022 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 899500 | 90 | 899500 | 1000000 | 100500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Purim logistics. Assessor remarks: Good.
2602 | Water and Sewerage Management | Supply Of Water Pipes To Water Projects In Dundori | To implement supply of water pipes to water projects in dundori for access to clean water and environmental sustainability | Supply Of Water Pipes To Water Projects In Dundori completed | 3110502 | Water Supplies and Sewerage | Bahati | Dundori | -0.232046, 36.174856 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/2021 | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 300000 | 100 | 300000 | 300000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: DMG holding. Assessor remarks: Good.
2603 | Water and Sewerage Management | Supply Of Water Tanks To Vulnerable Women In Dundori | To implement supply of water tanks to vulnerable women in dundori for access to clean water and environmental sustainability | Supply Of Water Tanks To Vulnerable Women In Dundori completed | 3110502 | Water Supplies and Sewerage | Bahati | Dundori | -0.2631, 36.187452 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | N/A | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 300000 | 100 | 300000 | 300000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Distribution across the ward.
2604 | Water and Sewerage Management | Supply Of Water Tanks To Vulnerable Women | To implement supply of water tanks to vulnerable women for access to clean water and environmental sustainability | Supply Of Water Tanks To Vulnerable Women completed | 3110502 | Water Supplies and Sewerage | Bahati | Dundori | -0.2631, 36.187452 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 800000 | 162276 | 162276 | Equitable | N/A | 162276 | 0 | 637724 | 393 | 637724 | 162276 | -475448 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Distribution across the ward.
2605 | Water and Sewerage Management | Supply Of Water Tanks To Vulnerables In Dundori Ward | To implement supply of water tanks to vulnerables in dundori ward for access to clean water and environmental sustainability | Supply Of Water Tanks To Vulnerables In Dundori Ward completed | 3110502 | Water Supplies and Sewerage | Bahati | Dundori | -0.2631, 36.187452 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 300000 | 20 | 300000 | 1500000 | 1200000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Distribution across the ward.
2606 | Water and Sewerage Management | Supply of water tanks to Vulnerable | To implement supply of water tanks to vulnerable for access to clean water and environmental sustainability | Supply of water tanks to Vulnerable completed | 3110502 | Water Supplies and Sewerage | Bahati | Dundori | -0.2631, 36.187452 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 637724 | 42.5 | 637724 | 1500000 | 862276 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Distribution across the ward.
2607 | Water and Sewerage Management | Construction of Kasambara borehole water tower, tank and piping | To construct Kasambara borehole water tower, tank and piping | Kasambara borehole water tower, tank and piping constructed | 3110502 | Water Supplies and Sewerage | Gilgil | Eburru/Mbaruk | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | N/A | 4000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 3571500 | 119 | 3571500 | 3000000 | -571500 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
2608 | Water and Sewerage Management | Construction of Nderit borehole water tower, tank and piping | To construct Nderit borehole water tower, tank and piping | Nderit borehole water tower, tank and piping constructed | 3110502 | Water Supplies and Sewerage | Gilgil | Eburru/Mbaruk | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | N/A | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3571500 | 89.3 | 3571500 | 3571501 | 428500 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
2609 | Water and Sewerage Management | Construction of Workers borehole, water tower tanks and piping | To construct Workers borehole, water tower tanks and piping | Workers borehole, water tower tanks and piping constructed | 3110502 | Water Supplies and Sewerage | Gilgil | Eburru/Mbaruk | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | N/A | 3500000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3571500 | 89.3 | 3571500 | 3227677 | 428500 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
2610 | Water and Sewerage Management | Eburru/Mbaruk Water Works | To implement eburru/mbaruk water works for access to clean water and environmental sustainability | Eburru/Mbaruk Water Works completed | 3110502 | Water Supplies and Sewerage | Gilgil | Eburru/Mbaruk | -0.488148, 36.156876 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 22-23 | 14832983.85 | 5177625.85 | 5177625.85 | Equitable | N/A | 5177625.85 | 0 | 2491100 | 48.1 | 2491100 | 2686526 | 2686525.85 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Value for money. Viable: Yes. Contractor: Online movers ltd box 16147-Nakuru. Assessor remarks: Well done.
2611 | Water and Sewerage Management | Fencing Of Kasambara Borehole | To secure Kasambara Borehole through fencing | Kasambara Borehole fenced and secured | 3110502 | Water Supplies and Sewerage | Gilgil | Eburru/Mbaruk | -0.36445, 36.239523 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | No information | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 394446 | 98.6 | 394446 | 400000 | 5554 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: It was viable. Contractor: Marinara. Assessor remarks: Successful project.
2612 | Water and Sewerage Management | Piping And Water Point From Echariria To Kirima | To provide water distribution infrastructure at And Water Point From Echariria To Kirima | Water piping at And Water Point From Echariria To Kirima completed | 3110502 | Water Supplies and Sewerage | Gilgil | Eburru/Mbaruk | -0.336579, 36.169605 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2492315 | 99.7 | 2492315 | 2500000 | 7685 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: No details. Assessor remarks: The project was fairly done but it's not operational at this moment because of political issues..
2613 | Water and Sewerage Management | Piping at Gema area College road and Kagema road | To provide water distribution infrastructure at Gema area College road and Kagema road | Water piping at Gema area College road and Kagema road completed | 3110502 | Water Supplies and Sewerage | Gilgil | Eburru/Mbaruk | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/23 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2408820 | 96.4 | 2408820 | 49776 | 91180 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2614 | Water and Sewerage Management | Piping at Greensteds-Dehavana area | To provide water distribution infrastructure at Greensteds-Dehavana area | Water piping at Greensteds-Dehavana area completed | 3110502 | Water Supplies and Sewerage | Gilgil | Eburru/Mbaruk | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1200000 | 100 | 1200000 | 1200000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
2615 | Water and Sewerage Management | Piping At Miti Mingi To Kiwanja Ndege | To provide water distribution infrastructure at Miti Mingi To Kiwanja Ndege | Water piping at Miti Mingi To Kiwanja Ndege completed | 3110502 | Water Supplies and Sewerage | Gilgil | Eburru/Mbaruk | -0.346735, 36.167249 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2023/24 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 500000 | 100 | 500000 | 500000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Not yet completed. Contractor: Unkworn. Assessor remarks: Done Fair work.
2616 | Water and Sewerage Management | Piping at Oljorai Borehole | To provide water distribution infrastructure at Oljorai Borehole | Water piping at Oljorai Borehole completed | 3110502 | Water Supplies and Sewerage | Gilgil | Eburru/Mbaruk | -0.36445, 36.239523 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | No information | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: It was viable. Contractor: Marinara. Assessor remarks: Successful project.
2617 | Water and Sewerage Management | Piping Of Water From Kirimato To Miririshwa | To provide water distribution infrastructure at Water From Kirimato To Miririshwa | Water piping at Water From Kirimato To Miririshwa completed | 3110502 | Water Supplies and Sewerage | Gilgil | Eburru/Mbaruk | -0.336579, 36.169605 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 998101 | 99.8 | 998101 | 1000000 | 1899 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: No details. Assessor remarks: The project was fairly done but it's not operational at this moment because of political issues..
2618 | Water and Sewerage Management | Provision And Installation Of Four Water Tanks (10,000 Lts) At Echararia Borehole And Kongasis Water Project | To implement provision and installation of four water tanks (10,000 lts) at echararia borehole and kongasis water project for access to clean water and environmental sustainability | Provision And Installation Of Four Water Tanks (10,000 Lts) At Echararia Borehole And Kongasis Water Project completed | 3110502 | Water Supplies and Sewerage | Gilgil | Eburru/Mbaruk | -0.334898, 36.175746 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | No information | 742583 | 742583 | 742583 | Equitable | N/A | 742583 | 0 | 735332 | 99 | 735332 | 742583 | 7251 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes it was viable and it meet the needs. Contractor: Rift supplies and services Ltd. Assessor remarks: Fairly done.
2619 | Water and Sewerage Management | Purchase of tanks, installation of piping at Losiro Water Project | To procure tanks, installation of piping at Losiro Water Project | Tanks, installation of piping at Losiro Water Project procured | 3110502 | Water Supplies and Sewerage | Gilgil | Eburru/Mbaruk | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
2620 | Water and Sewerage Management | Purchase Of Tanks, Installation Of Piping At Losirwa Water Project | To procure Tanks, Installation Of Piping At Losirwa Water Project | Tanks, Installation Of Piping At Losirwa Water Project procured | 3110502 | Water Supplies and Sewerage | Gilgil | Eburru/Mbaruk | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
2621 | Water and Sewerage Management | Completion Of Milimani Water Project/Satewa | To complete Milimani Water Project/Satewa | Milimani Water Project/Satewa completed | 3110502 | Water Supplies and Sewerage | Molo | Elburgon | -0.292714, 35.791345 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | - | 2000000 | 212.1 | 212.1 | Equitable | N/A | 212.1 | 0 | 1999788 | 942851.5 | 1999788 | 212 | -1999575.9 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete and functional.
2622 | Water and Sewerage Management | Construction of 150m3 Water Tank at Tegat | To construct 150m3 Water Tank at Tegat | 150m3 Water Tank at Tegat constructed | 3110502 | Water Supplies and Sewerage | Molo | Elburgon | -0.264914, 35.831575 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | - | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1800000 | 100 | 1800000 | 1800000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Quej Enterprises ltd. Assessor remarks: Operational.
2623 | Water and Sewerage Management | Drilling of Kapsita Borehole at St. Stephen centre | To implement drilling of kapsita borehole at st. stephen centre for access to clean water and environmental sustainability | Drilling of Kapsita Borehole at St. Stephen centre completed | 3110502 | Water Supplies and Sewerage | Molo | Elburgon | -0.294954, 35.766447 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | - | 1900000 | 1900000 | 1900000 | Equitable | N/A | 1900000 | 0 | 3680654 | 193.7 | 3680654 | 1900000 | -1780654 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: KEMASIO SUPPLIES. Assessor remarks: Drilled and capped.
2624 | Water and Sewerage Management | Nyakiambi/Karunga Borehole Completion | To implement nyakiambi/karunga borehole completion for access to clean water and environmental sustainability | Nyakiambi/Karunga Borehole Completion completed | 3110502 | Water Supplies and Sewerage | Molo | Elburgon | -0.264914, 35.831575 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | - | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 1500000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Quej Enterprises ltd. Assessor remarks: Operational.
2625 | Water and Sewerage Management | Pipe Laying For Ndimu Borehole Water | To implement pipe laying for ndimu borehole water for access to clean water and environmental sustainability | Pipe Laying For Ndimu Borehole Water completed | 3110502 | Water Supplies and Sewerage | Molo | Elburgon | -0.292714 35.791345 0 2700 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1484191 | 98.9 | 1484191 | 1500000 | 15809 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Wakasi Enterprise limited. Assessor remarks: Fair.
2626 | Water and Sewerage Management | Piping at Green Estate Water Project | To provide water distribution infrastructure at Green Estate Water Project | Water piping at Green Estate Water Project completed | 3110502 | Water Supplies and Sewerage | Molo | Elburgon | -0.306163 35.800133 0 72.9000015258789 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 936234 | 93.6 | 936234 | 1000000 | 63766 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: O.B.T.Limited. Assessor remarks: Work on progrss.
2627 | Water and Sewerage Management | Piping At Ndimu Water Borehole | To provide water distribution infrastructure at Ndimu Water Borehole | Water piping at Ndimu Water Borehole completed | 3110502 | Water Supplies and Sewerage | Molo | Elburgon | -0.292714 35.791345 0 2700 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 936234 | 93.6 | 936234 | 989608 | 63766 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Wakasi Enterprise limited. Assessor remarks: Fair.
2628 | Water and Sewerage Management | Piping at Ndimu water project | To provide water distribution infrastructure at Ndimu water project | Water piping at Ndimu water project completed | 3110502 | Water Supplies and Sewerage | Molo | Elburgon | -0.292714 35.791345 0 2700 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 936234 | 93.6 | 936234 | 989608 | 63766 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Euro Enterprises company limited. Assessor remarks: Complete and functional.
2629 | Water and Sewerage Management | Piping Of Chiponde-Ribot Water Project | To provide water distribution infrastructure at Chiponde-Ribot Water Project | Water piping at Chiponde-Ribot Water Project completed | 3110502 | Water Supplies and Sewerage | Molo | Elburgon | -0.264914, 35.831575 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | Ongoing | 1500000 | 1497485.99 | 1497485.99 | Equitable | N/A | 1497485.99 | 0 | 936234 | 62.5 | 936234 | 1497486 | 561251.99 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ashaki Engineering. Assessor remarks: Work in progress.
2630 | Water and Sewerage Management | Piping On Nyariche Nyakiambi-Karuga Water Project | To provide water distribution infrastructure at On Nyariche Nyakiambi-Karuga Water Project | Water piping at On Nyariche Nyakiambi-Karuga Water Project completed | 3110502 | Water Supplies and Sewerage | Molo | Elburgon | -0.294954 35.766447 0 2799.9990234375 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 995056 | 99.5 | 995056 | 1000000 | 4944 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: GILECHAM KENYA SUPPLIES. Assessor remarks: Good.
2631 | Water and Sewerage Management | Supply and Installation of 10m3 water tank at Ribot, Turi Farmers, Lower Cheponde | To procure and install 10m3 water tank at Ribot, Turi Farmers, Lower Cheponde | 10m3 water tank at Ribot, Turi Farmers, Lower Cheponde procured and installed | 3110502 | Water Supplies and Sewerage | Molo | Elburgon | -0.303215, 35.819011 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | - | 900000 | 900000 | 900000 | Equitable | N/A | 900000 | 0 | 757552 | 84.2 | 757552 | 757552 | 142448 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Project operational.
2632 | Water and Sewerage Management | Supply and Installation of Pipes for Nyariche Water Project | To procure and install Pipes for Nyariche Water Project | Pipes for Nyariche Water Project procured and installed | 3110502 | Water Supplies and Sewerage | Molo | Elburgon | -0.165752 35.696828 0 2299.9990234375 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/23 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 2235974 | 223.6 | 2235974 | 264026 | -1235974 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: No ownership documents.
2633 | Water and Sewerage Management | Supply and Installation of Pipes to Green Estate Water Project | To procure and install Pipes to Green Estate Water Project | Pipes to Green Estate Water Project procured and installed | 3110502 | Water Supplies and Sewerage | Molo | Elburgon | -0.165752 35.696828 0 2299.9990234375 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/23 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 2235974 | 223.6 | 2235974 | 951641 | -1235974 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: No ownership documents.
2634 | Water and Sewerage Management | Supply and Installation of Water pipes for Matumaiyu water works | To procure and install Water pipes for Matumaiyu water works | Water pipes for Matumaiyu water works procured and installed | 3110502 | Water Supplies and Sewerage | Molo | Elburgon | -0.165752 35.696828 0 2299.9990234375 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2905568 | 96.9 | 2905568 | 2905568 | 94432 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: No ownership documents.
2635 | Water and Sewerage Management | Supply of pipes to Elburgon water works | To implement supply of pipes to elburgon water works for access to clean water and environmental sustainability | Supply of pipes to Elburgon water works completed | 3110502 | Water Supplies and Sewerage | Molo | Elburgon | -0.260228 35.795537 2376.5 9.5 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | N/A | 2380000 | 2380000 | 2380000 | Equitable | N/A | 2380000 | 0 | 2326200 | 97.7 | 2326200 | 2380000 | 53800 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete project.
2636 | Water and Sewerage Management | Supply of pipes to Ndimu primary water project | To implement supply of pipes to ndimu primary water project for access to clean water and environmental sustainability | Supply of pipes to Ndimu primary water project completed | 3110502 | Water Supplies and Sewerage | Molo | Elburgon | -0.292714 35.791345 0 2700 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 989422 | 0 | 989422 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Euro Enterprises company limited. Assessor remarks: Complete and functional.
2637 | Water and Sewerage Management | Water Piping At Arimi Chieponde Nyariche | To implement water piping at arimi chieponde nyariche for access to clean water and environmental sustainability | Water Piping At Arimi Chieponde Nyariche completed | 3110502 | Water Supplies and Sewerage | Molo | Elburgon | -0.290391 35.774293 0 2900 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 1500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need to make followup on ownership documents.
2638 | Water and Sewerage Management | Construction Of Nyaturu Tank And Purchase And Connection Of Pipes | To construct Nyaturu Tank And Purchase And Connection Of Pipes | Nyaturu Tank And Purchase And Connection Of Pipes constructed | 3110502 | Water Supplies and Sewerage | Gilgil | Elementaita | -0.61958, 36.115215 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2200000 | 110 | 2200000 | 1949081 | -200000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In use.
2639 | Water and Sewerage Management | Construction of Nyaturu Tank, Purchase and connection of pipes | To construct Nyaturu Tank, Purchase and connection of pipes | Nyaturu Tank, Purchase and connection of pipes constructed | 3110502 | Water Supplies and Sewerage | Gilgil | Elementaita | -0.61958, 36.115215 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2200000 | 110 | 2200000 | 2000000 | -200000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In use.
2640 | Water and Sewerage Management | Construction Of Rerechua Tank | To construct Rerechua Tank | Rerechua Tank constructed | 3110502 | Water Supplies and Sewerage | Gilgil | Elementaita | -0.563348, 36.118021 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1187473 | 99 | 1187473 | 1200000 | 12527 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
2641 | Water and Sewerage Management | Construction of tank and supply of pipes for Oakland water project | To construct tank and supply of pipes for Oakland water project | Tank and supply of pipes for Oakland water project constructed | 3110502 | Water Supplies and Sewerage | Gilgil | Elementaita | -0.567279 36.11652 1971.0999755859375 35.24100112915039 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/23 | 2200000 | 2200000 | 2200000 | Equitable | N/A | 2200000 | 0 | 1165052 | 53 | 1165052 | 1814618 | 1034948 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
2642 | Water and Sewerage Management | Construction Of Tank At Kahuruko And Purchase And Connection Of Pipes | To construct Tank At Kahuruko And Purchase And Connection Of Pipes | Tank At Kahuruko And Purchase And Connection Of Pipes constructed | 3110502 | Water Supplies and Sewerage | Gilgil | Elementaita | -0.61958, 36.115215 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 2200000 | 2200000 | 2200000 | Equitable | N/A | 2200000 | 0 | 2200000 | 100 | 2200000 | 2200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In use.
2643 | Water and Sewerage Management | Construction Of Tank For Sokoro Water | To construct Tank For Sokoro Water | Tank For Sokoro Water constructed | 3110502 | Water Supplies and Sewerage | Gilgil | Elementaita | -0.56548, 36.140662 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1165052 | 97.1 | 1165052 | 1200000 | 34948 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In use.
2644 | Water and Sewerage Management | Construction Of Upper Kanorero Water Tank | To construct Upper Kanorero Water Tank | Upper Kanorero Water Tank constructed | 3110502 | Water Supplies and Sewerage | Gilgil | Elementaita | -0.602644, 36.117023 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 1300000 | 1300000 | 1272660 | Equitable | N/A | 1272660 | 0 | 1272660 | 97.9 | 1272660 | 1300000 | 27340 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Fully functional.
2645 | Water and Sewerage Management | Drilling Of Meli Borehole | To implement drilling of meli borehole for access to clean water and environmental sustainability | Drilling Of Meli Borehole completed | 3110502 | Water Supplies and Sewerage | Gilgil | Elementaita | -0.601384, 36.106642 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 4500000 | 880656.15 | 880656.15 | Equitable | N/A | 880656.15 | 0 | 3619344 | 411 | 3619344 | 880656 | -2738687.85 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Not equipped.
2646 | Water and Sewerage Management | Kahuho water project | To implement kahuho water project for access to clean water and environmental sustainability | Kahuho water project completed | 3110502 | Water Supplies and Sewerage | Gilgil | Elementaita | -0.618481 36.146879 2073.900146484375 1.034000039100647 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 0 | 0 | 0 | 800000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs repair.
2647 | Water and Sewerage Management | Kahuho West Water Tank - Construction Of Water Tank | To implement kahuho west water tank - construction of water tank for access to clean water and environmental sustainability | Kahuho West Water Tank - Construction Of Water Tank completed | 3110502 | Water Supplies and Sewerage | Gilgil | Elementaita | -0.640563, 36.145693 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1000000 | 4327.75 | 4327.75 | Equitable | N/A | 4327.75 | 0 | 995672 | 23006.7 | 995672 | 4328 | -991344.25 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In use.
2648 | Water and Sewerage Management | Makongo Tank - Construction Of Water Tank And Piping | To implement makongo tank - construction of water tank and piping for access to clean water and environmental sustainability | Makongo Tank - Construction Of Water Tank And Piping completed | 3110502 | Water Supplies and Sewerage | Gilgil | Elementaita | -0.570322, 36.095922 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1500000 | 19485 | 19485 | Equitable | N/A | 19485 | 0 | 1480515 | 7598.2 | 1480515 | 19485 | -1461030 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
2649 | Water and Sewerage Management | Maririgua tan-construction of water tank and piping | To implement maririgua tan-construction of water tank and piping for access to clean water and environmental sustainability | Maririgua tan-construction of water tank and piping completed | 3110502 | Water Supplies and Sewerage | Gilgil | Elementaita | -0.570322, 36.095922 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1407030 | 93.8 | 1407030 | 1407030 | 92970 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
2650 | Water and Sewerage Management | Miti Miti Centre - Completion Of Water Piping | To implement miti miti centre - completion of water piping for access to clean water and environmental sustainability | Miti Miti Centre - Completion Of Water Piping completed | 3110502 | Water Supplies and Sewerage | Gilgil | Elementaita | -0.526958, 36.073972 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1700000 | 8503 | 8503 | Equitable | N/A | 8503 | 0 | 1691497 | 19892.9 | 1691497 | 8503 | -1682994 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Done.
2651 | Water and Sewerage Management | Mitimingi Settlement Borehole Pipes | To implement mitimingi settlement borehole pipes for access to clean water and environmental sustainability | Mitimingi Settlement Borehole Pipes completed | 3110502 | Water Supplies and Sewerage | Gilgil | Elementaita | -0.664198 36.110342 2290.6 14.5 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 1700000 | 1700000 | 1700000 | Equitable | N/A | 1700000 | 0 | 1700000 | 100 | 1700000 | 1700000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: In use.
2652 | Water and Sewerage Management | Mugaa Water Tank And Piping | To implement mugaa water tank and piping for access to clean water and environmental sustainability | Mugaa Water Tank And Piping completed | 3110502 | Water Supplies and Sewerage | Gilgil | Elementaita | -0.558886, 36.07641 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 1998812 | 1998812 | 1998812 | Equitable | N/A | 1998812 | 0 | 1903550 | 95.2 | 1903550 | 1998812 | 95262 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Not Functional.
2653 | Water and Sewerage Management | Munanda Police Water Tank - Construction Of Tank Police Water Tank | To implement munanda police water tank - construction of tank police water tank for access to clean water and environmental sustainability | Munanda Police Water Tank - Construction Of Tank Police Water Tank completed | 3110502 | Water Supplies and Sewerage | Gilgil | Elementaita | -0.597591, 36.111653 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 998341 | 99.8 | 998341 | 1000000 | 1659 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs renovation.
2654 | Water and Sewerage Management | Muririgua Tan - Construction Of Water Tank And Piping | To implement muririgua tan - construction of water tank and piping for access to clean water and environmental sustainability | Muririgua Tan - Construction Of Water Tank And Piping completed | 3110502 | Water Supplies and Sewerage | Gilgil | Elementaita | -0.570322, 36.095922 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1407030 | 93.8 | 1407030 | 1500000 | 92970 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
2655 | Water and Sewerage Management | Ndamu Tank - Competion Of Piping Works | To implement ndamu tank - competion of piping works for access to clean water and environmental sustainability | Ndamu Tank - Competion Of Piping Works completed | 3110502 | Water Supplies and Sewerage | Gilgil | Elementaita | -0.55338 36.112845 1929.4 12.399999618530273 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 803938.3 | 13029.3 | 13029.3 | Equitable | N/A | 13029.3 | 0 | 790909 | 6070.2 | 790909 | 13029 | -777879.7 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Ues. Viable: Yes. Assessor remarks: Operational.
2656 | Water and Sewerage Management | Ndibai Village - Completion Of Water Tank And Water Piping | To implement ndibai village - completion of water tank and water piping for access to clean water and environmental sustainability | Ndibai Village - Completion Of Water Tank And Water Piping completed | 3110502 | Water Supplies and Sewerage | Gilgil | Elementaita | -0.553445 36.112768 2020.2 15 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1595000 | 6113 | 6113 | Equitable | N/A | 6113 | 0 | 1588887 | 25991.9 | 1588887 | 6113 | -1582774 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
2657 | Water and Sewerage Management | Purchase And Supply Of Mugaa Water Pipes | To procure and supply Mugaa Water Pipes | Mugaa Water Pipes procured and supplied | 3110502 | Water Supplies and Sewerage | Gilgil | Elementaita | -0.584117 36.108603 2110.400146484375 1.0089999437332153 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 2200000 | 2200000 | 2138170 | Equitable | N/A | 2138170 | 0 | 2138170 | 97.2 | 2138170 | 354414 | 61830 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Doing well.
2658 | Water and Sewerage Management | Purchase And Supply Of Water Pipes For Kaba Thayu | To procure and supply Water Pipes For Kaba Thayu | Water Pipes For Kaba Thayu procured and supplied | 3110502 | Water Supplies and Sewerage | Gilgil | Elementaita | -0.529647, 36.090633 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 5000000 | 5000000 | 4760582 | Equitable | N/A | 4760582 | 0 | 4760582 | 95.2 | 4760582 | 354414 | 239418 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
2659 | Water and Sewerage Management | Purchase And Supply Of Water Pipes For Mahiga / Settlement | To procure and supply Water Pipes For Mahiga / Settlement | Water Pipes For Mahiga / Settlement procured and supplied | 3110502 | Water Supplies and Sewerage | Gilgil | Elementaita | -0.529647, 36.090633 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 6000000 | 5733407.9 | 5733407.9 | Equitable | N/A | 5733407.9 | 0 | 1737675 | 30.3 | 1737675 | 354414 | 3995732.9 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
2660 | Water and Sewerage Management | Purchase And Supply Of Water Pipes For Ngesha "A" | To procure and supply Water Pipes For Ngesha "A" | Water Pipes For Ngesha "A" procured and supplied | 3110502 | Water Supplies and Sewerage | Gilgil | Elementaita | -0.529647, 36.090633 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 1500000 | 1500000 | 1403866 | Equitable | N/A | 1403866 | 0 | 1403866 | 93.6 | 1403866 | 354414 | 96134 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
2661 | Water and Sewerage Management | Construction Of Kikopey Water Tank | To construct Kikopey Water Tank | Kikopey Water Tank constructed | 3110502 | Water Supplies and Sewerage | Gilgil | Gilgil | -0.335397 36.14884 0 100 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 1083163 | 1083163 | 1083163 | Equitable | N/A | 1083163 | 0 | 981857 | 90.6 | 981857 | 1083163 | 101306 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: No details. Assessor remarks: Fairly done.
2662 | Water and Sewerage Management | Drilling of borehole and pump installation at Maji moto including piping | To provide access to clean water through borehole drilling at and pump installation at Maji moto including piping | Borehole drilled at and pump installation at Maji moto including piping | 3110502 | Water Supplies and Sewerage | Gilgil | Gilgil | -0.490013 36.320046 1998.323974609375 5.228000164031982 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/23 | 7096399 | 6500000 | 6500000 | Equitable | N/A | 6500000 | 0 | 1725669 | 26.5 | 1725669 | 3228677 | 4774331 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs maintainance.
2663 | Water and Sewerage Management | Bore Hole Drilling And Equipping (Siwot & Keringet) | To implement bore hole drilling and equipping (siwot & keringet) for access to clean water and environmental sustainability | Bore Hole Drilling And Equipping (Siwot & Keringet) completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | N/A | 8000000 | 8000000 | 8000000 | N/A | N/A | 8000000 | 0 | 7752314 | 96.9 | 7752314 | 8000000 | 247686 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
2664 | Water and Sewerage Management | Bore Hole Drilling And Equipping | To implement bore hole drilling and equipping for access to clean water and environmental sustainability | Bore Hole Drilling And Equipping completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 5000000 | 1496859.1 | 1496859.1 | N/A | N/A | 1496859.1 | 0 | 1496859 | 100 | 1496859 | 1496859 | 0.1 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
2665 | Water and Sewerage Management | Borehole, equipping pumphouse, pipes and tank at Arimi Borehole in Elburgon ward in Molo Subcounty | To implement borehole, equipping pumphouse, pipes and tank at arimi borehole in elburgon ward in molo subcounty for access to clean water and environmental sustainability | Borehole, equipping pumphouse, pipes and tank at Arimi Borehole in Elburgon ward in Molo Subcounty completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 2999887 | 0 | 243774 | Equitable | N/A | 243774 | 0 | 243774 | 100 | 243774 | 0 | -243774 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2666 | Water and Sewerage Management | Borehole Works | To implement borehole works for access to clean water and environmental sustainability | Borehole Works completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 5000000 | 163336.6 | 163336.6 | Equitable | N/A | 163336.6 | 0 | 146709 | 89.8 | 146709 | 163337 | 16627.6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2667 | Water and Sewerage Management | Completion And Operationalization Of Kiamunyi Line Water Project, Network Water Project, Subuku Water Project, Kamungei Water Project And Ol-Jorai Borehole | To complete And Operationalization Of Kiamunyi Line Water Project, Network Water Project, Subuku Water Project, Kamungei Water Project And Ol-Jorai Borehole | And Operationalization Of Kiamunyi Line Water Project, Network Water Project, Subuku Water Project, Kamungei Water Project And Ol-Jorai Borehole completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 150000000 | 10233413.15 | 10233413.15 | Equitable | N/A | 10233413.15 | 0 | 11025864 | 107.7 | 11025864 | 10233413 | -792450.85 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
2668 | Water and Sewerage Management | Completion of ongoing projects (Kiamunyi water project piping) | To complete ongoing projects (Kiamunyi water project piping) | Ongoing projects (Kiamunyi water project piping) completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/23 | 150000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 3805194 | 76.1 | 3805194 | 0 | 1194806 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2669 | Water and Sewerage Management | Construction Of Small Dams And Water Pans | To construct Small Dams And Water Pans | Small Dams And Water Pans constructed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 6000000 | 3183456 | 3183456 | Equitable | N/A | 3183456 | 0 | 1436265 | 45.1 | 1436265 | 3183456 | 1747191 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
2670 | Water and Sewerage Management | Construction Of Tank And Solarization Of Water Works In Kiamaina | To construct Tank And Solarization Of Water Works In Kiamaina | Tank And Solarization Of Water Works In Kiamaina constructed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 10000000 | 106500 | 106500 | Equitable | N/A | 106500 | 0 | 9893500 | 9289.7 | 9893500 | 106500 | -9787000 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
2671 | Water and Sewerage Management | Construction Of Water Projects | To construct Water Projects | Water Projects constructed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2020/21 | N/A | 11000000 | 31511641.01 | 32467867.01 | Equitable | N/A | 32467867.01 | 0 | 1936626 | 6.1 | 1936626 | 1936626 | 29575015.01 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
2672 | Water and Sewerage Management | County Water Works | To implement county water works for access to clean water and environmental sustainability | County Water Works completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 5687803.61 | 1696991.86 | 1696991.86 | N/A | N/A | 1696991.86 | 0 | 941663 | 55.5 | 941663 | 1696992 | 755328.86 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
2673 | Water and Sewerage Management | Desilting Of Morop Dam | To implement desilting of morop dam for access to clean water and environmental sustainability | Desilting Of Morop Dam completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 15000000 | 15000000 | 15000000 | Equitable | N/A | 15000000 | 0 | 14592200 | 97.3 | 14592200 | 0 | 407800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2674 | Water and Sewerage Management | Extension of piping of Naivasha Dry Port Water | To expand piping of Naivasha Dry Port Water to increase capacity | Piping of Naivasha Dry Port Water expanded | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 9600000 | 9600000 | 9600000 | Equitable | N/A | 9600000 | 0 | 5997919 | 62.5 | 5997919 | 9600000 | 3602081 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
2675 | Water and Sewerage Management | Laying Of Water Pipes In Kiamunyi / Ngata Bridge | To implement laying of water pipes in kiamunyi / ngata bridge for access to clean water and environmental sustainability | Laying Of Water Pipes In Kiamunyi / Ngata Bridge completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 20000000 | 14958.6 | 14958.6 | N/A | N/A | 14958.6 | 0 | 19985041 | 133602.3 | 19985041 | 14959 | -19970082.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2676 | Water and Sewerage Management | Laying Of Water Pipes In Maiella Ward | To implement laying of water pipes in maiella ward for access to clean water and environmental sustainability | Laying Of Water Pipes In Maiella Ward completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 9000000 | 644989.6 | 644989.6 | N/A | N/A | 644989.6 | 0 | 6471683 | 1003.4 | 6471683 | 2528317 | -5826693.4 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
2677 | Water and Sewerage Management | Litawa Water Project | To implement litawa water project for access to clean water and environmental sustainability | Litawa Water Project completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 5354143 | 499112.2 | 499112.2 | N/A | N/A | 499112.2 | 0 | 4855031 | 972.7 | 4855031 | 499112 | -4355918.8 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
2678 | Water and Sewerage Management | Mawalebo Water Project | To implement mawalebo water project for access to clean water and environmental sustainability | Mawalebo Water Project completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 5000000 | 916219.1 | 916219.1 | N/A | N/A | 916219.1 | 0 | 1116806 | 121.9 | 1116806 | 916219 | -200586.9 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
2679 | Water and Sewerage Management | Naivawass Works | To implement naivawass works for access to clean water and environmental sustainability | Naivawass Works completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 1750000 | 1750000 | 1750000 | N/A | N/A | 1750000 | 0 | 1750000 | 100 | 1750000 | 1750000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2680 | Water and Sewerage Management | Naruwasco Works | To implement naruwasco works for access to clean water and environmental sustainability | Naruwasco Works completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 2500000 | 2500000 | 2500000 | N/A | N/A | 2500000 | 0 | 1750000 | 70 | 1750000 | 2500000 | 750000 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
2681 | Water and Sewerage Management | Nyondia Water Project | To implement nyondia water project for access to clean water and environmental sustainability | Nyondia Water Project completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 4675825.95 | 4675825.95 | 4675825.95 | N/A | N/A | 4675825.95 | 0 | 485466 | 10.4 | 485466 | 4675826 | 4190359.95 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
2682 | Water and Sewerage Management | Piping of Senenet water project | To provide water distribution infrastructure at Senenet water project | Water piping at Senenet water project completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 5000000 | 0 | 5000000 | Equitable | N/A | 5000000 | 0 | 4855031 | 100 | 4855031 | 5000000 | -4855031 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
2683 | Purchase Of Water Tanks | Purchase Of Water Tanks | To procure Water Tanks | Water Tanks procured | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 3021214.55 | 27045.75 | 27045.75 | N/A | N/A | 27045.75 | 0 | 2994169 | 11070.8 | 2994169 | 27046 | -2967123.25 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2684 | Water and Sewerage Management | Rehabilitation Of Naruwassco Water Works | To rehabilitate Naruwassco Water Works to restore functionality | Naruwassco Water Works rehabilitated | 3110502 | Water Supplies and Sewerage | HQ | HQ | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 945567.85 | 945567.85 | 945567.85 | N/A | N/A | 945567.85 | 0 | 2994378 | 316.7 | 2994378 | 945568 | -2048810.15 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
2685 | Water and Sewerage Management | Completion Of Mirera Borehole | To complete Mirera Borehole | Mirera Borehole completed | 3110502 | Water Supplies and Sewerage | Naivasha | Hells Gate | -0.78226, 36.446978 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 999431 | 999431 | 999431 | Equitable | N/A | 999431 | 0 | 999431 | 100 | 999431 | 999431 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Project cost 999,431.
2686 | Water and Sewerage Management | Construction Of Two 10,000-Litre Tanks At Karai And Installation Of Water Pipes At Karai | To construct Two 10,000-Litre Tanks At Karai And Installation Of Water Pipes At Karai | Two 10,000-Litre Tanks At Karai And Installation Of Water Pipes At Karai constructed | 3110502 | Water Supplies and Sewerage | Naivasha | Hells Gate | -0.770225, 36.487134 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 2000000 | 2000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Project cost 1,000,000.
2687 | Water and Sewerage Management | Drilling Of Borehole At Mirera Focus Water Project Water Project | To provide access to clean water through borehole drilling at Mirera Focus Water Project Water Project | Borehole drilled at Mirera Focus Water Project Water Project | 3110502 | Water Supplies and Sewerage | Naivasha | Hells Gate | -0.837765, 36.55962 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2950064 | 98.3 | 2950064 | 3000000 | 49936 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Project cost 3,000,000.
2688 | Water And Sewerage Management | Mountain View Water Project Drilling Of Borehole And Installation Of Pump And Piping | To implement mountain view water project drilling of borehole and installation of pump and piping for access to clean water and environmental sustainability | Mountain View Water Project Drilling Of Borehole And Installation Of Pump And Piping completed | 3110502 | Water Supplies and Sewerage | Naivasha | Hells Gate | -0.777377, 36.456881 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 873268 | 873268 | 873268 | Equitable | N/A | 873268 | 0 | 2321284 | 265.8 | 2321284 | 873268 | -1448016 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The borehole is still in use, few repairs from then have been made.
2689 | Water and Sewerage Management | Mountain View Water Project (Piping, Water Tanks, Installation Of Solar Pumps) | To implement mountain view water project (piping, water tanks, installation of solar pumps) for access to clean water and environmental sustainability | Mountain View Water Project (Piping, Water Tanks, Installation Of Solar Pumps) completed | 3110502 | Water Supplies and Sewerage | Naivasha | Hells Gate | -0.777464, 36.456934 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 15000000 | 2439348.2 | 2439348.2 | Equitable | N/A | 2439348.2 | 0 | 2321284 | 95.2 | 2321284 | 118064 | 118064.2 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is going on well , few challenges here and there.
2690 | Piping At Nyamathi Water Project | Piping At Nyamathi Water Project | To provide water distribution infrastructure at Nyamathi Water Project | Water piping at Nyamathi Water Project completed | 3110502 | Water Supplies and Sewerage | Naivasha | Hells Gate | -0.779784, 36.519793 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1871034 | 93.6 | 1871034 | 34530 | 128966 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Project cost 6,999,000.00.
2691 | Water and Sewerage Management | Construction Of 2 Tanks And Piping At Kangata And Mama Mbushe | To construct 2 Tanks And Piping At Kangata And Mama Mbushe | 2 Tanks And Piping At Kangata And Mama Mbushe constructed | 3110502 | Water Supplies and Sewerage | Bahati | Kabatini | -0.196066, 36.197552 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2023 | 3000000 | 17.3 | 17.3 | Equitable | N/A | 17.3 | 0 | 2999983 | 17340942.2 | 2999983 | 17 | -2999965.7 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Yes. Contractor: Gyan enterprises. Assessor remarks: Project is yet to start because permit has not been paid to Kenya forest association ,the outlet [ope is one inch but the consumers needed atleast 3 inch intake pipe.
2692 | Water and Sewerage Management | Drilling, equipping and solarization of Mwaki Mugi Borehole | To implement drilling, equipping and solarization of mwaki mugi borehole for access to clean water and environmental sustainability | Drilling, equipping and solarization of Mwaki Mugi Borehole completed | 3110502 | Water Supplies and Sewerage | Bahati | Kabatini | -0.22502, 36.168369 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | N/A | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 1476692 | 24.6 | 1476692 | 6000000 | 4523308 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes. Assessor remarks: The project was never done the allocation was reallocated to kwa Jonathan borehole.
2693 | Water and Sewerage Management | Drilling Of Limuko Borehole | To implement drilling of limuko borehole for access to clean water and environmental sustainability | Drilling Of Limuko Borehole completed | 3110502 | Water Supplies and Sewerage | Bahati | Kabatini | -0.217267, 36.160385 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2022 | 2000000 | 1476692 | 1476692 | Equitable | N/A | 1476692 | 0 | 1476692 | 100 | 1476692 | 1476692 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Hantus enterprise ltd. Assessor remarks: Borehole operational,requires more reticulation and there is an existing court case the community want the county to refund money the used to buy the land.
2694 | Water and Sewerage Management | Piping At Kabatini Kwa Pastor To Moi Ndeffo Heroes | To provide water distribution infrastructure at Kabatini Kwa Pastor To Moi Ndeffo Heroes | Water piping at Kabatini Kwa Pastor To Moi Ndeffo Heroes completed | 3110502 | Water Supplies and Sewerage | Bahati | Kabatini | -0.216169 36.164536 2031.300048828125 72.9000015258789 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 8744 | 8744 | Equitable | N/A | 8744 | 0 | 1991256 | 22772.8 | 1991256 | 8744 | -1982512 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No it's not done. Viable: No. Contractor: Bitro construction. Assessor remarks: The fund were reallocated to piping at ngosur dam.
2695 | Water and Sewerage Management | Piping From Bahati Boys To JC Centre | To provide water distribution infrastructure at From Bahati Boys To JC Centre | Water piping at From Bahati Boys To JC Centre completed | 3110502 | Water Supplies and Sewerage | Bahati | Kabatini | -0.188579 36.170613 2132.299560546875 11.930000305175781 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 1640.6 | 1640.6 | Equitable | N/A | 1640.6 | 0 | 1998359 | 121806.6 | 1998359 | 1641 | -1996718.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Yes. Contractor: Navitas construction/ridgerock enterprise. Assessor remarks: Pipes are leaking,the project needs more piping and a bigger intake.
2696 | Water and Sewerage Management | Piping from Mutarakwa to Kabatini main tank 4 pipes | To provide water distribution infrastructure at from Mutarakwa to Kabatini main tank 4 pipes | Water piping at from Mutarakwa to Kabatini main tank 4 pipes completed | 3110502 | Water Supplies and Sewerage | Bahati | Kabatini | -0.196066, 36.197552 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2023 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 2000000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Yes. Contractor: Gyan enterprises. Assessor remarks: Project is yet to start because permit has not been paid to Kenya forest association ,the outlet [ope is one inch but the consumers needed atleast 3 inch intake pipe.
2697 | Water and Sewerage Management | Piping Of Kwa Muchina Water Project | To provide water distribution infrastructure at Kwa Muchina Water Project | Water piping at Kwa Muchina Water Project completed | 3110502 | Water Supplies and Sewerage | Bahati | Kabatini | -0.188579 36.170613 2132.299560546875 11.930000305175781 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1176286 | 98 | 1176286 | 1200000 | 23714 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Yes. Contractor: Navitas construction/ridgerock enterprise. Assessor remarks: Pipes are leaking,the project needs more piping and a bigger intake.
2698 | Water and Sewerage Management | Purchase And Supply Of 3000L Water Tank | To procure and supply 3000L Water Tank | 3000L Water Tank procured and supplied | 3110502 | Water Supplies and Sewerage | Bahati | Kabatini | -0.214433 36.162776 2030.4000244140625 10.21500015258789 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 1204 | 1204 | Equitable | N/A | 1204 | 0 | 1998796 | 166013 | 1998796 | 1204 | -1997592 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Willis samwa suppliers limited. Assessor remarks: Operational.
2699 | Water and Sewerage Management | Additional Fund To Kabazi Water Works | To implement additional fund to kabazi water works for access to clean water and environmental sustainability | Additional Fund To Kabazi Water Works completed | 3110502 | Water Supplies and Sewerage | Subukia | Kabazi | -0.077902 36.17096 2259.4 11.899999618530273 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | N/A | 4416057 | 4416057 | 4416057 | Equitable | N/A | 4416057 | 0 | 640770 | 14.5 | 640770 | 3775288 | 3775287 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Gutters require repairs.
2700 | Water and Sewerage Management | Construction of a storage tank, water intake and piping at Kiremba Water Project | To construct a storage tank, water intake and piping at Kiremba Water Project | A storage tank, water intake and piping at Kiremba Water Project constructed | 3110502 | Water Supplies and Sewerage | Subukia | Kabazi | -0.17004, 36.124855 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2023/24 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1997398 | 99.9 | 1997398 | 2000000 | 2602 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Mopawa investment ltd. Assessor remarks: Requires additional pipping.
2701 | Water and Sewerage Management | Construction of Kihoto storage tank | To construct Kihoto storage tank | Kihoto storage tank constructed | 3110502 | Water Supplies and Sewerage | Subukia | Kabazi | -0.15803, 36.079328 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2020/21 | 2800000 | 2800000 | 2800000 | Equitable | N/A | 2800000 | 0 | 2718933 | 97.1 | 2718933 | 499211 | 81067 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: Not indicated. Assessor remarks: To be operationalized.
2702 | Water and Sewerage Management | Construction of storage tank and equipping of Gitura Water Project | To construct storage tank and equipping of Gitura Water Project | Storage tank and equipping of Gitura Water Project constructed | 3110502 | Water Supplies and Sewerage | Subukia | Kabazi | -0.17004, 36.124855 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2023/24 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 3000000 | 150 | 3000000 | 2000000 | -1000000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Mopawa investment ltd. Assessor remarks: Requires additional pipping.
2703 | Water and Sewerage Management | Drilling of Mwireri Borehole and Ng'enda Borehole | To implement drilling of mwireri borehole and ng'enda borehole for access to clean water and environmental sustainability | Drilling of Mwireri Borehole and Ng'enda Borehole completed | 3110502 | Water Supplies and Sewerage | Subukia | Kabazi | -0.07176, 36.1704 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2023/24 | 7000000 | 7000000 | 7000000 | Equitable | N/A | 7000000 | 0 | 6305026 | 90.1 | 6305026 | 44962 | 694974 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: To be repaired.
2704 | Water and Sewerage Management | Kabazi Water Works In Solai, Ndungiri, Kamuohi, Kihoto And Jumuia Villages - Piping And Roofing Of Water Tanks | To implement kabazi water works in solai, ndungiri, kamuohi, kihoto and jumuia villages - piping and roofing of water tanks for access to clean water and environmental sustainability | Kabazi Water Works In Solai, Ndungiri, Kamuohi, Kihoto And Jumuia Villages - Piping And Roofing Of Water Tanks completed | 3110502 | Water Supplies and Sewerage | Subukia | Kabazi | -0.09011, 36.16711 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 15000000 | 14999999.6 | 14999999.6 | Equitable | N/A | 14999999.6 | 0 | 14613726 | 97.4 | 14613726 | 8586872 | 386273.6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Macnox contractors and Gen supplies. Assessor remarks: Pipping.
2705 | Water and Sewerage Management | Kabazi Water Works | To implement kabazi water works for access to clean water and environmental sustainability | Kabazi Water Works completed | 3110502 | Water Supplies and Sewerage | Subukia | Kabazi | -0.077902 36.17096 2259.4 11.899999618530273 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2019/20 | N/A | 15400000 | 13849622 | 13849622 | Equitable | N/A | 13849622 | 0 | 2547005 | 18.4 | 2547005 | 1165035 | 11302617 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Gutters require repairs.
2706 | Water and Sewerage Management | Piping of Ruiru Water Project | To provide water distribution infrastructure at Ruiru Water Project | Water piping at Ruiru Water Project completed | 3110502 | Water Supplies and Sewerage | Subukia | Kabazi | -0.07176 36.1704 0 783.315673828125 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | N/A | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 5000000 | 125 | 5000000 | 4000000 | -1000000 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: To be operationalized.
2707 | Water and Sewerage Management | Kabazi Water Works | To implement kabazi water works for access to clean water and environmental sustainability | Kabazi Water Works completed | 3110502 | Water Supplies and Sewerage | Subukia | Kabazi | -0.077902 36.17096 2259.4 11.899999618530273 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 584535 | 32537.4 | 32537.4 | Equitable | N/A | 32537.4 | 0 | 2547005 | 7827.9 | 2547005 | 1165035 | -2514467.6 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Gutters require repairs.
2708 | Water and Sewerage Management | Choronok Water Project - Construction of 50m3 Water tank | To implement choronok water project - construction of 50m3 water tank for access to clean water and environmental sustainability | Choronok Water Project - Construction of 50m3 Water tank completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Kamara | -0.21323 35.661657 2695.9 4.699999809265137 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/23 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Elwaso enterprise limited. Assessor remarks: Complete but needs fencing.
2709 | Water and Sewerage Management | Completion Of Mlima Water Project | To complete Mlima Water Project | Mlima Water Project completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Kamara | -0.149131, 35.715047 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2022/23 | 1376602.6 | 1376602.6 | 1376602.6 | Equitable | N/A | 1376602.6 | 0 | 1999697 | 145.3 | 1999697 | 1376603 | -623094.4 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: LUMISEAL ENTERPRISE. Assessor remarks: Presence of borehole and 18 solars, chain link and a gate.
2710 | Water and Sewerage Management | Kamara Location Waterworks | To implement kamara location waterworks for access to clean water and environmental sustainability | Kamara Location Waterworks completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Kamara | -0.08778 35.67402 2487.6 4.5 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 6743 | 6743 | Equitable | N/A | 6743 | 0 | 1993257 | 29560.4 | 1993257 | 6743 | -1986514 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: VESTA ENTERPRISES LTD. Assessor remarks: Project constructed in Kamara secondary instead of Kamara primary. It's being used as a classroom for secondary.
2711 | Water and Sewerage Management | Kamara Ward Water Works | To implement kamara ward water works for access to clean water and environmental sustainability | Kamara Ward Water Works completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Kamara | -0.149157 35.715017 2708.8 2.700000047683716 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 2033665 | 1950540 | 1950540 | Equitable | N/A | 1950540 | 0 | 1950540 | 100 | 1950540 | 1950540 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: LUMISEAL ENTERPRISE LTD. Assessor remarks: Project done.
2712 | Water and Sewerage Management | Kiptank Water Project Kamara Center | To implement kiptank water project kamara center for access to clean water and environmental sustainability | Kiptank Water Project Kamara Center completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Kamara | -0.149078, 35.715007 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2021/22 | 6500000 | 6500000 | 6500000 | Equitable | N/A | 6500000 | 0 | 6197806 | 95.4 | 6197806 | 6197806 | 302194 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: LUMISEAL ENTERPRISE LTD. Assessor remarks: Laying of pipes done from borehole to 2 community tanks and no extension of pipe laying networks to the community - according to the residents.
2713 | Water and Sewerage Management | Kiptenden Mau Water Works | To implement kiptenden mau water works for access to clean water and environmental sustainability | Kiptenden Mau Water Works completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Kamara | -0.149157 35.715017 2708.8 2.700000047683716 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 1992240 | 1992240 | Equitable | N/A | 1992240 | 0 | 1992240 | 100 | 1992240 | 1992240 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: LUMISEAL ENTERPRISE LTD. Assessor remarks: Project done.
2714 | Water and Sewerage Management | Mau Secondary Water Project - Drilling of borehole, equipping it for supply of two water tanks at Mau Village | To implement mau secondary water project - drilling of borehole, equipping it for supply of two water tanks at mau village for access to clean water and environmental sustainability | Mau Secondary Water Project - Drilling of borehole, equipping it for supply of two water tanks at Mau Village completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Kamara | -0.21323 35.661657 2695.9 4.699999809265137 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/23 | 7500000 | 3449503 | 3449503 | Equitable | N/A | 3449503 | 0 | 3025006 | 87.7 | 3025006 | 392312 | 424497 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Elwaso enterprise limited. Assessor remarks: Complete but needs fencing.
2715 | Water and Sewerage Management | Mau Summit Location Water Works | To implement mau summit location water works for access to clean water and environmental sustainability | Mau Summit Location Water Works completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Kamara | -0.17195 35.678957 2519.7999999999997 3.9000000953674316 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 4916 | 4916 | Equitable | N/A | 4916 | 0 | 1995084 | 40583.5 | 1995084 | 4916 | -1990168 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partialy. Contractor: ECLAT MERCHANTS LTD. Assessor remarks: Needs routine maintenance.
2716 | Water and Sewerage Management | Piping And Tank In Choronok, Sarambei, Pipeline, Kamara & Muchorwe Water Projects | To provide water distribution infrastructure at And Tank In Choronok, Sarambei, Pipeline, Kamara & Muchorwe Water Projects | Water piping at And Tank In Choronok, Sarambei, Pipeline, Kamara & Muchorwe Water Projects completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Kamara | -0.21326 35.661655 2696.4 3.200000047683716 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 7134660 | 7134660 | 7134660 | Equitable | N/A | 7134660 | 0 | 7134661 | 100 | 7134661 | 7134660 | -1 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Unknown. Assessor remarks: Complete and in use. Needs fencing.
2717 | Water and Sewerage Management | Piping in Kiwanja Ndege | To provide water distribution infrastructure at in Kiwanja Ndege | Water piping at in Kiwanja Ndege completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Kamara | -0.097643, 35.68589 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 31/06/2025 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 3492870 | 349.3 | 3492870 | 1000000 | -2492870 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: JOMIKOKA CONSTRUCTION (A) LTD. Assessor remarks: Complete.
2718 | Water and Sewerage Management | Tank Construction at Muchorwe - Kisii Ndogo Water Project | To implement tank construction at muchorwe - kisii ndogo water project for access to clean water and environmental sustainability | Tank Construction at Muchorwe - Kisii Ndogo Water Project completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Kamara | -0.193912, 35.687647 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | Ongoing | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 7134661 | 356.7 | 7134661 | 1958406 | -5134661 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Ongoing. Viable: Ongoing. Contractor: Messis construction company ltd. Assessor remarks: Ongoing.
2719 | Water and Sewerage Management | Drilling And Piping Of Lalwet Borehole | To implement drilling and piping of lalwet borehole for access to clean water and environmental sustainability | Drilling And Piping Of Lalwet Borehole completed | 3110502 | Water Supplies and Sewerage | Nakuru West | Kapkures | -0.324324, 36.018595 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 2924609 | 58.5 | 2924609 | 2075391 | 2075391 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Not viable. Project collapsed due to hole collapse. Assessor remarks: Hole collapsed during drilling..
2720 | Water and Sewerage Management | Water piping across Lalwet and Mogoon boreholes | To implement water piping across lalwet and mogoon boreholes for access to clean water and environmental sustainability | Water piping across Lalwet and Mogoon boreholes completed | 3110502 | Water Supplies and Sewerage | Nakuru West | Kapkures | -0.324324, 36.018595 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2021/22 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1424387 | 95 | 1424387 | 2075391 | 75613 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Not viable. Project collapsed due to hole collapse. Assessor remarks: Hole collapsed during drilling..
2721 | Water and Sewerage Management | Water Works At Ingobor Water Project | To implement water works at ingobor water project for access to clean water and environmental sustainability | Water Works At Ingobor Water Project completed | 3110502 | Water Supplies and Sewerage | Nakuru West | Kapkures | -0.324324, 36.036613 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1800000 | 8736 | 8736 | Equitable | N/A | 8736 | 0 | 1791264 | 20504.4 | 1791264 | 8736 | -1782528 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Has enhanced access to clean water. Assessor remarks: Pipe laying complete and in use.
2722 | Water and Sewerage Management | Drilling Of Borehole And Piping At Tulwet | To provide access to clean water through borehole drilling at And Piping At Tulwet | Borehole drilled at And Piping At Tulwet | 3110502 | Water Supplies and Sewerage | Nakuru West | Kapkures | -0.324324, 36.036613 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 1501505.6 | 1501505.6 | 1501505.6 | Equitable | N/A | 1501505.6 | 0 | 1998494 | 133.1 | 1998494 | 1501506 | -496988.4 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Collapsed during drilling.
2723 | Water and Sewerage Management | Installation Of Pipes And Water Tank At Tachasis (Kapkures Borehole) | To install Pipes And Water Tank At Tachasis (Kapkures Borehole) | Pipes And Water Tank At Tachasis (Kapkures Borehole) installed | 3110502 | Water Supplies and Sewerage | Nakuru West | Kapkures | -0.306306, 36.018533 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1898510 | 94.9 | 1898510 | 2000000 | 101490 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Improved access to clean water. Assessor remarks: Done and operational.
2724 | Water and Sewerage Management | Construction Of An Underground Tank 100,000L,Water Pump And 10,000L Overhead Supply Tank In Rhoda Market Kaptembwo Ward | To construct An Underground Tank 100,000L,Water Pump And 10,000L Overhead Supply Tank In Rhoda Market Kaptembwo Ward | An Underground Tank 100,000L,Water Pump And 10,000L Overhead Supply Tank In Rhoda Market Kaptembwo Ward constructed | 3110502 | Water Supplies and Sewerage | Nakuru West | Kaptembwo | -0.321856 36.057146 1774.885521028355 12.432000160217285 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Cyrus Boit. Viable: Yes. Assessor remarks: Floor is tiled BTW the walls need renovation,broken window panes.
2725 | Water and Sewerage Management | Purchasing Of 5,000L Water Tanks And Piping For Each Of The 14 Water Kiosks Across Kaptembwo Ward, Painting And Branding Of The Kiosks | To implement purchasing of 5,000l water tanks and piping for each of the 14 water kiosks across kaptembwo ward, painting and branding of the kiosks for access to clean water and environmental sustainability | Purchasing Of 5,000L Water Tanks And Piping For Each Of The 14 Water Kiosks Across Kaptembwo Ward, Painting And Branding Of The Kiosks completed | 3110502 | Water Supplies and Sewerage | Nakuru West | Kaptembwo | -0.29996 36.051202 1804.199951171875 26.304000854492188 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | N/A | 4398820 | 4398820 | 4398820 | Equitable | N/A | 4398820 | 0 | 601180 | 13.7 | 601180 | 2398820 | 3797640 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Contractor: Not awarded. Assessor remarks: The school have all the amenities pertaining classes the money should do another project.
2726 | Water and Sewerage Management | Additional Fund For Tendwet Water Project | To implement additional fund for tendwet water project for access to clean water and environmental sustainability | Additional Fund For Tendwet Water Project completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.506215 35.697313 0 34.400001525878906 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 500000 | 100 | 500000 | 500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Pump failure.
2727 | Water and Sewerage Management | Construction of powerhouse , connection of electricity, purchase of pumpset, piping at soitalam and repair of chebara water pump | To construct powerhouse , connection of electricity, purchase of pumpset, piping at soitalam and repair of chebara water pump | Powerhouse , connection of electricity, purchase of pumpset, piping at soitalam and repair of chebara water pump constructed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.468185 35.645505 2570.8999999999996 12.5 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1213650 | 60.7 | 1213650 | 1800000 | 786350 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes but they need one more. Assessor remarks: Need more class.
2728 | Water and Sewerage Management | Construction Of Water Tank At Saptet Water Project | To construct Water Tank At Saptet Water Project | Water Tank At Saptet Water Project constructed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.482883 35.707903 2706.2 10.5 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1838120 | 91.9 | 1838120 | 2000000 | 161880 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
2729 | Water and Sewerage Management | Drilling Of Borehole At Baraka/Bararget | To provide access to clean water through borehole drilling at Baraka/Bararget | Borehole drilled at Baraka/Bararget | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.417612, 35.723675 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2023 | 3000000 | 279843.65 | 279843.65 | Equitable | N/A | 279843.65 | 0 | 2720156 | 972 | 2720156 | 279844 | -2440312.35 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Initially the project was to be done at bararget but later changed to baseline.
2730 | Water and Sewerage Management | Installation Of Water Tank And Piping At Tuiyobei | To install Water Tank And Piping At Tuiyobei | Water Tank And Piping At Tuiyobei installed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.437227, 35.703787 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2022 | 300000 | 293202.4 | 293202.4 | Equitable | N/A | 293202.4 | 0 | 1277612 | 435.7 | 1277612 | 293202 | -984409.6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
2731 | Water and Sewerage Management | Installation Of Water Tank, Fencing And Piping At Silibwet Water Project | To install Water Tank, Fencing And Piping At Silibwet Water Project | Water Tank, Fencing And Piping At Silibwet Water Project installed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.471103 35.6416 2687.900146484375 5.099999904632568 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 1277612 | 319.4 | 1277612 | 400000 | -877612 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
2732 | Water and Sewerage Management | Piping And Installation Of Water Kiosk (10,000L Water Tank At Kpakwen Primary School) | To provide water distribution infrastructure at And Installation Of Water Kiosk (10,000L Water Tank At Kpakwen Primary School) | Water piping at And Installation Of Water Kiosk (10,000L Water Tank At Kpakwen Primary School) completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.463277, 35.709932 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | N/A | 2022 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1200000 | 100 | 1200000 | 1200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: Not yet started.
2733 | Water and Sewerage Management | Piping Of Water From Silibwet To Bandiat. | To provide water distribution infrastructure at Water From Silibwet To Bandiat | Water piping at Water From Silibwet To Bandiat completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.515075 35.718312 2624.1 4.800000190734863 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 1700000 | 1676965.6 | 1676965.6 | Equitable | N/A | 1676965.6 | 0 | 1676966 | 100 | 1676966 | 1676966 | -0.4 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Pump failed.
2734 | Water and Sewerage Management | Piping Water At Keringet From Kapkores | To provide water distribution infrastructure at Water At Keringet From Kapkores | Water piping at Water At Keringet From Kapkores completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.515075 35.718312 2624.1 4.800000190734863 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 2000000 | 2808.85 | 2808.85 | Equitable | N/A | 2808.85 | 0 | 1997191 | 71103.5 | 1997191 | 2809 | -1994382.15 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Pump failed.
2735 | Water and Sewerage Management | Piping Water At Tulwet | To provide water distribution infrastructure at Water At Tulwet | Water piping at Water At Tulwet completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.506213, 35.697315 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2020 | 1500000 | 812.5 | 812.5 | Equitable | N/A | 812.5 | 0 | 1499188 | 184515.4 | 1499188 | 813 | -1498375.5 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not in operation.
2736 | Water and Sewerage Management | Piping Water From Silibwet To Pombo | To provide water distribution infrastructure at Water From Silibwet To Pombo | Water piping at Water From Silibwet To Pombo completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.483387, 35.707437 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2021 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 950161 | 95 | 950161 | 1000000 | 49839 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
2737 | Water and Sewerage Management | Piping Water From Soitaran To Lelaibei Primary School And Installation Of Water Kiosk (10,000 Litres Water Tank | To provide water distribution infrastructure at Water From Soitaran To Lelaibei Primary School And Installation Of Water Kiosk (10,000 Litres Water Tank | Water piping at Water From Soitaran To Lelaibei Primary School And Installation Of Water Kiosk (10,000 Litres Water Tank completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.463277, 35.709932 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | N/A | 2022 | 1200000 | 1185427.2 | 1185427.2 | Equitable | N/A | 1185427.2 | 0 | 1164175 | 98.2 | 1164175 | 1185427 | 21252.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: Not yet started.
2738 | Water and Sewerage Management | Plumbing And Piping Water At Silibwet | To implement plumbing and piping water at silibwet for access to clean water and environmental sustainability | Plumbing And Piping Water At Silibwet completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.506213, 35.697315 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2020 | 1000000 | 4533.5 | 4533.5 | Equitable | N/A | 4533.5 | 0 | 995467 | 21958 | 995467 | 4534 | -990933.5 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not in operation.
2739 | Water and Sewerage Management | Purchase And Installation Of Water Tanks And Piping Of Saptet Water Project | To procure and install Water Tanks And Piping Of Saptet Water Project | Water Tanks And Piping Of Saptet Water Project procured and installed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.501323 35.714485 2647.8 6.300000190734863 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 1033.05 | 1033.05 | Equitable | N/A | 1033.05 | 0 | 1998967 | 193501.5 | 1998967 | 1033 | -1997933.95 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not in operation due to pu. P failure.
2740 | Water and Sewerage Management | Purchase and supply of 5,000 litres and 10,000 litres water tanks in Keringet ward | To procure and supply 5,000 litres and 10,000 litres water tanks in Keringet ward | 5,000 litres and 10,000 litres water tanks in Keringet ward procured and supplied | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.417738, 35.723725 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2024 | 799650 | 799650 | 799650 | Equitable | N/A | 799650 | 0 | 675973 | 84.5 | 675973 | 799650 | 123677 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
2741 | Water and Sewerage Management | Purchase and supply of water pipes and fittings to Keringet water projects | To procure and supply water pipes and fittings to Keringet water projects | Water pipes and fittings to Keringet water projects procured and supplied | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.417738, 35.723725 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2024 | 3400000 | 3400000 | 3400000 | Equitable | N/A | 3400000 | 0 | 3400000 | 100 | 3400000 | 3400000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
2742 | Water and Sewerage Management | Purchase And Supply Of Water Pipes In Keringet Ward | To procure and supply Water Pipes In Keringet Ward | Water Pipes In Keringet Ward procured and supplied | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.417738, 35.723725 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2024 | 1555411 | 1489820 | 1489820 | Equitable | N/A | 1489820 | 0 | 3400000 | 228.2 | 3400000 | 1089820 | -1910180 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
2743 | Water and Sewerage Management | Purchase of a skip | To procure a skip | A skip procured | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.427111 35.693151 2683.500244140625 40.32899856567383 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 700000 | 100 | 700000 | 700000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: 2017. Assessor remarks: Bought but no bus park.
2744 | Water and Sewerage Management | Water Piping From Bararget To Kiptulwa Primary School | To implement water piping from bararget to kiptulwa primary school for access to clean water and environmental sustainability | Water Piping From Bararget To Kiptulwa Primary School completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.417828, 35.723693 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2022 | 1300000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 1288830 | 99.1 | 1288830 | 1300000 | 11170 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
2745 | Water and Sewerage Management | Water Piping From Saptet To Soimet | To implement water piping from saptet to soimet for access to clean water and environmental sustainability | Water Piping From Saptet To Soimet completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.483387, 35.707437 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2021 | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 700000 | 100 | 700000 | 700000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
2746 | Water and Sewerage Management | Water Piping From Tulwet To Ndabibit Primary School | To implement water piping from tulwet to ndabibit primary school for access to clean water and environmental sustainability | Water Piping From Tulwet To Ndabibit Primary School completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.447195, 35.704157 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2023 | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 400000 | 100 | 400000 | 400000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Pump failure.
2747 | Water and Sewerage Management | Construction Of Water Tank At Chebara | To construct Water Tank At Chebara | Water Tank At Chebara constructed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Keringet | -0.471803, 35.68375 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2023 | 800000 | 992 | 992 | Equitable | N/A | 992 | 0 | 799008 | 80545.2 | 799008 | 992 | -798016 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: Pump failure.
2748 | Water and Sewerage Management | Gituamba Water Works And Piping | To implement gituamba water works and piping for access to clean water and environmental sustainability | Gituamba Water Works And Piping completed | 3110502 | Water Supplies and Sewerage | Bahati | Kiamaina | -0.24371, 36.130752 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1800000 | 2363.55 | 2363.55 | Equitable | N/A | 2363.55 | 0 | 1797636 | 76056.6 | 1797636 | 2364 | -1795272.45 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project was piped to community.
2749 | Water and Sewerage Management | Kiamaina Ward Water Works - Piping And Equipping Of Boreholes | To implement kiamaina ward water works - piping and equipping of boreholes for access to clean water and environmental sustainability | Kiamaina Ward Water Works - Piping And Equipping Of Boreholes completed | 3110502 | Water Supplies and Sewerage | Bahati | Kiamaina | -0.240658 36.110485 1920.5999755859375 2.799999952316284 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1998693 | 99.9 | 1998693 | 2000000 | 1307 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Pipes were laid on Heshima water project.
2750 | Water and Sewerage Management | Kiamaina Ward Water Works | To implement kiamaina ward water works for access to clean water and environmental sustainability | Kiamaina Ward Water Works completed | 3110502 | Water Supplies and Sewerage | Bahati | Kiamaina | -0.241345 36.138941 0 52.400001525878906 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1999000 | 100 | 1999000 | 2000000 | 1000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: Yes. Assessor remarks: No water on the pipeline.
2751 | Water and Sewerage Management | Menengai Sub-Location Water Works And Piping | To implement menengai sub-location water works and piping for access to clean water and environmental sustainability | Menengai Sub-Location Water Works And Piping completed | 3110502 | Water Supplies and Sewerage | Bahati | Kiamaina | -0.234697, 36.104025 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 3800000 | 2810 | 2810 | Equitable | N/A | 2810 | 0 | 3797190 | 135131.3 | 3797190 | 2810 | -3794380 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: No water on the pipeline.
2752 | Piping Extension At Menengai Water Project And St. Peters Primary Water Project | Piping Extension At Menengai Water Project And St. Peters Primary Water Project | To provide water distribution infrastructure at Extension At Menengai Water Project And St. Peters Primary Water Project | Water piping at Extension At Menengai Water Project And St. Peters Primary Water Project completed | 3110502 | Water Supplies and Sewerage | Bahati | Kiamaina | -0.241438 36.138958 0 45.599998474121094 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 2000112 | 516 | 516 | Equitable | N/A | 516 | 0 | 1999596 | 387518.6 | 1999596 | 516 | -1999080 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: Yes. Assessor remarks: Not operating because of lack of water pump.
2753 | Water and Sewerage Management | Purchase and supply of water pipes for Menengai water project and Kiamaina water projects | To procure and supply water pipes for Menengai water project and Kiamaina water projects | Water pipes for Menengai water project and Kiamaina water projects procured and supplied | 3110502 | Water Supplies and Sewerage | Bahati | Kiamaina | -0.246945 36.092048 2193.000244140625 8.399999618530273 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | N/A | 6500000 | 6500000 | 6500000 | Equitable | N/A | 6500000 | 0 | 6283710 | 96.7 | 6283710 | 25750 | 216290 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: Yes. Assessor remarks: No water on the lines from last year.
2754 | Water and Sewerage Management | Construction Of A Water Tank At Kihingo Centre And Piping | To construct A Water Tank At Kihingo Centre And Piping | A Water Tank At Kihingo Centre And Piping constructed | 3110502 | Water Supplies and Sewerage | Njoro | Kihingo | -0.433912 35.972216 2278.2001953125 35.13199996948242 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2300000 | 50.6 | 50.6 | Equitable | N/A | 50.6 | 0 | 2299949 | 4545353.8 | 2299949 | 134 | -2299898.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Market construction has stalled.
2755 | Water and Sewerage Management | Construction Of Mutitu A Water Tank And Piping Project | To construct Mutitu A Water Tank And Piping Project | Mutitu A Water Tank And Piping Project constructed | 3110502 | Water Supplies and Sewerage | Njoro | Kihingo | -0.440033 35.974742 2303.300048828125 10.100000381469727 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 1957364.28 | 1957364.28 | Equitable | N/A | 1957364.28 | 0 | 1957364 | 100 | 1957364 | 1957364 | 0.28 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: At that time. Viable: At that time. Assessor remarks: The facility need to be condemned due to its bad state.
2756 | Water and Sewerage Management | Mutito A Water Project - Drilling Of Borehole , Construction Of Water Tank And Water Kiosk And Piping Mutito A Water Project | To implement mutito a water project - drilling of borehole , construction of water tank and water kiosk and piping mutito a water project for access to clean water and environmental sustainability | Mutito A Water Project - Drilling Of Borehole , Construction Of Water Tank And Water Kiosk And Piping Mutito A Water Project completed | 3110502 | Water Supplies and Sewerage | Njoro | Kihingo | -0.433157, 35.959162 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2024 | 6000000 | 2854393.2 | 2854393.2 | Equitable | N/A | 2854393.2 | 0 | 3145607 | 110.2 | 3145607 | 2854393 | -291213.8 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires fencing.
2757 | Water and Sewerage Management | Piping of Stoo Mbili water project and Mutitua Jirani Kio water project | To provide water distribution infrastructure at Stoo Mbili water project and Mutitua Jirani Kio water project | Water piping at Stoo Mbili water project and Mutitua Jirani Kio water project completed | 3110502 | Water Supplies and Sewerage | Njoro | Kihingo | -0.421022 35.972845 2288.3 12.800000190734863 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | N/A | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3793061 | 94.8 | 3793061 | 3793061 | 206939 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: More piping required.
2758 | Water and Sewerage Management | Piping Of Water At Kihingo And Store Mbili Villages | To provide water distribution infrastructure at Water At Kihingo And Store Mbili Villages | Water piping at Water At Kihingo And Store Mbili Villages completed | 3110502 | Water Supplies and Sewerage | Njoro | Kihingo | -0.45226 35.996057 2172.8999999999996 4.900000095367432 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1383270 | 133.55 | 133.55 | Equitable | N/A | 133.55 | 0 | 1383136 | 1035669 | 1383136 | 134 | -1383002.45 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: DAKES CONTRACTOR. Assessor remarks: Requires maintenance.
2759 | Water and Sewerage Management | Purchase And Supply Of Water Pipes | To procure and supply Water Pipes | Water Pipes procured and supplied | 3110502 | Water Supplies and Sewerage | Njoro | Kihingo | -0.42206 35.969528 2213.5 11.399999618530273 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 983325 | 98.3 | 983325 | 1000000 | 16675 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires maintenance.
2760 | Water and Sewerage Management | Subuku Water Project Drilling And Equipping Borehole And Water Tank | To implement subuku water project drilling and equipping borehole and water tank for access to clean water and environmental sustainability | Subuku Water Project Drilling And Equipping Borehole And Water Tank completed | 3110502 | Water Supplies and Sewerage | Njoro | Kihingo | -0.42206 35.969528 2213.5 11.399999618530273 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 3075582 | 3075582 | 3075582 | Equitable | N/A | 3075582 | 0 | 2701604 | 87.8 | 2701604 | 3075582 | 373978 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires maintenance.
2761 | Water and Sewerage Management | Water Works At Mutito Water Project | To implement water works at mutito water project for access to clean water and environmental sustainability | Water Works At Mutito Water Project completed | 3110502 | Water Supplies and Sewerage | Njoro | Kihingo | -0.421022 35.972845 2288.3 12.800000190734863 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1472000 | 98.1 | 1472000 | 1500000 | 28000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: More piping required.
2762 | Water and Sewerage Management | Water Works At Subuku Water Project | To implement water works at subuku water project for access to clean water and environmental sustainability | Water Works At Subuku Water Project completed | 3110502 | Water Supplies and Sewerage | Njoro | Kihingo | -0.421022 35.972845 2288.3 12.800000190734863 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1886844 | 94.3 | 1886844 | 2000000 | 113156 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: More piping required.
2763 | Water and Sewerage Management | Water Works At Stoo Mbili | To implement water works at stoo mbili for access to clean water and environmental sustainability | Water Works At Stoo Mbili completed | 3110502 | Water Supplies and Sewerage | Njoro | Kihingo | -0.456623 35.981843 2308.8999999999996 6.599999904632568 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 3350496.75 | 151400.65 | 151400.65 | Equitable | N/A | 151400.65 | 0 | 151400 | 100 | 151400 | 151401 | 0.65 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: More piping and connection.
2764 | Water and Sewerage Management | Completion of Chebotoi, Ainamoi & Wamgong water projects | To complete Chebotoi, Ainamoi & Wamgong water projects | Chebotoi, Ainamoi & Wamgong water projects completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Kiptagich | -0.561612 35.630047 2531.5 68.9000015258789 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/23 | 4617560 | 4617560 | 4617560 | Equitable | N/A | 4617560 | 0 | 4560447 | 98.8 | 4560447 | 4560447 | 57113 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes, but didn't meet the needs. Assessor remarks: Not functional.
2765 | Water and Sewerage Management | Construction Of Chebotoi Water Project | To construct Chebotoi Water Project | Chebotoi Water Project constructed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Kiptagich | -0.56174, 35.630252 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 4013.45 | 4013.45 | Equitable | N/A | 4013.45 | 0 | 1995987 | 49732.4 | 1995987 | 4013 | -1991973.55 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes but it didn't meet the needs. Assessor remarks: Not functional.
2766 | Water and Sewerage Management | Construction Of Kiptagich Water Project | To construct Kiptagich Water Project | Kiptagich Water Project constructed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Kiptagich | -0.56174, 35.630252 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3999508 | 100 | 3999508 | 4000000 | 492 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes but it didn't meet the needs. Assessor remarks: Not functional.
2767 | Water and Sewerage Management | Construction Of Weir , Water Tank And Piping At Cheptuech - Irongo Water Project | To construct Weir , Water Tank And Piping At Cheptuech - Irongo Water Project | Weir , Water Tank And Piping At Cheptuech - Irongo Water Project constructed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Kiptagich | -0.500035 35.714295 2648.1 6.199999809265137 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3998496 | 100 | 3998496 | 4000000 | 1504 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not operational.
2768 | Water and Sewerage Management | Gikamba Water Projects, Piping And Supply Of Water | To implement gikamba water projects, piping and supply of water for access to clean water and environmental sustainability | Gikamba Water Projects, Piping And Supply Of Water completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Kiptagich | -0.658612, 35.604138 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2022 | 1500000 | 185290.8 | 185290.8 | Equitable | N/A | 185290.8 | 0 | 1314709 | 709.5 | 1314709 | 185291 | -1129418.2 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: Viable but not met the needs of the residents. Contractor: Don't know. Assessor remarks: The project has stalled.
2769 | Water and Sewerage Management | Piping And Water Tank At Ainamoi Water Project | To provide water distribution infrastructure at And Water Tank At Ainamoi Water Project | Water piping at And Water Tank At Ainamoi Water Project completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Kiptagich | -0.500035 35.714295 2648.1 6.199999809265137 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1797444 | 99.9 | 1797444 | 1800000 | 2556 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not operational.
2770 | Water and Sewerage Management | Piping And Water Tank At Kiptagich Water Project | To provide water distribution infrastructure at And Water Tank At Kiptagich Water Project | Water piping at And Water Tank At Kiptagich Water Project completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Kiptagich | -0.500035 35.714295 2648.1 6.199999809265137 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 608700 | 76.1 | 608700 | 800000 | 191300 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not operational.
2771 | Water and Sewerage Management | Piping And Water Tank At Oromoit Water Project | To provide water distribution infrastructure at And Water Tank At Oromoit Water Project | Water piping at And Water Tank At Oromoit Water Project completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Kiptagich | -0.500035 35.714295 2648.1 6.199999809265137 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 1797444 | 449.4 | 1797444 | 400000 | -1397444 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not operational.
2772 | Water and Sewerage Management | Piping Of Irongo Water Project | To provide water distribution infrastructure at Irongo Water Project | Water piping at Irongo Water Project completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Kiptagich | -0.583552 35.62763 2445.7 97.30000305175781 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 910824 | 113.9 | 910824 | 800000 | -110824 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes but it has not met the needs of the residents. Contractor: Don't know. Assessor remarks: The project has not been operationalized..
2773 | Water and Sewerage Management | Piping Of Kiptagich Water Project | To provide water distribution infrastructure at Kiptagich Water Project | Water piping at Kiptagich Water Project completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Kiptagich | -0.583552 35.62763 2445.7 97.30000305175781 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 910824 | 91.1 | 910824 | 1000000 | 89176 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes but it has not met the needs of the residents. Contractor: Don't know. Assessor remarks: The project has not been operationalized..
2774 | Water and Sewerage Management | Simatwet Water Project - Design And Construction Of Water Tank, Perimeter Fence And Piping Of Simatwet Water Project | To implement simatwet water project - design and construction of water tank, perimeter fence and piping of simatwet water project for access to clean water and environmental sustainability | Simatwet Water Project - Design And Construction Of Water Tank, Perimeter Fence And Piping Of Simatwet Water Project completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Kiptagich | -0.500035 35.714295 2648.1 6.199999809265137 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1600000 | 1600000 | 1600000 | Equitable | N/A | 1600000 | 0 | 1600000 | 100 | 1600000 | 1600000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not operational.
2775 | Water and Sewerage Management | Wangong Water Works | To implement wangong water works for access to clean water and environmental sustainability | Wangong Water Works completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Kiptagich | -0.583585, 35.628392 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 1000000 | 985304 | 985304 | Equitable | N/A | 985304 | 0 | 867448 | 88 | 867448 | 985304 | 117856 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Viable. Assessor remarks: Yet to start.
2776 | Water and Sewerage Management | Water Works At Chapsikwet Water Project | To implement water works at chapsikwet water project for access to clean water and environmental sustainability | Water Works At Chapsikwet Water Project completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Kiptagich | -0.561612 35.630047 2531.5 68.9000015258789 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1797444 | 89.9 | 1797444 | 2000000 | 202556 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes, but didn't meet the needs. Assessor remarks: Not functional.
2777 | Water and Sewerage Management | Drilling Of Borehole And Piping At Kio | To provide access to clean water through borehole drilling at And Piping At Kio | Borehole drilled at And Piping At Kio | 3110502 | Water Supplies and Sewerage | Kuresoi North | Kiptororo | -0.294178, 35.491267 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 5500000 | 2668728.55 | 2668728.55 | Equitable | N/A | 2668728.55 | 0 | 2545376 | 95.4 | 2545376 | 2668729 | 123352.55 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Fair.
2778 | Water and Sewerage Management | Drilling Of Borehole, Construction Of Water Tank And Piping Kongoi Centre | To implement drilling of borehole, construction of water tank and piping kongoi centre for access to clean water and environmental sustainability | Drilling Of Borehole, Construction Of Water Tank And Piping Kongoi Centre completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Kiptororo | -0.30261, 35.529464 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 4500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2500000 | 100 | 2500000 | 2500000 | 0 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Completed but solar was stolen. Viable: Partially, its serving the health center and not the public. Assessor remarks: The borehole is functional but two solar s belongs to dakuki contractor.
2779 | Water and Sewerage Management | Drilling of Kio Water Project | To implement drilling of kio water project for access to clean water and environmental sustainability | Drilling of Kio Water Project completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Kiptororo | -0.35799 35.554583 2617.9 8.300000190734863 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | N/A | 3600000 | 3600000 | 3600000 | Equitable | N/A | 3600000 | 0 | 2444006 | 67.9 | 2444006 | 4594 | 1155994 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Ongoing.
2780 | Water and Sewerage Management | Kio Water Works | To implement kio water works for access to clean water and environmental sustainability | Kio Water Works completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Kiptororo | -0.295213, 35.490188 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2700000 | 2700000 | 2700000 | Equitable | N/A | 2700000 | 0 | 0 | 0 | 0 | 2700000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Fair.
2781 | Water and Sewerage Management | Piping And Repairing Of Water Tank At Kuresoi Centre | To provide water distribution infrastructure at And Repairing Of Water Tank At Kuresoi Centre | Water piping at And Repairing Of Water Tank At Kuresoi Centre completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Kiptororo | -0.30261, 35.529464 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 3881121 | 3688508.7 | 3688508.7 | Equitable | N/A | 3688508.7 | 0 | 2950807 | 80 | 2950807 | 3688509 | 737701.7 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Completed but solar was stolen. Viable: Partially, its serving the health center and not the public. Assessor remarks: The borehole is functional but two solar s belongs to dakuki contractor.
2782 | Water and Sewerage Management | Piping Of Kio Water Project | To provide water distribution infrastructure at Kio Water Project | Water piping at Kio Water Project completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Kiptororo | -0.35799 35.554583 2617.9 8.300000190734863 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 2800000 | 2800000 | 2800000 | Equitable | N/A | 2800000 | 0 | 2800000 | 100 | 2800000 | 2800000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Ongoing.
2783 | Water and Sewerage Management | Drilling And Equipping Boreholes At Milimani And Unity Primary School | To implement drilling and equipping boreholes at milimani and unity primary school for access to clean water and environmental sustainability | Drilling And Equipping Boreholes At Milimani And Unity Primary School completed | 3110502 | Water Supplies and Sewerage | Naivasha | Lakeview | -0.720739, 36.43967 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 7542800.15 | 873777.75 | 873777.75 | Equitable | N/A | 873777.75 | 0 | 796146 | 91.1 | 796146 | 873778 | 77631.75 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Assessor remarks: High flouride levels, water not safe for drinking.
2784 | Water and Sewerage Management | Purchase And Supply Of Water Pipes And Fittings To Manera Estate | To procure and supply Water Pipes And Fittings To Manera Estate | Water Pipes And Fittings To Manera Estate procured and supplied | 3110502 | Water Supplies and Sewerage | Naivasha | Lakeview | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 1300000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 1266830 | 97.4 | 1266830 | 1300000 | 33170 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
2785 | Water and Sewerage Management | Purchase and supply of water pipes and fitting | To procure and supply water pipes and fitting | Water pipes and fitting procured and supplied | 3110502 | Water Supplies and Sewerage | Naivasha | Lakeview | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 4000000 | 0 | 4000000 | Equitable | N/A | 4000000 | 0 | 1266830 | 0 | 1266830 | 4000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
2786 | Water and Sewerage Management | Drilling of borehole at Nyonjoro Dispensary | To provide access to clean water through borehole drilling at Nyonjoro Dispensary | Borehole drilled at Nyonjoro Dispensary | 3110502 | Water Supplies and Sewerage | Bahati | Lanet Umoja | -0.247859, 36.151991 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2023/2024 | 10500000 | 10500000 | 10500000 | Equitable | N/A | 10500000 | 0 | 8054012 | 76.7 | 8054012 | 8054012 | 2445988 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Viable but has not met residents needs. Contractor: ENDROSE and WIlLY SAMWA. Assessor remarks: Needs equipping.
2787 | Water and Sewerage Management | Waterworks for Murunyu water project | To implement waterworks for murunyu water project for access to clean water and environmental sustainability | Waterworks for Murunyu water project completed | 3110502 | Water Supplies and Sewerage | Bahati | Lanet Umoja | -0.254124, 36.160413 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/2023 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1786771 | 89.3 | 1786771 | 213229 | 213229 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Partially.
2788 | Water and Sewerage Management | Drilling Of Borehole at Murunyu Dispensary | To provide access to clean water through borehole drilling at Murunyu Dispensary | Borehole drilled at Murunyu Dispensary | 3110502 | Water Supplies and Sewerage | Bahati | Lanet/Umoja | -0.247859, 36.151991 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2023/2024 | 4000000 | 0 | 4000000 | Equitable | N/A | 4000000 | 0 | 1773886 | 100 | 1773886 | 2226114 | -1773886 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Viable but has not met residents needs. Contractor: ENDROSE and WIlLY SAMWA. Assessor remarks: Needs equipping.
2789 | Water and Sewerage Management | Drilling Of Borehole At Ndege Ndimu | To provide access to clean water through borehole drilling at Ndege Ndimu | Borehole drilled at Ndege Ndimu | 3110502 | Water Supplies and Sewerage | Bahati | Lanet/Umoja | -0.301965, 36.172122 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2500000 | 100 | 2500000 | 2500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Not done.
2790 | Water and Sewerage Management | Drilling Of Borehole Murunyu Water Project | To provide access to clean water through borehole drilling at Murunyu Water Project | Borehole drilled at Murunyu Water Project | 3110502 | Water Supplies and Sewerage | Bahati | Lanet/Umoja | -0.247859, 36.151991 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2023/2024 | 894392 | 894392 | 894392 | Equitable | N/A | 894392 | 0 | 844287 | 94.4 | 844287 | 894392 | 50105 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Viable but has not met residents needs. Contractor: ENDROSE and WIlLY SAMWA. Assessor remarks: Needs equipping.
2791 | Water and Sewerage Management | Drilling Of Borehole, Pump And Piping Lamnyondeki | To implement drilling of borehole, pump and piping lamnyondeki for access to clean water and environmental sustainability | Drilling Of Borehole, Pump And Piping Lamnyondeki completed | 3110502 | Water Supplies and Sewerage | Bahati | Lanet/Umoja | -0.265977, 36.16637 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/2020 | 4000000 | 1615034.2 | 1615034.2 | Equitable | N/A | 1615034.2 | 0 | 1579317 | 97.8 | 1579317 | 1615034 | 35717.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes , very viable. Contractor: Njegwa investment limited. Assessor remarks: Functional.
2792 | Water and Sewerage Management | Drilling Of Muwa Borehole | To implement drilling of muwa borehole for access to clean water and environmental sustainability | Drilling Of Muwa Borehole completed | 3110502 | Water Supplies and Sewerage | Bahati | Lanet/Umoja | -0.280414, 36.158421 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 1000000 | 25 | 1000000 | 4000000 | 3000000 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes ,but has land disputes. Assessor remarks: Has land dispute, borehole covered with sand.
2793 | Water and Sewerage Management | Kiamunyeki Water Works | To implement kiamunyeki water works for access to clean water and environmental sustainability | Kiamunyeki Water Works completed | 3110502 | Water Supplies and Sewerage | Bahati | Lanet/Umoja | -0.282795, 36.144707 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional partially.
2794 | Water and Sewerage Management | Murunyu Water Works | To implement murunyu water works for access to clean water and environmental sustainability | Murunyu Water Works completed | 3110502 | Water Supplies and Sewerage | Bahati | Lanet/Umoja | -0.235022, 36.165638 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2020/21 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 1500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
2795 | Water and Sewerage Management | Ndege Ndimu Water Works | To implement ndege ndimu water works for access to clean water and environmental sustainability | Ndege Ndimu Water Works completed | 3110502 | Water Supplies and Sewerage | Bahati | Lanet/Umoja | -0.312207, 36.173024 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 2200000 | 1500001.05 | 1500001.05 | Equitable | N/A | 1500001.05 | 0 | 699999 | 46.7 | 699999 | 1500001 | 800002.05 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
2796 | Water and Sewerage Management | Piping At Murunyu Water Works | To provide water distribution infrastructure at Murunyu Water Works | Water piping at Murunyu Water Works completed | 3110502 | Water Supplies and Sewerage | Bahati | Lanet/Umoja | -0.23528, 36.167166 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/2021 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 500000 | 100 | 500000 | 500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: RIDGEROCK ENTERPRISES. Assessor remarks: Functional.
2797 | Water and Sewerage Management | Piping Of Baraka Water Project | To provide water distribution infrastructure at Baraka Water Project | Water piping at Baraka Water Project completed | 3110502 | Water Supplies and Sewerage | Bahati | Lanet/Umoja | -0.2625, 36.150548 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/2021 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1304295 | 87 | 1304295 | 1500000 | 195705 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Working.
2798 | Water and Sewerage Management | Piping Of Modern Water Project | To provide water distribution infrastructure at Modern Water Project | Water piping at Modern Water Project completed | 3110502 | Water Supplies and Sewerage | Bahati | Lanet/Umoja | -0.2625, 36.150548 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/2021 | 1000000 | 75538 | 75538 | Equitable | N/A | 75538 | 0 | 924462 | 1223.8 | 924462 | 75538 | -848924 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Working.
2799 | Water and Sewerage Management | Drilling of Lare borehole | To implement drilling of lare borehole for access to clean water and environmental sustainability | Drilling of Lare borehole completed | 3110502 | Water Supplies and Sewerage | Njoro | Lare | -0.449043 36.052612 2039.3 8.600000381469727 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/23 | 2800000 | 2800000 | 2800000 | Equitable | N/A | 2800000 | 0 | 2625300 | 93.8 | 2625300 | 2625300 | 174700 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need maintenance.
2800 | Water and Sewerage Management | Construction Of A Storage Water Tank,Installation Of Hdpe Water Pipes, Purchase Of A 10,000L Plastick Water Tank And Construction Of A Water Kiosk At Milimani | To construct A Storage Water Tank,Installation Of Hdpe Water Pipes, Purchase Of A 10,000L Plastick Water Tank And Construction Of A Water Kiosk At Milimani | A Storage Water Tank,Installation Of Hdpe Water Pipes, Purchase Of A 10,000L Plastick Water Tank And Construction Of A Water Kiosk At Milimani constructed | 3110502 | Water Supplies and Sewerage | Njoro | Lare | -0.497373 36.038613 2000.8 8.699999809265137 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 1010009 | 40.4 | 1010009 | 2500000 | 1489991 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need more pipings.
2801 | Water and Sewerage Management | Installation Of HDPE Water Pipes, Purchase Of A 10,000L Plastic Water Tank And Construction Of Water Kiosk At Lare Ward A | To install HDPE Water Pipes, Purchase Of A 10,000L Plastic Water Tank And Construction Of Water Kiosk At Lare Ward A | HDPE Water Pipes, Purchase Of A 10,000L Plastic Water Tank And Construction Of Water Kiosk At Lare Ward A installed | 3110502 | Water Supplies and Sewerage | Njoro | Lare | -0.477282, 36.037303 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2024 | 1400000 | 1400000 | 1400000 | Equitable | N/A | 1400000 | 0 | 1010009 | 72.1 | 1010009 | 1400000 | 389991 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need more piping.
2802 | Water and Sewerage Management | Installation Of HDPE Water Pipes, Purchase Of a 10,000L Plastic Water Tank And Construction Of Water Kiosk At Lare Ward B | To install HDPE Water Pipes, Purchase Of a 10,000L Plastic Water Tank And Construction Of Water Kiosk At Lare Ward B | HDPE Water Pipes, Purchase Of a 10,000L Plastic Water Tank And Construction Of Water Kiosk At Lare Ward B installed | 3110502 | Water Supplies and Sewerage | Njoro | Lare | -0.477282, 36.037303 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2024 | 1300000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 1010009 | 77.7 | 1010009 | 1300000 | 289991 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need more piping.
2803 | Water and Sewerage Management | Installation Of HDPE Water Pipes, Purchase Of A 10,000L Plastic Water Tank And Construction Of Water Kiosk At Mugumo | To install HDPE Water Pipes, Purchase Of A 10,000L Plastic Water Tank And Construction Of Water Kiosk At Mugumo | HDPE Water Pipes, Purchase Of A 10,000L Plastic Water Tank And Construction Of Water Kiosk At Mugumo installed | 3110502 | Water Supplies and Sewerage | Njoro | Lare | -0.477282, 36.037303 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2024 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 1500000 | 0 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need more piping.
2804 | Water and Sewerage Management | Installation Of Pipes At Karogoe Mugumo | To install Pipes At Karogoe Mugumo | Pipes At Karogoe Mugumo installed | 3110502 | Water Supplies and Sewerage | Njoro | Lare | -0.46423, 36.044957 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2020 | 2500000 | 54100.45 | 54100.45 | Equitable | N/A | 54100.45 | 0 | 2445900 | 4521 | 2445900 | 54100 | -2391799.55 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need more piping.
2805 | Water and Sewerage Management | Installation Of Water Pipes From Kariaini Water, Purchase Of 10000L Plastic Water Tank And Construction Of Water Kiosk At Block 3. | To install Water Pipes From Kariaini Water, Purchase Of 10000L Plastic Water Tank And Construction Of Water Kiosk At Block 3 | Water Pipes From Kariaini Water, Purchase Of 10000L Plastic Water Tank And Construction Of Water Kiosk At Block 3 installed | 3110502 | Water Supplies and Sewerage | Njoro | Lare | -0.477282, 36.037303 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2024 | 1500000 | 862.7 | 862.7 | Equitable | N/A | 862.7 | 0 | 1499137 | 173772.7 | 1499137 | 863 | -1498274.3 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need more piping.
2806 | Water and Sewerage Management | Installation Of Water Pipes, Purchase Of 10000L Plastic Water Tank And Construction Of Water Kiosk At Bagaria - Kirima Areas. | To install Water Pipes, Purchase Of 10000L Plastic Water Tank And Construction Of Water Kiosk At Bagaria - Kirima Areas | Water Pipes, Purchase Of 10000L Plastic Water Tank And Construction Of Water Kiosk At Bagaria - Kirima Areas installed | 3110502 | Water Supplies and Sewerage | Njoro | Lare | -0.477282, 36.037303 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2024 | 1629476 | 629 | 629 | Equitable | N/A | 629 | 0 | 1628847 | 258958.2 | 1628847 | 629 | -1628218 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need more piping.
2807 | Water and Sewerage Management | Installation Of Water Pipes, Purchase Of 10000L Plastic Water Tank And Construction Of Water Kiosk At Nganoini/Mugumo Areas. | To install Water Pipes, Purchase Of 10000L Plastic Water Tank And Construction Of Water Kiosk At Nganoini/Mugumo Areas | Water Pipes, Purchase Of 10000L Plastic Water Tank And Construction Of Water Kiosk At Nganoini/Mugumo Areas installed | 3110502 | Water Supplies and Sewerage | Njoro | Lare | -0.477282, 36.037303 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2024 | 1500000 | 9.55 | 9.55 | Equitable | N/A | 9.55 | 0 | 1499990 | 15706701.6 | 1499990 | 10 | -1499980.45 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need more piping.
2808 | Water and Sewerage Management | Installation Of Water Pipes, Purchase Of 10000L Plastic Water Tank And Construction Of Water Kiosk From Nguriga Slaughter House. | To install Water Pipes, Purchase Of 10000L Plastic Water Tank And Construction Of Water Kiosk From Nguriga Slaughter House | Water Pipes, Purchase Of 10000L Plastic Water Tank And Construction Of Water Kiosk From Nguriga Slaughter House installed | 3110502 | Water Supplies and Sewerage | Njoro | Lare | -0.477282, 36.037303 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2024 | 1500000 | 166 | 166 | Equitable | N/A | 166 | 0 | 1499834 | 903514.5 | 1499834 | 166 | -1499668 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need more piping.
2809 | Water and Sewerage Management | Purchase Of 10000L Plastic Water Tank And Construction Of Water Kiosk At Naishi Game. | To procure 10000L Plastic Water Tank And Construction Of Water Kiosk At Naishi Game | 10000L Plastic Water Tank And Construction Of Water Kiosk At Naishi Game procured | 3110502 | Water Supplies and Sewerage | Njoro | Lare | -0.435797, 36.044722 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2021 | 500000 | 63 | 63 | Equitable | N/A | 63 | 0 | 499937 | 793550.8 | 499937 | 63 | -499874 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need more pipings.
2810 | Water and Sewerage Management | Installation Of Water Pipes, Purchase Of 10,000L Plastic Water Tank And Construction Of A Water Kiosk At Bagaria | To install Water Pipes, Purchase Of 10,000L Plastic Water Tank And Construction Of A Water Kiosk At Bagaria | Water Pipes, Purchase Of 10,000L Plastic Water Tank And Construction Of A Water Kiosk At Bagaria installed | 3110502 | Water Supplies and Sewerage | Njoro | Lare | -0.477282, 36.037303 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2024 | 1133898 | 1133898 | 1133898 | Equitable | N/A | 1133898 | 0 | 1010009 | 89.1 | 1010009 | 112223 | 123889 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need more piping.
2811 | Water and Sewerage Management | Extension Piping Network In London And Milimani Apartments | To expand Piping Network In London And Milimani Apartments to increase capacity | Piping Network In London And Milimani Apartments expanded | 3110502 | Water Supplies and Sewerage | Nakuru West | London | -0.274103 36.054114 1880.728105673961 24 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 5358649 | 587820.45 | 587820.45 | Equitable | N/A | 587820.45 | 0 | 4770829 | 811.6 | 4770829 | 587820 | -4183008.55 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
2812 | Water and Sewerage Management | Maai Mahiu And Longonot Water Works-Construction Of Water Tanks, Drilling And Piping | To implement maai mahiu and longonot water works-construction of water tanks, drilling and piping for access to clean water and environmental sustainability | Maai Mahiu And Longonot Water Works-Construction Of Water Tanks, Drilling And Piping completed | 3110502 | Water Supplies and Sewerage | Naivasha | Maai Mahiu | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 14000000 | 14000000 | 14000000 | Equitable | N/A | 14000000 | 0 | 13454643 | 96.1 | 13454643 | 14000000 | 545357 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
2813 | Water and Sewerage Management | Maai Mahiu Ward Water Works - Drilling, Piping, Construction Of Water Tank And Installation Of Water Pump For; Karima Water Project, Githima Water Project, Longonot Water Project, Gichungu Water Project, Satelite Water Project, Vumilia Camp Water Project, Ruiru Water Project And Car Wash Association Water Project | To implement maai mahiu ward water works - drilling, piping, construction of water tank and installation of water pump for; karima water project, githima water project, longonot water project, gichungu water project, satelite water project, vumilia camp water project, ruiru water project and car wash association water project for access to clean water and environmental sustainability | Maai Mahiu Ward Water Works - Drilling, Piping, Construction Of Water Tank And Installation Of Water Pump For; Karima Water Project, Githima Water Project, Longonot Water Project, Gichungu Water Project, Satelite Water Project, Vumilia Camp Water Project, Ruiru Water Project And Car Wash Association Water Project completed | 3110502 | Water Supplies and Sewerage | Naivasha | Maai Mahiu | -1.007345, 36.534153 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 3983769 | 1203065.7 | 1203065.7 | Equitable | N/A | 1203065.7 | 0 | 889299 | 73.9 | 889299 | 1203066 | 313766.7 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: yes. Assessor remarks: Needs to be made operational.
2814 | Water and Sewerage Management | Maai Mahiu Water works | To implement maai mahiu water works for access to clean water and environmental sustainability | Maai Mahiu Water works completed | 3110502 | Water Supplies and Sewerage | Naivasha | Maai Mahiu | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 8000000 | 8000000 | 8000000 | Equitable | N/A | 8000000 | 0 | 2176522 | 27.2 | 2176522 | 8318914 | 5823478 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
2815 | Water and Sewerage Management | Water works in Maai Mahiu ward | To implement water works in maai mahiu ward for access to clean water and environmental sustainability | Water works in Maai Mahiu ward completed | 3110502 | Water Supplies and Sewerage | Naivasha | Maai Mahiu | -0.980225, 36.578677 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/23 | 7429608 | 7429608 | 7429608 | Equitable | N/A | 7429608 | 0 | 0 | 0 | 0 | 7205444 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Trenches affected by erosion.
2816 | Water and Sewerage Management | Water Works-Purchase Of Pipes And Pipe Laying In Maai Mahiu/Longonot | To implement water works-purchase of pipes and pipe laying in maai mahiu/longonot for access to clean water and environmental sustainability | Water Works-Purchase Of Pipes And Pipe Laying In Maai Mahiu/Longonot completed | 3110502 | Water Supplies and Sewerage | Naivasha | Maai Mahiu | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | N/A | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 0 | 0 | 0 | 2500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
2817 | Water and Sewerage Management | Longonot Water Works | To implement longonot water works for access to clean water and environmental sustainability | Longonot Water Works completed | 3110502 | Water Supplies and Sewerage | Naivasha | Maai Mahiu | -0.890168, 36.496111 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 3279350 | 54.7 | 3279350 | 6000000 | 2720650 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete/water at tap.
2818 | Water and Sewerage Management | Maai Mahiu Water Works | To implement maai mahiu water works for access to clean water and environmental sustainability | Maai Mahiu Water Works completed | 3110502 | Water Supplies and Sewerage | Naivasha | Maai Mahiu | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 1432516.9 | 1432516.9 | 1432516.9 | Equitable | N/A | 1432516.9 | 0 | 2176522 | 151.9 | 2176522 | 8318914 | -744005.1 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
2819 | Water and Sewerage Management | Construction Of A Water Reservoir And Pipe Work In Upper Maiella | To construct A Water Reservoir And Pipe Work In Upper Maiella | A Water Reservoir And Pipe Work In Upper Maiella constructed | 3110502 | Water Supplies and Sewerage | Naivasha | Maiella | -0.889533, 36.198517 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2023 | 5000000 | 313361.35 | 313361.35 | Equitable | N/A | 313361.35 | 0 | 313361 | 100 | 313361 | 313361 | 0.35 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: NO. Viable: NO. Assessor remarks: Not Operation...Defunct project.
2820 | Water and Sewerage Management | Drilling of borehole at Kirima | To provide access to clean water through borehole drilling at Kirima | Borehole drilled at Kirima | 3110502 | Water Supplies and Sewerage | Naivasha | Maiella | -0.83119 36.203515 0 156.89999389648438 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Yet to start. Objective met: Not yet. Viable: Not Yet. Assessor remarks: Microscope calibration to be done.No lab technician.
2821 | Water and Sewerage Management | Drilling Of Borehole At Natooli Water Project | To provide access to clean water through borehole drilling at Natooli Water Project | Borehole drilled at Natooli Water Project | 3110502 | Water Supplies and Sewerage | Naivasha | Maiella | -0.824917 36.203913 0 400 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | N/A | 3400000 | 3400000 | 3400000 | Equitable | N/A | 3400000 | 0 | 584820 | 17.2 | 584820 | 2400000 | 2815180 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: Yes. Condition: Good. Objective met: Not Yet. Viable: Not Yet. Assessor remarks: Awaiting for the Supply of items by the contractor.
2822 | Water and Sewerage Management | Fly Over-Tumaini Water Works | To implement fly over-tumaini water works for access to clean water and environmental sustainability | Fly Over-Tumaini Water Works completed | 3110502 | Water Supplies and Sewerage | Naivasha | Maiella | -0.817397, 36.223778 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2021 | 1113636 | 1018607.6 | 1018607.6 | Equitable | N/A | 1018607.6 | 0 | 1018608 | 100 | 1018608 | 1018608 | -0.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Yet to start. Objective met: Not yet. Viable: Not Yet. Contractor: Respor General Enterprises. Assessor remarks: Awarded .Yet To begin.
2823 | Water and Sewerage Management | Kiburuti Water Works | To implement kiburuti water works for access to clean water and environmental sustainability | Kiburuti Water Works completed | 3110502 | Water Supplies and Sewerage | Naivasha | Maiella | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 477444 | 95.5 | 477444 | 500000 | 22556 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2824 | Water and Sewerage Management | Kirima Water Works | To implement kirima water works for access to clean water and environmental sustainability | Kirima Water Works completed | 3110502 | Water Supplies and Sewerage | Naivasha | Maiella | -0.920628 36.204578 2270.4 7.5 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 500000 | 100 | 500000 | 500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Fabrica Construction Co Ltd. Assessor remarks: Yet to be handed over.
2825 | Water and Sewerage Management | Maeilla Ward Water Works - Drilling, Construction And Piping Of ADC Manyatta Jikaze Borehole: Installation Of A Water Tank At Ngondi | To implement maeilla ward water works - drilling, construction and piping of adc manyatta jikaze borehole: installation of a water tank at ngondi for access to clean water and environmental sustainability | Maeilla Ward Water Works - Drilling, Construction And Piping Of ADC Manyatta Jikaze Borehole: Installation Of A Water Tank At Ngondi completed | 3110502 | Water Supplies and Sewerage | Naivasha | Maiella | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 4982312 | 22738 | 22738 | Equitable | N/A | 22738 | 0 | 4959574 | 21811.8 | 4959574 | 22738 | -4936836 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2826 | Water and Sewerage Management | Maeilla Water Works | To implement maeilla water works for access to clean water and environmental sustainability | Maeilla Water Works completed | 3110502 | Water Supplies and Sewerage | Naivasha | Maiella | -0.893724 36.198464 2353.60009765625 26.42799949645996 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 1331984 | 1331984 | 1331984 | Equitable | N/A | 1331984 | 0 | 1305170 | 98 | 1305170 | 1331984 | 26814 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: NO. Viable: NO. Assessor remarks: Project damaged.No physical Fence visible.
2827 | Water and Sewerage Management | Maiella Ward Water Works | To implement maiella ward water works for access to clean water and environmental sustainability | Maiella Ward Water Works completed | 3110502 | Water Supplies and Sewerage | Naivasha | Maiella | -0.893724 36.198464 2353.60009765625 26.42799949645996 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 3195042 | 79702.5 | 79702.5 | Equitable | N/A | 79702.5 | 0 | 3115340 | 3908.7 | 3115340 | 79703 | -3035637.5 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: NO. Viable: NO. Assessor remarks: Project damaged.No physical Fence visible.
2828 | Water and Sewerage Management | Moindabi Water Works | To implement moindabi water works for access to clean water and environmental sustainability | Moindabi Water Works completed | 3110502 | Water Supplies and Sewerage | Naivasha | Maiella | -0.817397, 36.223778 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2021 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Yet to start. Objective met: Not yet. Viable: Not Yet. Contractor: Respor General Enterprises. Assessor remarks: Awarded .Yet To begin.
2829 | Water and Sewerage Management | Ndabibi Water Works | To implement ndabibi water works for access to clean water and environmental sustainability | Ndabibi Water Works completed | 3110502 | Water Supplies and Sewerage | Naivasha | Maiella | -0.817397, 36.223778 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2021 | 2500000 | 270597.15 | 270597.15 | Equitable | N/A | 270597.15 | 0 | 2229403 | 823.9 | 2229403 | 270597 | -1958805.85 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Yet to start. Objective met: Not yet. Viable: Not Yet. Contractor: Respor General Enterprises. Assessor remarks: Awarded .Yet To begin.
2830 | Water and Sewerage Management | Piping And Connection Of Water At Maiella | To provide water distribution infrastructure at And Connection Of Water At Maiella | Water piping at And Connection Of Water At Maiella completed | 3110502 | Water Supplies and Sewerage | Naivasha | Maiella | -0.796872 36.250812 1882.2 6.900000095367432 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 5782480 | 2688249 | 2688249 | Equitable | N/A | 2688249 | 0 | 3094231 | 115.1 | 3094231 | 2510600 | -405982 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Bad. Objective met: Not at all. Viable: Not at all. Contractor: Em Hech investment ltd.. Assessor remarks: Poorly done.
2831 | Water and Sewerage Management | Piping and installation of solar panels at Sero water project and Kipkonyo | To provide water distribution infrastructure at and installation of solar panels at Sero water project and Kipkonyo | Water piping at and installation of solar panels at Sero water project and Kipkonyo completed | 3110502 | Water Supplies and Sewerage | Naivasha | Maiella | -0.796872 36.250812 1882.2 6.900000095367432 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/23 | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 5788040 | 96.5 | 5788040 | 5788040 | 211960 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Bad. Objective met: Not at all. Viable: Not at all. Contractor: Em Hech investment ltd.. Assessor remarks: Poorly done.
2832 | Water and Sewerage Management | Water piping from Sero to Kongoni | To implement water piping from sero to kongoni for access to clean water and environmental sustainability | Water piping from Sero to Kongoni completed | 3110502 | Water Supplies and Sewerage | Naivasha | Maiella | -0.804403, 36.248343 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2023 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 569375 | 94.9 | 569375 | 569375 | 30625 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Nemoca Enterprises Ltd. Assessor remarks: In use.
2833 | Water and Sewerage Management | Borehole drilling in Milimani Water project, springs protection and water network distribution in Gatamaiyu areas | To provide access to clean water through borehole drilling at Milimani Water project, springs protection and water network distribution in Gatamaiyu areas | Borehole drilled at Milimani Water project, springs protection and water network distribution in Gatamaiyu areas | 3110502 | Water Supplies and Sewerage | Gilgil | Malewa West | -0.648649, 36.488825 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2023/24 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 2207666 | 44.2 | 2207666 | 293462 | 2792334 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
2834 | Water and Sewerage Management | Completion And Equipping Of Gwashare Borehole, Kasarani Borehole,Milimani Borehole And Purchase Of Land At St John | To complete and equip Gwashare Borehole, Kasarani Borehole,Milimani Borehole And Purchase Of Land At St John | Gwashare Borehole, Kasarani Borehole,Milimani Borehole And Purchase Of Land At St John completed and equipped | 3110502 | Water Supplies and Sewerage | Gilgil | Malewa West | -0.612613, 36.380458 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2020/21 | 11167851 | 6201313.55 | 6201313.55 | Equitable | N/A | 6201313.55 | 0 | 5699962 | 91.9 | 5699962 | 6201314 | 501351.55 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
2835 | Water and Sewerage Management | Drilling Of Turambete Borehole | To implement drilling of turambete borehole for access to clean water and environmental sustainability | Drilling Of Turambete Borehole completed | 3110502 | Water Supplies and Sewerage | Gilgil | Malewa West | -0.702703 36.471211 0 2000 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 2500000 | 430397.6 | 430397.6 | Equitable | N/A | 430397.6 | 0 | 2069602 | 480.9 | 2069602 | 430398 | -1639204.4 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
2836 | Water and Sewerage Management | Karate Borehole - Installation Of Solar (Solarization) | To implement karate borehole - installation of solar (solarization) for access to clean water and environmental sustainability | Karate Borehole - Installation Of Solar (Solarization) completed | 3110502 | Water Supplies and Sewerage | Gilgil | Malewa West | -0.702703 36.471211 0 2000 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2387739 | 95.5 | 2387739 | 2500000 | 112261 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
2837 | Water and Sewerage Management | Malewa West Water Work - Drilling Of 4 Boreholes, Construction Of Tanks And Installation Of Solar Water Pump And Piping Of Water Of Gatamaiyu, Kwa Njonjo, Nyondia And Karati Centre Boreholes And Kasarani Solar Water Pump | To implement malewa west water work - drilling of 4 boreholes, construction of tanks and installation of solar water pump and piping of water of gatamaiyu, kwa njonjo, nyondia and karati centre boreholes and kasarani solar water pump for access to clean water and environmental sustainability | Malewa West Water Work - Drilling Of 4 Boreholes, Construction Of Tanks And Installation Of Solar Water Pump And Piping Of Water Of Gatamaiyu, Kwa Njonjo, Nyondia And Karati Centre Boreholes And Kasarani Solar Water Pump completed | 3110502 | Water Supplies and Sewerage | Gilgil | Malewa West | -0.702703, 36.471211 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2021/22 | 4229322 | 3770269 | 3770269 | Equitable | N/A | 3770269 | 0 | 3099636 | 82.2 | 3099636 | 459053 | 670633 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Well maintained.
2838 | Water and Sewerage Management | Piping And Purchase Of 2 No. 10,000 L Water Tank At Green Valley Water Project | To provide water distribution infrastructure at And Purchase Of 2 No. 10,000 L Water Tank At Green Valley Water Project | Water piping at And Purchase Of 2 No. 10,000 L Water Tank At Green Valley Water Project completed | 3110502 | Water Supplies and Sewerage | Gilgil | Malewa West | -0.774775 36.417744 0 5099.9990234375 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 700000 | 417 | 417 | Equitable | N/A | 417 | 0 | 699583 | 167765.7 | 699583 | 417 | -699166 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
2839 | Water and Sewerage Management | Piping At Kasarani To Tarambeta And Booster Pump | To provide water distribution infrastructure at Kasarani To Tarambeta And Booster Pump | Water piping at Kasarani To Tarambeta And Booster Pump completed | 3110502 | Water Supplies and Sewerage | Gilgil | Malewa West | -0.702703, 36.291018 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2921/22 | 1500000 | 220415.5 | 220415.5 | Equitable | N/A | 220415.5 | 0 | 1279585 | 580.5 | 1279585 | 220416 | -1059169.5 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: More connectivity needed.
2840 | Water and Sewerage Management | Piping At Nyondia Water Works | To provide water distribution infrastructure at Nyondia Water Works | Water piping at Nyondia Water Works completed | 3110502 | Water Supplies and Sewerage | Gilgil | Malewa West | -0.612613, 36.398477 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2021-22 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
2841 | Water and Sewerage Management | Piping From Kasarani To Tarambeta Landing Beach | To provide water distribution infrastructure at From Kasarani To Tarambeta Landing Beach | Water piping at From Kasarani To Tarambeta Landing Beach completed | 3110502 | Water Supplies and Sewerage | Gilgil | Malewa West | -0.702703, 36.291018 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2921/22 | 1180279 | 1180279 | 1180279 | Equitable | N/A | 1180279 | 0 | 1180279 | 100 | 1180279 | 1180279 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: More connectivity needed.
2842 | Water and Sewerage Management | Tarambete water works (solarisation, installation of pump and 2 elevated tanks (10,000 litres), fencing | To implement tarambete water works (solarisation, installation of pump and 2 elevated tanks (10,000 litres), fencing for access to clean water and environmental sustainability | Tarambete water works (solarisation, installation of pump and 2 elevated tanks (10,000 litres), fencing completed | 3110502 | Water Supplies and Sewerage | Gilgil | Malewa West | -0.684685, 36.471073 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2024/25 | 3700000 | 3700000 | 3700000 | Equitable | N/A | 3700000 | 0 | 3612681 | 97.6 | 3612681 | 3700000 | 87319 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
2843 | Water and Sewerage Management | Mugumoini Bore Hole(Pipe Network) | To implement mugumoini bore hole(pipe network) for access to clean water and environmental sustainability | Mugumoini Bore Hole(Pipe Network) completed | 3110502 | Water Supplies and Sewerage | Gilgil | Malewa West | -0.702703 36.471211 0 2000 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2014/15 | 2014/15 | 2014/15 | 4607332 | 3308420 | 3308420 | Equitable | N/A | 3308420 | 0 | 2990874 | 90.4 | 2990874 | 3308420 | 317546 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
2844 | Water and Sewerage Management | Completion Of Kiplelmui Water Project | To complete Kiplelmui Water Project | Kiplelmui Water Project completed | 3110502 | Water Supplies and Sewerage | Molo | Mariashoni | -0.344047, 35.846218 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 197.55 | 197.55 | Equitable | N/A | 197.55 | 0 | 2999802 | 1518502.7 | 2999802 | 198 | -2999604.45 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Water quality wanting.
2845 | Water and Sewerage Management | Construction Of Tank And Piping At Kaptimom Water Project | To construct Tank And Piping At Kaptimom Water Project | Tank And Piping At Kaptimom Water Project constructed | 3110502 | Water Supplies and Sewerage | Molo | Mariashoni | -0.344245 35.873707 2389 7.5 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2359857 | 94.4 | 2359857 | 2500000 | 140143 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Elephant project.
2846 | Water and Sewerage Management | Construction Of Water Tank Of Oinoptich Centre | To construct Water Tank Of Oinoptich Centre | Water Tank Of Oinoptich Centre constructed | 3110502 | Water Supplies and Sewerage | Molo | Mariashoni | -0.315941 35.844828 2322.209591306301 14 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2497033 | 2497033 | 2497033 | Equitable | N/A | 2497033 | 0 | 2497033 | 100 | 2497033 | 2497033 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
2847 | Water and Sewerage Management | Drilling Of Borehole At Digital Village | To provide access to clean water through borehole drilling at Digital Village | Borehole drilled at Digital Village | 3110502 | Water Supplies and Sewerage | Molo | Mariashoni | -0.358225, 35.815535 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 5000000 | 514520.1 | 514520.1 | Equitable | N/A | 514520.1 | 0 | 4485480 | 871.8 | 4485480 | 514520 | -3970959.9 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Supply of water ok.
2848 | Water and Sewerage Management | Ndoswa Borehole Drilling and Equipping | To implement ndoswa borehole drilling and equipping for access to clean water and environmental sustainability | Ndoswa Borehole Drilling and Equipping completed | 3110502 | Water Supplies and Sewerage | Molo | Mariashoni | -0.366546 35.84684 2635.0971961053706 7.5 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/23 | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 0 | 0 | 0 | 6000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Supply of water.
2849 | Water and Sewerage Management | Piping, Equipping And Solarisation Of Digital Borehole | To implement piping, equipping and solarisation of digital borehole for access to clean water and environmental sustainability | Piping, Equipping And Solarisation Of Digital Borehole completed | 3110502 | Water Supplies and Sewerage | Molo | Mariashoni | -0.358254, 35.815491 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 3706316 | 154.4 | 3706316 | 2400000 | -1306316 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Supply of water to area is done.
2850 | Water and Sewerage Management | Piping Lawina Water Project | To provide water distribution infrastructure at Lawina Water Project | Water piping at Lawina Water Project completed | 3110502 | Water Supplies and Sewerage | Molo | Mariashoni | -0.343994, 35.846228 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 78110 | 78110 | Equitable | N/A | 78110 | 0 | 921890 | 1180.2 | 921890 | 78110 | -843780 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Not operational thus no water supply.
2851 | Water and Sewerage Management | Piping Of Oinoptich Water Project | To provide water distribution infrastructure at Oinoptich Water Project | Water piping at Oinoptich Water Project completed | 3110502 | Water Supplies and Sewerage | Molo | Mariashoni | -0.336516 35.875599 2348 27.5 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499938 | 100 | 1499938 | 1500000 | 62 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Pipes are not working thus no supply of water.
2852 | Water and Sewerage Management | Piping Sachangwan Lawina Water Project | To provide water distribution infrastructure at Sachangwan Lawina Water Project | Water piping at Sachangwan Lawina Water Project completed | 3110502 | Water Supplies and Sewerage | Molo | Mariashoni | -0.343994, 35.846228 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/23 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 921890 | 18.4 | 921890 | 4874477 | 4078110 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Not operational thus no water supply.
2853 | Water and Sewerage Management | Construction Of Nyakiambi Water Tank And Piping | To construct Nyakiambi Water Tank And Piping | Nyakiambi Water Tank And Piping constructed | 3110502 | Water Supplies and Sewerage | Njoro | Mau Narok | -0.600012 36.007202 0 141 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | N/A | 2100000 | 2100000 | 2100000 | Equitable | N/A | 2100000 | 0 | 0 | 0 | 0 | 2100000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: needs upgrading.
2854 | Water and Sewerage Management | Drilling And Equipping Of Borehole, At Majimingi | To implement drilling and equipping of borehole, at majimingi for access to clean water and environmental sustainability | Drilling And Equipping Of Borehole, At Majimingi completed | 3110502 | Water Supplies and Sewerage | Njoro | Mau Narok | -0.601445, 36.011229 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2019/20 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 2000000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: in good use.
2855 | Water and Sewerage Management | Drilling And Equipping Of Borehole, At Nyakiambi | To implement drilling and equipping of borehole, at nyakiambi for access to clean water and environmental sustainability | Drilling And Equipping Of Borehole, At Nyakiambi completed | 3110502 | Water Supplies and Sewerage | Njoro | Mau Narok | -0.601445, 36.011229 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2019/20 | 2498727 | 354073 | 354073 | Equitable | N/A | 354073 | 0 | 2144654 | 605.7 | 2144654 | 354073 | -1790581 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: in good use.
2856 | Water And Sewerage Management | Drilling Of Borehole At Mutukanio B | To provide access to clean water through borehole drilling at Mutukanio B | Borehole drilled at Mutukanio B | 3110502 | Water Supplies and Sewerage | Njoro | Mau Narok | -0.60628, 36.008692 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 801459 | 1894.35 | 1894.35 | Equitable | N/A | 1894.35 | 0 | 799565 | 42207.9 | 799565 | 1894 | -797670.65 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need solar.
2857 | Water and Sewerage Management | Installation Of Pipes At Segutiet Borehole | To install Pipes At Segutiet Borehole | Pipes At Segutiet Borehole installed | 3110502 | Water Supplies and Sewerage | Njoro | Mau Narok | -1.2841 36.8155 0 83800 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 1040.9 | 1040.9 | Equitable | N/A | 1040.9 | 0 | 998959 | 95970.7 | 998959 | 1041 | -997918.1 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: needs repair.
2858 | Water and Sewerage Management | Kianjoya Dam - Construction Of Dam | To implement kianjoya dam - construction of dam for access to clean water and environmental sustainability | Kianjoya Dam - Construction Of Dam completed | 3110502 | Water Supplies and Sewerage | Njoro | Mau Narok | -0.544487, 36.059952 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1100000 | 29621.65 | 29621.65 | Equitable | N/A | 29621.65 | 0 | 1070378 | 3613.5 | 1070378 | 29622 | -1040756.35 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: No. Viable: No. Assessor remarks: Not in use.
2859 | Water and Sewerage Management | Mahiga Water Works | To implement mahiga water works for access to clean water and environmental sustainability | Mahiga Water Works completed | 3110502 | Water Supplies and Sewerage | Njoro | Mau Narok | -0.503987, 36.053999 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 764 | 764 | Equitable | N/A | 764 | 0 | 1499236 | 196235.1 | 1499236 | 764 | -1498472 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Assessor remarks: Yes.
2860 | Water and Sewerage Management | Metta Water Project - Construction/Completion/Operationalization | To implement metta water project - construction/completion/operationalization for access to clean water and environmental sustainability | Metta Water Project - Construction/Completion/Operationalization completed | 3110502 | Water Supplies and Sewerage | Njoro | Mau Narok | -0.580995, 36.032157 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | N/A | 2999999 | 138183 | 138183 | Equitable | N/A | 138183 | 0 | 2861816 | 2071 | 2861816 | 138183 | -2723633 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need extra piping.
2861 | Water and Sewerage Management | Mukungugu Water Works | To implement mukungugu water works for access to clean water and environmental sustainability | Mukungugu Water Works completed | 3110502 | Water Supplies and Sewerage | Njoro | Mau Narok | -0.601831, 36.011598 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1261440 | 1261440 | 1261440 | Equitable | N/A | 1261440 | 0 | 1499236 | 118.9 | 1499236 | 1261440 | -237796 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: viable. Assessor remarks: in good state of repair.
2862 | Water and Sewerage Management | Nyakiambi Borehole Drilling | To implement nyakiambi borehole drilling for access to clean water and environmental sustainability | Nyakiambi Borehole Drilling completed | 3110502 | Water Supplies and Sewerage | Njoro | Mau Narok | -0.597155 35.996343 2588.8999999999996 5.300000190734863 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 670247.9 | 670247.9 | 670247.9 | Equitable | N/A | 670247.9 | 0 | 1329752 | 198.4 | 1329752 | 670248 | -659504.1 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: Not viable. Assessor remarks: Project stalled.
2863 | Water and Sewerage Management | Nyandimu Water Works | To implement nyandimu water works for access to clean water and environmental sustainability | Nyandimu Water Works completed | 3110502 | Water Supplies and Sewerage | Njoro | Mau Narok | -1.2841, 36.8155 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 5260317 | 5260317 | 5260317 | Equitable | N/A | 5260317 | 0 | 5260317 | 100 | 5260317 | 5260317 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: no. Viable: not viable. Assessor remarks: site handed over.
2864 | Water and Sewerage Management | Drilling, Equipping And Solanization Of Mukeo Borehole | To implement drilling, equipping and solanization of mukeo borehole for access to clean water and environmental sustainability | Drilling, Equipping And Solanization Of Mukeo Borehole completed | 3110502 | Water Supplies and Sewerage | Njoro | Mau Narok | -0.629267, 36.015822 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 8158170 | 163.2 | 8158170 | 5000000 | -3158170 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Working.
2865 | Water and Sewerage Management | Mau Narok Water Works (Mahiga Water Project; Mukeu Water Project; Block 9/Obwaka Water Project; Maji Mingi Water Project; Solarisation Of Mutikanio B Borehole) | To implement mau narok water works (mahiga water project; mukeu water project; block 9/obwaka water project; maji mingi water project; solarisation of mutikanio b borehole) for access to clean water and environmental sustainability | Mau Narok Water Works (Mahiga Water Project; Mukeu Water Project; Block 9/Obwaka Water Project; Maji Mingi Water Project; Solarisation Of Mutikanio B Borehole) completed | 3110502 | Water Supplies and Sewerage | Njoro | Mau Narok | -0.50398, 36.05382 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | N/A | 7398052 | 1633478.4 | 1633478.4 | Equitable | N/A | 1633478.4 | 0 | 5764574 | 352.9 | 5764574 | 1633478 | -4131095.6 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
2866 | Water and Sewerage Management | Piping And Water Kiosk(S) For Nyakiambi Water Project | To provide water distribution infrastructure at And Water Kiosk(S) For Nyakiambi Water Project | Water piping at And Water Kiosk(S) For Nyakiambi Water Project completed | 3110502 | Water Supplies and Sewerage | Njoro | Mau Narok | -1.2841 36.8155 0 85955 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 0 | 0 | 0 | 3500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: in good state of repair.
2867 | Water and Sewerage Management | Piping, Installation Of Water Kiosk And 10,000 Litre Water Tank At Mutukanio B | To implement piping, installation of water kiosk and 10,000 litre water tank at mutukanio b for access to clean water and environmental sustainability | Piping, Installation Of Water Kiosk And 10,000 Litre Water Tank At Mutukanio B completed | 3110502 | Water Supplies and Sewerage | Njoro | Mau Narok | -0.597047, 35.996113 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2019/20 | 645577 | 647577 | 647577 | Equitable | N/A | 647577 | 0 | 1395518 | 215.5 | 1395518 | 647577 | -747941 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No viable. Assessor remarks: Stalled project.
2868 | Water and Sewerage Management | Building Of Tank And Piping At Kaptich Water Project | To implement building of tank and piping at kaptich water project for access to clean water and environmental sustainability | Building Of Tank And Piping At Kaptich Water Project completed | 3110502 | Water Supplies and Sewerage | Njoro | Mauche | -0.565457, 36.036751 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2019 | 2848617 | 2848617 | 2848617 | Equitable | N/A | 2848617 | 0 | 3436946 | 120.7 | 3436946 | 2848617 | -588329 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not. Assessor remarks: Needs improvement.
2869 | Water and Sewerage Management | Construction Of Water Tank And Installation Of Pipes At Kamungei Water Project | To construct Water Tank And Installation Of Pipes At Kamungei Water Project | Water Tank And Installation Of Pipes At Kamungei Water Project constructed | 3110502 | Water Supplies and Sewerage | Njoro | Mauche | -0.553985, 36.044817 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2023 | 2495244 | 1296167 | 1296167 | Equitable | N/A | 1296167 | 0 | 1199077 | 92.5 | 1199077 | 896167 | 97090 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
2870 | Water and Sewerage Management | Construction of water tank for Tendwet Village-Kamaasai | To construct water tank for Tendwet Village-Kamaasai | Water tank for Tendwet Village-Kamaasai constructed | 3110502 | Water Supplies and Sewerage | Njoro | Mauche | -0.497753, 35.960733 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2023 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3710631 | 92.8 | 3710631 | 1998470 | 289369 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
2871 | Water and Sewerage Management | Drilling Of A Borehole At Kusumek Water Projects | To implement drilling of a borehole at kusumek water projects for access to clean water and environmental sustainability | Drilling Of A Borehole At Kusumek Water Projects completed | 3110502 | Water Supplies and Sewerage | Njoro | Mauche | -0.517562 35.973678 2471 8.399999618530273 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2431685 | 81.1 | 2431685 | 3000000 | 568315 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Very good.
2872 | Water and Sewerage Management | Drilling Of Borehole, Purchase Of Water Pump And Installation Of Pipes At Toplife Stock Theft Water Project | To implement drilling of borehole, purchase of water pump and installation of pipes at toplife stock theft water project for access to clean water and environmental sustainability | Drilling Of Borehole, Purchase Of Water Pump And Installation Of Pipes At Toplife Stock Theft Water Project completed | 3110502 | Water Supplies and Sewerage | Njoro | Mauche | -0.530482 35.94927 2635.2000000000003 9.600000381469727 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 5000000 | 1810593 | 1810593 | Equitable | N/A | 1810593 | 0 | 1810593 | 100 | 1810593 | 1810593 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
2873 | Water and Sewerage Management | Drilling Of Kiptenden Water Project | To implement drilling of kiptenden water project for access to clean water and environmental sustainability | Drilling Of Kiptenden Water Project completed | 3110502 | Water Supplies and Sewerage | Njoro | Mauche | -0.543692, 36.030627 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2024 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2498918 | 83.3 | 2498918 | 238767 | 501082 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
2874 | Water and Sewerage Management | Installation Of Pipes And Construction Of Water Kiosks At Kosimbei Water Project | To install Pipes And Construction Of Water Kiosks At Kosimbei Water Project | Pipes And Construction Of Water Kiosks At Kosimbei Water Project installed | 3110502 | Water Supplies and Sewerage | Njoro | Mauche | -0.530482 35.94927 2635.2000000000003 9.600000381469727 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 3800000 | 1003.2 | 1003.2 | Equitable | N/A | 1003.2 | 0 | 3798997 | 378687.9 | 3798997 | 1003 | -3797993.8 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
2875 | Water and Sewerage Management | Supply of pipes for Kapsir, Kaptich water projects and Tendwet Village-Kamaasai | To implement supply of pipes for kapsir, kaptich water projects and tendwet village-kamaasai for access to clean water and environmental sustainability | Supply of pipes for Kapsir, Kaptich water projects and Tendwet Village-Kamaasai completed | 3110502 | Water Supplies and Sewerage | Njoro | Mauche | -0.497753, 35.960733 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2023 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1589751 | 79.5 | 1589751 | 274494 | 410249 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
2876 | Tegunot / Siryat Water Project Piping Of Water | Tegunot / Siryat Water Project Piping Of Water | To implement tegunot / siryat water project piping of water for access to clean water and environmental sustainability | Tegunot / Siryat Water Project Piping Of Water completed | 3110502 | Water Supplies and Sewerage | Njoro | Mauche | -0.501963 35.980358 2388.7999999999997 13.699999809265137 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 499937.25 | 499937.25 | 499937.25 | Equitable | N/A | 499937.25 | 0 | 0 | 0 | 0 | 499937 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
2877 | Water and Sewerage Management | Construction Of Water Tank And Piping Work At Kaptich Water Project | To construct Water Tank And Piping Work At Kaptich Water Project | Water Tank And Piping Work At Kaptich Water Project constructed | 3110502 | Water Supplies and Sewerage | Njoro | Mauche | -0.539043, 36.016872 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2023 | 563053.7 | 563053.7 | 563053.7 | Equitable | N/A | 563053.7 | 0 | 3436946 | 610.4 | 3436946 | 563054 | -2873892.3 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
2878 | Water and Sewerage Management | Drilling Of Borehole At Kiratina | To provide access to clean water through borehole drilling at Kiratina | Borehole drilled at Kiratina | 3110502 | Water Supplies and Sewerage | Nakuru East | Menengai | -0.271879 36.103026 1889.5 18.309999465942383 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 685285 | 685285 | 685285 | Equitable | N/A | 685285 | 0 | 2306428 | 336.6 | 2306428 | 685285 | -1621143 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
2879 | Water and Sewerage Management | Drilling Of Borehole At Teachers Hyrax | To provide access to clean water through borehole drilling at Teachers Hyrax | Borehole drilled at Teachers Hyrax | 3110502 | Water Supplies and Sewerage | Nakuru East | Menengai | -0.275792, 36.114935 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 232704 | 232704 | Equitable | N/A | 232704 | 0 | 2767296 | 1189.2 | 2767296 | 232704 | -2534592 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
2880 | Water and Sewerage Management | Piping Of Water For Shiners Borehole To Neylan Tank | To provide water distribution infrastructure at Water For Shiners Borehole To Neylan Tank | Water piping at Water For Shiners Borehole To Neylan Tank completed | 3110502 | Water Supplies and Sewerage | Nakuru East | Menengai | -0.266251 36.100627 1913.5 20 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | N/A | 1300000 | 1294850 | 1294850 | Equitable | N/A | 1294850 | 0 | 0 | 0 | 0 | 1294850 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Nop. Viable: Nop. Assessor remarks: It's good for muhoro road to be upgraded to tarmac.
2881 | Water and Sewerage Management | Borehole Drilling in Mercy Njeri or Maciaro | To provide access to clean water through borehole drilling at Mercy Njeri or Maciaro | Borehole drilled at Mercy Njeri or Maciaro | 3110502 | Water Supplies and Sewerage | Rongai | Menengai West | -0.144462, 36.009498 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/23 | 3550000 | 3550000 | 3550000 | Equitable | N/A | 3550000 | 0 | 1858667 | 52.4 | 1858667 | 1641529 | 1691333 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Borehole did not yield water.
2882 | Water and Sewerage Management | Completion Of Water Works In Olrongai | To complete Water Works In Olrongai | Water Works In Olrongai completed | 3110502 | Water Supplies and Sewerage | Rongai | Menengai West | -0.166762 36.007934 0 600 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 937568 | 62.5 | 937568 | 1500000 | 562432 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs renovation.
2883 | Water and Sewerage Management | Ol Rongai Water Works And Piping - Piping Of Ol Rongai Water Project | To implement ol rongai water works and piping - piping of ol rongai water project for access to clean water and environmental sustainability | Ol Rongai Water Works And Piping - Piping Of Ol Rongai Water Project completed | 3110502 | Water Supplies and Sewerage | Rongai | Menengai West | -0.146435 36.009523 1826 13.850000381469727 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 3999709 | 3999709 | 3999709 | Equitable | N/A | 3999709 | 0 | 3999709 | 100 | 3999709 | 3999709 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
2884 | Water and Sewerage Management | Water Piping in Ol-Rongai Number 4 Milimani area | To implement water piping in ol-rongai number 4 milimani area for access to clean water and environmental sustainability | Water Piping in Ol-Rongai Number 4 Milimani area completed | 3110502 | Water Supplies and Sewerage | Rongai | Menengai West | -0.178417, 35.990588 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/23 | 2600000 | 2600000 | 2600000 | Equitable | N/A | 2600000 | 0 | 0 | 0 | 0 | 2600000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
2885 | Water and Sewerage Management | Construction of Sachangwan water tank | To construct Sachangwan water tank | Sachangwan water tank constructed | 3110502 | Water Supplies and Sewerage | Molo | Molo | -0.240585, 35.715565 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1765520 | 88.3 | 1765520 | 33 | 234480 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Nice one.
2886 | Water and Sewerage Management | Drilling of Borehole at Mukinyai Cattle dip in Sachagwan and Matumaini Shopping Centre | To provide access to clean water through borehole drilling at Mukinyai Cattle dip in Sachagwan and Matumaini Shopping Centre | Borehole drilled at Mukinyai Cattle dip in Sachagwan and Matumaini Shopping Centre | 3110502 | Water Supplies and Sewerage | Molo | Molo | -0.205754, 35.787253 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2023/24 | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 2999296 | 50 | 2999296 | 3000704 | 3000704 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Very viable. Viable: Yes. Contractor: M/S Strafield contractors ltd. Assessor remarks: Good.
2887 | Water and Sewerage Management | Completion Of Chesoen Dam Through Construction Of A Powerhouse, Installation Of A Water Pump And Electricity And Laying Of Water Pipes Within Areas Covering Chesoen, Gitingi Amd Borop | To complete Chesoen Dam Through Construction Of A Powerhouse, Installation Of A Water Pump And Electricity And Laying Of Water Pipes Within Areas Covering Chesoen, Gitingi Amd Borop | Chesoen Dam Through Construction Of A Powerhouse, Installation Of A Water Pump And Electricity And Laying Of Water Pipes Within Areas Covering Chesoen, Gitingi Amd Borop completed | 3110502 | Water Supplies and Sewerage | Molo | Molo Central | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 1100000 | 1100000 | 1100000 | Equitable | N/A | 1100000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
2888 | Water and Sewerage Management | Construction Of A 100,000 Litre Water Tank Near G.S.U Camp In Sachang'Wan | To construct A 100,000 Litre Water Tank Near G.S.U Camp In Sachang'Wan | A 100,000 Litre Water Tank Near G.S.U Camp In Sachang'Wan constructed | 3110502 | Water Supplies and Sewerage | Molo | Molo Central | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 1200000 | 1195366.08 | 1195366.08 | Equitable | N/A | 1195366.08 | 0 | 9893500 | 827.7 | 9893500 | 106500 | -8698133.92 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
2889 | Water and Sewerage Management | Construction Of Green Garden Water Tank | To construct Green Garden Water Tank | Green Garden Water Tank constructed | 3110502 | Water Supplies and Sewerage | Molo | Molo Central | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 3899403 | 194403 | 194403 | Equitable | N/A | 194403 | 0 | 1436265 | 738.8 | 1436265 | 3183456 | -1241862 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
2890 | Water and Sewerage Management | Construction Of Milimani Water Tank | To construct Milimani Water Tank | Milimani Water Tank constructed | 3110502 | Water Supplies and Sewerage | Molo | Molo Central | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 2600000 | 32.8 | 32.8 | Equitable | N/A | 32.8 | 0 | 1436265 | 4378856.7 | 1436265 | 3183456 | -1436232.2 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
2891 | Water and Sewerage Management | Kenyatta Borehole Drilling | To implement kenyatta borehole drilling for access to clean water and environmental sustainability | Kenyatta Borehole Drilling completed | 3110502 | Water Supplies and Sewerage | Molo | Molo Central | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 2796333.5 | 1041227.5 | 1041227.5 | Equitable | N/A | 1041227.5 | 0 | 1496859 | 143.8 | 1496859 | 1496859 | -455631.5 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
2892 | Water and Sewerage Management | Laying Of Water Pipes( 2 And 1.5 Inches) From The Green Garden Borehole To Surrounding Areas In Tayari And Gatiiguru Area Molo | To implement laying of water pipes( 2 and 1.5 inches) from the green garden borehole to surrounding areas in tayari and gatiiguru area molo for access to clean water and environmental sustainability | Laying Of Water Pipes( 2 And 1.5 Inches) From The Green Garden Borehole To Surrounding Areas In Tayari And Gatiiguru Area Molo completed | 3110502 | Water Supplies and Sewerage | Molo | Molo Central | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 1700000 | 1700000 | 1700000 | Equitable | N/A | 1700000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
2893 | Water and Sewerage Management | Laying Of Water Pipes From Migeremuka Borehole To Supply Water In The Migeremuka Areas | To implement laying of water pipes from migeremuka borehole to supply water in the migeremuka areas for access to clean water and environmental sustainability | Laying Of Water Pipes From Migeremuka Borehole To Supply Water In The Migeremuka Areas completed | 3110502 | Water Supplies and Sewerage | Molo | Molo Central | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 1000000 | 968855 | 968855 | Equitable | N/A | 968855 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
2894 | Water and Sewerage Management | Piping Of Matumani/Mugeremukia Water Project | To provide water distribution infrastructure at Matumani/Mugeremukia Water Project | Water piping at Matumani/Mugeremukia Water Project completed | 3110502 | Water Supplies and Sewerage | Molo | Molo Central | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 3000000 | 2045 | 2045 | Equitable | N/A | 2045 | 0 | 485466 | 23739.2 | 485466 | 5000000 | -483421 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
2895 | Water and Sewerage Management | Chelele Water Project - Construction Of 50M3 Tank And Laying Of Pipes | To implement chelele water project - construction of 50m3 tank and laying of pipes for access to clean water and environmental sustainability | Chelele Water Project - Construction Of 50M3 Tank And Laying Of Pipes completed | 3110502 | Water Supplies and Sewerage | Rongai | Mosop | -0.215495 35.822015 1909.6000000000001 23.200000762939453 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 3955200 | 55200 | 55200 | Equitable | N/A | 55200 | 0 | 3900000 | 7065.2 | 3900000 | 55200 | -3844800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Kina investment. Assessor remarks: Good work.
2896 | Water and Sewerage Management | Construction Of Tank, And Laying Of Pipes At Sumeek,Rigogo Water Project | To construct Tank, And Laying Of Pipes At Sumeek,Rigogo Water Project | Tank, And Laying Of Pipes At Sumeek,Rigogo Water Project constructed | 3110502 | Water Supplies and Sewerage | Rongai | Mosop | -0.250735 35.841887 2190.1 9.699999809265137 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 2600000 | 28012.8 | 28012.8 | Equitable | N/A | 28012.8 | 0 | 2571987 | 9181.5 | 2571987 | 28013 | -2543974.2 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Ndowfra ltd. Assessor remarks: Good work.
2897 | Water and Sewerage Management | Construction Of Water Tank And Piping At Matuiku Water Project | To construct Water Tank And Piping At Matuiku Water Project | Water Tank And Piping At Matuiku Water Project constructed | 3110502 | Water Supplies and Sewerage | Rongai | Mosop | -0.24922 35.83006 2174.3999999999996 7 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 1400000 | 1389494 | 1389494 | Equitable | N/A | 1389494 | 0 | 1389494 | 100 | 1389494 | 1389494 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Chapakaz. Assessor remarks: Good work.
2898 | Water and Sewerage Management | Construction Of Water Tank And Piping At Sumeek-Ndusu,Rigogo Water Project | To construct Water Tank And Piping At Sumeek-Ndusu,Rigogo Water Project | Water Tank And Piping At Sumeek-Ndusu,Rigogo Water Project constructed | 3110502 | Water Supplies and Sewerage | Rongai | Mosop | -0.250735 35.841887 2190.1 9.699999809265137 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 1400000 | 1395625 | 1395625 | Equitable | N/A | 1395625 | 0 | 1389494 | 99.6 | 1389494 | 1395625 | 6131 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Ndowfra ltd. Assessor remarks: Good work.
2899 | Water and Sewerage Management | Drilling and equipping of Ogilgei Borehole | To implement drilling and equipping of ogilgei borehole for access to clean water and environmental sustainability | Drilling and equipping of Ogilgei Borehole completed | 3110502 | Water Supplies and Sewerage | Rongai | Mosop | -0.30221, 35.952852 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2024 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 2857319 | 81.6 | 2857319 | 3500000 | 642681 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Viable. Contractor: Not yet awarded. Assessor remarks: Not yet awarded.
2900 | Water and Sewerage Management | Equipping Of Ngecha Borehole | To equip Ngecha Borehole with necessary facilities and equipment | Ngecha Borehole equipped | 3110502 | Water Supplies and Sewerage | Rongai | Mosop | -0.308765, 35.938308 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2022 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2857319 | 95.2 | 2857319 | 838570 | 142681 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Weirodlimited. Assessor remarks: Good workmanship.
2901 | Water and Sewerage Management | Laying Of Pipes Lelechwet, Chepseon Water Project | To implement laying of pipes lelechwet, chepseon water project for access to clean water and environmental sustainability | Laying Of Pipes Lelechwet, Chepseon Water Project completed | 3110502 | Water Supplies and Sewerage | Rongai | Mosop | -0.212327, 35.820707 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2022 | 1155282 | 3261 | 3261 | Equitable | N/A | 3261 | 0 | 1152021 | 35327.2 | 1152021 | 3261 | -1148760 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Jitahidi enterprise. Assessor remarks: Stalled.
2902 | Water and Sewerage Management | Laying Of Water Pipes Lelechwet Kapkures | To implement laying of water pipes lelechwet kapkures for access to clean water and environmental sustainability | Laying Of Water Pipes Lelechwet Kapkures completed | 3110502 | Water Supplies and Sewerage | Rongai | Mosop | -0.216828, 35.824175 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2021 | 1000000 | 3822 | 3822 | Equitable | N/A | 3822 | 0 | 996178 | 26064.3 | 996178 | 3822 | -992356 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Mathioya. Assessor remarks: Stalled project.
2903 | Water and Sewerage Management | Lelechwet Water Tank - Construction Of 200M3 Water Tank And Pipes | To implement lelechwet water tank - construction of 200m3 water tank and pipes for access to clean water and environmental sustainability | Lelechwet Water Tank - Construction Of 200M3 Water Tank And Pipes completed | 3110502 | Water Supplies and Sewerage | Rongai | Mosop | -0.248192, 35.808833 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2024 | 3897641.41 | 1231519.41 | 1231519.41 | Equitable | N/A | 1231519.41 | 0 | 1231519 | 100 | 1231519 | 1231519 | 0.41 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Kefalice. Assessor remarks: Good work.
2904 | Water and Sewerage Management | Mbama Intake Project - Intake Works | To implement mbama intake project - intake works for access to clean water and environmental sustainability | Mbama Intake Project - Intake Works completed | 3110502 | Water Supplies and Sewerage | Rongai | Mosop | -0.21216, 35.816242 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2022 | 3093894 | 1387151 | 1387151 | Equitable | N/A | 1387151 | 0 | 1356326 | 97.8 | 1356326 | 30825 | 30825 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: Yes. Viable: Viable. Contractor: Roy n alvis. Assessor remarks: Stalled.
2905 | Water and Sewerage Management | Mosop Water Works | To implement mosop water works for access to clean water and environmental sustainability | Mosop Water Works completed | 3110502 | Water Supplies and Sewerage | Rongai | Mosop | 0.02967, 36.165311 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2022 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Dopelight investment limited. Assessor remarks: Complete and operational.
2906 | Water and Sewerage Management | Moyaset Piping | To implement moyaset piping for access to clean water and environmental sustainability | Moyaset Piping completed | 3110502 | Water Supplies and Sewerage | Rongai | Mosop | -0.218702, 35.837082 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2022 | 800000 | 1033.3 | 1033.3 | Equitable | N/A | 1033.3 | 0 | 798967 | 77321.9 | 798967 | 1033 | -797933.7 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: M/ s samues. Assessor remarks: Good.
2907 | Water and Sewerage Management | Muthiga Water Works | To implement muthiga water works for access to clean water and environmental sustainability | Muthiga Water Works completed | 3110502 | Water Supplies and Sewerage | Rongai | Mosop | -0.242267, 35.858063 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | Vired | 1600000 | 1600000 | 1600000 | Equitable | N/A | 1600000 | 0 | 0 | 0 | 0 | 1600000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Not. Contractor: Vired. Assessor remarks: Vired.
2908 | Water and Sewerage Management | Ngata Location Water Works(Purchase And Laying Of Pipes) | To implement ngata location water works(purchase and laying of pipes) for access to clean water and environmental sustainability | Ngata Location Water Works(Purchase And Laying Of Pipes) completed | 3110502 | Water Supplies and Sewerage | Rongai | Mosop | -0.23233, 35.837018 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2021 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 995860 | 99.6 | 995860 | 1000000 | 4140 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Kefalice. Assessor remarks: Good work.
2909 | Water and Sewerage Management | Ngecha Water Project | To implement ngecha water project for access to clean water and environmental sustainability | Ngecha Water Project completed | 3110502 | Water Supplies and Sewerage | Rongai | Mosop | -0.318548, 35.973835 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | To be vired | 3000000 | 374966 | 374966 | Equitable | N/A | 374966 | 0 | 371075 | 99 | 371075 | 374966 | 3891 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Viable but money was not enough. Contractor: Not indicated. Assessor remarks: Money vired.
2910 | Water and Sewerage Management | Piping And Water Tank At Boror Nairobi Water Project | To provide water distribution infrastructure at And Water Tank At Boror Nairobi Water Project | Water piping at And Water Tank At Boror Nairobi Water Project completed | 3110502 | Water Supplies and Sewerage | Rongai | Mosop | -0.25239, 35.833605 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2022 | 2000000 | 1502917 | 1502917 | Equitable | N/A | 1502917 | 0 | 1468319 | 97.7 | 1468319 | 1502917 | 34598 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Jitahidi enterprise. Assessor remarks: Good work.
2911 | Water and Sewerage Management | Piping At Kerma Borehole | To provide water distribution infrastructure at Kerma Borehole | Water piping at Kerma Borehole completed | 3110502 | Water Supplies and Sewerage | Rongai | Mosop | -0.31842, 35.973403 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2022 | 900000 | 838570.36 | 838570.36 | Equitable | N/A | 838570.36 | 0 | 2857319 | 340.7 | 2857319 | 838570 | -2018748.64 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Westan. Assessor remarks: Good workmanship.
2912 | Water and Sewerage Management | Pipping at Kerma Water Project | To implement pipping at kerma water project for access to clean water and environmental sustainability | Pipping at Kerma Water Project completed | 3110502 | Water Supplies and Sewerage | Rongai | Mosop | -0.318548, 35.973835 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | To be vired | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 2495931 | 356.6 | 2495931 | 700000 | -1795931 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Viable but money was not enough. Contractor: Not indicated. Assessor remarks: Money vired.
2913 | Water and Sewerage Management | Water Works At Boror Nairobi Mbama | To implement water works at boror nairobi mbama for access to clean water and environmental sustainability | Water Works At Boror Nairobi Mbama completed | 3110502 | Water Supplies and Sewerage | Rongai | Mosop | -0.235082, 35.829002 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2023 | 1000000 | 997966.56 | 997966.56 | Equitable | N/A | 997966.56 | 0 | 997967 | 100 | 997967 | 997967 | -0.44 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Contractor: Johtech. Assessor remarks: Good.
2914 | Water and Sewerage Management | Piping Of Sumeek Water Project | To provide water distribution infrastructure at Sumeek Water Project | Water piping at Sumeek Water Project completed | 3110502 | Water Supplies and Sewerage | Rongai | Mosop | -0.318548, 35.973835 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | To be vired | 2500000 | 4069 | 4069 | Equitable | N/A | 4069 | 0 | 2495931 | 61340.2 | 2495931 | 4069 | -2491862 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Viable but money was not enough. Contractor: Not indicated. Assessor remarks: Money vired.
2915 | Water and Sewerage Management | Murindat Water Works | To implement murindat water works for access to clean water and environmental sustainability | Murindat Water Works completed | 3110502 | Water Supplies and Sewerage | Gilgil | Murindat | -0.411137, 36.311427 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2023/24 | 5000000 | 597406 | 597406 | Equitable | N/A | 597406 | 0 | 584640 | 97.9 | 584640 | 597406 | 12766 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Bad. Objective met: Not done. Viable: Yet to start. Assessor remarks: Not done.
2916 | Water and Sewerage Management | Upper Langa Langa Extention Water Works | To implement upper langa langa extention water works for access to clean water and environmental sustainability | Upper Langa Langa Extention Water Works completed | 3110502 | Water Supplies and Sewerage | Gilgil | Murindat | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 2001549 | 2001549 | 2001549 | Equitable | N/A | 2001549 | 0 | 1686296 | 84.2 | 1686296 | 2001549 | 315253 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
2917 | Water and Sewerage Management | Construction Of Kahuho Water Tank | To construct Kahuho Water Tank | Kahuho Water Tank constructed | 3110502 | Water Supplies and Sewerage | Naivasha | Naivasha East | -0.742074, 36.53051 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2023 | 1500000 | 208043 | 208043 | Equitable | N/A | 208043 | 0 | 208043 | 100 | 208043 | 208043 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: No. Assessor remarks: Pipe supplied but diverted to another project.
2918 | Water and Sewerage Management | Construction Of Maraigushu Water Tank | To construct Maraigushu Water Tank | Maraigushu Water Tank constructed | 3110502 | Water Supplies and Sewerage | Naivasha | Naivasha East | -0.742074, 36.53051 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2023 | 1499866 | 134594.8 | 134594.8 | Equitable | N/A | 134594.8 | 0 | 1364053 | 1013.5 | 1364053 | 134595 | -1229458.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: No. Assessor remarks: Pipe supplied but diverted to another project.
2919 | Water and Sewerage Management | Drilling Of Borehole At Kinungi Water Project | To provide access to clean water through borehole drilling at Kinungi Water Project | Borehole drilled at Kinungi Water Project | 3110502 | Water Supplies and Sewerage | Naivasha | Naivasha East | -0.802878, 36.531191 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2022-23 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 2103335 | 52.6 | 2103335 | 4000000 | 1896665 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: After drilling the water was not obtained.
2920 | Water and Sewerage Management | Piping At Kiruku Water Project | To provide water distribution infrastructure at Kiruku Water Project | Water piping at Kiruku Water Project completed | 3110502 | Water Supplies and Sewerage | Naivasha | Naivasha East | -0.779672, 36.519938 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2023 | 1000000 | 989642.4 | 989642.4 | Equitable | N/A | 989642.4 | 0 | 989642 | 100 | 989642 | 989642 | 0.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Pipe in use.
2921 | Water and Sewerage Management | Piping Of Sisioni Water Projects | To provide water distribution infrastructure at Sisioni Water Projects | Water piping at Sisioni Water Projects completed | 3110502 | Water Supplies and Sewerage | Naivasha | Naivasha East | -0.883097, 36.565648 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2020 | 988356 | 988356 | 988356 | Equitable | N/A | 988356 | 0 | 972349 | 98.4 | 972349 | 988356 | 16007 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: A Very good project with impact.
2922 | Water and Sewerage Management | Purchase And Supply Of 2.5Inch Water Pipes For Kiambogo Water | To procure and supply 2.5Inch Water Pipes For Kiambogo Water | 2.5Inch Water Pipes For Kiambogo Water procured and supplied | 3110502 | Water Supplies and Sewerage | Naivasha | Naivasha East | -0.844545 36.545487 2469.2000000000003 5.400000095367432 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 1193845 | 1193845 | 1193845 | Equitable | N/A | 1193845 | 0 | 1193845 | 100 | 1193845 | 1193845 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: 2023. Assessor remarks: Supplied 1 inch pipes.
2923 | Water and Sewerage Management | Purchase Of 4" and 2.5" Water Pipes For Kiambogo Munyu Area | To procure 4" and 2.5" Water Pipes For Kiambogo Munyu Area | 4" and 2.5" Water Pipes For Kiambogo Munyu Area procured | 3110502 | Water Supplies and Sewerage | Naivasha | Naivasha East | -0.844545 36.545487 2469.2000000000003 5.400000095367432 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 996440 | 99.6 | 996440 | 1000000 | 3560 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: 2023. Assessor remarks: Supplied 1 inch pipes.
2924 | Water and Sewerage Management | Supply Of 2.5 Inch Pipes For Sision Water | To implement supply of 2.5 inch pipes for sision water for access to clean water and environmental sustainability | Supply Of 2.5 Inch Pipes For Sision Water completed | 3110502 | Water Supplies and Sewerage | Naivasha | Naivasha East | -0.867345 36.535489 2460 5.611999988555908 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 479590 | 95.9 | 479590 | 500000 | 20410 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Project combine with another project to construct mateenity.
2925 | Water and Sewerage Management | Supply Of 4 Inch HDPE Pipes For Maraigushu Water Project | To implement supply of 4 inch hdpe pipes for maraigushu water project for access to clean water and environmental sustainability | Supply Of 4 Inch HDPE Pipes For Maraigushu Water Project completed | 3110502 | Water Supplies and Sewerage | Naivasha | Naivasha East | -0.791159, 36.542467 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 334725 | 66.9 | 334725 | 500000 | 165275 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
2926 | Water and Sewerage Management | Drilling Of Borehole For Sisioni Water Project | To provide access to clean water through borehole drilling at For Sisioni Water Project | Borehole drilled at For Sisioni Water Project | 3110502 | Water Supplies and Sewerage | Naivasha | Naivasha East | -0.802878, 36.531191 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2022-23 | 319308 | 319308 | 319308 | Equitable | N/A | 319308 | 0 | 319308 | 100 | 319308 | 319308 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: After drilling the water was not obtained.
2927 | Water and Sewerage Management | Drilling Of A Borehole At Mzee Wanyama | To implement drilling of a borehole at mzee wanyama for access to clean water and environmental sustainability | Drilling Of A Borehole At Mzee Wanyama completed | 3110502 | Water Supplies and Sewerage | Nakuru East | Nakuru East | -0.36993, 36.149658 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/2022 | 4000000 | 583422 | 583422 | Equitable | N/A | 583422 | 0 | 3269095 | 560.3 | 3269095 | 583422 | -2685673 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Cubango east africa limited. Assessor remarks: Project very efficient.
2928 | Water and Sewerage Management | Muguga Water Project-Piping At Barnabas | To implement muguga water project-piping at barnabas for access to clean water and environmental sustainability | Muguga Water Project-Piping At Barnabas completed | 3110502 | Water Supplies and Sewerage | Nakuru East | Nakuru East | -0.310242, 36.145721 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/2020 | 3500000 | 6349.75 | 6349.75 | Equitable | N/A | 6349.75 | 0 | 3493650 | 55020.3 | 3493650 | 6350 | -3487300.25 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Bonca investment⁷. Assessor remarks: Complete.
2929 | Water And Sewerage Management | Cheptoroi Borehole Installation Of Pump And Construction Of Water Tank And Piping | To implement cheptoroi borehole installation of pump and construction of water tank and piping for access to clean water and environmental sustainability | Cheptoroi Borehole Installation Of Pump And Construction Of Water Tank And Piping completed | 3110502 | Water Supplies and Sewerage | Njoro | Nessuit | -0.368773, 35.897801 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 2000000 | 148529 | 148529 | Equitable | N/A | 148529 | 0 | 1851471 | 1246.5 | 1851471 | 148529 | -1702942 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Pump has never been installed.
2930 | Water and Sewerage Management | Construction of 100,000L water tank and piping at Kipkogo borehole | To construct 100,000L water tank and piping at Kipkogo borehole | 100,000L water tank and piping at Kipkogo borehole constructed | 3110502 | Water Supplies and Sewerage | Njoro | Nessuit | -0.41201, 35.936917 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2025/26 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 1554958 | 31.1 | 1554958 | 3094832 | 3445042 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Ongoing. Viable: Ongoing. Assessor remarks: Five water kiosk for Tagitech Water project and 800 meters piping.
2931 | Water and Sewerage Management | Construction Of Weir And Piping Of Water From River Kipkogo And Construction Of Water Tank At Sigaon | To construct Weir And Piping Of Water From River Kipkogo And Construction Of Water Tank At Sigaon | Weir And Piping Of Water From River Kipkogo And Construction Of Water Tank At Sigaon constructed | 3110502 | Water Supplies and Sewerage | Njoro | Nessuit | -0.402693 35.886069 2460.500244140625 6.163000106811523 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2624984 | 278606.8 | 278606.8 | Equitable | N/A | 278606.8 | 0 | 2346377 | 842.2 | 2346377 | 278607 | -2067770.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Project was vandalized and doesn't serve the residents as required. Fence not available.
2932 | Water and Sewerage Management | Construction Of Weir Intake And Fencing Of Kware Springs And Tarakwet Spring | To construct Weir Intake And Fencing Of Kware Springs And Tarakwet Spring | Weir Intake And Fencing Of Kware Springs And Tarakwet Spring constructed | 3110502 | Water Supplies and Sewerage | Njoro | Nessuit | -0.37894, 35.898381 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 500000 | 132.8 | 132.8 | Equitable | N/A | 132.8 | 0 | 499867 | 376405.9 | 499867 | 133 | -499734.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The project was vandalized and human encroachment led to cutting of trees and volume of water has reduced..
2933 | Water and Sewerage Management | Drilling Of Borehole At Tuei | To provide access to clean water through borehole drilling at Tuei | Borehole drilled at Tuei | 3110502 | Water Supplies and Sewerage | Njoro | Nessuit | -0.362196, 35.871931 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2900000 | 2900000 | 2900000 | Equitable | N/A | 2900000 | 0 | 2567544 | 88.5 | 2567544 | 2900000 | 332456 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: No. Viable: No, the volume of water is low. Assessor remarks: Water volume is low.
2934 | Water and Sewerage Management | Installation Of Pipes And Construction Of A Water Tank At Sigotik | To install Pipes And Construction Of A Water Tank At Sigotik | Pipes And Construction Of A Water Tank At Sigotik installed | 3110502 | Water Supplies and Sewerage | Njoro | Nessuit | -0.357531 35.895056 2383.815673828125 5.058000087738037 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 2700000 | 2700000 | 2700000 | Equitable | N/A | 2700000 | 0 | 2499739 | 92.6 | 2499739 | 2700000 | 200261 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: Yes, but it didn't meet the resident's needs. Assessor remarks: Plastic Water tank stolen.
2935 | Water and Sewerage Management | Installation Of Pipes And Construction Of Water Kiosks Cheptoroi | To install Pipes And Construction Of Water Kiosks Cheptoroi | Pipes And Construction Of Water Kiosks Cheptoroi installed | 3110502 | Water Supplies and Sewerage | Njoro | Nessuit | -0.357531 35.895056 2383.815673828125 5.058000087738037 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 2500000 | 261.5 | 261.5 | Equitable | N/A | 261.5 | 0 | 2499739 | 955923.1 | 2499739 | 262 | -2499477.5 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: Yes, but it didn't meet the resident's needs. Assessor remarks: Plastic Water tank stolen.
2936 | Water and Sewerage Management | Takitech Borehole Piping And Construction Of Water Kiosks | To implement takitech borehole piping and construction of water kiosks for access to clean water and environmental sustainability | Takitech Borehole Piping And Construction Of Water Kiosks completed | 3110502 | Water Supplies and Sewerage | Njoro | Nessuit | -0.424694, 35.92853 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2019/20 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1878095 | 93.9 | 1878095 | 2000000 | 121905 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The funds were used to construct 50M³ masonry water tank at Ruto's residence and piping done from the borehole to the water tank.
2937 | Water and Sewerage Management | Design And Construction Of Tagitech Water Kiosk And Piping | To design and construct Tagitech Water Kiosk And Piping | Tagitech Water Kiosk And Piping designed and constructed | 3110502 | Water Supplies and Sewerage | Njoro | Nessuit | -0.356677 35.883444 2389.259997959072 5.46999979019165 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 1100000 | 1100000 | 1100000 | Equitable | N/A | 1100000 | 0 | 1851471 | 168.3 | 1851471 | 1100000 | -751471 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: MARKVEC ENT LIMITED. Assessor remarks: Poor workmanship and there is no latrine constructed.
2938 | Water and Sewerage Management | Construction Of A Water Tank At Sosiot Water Project | To construct A Water Tank At Sosiot Water Project | A Water Tank At Sosiot Water Project constructed | 3110502 | Water Supplies and Sewerage | Njoro | Njoro | -0.38562 35.936234 2263.509521484375 16.58799934387207 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1998917 | 99.9 | 1998917 | 2000000 | 1083 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: In good state.
2939 | Water and Sewerage Management | Construction Of Rumwe Tank | To construct Rumwe Tank | Rumwe Tank constructed | 3110502 | Water Supplies and Sewerage | Njoro | Njoro | -0.33297, 35.946161 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2020 | 2000000 | 78730 | 78730 | Equitable | N/A | 78730 | 0 | 1921270 | 2440.3 | 1921270 | 78730 | -1842540 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes. Contractor: Slink supplier. Assessor remarks: Good work done.
2940 | Water and Sewerage Management | Construction Of Storage Water Tank In Upper Piane | To construct Storage Water Tank In Upper Piane | Storage Water Tank In Upper Piane constructed | 3110502 | Water Supplies and Sewerage | Njoro | Njoro | -0.337804, 35.993675 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2020 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1998917 | 99.9 | 1998917 | 1000000 | 1083 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: In good state.
2941 | Water and Sewerage Management | Drilling And Equipping Of Jordan Borehole | To implement drilling and equipping of jordan borehole for access to clean water and environmental sustainability | Drilling And Equipping Of Jordan Borehole completed | 3110502 | Water Supplies and Sewerage | Njoro | Njoro | -0.288202, 35.87854 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2025 | 1872774 | 1872774 | 1872774 | Equitable | N/A | 1872774 | 0 | 1843027 | 98.4 | 1843027 | 1872774 | 29747 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Yes. Contractor: Not available. Assessor remarks: Only drilling and lining done.
2942 | Water and Sewerage Management | Drilling And Equipping Of Njoro Police Post Borehole | To implement drilling and equipping of njoro police post borehole for access to clean water and environmental sustainability | Drilling And Equipping Of Njoro Police Post Borehole completed | 3110502 | Water Supplies and Sewerage | Njoro | Njoro | -0.331744, 35.945973 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2019 | 2350423.7 | 2350423.7 | 2350423.7 | Equitable | N/A | 2350423.7 | 0 | 2649576 | 112.7 | 2649576 | 1350424 | -299152.3 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ridgerock enterprise. Assessor remarks: Complete awaiting Jewathu piping.
2943 | Water and Sewerage Management | Kamwayo Water Project - Piping Of Kamwayo Water Project | To implement kamwayo water project - piping of kamwayo water project for access to clean water and environmental sustainability | Kamwayo Water Project - Piping Of Kamwayo Water Project completed | 3110502 | Water Supplies and Sewerage | Njoro | Njoro | -0.296612 35.883503 2158.858642578125 11.8100004196167 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 1432.5 | 1432.5 | Equitable | N/A | 1432.5 | 0 | 1998568 | 139516.1 | 1998568 | 1433 | -1997135.5 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: Not available. Assessor remarks: Poor design of work.
2944 | Water and Sewerage Management | Kosoa Water Projects In Kamwaura | To implement kosoa water projects in kamwaura for access to clean water and environmental sustainability | Kosoa Water Projects In Kamwaura completed | 3110502 | Water Supplies and Sewerage | Njoro | Njoro | -0.286075, 35.861546 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2020 | 4677917 | 27418 | 27418 | Equitable | N/A | 27418 | 0 | 4650499 | 16961.5 | 4650499 | 27418 | -4623081 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: In good state.
2945 | Water and Sewerage Management | Njoro Water Works | To implement njoro water works for access to clean water and environmental sustainability | Njoro Water Works completed | 3110502 | Water Supplies and Sewerage | Njoro | Njoro | -0.367753 35.97066 2090.9 9.399999618530273 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2020/21 | 2020/21 | 5000000 | 2500080 | 2500080 | Equitable | N/A | 2500080 | 0 | 2494389 | 99.8 | 2494389 | 2500000 | 5691 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: no. Viable: yes but has issues. Contractor: na. Assessor remarks: work done.
2946 | Water and Sewerage Management | Piping Of Jawatho Water Project | To provide water distribution infrastructure at Jawatho Water Project | Water piping at Jawatho Water Project completed | 3110502 | Water Supplies and Sewerage | Njoro | Njoro | -0.332133, 35.945717 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2018 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 990000 | 99 | 990000 | 1000000 | 10000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: Live World Enterprise. Assessor remarks: Work incomplete.
2947 | Water and Sewerage Management | Purchase And Supply Of Water Pipes At Kamwaura Water Project | To procure and supply Water Pipes At Kamwaura Water Project | Water Pipes At Kamwaura Water Project procured and supplied | 3110502 | Water Supplies and Sewerage | Njoro | Njoro | -0.296612 35.883503 2158.858642578125 11.8100004196167 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: Not available. Assessor remarks: Poor design of work.
2948 | Water and Sewerage Management | Purchase And Supply Of Water Pipes At Sosiot Farm | To procure and supply Water Pipes At Sosiot Farm | Water Pipes At Sosiot Farm procured and supplied | 3110502 | Water Supplies and Sewerage | Njoro | Njoro | -0.336696, 35.995728 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 990098 | 99 | 990098 | 1000000 | 9902 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Contractor: trizza logisticcs. Assessor remarks: work well done.
2949 | Water and Sewerage Management | Supply Of Pipes To Piave Borehole | To implement supply of pipes to piave borehole for access to clean water and environmental sustainability | Supply Of Pipes To Piave Borehole completed | 3110502 | Water Supplies and Sewerage | Njoro | Njoro | -0.336684, 35.995746 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2019 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1200000 | 100 | 1200000 | 1200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Ridgerock enterprises. Assessor remarks: Good work.
2950 | Water and Sewerage Management | Supply Of Water Pipes In Sociot | To implement supply of water pipes in sociot for access to clean water and environmental sustainability | Supply Of Water Pipes In Sociot completed | 3110502 | Water Supplies and Sewerage | Njoro | Njoro | -0.296612 35.883503 2158.858642578125 11.8100004196167 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 990098 | 99 | 990098 | 1000000 | 9902 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: Not available. Assessor remarks: Poor design of work.
2951 | Water and Sewerage Management | Additional Fund For Nyota Water Works | To implement additional fund for nyota water works for access to clean water and environmental sustainability | Additional Fund For Nyota Water Works completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Nyota | -0.355807 35.688607 2814.6 13.600000381469727 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 1141646 | 1141646 | 1141646 | Equitable | N/A | 1141646 | 0 | 1141646 | 100 | 1141646 | 1141646 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: CEDER RED INVESTMENTS LTD.. Assessor remarks: Done to Completion.
2952 | Water and Sewerage Management | Chesirikwa Water Works | To implement chesirikwa water works for access to clean water and environmental sustainability | Chesirikwa Water Works completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Nyota | -0.391423 35.716408 2718.2 14.399999618530273 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 52370.35 | 52370.35 | Equitable | N/A | 52370.35 | 0 | 947630 | 1809.5 | 947630 | 52370 | -895259.65 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: HOLSAN HOLDING LTD. Assessor remarks: Good.
2953 | Water and Sewerage Management | Construction of Tank and Piping of Seguton Water Project | To construct Tank and Piping of Seguton Water Project | Tank and Piping of Seguton Water Project constructed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Nyota | -0.425385, 35.629443 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022-2023 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2952938 | 98.4 | 2952938 | 2952938 | 47062 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Faucets need replacement.
2954 | Water and Sewerage Management | Drilling, Equipping And Piping Of Seguton/Langwenda Water Project | To implement drilling, equipping and piping of seguton/langwenda water project for access to clean water and environmental sustainability | Drilling, Equipping And Piping Of Seguton/Langwenda Water Project completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Nyota | -0.37308 35.677892 2768.6 5.099999904632568 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 4250000 | 1250794.35 | 1250794.35 | Equitable | N/A | 1250794.35 | 0 | 1250794 | 100 | 1250794 | 1250794 | 0.35 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Well done.
2955 | Water and Sewerage Management | Drilling Of Borehole At Lulukwet Water Project | To provide access to clean water through borehole drilling at Lulukwet Water Project | Borehole drilled at Lulukwet Water Project | 3110502 | Water Supplies and Sewerage | Kuresoi North | Nyota | -0.301275, 35.542787 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | - | 3100000 | 850089.34 | 850089.34 | Equitable | N/A | 850089.34 | 0 | 850089 | 100 | 850089 | 850089 | 0.34 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good, well done.
2956 | Water and Sewerage Management | Drilling of borehole at Temoyotta and Tachasis Water projects | To provide access to clean water through borehole drilling at Temoyotta and Tachasis Water projects | Borehole drilled at Temoyotta and Tachasis Water projects | 3110502 | Water Supplies and Sewerage | Kuresoi North | Nyota | -0.391423 35.716408 2718.2 14.399999618530273 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/23 | 6000000 | 5500000 | 5500000 | Equitable | N/A | 5500000 | 0 | 999131 | 18.2 | 999131 | 869 | 4500869 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: HOLSAN HOLDING LTD. Assessor remarks: Good.
2957 | Water and Sewerage Management | Nyota Ward Water Works | To implement nyota ward water works for access to clean water and environmental sustainability | Nyota Ward Water Works completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Nyota | -0.391423 35.716408 2718.2 14.399999618530273 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 4200000 | 653852.6 | 653852.6 | Equitable | N/A | 653852.6 | 0 | 539914 | 82.6 | 539914 | 653853 | 113938.6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: HOLSAN HOLDING LTD. Assessor remarks: Good.
2958 | Water and Sewerage Management | Piping And Construction Of Water Kiosk At Tarakwa Water Project | To provide water distribution infrastructure at And Construction Of Water Kiosk At Tarakwa Water Project | Water piping at And Construction Of Water Kiosk At Tarakwa Water Project completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Nyota | -0.408713, 35.65448 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021-2022 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
2959 | Water and Sewerage Management | Piping and equipping of Mung'etho Water project | To provide water distribution infrastructure at and equipping of Mung'etho Water project | Water piping at and equipping of Mung'etho Water project completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Nyota | -0.361442, 35.708045 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2023-2025 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: HOLDSAN HOLDINGS LTD.. Assessor remarks: Going on steadily.
2960 | Water and Sewerage Management | Piping At Chepkimoiyo Health Centre And Construction Of Two (2) Water Kiosk | To provide water distribution infrastructure at Chepkimoiyo Health Centre And Construction Of Two (2) Water Kiosk | Water piping at Chepkimoiyo Health Centre And Construction Of Two (2) Water Kiosk completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Nyota | -0.352788, 35.592343 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2022-2023 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1912719 | 95.6 | 1912719 | 1912719 | 87281 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Good. Viable: Yes. Assessor remarks: Will be if great help if complete.
2961 | Water and Sewerage Management | Tarakwa Water Works | To implement tarakwa water works for access to clean water and environmental sustainability | Tarakwa Water Works completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Nyota | -0.391423 35.716408 2718.2 14.399999618530273 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 3750000 | 1307422.8 | 1307422.8 | Equitable | N/A | 1307422.8 | 0 | 1307423 | 100 | 1307423 | 1307423 | -0.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: HOLSAN HOLDING LTD. Assessor remarks: Good.
2962 | Water and Sewerage Management | Piping and tank installation at Sher Kasarani | To provide water distribution infrastructure at and tank installation at Sher Kasarani | Water piping at and tank installation at Sher Kasarani completed | 3110502 | Water Supplies and Sewerage | Naivasha | Olkaria | 0.836945, 36.357213 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1988876 | 99.4 | 1988876 | 1988876 | 11124 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: It's operational.
2963 | Water and Sewerage Management | Piping and Tank Installation at Narasha | To provide water distribution infrastructure at and Tank Installation at Narasha | Water piping at and Tank Installation at Narasha completed | 3110502 | Water Supplies and Sewerage | Naivasha | Olkaria | 0.836945, 36.357213 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 522472 | 0 | 522472 | Equitable | N/A | 522472 | 0 | 1899987 | 0 | 1899987 | 522472 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: It's operational.
2964 | Water and Sewerage Management | Piping and tank Installation at Sher Kasarani | To provide water distribution infrastructure at and tank Installation at Sher Kasarani | Water piping at and tank Installation at Sher Kasarani completed | 3110502 | Water Supplies and Sewerage | Naivasha | Olkaria | 0.836945, 36.357213 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1988876 | 99.4 | 1988876 | 1988876 | 11124 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: It's operational.
2965 | Water and Sewerage Management | Piping and tank installation at Top Camp - Kwa Muhia | To provide water distribution infrastructure at and tank installation at Top Camp - Kwa Muhia | Water piping at and tank installation at Top Camp - Kwa Muhia completed | 3110502 | Water Supplies and Sewerage | Naivasha | Olkaria | -0.816175 36.323888 1876.199951171875 11.899999618530273 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | N/A | 500000 | 0 | 500000 | Equitable | N/A | 500000 | 0 | 1899987 | 0 | 1899987 | 500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes as improved security. Assessor remarks: The installed lights are working promptly.
2966 | Water and Sewerage Management | Piping And Tanks Installation At Narasha | To provide water distribution infrastructure at And Tanks Installation At Narasha | Water piping at And Tanks Installation At Narasha completed | 3110502 | Water Supplies and Sewerage | Naivasha | Olkaria | 0.836945, 36.357213 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1899987 | 95 | 1899987 | 2000000 | 100013 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: It's operational.
2967 | Water and Sewerage Management | Sher Academy Water Tank - Installation Of A Water Tank At Sher Academy | To implement sher academy water tank - installation of a water tank at sher academy for access to clean water and environmental sustainability | Sher Academy Water Tank - Installation Of A Water Tank At Sher Academy completed | 3110502 | Water Supplies and Sewerage | Naivasha | Olkaria | 0.837016, 36.366272 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 2988940 | 2988940 | 2988940 | Equitable | N/A | 2988940 | 0 | 2410512 | 80.6 | 2410512 | 2988940 | 578428 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Ni it was not done. Assessor remarks: Yet to start.
2968 | Water and Sewerage Management | Drilling of Nyakinyua Borehole | To implement drilling of nyakinyua borehole for access to clean water and environmental sustainability | Drilling of Nyakinyua Borehole completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Sirikwa | -0.239017, 35.665917 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/23 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3210486 | 91.7 | 3210486 | 0 | 289514 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: The borehole and contract for implementation of the second phase has been awarded and site handed over to the contractor.
2969 | Water and Sewerage Management | Piping And Distribution Of Water In Sirikwa | To provide water distribution infrastructure at Water In Sirikwa | Water piping at Water In Sirikwa completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Sirikwa | -0.283492, 35.673157 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2997851 | 99.9 | 2997851 | 3000000 | 2149 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Tank needs fencing, enhance distribution to all the villages.
2970 | Water and Sewerage Management | Sirikwa Water Works | To implement sirikwa water works for access to clean water and environmental sustainability | Sirikwa Water Works completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Sirikwa | -0.278173, 35.660898 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2019/20 | 2019/20 | 4193771 | 690066.1 | 690066.1 | Equitable | N/A | 690066.1 | 0 | 119848 | 17.4 | 119848 | 119848 | 570218.1 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is in use and members of the public get their water here, more piping needed to reach more households.
2971 | Water and Sewerage Management | Sirikwa Water Project - Design And Construction Of Tank, Piping And Distribution | To implement sirikwa water project - design and construction of tank, piping and distribution for access to clean water and environmental sustainability | Sirikwa Water Project - Design And Construction Of Tank, Piping And Distribution completed | 3110502 | Water Supplies and Sewerage | Kuresoi North | Sirikwa | -0.297153, 35.629421 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 7754897.1 | 592903.1 | 592903.1 | Equitable | N/A | 592903.1 | 0 | 3262001 | 550.2 | 3262001 | 592903 | -2669097.9 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes,but it has not meet the needs of the residents, money needs to be allocated for water source. Assessor remarks: Project is not operational the source has high water turbidity,the tank nèeds to be fenced to secure it,,.
2972 | Water and Sewerage Management | Athinai Sub Location Water Works | To implement athinai sub location water works for access to clean water and environmental sustainability | Athinai Sub Location Water Works completed | 3110502 | Water Supplies and Sewerage | Rongai | Soin | -0.008958, 36.039238 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | FY 2023 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1786812 | 99.3 | 1786812 | 1800000 | 13188 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Piping needs extension.
2973 | Water and Sewerage Management | Construction Of Lomolo Borehole And Piping | To construct Lomolo Borehole And Piping | Lomolo Borehole And Piping constructed | 3110502 | Water Supplies and Sewerage | Rongai | Soin | 0.018446, 36.032083 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 2671062 | 2671062 | 2671062 | Equitable | N/A | 2671062 | 0 | 0 | 0 | 0 | 2671062 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Working q.
2974 | Water and Sewerage Management | Soin Ward Water Projects - Drilling Of Morop Borehole And Kokwomoi Borehole And Water Works At Testai / Banita | To implement soin ward water projects - drilling of morop borehole and kokwomoi borehole and water works at testai / banita for access to clean water and environmental sustainability | Soin Ward Water Projects - Drilling Of Morop Borehole And Kokwomoi Borehole And Water Works At Testai / Banita completed | 3110502 | Water Supplies and Sewerage | Rongai | Soin | -0.062307, 36.062092 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | N/A | 334333.8 | 334333.8 | 334333.8 | Equitable | N/A | 334333.8 | 0 | 2851216 | 852.8 | 2851216 | 334334 | -2516882.2 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The water in use.
2975 | Water and Sewerage Management | Soin Water Works - Kabarnet Farm Water Works, Kipsyenan Water Works, Athinai Sub Location Water Works, Morop Water Works | To implement soin water works - kabarnet farm water works, kipsyenan water works, athinai sub location water works, morop water works for access to clean water and environmental sustainability | Soin Water Works - Kabarnet Farm Water Works, Kipsyenan Water Works, Athinai Sub Location Water Works, Morop Water Works completed | 3110502 | Water Supplies and Sewerage | Rongai | Soin | -0.097772 35.930847 1669.8000000000002 3.5999999046325684 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 8336597 | 2010266.1 | 2010266.1 | Equitable | N/A | 2010266.1 | 0 | 1890733 | 94.1 | 1890733 | 2010266 | 119533.1 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Bikon Engineering. Assessor remarks: Residents are grateful.
2976 | Water and Sewerage Management | Soin Water Works | To implement soin water works for access to clean water and environmental sustainability | Soin Water Works completed | 3110502 | Water Supplies and Sewerage | Rongai | Soin | -0.008958, 36.039238 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | FY 2023 | 4430000 | 10360000 | 10360000 | Equitable | N/A | 10360000 | 0 | 4204030 | 40.6 | 4204030 | 4430000 | 6155970 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Piping needs extension.
2977 | Water and Sewerage Management | Drilling of Borehole at Kimamoi water Project and Kokwomoi Water project | To provide access to clean water through borehole drilling at Kimamoi water Project and Kokwomoi Water project | Borehole drilled at Kimamoi water Project and Kokwomoi Water project | 3110502 | Water Supplies and Sewerage | Rongai | Soin | -0.03435, 36.031945 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | FY 2025 | 7000000 | 7000000 | 7000000 | Equitable | N/A | 7000000 | 0 | 5164832 | 73.8 | 5164832 | 891794 | 1835168 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/S Sagit Global Limited. Assessor remarks: Work done to satisfaction.
2978 | Water and Sewerage Management | Arutani Water Tank And Piping | To implement arutani water tank and piping for access to clean water and environmental sustainability | Arutani Water Tank And Piping completed | 3110502 | Water Supplies and Sewerage | Rongai | Solai | 0.069247, 36.177572 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021 | 2300000 | 2298889.2 | 2298889.2 | Equitable | N/A | 2298889.2 | 0 | 2298889 | 100 | 2298889 | 2298889 | 0.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The tank is in good condition.
2979 | Water and Sewerage Management | Borehole Drilling at Chemarmar and Kiametha-Arutani | To provide access to clean water through borehole drilling at Chemarmar and Kiametha-Arutani | Borehole drilled at Chemarmar and Kiametha-Arutani | 3110502 | Water Supplies and Sewerage | Rongai | Solai | 0.176144 36.176929 1613.39599609375 6.4720001220703125 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | N/A | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 5730199 | 95.5 | 5730199 | 269802 | 269801 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is functional.
2980 | Water and Sewerage Management | Construction Of Chemarmar Water Trough | To construct Chemarmar Water Trough | Chemarmar Water Trough constructed | 3110502 | Water Supplies and Sewerage | Rongai | Solai | 0.069247, 36.177572 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2021 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 449948 | 90 | 449948 | 500000 | 50052 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The tank is in good condition.
2981 | Water and Sewerage Management | Construction Of Water Tanks At Arus And Kiambogo Plus Piping | To construct Water Tanks At Arus And Kiambogo Plus Piping | Water Tanks At Arus And Kiambogo Plus Piping constructed | 3110502 | Water Supplies and Sewerage | Rongai | Solai | 0.078187 36.194685 1926.3 18.100000381469727 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 2800000 | 2800000 | 2800000 | Equitable | N/A | 2800000 | 0 | 2999760 | 107.1 | 2999760 | 2800000 | -199760 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: arden. Assessor remarks: The contract was terminated/vyed.
2982 | Water and Sewerage Management | Construction of water trough and pipes supply at Nyamamithi and Kapkatoro | To construct water trough and pipes supply at Nyamamithi and Kapkatoro | Water trough and pipes supply at Nyamamithi and Kapkatoro constructed | 3110502 | Water Supplies and Sewerage | Rongai | Solai | 0.078187 36.194685 1926.3 18.100000381469727 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | N/A | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 2999760 | 166.7 | 2999760 | 1750169 | -1199760 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: arden. Assessor remarks: The contract was terminated/vyed.
2983 | Water and Sewerage Management | Drilling And Capping Of Arutani Borehole | To implement drilling and capping of arutani borehole for access to clean water and environmental sustainability | Drilling And Capping Of Arutani Borehole completed | 3110502 | Water Supplies and Sewerage | Rongai | Solai | -0.074664, 36.115103 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2022 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2499685 | 100 | 2499685 | 2500000 | 315 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
2984 | Water and Sewerage Management | Drilling And Equipping Of Chemassis Borehole | To implement drilling and equipping of chemassis borehole for access to clean water and environmental sustainability | Drilling And Equipping Of Chemassis Borehole completed | 3110502 | Water Supplies and Sewerage | Rongai | Solai | 0.015959 36.1597 1585.875 5.960999965667725 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 5471976 | 2900290.8 | 2900290.8 | Equitable | N/A | 2900290.8 | 0 | 2899355 | 100 | 2899355 | 2900291 | 935.8 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
2985 | Water and Sewerage Management | Muteithia Water Works | To implement muteithia water works for access to clean water and environmental sustainability | Muteithia Water Works completed | 3110502 | Water Supplies and Sewerage | Rongai | Solai | 0.11082 36.218 1789.6 15.600000381469727 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 1598853 | 319.8 | 1598853 | 500000 | -1098853 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
2986 | Water and Sewerage Management | Ngendaptich Tuiyotich Water Project Piping | To implement ngendaptich tuiyotich water project piping for access to clean water and environmental sustainability | Ngendaptich Tuiyotich Water Project Piping completed | 3110502 | Water Supplies and Sewerage | Rongai | Solai | 0.04618, 36.140841 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2019 | 2000000 | 739370 | 739370 | Equitable | N/A | 739370 | 0 | 1260630 | 170.5 | 1260630 | 739370 | -521260 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
2987 | Water and Sewerage Management | Nyamamithi Water Project - Drilling Of Borehole And Installation Of Pump | To implement nyamamithi water project - drilling of borehole and installation of pump for access to clean water and environmental sustainability | Nyamamithi Water Project - Drilling Of Borehole And Installation Of Pump completed | 3110502 | Water Supplies and Sewerage | Rongai | Solai | 0.113312, 36.222792 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2022 | 2056072 | 2056072 | 2056072 | Equitable | N/A | 2056072 | 0 | 2045996 | 99.5 | 2045996 | 2056072 | 10076 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
2988 | Water and Sewerage Management | Nyamamithi Water Works | To implement nyamamithi water works for access to clean water and environmental sustainability | Nyamamithi Water Works completed | 3110502 | Water Supplies and Sewerage | Rongai | Solai | 0.11082 36.218 1789.6 15.600000381469727 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 1811404 | 1811404 | 1811404 | Equitable | N/A | 1811404 | 0 | 1598853 | 88.3 | 1598853 | 500000 | 212551 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
2989 | Water and Sewerage Management | Piping and Rehabilitation of water tank at Kamosop | To provide water distribution infrastructure at and Rehabilitation of water tank at Kamosop | Water piping at and Rehabilitation of water tank at Kamosop completed | 3110502 | Water Supplies and Sewerage | Rongai | Solai | 0.16787 36.159957 1580.02001953125 18.270000457763672 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 953415 | 95.3 | 953415 | 953416 | 46585 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is complete.
2990 | Water and Sewerage Management | Piping And Storage Improvement At Sigito Murum Water Projects | To provide water distribution infrastructure at And Storage Improvement At Sigito Murum Water Projects | Water piping at And Storage Improvement At Sigito Murum Water Projects completed | 3110502 | Water Supplies and Sewerage | Rongai | Solai | 0.11082 36.218 1789.6 15.600000381469727 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1997984 | 199.8 | 1997984 | 1000000 | -997984 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
2991 | Water and Sewerage Management | Purchase And Installation Of Water Pipes Of Ewani Water Project | To procure and install Water Pipes Of Ewani Water Project | Water Pipes Of Ewani Water Project procured and installed | 3110502 | Water Supplies and Sewerage | Rongai | Solai | -0.060176 36.104307 1695.93603515625 15.730999946594238 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3499801 | 100 | 3499801 | 3500000 | 199 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Good. Objective met: No. Viable: No. Assessor remarks: Stalled.
2992 | Water and Sewerage Management | Purchase And Supply Of Pipes For Solai Water Works | To procure and supply Pipes For Solai Water Works | Pipes For Solai Water Works procured and supplied | 3110502 | Water Supplies and Sewerage | Rongai | Solai | -0.060176 36.104307 1695.93603515625 15.730999946594238 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 654880 | 654880 | 654880 | Equitable | N/A | 654880 | 0 | 1900596 | 290.2 | 1900596 | 654880 | -1245716 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Good. Objective met: No. Viable: No. Assessor remarks: Stalled.
2993 | Water and Sewerage Management | Rehabilitation Of Limuru Water Tank And Piping | To rehabilitate Limuru Water Tank And Piping to restore functionality | Limuru Water Tank And Piping rehabilitated | 3110502 | Water Supplies and Sewerage | Rongai | Solai | 0.069247, 36.177572 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021 | 1200000 | 1197810.2 | 1197810.2 | Equitable | N/A | 1197810.2 | 0 | 1197810 | 100 | 1197810 | 1197810 | 0.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The tank is in good condition.
2994 | Water and Sewerage Management | Sigito Water Project - Piping | To implement sigito water project - piping for access to clean water and environmental sustainability | Sigito Water Project - Piping completed | 3110502 | Water Supplies and Sewerage | Rongai | Solai | 0.04618, 36.140841 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2019 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 998215 | 99.8 | 998215 | 1000000 | 1785 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
2995 | Water and Sewerage Management | Supply Of Water Pipes To Sigito/Murram Water Project | To implement supply of water pipes to sigito/murram water project for access to clean water and environmental sustainability | Supply Of Water Pipes To Sigito/Murram Water Project completed | 3110502 | Water Supplies and Sewerage | Rongai | Solai | 0.023174 36.146624 1550.736083984375 9.659000396728516 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 500000 | 2700 | 2700 | Equitable | N/A | 2700 | 0 | 497300 | 18418.5 | 497300 | 2700 | -494600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
2996 | Water and Sewerage Management | Supply Of Water Pipes To Solai Ward Water Works | To implement supply of water pipes to solai ward water works for access to clean water and environmental sustainability | Supply Of Water Pipes To Solai Ward Water Works completed | 3110502 | Water Supplies and Sewerage | Rongai | Solai | 0.023174 36.146624 1550.736083984375 9.659000396728516 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1900596 | 95 | 1900596 | 2000000 | 99404 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
2997 | Water and Sewerage Management | Water Tank And Piping At Tisobei Water Project | To implement water tank and piping at tisobei water project for access to clean water and environmental sustainability | Water Tank And Piping At Tisobei Water Project completed | 3110502 | Water Supplies and Sewerage | Rongai | Solai | -0.083917, 36.128243 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2020 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 694169 | 69.4 | 694169 | 2298889 | 305831 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
2998 | Water and Sewerage Management | Completion Of Lower Solai Water Project | To complete Lower Solai Water Project | Lower Solai Water Project completed | 3110502 | Water Supplies and Sewerage | Rongai | Solai | 0.18324 36.184717 1648.8 7.199999809265137 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 4000000 | 508715 | 508715 | Equitable | N/A | 508715 | 0 | 3491285 | 686.3 | 3491285 | 508715 | -2982570 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
2999 | Water and Sewerage Management | Construction Of 2 Water Tanks At The Shrine | To construct 2 Water Tanks At The Shrine | 2 Water Tanks At The Shrine constructed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | -0.024925 36.251015 2248.60009765625 4 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 1253078 | 1253078 | 1253078 | Equitable | N/A | 1253078 | 0 | 1253078 | 100 | 1253078 | 1253078 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes, community enjoying access to clean water.. Viable: Yes. Contractor: Details not provided. Assessor remarks: Water tanks constructed and piping done.
3000 | Water and Sewerage Management | Construction Of Gituamba Kianoe (Nguba Farm) Water Tank | To construct Gituamba Kianoe (Nguba Farm) Water Tank | Gituamba Kianoe (Nguba Farm) Water Tank constructed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | -0.004125 36.219987 1997.199951171875 8.61400032043457 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1198895 | 99.9 | 1198895 | 1200000 | 1105 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes.. Viable: Yes.. Contractor: Information not available. Assessor remarks: Water tank in good condition.
3001 | Water and Sewerage Management | Construction Of Shrine Water Tank | To construct Shrine Water Tank | Shrine Water Tank constructed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | -0.06491 36.13243 0 1622 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1253078 | 69.6 | 1253078 | 1800000 | 546922 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Requires renovation.
3002 | Water and Sewerage Management | Construction Of Tank And Piping Of Araki Water Project | To construct Tank And Piping Of Araki Water Project | Tank And Piping Of Araki Water Project constructed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | -0.025943, 36.229345 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2021/2022 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2483954 | 99.4 | 2483954 | 2500000 | 16046 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: Yes.
3003 | Water and Sewerage Management | Drilling Of Borehole, Installation Of Pump And Solar Panels And Piping Of Subukia Valley Water Project | To implement drilling of borehole, installation of pump and solar panels and piping of subukia valley water project for access to clean water and environmental sustainability | Drilling Of Borehole, Installation Of Pump And Solar Panels And Piping Of Subukia Valley Water Project completed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | -0.040933 36.220476 2150.7001953125 100 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 1658854 | 1658854 | 1658854 | Equitable | N/A | 1658854 | 0 | 1658854 | 100 | 1658854 | 1658854 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: The project is operational, community accessing water supply.
3004 | Water and Sewerage Management | Drilling Of Tetu Kirima Kibugi Borehole | To implement drilling of tetu kirima kibugi borehole for access to clean water and environmental sustainability | Drilling Of Tetu Kirima Kibugi Borehole completed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | -0.04678 36.170557 2107.6 2.5 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 3661174 | 183.1 | 3661174 | 2000000 | -1661174 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: GREATRIFT GENERAL MERCHANT. Assessor remarks: Completed and functional.
3005 | Water and Sewerage Management | Gatundu Water Piping | To implement gatundu water piping for access to clean water and environmental sustainability | Gatundu Water Piping completed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | -0.02504, 36.175968 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2023/2024 | 200000 | 2905.4 | 2905.4 | Equitable | N/A | 2905.4 | 0 | 197095 | 6783.7 | 197095 | 2905 | -194189.6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: Completed and is in good working condition.
3006 | Water and Sewerage Management | Installation Of Water Pipes At ACK Munanda Water | To install Water Pipes At ACK Munanda Water | Water Pipes At ACK Munanda Water installed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | -0.042368, 36.190708 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2918/2019 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 494803 | 99 | 494803 | 500000 | 5197 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: Water Supply to the local community provided and functional.
3007 | Water and Sewerage Management | Piping and fencing of Morro Water Project | To provide water distribution infrastructure at and fencing of Morro Water Project | Water piping at and fencing of Morro Water Project completed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | 0.007568 36.223208 2011.8999999999999 7.300000190734863 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/23 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2491135 | 99.6 | 2491135 | 8865 | 8865 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: Community have access to water from the boreho.
3008 | Water and Sewerage Management | Piping of ACK Munanda Water Project | To provide water distribution infrastructure at ACK Munanda Water Project | Water piping at ACK Munanda Water Project completed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | -0.042373 36.190825 2331.5 4.800000190734863 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/23 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2994215 | 99.8 | 2994215 | 5785 | 5785 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: M/s kemeja enterprises limited. Assessor remarks: Good condition.
3009 | Water and Sewerage Management | Piping of Araki Water Project | To provide water distribution infrastructure at Araki Water Project | Water piping at Araki Water Project completed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | -0.042373 36.190825 2331.5 4.800000190734863 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/23 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1465335 | 97.7 | 1465335 | 1465335 | 34665 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: M/s kemeja enterprises limited. Assessor remarks: Good condition.
3010 | Water and Sewerage Management | Piping of Subukia Valley Borehole | To provide water distribution infrastructure at Subukia Valley Borehole | Water piping at Subukia Valley Borehole completed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | -0.04678 36.170557 2107.6 2.5 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/23 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2863256 | 95.4 | 2863256 | 2863256 | 136744 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: GREATRIFT GENERAL MERCHANT. Assessor remarks: Completed and functional.
3011 | Water and Sewerage Management | Piping, Purchase And Installation Of Solar Panels Subukia Valley Borehole | To implement piping, purchase and installation of solar panels subukia valley borehole for access to clean water and environmental sustainability | Piping, Purchase And Installation Of Solar Panels Subukia Valley Borehole completed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | -0.040933 36.220476 2150.7001953125 100 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2200000 | 1556509 | 1556509 | Equitable | N/A | 1556509 | 0 | 643491 | 41.3 | 643491 | 1556509 | 913018 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: The project is operational, community accessing water supply.
3012 | Water and Sewerage Management | Purchase And Installation Of Water Pump, Solar Panels And Construction Of Water Tank For Arash B Kirima Borehole | To procure and install Water Pump, Solar Panels And Construction Of Water Tank For Arash B Kirima Borehole | Water Pump, Solar Panels And Construction Of Water Tank For Arash B Kirima Borehole procured and installed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | -0.031385 36.202473 2223.800048828125 12.100000381469727 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 2510867 | 2510867 | 2510867 | Equitable | N/A | 2510867 | 0 | 2734410 | 108.9 | 2734410 | 2510867 | -223543 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: Borehole already drilled and capped. The water tank and equipping yet to be done..
3013 | Water and Sewerage Management | Purchase And Installation Of Water Pump, Solar Panels And Piping For Arash A Mutito Mumui Water Projects | To procure and install Water Pump, Solar Panels And Piping For Arash A Mutito Mumui Water Projects | Water Pump, Solar Panels And Piping For Arash A Mutito Mumui Water Projects procured and installed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | -0.031385 36.202473 2223.800048828125 12.100000381469727 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2966642 | 98.9 | 2966642 | 3000000 | 33358 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: Borehole already drilled and capped. The water tank and equipping yet to be done..
3014 | Water and Sewerage Management | Quarry Water Project Subukia Town | To implement quarry water project subukia town for access to clean water and environmental sustainability | Quarry Water Project Subukia Town completed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | -0.006327, 36.23532 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2022 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 2500000 | 62.5 | 2500000 | 4000000 | 1500000 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: Not known. Assessor remarks: Further measures to be taken due to tank not having water.
3015 | Water and Sewerage Management | Subukia Valley Borehole Supply Of Pipes | To implement subukia valley borehole supply of pipes for access to clean water and environmental sustainability | Subukia Valley Borehole Supply Of Pipes completed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | -0.04678 36.170557 2107.6 2.5 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 500000 | 100 | 500000 | 500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: GREATRIFT GENERAL MERCHANT. Assessor remarks: Completed and functional.
3016 | Water and Sewerage Management | Supply Of Pipes 1.5 At Edgewood Water Project | To implement supply of pipes 1.5 at edgewood water project for access to clean water and environmental sustainability | Supply Of Pipes 1.5 At Edgewood Water Project completed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | -0.017397 36.198328 2205.8999999999996 7 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 288467 | 57.7 | 288467 | 500000 | 211533 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: Water provided , community have access to safe and clean water.
3017 | Water and Sewerage Management | Supply Of Pipes 1.5 At Gituamba Kirima | To implement supply of pipes 1.5 at gituamba kirima for access to clean water and environmental sustainability | Supply Of Pipes 1.5 At Gituamba Kirima completed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | -0.017397 36.198328 2205.8999999999996 7 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 200000 | 200000 | 200000 | Equitable | N/A | 200000 | 0 | 200000 | 100 | 200000 | 200000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: Water provided , community have access to safe and clean water.
3018 | Water and Sewerage Management | Supply Of Pipes And Fencing At Miloreni Kiguu Maria Project | To implement supply of pipes and fencing at miloreni kiguu maria project for access to clean water and environmental sustainability | Supply Of Pipes And Fencing At Miloreni Kiguu Maria Project completed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | -0.017397 36.198328 2205.8999999999996 7 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: Water provided , community have access to safe and clean water.
3019 | Water and Sewerage Management | Supply Of Pipes At Araki Water Project | To implement supply of pipes at araki water project for access to clean water and environmental sustainability | Supply Of Pipes At Araki Water Project completed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | -0.017397 36.198328 2205.8999999999996 7 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 1000000 | 200 | 1000000 | 500000 | -500000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: Water provided , community have access to safe and clean water.
3020 | Water and Sewerage Management | Supply Of Pipes At Gatongu Water Project And Fencing Intake Area | To implement supply of pipes at gatongu water project and fencing intake area for access to clean water and environmental sustainability | Supply Of Pipes At Gatongu Water Project And Fencing Intake Area completed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | -0.017397 36.198328 2205.8999999999996 7 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: Water provided , community have access to safe and clean water.
3021 | Water and Sewerage Management | Supply Of Pipes At Muagagi Water Project | To implement supply of pipes at muagagi water project for access to clean water and environmental sustainability | Supply Of Pipes At Muagagi Water Project completed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | -0.017397 36.198328 2205.8999999999996 7 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: Water provided , community have access to safe and clean water.
3022 | Water and Sewerage Management | Kware Piping Subukia Water Projects | To implement kware piping subukia water projects for access to clean water and environmental sustainability | Kware Piping Subukia Water Projects completed | 3110502 | Water Supplies and Sewerage | Subukia | Subukia | -0.042373 36.190825 2331.5 4.800000190734863 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 2399639 | 100 | 2399639 | 2400000 | 361 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: M/s kemeja enterprises limited. Assessor remarks: Good condition.
3023 | Water and Sewerage Management | Chemaner water projects | To implement chemaner water projects for access to clean water and environmental sustainability | Chemaner water projects completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Tinet | -0.382711 35.659263 0 2900 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | N/A | 2917432 | 0 | 2917432 | Equitable | N/A | 2917432 | 0 | 5943082 | 0 | 5943082 | 2917432 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Bad condition.
3024 | Water and Sewerage Management | Construction Of Chagoror Water Project | To construct Chagoror Water Project | Chagoror Water Project constructed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Tinet | -0.445126 35.609035 0 2200 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999183 | 99.9 | 999183 | 1000000 | 817 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: Yes but not meet the need. Assessor remarks: Converted to staff quarters.
3025 | Water and Sewerage Management | Kimugul Water Projects | To implement kimugul water projects for access to clean water and environmental sustainability | Kimugul Water Projects completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Tinet | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | N/A | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 2953304 | 73.8 | 2953304 | 258342 | 1046696 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
3026 | Water and Sewerage Management | Taita water projects | To implement taita water projects for access to clean water and environmental sustainability | Taita water projects completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Tinet | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | N/A | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 5943082 | 99.1 | 5943082 | 56918 | 56918 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
3027 | Water and Sewerage Management | Completion Of Piping At Muchorwe Center | To complete Piping At Muchorwe Center | Piping At Muchorwe Center completed | 3110502 | Water Supplies and Sewerage | Molo | Turi | -0.329538 35.694883 2755.300048828125 8.5 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 500000 | 100 | 500000 | 50067 | 0 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Very Good. Objective met: No. Viable: Yes. Assessor remarks: The project is on an individual's land. The owner of the land does not give the community water. The is no access to the project. The gate is locked.
3028 | Water and Sewerage Management | Construction Of A Water Tank At Mitoni Water Project | To construct A Water Tank At Mitoni Water Project | A Water Tank At Mitoni Water Project constructed | 3110502 | Water Supplies and Sewerage | Molo | Turi | -0.279945 35.774557 2458.800048828125 7 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999941 | 100 | 999941 | 1000000 | 59 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: Yes. Assessor remarks: The department to follow up to process the title. The water tank is not in use since the time it was constructed. No water connection. The residents are seeing it as a white elephant project.
3029 | Water and Sewerage Management | Drilling and equipping of Kiambiria Water project and piping | To implement drilling and equipping of kiambiria water project and piping for access to clean water and environmental sustainability | Drilling and equipping of Kiambiria Water project and piping completed | 3110502 | Water Supplies and Sewerage | Molo | Turi | -0.309015, 35.691207 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/23 | 4000000 | 3100000 | 3100000 | Equitable | N/A | 3100000 | 0 | 2768193 | 89.3 | 2768193 | 617162 | 331807 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is complete awaiting commissioning.
3030 | Water and Sewerage Management | Drilling Of A Borehole At Ndenderu A | To implement drilling of a borehole at ndenderu a for access to clean water and environmental sustainability | Drilling Of A Borehole At Ndenderu A completed | 3110502 | Water Supplies and Sewerage | Molo | Turi | -0.270808 35.756023 2454.900146484375 8.100000381469727 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 2300000 | 2300000 | 2300000 | Equitable | N/A | 2300000 | 0 | 1999956 | 87 | 1999956 | 2300000 | 300044 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Fully piping is required.
3031 | Water and Sewerage Management | Drilling of Mkorombosi water project | To implement drilling of mkorombosi water project for access to clean water and environmental sustainability | Drilling of Mkorombosi water project completed | 3110502 | Water Supplies and Sewerage | Molo | Turi | -0.330723, 35.75336 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/23 | 2500000 | 2500000 | 3256143 | Equitable | N/A | 3256143 | 0 | 2638981 | 105.6 | 2638981 | 617162 | -138981 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Excellent work.
3032 | Water and Sewerage Management | Drilling of Turi farmers water project | To implement drilling of turi farmers water project for access to clean water and environmental sustainability | Drilling of Turi farmers water project completed | 3110502 | Water Supplies and Sewerage | Molo | Turi | -0.296542, 35.743885 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/23 | 2500000 | 2500000 | 3156143 | Equitable | N/A | 3156143 | 0 | 3134158 | 125.4 | 3134158 | 3134158 | -634158 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes once it's completed. Viable: Yes. Assessor remarks: The project is ongoing.
3033 | Water and Sewerage Management | Kiambiriria Water Works | To implement kiambiriria water works for access to clean water and environmental sustainability | Kiambiriria Water Works completed | 3110502 | Water Supplies and Sewerage | Molo | Turi | -0.309072, 35.691193 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 900000 | 900000 | 900000 | Equitable | N/A | 900000 | 0 | 3708209 | 412 | 3708209 | 291791 | -2808209 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is complete awaiting commissioning.
3034 | Water and Sewerage Management | Michatha Water Project Piping Works | To implement michatha water project piping works for access to clean water and environmental sustainability | Michatha Water Project Piping Works completed | 3110502 | Water Supplies and Sewerage | Molo | Turi | -0.284958 35.743667 2557.7000000000003 9.600000381469727 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 500000 | 77 | 77 | Equitable | N/A | 77 | 0 | 499923 | 649250.6 | 499923 | 77 | -499846 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yea. Viable: Yes. Assessor remarks: In good condition.
3035 | Water and Sewerage Management | Milima Mitatu Piping Works | To implement milima mitatu piping works for access to clean water and environmental sustainability | Milima Mitatu Piping Works completed | 3110502 | Water Supplies and Sewerage | Molo | Turi | -1.281229 36.821402 0 291468.7964650597 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 400000 | 1282.1 | 1282.1 | Equitable | N/A | 1282.1 | 0 | 398718 | 31098.8 | 398718 | 1282 | -397435.9 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: YES. Viable: YES. Assessor remarks: the project is in use.
3036 | Water and Sewerage Management | Mona-Michatha Water Project - Piping Of Mona-Michatha Water Project | To implement mona-michatha water project - piping of mona-michatha water project for access to clean water and environmental sustainability | Mona-Michatha Water Project - Piping Of Mona-Michatha Water Project completed | 3110502 | Water Supplies and Sewerage | Molo | Turi | -0.27483, 35.724585 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 500000 | 100 | 500000 | 500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The pipes are underneath the ground hence difficult to see but people downstream are accessing the water.
3037 | Water and Sewerage Management | Piping And Solarization Of Mona Water Project Works | To provide water distribution infrastructure at And Solarization Of Mona Water Project Works | Water piping at And Solarization Of Mona Water Project Works completed | 3110502 | Water Supplies and Sewerage | Molo | Turi | -0.301302, 35.708952 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1888909 | 94.4 | 1888909 | 499923 | 111091 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes but once it has been operationalised. Viable: No. Assessor remarks: The project is misused. There are animal tied to the sola poles.
3038 | Water and Sewerage Management | Piping Of Milima Mitatu Water Project | To provide water distribution infrastructure at Milima Mitatu Water Project | Water piping at Milima Mitatu Water Project completed | 3110502 | Water Supplies and Sewerage | Molo | Turi | -0.30192 35.711143 2702.8 12.199999809265137 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 500000 | 498589.3 | 498589.3 | Equitable | N/A | 498589.3 | 0 | 797936 | 160 | 797936 | 498589 | -299346.7 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is on road reserve.
3039 | Water and Sewerage Management | Purchasing Of Water Pump And Power Connection For Valley Water Project | To implement purchasing of water pump and power connection for valley water project for access to clean water and environmental sustainability | Purchasing Of Water Pump And Power Connection For Valley Water Project completed | 3110502 | Water Supplies and Sewerage | Molo | Turi | -0.270808 35.756023 2454.900146484375 8.100000381469727 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 1400000 | 1400000 | 1400000 | Equitable | N/A | 1400000 | 0 | 797936 | 57 | 797936 | 1400000 | 602064 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Fully piping is required.
3040 | Water and Sewerage Management | Rehabilitation Of Kwa Nyakundi Water Project | To rehabilitate Kwa Nyakundi Water Project to restore functionality | Kwa Nyakundi Water Project rehabilitated | 3110502 | Water Supplies and Sewerage | Molo | Turi | -0.301193 35.70907 2682 10.699999809265137 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 497237 | 99.4 | 497237 | 500000 | 2763 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The title is under some self help group and now an individual is claiming ownership. The county government of Nakuru needs to follow up.
3041 | Water and Sewerage Management | Piping At Michatha Water Project | To provide water distribution infrastructure at Michatha Water Project | Water piping at Michatha Water Project completed | 3110502 | Water Supplies and Sewerage | Molo | Turi | -0.30192 35.711143 2702.8 12.199999809265137 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 499923 | 499923 | 499923 | Equitable | N/A | 499923 | 0 | 499923 | 100 | 499923 | 499923 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is on road reserve.
3042 | Water and Sewerage Management | Completion and Piping and solarization of Rajuera Borehole | To complete and Piping and solarization of Rajuera Borehole | And Piping and solarization of Rajuera Borehole completed | 3110502 | Water Supplies and Sewerage | Rongai | Visoi | -0.125295 35.935638 1744.699951171875 6 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/23 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2240900 | 89.6 | 2240900 | 57432 | 259100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: M/s AfelaLimited. Assessor remarks: Good.
3043 | Water and Sewerage Management | Completion Of Drilling Of Burgei Water Works | To complete Drilling Of Burgei Water Works | Drilling Of Burgei Water Works completed | 3110502 | Water Supplies and Sewerage | Rongai | Visoi | -0.125295 35.935638 1744.699951171875 6 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 1500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: M/s AfelaLimited. Assessor remarks: Good.
3044 | Water and Sewerage Management | Completion Of Rajuera Borehole | To complete Rajuera Borehole | Rajuera Borehole completed | 3110502 | Water Supplies and Sewerage | Rongai | Visoi | -0.125295 35.935638 1744.699951171875 6 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1800000 | 57432 | 57432 | Equitable | N/A | 57432 | 0 | 1742568 | 3034.1 | 1742568 | 57432 | -1685136 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: M/s AfelaLimited. Assessor remarks: Good.
3045 | Water and Sewerage Management | Completion Of Umoja Borehole (Piping And Installation Of Water Tank) | To complete Umoja Borehole (Piping And Installation Of Water Tank) | Umoja Borehole (Piping And Installation Of Water Tank) completed | 3110502 | Water Supplies and Sewerage | Rongai | Visoi | -0.198778, 35.936028 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 3449399 | 3449399 | 3449399 | Equitable | N/A | 3449399 | 0 | 3328973 | 96.5 | 3328973 | 3449399 | 120426 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Ms Tirus. Assessor remarks: Good.
3046 | Water and Sewerage Management | Drilling of Nuithuit Borehole | To implement drilling of nuithuit borehole for access to clean water and environmental sustainability | Drilling of Nuithuit Borehole completed | 3110502 | Water Supplies and Sewerage | Rongai | Visoi | -0.149943 35.881463 1841.6 9.300000190734863 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/23 | 3600000 | 3600000 | 3600000 | Equitable | N/A | 3600000 | 0 | 3132139 | 87 | 3132139 | 960298 | 467861 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Very good.
3047 | Water and Sewerage Management | Equipping of Burgei Borehole | To equip Burgei Borehole with necessary facilities and equipment | Burgei Borehole equipped | 3110502 | Water Supplies and Sewerage | Rongai | Visoi | -0.149943 35.881463 1841.6 9.300000190734863 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1265104 | 84.3 | 1265104 | 1500000 | 234896 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Very good.
3048 | Water and Sewerage Management | Piping At Lower Kimangu | To provide water distribution infrastructure at Lower Kimangu | Water piping at Lower Kimangu completed | 3110502 | Water Supplies and Sewerage | Rongai | Visoi | -0.205011 35.84867 1901.199951171875 29.555999755859375 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 547597 | 547597 | 547597 | Equitable | N/A | 547597 | 0 | 535000 | 97.7 | 535000 | 0 | 12597 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
3049 | Water and Sewerage Management | Piping at Undugu, Jamii and Kware | To provide water distribution infrastructure at Undugu, Jamii and Kware | Water piping at Undugu, Jamii and Kware completed | 3110502 | Water Supplies and Sewerage | Rongai | Visoi | -0.205011 35.84867 1901.199951171875 29.555999755859375 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/23 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1650019 | 91.7 | 1650019 | 1650019 | 149981 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
3050 | Water and Sewerage Management | Piping Of Deloraine Water Project | To provide water distribution infrastructure at Deloraine Water Project | Water piping at Deloraine Water Project completed | 3110502 | Water Supplies and Sewerage | Rongai | Visoi | -0.124687 35.938452 1740.800048828125 26.23200035095215 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 500000 | 498040.2 | 498040.2 | Equitable | N/A | 498040.2 | 0 | 498040 | 100 | 498040 | 498040 | 0.2 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: No. Viable: No. Assessor remarks: Good.
3051 | Water and Sewerage Management | Piping of Lengenet -Kapkalet NARUWASCO water | To provide water distribution infrastructure at Lengenet -Kapkalet NARUWASCO water | Water piping at Lengenet -Kapkalet NARUWASCO water completed | 3110502 | Water Supplies and Sewerage | Rongai | Visoi | -0.120545, 35.88465 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2324 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1432414 | 95.5 | 1432414 | 1432414 | 67586 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Lamrinet kenya limited. Assessor remarks: Good.
3052 | Water and Environment | Piping of Shalom A- Moroto and Shalom B -Jirani Mwema and Purchase of two 10,000litres water tank | To provide water distribution infrastructure at Shalom A- Moroto and Shalom B -Jirani Mwema and Purchase of two 10,000litres water tank | Water piping at Shalom A- Moroto and Shalom B -Jirani Mwema and Purchase of two 10,000litres water tank completed | 3110502 | Water Supplies and Sewerage | Rongai | Visoi | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | N/A | 2800000 | 2800000 | 2800000 | Equitable | N/A | 2800000 | 0 | 2436957 | 87 | 2436957 | 13459 | 363043 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
3053 | Water and Sewerage Management | Purchase And Supply Of Pipes At Shalom A Water Project | To procure and supply Pipes At Shalom A Water Project | Pipes At Shalom A Water Project procured and supplied | 3110502 | Water Supplies and Sewerage | Rongai | Visoi | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 485996 | 97.2 | 485996 | 223970 | 14004 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3054 | Water and Sewerage Management | Purchase And Supply Of Pipes For Supplying Water To Tuiyotich And Kandutura | To procure and supply Pipes For Supplying Water To Tuiyotich And Kandutura | Pipes For Supplying Water To Tuiyotich And Kandutura procured and supplied | 3110502 | Water Supplies and Sewerage | Rongai | Visoi | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 703707 | 70.4 | 703707 | 0 | 296293 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3055 | Water and Sewerage Management | Tabot/Tuiyotich Water Project | To implement tabot/tuiyotich water project for access to clean water and environmental sustainability | Tabot/Tuiyotich Water Project completed | 3110502 | Water Supplies and Sewerage | Rongai | Visoi | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 1500000 | 801 | 801 | Equitable | N/A | 801 | 0 | 1499199 | 187165.9 | 1499199 | 801 | -1498398 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
3056 | Water and Sewerage Management | Visoi water works | To implement visoi water works for access to clean water and environmental sustainability | Visoi water works completed | 3110502 | Water Supplies and Sewerage | Rongai | Visoi | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 2350000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 2335647 | 0 | 2335647 | 2000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
3057 | Water and Sewerage Management | Water Piping At Ngesumin And X-Batler | To implement water piping at ngesumin and x-batler for access to clean water and environmental sustainability | Water Piping At Ngesumin And X-Batler completed | 3110502 | Water Supplies and Sewerage | Rongai | Visoi | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 900000 | 900000 | 900000 | Equitable | N/A | 900000 | 0 | 861000 | 95.7 | 861000 | 1650019 | 39000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3058 | Water and Sewerage Management | Water Piping In Kandutura, Kimangu, Mawe And Jamii | To implement water piping in kandutura, kimangu, mawe and jamii for access to clean water and environmental sustainability | Water Piping In Kandutura, Kimangu, Mawe And Jamii completed | 3110502 | Water Supplies and Sewerage | Rongai | Visoi | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1846952 | 92.3 | 1846952 | 2000000 | 153048 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3059 | Water and Sewerage Management | Water Works - Piping Of Water From Sobea To Deloraine | To implement water works - piping of water from sobea to deloraine for access to clean water and environmental sustainability | Water Works - Piping Of Water From Sobea To Deloraine completed | 3110502 | Water Supplies and Sewerage | Rongai | Visoi | -0.125166 35.938548 1742 21.430999755859375 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 421 | 421 | Equitable | N/A | 421 | 0 | 1199579 | 284935.6 | 1199579 | 421 | -1199158 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
3060 | Water and Sewerage Management | Drilling And Completion Of Umoja Water Borehole | To implement drilling and completion of umoja water borehole for access to clean water and environmental sustainability | Drilling And Completion Of Umoja Water Borehole completed | 3110502 | Water Supplies and Sewerage | Rongai | Visoi | -0.119957 35.933578 1710.7 7 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 1342243.3 | 1342243.3 | 1342243.3 | Equitable | N/A | 1342243.3 | 0 | 1342243 | 100 | 1342243 | 1342243 | 0.3 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
3061 | Water and Sewerage Management | Connection of water in County Council Residential Estate | To implement connection of water in county council residential estate for access to clean water and environmental sustainability | Connection of water in County Council Residential Estate completed | 3110502 | Water Supplies and Sewerage | Naivasha | Viwandani | -0.712072 36.436638 1885.656 0.9549999833106995 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2367300 | 78.9 | 2367300 | 3000000 | 632700 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Assessor remarks: Not started.
3062 | Water and Sewerage Management | Connection Of Water In County Council Residentials Estates | To implement connection of water in county council residentials estates for access to clean water and environmental sustainability | Connection Of Water In County Council Residentials Estates completed | 3110502 | Water Supplies and Sewerage | Naivasha | Viwandani | -0.712072 36.436638 1885.656 0.9549999833106995 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2367300 | 78.9 | 2367300 | 3000000 | 632700 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Assessor remarks: Not started.
3063 | Water and Sewerage Management | Connection of water to CCCR residential houses | To implement connection of water to cccr residential houses for access to clean water and environmental sustainability | Connection of water to CCCR residential houses completed | 3110502 | Water Supplies and Sewerage | Naivasha | Viwandani | -0.71766 36.442854 1917.1319026947021 49.76555278365609 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 1500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete and functional.
3064 | Water and Sewerage Management | Additional Piping At Wei, Akuisi And Nganoini Water Works | To implement additional piping at wei, akuisi and nganoini water works for access to clean water and environmental sustainability | Additional Piping At Wei, Akuisi And Nganoini Water Works completed | 3110502 | Water Supplies and Sewerage | Subukia | Waseges | 0.08815 36.229812 1777.6 13.199999809265137 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | N/A | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3446244 | 98.5 | 3446244 | 3500000 | 53756 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The toilets is in use.
3065 | Akuiz Borehole - Drilling, Equipping Construction Of Water Tank And Installation Of Solar Panels At Akuiz Borehole | Akuiz Borehole - Drilling, Equipping Construction Of Water Tank And Installation Of Solar Panels At Akuiz Borehole | To implement akuiz borehole - drilling, equipping construction of water tank and installation of solar panels at akuiz borehole for access to clean water and environmental sustainability | Akuiz Borehole - Drilling, Equipping Construction Of Water Tank And Installation Of Solar Panels At Akuiz Borehole completed | 3110502 | Water Supplies and Sewerage | Subukia | Waseges | 0.116735 36.274342 1803.2 9.800000190734863 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 394720 | 394720 | 394720 | Equitable | N/A | 394720 | 0 | 394500 | 99.9 | 394500 | 394720 | 220 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Maintenance.
3066 | Chania Igana / Nganoini Water Works | Chania Igana / Nganoini Water Works | To implement chania igana / nganoini water works for access to clean water and environmental sustainability | Chania Igana / Nganoini Water Works completed | 3110502 | Water Supplies and Sewerage | Subukia | Waseges | 0.02338 36.262172 1995.300048828125 5.199999809265137 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 997931.01 | 997931.01 | 997931.01 | Equitable | N/A | 997931.01 | 0 | 912210 | 91.4 | 912210 | 997931 | 85721.01 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The land has already been purchased.
3067 | Water and Sewerage Management | Construction Of Storage Tank And Piping At Wei Borehole Water Project | To construct Storage Tank And Piping At Wei Borehole Water Project | Storage Tank And Piping At Wei Borehole Water Project constructed | 3110502 | Water Supplies and Sewerage | Subukia | Waseges | 0.146943 36.2423 1696.7 18.299999237060547 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2500000 | 639.45 | 639.45 | Equitable | N/A | 639.45 | 0 | 2499361 | 390861.1 | 2499361 | 639 | -2498721.55 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Construction is Ongoing.
3068 | Water and Sewerage Management | Construction Of Storage Tank, Piping, Installation Of Solar Panels And Pumping Machines At Ngamini Borehole Water Project | To construct Storage Tank, Piping, Installation Of Solar Panels And Pumping Machines At Ngamini Borehole Water Project | Storage Tank, Piping, Installation Of Solar Panels And Pumping Machines At Ngamini Borehole Water Project constructed | 3110502 | Water Supplies and Sewerage | Subukia | Waseges | 0.116735 36.274342 1803.2 9.800000190734863 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3499874 | 100 | 3499874 | 3500000 | 126 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Maintenance.
3069 | Water and Sewerage Management | Drilling of Kiriko Borehole, Polepole borehole, Suswa borehole and Kianoe-Kirima borehole in Waseges Ward | To implement drilling of kiriko borehole, polepole borehole, suswa borehole and kianoe-kirima borehole in waseges ward for access to clean water and environmental sustainability | Drilling of Kiriko Borehole, Polepole borehole, Suswa borehole and Kianoe-Kirima borehole in Waseges Ward completed | 3110502 | Water Supplies and Sewerage | Subukia | Waseges | 0.146619, 36.242473 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | N/A | 14000000 | 14000000 | 14000000 | Equitable | N/A | 14000000 | 0 | 10458673 | 74.7 | 10458673 | 2588264 | 3541327 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: Yes. Assessor remarks: Needs Solarization and piping.
3070 | Water and Sewerage Management | Waseges Water Works - Drilling Of Borehole At Kiriko, Additional Piping At Akuis, Wei And Surugutul Water Projects, Construction Of An Inlet And Piping At Kironu Water Projects And Construction Of A Water Tank At Kasi Water Project, Piping At Wei Sec To Tapland Area And Piping At Wiyumiririe Primary To Pondamali Center And Drilling Of Gituamba Borehole Plus Installation Of Solar Security Lights At Wei,Akuisi And Ngamini Boreholes | To implement waseges water works - drilling of borehole at kiriko, additional piping at akuis, wei and surugutul water projects, construction of an inlet and piping at kironu water projects and construction of a water tank at kasi water project, piping at wei sec to tapland area and piping at wiyumiririe primary to pondamali center and drilling of gituamba borehole plus installation of solar security lights at wei,akuisi and ngamini boreholes for access to clean water and environmental sustainability | Waseges Water Works - Drilling Of Borehole At Kiriko, Additional Piping At Akuis, Wei And Surugutul Water Projects, Construction Of An Inlet And Piping At Kironu Water Projects And Construction Of A Water Tank At Kasi Water Project, Piping At Wei Sec To Tapland Area And Piping At Wiyumiririe Primary To Pondamali Center And Drilling Of Gituamba Borehole Plus Installation Of Solar Security Lights At Wei,Akuisi And Ngamini Boreholes completed | 3110502 | Water Supplies and Sewerage | Subukia | Waseges | 0.019092, 36.24071 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 10500000 | 8187179.25 | 8187179.25 | Equitable | N/A | 8187179.25 | 0 | 6925477 | 84.6 | 6925477 | 8187179 | 1261702.25 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: The project is yet to start.
3071 | Water and Sewerage Management | Equipping And Solarisation Of Ndashata Water Project | To equip And Solarisation Of Ndashata Water Project with necessary facilities and equipment | And Solarisation Of Ndashata Water Project equipped | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Amalo | -0.63908, 35.658645 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2023 | 2500000 | 222722 | 222722 | Equitable | N/A | 222722 | 0 | 2277278 | 1022.5 | 2277278 | 222722 | -2054556 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: yes. Viable: yes. Assessor remarks: done.
3072 | Water and Sewerage Management | Installation of pump and laying of pipes at Ndasiata | To install pump and laying of pipes at Ndasiata | Pump and laying of pipes at Ndasiata installed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Amalo | -0.638923, 35.65338 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2025 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 1480098 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: project completed.
3073 | Water and Sewerage Management | Renovation Of 2 Gatangi Tanks In Wanyororo | To rehabilitate 2 Gatangi Tanks In Wanyororo to restore functionality | 2 Gatangi Tanks In Wanyororo rehabilitated | 3110504 | Other Infrastructure and Civil Works | Bahati | Bahati | -0.160234 36.102195 1851.86962890625 30.295000076293945 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 1745951.45 | 1745951.45 | 1745951.45 | Equitable | N/A | 1745951.45 | 0 | 1737845 | 99.5 | 1737845 | 1745951 | 8106.45 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes. Assessor remarks: Nor started.
3074 | Water and Sewerage Management | Installation Of Electricity, Borehole Pump And Piping And Other Borehole Equipment At Bongo Borehole | To install Electricity, Borehole Pump And Piping And Other Borehole Equipment At Bongo Borehole | Electricity, Borehole Pump And Piping And Other Borehole Equipment At Bongo Borehole installed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Barut | 0.3533, 36.049 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2022 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Completed.
3075 | Water and Sewerage Management | Drilling Of Gituru Estate Community Borehole | To implement drilling of gituru estate community borehole for access to clean water and environmental sustainability | Drilling Of Gituru Estate Community Borehole completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Biashara-Naivasha | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 3300000 | 3538603.5 | 3538603.5 | Equitable | N/A | 3538603.5 | 0 | 3489071 | 98.6 | 3489071 | 3538604 | 49532.5 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3076 | Water and Sewerage Management | Installation Of Solar And Fencing Of Kirima Borehole | To install Solar And Fencing Of Kirima Borehole | Solar And Fencing Of Kirima Borehole installed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Biashara-Naivasha | -0.721687, 36.520472 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2022 | 2500000 | 199644.6 | 199644.6 | Equitable | N/A | 199644.6 | 0 | 2300355 | 1152.2 | 2300355 | 199645 | -2100710.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Additional batteries for more efficient power backup.
3077 | Water and Sewerage Management | Installation Of Solar Panels And Pump For Muteithia Boreholes | To install Solar Panels And Pump For Muteithia Boreholes | Solar Panels And Pump For Muteithia Boreholes installed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Biashara-Naivasha | -0.721687, 36.520472 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2022 | 5500000 | 7000000 | 7000000 | Equitable | N/A | 7000000 | 0 | 6949166 | 99.3 | 6949166 | 7000000 | 50834 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Additional batteries for more efficient power backup.
3078 | Water and Sewerage Management | Installation Of Solar Power And Purchase And Supply Of Water Tank And Fencing Of Kambi Ndoro Borehole | To install Solar Power And Purchase And Supply Of Water Tank And Fencing Of Kambi Ndoro Borehole | Solar Power And Purchase And Supply Of Water Tank And Fencing Of Kambi Ndoro Borehole installed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Biashara-Naivasha | -0.721687, 36.520472 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2022 | 4000000 | 262862.8 | 262862.8 | Equitable | N/A | 262862.8 | 0 | 3737137 | 1421.7 | 3737137 | 262863 | -3474274.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Additional batteries for more efficient power backup.
3079 | Water and Sewerage Management | Installation of Solar, repair of steel tank and construction of 3m tower at Kahuru water project | To install Solar, repair of steel tank and construction of 3m tower at Kahuru water project | Solar, repair of steel tank and construction of 3m tower at Kahuru water project installed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Biashara-Naivasha | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3914855 | 97.9 | 3914855 | 4000000 | 85145 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3080 | Water and Sewerage Management | Kambi Ndoro Borehole - Purchase Of Pumps And Construction Of Pump House | To implement kambi ndoro borehole - purchase of pumps and construction of pump house for access to clean water and environmental sustainability | Kambi Ndoro Borehole - Purchase Of Pumps And Construction Of Pump House completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Biashara-Naivasha | -0.701617, 36.532842 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2022 | 2000000 | 1335.85 | 1335.85 | Equitable | N/A | 1335.85 | 0 | 1998664 | 149617.4 | 1998664 | 1336 | -1997328.15 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Working well.
3081 | Water and Sewerage Management | Kamurugu Water Project - Installation Of Solar | To implement kamurugu water project - installation of solar for access to clean water and environmental sustainability | Kamurugu Water Project - Installation Of Solar completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Biashara-Naivasha | -0.725647, 36.486758 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2016 | 3000000 | 242912 | 242912 | Equitable | N/A | 242912 | 0 | 2757088 | 1135 | 2757088 | 242912 | -2514176 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Initial drilling delivered less water hence drilled deeper..
3082 | Water and Sewerage Management | Muteithia Borehole - Deepening , Fencing And Pump Construction of Pump House | To implement muteithia borehole - deepening , fencing and pump construction of pump house for access to clean water and environmental sustainability | Muteithia Borehole - Deepening , Fencing And Pump Construction of Pump House completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Biashara-Naivasha | -0.721865, 36.520293 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2022 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2498988 | 100 | 2498988 | 2500000 | 1012 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Additional of storage tanks...
3083 | Water and Sewerage Management | Construction Of Sewer Line At Abongoloya Area | To construct Sewer Line At Abongoloya Area | Sewer Line At Abongoloya Area constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1329591 | 88.6 | 1329591 | 1500000 | 170409 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3084 | Water and Sewerage Management | Bavuni Borehole Power Connection And Water Works | To implement bavuni borehole power connection and water works for access to clean water and environmental sustainability | Bavuni Borehole Power Connection And Water Works completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Dundori | -0.252415, 36.187695 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/2020 | 500000 | 449018.72 | 449018.72 | Equitable | N/A | 449018.72 | 0 | 449019 | 100 | 449019 | 449019 | -0.28 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: Sagimwa Co. Assessor remarks: Complete.
3085 | Water and Sewerage Management | Construction of a raised water tower at Wanyororo Borehole | To construct a raised water tower at Wanyororo Borehole | A raised water tower at Wanyororo Borehole constructed | 3110504 | Other Infrastructure and Civil Works | Bahati | Dundori | -0.252138, 36.187568 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/2023 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1869850 | 93.5 | 1869850 | 1869850 | 130150 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Kewaska company. Assessor remarks: Good require operationalization.
3086 | Water and Sewerage Management | Desalination Of Wanyororo Dam | To implement desalination of wanyororo dam for access to clean water and environmental sustainability | Desalination Of Wanyororo Dam completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Dundori | -0.256626, 36.185103 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/2020 | 1197111 | 261272.9 | 261272.9 | Equitable | N/A | 261272.9 | 0 | 935838 | 358.2 | 935838 | 261273 | -674565.1 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ardent logistics. Assessor remarks: Good require desalination.
3087 | Water and Sewerage Management | Dundori Water Power Connection | To implement dundori water power connection for access to clean water and environmental sustainability | Dundori Water Power Connection completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Dundori | -0.239802 36.241437 2324.000244140625 5.599999904632568 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 448311 | 448311 | 448311 | Equitable | N/A | 448311 | 0 | 448311 | 100 | 448311 | 448311 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
3088 | Water and Sewerage Management | Equipping, Solarisation And Other Water Works At Dundori Borehole | To implement equipping, solarisation and other water works at dundori borehole for access to clean water and environmental sustainability | Equipping, Solarisation And Other Water Works At Dundori Borehole completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Dundori | -0.246383, 36.238453 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/2022 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 3000000 | 100 | 3000000 | 3000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Triyan general. Assessor remarks: Good.
3089 | Water and Sewerage Management | Expansion of Bavuni Kiamunyeki Dam | To expand Bavuni Kiamunyeki Dam to increase capacity | Bavuni Kiamunyeki Dam expanded | 3110504 | Other Infrastructure and Civil Works | Bahati | Dundori | -0.214128, 36.188707 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/2023 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 977267 | 97.7 | 977267 | 0 | 22733 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition, require maintenance and fencing.
3090 | Water and Sewerage Management | Installation Of Solar Panel And Water Works At Bavuni Water Borehole | To install Solar Panel And Water Works At Bavuni Water Borehole | Solar Panel And Water Works At Bavuni Water Borehole installed | 3110504 | Other Infrastructure and Civil Works | Bahati | Dundori | -0.235943, 36.182293 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/2021 | 2500000 | 2116872.72 | 2116872.72 | Equitable | N/A | 2116872.72 | 0 | 383127 | 18.1 | 383127 | 1000000 | 1733745.72 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Metro EDD company. Assessor remarks: Good.
3091 | Water and Sewerage Management | Installation of solar panels for Githioro water project and Karuchwa project | To install solar panels for Githioro water project and Karuchwa project | Solar panels for Githioro water project and Karuchwa project installed | 3110504 | Other Infrastructure and Civil Works | Bahati | Dundori | -0.258463, 36.188812 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/2023 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 1709978 | 57 | 1709978 | 336054 | 1290022 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Kabawahe company Ltd. Assessor remarks: Functional.
3092 | Water and Sewerage Management | Purchase And Installation Of Solar Panel In Wanyororo Water Project | To procure and install Solar Panel In Wanyororo Water Project | Solar Panel In Wanyororo Water Project procured and installed | 3110504 | Other Infrastructure and Civil Works | Bahati | Dundori | -0.2523 36.18779 2039.2 19.399999618530273 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 2200000 | 2200000 | 2200000 | Equitable | N/A | 2200000 | 0 | 2199894 | 100 | 2199894 | 2200000 | 106 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Metro EDD company. Assessor remarks: Good.
3093 | Water and Sewerage Management | Wanyoro Borehole Power Connection And Water Works | To implement wanyoro borehole power connection and water works for access to clean water and environmental sustainability | Wanyoro Borehole Power Connection And Water Works completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Dundori | -0.252415, 36.187695 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/2020 | 542370 | 542370 | 542370 | Equitable | N/A | 542370 | 0 | 541279 | 99.8 | 541279 | 542370 | 1091 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: Sagimwa Co. Assessor remarks: Complete.
3094 | Water and Sewerage Management | Construction of 2 public toilets at Nderit water point and Oldupei market | To construct 2 public toilets at Nderit water point and Oldupei market | 2 public toilets at Nderit water point and Oldupei market constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Eburru/Mbaruk | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/23 | 1242583 | 1242583 | 1242583 | Equitable | N/A | 1242583 | 0 | 3571500 | 287.4 | 3571500 | 1242583 | -2328917 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3095 | Water and Sewerage Management | Equipping And Solarisation Of Kirima Borehole | To equip And Solarisation Of Kirima Borehole with necessary facilities and equipment | And Solarisation Of Kirima Borehole equipped | 3110504 | Other Infrastructure and Civil Works | Gilgil | Eburru/Mbaruk | -0.344725, 36.173544 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | No details | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 5799954 | 96.7 | 5799954 | 6000000 | 200046 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: It's viable and it meet the needs of the area. Contractor: Crater enterprises. Assessor remarks: Fairy done.
3096 | Water and Sewerage Management | Equipping Of Kasambara Borehole | To equip Kasambara Borehole with necessary facilities and equipment | Kasambara Borehole equipped | 3110504 | Other Infrastructure and Civil Works | Gilgil | Eburru/Mbaruk | -0.36445, 36.239523 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | Not available | 4800000 | 4800000 | 4800000 | Equitable | N/A | 4800000 | 0 | 4699964 | 97.9 | 4699964 | 4800000 | 100036 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: It was viable. Contractor: Marinara investments Ltd. Assessor remarks: Very Good project.
3097 | Water and Sewerage Management | Equipping Of Workers Borehole | To equip Workers Borehole with necessary facilities and equipment | Workers Borehole equipped | 3110504 | Other Infrastructure and Civil Works | Gilgil | Eburru/Mbaruk | -0.342227, 36.151336 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2021/22 | 4900000 | 4900000 | 4900000 | Equitable | N/A | 4900000 | 0 | 4895816 | 99.9 | 4895816 | 4900000 | 4184 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Mwea construction. Assessor remarks: Low usability/ low utilization rate.
3098 | Water and Sewerage Management | Equipping, Solarisation And Fencing Of Nderit Borehole | To implement equipping, solarisation and fencing of nderit borehole for access to clean water and environmental sustainability | Equipping, Solarisation And Fencing Of Nderit Borehole completed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Eburru/Mbaruk | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 5991939 | 99.9 | 5991939 | 6000000 | 8061 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3099 | Water and Sewerage Management | Extention Of Echariria Water Piping | To implement extention of echariria water piping for access to clean water and environmental sustainability | Extention Of Echariria Water Piping completed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Eburru/Mbaruk | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3100 | Water and Sewerage Management | Extention Of Piping From Gema -Witemere Road | To implement extention of piping from gema -witemere road for access to clean water and environmental sustainability | Extention Of Piping From Gema -Witemere Road completed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Eburru/Mbaruk | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 500000 | 100 | 500000 | 500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3101 | Water and Sewerage Management | Extention Of Upper Baraka Village | To implement extention of upper baraka village for access to clean water and environmental sustainability | Extention Of Upper Baraka Village completed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Eburru/Mbaruk | -0.355649, 36.194914 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 22/23 | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 267937 | 67 | 267937 | 400000 | 132063 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Unspecified. Assessor remarks: Residents have piped water.
3102 | Water and Sewerage Management | Solarization Of Kiungururia Borehole | To implement solarization of kiungururia borehole for access to clean water and environmental sustainability | Solarization Of Kiungururia Borehole completed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Eburru/Mbaruk | -0.344725, 36.173544 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | No details | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 1500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: It's viable and it meet the needs of the area. Contractor: Crater enterprises. Assessor remarks: Fairy done.
3103 | Water and Sewerage Management | Equipping at Mwangi Michuki borehole | To equip at Mwangi Michuki borehole with necessary facilities and equipment | At Mwangi Michuki borehole equipped | 3110504 | Other Infrastructure and Civil Works | Molo | Elburgon | -0.292714, 35.791345 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | - | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 782988 | 97.9 | 782988 | 17012 | 17012 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yea. Viable: Yes. Contractor: FINO Limited. Assessor remarks: Completed.
3104 | Water and Sewerage Management | Equipping Of Mwangi Michuki Borehole | To equip Mwangi Michuki Borehole with necessary facilities and equipment | Mwangi Michuki Borehole equipped | 3110504 | Other Infrastructure and Civil Works | Molo | Elburgon | -0.292714, 35.791345 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | - | 3000000 | 800482 | 800482 | Equitable | N/A | 800482 | 0 | 2199518 | 274.8 | 2199518 | 800482 | -1399036 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yea. Viable: Yes. Contractor: FINO Limited. Assessor remarks: Completed.
3105 | Water and Sewerage Management | Installation of Solar panels at Elburgon Industrial Water Project | To install Solar panels at Elburgon Industrial Water Project | Solar panels at Elburgon Industrial Water Project installed | 3110504 | Other Infrastructure and Civil Works | Molo | Elburgon | -0.300373 35.797558 0 52.400001525878906 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | N/A | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1685561 | 93.6 | 1685561 | 1800000 | 114439 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
3106 | Water and Sewerage Management | Installation of Solar panels at Kasarani Water Projects | To install Solar panels at Kasarani Water Projects | Solar panels at Kasarani Water Projects installed | 3110504 | Other Infrastructure and Civil Works | Molo | Elburgon | -0.294954 35.766447 0 2799.9990234375 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | N/A | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1685561 | 93.6 | 1685561 | 1800000 | 114439 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3107 | Water and Sewerage Management | Installation Of Solar Panels At Saptet Water Project | To install Solar Panels At Saptet Water Project | Solar Panels At Saptet Water Project installed | 3110504 | Other Infrastructure and Civil Works | Molo | Elburgon | -0.294954 35.766447 0 2799.9990234375 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1685561 | 93.6 | 1685561 | 1800000 | 114439 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3108 | Water and Sewerage Management | Hawaziporrah Cattle Dip Eleveted Tank And Pipes | To implement hawaziporrah cattle dip eleveted tank and pipes for access to clean water and environmental sustainability | Hawaziporrah Cattle Dip Eleveted Tank And Pipes completed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Elementaita | -0.565733 36.116574 1961.0999755859375 92.9000015258789 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 4303743 | 4303743 | 4210834 | Equitable | N/A | 4210834 | 0 | 4210834 | 97.8 | 4210834 | 4303743 | 92909 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: Stalled.
3109 | Water and Sewerage Management | Purchase and installation of submersible water pump for Mogaa water project | To procure and install submersible water pump for Mogaa water project | Submersible water pump for Mogaa water project procured and installed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Elementaita | -0.633558 36.114698 2875.204 4.869999885559082 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 3758989 | 375.9 | 3758989 | 1000000 | -2758989 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Needs renovation.
3110 | Water And Sewerage Management | Settlement Borehole - Installation Of Solar Panel And Purchase Of Submersible Water Pump | To implement settlement borehole - installation of solar panel and purchase of submersible water pump for access to clean water and environmental sustainability | Settlement Borehole - Installation Of Solar Panel And Purchase Of Submersible Water Pump completed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Elementaita | -0.529775, 36.090549 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 3400000 | 1480 | 1480 | Equitable | N/A | 1480 | 0 | 3398520 | 229629.7 | 3398520 | 1480 | -3397040 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Function.
3111 | Water and Sewerage Management | Solarization and equipping of Meli Borehole | To implement solarization and equipping of meli borehole for access to clean water and environmental sustainability | Solarization and equipping of Meli Borehole completed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Elementaita | -0.663792, 36.11113 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/23 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3327547 | 95.1 | 3327547 | 3327547 | 172453 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: In use.
3112 | Water and Sewerage Management | Solarization Of Inua Hustler Borehole | To implement solarization of inua hustler borehole for access to clean water and environmental sustainability | Solarization Of Inua Hustler Borehole completed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Elementaita | -0.663792, 36.11113 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3443479 | 98.4 | 3443479 | 3327547 | 56521 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: In use.
3113 | Water and Sewerage Management | Construction and expansion of sewer lines at Pangani USAID and Kimathi Estate | To construct and expansion of sewer lines at Pangani USAID and Kimathi Estate | And expansion of sewer lines at Pangani USAID and Kimathi Estate constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Flamingo | -0.303637, 36.074191 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/2023 | 11514821 | 11514821 | 11514821 | Equitable | N/A | 11514821 | 0 | 10168311 | 88.3 | 10168311 | 227200 | 1346510 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: BFC Enterprises. Assessor remarks: Completed and in use.
3114 | Water and Sewerage Management | Rehabilitation and connection to sewer lines 3 no of toilet blocks at Flamingo estate | To rehabilitate connection to sewer lines 3 no of toilet blocks at Flamingo estate to restore functionality | Connection to sewer lines 3 no of toilet blocks at Flamingo estate rehabilitated | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Flamingo | -0.303767, 36.078671 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2013/2014 | 4500000 | 4500000 | 4500000 | Equitable | N/A | 4500000 | 0 | 4045314 | 89.9 | 4045314 | 4045314 | 454686 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: In use.
3115 | Water and Sewerage Management | Rehabilitation Of Toilet And New Sewer Line System At Kimathi Estate | To rehabilitate Toilet And New Sewer Line System At Kimathi Estate to restore functionality | Toilet And New Sewer Line System At Kimathi Estate rehabilitated | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Flamingo | -0.30363, 36.078623 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2020/21 | 514820.55 | 514820.55 | 514820.55 | Equitable | N/A | 514820.55 | 0 | 3485179 | 677 | 3485179 | 514821 | -2970358.45 | Stalled | 75 | 100 | STALLED DUE TO INSUFFICIEN FUNDS | 2018 | N/A | -2970358.45 | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Complete.
3116 | Water and Sewerage Management | Maji Moto Spring And Intake Fencing | To implement maji moto spring and intake fencing for access to clean water and environmental sustainability | Maji Moto Spring And Intake Fencing completed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Gilgil | -0.506051 36.327303 1989.4000244140625 60 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 1651955 | 1651955 | 1651955 | Equitable | N/A | 1651955 | 0 | 1620000 | 98.1 | 1620000 | 1651955 | 31955 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Partially. Viable: Viable. Assessor remarks: The social hall was vandalized.
3117 | Water and Sewerage Management | Completion Of Desilting Of Storm Water Retention Pond At Old Town Treatment Works | To complete Desilting Of Storm Water Retention Pond At Old Town Treatment Works | Desilting Of Storm Water Retention Pond At Old Town Treatment Works completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2018/19 | 2018/19 | 497054 | 1052856 | 1052856 | N/A | N/A | 1052856 | 0 | 4941252 | 469.3 | 4941252 | 497054 | -3888396 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3118 | Water and Sewerage Management | Construction Of Office And Sanitary Facility Eco-Toilets I (Gioto) | To construct Office And Sanitary Facility Eco-Toilets I (Gioto) | Office And Sanitary Facility Eco-Toilets I (Gioto) constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 2000000 | 2000000 | 2000000 | N/A | N/A | 2000000 | 0 | 7025864 | 351.3 | 7025864 | 2000000 | -5025864 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
3119 | Water and Sewerage Management | Construction/Rehabilitation Of Sanitation Facilities | To implement construction/rehabilitation of sanitation facilities for access to clean water and environmental sustainability | Construction/Rehabilitation Of Sanitation Facilities completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 3400000 | 3400000 | 3400000 | Equitable | N/A | 3400000 | 0 | 7025864 | 206.6 | 7025864 | 3400000 | -3625864 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3120 | Water and Sewerage Management | Desilting of Storm Water retention Pond at Old Town treatment Works | To implement desilting of storm water retention pond at old town treatment works for access to clean water and environmental sustainability | Desilting of Storm Water retention Pond at Old Town treatment Works completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2022/23 | 2022/23 | 10000000 | 4000000 | 4000000 | N/A | N/A | 4000000 | 0 | 4899098 | 122.5 | 4899098 | 497054 | -899098 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3121 | Climate Change Resilience and County Energy Development | Establishment Of Energy Centres For Promotion Of Renewable Energy Technologies | To implement establishment of energy centres for promotion of renewable energy technologies for access to clean water and environmental sustainability | Establishment Of Energy Centres For Promotion Of Renewable Energy Technologies completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 4000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
3122 | Climate Change Resilience and County Energy Development | Extension of Dry port water in Maai Mahiu | To expand Dry port water in Maai Mahiu to increase capacity | Dry port water in Maai Mahiu expanded | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | N/A | 6600000 | 6600000 | 6600000 | Equitable | N/A | 6600000 | 0 | 5997919 | 90.9 | 5997919 | 9600000 | 602081 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
3123 | Water and Sewerage Management | Fencing, Construction Of Access Road, Eco Toilet And Office At Naivasha Dumpsite | To implement fencing, construction of access road, eco toilet and office at naivasha dumpsite for access to clean water and environmental sustainability | Fencing, Construction Of Access Road, Eco Toilet And Office At Naivasha Dumpsite completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 10000000 | 8000000 | 8000000 | N/A | N/A | 8000000 | 0 | 7789133 | 97.4 | 7789133 | 8000000 | 210867 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3124 | Environmental Management | Fencing Of Gioto Disposal Site | To secure Gioto Disposal Site through fencing | Gioto Disposal Site fenced and secured | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 3303249.45 | 3303249.45 | 3303249.45 | N/A | N/A | 3303249.45 | 0 | 4696751 | 142.2 | 4696751 | 3303249 | -1393501.55 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
3125 | Water and Sewerage Management | Other County Development Projects | To implement other county development projects for access to clean water and environmental sustainability | Other County Development Projects completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 3728738 | 3728738 | 3728738 | N/A | N/A | 3728738 | 0 | 7089732 | 190.1 | 7089732 | 3728738 | -3360994 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
3126 | Environmental Management | Purchase And Installation Of Litter Bins | To procure and install Litter Bins | Litter Bins procured and installed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 6000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2870026 | 95.7 | 2870026 | 27046 | 129974 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3127 | Climate Change Resilience and County Energy Development | Rain Water (Roof) Catchment Promotion Programme | To implement rain water (roof) catchment promotion programme for access to clean water and environmental sustainability | Rain Water (Roof) Catchment Promotion Programme completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 5000000 | 2898633 | 2898633 | Equitable | N/A | 2898633 | 0 | 2884920 | 99.5 | 2884920 | 2898633 | 13713 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
3128 | Water and Sewerage Management | Rehabilitation Of Water Supplies (Existing System) | To rehabilitate Water Supplies (Existing System) to restore functionality | Water Supplies (Existing System) rehabilitated | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.695026, 36.480933 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2021/22 | 3000000 | 5622.1 | 5622.1 | N/A | N/A | 5622.1 | 0 | 2994378 | 53260.8 | 2994378 | 5622 | -2988755.9 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
3129 | Water and Sewerage Management | Salgaa Area Programme (World Vision) Counterpart funding | To implement salgaa area programme (world vision) counterpart funding for access to clean water and environmental sustainability | Salgaa Area Programme (World Vision) Counterpart funding completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.391082, 35.742475 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 17000000 | 16970338.09 | 16970338.09 | N/A | N/A | 16970338.09 | 0 | 0 | 0 | 0 | 16970338 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Project moved from baraget to baseline.
3130 | Water and Sewerage Management | Solarization of borehole NGC in London | To implement solarization of borehole ngc in london for access to clean water and environmental sustainability | Solarization of borehole NGC in London completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 5000000 | 0 | 5000000 | Equitable | N/A | 5000000 | 0 | 5000000 | 100 | 5000000 | 5000000 | -5000000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3131 | Water and Sewerage Management | Solarization Of Water Boreholes | To implement solarization of water boreholes for access to clean water and environmental sustainability | Solarization Of Water Boreholes completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 5000000 | 100 | 5000000 | 5000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3132 | Water and Sewerage Management | Desilting Kameno Dam | To implement desilting kameno dam for access to clean water and environmental sustainability | Desilting Kameno Dam completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Hells Gate | -0.804589, 36.475493 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 4000000 | 1644 | 1644 | Equitable | N/A | 1644 | 0 | 3998356 | 243209 | 3998356 | 1644 | -3996712 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project was done at a cost of 4,000,000.
3133 | Water and Sewerage Management | Installation of solar panel system at Mirera, Suswa water projects | To install solar panel system at Mirera, Suswa water projects | Solar panel system at Mirera, Suswa water projects installed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Hells Gate | -0.778189, 36.42932 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/23 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2997737 | 149.9 | 2997737 | 1821159 | -997737 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project was transferred to Mwiciringiri water project.
3134 | Water and Sewerage Management | Water Pump Installation And Installation Of Solar Panels In Rubiri | To implement water pump installation and installation of solar panels in rubiri for access to clean water and environmental sustainability | Water Pump Installation And Installation Of Solar Panels In Rubiri completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Hells Gate | -0.804832, 36.454011 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 3000000 | 4023541.4 | 4023541.4 | Equitable | N/A | 4023541.4 | 0 | 4023541 | 100 | 4023541 | 4023541 | 0.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Peribas limited. Assessor remarks: The project is helping the community to access water from shorter distance.
3135 | Water and Sewerage Management | Desilting of Ngosur Dam and Building of water Intake | To implement desilting of ngosur dam and building of water intake for access to clean water and environmental sustainability | Desilting of Ngosur Dam and Building of water Intake completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Kabatini | -0.214433 36.162776 2030.4000244140625 10.21500015258789 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/23 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 799335 | 79.9 | 799335 | 799335 | 200665 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Willis samwa suppliers limited. Assessor remarks: Operational.
3136 | Water and Sewerage Management | Expansion And Distillation Of Crater Dam,Gozul Dam; Construction Of Water Tank At Wendo Tank At Ut Public Utility Ground, Jonathan Ground, Mariru Ground ; Piping Of Thayu, Gatitu And Muchina Farm Water Project, Rurii Moi Ndeffo And Kimende | To expand And Distillation Of Crater Dam,Gozul Dam; Construction Of Water Tank At Wendo Tank At Ut Public Utility Ground, Jonathan Ground, Mariru Ground ; Piping Of Thayu, Gatitu And Muchina Farm Water Project, Rurii Moi Ndeffo And Kimende to increase capacity | And Distillation Of Crater Dam,Gozul Dam; Construction Of Water Tank At Wendo Tank At Ut Public Utility Ground, Jonathan Ground, Mariru Ground ; Piping Of Thayu, Gatitu And Muchina Farm Water Project, Rurii Moi Ndeffo And Kimende expanded | 3110504 | Other Infrastructure and Civil Works | Bahati | Kabatini | -0.230755, 36.163102 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2021 | 6802994.55 | 141926.6 | 141926.6 | Equitable | N/A | 141926.6 | 0 | 6661068 | 4693.3 | 6661068 | 141927 | -6519141.4 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
3137 | Water and Sewerage Management | Installation of solar system at Kabatini borehole | To install solar system at Kabatini borehole | Solar system at Kabatini borehole installed | 3110504 | Other Infrastructure and Civil Works | Bahati | Kabatini | -0.231931, 36.147504 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2022 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1841804 | 92.1 | 1841804 | 1841804 | 158196 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Yes at that time. Viable: Yes. Contractor: Jecy company limited. Assessor remarks: Currently not operational pending a court case.
3138 | Water and Sewerage Management | Installation Of Solar System At Kwa Amos Borehole | To install Solar System At Kwa Amos Borehole | Solar System At Kwa Amos Borehole installed | 3110504 | Other Infrastructure and Civil Works | Bahati | Kabatini | -0.231931, 36.147504 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2022 | 2000000 | 118480 | 118480 | Equitable | N/A | 118480 | 0 | 1881520 | 1588 | 1881520 | 118480 | -1763040 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Yes at that time. Viable: Yes. Contractor: Jecy company limited. Assessor remarks: Currently not operational pending a court case.
3139 | Water and Sewerage Management | Limuko Borehole Solar Installation | To implement limuko borehole solar installation for access to clean water and environmental sustainability | Limuko Borehole Solar Installation completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Kabatini | -0.245966 36.145761 1928.199951171875 9.814000129699707 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2500000 | 100 | 2500000 | 2500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Yed. Contractor: Gee-el construction works ltd. Assessor remarks: Operational but it only serves the school ( heroes technical, heroes girls and boys) it doesn't serve the community.
3140 | Water and Sewerage Management | Rehabilitation of Gitu Borehole, solarization and Piping to Nyathuna area | To rehabilitate Gitu Borehole, solarization and Piping to Nyathuna area to restore functionality | Gitu Borehole, solarization and Piping to Nyathuna area rehabilitated | 3110504 | Other Infrastructure and Civil Works | Bahati | Kabatini | -0.184111 36.192215 2261.89697265625 10.04699993133545 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/23 | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 2604780 | 43.4 | 2604780 | 1425940 | 3395220 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes. Assessor remarks: The project was reallocated to UT borehole which was intiatially meant for gitu borehole.
3141 | Water and Sewerage Management | Rehabilitation of River Muriundu and West Acre through planting of giant bamboos and pegging of Riparian lane | To rehabilitate River Muriundu and West Acre through planting of giant bamboos and pegging of Riparian lane to restore functionality | River Muriundu and West Acre through planting of giant bamboos and pegging of Riparian lane rehabilitated | 3110504 | Other Infrastructure and Civil Works | Bahati | Kabatini | -0.213417 36.162894 2030.4000244140625 14.807999610900879 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/23 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 968745 | 96.9 | 968745 | 31255 | 31255 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Kundoki. Assessor remarks: Partially in good condition.
3142 | Water and Sewerage Management | Solarization and Construction of elevated tank at Limuko borehole | To implement solarization and construction of elevated tank at limuko borehole for access to clean water and environmental sustainability | Solarization and Construction of elevated tank at Limuko borehole completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Kabatini | -0.231931, 36.147504 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2698044 | 89.9 | 2698044 | 2698044 | 301956 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Yes at that time. Viable: Yes. Contractor: Jecy company limited. Assessor remarks: Currently not operational pending a court case.
3143 | Water and Sewerage Management | Renovation Of Kingochoch Water Tank | To rehabilitate Kingochoch Water Tank to restore functionality | Kingochoch Water Tank rehabilitated | 3110504 | Other Infrastructure and Civil Works | Subukia | Kabazi | -0.158008 36.079218 1887.2 9 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 499210.64 | 499210.64 | 499210.64 | Equitable | N/A | 499210.64 | 0 | 2718933 | 544.6 | 2718933 | 499211 | -2219722.36 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: Not indicated. Assessor remarks: Funds to be allocated for pipping.
3144 | Water and Sewerage Management | Jogoo water project - desilting and relaying of pipes | To implement jogoo water project - desilting and relaying of pipes for access to clean water and environmental sustainability | Jogoo water project - desilting and relaying of pipes completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Kamara | -0.21323 35.661657 2695.9 4.699999809265137 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | N/A | 634660 | 634660 | 634660 | Equitable | N/A | 634660 | 0 | 3988715.36 | 628.5 | 3988715.36 | 634660 | -3354055.36 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Elwaso enterprise limited. Assessor remarks: Complete but needs fencing.
3145 | Water and Sewerage Management | Protection And Piping Of Sarambei Spring | To implement protection and piping of sarambei spring for access to clean water and environmental sustainability | Protection And Piping Of Sarambei Spring completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Kamara | -0.162838 35.693123 2518.6 6.599999904632568 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 2999994.9 | 2999994.9 | 2999994.9 | Equitable | N/A | 2999994.9 | 0 | 2999995 | 100 | 2999995 | 2999995 | -0.1 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Needs maintenance.
3146 | Water and Sewerage Management | Installation Of Electicity At Ingobor Borehole (Phase II) | To install Electicity At Ingobor Borehole (Phase II) | Electicity At Ingobor Borehole (Phase II) installed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kapkures | -0.306306, 36.018533 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 723963 | 723963 | 723963 | Equitable | N/A | 723963 | 0 | 723722 | 100 | 723722 | 723963 | 241 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Improved access to clean water. Assessor remarks: Completed and operating..
3147 | Water and Sewerage Management | Purchase Of Sub Massive Pump At Ingobor | To procure Sub Massive Pump At Ingobor | Sub Massive Pump At Ingobor procured | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kapkures | -0.324324 36.036613 0 2000 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 1500000 | 2347.2 | 2347.2 | Equitable | N/A | 2347.2 | 0 | 1497653 | 63805.9 | 1497653 | 2347 | -1495305.8 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Has enhanced access to clean water. Assessor remarks: Done and in operation.
3148 | Water and Sewerage Management | Construction Of Powerhouse, Connection Of Electricty, Purchase Of Pumpset And Piping At Soitaran Water Project | To construct Powerhouse, Connection Of Electricty, Purchase Of Pumpset And Piping At Soitaran Water Project | Powerhouse, Connection Of Electricty, Purchase Of Pumpset And Piping At Soitaran Water Project constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Keringet | -0.468185 35.645505 2570.8999999999996 12.5 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1213650 | 67.4 | 1213650 | 1800000 | 586350 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes but they need one more. Assessor remarks: Need more class.
3149 | Water and Sewerage Management | Purchase Of Pump, Storage Tank And Piping Water At Soitaran | To procure Pump, Storage Tank And Piping Water At Soitaran | Pump, Storage Tank And Piping Water At Soitaran procured | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Keringet | -0.501323 35.714485 2647.8 6.300000190734863 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2999867.01 | 2999867.01 | 2999867.01 | Equitable | N/A | 2999867.01 | 0 | 2999867 | 100 | 2999867 | 2999867 | 0.01 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not in operation due to pu. P failure.
3150 | Water and Sewerage Management | Purchase Of Pump,Tank And Piping Of Water At Tendwet | To procure Pump,Tank And Piping Of Water At Tendwet | Pump,Tank And Piping Of Water At Tendwet procured | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Keringet | -0.506213, 35.697315 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2020 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2320356 | 92.8 | 2320356 | 2500000 | 179644 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not in operation.
3151 | Water and Sewerage Management | Rehabilitation of borehole | To rehabilitate borehole to restore functionality | Borehole rehabilitated | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Keringet | -0.447173, 35.704185 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2024 | 1300000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 1292141 | 99.4 | 1292141 | 1292141 | 7859 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Pump failure.
3152 | Water and Sewerage Management | Renovation Of Water Tank And Piping At Kapseger Water Project | To rehabilitate Water Tank And Piping At Kapseger Water Project to restore functionality | Water Tank And Piping At Kapseger Water Project rehabilitated | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Keringet | -0.499863, 35.733418 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2024 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 500000 | 100 | 500000 | 500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: Not yet started.
3153 | Water and Sewerage Management | Repair of Chebara water pump and accessories | To rehabilitate Chebara water pump and accessories to restore functionality | Chebara water pump and accessories rehabilitated | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Keringet | -0.471772, 35.683075 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2022 | 200000 | 0 | 200000 | Equitable | N/A | 200000 | 0 | 0 | 0 | 0 | 200000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
3154 | Water and Sewerage Management | Mugumoini Water Project-Equipping And Piping In Ndeffo | To implement mugumoini water project-equipping and piping in ndeffo for access to clean water and environmental sustainability | Mugumoini Water Project-Equipping And Piping In Ndeffo completed | 3110504 | Other Infrastructure and Civil Works | Njoro | Kihingo | -0.479294, 35.97843 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2023 | 2500000 | 39.05 | 39.05 | Equitable | N/A | 39.05 | 0 | 2499961 | 6401948.8 | 2499961 | 39 | -2499921.95 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Maintenance required.
3155 | Water and Sewerage Management | Cheptuech Spring Protection | To implement cheptuech spring protection for access to clean water and environmental sustainability | Cheptuech Spring Protection completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.59162 35.645365 2576.7 24.700000762939453 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 0 | 0 | 0 | 700000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: No. Viable: Viable but needs not met. Assessor remarks: Need concrete road for a permanent solution.
3156 | Water and Sewerage Management | Construction Of Table Tops And 10,000 Litre Water Tank At Sugutek Tea Buying Centre | To construct Table Tops And 10,000 Litre Water Tank At Sugutek Tea Buying Centre | Table Tops And 10,000 Litre Water Tank At Sugutek Tea Buying Centre constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.599537 35.609858 2621.7000000000003 7.800000190734863 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 381979 | 381979 | 381979 | Equitable | N/A | 381979 | 0 | 0 | 0 | 0 | 381979 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes, expected to meet the needs of the residents. Assessor remarks: Ongoing.
3157 | Water and Sewerage Management | Construction Of Water Harvesting Site And Pump House At Kiborowa Water Project And Solar Panels | To construct Water Harvesting Site And Pump House At Kiborowa Water Project And Solar Panels | Water Harvesting Site And Pump House At Kiborowa Water Project And Solar Panels constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.605202, 35.598687 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 3998496 | 199.9 | 3998496 | 2000000 | -1998496 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is good, well secured and functional.
3158 | Water and Sewerage Management | Desilting And Rehabilitation Of Chikamba Water Project | To implement desilting and rehabilitation of chikamba water project for access to clean water and environmental sustainability | Desilting And Rehabilitation Of Chikamba Water Project completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.561612 35.630047 2531.5 68.9000015258789 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 1797444 | 256.8 | 1797444 | 700000 | -1097444 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes, but didn't meet the needs. Assessor remarks: Not functional.
3159 | Water and Sewerage Management | Oromoit Water Project Construction Of Generator House | To implement oromoit water project construction of generator house for access to clean water and environmental sustainability | Oromoit Water Project Construction Of Generator House completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.590645 35.59291 2486.400146484375 50.5 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Stalled | 90 | N/A | Land Dispute | 2016 | N/A | N/A | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functions.
3160 | Water and Sewerage Management | Spring Protection And Piping At Oromoit Water Project | To implement spring protection and piping at oromoit water project for access to clean water and environmental sustainability | Spring Protection And Piping At Oromoit Water Project completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.500035 35.714295 2648.1 6.199999809265137 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 3998496 | 571.2 | 3998496 | 700000 | -3298496 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not operational.
3161 | Water and Sewerage Management | Spring Protection And Piping At Simotwet Water Project | To implement spring protection and piping at simotwet water project for access to clean water and environmental sustainability | Spring Protection And Piping At Simotwet Water Project completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.500035 35.714295 2648.1 6.199999809265137 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 3998496 | 399.8 | 3998496 | 1000000 | -2998496 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not operational.
3162 | Water and Sewerage Management | Desilting of Ogilgei dam | To implement desilting of ogilgei dam for access to clean water and environmental sustainability | Desilting of Ogilgei dam completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Kiptororo | -0.325895 35.49856 0 2599.9990234375 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | N/A | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 759293 | 30.4 | 759293 | 1592793 | 1740707 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yess. Viable: Yes. Assessor remarks: There some equipments but require,e.g fridge, outpatient screen,weight and height weighing scale,electricity installation,drip stand , mch seats and chairs.
3163 | Water and Sewerage Management | Solarization And Equipping And Piping Of Kongoi Water Project | To implement solarization and equipping and piping of kongoi water project for access to clean water and environmental sustainability | Solarization And Equipping And Piping Of Kongoi Water Project completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Kiptororo | -0.358042, 35.55575 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1492793 | 74.6 | 1492793 | 2000000 | 507207 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Ongoing.
3164 | Water and Sewerage Management | Rehabilitation Of Sewer Line At Shauri Yako | To rehabilitate Sewer Line At Shauri Yako to restore functionality | Sewer Line At Shauri Yako rehabilitated | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Kivumbini | -0.298813, 36.081315 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3031776 | 75.8 | 3031776 | 4000000 | 968224 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Improved sewerline.
3165 | Water and Sewerage Management | Completion Of Murunyu Water Project (Pump And Solar) | To complete Murunyu Water Project (Pump And Solar) | Murunyu Water Project (Pump And Solar) completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Lanet/Umoja | -0.265808, 36.166458 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2024/25 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 2000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes , very viable. Assessor remarks: Functional.
3166 | Water and Sewerage Management | Equiping of Murunyu Dispensary - Purchase Of 10000 Litres Water Tanks | To implement equiping of murunyu dispensary - purchase of 10000 litres water tanks for access to clean water and environmental sustainability | Equiping of Murunyu Dispensary - Purchase Of 10000 Litres Water Tanks completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Lanet/Umoja | -0.247441, 36.152691 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/1019 | 1869954 | 0 | 340755.05 | Equitable | N/A | 340755.05 | 0 | 42680 | 100 | 42680 | 340755 | -42680 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Tank is less than 10,000ltrs.
3167 | Water and Sewerage Management | Installation Of Pump And Purchase Of 10000 Litres Water Tank At Modern | To install Pump And Purchase Of 10000 Litres Water Tank At Modern | Pump And Purchase Of 10000 Litres Water Tank At Modern installed | 3110504 | Other Infrastructure and Civil Works | Bahati | Lanet/Umoja | -0.282202, 36.155693 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 1869954 | 340755.05 | 340755.05 | Equitable | N/A | 340755.05 | 0 | 1529199 | 448.8 | 1529199 | 340755 | -1188443.95 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
3168 | Water and Sewerage Management | Installation Of Water Pumps And Solar Panel At Kiamunyeki Water Project | To install Water Pumps And Solar Panel At Kiamunyeki Water Project | Water Pumps And Solar Panel At Kiamunyeki Water Project installed | 3110504 | Other Infrastructure and Civil Works | Bahati | Lanet/Umoja | -0.276553, 36.144895 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 1922411 | 1922411 | 1922411 | Equitable | N/A | 1922411 | 0 | 1845061 | 96 | 1845061 | 1922411 | 77350 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Not functioning.
3169 | Water and Sewerage Management | Construction Of Intake Structures For Ndurumoro Water Project | To construct Intake Structures For Ndurumoro Water Project | Intake Structures For Ndurumoro Water Project constructed | 3110504 | Other Infrastructure and Civil Works | Njoro | Lare | -0.474195, 36.052067 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2021 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 484996 | 97 | 484996 | 500000 | 15004 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Need renovation and more water provision in the area because it is inadequate..
3170 | Water and Sewerage Management | Construction Of A Manger And Supply Of 200 Meters Water Pipes | To construct A Manger And Supply Of 200 Meters Water Pipes | A Manger And Supply Of 200 Meters Water Pipes constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maai Mahiu | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 500000 | 495436 | 495436 | Equitable | N/A | 495436 | 0 | 0 | 0 | 0 | 495436 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
3171 | Water and Sewerage Management | Design And Construction Of Kijabe Water Intake (Monkey Corner) | To design and construct Kijabe Water Intake (Monkey Corner) | Kijabe Water Intake (Monkey Corner) designed and constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maai Mahiu | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 1500000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
3172 | Water and Sewerage Management | Equipping Of Borehole At Natooli Water Project | To equip Borehole At Natooli Water Project with necessary facilities and equipment | Borehole At Natooli Water Project equipped | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maiella | -0.824917 36.203913 0 400 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 584820 | 19.5 | 584820 | 3000000 | 2415180 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: Yes. Condition: Good. Objective met: Not Yet. Viable: Not Yet. Assessor remarks: Awaiting for the Supply of items by the contractor.
3173 | Water and Sewerage Management | Installation Of Water Pump At Tangi Tatu Water Project | To install Water Pump At Tangi Tatu Water Project | Water Pump At Tangi Tatu Water Project installed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maiella | -0.796872 36.250812 1882.2 6.900000095367432 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 695072 | 695072 | 695072 | Equitable | N/A | 695072 | 0 | 657778 | 94.6 | 657778 | 695072 | 37294 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Bad. Objective met: Not at all. Viable: Not at all. Contractor: Em Hech investment ltd.. Assessor remarks: Poorly done.
3174 | Water and Sewerage Management | Solar Panel Installation At Natooli Water Project | To implement solar panel installation at natooli water project for access to clean water and environmental sustainability | Solar Panel Installation At Natooli Water Project completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maiella | -0.796872 36.250812 1882.2 6.900000095367432 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | N/A | 3600000 | 3600000 | 3600000 | Equitable | N/A | 3600000 | 0 | 657778 | 18.3 | 657778 | 1600000 | 2942222 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Bad. Objective met: Not at all. Viable: Not at all. Contractor: Em Hech investment ltd.. Assessor remarks: Poorly done.
3175 | Water and Sewerage Management | Equipping Of Mlimani Borehole And Solarisation | To equip Mlimani Borehole And Solarisation with necessary facilities and equipment | Mlimani Borehole And Solarisation equipped | 3110504 | Other Infrastructure and Civil Works | Gilgil | Malewa West | -0.630631, 36.488697 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2023/24 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2500000 | 100 | 2500000 | 2500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
3176 | Water and Sewerage Management | Purchase And Installation Of Water Pump at Mulimani Borehole In Gatamaiyu | To procure and install Water Pump at Mulimani Borehole In Gatamaiyu | Water Pump at Mulimani Borehole In Gatamaiyu procured and installed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Malewa West | -0.648649, 36.488825 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2023/24 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 1500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
3177 | Water and Sewerage Management | Equipping and Piping of digital-Timbelion Water Project | To equip and Piping of digital-Timbelion Water Project with necessary facilities and equipment | And Piping of digital-Timbelion Water Project equipped | 3110504 | Other Infrastructure and Civil Works | Molo | Mariashoni | -0.355552, 35.814058 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/23 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3706316 | 92.7 | 3706316 | 293684 | 293684 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Piping supply to people.
3178 | Equipping and Solarization of Mukeo, Mahiga, Majimingi and Moraj Boreholes | Equipping and Solarization of Mukeo, Mahiga, Majimingi and Moraj Boreholes | To equip and Solarization of Mukeo, Mahiga, Majimingi and Moraj Boreholes with necessary facilities and equipment | And Solarization of Mukeo, Mahiga, Majimingi and Moraj Boreholes equipped | 3110504 | Other Infrastructure and Civil Works | Njoro | Mau Narok | -1.2841 36.8155 0 85955 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/23 | 15000000 | 15000000 | 15000000 | Equitable | N/A | 15000000 | 0 | 8158170 | 54.4 | 8158170 | 8158170 | 6841830 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: in good state of repair.
3179 | Water and Sewerage Management | Equipping Gatimu Borehole | To equip Gatimu Borehole with necessary facilities and equipment | Gatimu Borehole equipped | 3110504 | Other Infrastructure and Civil Works | Njoro | Mau Narok | -1.2841 36.8155 0 85955 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1261440 | 316606 | 316606 | Equitable | N/A | 316606 | 0 | 944834 | 298.4 | 944834 | 316606 | -628228 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: in good state of repair.
3180 | Construction Of A Weir Wall For Gravity Water Flow And Buying Of Pipes At Teret Sub Location Water Project | Construction Of A Weir Wall For Gravity Water Flow And Buying Of Pipes At Teret Sub Location Water Project | To construct A Weir Wall For Gravity Water Flow And Buying Of Pipes At Teret Sub Location Water Project | A Weir Wall For Gravity Water Flow And Buying Of Pipes At Teret Sub Location Water Project constructed | 3110504 | Other Infrastructure and Civil Works | Njoro | Mauche | -0.465378, 35.952084 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2018 | 2000000 | 7 | 7 | Equitable | N/A | 7 | 0 | 1999993 | 28571328.6 | 1999993 | 7 | -1999986 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Needs improvement.
3181 | Water and Sewerage Management | Expansion of intake and supply of steel and normal pipes for Kitoben Water Springs | To expand intake and supply of steel and normal pipes for Kitoben Water Springs to increase capacity | Intake and supply of steel and normal pipes for Kitoben Water Springs expanded | 3110504 | Other Infrastructure and Civil Works | Njoro | Mauche | -0.478383, 35.943668 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2024 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2954102 | 98.5 | 2954102 | 13746 | 45898 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Needs improvement.
3182 | Water and Sewerage Management | Installation Of Solar Panels at Kamungei Water Project | To install Solar Panels at Kamungei Water Project | Solar Panels at Kamungei Water Project installed | 3110504 | Other Infrastructure and Civil Works | Njoro | Mauche | -0.55395, 36.044742 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2023 | 2300000 | 2300000 | 2300000 | Equitable | N/A | 2300000 | 0 | 4881268 | 212.2 | 4881268 | 1300000 | -2581268 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
3183 | Water and Sewerage Management | Installation Of Solar Panels At Top Life Water Project | To install Solar Panels At Top Life Water Project | Solar Panels At Top Life Water Project installed | 3110504 | Other Infrastructure and Civil Works | Njoro | Mauche | -0.55395, 36.044742 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2023 | 5300000 | 418731.65 | 418731.65 | Equitable | N/A | 418731.65 | 0 | 4881268 | 1165.7 | 4881268 | 418732 | -4462536.35 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
3184 | Water and Sewerage Management | Solar Powered Installation Pump And Water Piping At Kiratina Borehole | To implement solar powered installation pump and water piping at kiratina borehole for access to clean water and environmental sustainability | Solar Powered Installation Pump And Water Piping At Kiratina Borehole completed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Menengai | -0.28519 36.122662 1848.699951171875 42.5 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
3185 | Water and Sewerage Management | Installation of solar panels at Kenyatta Phase I borehole | To install solar panels at Kenyatta Phase I borehole | Solar panels at Kenyatta Phase I borehole installed | 3110504 | Other Infrastructure and Civil Works | Molo | Molo | -0.208132 35.787935 0 699.9990234375 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 3016836 | 150.8 | 3016836 | 2000000 | -1016836 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Mafigah east African ltd. Assessor remarks: Good.
3186 | Water and Sewerage Management | Installation of Solar panels at Tayari Borehole | To install Solar panels at Tayari Borehole | Solar panels at Tayari Borehole installed | 3110504 | Other Infrastructure and Civil Works | Molo | Molo | -0.208132 35.787935 0 699.9990234375 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Mafigah east African ltd. Assessor remarks: Good.
3187 | Distilling Of Chesoin Dam And Piping | Distilling Of Chesoin Dam And Piping | To implement distilling of chesoin dam and piping for access to clean water and environmental sustainability | Distilling Of Chesoin Dam And Piping completed | 3110504 | Other Infrastructure and Civil Works | Molo | Molo Central | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 2910000 | 758.3 | 758.3 | Equitable | N/A | 758.3 | 0 | 14592200 | 1924330.7 | 14592200 | 0 | -14591441.7 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
3188 | Climate Change Resilience and County Energy Development | Fencing And Fixing A Metallic Gate At Migeremuka Borehole In Molo | To secure And Fixing A Metallic Gate At Migeremuka Borehole In Molo through fencing | And Fixing A Metallic Gate At Migeremuka Borehole In Molo fenced and secured | 3110504 | Other Infrastructure and Civil Works | Molo | Molo Central | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
3189 | Environmental Management | Purchase And Distribution Of Waste Litter Bins | To procure And Distribution Of Waste Litter Bins | And Distribution Of Waste Litter Bins procured | 3110504 | Other Infrastructure and Civil Works | Molo | Molo Central | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2020/21 | 2020/21 | 2100000 | 2100000 | 2100000 | Equitable | N/A | 2100000 | 0 | 2870026 | 136.7 | 2870026 | 27046 | -770026 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3190 | Water and Sewerage Management | Rehabilitation Of Tekek Water Intake And Tank | To rehabilitate Tekek Water Intake And Tank to restore functionality | Tekek Water Intake And Tank rehabilitated | 3110504 | Other Infrastructure and Civil Works | Molo | Molo Central | -0.695026, 36.480933 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2021/22 | 2997023 | 2997023 | 2997023 | Equitable | N/A | 2997023 | 0 | 2994378 | 99.9 | 2994378 | 945568 | 2645 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good work.
3191 | Water and Sewerage Management | Construction Of Water Tank And Laying Of Pipes At Boror,Nairobi And Mbama | To construct Water Tank And Laying Of Pipes At Boror,Nairobi And Mbama | Water Tank And Laying Of Pipes At Boror,Nairobi And Mbama constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Mosop | -0.250735 35.841887 2190.1 9.699999809265137 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1487442 | 74.4 | 1487442 | 2000000 | 512558 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Ndowfra ltd. Assessor remarks: Good work.
3192 | Water and Sewerage Management | Kerma Borehole - Purchase And Installation Of Pump And Water Piping | To implement kerma borehole - purchase and installation of pump and water piping for access to clean water and environmental sustainability | Kerma Borehole - Purchase And Installation Of Pump And Water Piping completed | 3110504 | Other Infrastructure and Civil Works | Rongai | Mosop | -0.314718, 35.970947 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2018 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2479575 | 99.2 | 2479575 | 2500000 | 20425 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Marileon. Assessor remarks: Good.
3193 | Water and Sewerage Management | Pumps And Piping At Ngecha B Water Project | To implement pumps and piping at ngecha b water project for access to clean water and environmental sustainability | Pumps And Piping At Ngecha B Water Project completed | 3110504 | Other Infrastructure and Civil Works | Rongai | Mosop | -0.318548, 35.973835 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | To be vired | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Viable but money was not enough. Contractor: Not indicated. Assessor remarks: Money vired.
3194 | Water and Sewerage Management | Ihindu Water Project Installation Of Pump And Solar Panels | To implement ihindu water project installation of pump and solar panels for access to clean water and environmental sustainability | Ihindu Water Project Installation Of Pump And Solar Panels completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Naivasha East | -0.842147, 36.561961 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1522836 | 76.1 | 1522836 | 2000000 | 477164 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: The project was not done.
3195 | Water and Sewerage Management | Solarization of Mwega Water Project | To implement solarization of mwega water project for access to clean water and environmental sustainability | Solarization of Mwega Water Project completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Naivasha East | -0.791138, 36.542388 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/23 | 4500000 | 4500000 | 4500000 | Equitable | N/A | 4500000 | 0 | 4497737 | 99.9 | 4497737 | 988356 | 2263 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Very successful project but require fencing.
3196 | Water and Sewerage Management | Equipping of Mzee Wanyama Borehole | To equip Mzee Wanyama Borehole with necessary facilities and equipment | Mzee Wanyama Borehole equipped | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Nakuru East | -0.36993, 36.149658 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/2023 | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 5902135 | 98.4 | 5902135 | 583422 | 97865 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Great rift general merchant. Assessor remarks: Project ok.
3197 | Water and Sewerage Management | Electricity Connection at Cheptoroi Borehole | To implement electricity connection at cheptoroi borehole for access to clean water and environmental sustainability | Electricity Connection at Cheptoroi Borehole completed | 3110504 | Other Infrastructure and Civil Works | Njoro | Nessuit | -0.393269 35.899167 2373.8199106296524 23.284765243530273 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: The toilet currently has cracks and poses a risk to the users. A new block should be constructed urgently.
3198 | Water and Sewerage Management | Equipping of Cheptoroi borehole | To equip Cheptoroi borehole with necessary facilities and equipment | Cheptoroi borehole equipped | 3110504 | Other Infrastructure and Civil Works | Njoro | Nessuit | -0.433936 35.919127 2591.218994140625 3.7899999618530273 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 1990109 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The funds drilled borehole, constructed control panel, 100,000 litre water tank and water kiosk..
3199 | Water and Sewerage Management | Installation Of A Pump, Construction Of Water Kiosk, Solar Panels And Piping At Kipkogo Borehole | To install A Pump, Construction Of Water Kiosk, Solar Panels And Piping At Kipkogo Borehole | A Pump, Construction Of Water Kiosk, Solar Panels And Piping At Kipkogo Borehole installed | 3110504 | Other Infrastructure and Civil Works | Njoro | Nessuit | -0.409844, 35.869773 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 1554958 | 38.9 | 1554958 | 4000000 | 2445042 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/S STARFIELD CONTRACTORS LIMITED. Assessor remarks: Water project is functional, piping was done to the main tank. Due to insufficient funds the contractor was not able to construct a water kiosk instead a water point was constructed..
3200 | Water and Sewerage Management | Installation Of A Pump, Construction Of Water Kiosk, Solar Panels And Piping At Tuei Borehole | To install A Pump, Construction Of Water Kiosk, Solar Panels And Piping At Tuei Borehole | A Pump, Construction Of Water Kiosk, Solar Panels And Piping At Tuei Borehole installed | 3110504 | Other Infrastructure and Civil Works | Njoro | Nessuit | -0.409844, 35.869773 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 2499739 | 62.5 | 2499739 | 4000000 | 1500261 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/S STARFIELD CONTRACTORS LIMITED. Assessor remarks: Water project is functional, piping was done to the main tank. Due to insufficient funds the contractor was not able to construct a water kiosk instead a water point was constructed..
3201 | Water and Sewerage Management | Installation of control panels/kiosks at the borehole site, construction of 100,000 litre capacity tank and construction of five water points at Tuei borehole | To install control panels/kiosks at the borehole site, construction of 100,000 litre capacity tank and construction of five water points at Tuei borehole | Control panels/kiosks at the borehole site, construction of 100,000 litre capacity tank and construction of five water points at Tuei borehole installed | 3110504 | Other Infrastructure and Civil Works | Njoro | Nessuit | -0.362587, 35.871741 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2023/24 | 6500000 | 6500000 | 6500000 | Equitable | N/A | 6500000 | 0 | 0 | 0 | 0 | 6292858 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Yes. Assessor remarks: Requires rehabilitation due to low volume of water output.
3202 | Water and Sewerage Management | Installation Of Solar Panels at Takitech Borehole (Solarisation) | To install Solar Panels at Takitech Borehole (Solarisation) | Solar Panels at Takitech Borehole (Solarisation) installed | 3110504 | Other Infrastructure and Civil Works | Njoro | Nessuit | -0.424891, 35.917451 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2024/25 | 4931746 | 4021803 | 4021803 | Equitable | N/A | 4021803 | 0 | 909943 | 22.6 | 909943 | 4021803 | 3111860 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: PATRIKA GENERAL ENTERPRISES. Assessor remarks: The money was initially for borehole solarization, the National government took over the project therefore the funds were redirected toward construction of 50,000M³ masonry tank and approximately 3km piping works.
3203 | Water and Sewerage Management | Rehabilitation of Chebtebes and Amani dams | To rehabilitate Chebtebes and Amani dams to restore functionality | Chebtebes and Amani dams rehabilitated | 3110504 | Other Infrastructure and Civil Works | Njoro | Nessuit | -0.424708 35.951331 2344.498779296875 9.62399959564209 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 1928105 | 0 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The contractor abandoned the two projects due to insufficient funds.
3204 | Water and Sewerage Management | Completion of a control Panel/ house, equipping and piping of Belbur borehole | To complete a control Panel/ house, equipping and piping of Belbur borehole | A control Panel/ house, equipping and piping of Belbur borehole completed | 3110504 | Other Infrastructure and Civil Works | Njoro | Njoro | -0.303659, 35.89102 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2020 | 4791102 | 4791102 | 4791102 | Equitable | N/A | 4791102 | 0 | 4588656 | 95.8 | 4588656 | 4588656 | 202446 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: Jecy Co Ltd. Assessor remarks: Lining to be done.
3205 | Water and Sewerage Management | Distillation And Expansion Of Piave Dams | To implement distillation and expansion of piave dams for access to clean water and environmental sustainability | Distillation And Expansion Of Piave Dams completed | 3110504 | Other Infrastructure and Civil Works | Njoro | Njoro | -0.332084 35.954071 2142.400146484375 15.730999946594238 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 3400000 | 3400000 | 3400000 | Equitable | N/A | 3400000 | 0 | 3388870 | 99.7 | 3388870 | 3400000 | 11130 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Humble touch designers. Assessor remarks: Well done understaking.
3206 | Water and Sewerage Management | Equipping Of Natu Borehole | To equip Natu Borehole with necessary facilities and equipment | Natu Borehole equipped | 3110504 | Other Infrastructure and Civil Works | Njoro | Njoro | -0.338884, 36.004589 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2019 | 1300000 | 305611 | 305611 | Equitable | N/A | 305611 | 0 | 305611 | 100 | 305611 | 305611 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Trizah logistics. Assessor remarks: In good state.
3207 | Water and Sewerage Management | Equipping, Solarization and Piping and purchase of water tank for borehole at Njokerio Dispensary | To implement equipping, solarization and piping and purchase of water tank for borehole at njokerio dispensary for access to clean water and environmental sustainability | Equipping, Solarization and Piping and purchase of water tank for borehole at Njokerio Dispensary completed | 3110504 | Other Infrastructure and Civil Works | Njoro | Njoro | -0.389818 35.931233 2298.1 6.099999904632568 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/23 | 2350423.7 | 0 | 5000000 | Equitable | N/A | 5000000 | 0 | 4706899 | 100 | 4706899 | 4706899 | -4706899 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good state.
3208 | Water and Sewerage Management | Provision of wayleave across the Railway Line for Rumwe Water Project | To implement provision of wayleave across the railway line for rumwe water project for access to clean water and environmental sustainability | Provision of wayleave across the Railway Line for Rumwe Water Project completed | 3110504 | Other Infrastructure and Civil Works | Njoro | Njoro | -0.296612 35.883503 2158.858642578125 11.8100004196167 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 1700000 | 0 | 1700000 | Equitable | N/A | 1700000 | 0 | 0 | 0 | 0 | 1700000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: Not available. Assessor remarks: Poor design of work.
3209 | Water and Sewerage Management | Completion of Equipping, Solarisation And Piping At Lulukwet Water Project | To complete Equipping, Solarisation And Piping At Lulukwet Water Project | Equipping, Solarisation And Piping At Lulukwet Water Project completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Nyota | -0.301692, 35.543018 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | - | 850089 | 850089 | 850089 | Equitable | N/A | 850089 | 0 | 600044 | 70.6 | 600044 | 71245 | 250045 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
3210 | Water and Sewerage Management | Equipping, Solarisation And Piping At Lulukwet Water Project | To implement equipping, solarisation and piping at lulukwet water project for access to clean water and environmental sustainability | Equipping, Solarisation And Piping At Lulukwet Water Project completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Nyota | -0.301692, 35.543018 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | - | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 4000000 | 100 | 4000000 | 4000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
3211 | Water and Sewerage Management | Equipping, Solarisation, Installation Of Pump And Piping At Seguton Water Project | To implement equipping, solarisation, installation of pump and piping at seguton water project for access to clean water and environmental sustainability | Equipping, Solarisation, Installation Of Pump And Piping At Seguton Water Project completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Nyota | -0.391423 35.716408 2718.2 14.399999618530273 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 5360191 | 89.3 | 5360191 | 6000000 | 639809 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: HOLSAN HOLDING LTD. Assessor remarks: Good.
3212 | Water and Sewerage Management | Equipping solarization, installation of pump and piping at Seguton Water Project | To equip solarization, installation of pump and piping at Seguton Water Project with necessary facilities and equipment | Solarization, installation of pump and piping at Seguton Water Project equipped | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Nyota | -0.391423 35.716408 2718.2 14.399999618530273 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 5360191 | 89.3 | 5360191 | 5360191 | 639809 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: HOLSAN HOLDING LTD. Assessor remarks: Good.
3213 | Water and Sewerage Management | Ongoing Temoyotta Water Project Pumping Unit, Pump House, Tank Renovation Piping And Power Connection) | To implement ongoing temoyotta water project pumping unit, pump house, tank renovation piping and power connection) for access to clean water and environmental sustainability | Ongoing Temoyotta Water Project Pumping Unit, Pump House, Tank Renovation Piping And Power Connection) completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Nyota | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | N/A | 2479793.48 | 2479793.48 | 2479793.48 | Equitable | N/A | 2479793.48 | 0 | 0 | 0 | 0 | 2479793 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
3214 | Water and Sewerage Management | Beautification and Landscaping at Kamere beach | To implement beautification and landscaping at kamere beach for access to clean water and environmental sustainability | Beautification and Landscaping at Kamere beach completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Olkaria | -0.815759, 36.322371 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 1500000 | 0 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: Yes. Viable: No. Contractor: Domestic enterprises and general supplies. Assessor remarks: The project needs more touch.
3215 | Environmental Management | Purchase and supply of dustbins | To procure and supply dustbins | Dustbins procured and supplied | 3110504 | Other Infrastructure and Civil Works | Naivasha | Olkaria | 0.837016, 36.366272 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 3000000 | 2999544 | 2999544 | Equitable | N/A | 2999544 | 0 | 2999544 | 100 | 2999544 | 2999544 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Dustbins majorly left in schools.
3216 | Water and Sewerage Management | Construction Of Sewer Line At Public Toilet In Pondamali | To construct Sewer Line At Public Toilet In Pondamali | Sewer Line At Public Toilet In Pondamali constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Rhonda | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 1248085 | 1248085 | 1248085 | Equitable | N/A | 1248085 | 0 | 0 | 0 | 0 | 1248085 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
3217 | Water and Sewerage Management | Desilting of Kapsirich dam | To implement desilting of kapsirich dam for access to clean water and environmental sustainability | Desilting of Kapsirich dam completed | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.021437, 36.075257 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/23 | 1300000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 1179082 | 90.7 | 1179082 | 0 | 120918 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is ok.
3218 | Water and Sewerage Management | Equipping of Majani Mingi Borehole, Kabarnet farm Water works and Morop water works | To equip Majani Mingi Borehole, Kabarnet farm Water works and Morop water works with necessary facilities and equipment | Majani Mingi Borehole, Kabarnet farm Water works and Morop water works equipped | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.05584, 36.02626 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | N/A | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 5164832 | 129.1 | 5164832 | 4000000 | -1164832 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Water table is low.
3219 | Water and Sewerage Management | Fencing and Installation of Gate at Kapsetek Dam | To secure and Installation of Gate at Kapsetek Dam through fencing | And Installation of Gate at Kapsetek Dam fenced and secured | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.081942, 35.871353 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | N/A | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 0 | 0 | 0 | 700000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Regular desilting of the dam recommended.
3220 | Lower Solai Water Project - Construction Of Water Reservoir And Piping Of Lower Solai Water Project | Lower Solai Water Project - Construction Of Water Reservoir And Piping Of Lower Solai Water Project | To implement lower solai water project - construction of water reservoir and piping of lower solai water project for access to clean water and environmental sustainability | Lower Solai Water Project - Construction Of Water Reservoir And Piping Of Lower Solai Water Project completed | 3110504 | Other Infrastructure and Civil Works | Rongai | Solai | 0.078187 36.194685 1926.3 18.100000381469727 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 631107 | 631107 | 631107 | Equitable | N/A | 631107 | 0 | 630663 | 99.9 | 630663 | 631107 | 444 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: arden. Assessor remarks: The contract was terminated/vyed.
3221 | Water and Sewerage Management | Renovation Of Chemasis Water Intake | To rehabilitate Chemasis Water Intake to restore functionality | Chemasis Water Intake rehabilitated | 3110504 | Other Infrastructure and Civil Works | Rongai | Solai | 0.176262, 36.176939 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2024 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 995268 | 99.5 | 995268 | 1000000 | 4732 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
3222 | Water and Sewerage Management | Installation Of Solar Panels At Arash Kirima Borehole | To install Solar Panels At Arash Kirima Borehole | Solar Panels At Arash Kirima Borehole installed | 3110504 | Other Infrastructure and Civil Works | Subukia | Subukia | -0.042468 36.190708 2287.6 7.300000190734863 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 643491 | 32.2 | 643491 | 2000000 | 1356509 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: M/s kameja enterprises limited. Assessor remarks: Good condition.
3223 | Water and Sewerage Management | Purchase And Installation Of Edgewood Borehole Solar Panels | To procure and install Edgewood Borehole Solar Panels | Edgewood Borehole Solar Panels procured and installed | 3110504 | Other Infrastructure and Civil Works | Subukia | Subukia | -0.017333, 36.198352 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 11/03/2020 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1996662 | 99.8 | 1996662 | 2000000 | 3338 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes.. Viable: Yes the project was successful.. Contractor: Information not available. Assessor remarks: Good work with the panels.
3224 | Water and Sewerage Management | Purchase And Installation Of Hydrum Pump, Sola Panels And Piping At Gawasu Water Project | To procure and install Hydrum Pump, Sola Panels And Piping At Gawasu Water Project | Hydrum Pump, Sola Panels And Piping At Gawasu Water Project procured and installed | 3110504 | Other Infrastructure and Civil Works | Subukia | Subukia | -0.031385 36.202473 2223.800048828125 12.100000381469727 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2997632 | 99.9 | 2997632 | 3000000 | 2368 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: Borehole already drilled and capped. The water tank and equipping yet to be done..
3225 | Water and Sewerage Management | Purchase And Installation Of Morro Borehole Solar Panels | To procure and install Morro Borehole Solar Panels | Morro Borehole Solar Panels procured and installed | 3110504 | Other Infrastructure and Civil Works | Subukia | Subukia | -0.017333, 36.198352 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 11/03/2020 | 2000000 | 112.3 | 112.3 | Equitable | N/A | 112.3 | 0 | 1999888 | 1780844.2 | 1999888 | 112 | -1999775.7 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes.. Viable: Yes the project was successful.. Contractor: Information not available. Assessor remarks: Good work with the panels.
3226 | Water and Sewerage Management | Purchase And Installation Of Plastic Garbage Bins In Subukia | To procure and install Plastic Garbage Bins In Subukia | Plastic Garbage Bins In Subukia procured and installed | 3110504 | Other Infrastructure and Civil Works | Subukia | Subukia | 0.002948 36.229185 1993.0999755859375 52.52199935913086 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 674464 | 674464 | 674464 | Equitable | N/A | 674464 | 0 | 637536 | 94.5 | 637536 | 674464 | 36928 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: The business community and road users are enjoying the service. Security improved.s.
3227 | Water and Sewerage Management | Installation Of Marwa Borehole Pump | To install Marwa Borehole Pump | Marwa Borehole Pump installed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Tinet | -0.445126 35.609035 0 2200 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 710717 | 71.1 | 710717 | 1000000 | 289283 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: Yes but not meet the need. Assessor remarks: Converted to staff quarters.
3228 | Water and Sewerage Management | Completion of valley water project solarization and piping | To complete valley water project solarization and piping | Valley water project solarization and piping completed | 3110504 | Other Infrastructure and Civil Works | Molo | Turi | -0.27073, 35.756647 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 3079231 | 307.9 | 3079231 | 950543 | -2079231 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
3229 | Water and Sewerage Management | Construction Of 50M3 Tank At Mkorombosi | To construct 50M3 Tank At Mkorombosi | 50M3 Tank At Mkorombosi constructed | 3110504 | Other Infrastructure and Civil Works | Molo | Turi | -0.330793, 35.753182 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 900000 | 900000 | 900000 | Equitable | N/A | 900000 | 0 | 891023 | 99 | 891023 | 900000 | 8977 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: People are happy with the project.
3230 | Water and Sewerage Management | Fencing Of Giteru Water Project Works Land | To secure Giteru Water Project Works Land through fencing | Giteru Water Project Works Land fenced and secured | 3110504 | Other Infrastructure and Civil Works | Molo | Turi | -0.268917, 35.775012 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 572465 | 95.4 | 572465 | 498589 | 27535 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Well done.
3231 | Water and Sewerage Management | Ndenderu A Water Project Solarization and Piping | To implement ndenderu a water project solarization and piping for access to clean water and environmental sustainability | Ndenderu A Water Project Solarization and Piping completed | 3110504 | Other Infrastructure and Civil Works | Molo | Turi | -0.30944, 35.74908 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/23 | 3000000 | 3000000 | 3400000 | Equitable | N/A | 3400000 | 0 | 3079231 | 102.6 | 3079231 | 143550 | -79231 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No, it would have been met if it was equipped. Viable: No. Assessor remarks: The borehole was only drilled but was never equipped.
3232 | Water and Sewerage Management | Ngenia water project solarization and piping at Mona center | To implement ngenia water project solarization and piping at mona center for access to clean water and environmental sustainability | Ngenia water project solarization and piping at Mona center completed | 3110504 | Other Infrastructure and Civil Works | Molo | Turi | -0.284958 35.743667 2557.7000000000003 9.600000381469727 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/23 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1949800 | 97.5 | 1949800 | 50067 | 50200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yea. Viable: Yes. Assessor remarks: In good condition.
3233 | Water and Sewerage Management | Purchase of Water Pump and power connection for Valley Water Project | To procure Water Pump and power connection for Valley Water Project | Water Pump and power connection for Valley Water Project procured | 3110504 | Other Infrastructure and Civil Works | Molo | Turi | -0.270993, 35.75597 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 1400000 | 1400000 | 1400000 | Equitable | N/A | 1400000 | 0 | 797936 | 57 | 797936 | 1400000 | 602064 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good working condition. Piping is not fully complete.
3234 | Water and Sewerage Management | Supply Of Water Pipes For Ndenderu A Farm | To implement supply of water pipes for ndenderu a farm for access to clean water and environmental sustainability | Supply Of Water Pipes For Ndenderu A Farm completed | 3110504 | Other Infrastructure and Civil Works | Molo | Turi | -0.306118, 35.750638 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | N/A | 480000 | 480000 | 480000 | Equitable | N/A | 480000 | 0 | 1499906 | 312.5 | 1499906 | 480000 | -1019906 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
3235 | Water and Sewerage Management | Construction Of Water Intake And Piping At Surutia Water Project | To construct Water Intake And Piping At Surutia Water Project | Water Intake And Piping At Surutia Water Project constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Visoi | -0.112228 35.887368 1817.7 20.799999237060547 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 1500000 | 1448144 | 1448144 | Equitable | N/A | 1448144 | 0 | 1448144 | 100 | 1448144 | 1448144 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
3236 | Water and Sewerage Management | Rehabilitation Of Burgei Borehole | To rehabilitate Burgei Borehole to restore functionality | Burgei Borehole rehabilitated | 3110504 | Other Infrastructure and Civil Works | Rongai | Visoi | -0.149943 35.881463 1841.6 9.300000190734863 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 1400000 | 1284290 | 1284290 | Equitable | N/A | 1284290 | 0 | 1265104 | 98.5 | 1265104 | 1284290 | 19186 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Very good.
3237 | Water and Sewerage Management | Connection Of Water To CCCR Residential Houses | To implement connection of water to cccr residential houses for access to clean water and environmental sustainability | Connection Of Water To CCCR Residential Houses completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Viwandani | -0.711889, 36.43651 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1500000 | 100 | 1500000 | 1500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: No. Assessor remarks: Not started.
3238 | Water and Sewerage Management | Construction of a melting kiln at Komokomo County Council | To construct a melting kiln at Komokomo County Council | A melting kiln at Komokomo County Council constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Viwandani | -0.711889, 36.43651 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: No. Assessor remarks: Not started.
3239 | Water and Sewerage Management | Rehabilitation Of Sewer In Naivasha Town CBD | To rehabilitate Sewer In Naivasha Town CBD to restore functionality | Sewer In Naivasha Town CBD rehabilitated | 3110504 | Other Infrastructure and Civil Works | Naivasha | Viwandani | -0.71773 36.433963 1895.0999755859375 44.172000885009766 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 4500000 | 4498816.4 | 4498816.4 | Equitable | N/A | 4498816.4 | 0 | 0 | 0 | 0 | 4498816 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Assessor remarks: Operational.
3240 | Water and Sewerage Management | Construction Of Intake, Pipeline And Storage Tank At Upendo, Kianoe, Kirima -Water Works | To construct Intake, Pipeline And Storage Tank At Upendo, Kianoe, Kirima -Water Works | Intake, Pipeline And Storage Tank At Upendo, Kianoe, Kirima -Water Works constructed | 3110504 | Other Infrastructure and Civil Works | Subukia | Waseges | 0.080873 36.244899 0 20.445999145507812 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2500000 | 512.95 | 512.95 | Equitable | N/A | 512.95 | 0 | 2499487 | 487276.9 | 2499487 | 513 | -2498974.05 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
3241 | Water and Sewerage Management | Construction Of Intake,Storage Tank And Piping Of Sugutek Water Project | To construct Intake,Storage Tank And Piping Of Sugutek Water Project | Intake,Storage Tank And Piping Of Sugutek Water Project constructed | 3110504 | Other Infrastructure and Civil Works | Subukia | Waseges | 0.146943 36.2423 1696.7 18.299999237060547 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2000000 | 955 | 955 | Equitable | N/A | 955 | 0 | 1999045 | 209324.1 | 1999045 | 639 | -1998090 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Construction is Ongoing.
3242 | Water and Sewerage Management | Design And Construction Of Intake Pump, Installation Of Solar Panels, Pumping Machines, Piping And Repair Of Storage Tank Of Kasi Water Project | To design and construct Intake Pump, Installation Of Solar Panels, Pumping Machines, Piping And Repair Of Storage Tank Of Kasi Water Project | Intake Pump, Installation Of Solar Panels, Pumping Machines, Piping And Repair Of Storage Tank Of Kasi Water Project designed and constructed | 3110504 | Other Infrastructure and Civil Works | Subukia | Waseges | 0.126515 36.265512 1675.1 8.600000381469727 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1995163 | 1995163 | 1995163 | Equitable | N/A | 1995163 | 0 | 1995163 | 100 | 1995163 | 1995163 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The toilets are in use.
3243 | Water and Sewerage Management | Design, Rehabilitation Of Intake, Piping And Construction Of Storage Tank Of Berur Water Project | To implement design, rehabilitation of intake, piping and construction of storage tank of berur water project for access to clean water and environmental sustainability | Design, Rehabilitation Of Intake, Piping And Construction Of Storage Tank Of Berur Water Project completed | 3110504 | Other Infrastructure and Civil Works | Subukia | Waseges | 0.126515 36.265512 1675.1 8.600000381469727 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2494757 | 99.8 | 2494757 | 2500000 | 5243 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The toilets are in use.
3244 | Water and Sewerage Management | Gathiini Gustion Shallow Wells - Excavation And Digging Of Gathiini Shallows Well | To implement gathiini gustion shallow wells - excavation and digging of gathiini shallows well for access to clean water and environmental sustainability | Gathiini Gustion Shallow Wells - Excavation And Digging Of Gathiini Shallows Well completed | 3110504 | Other Infrastructure and Civil Works | Subukia | Waseges | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | N/A | 1198073.52 | 1198073.52 | 1198073.52 | Equitable | N/A | 1198073.52 | 0 | 0 | 0 | 0 | 1198074 | 0 | Stalled | 0 | N/A | Residents Prefer Borehole instead of shallow wells and hence require Additional funding | 2017 | N/A | N/A | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Project stalled. Reason: Residents Prefer Borehole instead of shallow wells and hence require Additional funding.
3245 | Water and Sewerage Management | Installation of Solar Panel at Kahawa Borehole in Wiyumiririe | To install Solar Panel at Kahawa Borehole in Wiyumiririe | Solar Panel at Kahawa Borehole in Wiyumiririe installed | 3110504 | Other Infrastructure and Civil Works | Subukia | Waseges | 0.12653 36.26655 1759.5 10.600000381469727 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 450442 | 22.5 | 450442 | 2000000 | 1549558 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs maintenance.
3246 | Water and Sewerage Management | Installation Of Solar Panel, Equipping And Pumping Machiness At Wei Borehole Water Project | To install Solar Panel, Equipping And Pumping Machiness At Wei Borehole Water Project | Solar Panel, Equipping And Pumping Machiness At Wei Borehole Water Project installed | 3110504 | Other Infrastructure and Civil Works | Subukia | Waseges | 0.116735 36.274342 1803.2 9.800000190734863 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 3500000 | 186.6 | 186.6 | Equitable | N/A | 186.6 | 0 | 3499813 | 1875569.7 | 3499813 | 187 | -3499626.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Maintenance.
3247 | Environmental Management | Climate Change Mitigation Programme (1% Of Equitable Development) | To implement climate change mitigation programme (1% of equitable development) for access to clean water and environmental sustainability | Climate Change Mitigation Programme (1% Of Equitable Development) completed | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 32240723 | 32240723 | 25240723 | N/A | N/A | 25240723 | 0 | 0 | 0 | 0 | 33312923 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
3248 | Environmental Management | Nyayo Gardens - Rehabilitation Of Nyayo Gardens (Ongoing 2017/18) | To implement nyayo gardens - rehabilitation of nyayo gardens (ongoing 2017/18) for access to clean water and environmental sustainability | Nyayo Gardens - Rehabilitation Of Nyayo Gardens (Ongoing 2017/18) completed | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 6957806 | 255930.75 | 255930.75 | N/A | N/A | 255930.75 | 0 | 20000000 | 7814.6 | 20000000 | 8000000 | -19744069.25 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3249 | Water and Sewerage Management | Bush Clearing And Road Rehabilitation Through Kazi Mtaani | To improve the condition of And Road Rehabilitation Through Kazi Mtaani | And Road Rehabilitation Through Kazi Mtaani improved | 3110599 | Other Infrastructure and Civil Works | Njoro | Kihingo | -0.474192 35.992925 2289.7 13.357000350952148 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 4000000 | 3968376 | 3968376 | Equitable | N/A | 3968376 | 0 | 3968376 | 100 | 3968376 | 3968376 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires maintenance.
3250 | Water and Sewerage Management | Bush Clearing And Road Rehabilitation Through Kazi Mtaani | To improve the condition of And Road Rehabilitation Through Kazi Mtaani | And Road Rehabilitation Through Kazi Mtaani improved | 3110599 | Other Infrastructure and Civil Works | Njoro | Mauche | -0.538202 35.986685 2491.3999999999996 12.800000190734863 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 3926860 | 98.2 | 3926860 | 0 | 73140 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Don't know. Assessor remarks: Need improvement.
3251 | Water and Sewerage Management | Fabrication Of Waste Skip Loader | To implement fabrication of waste skip loader for access to clean water and environmental sustainability | Fabrication Of Waste Skip Loader completed | 3110799 | N/A | HQ | HQ | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 4970000 | 99.4 | 4970000 | 5000000 | 30000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3252 | Water and Sewerage Management | Procurement Of Waste Trolleys 100 No. | To procure and supply Waste Trolleys 100 No | Waste Trolleys 100 No procured and supplied | 3110799 | N/A | HQ | HQ | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999758 | 100 | 999758 | 1000000 | 242 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3253 | Water and Sewerage Management | Purchase Of 5No. Skips | To procure 5No. Skips | 5No. Skips procured | 3110799 | N/A | HQ | HQ | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2018/19 | 2018/19 | 1900000 | 1900000 | 1900000 | Equitable | N/A | 1900000 | 0 | 2494000 | 131.3 | 2494000 | 1900000 | -594000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3254 | Water and Sewerage Management | Purchase Of A Skips (Waste Collection Unit) | To procure A Skips (Waste Collection Unit) | A Skips (Waste Collection Unit) procured | 3110799 | N/A | Kuresoi South | Keringet | -0.426622, 35.692727 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2022 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 700000 | 140 | 700000 | 500000 | -200000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In use.
3255 | Environmental Management | Purchase of Air Quality Test Kit | To procure Air Quality Test Kit | Air Quality Test Kit procured | 3111107 | Purchase of Laboratory Equipment | HQ | HQ | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2022/23 | N/A | 2000000 | 1000000 | 1000000 | N/A | N/A | 1000000 | 0 | 2994169 | 299.4 | 2994169 | 1000000 | -1994169 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
3256 | Water and Sewerage Management | Purchase Of Terrameter (1 No.) | To procure Terrameter (1 No.) | Terrameter (1 No.) procured | 3111107 | Purchase of Laboratory Equipment | HQ | HQ | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | N/A | 8000000 | 2200000 | 1000000 | Equitable | N/A | 1000000 | 0 | 5800000 | 263.6 | 5800000 | 1000000 | -3600000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
3257 | Water and Sewerage Management | Purchase of Anti-chlorine Machine at Kapnandi borehole | To procure Anti-chlorine Machine at Kapnandi borehole | Anti-chlorine Machine at Kapnandi borehole procured | 3111120 | Purchase of Specialized Plant. - | Nakuru West | Kapkures | -0.31982, 36.022104 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | 2022/23 | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 2917562 | 972.5 | 2917562 | 300000 | -2617562 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/S SAGIT GLOBAL LTD. Assessor remarks: completed and functional.
3258 | Water and Sewerage Management | Purchase of skip Bins for Heshima and Maili Sita Markets | To procure skip Bins for Heshima and Maili Sita Markets | Skip Bins for Heshima and Maili Sita Markets procured | 3111120 | Purchase of Specialized Plant. - | Bahati | Kiamaina | -0.24492, 36.112947 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | N/A | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | -1000000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires additional one.
3259 | Water and Sewerage Management | Servicing Of Tractor In Environment | To implement servicing of tractor in environment for access to clean water and environmental sustainability | Servicing Of Tractor In Environment completed | 3111201 | Overhaul of Plant, Machinery and Equipment | Molo | Elburgon | -0.308342 35.807555 2442.7 11.300000190734863 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 400000 | 1100 | 1100 | Equitable | N/A | 1100 | 0 | 398900 | 36263.6 | 398900 | 1100 | -397800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Project operational.
3260 | Water and Sewerage Management | Roofing And Renovation Of Kahuho Tank | To implement roofing and renovation of kahuho tank for access to clean water and environmental sustainability | Roofing And Renovation Of Kahuho Tank completed | 3111299 | Rehabilitation & Renovation - | Gilgil | Elementaita | -0.553538, 36.112757 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 700000 | 700000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1489746 | 212.8 | 1489746 | 700000 | -789746 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
3261 | Water and Sewerage Management | Repair Of 2 Water Tanks In Kiamunyeki | To rehabilitate 2 Water Tanks In Kiamunyeki to restore functionality | 2 Water Tanks In Kiamunyeki rehabilitated | 3111299 | Rehabilitation & Renovation - | Bahati | Lanet/Umoja | -0.283645, 36.150508 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 4100 | 4100 | Equitable | N/A | 4100 | 0 | 1995900 | 48680.5 | 1995900 | 4100 | -1991800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional but the repaired tank is not functional due to leakages.
3262 | Water and Sewerage Management | Repairing Of Kiamunyeki Borehole | To implement repairing of kiamunyeki borehole for access to clean water and environmental sustainability | Repairing Of Kiamunyeki Borehole completed | 3111299 | Rehabilitation & Renovation - | Bahati | Lanet/Umoja | -0.280414, 36.158421 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2021/22 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes ,but has land disputes. Assessor remarks: Has land dispute, borehole covered with sand.
3263 | Water and Sewerage Management | Tree Nursery Seedlings | To implement tree nursery seedlings for access to clean water and environmental sustainability | Tree Nursery Seedlings completed | 3111305 | Beautification and Tree Planting | Nakuru West | Barut | -0.3654 36.05454 0 2000 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 400000 | 400000 | 400000 | Equitable | N/A | 400000 | 0 | 398300 | 99.6 | 398300 | 400000 | 1700 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: GREAT RIFT GENERAL MERCHANTS. Assessor remarks: Completed.
3264 | Environmental Management | Climate Change Mitigation And Adaptation (Tree Growing) | To implement climate change mitigation and adaptation (tree growing) for access to clean water and environmental sustainability | Climate Change Mitigation And Adaptation (Tree Growing) completed | 3111305 | Beautification and Tree Planting | HQ | HQ | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 5000000 | 2550 | 2550 | N/A | N/A | 2550 | 0 | 4997450 | 195978.4 | 4997450 | 2550 | -4994900 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3265 | Water and Sewerage Management | Kabazi Ward Greening And Beautitification - Tree Planting And Beautification Of Kabazi Ward | To implement kabazi ward greening and beautitification - tree planting and beautification of kabazi ward for access to clean water and environmental sustainability | Kabazi Ward Greening And Beautitification - Tree Planting And Beautification Of Kabazi Ward completed | 3111305 | Beautification and Tree Planting | Subukia | Kabazi | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2017/18 | 2017/18 | 2017/18 | 1500000 | 501021 | 501021 | Equitable | N/A | 501021 | 0 | 485500 | 96.9 | 485500 | 501021 | 15521 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3266 | Water and Sewerage Management | Planting Trees To Rehabilitate River Ndarugu | To implement planting trees to rehabilitate river ndarugu for access to clean water and environmental sustainability | Planting Trees To Rehabilitate River Ndarugu completed | 3111305 | Beautification and Tree Planting | Nakuru West | Kaptembwo | -0.311443 36.059645 1781.5999755859375 4.184999942779541 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 159493 | 159493 | Equitable | N/A | 159493 | 0 | 1840507 | 1154 | 1840507 | 159493 | -1681014 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: U193. Assessor remarks: Not yet levellized.
3267 | Water and Sewerage Management | Purchase And Supply Of Tree Seedlings | To procure and supply Tree Seedlings | Tree Seedlings procured and supplied | 3111305 | Beautification and Tree Planting | Njoro | Kihingo | -0.433932 35.972208 2278.2001953125 27.77400016784668 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 983325 | 98.3 | 983325 | 1000000 | 16675 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Market construction ongoing.
3268 | Water and Sewerage Management | Tree Seedlings For Kihingo Ward | To implement tree seedlings for kihingo ward for access to clean water and environmental sustainability | Tree Seedlings For Kihingo Ward completed | 3111305 | Beautification and Tree Planting | Njoro | Kihingo | -0.443013 35.969212 2274.8 8.800000190734863 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 2500 | 2500 | Equitable | N/A | 2500 | 0 | 997500 | 39900 | 997500 | 2500 | -995000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Requires fencing, levelling and installation of goalposts.
3269 | Water and Sewerage Management | Acquisition Of Tree Seedlings In Kiptororo Ward | To procure Tree Seedlings In Kiptororo Ward | Tree Seedlings In Kiptororo Ward procured | 3111305 | Beautification and Tree Planting | Kuresoi North | Kiptororo | -0.377203 35.505747 0 800 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2018/19 | 2018/19 | 2018/19 | 1140886.7 | 1051.7 | 1051.7 | Equitable | N/A | 1051.7 | 0 | 1139835 | 108380.2 | 1139835 | 1052 | -1138783.3 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The bridge was constructed but no gurd rails.
3270 | Water and Sewerage Management | Purchase And Supply Of Tree Seedlings | To procure and supply Tree Seedlings | Tree Seedlings procured and supplied | 3111305 | Beautification and Tree Planting | Kuresoi North | Kiptororo | -0.302609 35.529464 2597.6 28.100000381469727 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1966860 | 98.3 | 1966860 | 3228 | 33140 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Routine maintenance and spot improvement is required.
3271 | Water and Sewerage Management | Tree Planting At Namuncha Water Catchments | To implement tree planting at namuncha water catchments for access to clean water and environmental sustainability | Tree Planting At Namuncha Water Catchments completed | 3111305 | Beautification and Tree Planting | Naivasha | Maai Mahiu | -1.062633, 36.549497 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 998176 | 99.8 | 998176 | 998176 | 1824 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good for environmental conservation.
3272 | Water and Sewerage Management | Tree Planitng At Namucha Water Catchment | To implement tree planitng at namucha water catchment for access to clean water and environmental sustainability | Tree Planitng At Namucha Water Catchment completed | 3111305 | Beautification and Tree Planting | Naivasha | Maai Mahiu | -1.062633, 36.549497 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 998176 | 99.8 | 998176 | 1000000 | 1824 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good for environmental conservation.
3273 | Water and Sewerage Management | Tree Planting At Kijabe Water Catchments | To implement tree planting at kijabe water catchments for access to clean water and environmental sustainability | Tree Planting At Kijabe Water Catchments completed | 3111305 | Beautification and Tree Planting | Naivasha | Maai Mahiu | -1.062633, 36.549497 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 970000 | 970000 | Equitable | N/A | 970000 | 0 | 970000 | 100 | 970000 | 970000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good for environmental conservation.
3274 | Water and Sewerage Management | Purchase Of Tree Seedlings | To procure Tree Seedlings | Tree Seedlings procured | 3111305 | Beautification and Tree Planting | Njoro | Njoro | -0.305133 35.915642 2158.858642578125 27.304000854492188 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 2400000 | 43747 | 43747 | Equitable | N/A | 43747 | 0 | 2356253 | 5386.1 | 2356253 | 43747 | -2312506 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Mamenyi Solutions. Assessor remarks: In good state.
3275 | Water and Sewerage Management | Beautification And Landscaping At Kamere Beach | To implement beautification and landscaping at kamere beach for access to clean water and environmental sustainability | Beautification And Landscaping At Kamere Beach completed | 3111305 | Beautification and Tree Planting | Naivasha | Olkaria | -0.815759, 36.322371 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2021/22 | 2021/22 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 1500000 | 0 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: Yes. Viable: No. Contractor: Domestic enterprises and general supplies. Assessor remarks: The project needs more touch.
3276 | Water and Sewerage Management | Climate Change Mitigation (Planting Trees) In 2 Schools-Olkaria And Narasha Primary | To implement climate change mitigation (planting trees) in 2 schools-olkaria and narasha primary for access to clean water and environmental sustainability | Climate Change Mitigation (Planting Trees) In 2 Schools-Olkaria And Narasha Primary completed | 3111305 | Beautification and Tree Planting | Naivasha | Olkaria | -0.918725, 36.267243 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499793 | 100 | 1499793 | 1500000 | 207 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The trees dried up due to harsh weather.
3277 | Water and Sewerage Management | Purchase of Tree Seedlings for Farmers | To procure Tree Seedlings for Farmers | Tree Seedlings for Farmers procured | 3111305 | Beautification and Tree Planting | Kuresoi North | Sirikwa | -0.249192 35.682062 2664.4 19.399999618530273 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2022/23 | 2022/23 | N/A | 1303187 | 1303187 | 1303187 | Equitable | N/A | 1303187 | 0 | 1176780 | 90.3 | 1176780 | 0 | 126407 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: No land purchased.
3278 | Water and Sewerage Management | Supply Of Indigenous Tree Seedlings | To implement supply of indigenous tree seedlings for access to clean water and environmental sustainability | Supply Of Indigenous Tree Seedlings completed | 3111399 | Purchase. of Certified Seeds - Ot | Kuresoi North | Kiptororo | -0.406703 35.561853 0 800 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | 2019/20 | 1900000 | 3227.5 | 3227.5 | Equitable | N/A | 3227.5 | 0 | 1896773 | 58769.1 | 1896773 | 3228 | -1893545.5 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Requires renovation.
3279 | Water and Sewerage Management | Purchase Of Waste Disposal Sites(Waste Transfer Stations) | To procure Waste Disposal Sites(Waste Transfer Stations) | Waste Disposal Sites(Waste Transfer Stations) procured | 3130101 | Acquisition of Land | HQ | HQ | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2019/20 | 2019/20 | N/A | 15000000 | 1387000 | 1387000 | N/A | N/A | 1387000 | 0 | 13613000 | 981.5 | 13613000 | 1387000 | -12226000 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
3280 | Water and Sewerage Management | Purchase Of Land And Drilling Of New Ingobor Borehole And Equipping | To acquire land for And Drilling Of New Ingobor Borehole And Equipping | Land for And Drilling Of New Ingobor Borehole And Equipping acquired | 3130101 | Acquisition of Land | Nakuru West | Kapkures | -0.306306, 36.018533 | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2016/17 | 2016/17 | 2016/17 | 2437096.6 | 5255.6 | 5255.6 | Equitable | N/A | 5255.6 | 0 | 2431841 | 46271.4 | 2431841 | 5256 | -2426585.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Improved access to clean water. Assessor remarks: Completed and operational.
3281 | Water and Sewerage Management | Purchase of Tree Seeds across the ward - Eburru Mbaruk Ward | To procure Tree Seeds across the ward - Eburru Mbaruk Ward | Tree Seeds across the ward - Eburru Mbaruk Ward procured | 4130299 | N/A | HQ | HQ | N/A | 4572 | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | WATER, ENVIRONMENT, ENERGY AND NATURAL RESOURCES | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 922425 | 100 | 922425 | 0 | -922425 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3282 | County Debt Management (as per the County Medium Term Debt Management Strategy Paper) | County Debt Management (as per the County Medium Term Debt Management Strategy Paper) | To implement county debt management (as per the county medium term debt management strategy paper) for improved service delivery | County Debt Management (as per the County Medium Term Debt Management Strategy Paper) completed | 2211314 | Write Offs/ Bad Debt Expenses from Previous Years (Pending Bills) | HQ | HQ | -0.173672, 35.862823 | 4573 | COUNTY ASSEMBLY OF NAKURU | COUNTY ASSEMBLY OF NAKURU | N/A | 2022/23 | 2022/23 | 2022/23 | 15000000 | 15000000 | 15000000 | N/A | N/A | 15000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3283 | Debt Management (outstanding legal fees) | Debt Management (outstanding legal fees) | To implement debt management (outstanding legal fees) for improved service delivery | Debt Management (outstanding legal fees) completed | 2211314 | Write Offs/ Bad Debt Expenses from Previous Years (Pending Bills) | HQ | HQ | -0.173672, 35.862823 | 4573 | COUNTY ASSEMBLY OF NAKURU | COUNTY ASSEMBLY OF NAKURU | N/A | 2021/22 | 2021/22 | 2021/22 | 15853014 | 853014 | 853014 | N/A | N/A | 853014 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3284 | Completion of the Office Block II (chambers) - project variation | Completion of the Office Block II (chambers) - project variation | To complete the Office Block II (chambers) - project variation | The Office Block II (chambers) - project variation completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | -0.173672, 35.862823 | 4573 | COUNTY ASSEMBLY OF NAKURU | COUNTY ASSEMBLY OF NAKURU | N/A | 2022/23 | 2022/23 | 2022/23 | 40000000 | 40000000 | 40000000 | N/A | N/A | 40000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3285 | Construction of Ward Office | Construction of Ward Office | To construct Ward Office | Ward Office constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | -0.173672, 35.862823 | 4573 | COUNTY ASSEMBLY OF NAKURU | COUNTY ASSEMBLY OF NAKURU | N/A | 2023/24 | 2023/24 | 2023/24 | 36995247 | 79000000 | 67687447 | N/A | N/A | 67687447 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3286 | Design and construction of Ward Offices | Design and construction of Ward Offices | To design and construct Ward Offices | Ward Offices designed and constructed | 3110299 | Construction of Buildings - Ot | HQ | HQ | -0.173672, 35.862823 | 4573 | COUNTY ASSEMBLY OF NAKURU | COUNTY ASSEMBLY OF NAKURU | N/A | 2022/23 | 2022/23 | 2022/23 | 27000000 | 5000000 | 2000000 | N/A | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3287 | Completion of Office Block | Completion of Office Block | To complete Office Block | Office Block completed | 3110302 | Refurbishment of Non-Residential Buildings | HQ | HQ | -0.173672, 35.862823 | 4573 | COUNTY ASSEMBLY OF NAKURU | COUNTY ASSEMBLY OF NAKURU | N/A | 2021/22 | 2021/22 | 2021/22 | 4173827.9 | 4173828 | 4173828 | N/A | N/A | 4173828 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3288 | Completion of the Phase II office Block | Completion of the Phase II office Block | To complete the Phase II office Block | The Phase II office Block completed | 3110302 | Refurbishment of Non-Residential Buildings | HQ | HQ | -0.173672, 35.862823 | 4573 | COUNTY ASSEMBLY OF NAKURU | COUNTY ASSEMBLY OF NAKURU | N/A | 2021/22 | 2021/22 | 2021/22 | 91700000 | 26729215.15 | 16729215.15 | N/A | N/A | 16729215.15 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3289 | Construction of Phase II Block and Consultancy | Construction of Phase II Block and Consultancy | To construct Phase II Block and Consultancy | Phase II Block and Consultancy constructed | 3110302 | Refurbishment of Non-Residential Buildings | HQ | HQ | -0.173672, 35.862823 | 4573 | COUNTY ASSEMBLY OF NAKURU | COUNTY ASSEMBLY OF NAKURU | N/A | 2021/22 | 2021/22 | 2021/22 | 10025725 | 10025725 | 10025725 | N/A | N/A | 10025725 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3290 | Refurbishment of buildings (Repair and civil works) and cabro works | Refurbishment of buildings (Repair and civil works) and cabro works | To implement refurbishment of buildings (repair and civil works) and cabro works for improved service delivery | Refurbishment of buildings (Repair and civil works) and cabro works completed | 3110302 | Refurbishment of Non-Residential Buildings | HQ | HQ | -0.173672, 35.862823 | 4573 | COUNTY ASSEMBLY OF NAKURU | COUNTY ASSEMBLY OF NAKURU | N/A | 2022/23 | 2022/23 | 2022/23 | 9000000 | 9000000 | 7000000 | N/A | N/A | 7000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3291 | Refurbishment of Buildings | Refurbishment of Buildings | To implement refurbishment of buildings for improved service delivery | Refurbishment of Buildings completed | 3110302 | Refurbishment of Non-Residential Buildings | HQ | HQ | -0.173672, 35.862823 | 4573 | COUNTY ASSEMBLY OF NAKURU | COUNTY ASSEMBLY OF NAKURU | N/A | 2021/22 | 2021/22 | 2021/22 | 391034 | 4516.6 | 4516.6 | N/A | N/A | 4516.6 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3292 | Refurbishment of Hansard Equipment | Refurbishment of Hansard Equipment | To implement refurbishment of hansard equipment for improved service delivery | Refurbishment of Hansard Equipment completed | 3110302 | Refurbishment of Non-Residential Buildings | HQ | HQ | -0.173672, 35.862823 | 4573 | COUNTY ASSEMBLY OF NAKURU | COUNTY ASSEMBLY OF NAKURU | N/A | 2019/20 | 2019/20 | 2019/20 | 40028000 | 131685.3 | 131685.3 | N/A | N/A | 131685.3 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3293 | Refurbishment/Maintenance of buildings | Refurbishment/Maintenance of buildings | To implement refurbishment/maintenance of buildings for improved service delivery | Refurbishment/Maintenance of buildings completed | 3110302 | Refurbishment of Non-Residential Buildings | HQ | HQ | -0.173672, 35.862823 | 4573 | COUNTY ASSEMBLY OF NAKURU | COUNTY ASSEMBLY OF NAKURU | N/A | 2023/24 | 2023/24 | 2023/24 | 8542869 | 0 | 8542869 | N/A | N/A | 8542869 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3294 | Refurbishment of Buildings | Refurbishment of Buildings | To implement refurbishment of buildings for improved service delivery | Refurbishment of Buildings completed | 3110399 | Refurbishment of Buildgs - Oth | HQ | HQ | -0.173672, 35.862823 | 4573 | COUNTY ASSEMBLY OF NAKURU | COUNTY ASSEMBLY OF NAKURU | N/A | 2023/24 | 2023/24 | 2023/24 | 6700000 | 0 | 7666205 | N/A | N/A | 7666205 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3295 | Refurbishment of existing buildings, provision of disability access - ramps, lifts, and other related facilities | Refurbishment of existing buildings, provision of disability access - ramps, lifts, and other related facilities | To implement refurbishment of existing buildings, provision of disability access - ramps, lifts, and other related facilities for improved service delivery | Refurbishment of existing buildings, provision of disability access - ramps, lifts, and other related facilities completed | 3110399 | Refurbishment of Buildgs - Oth | HQ | HQ | -0.173672, 35.862823 | 4573 | COUNTY ASSEMBLY OF NAKURU | COUNTY ASSEMBLY OF NAKURU | N/A | 2021/22 | 2021/22 | 2021/22 | 21032762 | 25190171.7 | 12032530.7 | N/A | N/A | 12032530.7 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3296 | Design and construction of Acceleration Lane | Design and construction of Acceleration Lane | To design and construct Acceleration Lane | Acceleration Lane designed and constructed | 3110499 | Construction of Roads - Other | HQ | HQ | -0.173672, 35.862823 | 4573 | COUNTY ASSEMBLY OF NAKURU | COUNTY ASSEMBLY OF NAKURU | N/A | 2022/23 | 2022/23 | 2022/23 | 3000000 | 10000000 | 10000000 | N/A | N/A | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3297 | Borehole drilling at executive residence and solarization | Borehole drilling at executive residence and solarization | To provide access to clean water through borehole drilling at executive residence and solarization | Borehole drilled at executive residence and solarization | 3110502 | Water Supplies and Sewerage | HQ | HQ | -0.173672, 35.862823 | 4573 | COUNTY ASSEMBLY OF NAKURU | COUNTY ASSEMBLY OF NAKURU | N/A | 2023/24 | 2023/24 | 2023/24 | 10500000 | 0 | 10500000 | N/A | N/A | 10500000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3298 | Pump installation and solarization at county assembly borehole | Pump installation and solarization at county assembly borehole | To implement pump installation and solarization at county assembly borehole for improved service delivery | Pump installation and solarization at county assembly borehole completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | -0.173672, 35.862823 | 4573 | COUNTY ASSEMBLY OF NAKURU | COUNTY ASSEMBLY OF NAKURU | N/A | 2023/24 | 2023/24 | 2023/24 | 3650000 | 0 | 3650000 | N/A | N/A | 3650000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3299 | Completion of Public Gallery | Completion of Public Gallery | To complete Public Gallery | Public Gallery completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4573 | COUNTY ASSEMBLY OF NAKURU | COUNTY ASSEMBLY OF NAKURU | N/A | 2021/22 | 2021/22 | 2021/22 | 329742 | 329742.8 | 329742.8 | N/A | N/A | 329742.8 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3300 | Construction of members offices | Construction of members offices | To construct members offices | Members offices constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4573 | COUNTY ASSEMBLY OF NAKURU | COUNTY ASSEMBLY OF NAKURU | N/A | 2023/24 | 2023/24 | 2023/24 | 45000000 | 0 | 45000000 | N/A | N/A | 45000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3301 | Construction of perimeter wall and installation of CCTV cameras | Construction of perimeter wall and installation of CCTV cameras | To construct perimeter wall and installation of CCTV cameras | Perimeter wall and installation of CCTV cameras constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4573 | COUNTY ASSEMBLY OF NAKURU | COUNTY ASSEMBLY OF NAKURU | N/A | 2022/23 | 2022/23 | 2022/23 | 12000000 | 8500000 | 8500000 | N/A | N/A | 8500000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3302 | Construction of Perimeter wall / security gate at the Rear | Construction of Perimeter wall / security gate at the Rear | To construct Perimeter wall / security gate at the Rear | Perimeter wall / security gate at the Rear constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4573 | COUNTY ASSEMBLY OF NAKURU | COUNTY ASSEMBLY OF NAKURU | N/A | 2021/22 | 2021/22 | 2021/22 | 10000000 | 590850 | 590850 | N/A | N/A | 590850 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3303 | Construction of underground parking | Construction of underground parking | To construct underground parking | Underground parking constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4573 | COUNTY ASSEMBLY OF NAKURU | COUNTY ASSEMBLY OF NAKURU | N/A | 2024/25 | 2024/25 | 2024/25 | 125000000 | 125000000 | 25000000 | N/A | N/A | 25000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3304 | Driveway / cabro paving | Driveway / cabro paving | To implement driveway / cabro paving for improved service delivery | Driveway / cabro paving completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4573 | COUNTY ASSEMBLY OF NAKURU | COUNTY ASSEMBLY OF NAKURU | N/A | 2021/22 | 2021/22 | 2021/22 | 5000000 | 2208000 | 2208000 | N/A | N/A | 2208000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3305 | Equipping and Configuration of the Chamber | Equipping and Configuration of the Chamber | To equip and Configuration of the Chamber with necessary facilities and equipment | And Configuration of the Chamber equipped | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4573 | COUNTY ASSEMBLY OF NAKURU | COUNTY ASSEMBLY OF NAKURU | N/A | 2021/22 | 2021/22 | 2021/22 | 25000000 | 2502980 | 2502980 | N/A | N/A | 2502980 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3306 | Landscaping of Speakers House | Landscaping of Speakers House | To implement landscaping of speakers house for improved service delivery | Landscaping of Speakers House completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4573 | COUNTY ASSEMBLY OF NAKURU | COUNTY ASSEMBLY OF NAKURU | N/A | 2021/22 | 2021/22 | 2021/22 | 15000000 | 15000000 | 15000000 | N/A | N/A | 15000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3307 | Purchase and installation of a water treatment plant | Purchase and installation of a water treatment plant | To procure and install a water treatment plant | A water treatment plant procured and installed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4573 | COUNTY ASSEMBLY OF NAKURU | COUNTY ASSEMBLY OF NAKURU | N/A | 2020/21 | 2020/21 | 2020/21 | 5000000 | 142306.4 | 142306.4 | N/A | N/A | 142306.4 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3308 | Security Installation works at Executive Residence | Security Installation works at Executive Residence | To implement security installation works at executive residence for improved service delivery | Security Installation works at Executive Residence completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4573 | COUNTY ASSEMBLY OF NAKURU | COUNTY ASSEMBLY OF NAKURU | N/A | 2022/23 | 2022/23 | 2022/23 | 12000000 | 3000000 | 2320100 | N/A | N/A | 2320100 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3309 | Solarization and Power Upgrade of the Assembly lighting system. | Solarization and Power Upgrade of the Assembly lighting system. | To implement solarization and power upgrade of the assembly lighting system. for improved service delivery | Solarization and Power Upgrade of the Assembly lighting system. completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4573 | COUNTY ASSEMBLY OF NAKURU | COUNTY ASSEMBLY OF NAKURU | N/A | 2022/23 | 2022/23 | 2022/23 | 5000000 | 6500000 | 5000000 | N/A | N/A | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3310 | Completion of Speakers Residence (landscaping, civil works and electricals) | Completion of Speakers Residence (landscaping, civil works and electricals) | To complete Speakers Residence (landscaping, civil works and electricals) | Speakers Residence (landscaping, civil works and electricals) completed | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4573 | COUNTY ASSEMBLY OF NAKURU | COUNTY ASSEMBLY OF NAKURU | N/A | 2022/23 | 2022/23 | 2022/23 | 15000000 | 15000000 | 8619025 | N/A | N/A | 8619025 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3311 | Proposed construction of the gate and associated civil works (Executive residence) | Proposed construction of the gate and associated civil works (Executive residence) | To undertake the proposed construction of the gate and associated civil works (Executive residence) | Proposed construction of the gate and associated civil works (Executive residence) implemented | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4573 | COUNTY ASSEMBLY OF NAKURU | COUNTY ASSEMBLY OF NAKURU | N/A | 2022/23 | 2022/23 | 2022/23 | 4683250 | 4683250 | 8662214 | N/A | N/A | 8662214 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3312 | Hansard Improvement Phase II | Hansard Improvement Phase II | To implement hansard improvement phase ii for improved service delivery | Hansard Improvement Phase II completed | 3111111 | Purchase of ICT networking and Communications Equipment | HQ | HQ | -0.173672, 35.862823 | 4573 | COUNTY ASSEMBLY OF NAKURU | COUNTY ASSEMBLY OF NAKURU | N/A | 2022/23 | 2022/23 | 2022/23 | 22000000 | 27000000 | 33380975 | N/A | N/A | 33380975 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3313 | Structured cabling and Hansard Improvement Phase II | Structured cabling and Hansard Improvement Phase II | To implement structured cabling and hansard improvement phase ii for improved service delivery | Structured cabling and Hansard Improvement Phase II completed | 3111111 | Purchase of ICT networking and Communications Equipment | HQ | HQ | -0.173672, 35.862823 | 4573 | COUNTY ASSEMBLY OF NAKURU | COUNTY ASSEMBLY OF NAKURU | N/A | 2022/23 | 2022/23 | 2022/23 | 22000000 | 0 | 7226005.6 | N/A | N/A | 7226005.6 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3314 | Purchase and installation of water packaging plants | Purchase and installation of water packaging plants | To procure and install water packaging plants | Water packaging plants procured and installed | 3111120 | Purchase of Specialized Plant. - | HQ | HQ | -0.173672, 35.862823 | 4573 | COUNTY ASSEMBLY OF NAKURU | COUNTY ASSEMBLY OF NAKURU | N/A | 2022/23 | 2022/23 | 2022/23 | 7000000 | 7000000 | 2000000 | N/A | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3315 | Design and Consultancy for the construction of Basement Parking and Members Offices | Design and Consultancy for the construction of Basement Parking and Members Offices | To implement design and consultancy for the construction of basement parking and members offices for improved service delivery | Design and Consultancy for the construction of Basement Parking and Members Offices completed | 3111401 | Pre-Feasibility, Feasibility & Appraisal Studies | HQ | HQ | -0.173672, 35.862823 | 4573 | COUNTY ASSEMBLY OF NAKURU | COUNTY ASSEMBLY OF NAKURU | N/A | 2023/24 | 2024/25 | 2024/25 | 20000000 | 40000000 | 41652244 | N/A | N/A | 41652244 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3316 | Development of the Strategic Plan | Development of the Strategic Plan | To develop the Strategic Plan | The Strategic Plan developed | 3111403 | Research | HQ | HQ | -0.173672, 35.862823 | 4573 | COUNTY ASSEMBLY OF NAKURU | COUNTY ASSEMBLY OF NAKURU | N/A | 2021/22 | 2021/22 | 2021/22 | 3000000 | 2926200 | 2926200 | N/A | N/A | 2926200 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3317 | General Administration, Planning and Support Services | PSTD Outstanding Contract Retention - development | To implement pstd outstanding contract retention - development for improved service delivery | PSTD Outstanding Contract Retention - development completed | 2211314 | Write Offs/ Bad Debt Expenses from Previous Years (Pending Bills) | HQ | HQ | N/A | 4574 | PUBLIC SERVICE TRAINING AND DEVOLUTION | PUBLIC SERVICE TRAINING AND DEVOLUTION | N/A | 2022/23 | 2022/23 | N/A | 2002976.4 | 2002976.4 | 2002976.4 | N/A | N/A | 2002976.4 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
3318 | Administration, Planning and Support Services | Construction of Administration office in Kuresoi North Sub County Office | To construct Administration office in Kuresoi North Sub County Office | Administration office in Kuresoi North Sub County Office constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4574 | PUBLIC SERVICE TRAINING AND DEVOLUTION | PUBLIC SERVICE TRAINING AND DEVOLUTION | N/A | 2021/22 | 2021/22 | N/A | 8000000 | 7500000 | 7500000 | N/A | N/A | 7500000 | 0 | 4165126 | 55.5 | 4165126 | 7500000 | 3334874 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
3319 | General Administration, Planning and Support Services | Construction of Sub County Administration office in Rongai Sub County | To construct Sub County Administration office in Rongai Sub County | Sub County Administration office in Rongai Sub County constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4574 | PUBLIC SERVICE TRAINING AND DEVOLUTION | PUBLIC SERVICE TRAINING AND DEVOLUTION | N/A | 2021/22 | 2021/22 | N/A | 8000000 | 7106210 | 7106210 | N/A | N/A | 7106210 | 0 | 4165126 | 58.6 | 4165126 | 2941084 | 2941084 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
3320 | Administration, Planning and Support Services | Construction of Ward Offices in Gilgil Sub County | To construct Ward Offices in Gilgil Sub County | Ward Offices in Gilgil Sub County constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4574 | PUBLIC SERVICE TRAINING AND DEVOLUTION | PUBLIC SERVICE TRAINING AND DEVOLUTION | N/A | 2021/22 | 2021/22 | N/A | 5000000 | 4236750 | 4236750 | N/A | N/A | 4236750 | 0 | 1659800 | 39.2 | 1659800 | 1659800 | 2576950 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
3321 | Administration, Planning and Support Services | Construction of Ward Offices in Kuresoi North Sub County | To construct Ward Offices in Kuresoi North Sub County | Ward Offices in Kuresoi North Sub County constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4574 | PUBLIC SERVICE TRAINING AND DEVOLUTION | PUBLIC SERVICE TRAINING AND DEVOLUTION | N/A | 2021/22 | 2021/22 | N/A | 5000000 | 5000000 | 5000000 | N/A | N/A | 5000000 | 0 | 4629722 | 92.6 | 4629722 | 4984660 | 370278 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
3322 | Administration, Planning and Support Services | Construction of Ward Offices in Kuresoi South Sub County | To construct Ward Offices in Kuresoi South Sub County | Ward Offices in Kuresoi South Sub County constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4574 | PUBLIC SERVICE TRAINING AND DEVOLUTION | PUBLIC SERVICE TRAINING AND DEVOLUTION | N/A | 2021/22 | 2021/22 | N/A | 5000000 | 4984660 | 4984660 | N/A | N/A | 4984660 | 0 | 4629722 | 92.9 | 4629722 | 4984660 | 354938 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
3323 | Administration, Planning and Support Services | Construction of Ward Offices in Molo Sub County | To construct Ward Offices in Molo Sub County | Ward Offices in Molo Sub County constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4574 | PUBLIC SERVICE TRAINING AND DEVOLUTION | PUBLIC SERVICE TRAINING AND DEVOLUTION | N/A | 2021/22 | 2021/22 | N/A | 5000000 | 4500000 | 4500000 | N/A | N/A | 4500000 | 0 | 2483870 | 55.2 | 2483870 | 2483870 | 2016130 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
3324 | Administration, Planning and Support Services | Construction of Ward Offices in Njoro Sub County | To construct Ward Offices in Njoro Sub County | Ward Offices in Njoro Sub County constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4574 | PUBLIC SERVICE TRAINING AND DEVOLUTION | PUBLIC SERVICE TRAINING AND DEVOLUTION | N/A | 2021/22 | 2021/22 | N/A | 5000000 | 4484600 | 4484600 | N/A | N/A | 4484600 | 0 | 4533975 | 101.1 | 4533975 | 4484600 | -49375 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
3325 | General Administration, Planning and Support Services | Construction at Lakeview Ward Offices | To construct at Lakeview Ward Offices | At Lakeview Ward Offices constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Lakeview | -0.728859, 36.438146 | 4574 | PUBLIC SERVICE TRAINING AND DEVOLUTION | PUBLIC SERVICE TRAINING AND DEVOLUTION | N/A | 2022/23 | 2022/23 | N/A | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No.
3326 | General Administration, Planning and Support Services | Construction of toilets, connection of electricity, fencing and equipping of Ward administration office in Elementaita ward | To construct toilets, connection of electricity, fencing and equipping of Ward administration office in Elementaita ward | Toilets, connection of electricity, fencing and equipping of Ward administration office in Elementaita ward constructed | 3110302 | Refurbishment of Non-Residential Buildings | HQ | HQ | N/A | 4574 | PUBLIC SERVICE TRAINING AND DEVOLUTION | PUBLIC SERVICE TRAINING AND DEVOLUTION | N/A | 2021/22 | 2021/22 | N/A | 3500000 | 3488950 | 3488950 | N/A | N/A | 3488950 | 0 | 2933955 | 84.1 | 2933955 | 554995 | 554995 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
3327 | General Administration, Planning and Support Services | Refurbishment of HQ Offices | To implement refurbishment of hq offices for improved service delivery | Refurbishment of HQ Offices completed | 3110302 | Refurbishment of Non-Residential Buildings | HQ | HQ | N/A | 4574 | PUBLIC SERVICE TRAINING AND DEVOLUTION | PUBLIC SERVICE TRAINING AND DEVOLUTION | N/A | 2021/22 | 2021/22 | N/A | 2891950 | 1997400 | 1997400 | N/A | N/A | 1997400 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
3328 | General Administration, Planning and Support Services | Refurbishment of Molo Sub County Headquarters Offices | To implement refurbishment of molo sub county headquarters offices for improved service delivery | Refurbishment of Molo Sub County Headquarters Offices completed | 3110302 | Refurbishment of Non-Residential Buildings | HQ | HQ | N/A | 4574 | PUBLIC SERVICE TRAINING AND DEVOLUTION | PUBLIC SERVICE TRAINING AND DEVOLUTION | N/A | 2021/22 | 2021/22 | N/A | 1000000 | 1000000 | 1000000 | N/A | N/A | 1000000 | 0 | 969861 | 97 | 969861 | 0 | 30139 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
3329 | General Administration, Planning and Support Services | Construction of perimeter wall around Ward Administrator's office and gate | To construct perimeter wall around Ward Administrator's office and gate | Perimeter wall around Ward Administrator's office and gate constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Barut | -0.3232 36.05452 0 2000 | 4574 | PUBLIC SERVICE TRAINING AND DEVOLUTION | PUBLIC SERVICE TRAINING AND DEVOLUTION | N/A | 2022/23 | 2022/23 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 491540 | 16.4 | 491540 | 2993450 | 2508460 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: MAJESTIC E.A LTDMAJESTIC E.A LTD. Assessor remarks: Completed.
3330 | County Coordination of Policy formulation | Construction of a fence in Tinet Ward Office | To construct a fence in Tinet Ward Office | A fence in Tinet Ward Office constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4574 | PUBLIC SERVICE TRAINING AND DEVOLUTION | PUBLIC SERVICE TRAINING AND DEVOLUTION | N/A | 2021/22 | 2021/22 | 2021/22 | 500000 | 500000 | 500000 | N/A | N/A | 500000 | 0 | 2483870 | 496.8 | 2483870 | 2483870 | -1983870 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3331 | County Coordination of Policy formulation | Construction of fence in Kuresoi North Sub County Headquarters | To construct fence in Kuresoi North Sub County Headquarters | Fence in Kuresoi North Sub County Headquarters constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4574 | PUBLIC SERVICE TRAINING AND DEVOLUTION | PUBLIC SERVICE TRAINING AND DEVOLUTION | N/A | 2021/22 | 2021/22 | N/A | 1500000 | 1500000 | 1500000 | N/A | N/A | 1500000 | 0 | 4629722 | 308.6 | 4629722 | 4984660 | -3129722 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
3332 | County Coordination of Policy formulation | Construction of toilets in Sirikwa and Nyota Ward Offices | To construct toilets in Sirikwa and Nyota Ward Offices | Toilets in Sirikwa and Nyota Ward Offices constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4574 | PUBLIC SERVICE TRAINING AND DEVOLUTION | PUBLIC SERVICE TRAINING AND DEVOLUTION | N/A | 2021/22 | 2021/22 | 2021/22 | 1400000 | 1400000 | 1400000 | N/A | N/A | 1400000 | 0 | 2800000 | 200 | 2800000 | 2800000 | -1400000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3333 | County Coordination of Policy formulation | Construction of toilets in Tinet Ward Office | To construct toilets in Tinet Ward Office | Toilets in Tinet Ward Office constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4574 | PUBLIC SERVICE TRAINING AND DEVOLUTION | PUBLIC SERVICE TRAINING AND DEVOLUTION | N/A | 2021/22 | 2021/22 | 2021/22 | 700000 | 700000 | 700000 | N/A | N/A | 700000 | 0 | 2483870 | 354.8 | 2483870 | 2483870 | -1783870 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3334 | Co-ordination of Disaster Management and Humanitarian Assistance | Fencing of Mosop Ward Administrator office | To secure Mosop Ward Administrator office through fencing | Mosop Ward Administrator office fenced and secured | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4574 | PUBLIC SERVICE TRAINING AND DEVOLUTION | PUBLIC SERVICE TRAINING AND DEVOLUTION | N/A | 2021/22 | 2021/22 | N/A | 400000 | 400000 | 400000 | N/A | N/A | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
3335 | General Administration, Planning and Support Services | Fencing and installation of gate at Kabatini Ward Administrator’s Offices | To secure and installation of gate at Kabatini Ward Administrator’s Offices through fencing | And installation of gate at Kabatini Ward Administrator’s Offices fenced and secured | 3110504 | Other Infrastructure and Civil Works | Bahati | Kabatini | -0.215433 36.164478 2027.0999755859375 70.4209976196289 | 4574 | PUBLIC SERVICE TRAINING AND DEVOLUTION | PUBLIC SERVICE TRAINING AND DEVOLUTION | N/A | 2022/23 | 2022/23 | 2022/23 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 971300 | 97.1 | 971300 | 971300 | 28700 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Great rift general merchants. Assessor remarks: Good and Operational.
3336 | Administration, Planning and Support Services | Equipping of kiamaina ward office (purchase of a printer and preparation of ward projects bonchures | To equip kiamaina ward office (purchase of a printer and preparation of ward projects bonchures with necessary facilities and equipment | Kiamaina ward office (purchase of a printer and preparation of ward projects bonchures equipped | 3110504 | Other Infrastructure and Civil Works | Bahati | Kiamaina | -0.231543, 36.116893 | 4574 | PUBLIC SERVICE TRAINING AND DEVOLUTION | PUBLIC SERVICE TRAINING AND DEVOLUTION | N/A | 2020/21 | 2020/21 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No.
3337 | General Administration, Planning and Support Services | Fencing of ward admin block | To secure ward admin block through fencing | Ward admin block fenced and secured | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Rhonda | -0.313599, 36.067283 | 4574 | PUBLIC SERVICE TRAINING AND DEVOLUTION | PUBLIC SERVICE TRAINING AND DEVOLUTION | N/A | 2020/21 | 2020/21 | 20/21 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1269272 | 84.6 | 1269272 | 1500000 | 230728 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Worksman international CO. LTD.
3338 | General Administration, Planning and Support Services | Construction of a pit latrine at Ward Administrator's Office | To construct a pit latrine at Ward Administrator's Office | A pit latrine at Ward Administrator's Office constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Barut | -0.324324, 36.054632 | 4574 | PUBLIC SERVICE TRAINING AND DEVOLUTION | PUBLIC SERVICE TRAINING AND DEVOLUTION | N/A | 2022/23 | 2022/23 | 2022 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 491540 | 98.3 | 491540 | 2993450 | 8460 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: PIKVIRD SUPPLIES.
3339 | Administration, Planning and Support Services | Equipping of Ward Administrator's Office (desktop computer, printing machine) | To equip Ward Administrator's Office (desktop computer, printing machine) with necessary facilities and equipment | Ward Administrator's Office (desktop computer, printing machine) equipped | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Rhonda | -0.313607, 36.067215 | 4574 | PUBLIC SERVICE TRAINING AND DEVOLUTION | PUBLIC SERVICE TRAINING AND DEVOLUTION | N/A | 2021/22 | 2021/22 | Not indicated | 341407 | 341407 | 341407 | Equitable | N/A | 341407 | 0 | 341407 | 100 | 341407 | 80950 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes. Contractor: Not indicated.
3340 | Administration, Planning and Support Services | Construction of Ward Offices in Gilgil Sub County | To construct Ward Offices in Gilgil Sub County | Ward Offices in Gilgil Sub County constructed | 4130299 | N/A | HQ | HQ | N/A | 4574 | PUBLIC SERVICE TRAINING AND DEVOLUTION | PUBLIC SERVICE TRAINING AND DEVOLUTION | N/A | 2019/20 | 2019/20 | 2019/20 | 4369535 | 1659800 | 1659800 | N/A | N/A | 1659800 | 0 | 1659800 | 100 | 1659800 | 1659800 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3341 | Administration, Planning and Support Services | Construction of Ward Offices in Lanet Umoja in Sub County | To construct Ward Offices in Lanet Umoja in Sub County | Ward Offices in Lanet Umoja in Sub County constructed | 4130299 | N/A | HQ | HQ | N/A | 4574 | PUBLIC SERVICE TRAINING AND DEVOLUTION | PUBLIC SERVICE TRAINING AND DEVOLUTION | N/A | 2019/20 | 2019/20 | 2019/20 | 4629722 | 1692600 | 1692600 | N/A | N/A | 1692600 | 0 | 1692600 | 100 | 1692600 | 1692600 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3342 | Administration, Planning and Support Services | Construction of Ward Offices in Molo Sub County | To construct Ward Offices in Molo Sub County | Ward Offices in Molo Sub County constructed | 4130299 | N/A | HQ | HQ | N/A | 4574 | PUBLIC SERVICE TRAINING AND DEVOLUTION | PUBLIC SERVICE TRAINING AND DEVOLUTION | N/A | 2019/20 | 2019/20 | 2019/20 | 4789015 | 2483870 | 2483870 | N/A | N/A | 2483870 | 0 | 2483870 | 100 | 2483870 | 2483870 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3343 | Administration, Planning and Support Services | Construction of Ward Offices in Nakuru West Sub County | To construct Ward Offices in Nakuru West Sub County | Ward Offices in Nakuru West Sub County constructed | 4130299 | N/A | HQ | HQ | N/A | 4574 | PUBLIC SERVICE TRAINING AND DEVOLUTION | PUBLIC SERVICE TRAINING AND DEVOLUTION | N/A | 2019/20 | 2019/20 | 2019/20 | 4629722 | 4629722 | 4629722 | N/A | N/A | 4629722 | 0 | 4629722 | 100 | 4629722 | 4629722 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3344 | Administration, Planning and Support Services | Construction of Ward Offices in Njoro Sub County | To construct Ward Offices in Njoro Sub County | Ward Offices in Njoro Sub County constructed | 4130299 | N/A | HQ | HQ | N/A | 4574 | PUBLIC SERVICE TRAINING AND DEVOLUTION | PUBLIC SERVICE TRAINING AND DEVOLUTION | N/A | 2019/20 | 2019/20 | N/A | 4533975 | 4533975 | 4533975 | N/A | N/A | 4533975 | 0 | 4533975 | 100 | 4533975 | 4484600 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
3345 | Administration, Planning and Support Services | Construction of Ward Offices in Rongai Sub County | To construct Ward Offices in Rongai Sub County | Ward Offices in Rongai Sub County constructed | 4130299 | N/A | HQ | HQ | N/A | 4574 | PUBLIC SERVICE TRAINING AND DEVOLUTION | PUBLIC SERVICE TRAINING AND DEVOLUTION | N/A | 2019/20 | 2019/20 | 2019/20 | 4499130 | 1569650 | 1569650 | N/A | N/A | 1569650 | 0 | 1569650 | 100 | 1569650 | 1569650 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3346 | Administration, Planning and Support Services | Construction of Ward Offices in Subukia Sub County | To construct Ward Offices in Subukia Sub County | Ward Offices in Subukia Sub County constructed | 4130299 | N/A | HQ | HQ | N/A | 4574 | PUBLIC SERVICE TRAINING AND DEVOLUTION | PUBLIC SERVICE TRAINING AND DEVOLUTION | N/A | 2020/21 | 2020/21 | 2020/21 | 6048565 | 2844546 | 2844546 | N/A | N/A | 2844546 | 0 | 2843795 | 100 | 2843795 | 2844546 | 751 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3347 | Education Outstanding Contract Retention - development | Education Outstanding Contract Retention - development | To implement education outstanding contract retention - development for access to quality education and training | Education Outstanding Contract Retention - development completed | 2211314 | Write Offs/ Bad Debt Expenses from Previous Years (Pending Bills) | HQ | HQ | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | N/A | 15499456.64 | 15499456.64 | 15499456.64 | Equitable | N/A | 15499456.64 | 0 | 8708588 | 56.2 | 8708588 | 0 | 6790868.64 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
3348 | Allocation for Rehabilitation of Youth Polytechnics | Allocation for Rehabilitation of Youth Polytechnics | To implement allocation for rehabilitation of youth polytechnics for access to quality education and training | Allocation for Rehabilitation of Youth Polytechnics completed | 2510118 | N/A | HQ | HQ | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | N/A | 66289894 | 66289894 | 66289894 | Equitable | N/A | 66289894 | 0 | 10193360 | 15.4 | 10193360 | 66289894 | 56096534 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
3349 | Conditional Allocation for Rehabilitation of Youth Polytechnics | Conditional Allocation for Rehabilitation of Youth Polytechnics | To implement conditional allocation for rehabilitation of youth polytechnics for access to quality education and training | Conditional Allocation for Rehabilitation of Youth Polytechnics completed | 2510118 | N/A | HQ | HQ | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | N/A | 66289894 | 755126 | 0 | Equitable | N/A | 0 | 755126 | 10193360 | 1349.9 | 10193360 | 66289894 | -9438234 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
3350 | Construction And Equipping ECDE Class And Pupils Toilet At Lelaitich Primary School | Construction And Equipping ECDE Class And Pupils Toilet At Lelaitich Primary School | To construct and equip ECDE Class And Pupils Toilet At Lelaitich Primary School | ECDE Class And Pupils Toilet At Lelaitich Primary School constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Amalo | -0.676213, 35.657443 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2020 | 1800000 | 1789810 | 1789810 | Equitable | N/A | 1789810 | 0 | 646075 | 36.1 | 646075 | 646075 | 1143735 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: partially. Viable: partially.
3351 | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Kwendo ECD | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Kwendo ECD | To construct 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Kwendo ECD | 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Kwendo ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Amalo | -0.570768, 35.664825 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016 | 1000000 | 992345 | 992345 | Equitable | N/A | 992345 | 0 | 1499996 | 151.2 | 1499996 | 992345 | -507651 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: no. Viable: no.
3352 | Construction Of ECDE Classroom At Kabigeriet | Construction Of ECDE Classroom At Kabigeriet | To construct ECDE Classroom At Kabigeriet | ECDE Classroom At Kabigeriet constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Amalo | -0.570777, 35.664768 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2018 | 1200000 | 1099217 | 1099217 | Equitable | N/A | 1099217 | 0 | 416194 | 37.9 | 416194 | 1349217 | 683023 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes.
3353 | Construction Of One ECDE Classroom At Gorofa | Construction Of One ECDE Classroom At Gorofa | To construct One ECDE Classroom At Gorofa | One ECDE Classroom At Gorofa constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Amalo | -0.652603, 35.651755 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2024 | 1200000 | 1099217 | 1099217 | Equitable | N/A | 1099217 | 0 | 1199956 | 109.2 | 1199956 | 1349217 | -100739 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes.
3354 | Construction of Sigowet ECDE classroom | Construction of Sigowet ECDE classroom | To construct Sigowet ECDE classroom | Sigowet ECDE classroom constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Amalo | -0.652603, 35.651755 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2024 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1199956 | 80 | 1199956 | 1429210 | 300044 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes.
3355 | Construction Of An ECD Classroom At Ndashata ECDE | Construction Of An ECD Classroom At Ndashata ECDE | To construct An ECD Classroom At Ndashata ECDE | An ECD Classroom At Ndashata ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Amalo | -0.679731 35.639555 2433.82666015625 4.373000144958496 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1200000 | 416194 | 416194 | Equitable | N/A | 416194 | 0 | 416194 | 100 | 416194 | 416194 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: no. Viable: yes. Assessor remarks: not yet done.
3356 | Construction Of An ECDE Class Water Tank And Sanitation Facility At Barasta School | Construction Of An ECDE Class Water Tank And Sanitation Facility At Barasta School | To construct An ECDE Class Water Tank And Sanitation Facility At Barasta School | An ECDE Class Water Tank And Sanitation Facility At Barasta School constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Bahati | Bahati | -0.147818 36.090577 1844.547607421875 6.189000129699707 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1997862 | 99.9 | 1997862 | 2000000 | 2138 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The water tank was broken and no toilet.
3357 | Construction and equipping of two ECD classrooms at NYS Primary School | Construction and equipping of two ECD classrooms at NYS Primary School | To construct and equip two ECD classrooms at NYS Primary School | Two ECD classrooms at NYS Primary School constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Biashara-Naivasha | -0.661265, 36.48513 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2023 | 3000000 | 2794857 | 2794857 | Equitable | N/A | 2794857 | 0 | 2779040 | 99.4 | 2779040 | 2779040 | 15817 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Dakuki contractors.
3358 | Construction Of 2 ECDE Classroom At Kinamba ECDE | Construction Of 2 ECDE Classroom At Kinamba ECDE | To construct 2 ECDE Classroom At Kinamba ECDE | 2 ECDE Classroom At Kinamba ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Biashara-Naivasha | -0.718757, 36.483535 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2021 | 2400000 | 2389990 | 2389990 | Equitable | N/A | 2389990 | 0 | 2389990 | 100 | 2389990 | 2389990 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Dakuki.
3359 | Construction Of Kinamba Polytechnic | Construction Of Kinamba Polytechnic | To construct Kinamba Polytechnic | Kinamba Polytechnic constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Biashara-Naivasha | -0.725923, 36.486655 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | 2019 | 11011771 | 11011771 | 11011771 | Equitable | N/A | 11011771 | 0 | 10999070 | 99.9 | 10999070 | 11011771 | 12701 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Dakuki.
3360 | Construction Of St. Paul ECDE Classroom | Construction Of St. Paul ECDE Classroom | To construct St. Paul ECDE Classroom | St. Paul ECDE Classroom constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Biashara-Naivasha | -0.639473, 36.494277 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | 2016 | 1300000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 2389990 | 183.8 | 2389990 | 1300000 | -1089990 | Vired | 90 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
3361 | Construction of St Paul ECD | Construction of St Paul ECD | To construct St Paul ECD | St Paul ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Biashara-Naivasha | -0.639473, 36.494277 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | 2016 | 1300000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 8683480 | 668 | 8683480 | 1300000 | -7383480 | Vired | 90 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
3362 | Construction and equipping of 2 ECDE classes at Crates Primary School | Construction and equipping of 2 ECDE classes at Crates Primary School | To construct and equip 2 ECDE classes at Crates Primary School | 2 ECDE classes at Crates Primary School constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru East | Biashara-Nakuru | -0.285216, 36.093812 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2022/23 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2932410 | 97.7 | 2932410 | 0 | 67590 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3363 | Construction of Administration Block and Toilet at Kariba Road Primary and St Marys Primary | Construction of Administration Block and Toilet at Kariba Road Primary and St Marys Primary | To construct Administration Block and Toilet at Kariba Road Primary and St Marys Primary | Administration Block and Toilet at Kariba Road Primary and St Marys Primary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru East | Biashara-Nakuru | -0.293619, 36.073886 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2022/23 | 4200000 | 4200000 | 4200000 | Equitable | N/A | 4200000 | 0 | 4200000 | 100 | 4200000 | 4200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3364 | Construction of Administration Block at St Pauls Primary | Construction of Administration Block at St Pauls Primary | To construct Administration Block at St Pauls Primary | Administration Block at St Pauls Primary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru East | Biashara-Nakuru | -0.296069, 36.07874 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2022/23 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3378688 | 96.5 | 3378688 | 3378688 | 121312 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Yes. Contractor: Joly general merchants.
3365 | Construction of an Administration Block at Ngala School for the deaf | Construction of an Administration Block at Ngala School for the deaf | To construct an Administration Block at Ngala School for the deaf | An Administration Block at Ngala School for the deaf constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru East | Biashara-Nakuru | -0.291864, 36.075578 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2022/2023 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 3378688 | 96.5 | 3378688 | 3378688 | 121312 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Joly General merchants ltd.
3366 | Kaburi ECDE construction of I classroom | Kaburi ECDE construction of I classroom | To implement kaburi ecde construction of i classroom for access to quality education and training | Kaburi ECDE construction of I classroom completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Bahati | Dundori | -0.237247 36.23572 2418 3.0999999046325684 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2017/18 | 2017/18 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1168060 | 97.3 | 1168060 | 1200000 | 31940 | Vired | 25 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: M/s Tripple. Assessor remarks: The was not fully completed, lacks water tank , terrazzo and electricity..
3367 | Construction and equipping of ECDE classroom at Kamathatha and toilet | Construction and equipping of ECDE classroom at Kamathatha and toilet | To construct and equip ECDE classroom at Kamathatha and toilet | ECDE classroom at Kamathatha and toilet constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Eburru/Mbaruk | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2022/23 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1738820 | 96.6 | 1738820 | 61180 | 61180 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3368 | Construction Of 1 Classroom At Cider ECD | Construction Of 1 Classroom At Cider ECD | To construct 1 Classroom At Cider ECD | 1 Classroom At Cider ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Eburru/Mbaruk | -0.616508, 36.256504 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | Unspecified | 1200000 | 1199996 | 1199996 | Equitable | N/A | 1199996 | 0 | 6796 | 0.6 | 6796 | 1199996 | 1193200 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: Partially. Condition: Bad. Objective met: No value for money. Viable: No. Contractor: Unspecified.
3369 | Construction Of 1 Classroom At Kelelwa ECD | Construction Of 1 Classroom At Kelelwa ECD | To construct 1 Classroom At Kelelwa ECD | 1 Classroom At Kelelwa ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Eburru/Mbaruk | -0.616508, 36.256504 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | Unspecified | 1200000 | 6796 | 6796 | Equitable | N/A | 6796 | 0 | 6796 | 100 | 6796 | 6796 | 0 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: Partially. Condition: Bad. Objective met: No value for money. Viable: No. Contractor: Unspecified.
3370 | Construction Of ECD Classrooms At Losirwa ECDE, Emkwen ECDE And Cypress ECDE | Construction Of ECD Classrooms At Losirwa ECDE, Emkwen ECDE And Cypress ECDE | To construct ECD Classrooms At Losirwa ECDE, Emkwen ECDE And Cypress ECDE | ECD Classrooms At Losirwa ECDE, Emkwen ECDE And Cypress ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Eburru/Mbaruk | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | N/A | 4100000 | 4100000 | 4100000 | Equitable | N/A | 4100000 | 0 | 6796 | 0.2 | 6796 | 4100000 | 4093204 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
3371 | Construction of ECDE Classroom at Losiro, Emkwen and Cypress | Construction of ECDE Classroom at Losiro, Emkwen and Cypress | To construct ECDE Classroom at Losiro, Emkwen and Cypress | ECDE Classroom at Losiro, Emkwen and Cypress constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Eburru/Mbaruk | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | N/A | 4100000 | 4100000 | 4100000 | Equitable | N/A | 4100000 | 0 | 2160890 | 52.7 | 2160890 | 4100000 | 1939110 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
3372 | Construction of Kapkures ECDE classroom, equipping and toilet | Construction of Kapkures ECDE classroom, equipping and toilet | To construct Kapkures ECDE classroom, equipping and toilet | Kapkures ECDE classroom, equipping and toilet constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Eburru/Mbaruk | -0.520686, 36.126673 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | Unspecified | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1710442 | 95 | 1710442 | 1710442 | 89558 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: Partially. Condition: Yet to start. Objective met: No. Viable: No. Contractor: Unspecified.
3373 | Construction and Equipping of One classroom ECD at Ndimu | Construction and Equipping of One classroom ECD at Ndimu | To construct and equip One classroom ECD at Ndimu | One classroom ECD at Ndimu constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Elburgon | -0.279925, 35.765083 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | - | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1478089 | 98.5 | 1478089 | 1478090 | 21911 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3374 | Construction Of I ECDE Classroom At Kamirithu | Construction Of I ECDE Classroom At Kamirithu | To construct I ECDE Classroom At Kamirithu | I ECDE Classroom At Kamirithu constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Elburgon | -0.309157 35.80994 2403.900146484375 10.199999809265137 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1202494 | 1202494 | Equitable | N/A | 1202494 | 0 | 1194994 | 99.4 | 1194994 | 1202494 | 7500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Funtional.
3375 | Design And Construction Of Mucharage ECDE | Design And Construction Of Mucharage ECDE | To design and construct Mucharage ECDE | Mucharage ECDE designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Elburgon | -0.307435 35.749389 0 2599.9990234375 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1194994 | 119.5 | 1194994 | 1000000 | -194994 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need some repairs and maintainance.
3376 | Design And Construction Of Nyakiambi Karunga ECDE | Design And Construction Of Nyakiambi Karunga ECDE | To design and construct Nyakiambi Karunga ECDE | Nyakiambi Karunga ECDE designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Elburgon | -0.180252 35.704339 0 3299.9990234375 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete and functional.
3377 | Design And Construction Of Tegat ECDE | Design And Construction Of Tegat ECDE | To design and construct Tegat ECDE | Tegat ECDE designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Elburgon | -0.27156 35.816038 2145.7 13.600000381469727 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1194994 | 119.5 | 1194994 | 1000000 | -194994 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need some repair and maintainance.
3378 | Construction Of 1No. Classroom At Muriricua Primary ECD | Construction Of 1No. Classroom At Muriricua Primary ECD | To construct 1No. Classroom At Muriricua Primary ECD | 1No. Classroom At Muriricua Primary ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Elementaita | -0.566243 36.119887 1951.9 7.5 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1198280 | 409770 | 409770 | Equitable | N/A | 409770 | 0 | 1166090 | 284.6 | 1166090 | 409770 | -756320 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
3379 | Construction Of Matuiku ECDE Classroom | Construction Of Matuiku ECDE Classroom | To construct Matuiku ECDE Classroom | Matuiku ECDE Classroom constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Elementaita | -0.581133 36.06226 2358 7.5 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1200000 | 1109905 | 1109905 | Equitable | N/A | 1109905 | 0 | 80430 | 7.2 | 80430 | 1109905 | 1029475 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good state of tepair.
3380 | Design And Construction Of Mbombo ECDE And Toilets | Design And Construction Of Mbombo ECDE And Toilets | To design and construct Mbombo ECDE And Toilets | Mbombo ECDE And Toilets designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Elementaita | -0.555641 36.103909 1951.146 0.6809999942779541 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | N/A | 1664971 | 1664971 | 1664971 | Equitable | N/A | 1664971 | 0 | 1199700 | 72.1 | 1199700 | 1000000 | 465271 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Stalled.
3381 | Construction Of ECD Administration Block At Lake View ECD | Construction Of ECD Administration Block At Lake View ECD | To construct ECD Administration Block At Lake View ECD | ECD Administration Block At Lake View ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru East | Flamingo | -0.305502, 36.07834 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/2020 | 3495558 | 1068473 | 1068473 | Equitable | N/A | 1068473 | 0 | 3449870 | 322.9 | 3449870 | 1068473 | -2381397 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Nalah women company limited.
3382 | Design And Construction Of 2 No ECDE Classes At Lake View ECD | Design And Construction Of 2 No ECDE Classes At Lake View ECD | To design and construct 2 No ECDE Classes At Lake View ECD | 2 No ECDE Classes At Lake View ECD designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru East | Flamingo | -0.305357, 36.078337 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/2020 | 2400000 | 2390952 | 2390952 | Equitable | N/A | 2390952 | 0 | 2390952 | 100 | 2390952 | 2390952 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: M/s NaxxyLimited.
3383 | Construction Of Classroom At View Point ECDE, Furnitures, Fencing And Installation Of A Gate | Construction Of Classroom At View Point ECDE, Furnitures, Fencing And Installation Of A Gate | To construct Classroom At View Point ECDE, Furnitures, Fencing And Installation Of A Gate | Classroom At View Point ECDE, Furnitures, Fencing And Installation Of A Gate constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Gilgil | -0.490004 36.320031 2012.025634765625 10.036999702453613 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | 2021/22 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1174020 | 97.8 | 1174020 | 1200000 | 25980 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs renovation.
3384 | Construction of classroom with terrazzo floor, construction of toilet, furniture and tank with gutters for Utumishi ECD | Construction of classroom with terrazzo floor, construction of toilet, furniture and tank with gutters for Utumishi ECD | To construct classroom with terrazzo floor, construction of toilet, furniture and tank with gutters for Utumishi ECD | Classroom with terrazzo floor, construction of toilet, furniture and tank with gutters for Utumishi ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Gilgil | -0.474823, 36.333885 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2022/2023 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1682085 | 93.4 | 1682085 | 1682085 | 117915 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
3385 | Construction Of St. Patrick ECDE One Classroom Plus Furniture | Construction Of St. Patrick ECDE One Classroom Plus Furniture | To construct St. Patrick ECDE One Classroom Plus Furniture | St. Patrick ECDE One Classroom Plus Furniture constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Gilgil | -0.506473, 36.327503 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/2020 | 1600000 | 3509.2 | 3509.2 | Equitable | N/A | 3509.2 | 0 | 3509 | 100 | 3509 | 3509 | 0.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Glasammur construction limited.
3386 | Design And Construction Of Kanyawa ECD Classroom, Tank, Furnitures, Swings And Toilets | Design And Construction Of Kanyawa ECD Classroom, Tank, Furnitures, Swings And Toilets | To design and construct Kanyawa ECD Classroom, Tank, Furnitures, Swings And Toilets | Kanyawa ECD Classroom, Tank, Furnitures, Swings And Toilets designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Gilgil | -0.507742, 36.323612 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1797480 | 89.9 | 1797480 | 2000000 | 202520 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3387 | Kambi Somali ECDE - Floor Renovation Of 2 Classroom, Veranda And Painting And Building Of Wall Cupboards And Toilets | Kambi Somali ECDE - Floor Renovation Of 2 Classroom, Veranda And Painting And Building Of Wall Cupboards And Toilets | To implement kambi somali ecde - floor renovation of 2 classroom, veranda and painting and building of wall cupboards and toilets for access to quality education and training | Kambi Somali ECDE - Floor Renovation Of 2 Classroom, Veranda And Painting And Building Of Wall Cupboards And Toilets completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Gilgil | -0.50955, 36.31529 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3388 | Completion of 2 no. Dormitories at Pangani Special School | Completion of 2 no. Dormitories at Pangani Special School | To complete 2 no. Dormitories at Pangani Special School | 2 no. Dormitories at Pangani Special School completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | N/A | 5000000 | 0 | 5000000 | Equitable | N/A | 5000000 | 0 | 0 | 0 | 0 | 5000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
3389 | Completion of Administration block and modern toilet at Molo Polytechnic | Completion of Administration block and modern toilet at Molo Polytechnic | To complete Administration block and modern toilet at Molo Polytechnic | Administration block and modern toilet at Molo Polytechnic completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2022/23 | 2915837 | 2915837 | 2915837 | Equitable | N/A | 2915837 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3390 | Construction and equipping of Maombi ECDE, toilet and completion and equipping of Ruiru ECDE | Construction and equipping of Maombi ECDE, toilet and completion and equipping of Ruiru ECDE | To construct and equip Maombi ECDE, toilet and completion and equipping of Ruiru ECDE | Maombi ECDE, toilet and completion and equipping of Ruiru ECDE constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 269520 | 13.5 | 269520 | 509920 | 1730480 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3391 | Construction of classroom and toilets in Lakeview and Langalanga ECDE | Construction of classroom and toilets in Lakeview and Langalanga ECDE | To construct classroom and toilets in Lakeview and Langalanga ECDE | Classroom and toilets in Lakeview and Langalanga ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | N/A | 900000 | 900000 | 900000 | Equitable | N/A | 900000 | 0 | 0 | 0 | 0 | 900000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
3392 | Construction Of ECD Centre Of Excellence | Construction Of ECD Centre Of Excellence | To construct ECD Centre Of Excellence | ECD Centre Of Excellence constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | HQ | HQ | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 23466338.86 | 1306335.75 | 1306335.75 | Equitable | N/A | 1306335.75 | 0 | 19900008 | 1523.3 | 19900008 | 3566331 | -18593672.25 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3393 | Construction of 1 ECD classroom, toilet and water tank at Kamuyu | Construction of 1 ECD classroom, toilet and water tank at Kamuyu | To construct 1 ECD classroom, toilet and water tank at Kamuyu | 1 ECD classroom, toilet and water tank at Kamuyu constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Hells Gate | -0.835837, 36.497961 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | 29th November 2024 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1487282 | 74.4 | 1487282 | 1911040 | 512718 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: WANJIP G. ENTERPRISES.
3394 | Construction of 1 ECD classroom, toilet and water tank at Mountain View | Construction of 1 ECD classroom, toilet and water tank at Mountain View | To construct 1 ECD classroom, toilet and water tank at Mountain View | 1 ECD classroom, toilet and water tank at Mountain View constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Hells Gate | -0.835837, 36.497961 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | 29th November 2024 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1487282 | 74.4 | 1487282 | 1911040 | 512718 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: WANJIP G. ENTERPRISES.
3395 | Construction Of One ECD Classroom, Toilet and Water Tank At Kamuyu | Construction Of One ECD Classroom, Toilet and Water Tank At Kamuyu | To construct One ECD Classroom, Toilet and Water Tank At Kamuyu | One ECD Classroom, Toilet and Water Tank At Kamuyu constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Hells Gate | -0.835837, 36.497961 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | 29th November 2024 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 1487282 | 49.6 | 1487282 | 3000000 | 1512718 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: WANJIP G. ENTERPRISES.
3396 | Construction Of One E.C.D Classroom, Toilet And Water Tank At Mountain View | Construction Of One E.C.D Classroom, Toilet And Water Tank At Mountain View | To construct One E.C.D Classroom, Toilet And Water Tank At Mountain View | One E.C.D Classroom, Toilet And Water Tank At Mountain View constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Hells Gate | -0.835837, 36.497961 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | 29th November 2024 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 1487282 | 49.6 | 1487282 | 3000000 | 1512718 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: WANJIP G. ENTERPRISES.
3397 | Karagita ECDE - Construction Of One Classroom And Equiping | Karagita ECDE - Construction Of One Classroom And Equiping | To implement karagita ecde - construction of one classroom and equiping for access to quality education and training | Karagita ECDE - Construction Of One Classroom And Equiping completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Hells Gate | -0.776669, 36.433058 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 1998654 | 1998654 | Equitable | N/A | 1998654 | 0 | 1998654 | 100 | 1998654 | 1998654 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yed.
3398 | Longonot DEB Pri School ECDE - Construction Of Two Classrooms And Equiping | Longonot DEB Pri School ECDE - Construction Of Two Classrooms And Equiping | To implement longonot deb pri school ecde - construction of two classrooms and equiping for access to quality education and training | Longonot DEB Pri School ECDE - Construction Of Two Classrooms And Equiping completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Hells Gate | -0.814865, 36.399555 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2600000 | 86.7 | 2600000 | 3000000 | 400000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3399 | Completion Of Murungaru ECD | Completion Of Murungaru ECD | To complete Murungaru ECD | Murungaru ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Bahati | Kabatini | -0.185964 36.168814 2112.656005859375 15.793000221252441 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1070 | 1070 | Equitable | N/A | 1070 | 0 | 1070 | 100 | 1070 | 1070 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Glazer general supplies. Assessor remarks: Wall has a crack,they need an extra room,more tables and the floor should be redone.
3400 | Completion Of St John ECD | Completion Of St John ECD | To complete St John ECD | St John ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Bahati | Kabatini | -0.185964 36.168814 2112.656005859375 15.793000221252441 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 5 | 5 | Equitable | N/A | 5 | 0 | 5 | 100 | 5 | 5 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Glazer general supplies. Assessor remarks: Wall has a crack,they need an extra room,more tables and the floor should be redone.
3401 | Construction And Equipping Of A Workshop At Wendo Polytechnic | Construction And Equipping Of A Workshop At Wendo Polytechnic | To construct and equip A Workshop At Wendo Polytechnic | A Workshop At Wendo Polytechnic constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Bahati | Kabatini | -0.18076 36.180676 1937.9000244140625 98.4000015258789 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 2500000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 300000 | 100 | 300000 | 300000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s tripple general supplies. Assessor remarks: Operational but the roof need to be redone.
3402 | Design And Construction Of Limuko ECDE | Design And Construction Of Limuko ECDE | To design and construct Limuko ECDE | Limuko ECDE designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Bahati | Kabatini | -0.214235 36.163212 2030.4000244140625 10.031000137329102 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 1964573 | 1964573 | Equitable | N/A | 1964573 | 0 | 1950470 | 99.3 | 1950470 | 2000000 | 14103 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s wakasi enterprise. Assessor remarks: Operational but the floor needs renovation.
3403 | Construction Of 1 ECD Classroom At Banita ECD | Construction Of 1 ECD Classroom At Banita ECD | To construct 1 ECD Classroom At Banita ECD | 1 ECD Classroom At Banita ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Subukia | Kabazi | -0.118417, 36.073703 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/2020 | 1200000 | 37 | 37 | Equitable | N/A | 37 | 0 | 37 | 100 | 37 | 37 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated.
3404 | Construction Of 1 ECD Classroom Ndungiri ECD | Construction Of 1 ECD Classroom Ndungiri ECD | To construct 1 ECD Classroom Ndungiri ECD | 1 ECD Classroom Ndungiri ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Subukia | Kabazi | -0.118417, 36.073703 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/2020 | 1200000 | 40 | 40 | Equitable | N/A | 40 | 0 | 37 | 92.5 | 37 | 40 | 3 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated.
3405 | Construction Of 1 Jumatatu ECDE | Construction Of 1 Jumatatu ECDE | To construct 1 Jumatatu ECDE | 1 Jumatatu ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Subukia | Kabazi | -0.09353 36.13189 0 1787 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 758890 | 758890 | Equitable | N/A | 758890 | 0 | 682652 | 90 | 682652 | 758890 | 76238 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Lemyna works ltd. Assessor remarks: Requires water tank and toilets.
3406 | Construction Of Ampiva ECD And Toilets And Completion Of Ruiru ECD Plus Toilets | Construction Of Ampiva ECD And Toilets And Completion Of Ruiru ECD Plus Toilets | To construct Ampiva ECD And Toilets And Completion Of Ruiru ECD Plus Toilets | Ampiva ECD And Toilets And Completion Of Ruiru ECD Plus Toilets constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Subukia | Kabazi | -0.12904 36.15429 0 220 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 699162 | 35 | 699162 | 2000000 | 1300838 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Requires renovations, additional classroom and furniture.
3407 | Construction Of Edao, Akuisi, Munyaka ECDE Classrooms, Renovation And Equipment Of Odm Primary, Kihoto And Kabazi Primary ECDE | Construction Of Edao, Akuisi, Munyaka ECDE Classrooms, Renovation And Equipment Of Odm Primary, Kihoto And Kabazi Primary ECDE | To construct Edao, Akuisi, Munyaka ECDE Classrooms, Renovation And Equipment Of Odm Primary, Kihoto And Kabazi Primary ECDE | Edao, Akuisi, Munyaka ECDE Classrooms, Renovation And Equipment Of Odm Primary, Kihoto And Kabazi Primary ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Subukia | Kabazi | -0.106772 36.057525 1617.2 12.600000381469727 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | 2021/22 | 5500000 | 5500000 | 5500000 | Equitable | N/A | 5500000 | 0 | 3745310 | 68.1 | 3745310 | 0 | 1754690 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: Start back engineering and consultancy company ltdncy. Assessor remarks: Requires completion.
3408 | Construction Of Mika ECDE Toilet | Construction Of Mika ECDE Toilet | To construct Mika ECDE Toilet | Mika ECDE Toilet constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Subukia | Kabazi | -0.12904 36.15429 0 220 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | N/A | 472895 | 472895 | 472895 | Equitable | N/A | 472895 | 0 | 682652 | 144.4 | 682652 | 472895 | -209757 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Requires renovations, additional classroom and furniture.
3409 | Construction Of ECD Class At Choronok ECD | Construction Of ECD Class At Choronok ECD | To construct ECD Class At Choronok ECD | ECD Class At Choronok ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Kamara | -0.176655, 35.698202 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2020/21 | 800000 | 1199975 | 1199975 | Equitable | N/A | 1199975 | 0 | 1199975 | 100 | 1199975 | 1199975 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Not indicated.
3410 | Construction Of ECDE Class At Kaproret | Construction Of ECDE Class At Kaproret | To construct ECDE Class At Kaproret | ECDE Class At Kaproret constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Kamara | -0.176655, 35.698202 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2020/21 | 1200000 | 1199975 | 1199975 | Equitable | N/A | 1199975 | 0 | 1199975 | 100 | 1199975 | 1199975 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Not indicated.
3411 | Construction And Equipping Of Two ECDE Classrooms At Kapnandi ECDE | Construction And Equipping Of Two ECDE Classrooms At Kapnandi ECDE | To construct and equip Two ECDE Classrooms At Kapnandi ECDE | Two ECDE Classrooms At Kapnandi ECDE constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | Kapkures | -0.319488, 36.02239 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 3500000 | 3499700 | 3499700 | Equitable | N/A | 3499700 | 0 | 279231 | 8 | 279231 | 3499700 | 3220469 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Mugima Enterprises LTD.
3412 | Construction Of A Classroom At Tulwet ECD | Construction Of A Classroom At Tulwet ECD | To construct A Classroom At Tulwet ECD | A Classroom At Tulwet ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | Kapkures | -0.32933, 36.034112 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1478771 | 279231 | 279231 | Equitable | N/A | 279231 | 0 | 279231 | 100 | 279231 | 279231 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ngambo Hardware.
3413 | Construction Of Administration Block At Ingobor ECDE | Construction Of Administration Block At Ingobor ECDE | To construct Administration Block At Ingobor ECDE | Administration Block At Ingobor ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | Kapkures | -0.306306 36.018533 0 2000 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | N/A | 2700000 | 2680835 | 2680835 | Equitable | N/A | 2680835 | 0 | 800 | 0 | 800 | 2680835 | 2680035 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Not constructed. Viable: Viable but has not been implemented. Assessor remarks: Not done.
3414 | Construction Of Administration Block At Kapkures Tulwet ECDE | Construction Of Administration Block At Kapkures Tulwet ECDE | To construct Administration Block At Kapkures Tulwet ECDE | Administration Block At Kapkures Tulwet ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | Kapkures | -0.306306 36.018533 0 2000 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 2500000 | 800 | 800 | Equitable | N/A | 800 | 0 | 800 | 100 | 800 | 800 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Not constructed. Viable: Viable but has not been implemented. Assessor remarks: Not done.
3415 | Construction Of An Administration Block At Ingobor | Construction Of An Administration Block At Ingobor | To construct An Administration Block At Ingobor | An Administration Block At Ingobor constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | Kapkures | -0.306306 36.018533 0 2000 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 800 | 0 | 800 | 2500000 | 2499200 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Not constructed. Viable: Viable but has not been implemented. Assessor remarks: Not done.
3416 | Construction Of An Administration Block At Mogoon ECDE | Construction Of An Administration Block At Mogoon ECDE | To construct An Administration Block At Mogoon ECDE | An Administration Block At Mogoon ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | Kapkures | -0.288288 36.05451 0 2000 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | N/A | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 800 | 0 | 800 | 2500000 | 2499200 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Viable. But not done. Assessor remarks: Not done on the ground.
3417 | Construction Of And Equipping Of A Classroom At Tulwet | Construction Of And Equipping Of A Classroom At Tulwet | To construct And Equipping Of A Classroom At Tulwet | And Equipping Of A Classroom At Tulwet constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | Kapkures | -0.324324, 36.036613 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 279231 | 18.6 | 279231 | 1500000 | 1220769 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Improved learning environment.
3418 | Construction Of A Vocational Centre At Kaptembwo Resource Center | Construction Of A Vocational Centre At Kaptembwo Resource Center | To construct A Vocational Centre At Kaptembwo Resource Center | A Vocational Centre At Kaptembwo Resource Center constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | Kaptembwo | -0.317779, 36.052984 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | 2021/22 | 10000000 | 0 | 10000000 | Equitable | N/A | 10000000 | 0 | 9999900 | 100 | 9999900 | 10000000 | -9999900 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes,since it's the only VOCATIONAL training center in the ward. Contractor: SAMWAYS MERCHANTS.
3419 | Construction Of A Vocational Centre At Kaptembwo Resourse Center | Construction Of A Vocational Centre At Kaptembwo Resourse Center | To construct A Vocational Centre At Kaptembwo Resourse Center | A Vocational Centre At Kaptembwo Resourse Center constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | Kaptembwo | -0.317779, 36.052984 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | 2021/22 | 10000000 | 10000000 | 10000000 | Equitable | N/A | 10000000 | 0 | 9999900 | 100 | 9999900 | 10000000 | 100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes,since it's the only VOCATIONAL training center in the ward. Contractor: SAMWAYS MERCHANTS.
3420 | Construction of an ECDE Administration block at Kibowen Komen ECDE | Construction of an ECDE Administration block at Kibowen Komen ECDE | To construct an ECDE Administration block at Kibowen Komen ECDE | An ECDE Administration block at Kibowen Komen ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | Kaptembwo | -0.310573 36.053491 1787.5 6.389999866485596 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2022/23 | 3800000 | 3800000 | 3800000 | Equitable | N/A | 3800000 | 0 | 3800000 | 100 | 3800000 | 3800000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: It met the needs of the residents. Contractor: M/S SILBO HOLDINGS. Assessor remarks: Complete.
3421 | Construction of ECDE classroom, ECDE kitchen and purchase of playing equipment at Eleeingong'och | Construction of ECDE classroom, ECDE kitchen and purchase of playing equipment at Eleeingong'och | To construct ECDE classroom, ECDE kitchen and purchase of playing equipment at Eleeingong'och | ECDE classroom, ECDE kitchen and purchase of playing equipment at Eleeingong'och constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | Kaptembwo | -0.320788 36.057104 1780.0986245613312 98.4000015258789 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | N/A | 3800000 | 3800000 | 3800000 | Equitable | N/A | 3800000 | 0 | 3595630 | 94.6 | 3595630 | 3595630 | 204370 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: A very viable project,it met the needs of the residents. Contractor: CYRUS BOIT NGAMBO HARDWARES. Assessor remarks: A very viable project.
3422 | Construction & equipping of Saptet Polytechnic workshop | Construction & equipping of Saptet Polytechnic workshop | To construct & equipping of Saptet Polytechnic workshop | & equipping of Saptet Polytechnic workshop constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Keringet | -0.484797, 35.699813 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2024 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1986650 | 99.3 | 1986650 | 1986650 | 13350 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
3423 | Construction of 1 ECDE class, teacher & pupils toilet & water tank at Ribot | Construction of 1 ECDE class, teacher & pupils toilet & water tank at Ribot | To construct 1 ECDE class, teacher & pupils toilet & water tank at Ribot | 1 ECDE class, teacher & pupils toilet & water tank at Ribot constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Keringet | -0.53935 35.711058 2660.000244140625 24.600000381469727 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 747140 | 49.8 | 747140 | 721470 | 752860 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Class olmost complete but toilet and water tank not yet constructed.
3424 | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Tembwo ECD | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Tembwo ECD | To construct 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Tembwo ECD | 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Tembwo ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Keringet | -0.421928 35.666268 2651.5 5.599999904632568 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1199990 | 1199990 | 1199990 | Equitable | N/A | 1199990 | 0 | 1199990 | 100 | 1199990 | 1199990 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
3425 | Construction of 2 ECDE classroom at Upendo and renovation of teta youth polytechnique | Construction of 2 ECDE classroom at Upendo and renovation of teta youth polytechnique | To construct 2 ECDE classroom at Upendo and renovation of teta youth polytechnique | 2 ECDE classroom at Upendo and renovation of teta youth polytechnique constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Keringet | -0.421928 35.666268 2651.5 5.599999904632568 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2022/23 | 2200000 | 2200000 | 2200000 | Equitable | N/A | 2200000 | 0 | 1852800 | 84.2 | 1852800 | 2200000 | 347200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
3426 | Construction of Administration block at Saptet Polytechnic | Construction of Administration block at Saptet Polytechnic | To construct Administration block at Saptet Polytechnic | Administration block at Saptet Polytechnic constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Keringet | -0.485055, 35.699632 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2023 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2482045 | 99.3 | 2482045 | 2482045 | 17955 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
3427 | Kibanguui ECD | Kibanguui ECD | To implement kibanguui ecd for access to quality education and training | Kibanguui ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Keringet | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2015/16 | 2015/16 | 2015/16 | 1190844 | 1190000 | 1190000 | Equitable | N/A | 1190000 | 0 | 0 | 0 | 0 | 1190000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3428 | Construction Of Saptet ECD Classroom | Construction Of Saptet ECD Classroom | To construct Saptet ECD Classroom | Saptet ECD Classroom constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Keringet | -0.50589, 35.698535 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1330000 | 183305 | 183305 | Equitable | N/A | 183305 | 0 | 667928 | 364.4 | 667928 | 183305 | -484623 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3429 | Construction Of Tendwet ECD Classroom | Construction Of Tendwet ECD Classroom | To construct Tendwet ECD Classroom | Tendwet ECD Classroom constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Keringet | -0.50589, 35.698535 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1330000 | 851233 | 851233 | Equitable | N/A | 851233 | 0 | 312620 | 36.7 | 312620 | 538613 | 538613 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3430 | Construction and equipping of Wendani Polytechnic | Construction and equipping of Wendani Polytechnic | To construct and equip Wendani Polytechnic | Wendani Polytechnic constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Kihingo | -0.447143, 35.965092 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2015 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 0 | 0 | 0 | 3992580 | 0 | Vired | 25 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No.
3431 | Construction of 1 ECDE classroom at Cheptebos and Kiplemeiywo ECDE | Construction of 1 ECDE classroom at Cheptebos and Kiplemeiywo ECDE | To construct 1 ECDE classroom at Cheptebos and Kiplemeiywo ECDE | 1 ECDE classroom at Cheptebos and Kiplemeiywo ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Kiptagich | -0.586967 35.633358 2444.3999999999996 12.399999618530273 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | N/A | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 1270177 | 50.8 | 1270177 | 2468070 | 1229823 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Don't. Assessor remarks: The project is complete but does not have toilets and windows are shattered.
3432 | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Kibirech ECD | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Kibirech ECD | To construct 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Kibirech ECD | 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Kibirech ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Kiptagich | -0.586967 35.633358 2444.3999999999996 12.399999618530273 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1500000 | 229823 | 229823 | Equitable | N/A | 229823 | 0 | 1270177 | 552.7 | 1270177 | 229823 | -1040354 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Don't. Assessor remarks: The project is complete but does not have toilets and windows are shattered.
3433 | Construction Of Administration Block At Cheptuech Polytechnic | Construction Of Administration Block At Cheptuech Polytechnic | To construct Administration Block At Cheptuech Polytechnic | Administration Block At Cheptuech Polytechnic constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Kiptagich | -0.57288 35.613184 2454 5.099999904632568 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | N/A | 900000 | 900000 | 900000 | Equitable | N/A | 900000 | 0 | 0 | 0 | 0 | 900000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes viable but not yet started. Contractor: Don't know. Assessor remarks: The project has not started..
3434 | Construction Of Ekabugunot ECDE | Construction Of Ekabugunot ECDE | To construct Ekabugunot ECDE | Ekabugunot ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Kiptagich | -0.536993 35.578477 2446.5 5.900000095367432 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2014/15 | 2014/15 | 2014/15 | 999363 | 999363 | 999363 | Equitable | N/A | 999363 | 0 | 1199995 | 120.1 | 1199995 | 999363 | -200632 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes but didn't meet to he needs of the area residents. Assessor remarks: Project not started.
3435 | Construction Of Emitik ECD Classroom | Construction Of Emitik ECD Classroom | To construct Emitik ECD Classroom | Emitik ECD Classroom constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Kiptagich | -0.63565 35.6059 2318.2000000000003 14.899999618530273 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1200000 | 1199740 | 1199740 | Equitable | N/A | 1199740 | 0 | 1199995 | 100 | 1199995 | 1799740 | -255 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Yes but needs not met. Assessor remarks: Uncompleted and can't be used.
3436 | Construction Of Kipkebei ECD Class | Construction Of Kipkebei ECD Class | To construct Kipkebei ECD Class | Kipkebei ECD Class constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Kiptagich | -0.536993 35.578477 2446.5 5.900000095367432 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1100000 | 1047500 | 1047500 | Equitable | N/A | 1047500 | 0 | 1199995 | 114.6 | 1199995 | 1047500 | -152495 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes but didn't meet to he needs of the area residents. Assessor remarks: Project not started.
3437 | Construction Of Lelpanga ECD Class | Construction Of Lelpanga ECD Class | To construct Lelpanga ECD Class | Lelpanga ECD Class constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Kiptagich | -0.536993 35.578477 2446.5 5.900000095367432 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1147660 | 95.6 | 1147660 | 1800000 | 52340 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes but didn't meet to he needs of the area residents. Assessor remarks: Project not started.
3438 | Construction Of Ole Tachasis ECD Class | Construction Of Ole Tachasis ECD Class | To construct Ole Tachasis ECD Class | Ole Tachasis ECD Class constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Kiptagich | -0.63565 35.6059 2318.2000000000003 14.899999618530273 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1157750 | 1157750 | Equitable | N/A | 1157750 | 0 | 1147660 | 99.1 | 1147660 | 1200000 | 10090 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Yes but needs not met. Assessor remarks: Uncompleted and can't be used.
3439 | Construction Of One Classroom At Sukutek ECDE | Construction Of One Classroom At Sukutek ECDE | To construct One Classroom At Sukutek ECDE | One Classroom At Sukutek ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Kiptagich | -0.536993 35.578477 2446.5 5.900000095367432 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199995 | 100 | 1199995 | 1200000 | 5 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes but didn't meet to he needs of the area residents. Assessor remarks: Project not started.
3440 | Construction Of Sitotwet ECD Classroom | Construction Of Sitotwet ECD Classroom | To construct Sitotwet ECD Classroom | Sitotwet ECD Classroom constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Kiptagich | -0.598048 35.611248 2413 13.800000190734863 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1200000 | 202597 | 202597 | Equitable | N/A | 202597 | 0 | 1199995 | 592.3 | 1199995 | 202597 | -997398 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Don't know. Assessor remarks: The project is complete but there are no toilets.
3441 | Chemare ECD - Design And Construction Of 1. No ECD Classroom At Kipkoimet ECD | Chemare ECD - Design And Construction Of 1. No ECD Classroom At Kipkoimet ECD | To implement chemare ecd - design and construction of 1. no ecd classroom at kipkoimet ecd for access to quality education and training | Chemare ECD - Design And Construction Of 1. No ECD Classroom At Kipkoimet ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Kiptororo | -0.374828 35.553043 2592.5 3.799999952316284 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2017/18 | 2017/18 | N/A | 1200000 | 376428 | 376428 | Equitable | N/A | 376428 | 0 | 648869 | 172.4 | 648869 | 376428 | -272441 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: No. Assessor remarks: The project is complete but poorly sited, structure not in use..
3442 | Construction and equipping of Chepuyet ECD | Construction and equipping of Chepuyet ECD | To construct and equip Chepuyet ECD | Chepuyet ECD constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Kiptororo | -0.376934, 35.529857 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 516100 | 34.4 | 516100 | 941950 | 983900 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3443 | Construction and equipping of Kiamashamba ECD | Construction and equipping of Kiamashamba ECD | To construct and equip Kiamashamba ECD | Kiamashamba ECD constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Kiptororo | -0.376934, 35.529857 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1317150 | 87.8 | 1317150 | 136020 | 182850 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3444 | Construction Of An ECD Classroom At Chebuiyot | Construction Of An ECD Classroom At Chebuiyot | To construct An ECD Classroom At Chebuiyot | An ECD Classroom At Chebuiyot constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Kiptororo | -0.376802 35.529802 2495.7 15.600000381469727 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499880 | 100 | 1499880 | 1000000 | 120 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The classroom is complete and in use.
3445 | Construction Of Classroom At Kio ECD | Construction Of Classroom At Kio ECD | To construct Classroom At Kio ECD | Classroom At Kio ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Kiptororo | -0.325313, 35.500022 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1199980 | 1199980 | Equitable | N/A | 1199980 | 0 | 1199980 | 100 | 1199980 | 1199980 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yess. Viable: Yess but requires ECD toilet as per the pho information.
3446 | Construction Of Classroom At Kipkewa ECD | Construction Of Classroom At Kipkewa ECD | To construct Classroom At Kipkewa ECD | Classroom At Kipkewa ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Kiptororo | -0.325313, 35.500022 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1151750 | 1151750 | Equitable | N/A | 1151750 | 0 | 1151750 | 100 | 1151750 | 1151750 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yess. Viable: Yess but requires ECD toilet as per the pho information.
3447 | Construction Of Classroom At Kongoi ECD | Construction Of Classroom At Kongoi ECD | To construct Classroom At Kongoi ECD | Classroom At Kongoi ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Kiptororo | -0.325313, 35.500022 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1199898 | 1199898 | Equitable | N/A | 1199898 | 0 | 1198898 | 99.9 | 1198898 | 1199898 | 1000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yess. Viable: Yess but requires ECD toilet as per the pho information.
3448 | Construction Of Classroom At Seguton ECD | Construction Of Classroom At Seguton ECD | To construct Classroom At Seguton ECD | Classroom At Seguton ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Kiptororo | -0.325313, 35.500022 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1199830 | 1199830 | Equitable | N/A | 1199830 | 0 | 1199830 | 100 | 1199830 | 1199830 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yess. Viable: Yess but requires ECD toilet as per the pho information.
3449 | Construction Of Classroom At Taragonik ECD | Construction Of Classroom At Taragonik ECD | To construct Classroom At Taragonik ECD | Classroom At Taragonik ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Kiptororo | -0.325313, 35.500022 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1151750 | 1151750 | Equitable | N/A | 1151750 | 0 | 1151750 | 100 | 1151750 | 1151750 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yess. Viable: Yess but requires ECD toilet as per the pho information.
3450 | Construction of 5 day care classrooms at Lakeview ECDE | Construction of 5 day care classrooms at Lakeview ECDE | To construct 5 day care classrooms at Lakeview ECDE | 5 day care classrooms at Lakeview ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Lakeview | -0.733707, 36.434517 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2022/23 | 7500000 | 0 | 7500000 | Equitable | N/A | 7500000 | 0 | 7157555 | 100 | 7157555 | 465 | -7157555 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Yed.
3451 | Construction Of One ECDE Classroom At Unity Primary | Construction Of One ECDE Classroom At Unity Primary | To construct One ECDE Classroom At Unity Primary | One ECDE Classroom At Unity Primary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Lakeview | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 7157555 | 596.5 | 7157555 | 1200000 | -5957555 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
3452 | Construction of two ECDE classsrooms at Unity ECD | Construction of two ECDE classsrooms at Unity ECD | To construct two ECDE classsrooms at Unity ECD | Two ECDE classsrooms at Unity ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Lakeview | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | N/A | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 7157555 | 100 | 7157555 | 3000000 | -7157555 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
3453 | Design And Construction ECD Classroom And Equipping At Umoja Primary School | Design And Construction ECD Classroom And Equipping At Umoja Primary School | To design and construct ECD Classroom And Equipping At Umoja Primary School | ECD Classroom And Equipping At Umoja Primary School designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Bahati | Lanet/Umoja | -0.269832, 36.164046 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | 2020/2021 | 1800000 | 1680900 | 1680900 | Equitable | N/A | 1680900 | 0 | 1695002 | 100.8 | 1695002 | 1800000 | -14102 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes.
3454 | Construction Of Classroom At Prison ECD | Construction Of Classroom At Prison ECD | To construct Classroom At Prison ECD | Classroom At Prison ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | London | -0.273641, 36.058444 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 221 | 221 | Equitable | N/A | 221 | 0 | 221 | 100 | 221 | 221 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3455 | Construction Of Classroom At Uhuru Primary ECD | Construction Of Classroom At Uhuru Primary ECD | To construct Classroom At Uhuru Primary ECD | Classroom At Uhuru Primary ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | London | -0.273641, 36.058444 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1480 | 1480 | Equitable | N/A | 1480 | 0 | 221 | 14.9 | 221 | 1480 | 1259 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3456 | Construction of ECDE classroom and Toilet and Equipping at Moi Primary School | Construction of ECDE classroom and Toilet and Equipping at Moi Primary School | To construct ECDE classroom and Toilet and Equipping at Moi Primary School | ECDE classroom and Toilet and Equipping at Moi Primary School constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | London | -0.277232 36.067338 1862.4909989898247 8 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | N/A | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 1480 | 0.1 | 1480 | 1763240 | 1798520 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: ..
3457 | 1 ECD Class At Ngeya Primary | 1 ECD Class At Ngeya Primary | To implement 1 ecd class at ngeya primary for access to quality education and training | 1 ECD Class At Ngeya Primary completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maai Mahiu | -0.979769, 36.583913 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 955540 | 79.6 | 955540 | 1200000 | 244460 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3458 | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Ereri ECD | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Ereri ECD | To construct 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Ereri ECD | 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Ereri ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maai Mahiu | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1200001 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199672 | 100 | 1199672 | 1199240 | 328 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
3459 | Construction of a Polytechnic at Maai Mahiu | Construction of a Polytechnic at Maai Mahiu | To construct a Polytechnic at Maai Mahiu | A Polytechnic at Maai Mahiu constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maai Mahiu | -0.990353, 36.586414 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | N/A | 10000000 | 10000000 | 10000000 | Equitable | N/A | 10000000 | 0 | 8116489 | 81.2 | 8116489 | 1782181 | 1883511 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Once operational hands on courses will be offered and the objective will be met.. Viable: Yes..
3460 | Design And Construction Of Karima Pry ECDE | Design And Construction Of Karima Pry ECDE | To design and construct Karima Pry ECDE | Karima Pry ECDE designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maai Mahiu | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | 2021/22 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1182650 | 98.6 | 1182650 | 30 | 17350 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3461 | Design And Construction Of Nyakinyua ECDE | Design And Construction Of Nyakinyua ECDE | To design and construct Nyakinyua ECDE | Nyakinyua ECDE designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maai Mahiu | -1.064995, 36.535631 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 818350 | 68.2 | 818350 | 1200000 | 381650 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes..
3462 | Design And Construction Of Rare ECDE | Design And Construction Of Rare ECDE | To design and construct Rare ECDE | Rare ECDE designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maai Mahiu | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | 2021/22 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1177460 | 98.1 | 1177460 | 30 | 22540 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3463 | Completion Of A Polytechnic At Kipkonyo | Completion Of A Polytechnic At Kipkonyo | To complete A Polytechnic At Kipkonyo | A Polytechnic At Kipkonyo completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maiella | -0.892283 36.198894 2353.60009765625 10 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 4000000 | 577071 | 3894092 | Equitable | N/A | 3894092 | 0 | 3894092 | 674.8 | 3894092 | 577071 | -3317021 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Damaged windows and floor.
3464 | Completion Of A Polytechnic At Ndabibi | Completion Of A Polytechnic At Ndabibi | To complete A Polytechnic At Ndabibi | A Polytechnic At Ndabibi completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maiella | -0.804803 36.246244 0 22.5 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 4000000 | 105908 | 105908 | Equitable | N/A | 105908 | 0 | 3894092 | 3676.9 | 3894092 | 105908 | -3788184 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Eruc Africa Ltd. Assessor remarks: In use.
3465 | Completion Of A Polytechnic In Maiella | Completion Of A Polytechnic In Maiella | To complete A Polytechnic In Maiella | A Polytechnic In Maiella completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maiella | -0.892283 36.198894 2353.60009765625 10 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 172500 | 172500 | Equitable | N/A | 172500 | 0 | 826780 | 479.3 | 826780 | 172500 | -654280 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Damaged windows and floor.
3466 | Construction and equipping of 1 ECD classroom at Nkapani | Construction and equipping of 1 ECD classroom at Nkapani | To construct and equip 1 ECD classroom at Nkapani | 1 ECD classroom at Nkapani constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maiella | -0.831127 36.203445 2035.699951171875 87.5999984741211 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2022/23 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 2499394 | 166.6 | 2499394 | 1500000 | -999394 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Josliz Enterprises. Assessor remarks: on good condition.
3467 | Construction Of 2 ECD Classes At Tumaini | Construction Of 2 ECD Classes At Tumaini | To construct 2 ECD Classes At Tumaini | 2 ECD Classes At Tumaini constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maiella | -0.831127 36.203445 2035.699951171875 87.5999984741211 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 2500000 | 2499394 | 2499394 | Equitable | N/A | 2499394 | 0 | 2499394 | 100 | 2499394 | 2499394 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Josliz Enterprises. Assessor remarks: on good condition.
3468 | Construction Of 2 ECD Classrooms In Tangi Tatu | Construction Of 2 ECD Classrooms In Tangi Tatu | To construct 2 ECD Classrooms In Tangi Tatu | 2 ECD Classrooms In Tangi Tatu constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maiella | -0.831127 36.203445 2035.699951171875 87.5999984741211 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | 2021/22 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2499394 | 100 | 2499394 | 2399999 | 606 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Josliz Enterprises. Assessor remarks: on good condition.
3469 | Construction of 2 no ECDE classrroms at Moi Ndabi ECDE | Construction of 2 no ECDE classrroms at Moi Ndabi ECDE | To construct 2 no ECDE classrroms at Moi Ndabi ECDE | 2 no ECDE classrroms at Moi Ndabi ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maiella | -0.804803 36.246244 0 22.5 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | N/A | 2400000 | 0 | 2400000 | Equitable | N/A | 2400000 | 0 | 2499394 | 0 | 2499394 | 2400000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Eruc Africa Ltd. Assessor remarks: In use.
3470 | Construction Of ECD Classroom And 2 Door Toilet At Emmanuel And Ndabibi Primary School | Construction Of ECD Classroom And 2 Door Toilet At Emmanuel And Ndabibi Primary School | To construct ECD Classroom And 2 Door Toilet At Emmanuel And Ndabibi Primary School | ECD Classroom And 2 Door Toilet At Emmanuel And Ndabibi Primary School constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maiella | -0.831127 36.203445 2035.699951171875 87.5999984741211 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Josliz Enterprises. Assessor remarks: on good condition.
3471 | Design And Construction Of ECD Classroom At Natooli | Design And Construction Of ECD Classroom At Natooli | To design and construct ECD Classroom At Natooli | ECD Classroom At Natooli designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maiella | -0.831127 36.203445 2035.699951171875 87.5999984741211 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2499394 | 100 | 2499394 | 2500000 | 606 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Josliz Enterprises. Assessor remarks: on good condition.
3472 | Design And Construction Of ECD Classroom At Ndabibi Central | Design And Construction Of ECD Classroom At Ndabibi Central | To design and construct ECD Classroom At Ndabibi Central | ECD Classroom At Ndabibi Central designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maiella | -0.831127 36.203445 2035.699951171875 87.5999984741211 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | 2020/21 | 2739065 | 2739065 | 2739065 | Equitable | N/A | 2739065 | 0 | 2499394 | 91.2 | 2499394 | 2739065 | 239671 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Josliz Enterprises. Assessor remarks: on good condition.
3473 | Design And Construction Of ECD Classroom At Ngondi | Design And Construction Of ECD Classroom At Ngondi | To design and construct ECD Classroom At Ngondi | ECD Classroom At Ngondi designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maiella | -0.831127 36.203445 2035.699951171875 87.5999984741211 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2499394 | 100 | 2499394 | 2500000 | 606 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Josliz Enterprises. Assessor remarks: on good condition.
3474 | Nkampani Nursery School | Nkampani Nursery School | To implement nkampani nursery school for access to quality education and training | Nkampani Nursery School completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Maiella | -0.920628 36.204578 2270.4 7.5 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 2400000 | 2297135 | 2297135 | Equitable | N/A | 2297135 | 0 | 0 | 0 | 0 | 997135 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Fabrica Construction Co Ltd. Assessor remarks: Yet to be handed over.
3475 | Construction of classroom, toilets, terrazzo floor, furniture and tank with gutters in Marula ECD | Construction of classroom, toilets, terrazzo floor, furniture and tank with gutters in Marula ECD | To construct classroom, toilets, terrazzo floor, furniture and tank with gutters in Marula ECD | Classroom, toilets, terrazzo floor, furniture and tank with gutters in Marula ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Malewa West | -0.684685 36.417015 0 2000 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: N//A. Viable: N//A. Assessor remarks: N//A.
3476 | Construction And Equipping Of Tuiyobei ECD Classrooms, Toilets And Water Tank | Construction And Equipping Of Tuiyobei ECD Classrooms, Toilets And Water Tank | To construct and equip Tuiyobei ECD Classrooms, Toilets And Water Tank | Tuiyobei ECD Classrooms, Toilets And Water Tank constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Mariashoni | -0.349579, 35.801559 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1914000 | 95.7 | 1914000 | 2000000 | 86000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes.
3477 | Construction Of 1 Kiplelmoi ECD Classrooms, Toilets, Purchase Of Equipments And Water Tank | Construction Of 1 Kiplelmoi ECD Classrooms, Toilets, Purchase Of Equipments And Water Tank | To construct 1 Kiplelmoi ECD Classrooms, Toilets, Purchase Of Equipments And Water Tank | 1 Kiplelmoi ECD Classrooms, Toilets, Purchase Of Equipments And Water Tank constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Mariashoni | -0.343994, 35.846228 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 1999952 | 1999952 | Equitable | N/A | 1999952 | 0 | 1996707 | 99.8 | 1996707 | 1999952 | 3245 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3478 | Construction of a class and a Toilet plus equipping (Kamungei Primary ECD) | Construction of a class and a Toilet plus equipping (Kamungei Primary ECD) | To construct a class and a Toilet plus equipping (Kamungei Primary ECD) | A class and a Toilet plus equipping (Kamungei Primary ECD) constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Mariashoni | -0.338892 35.806045 2586 6 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2022/23 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1990590 | 99.5 | 1990590 | 1990590 | 9410 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partly. Viable: Partly. Assessor remarks: Toiler not contructed.
3479 | Construction Of Classroom At Rombei ECDE, Oinoptich ECDE, Ndoswa ECDE And Timoo ECDE | Construction Of Classroom At Rombei ECDE, Oinoptich ECDE, Ndoswa ECDE And Timoo ECDE | To construct Classroom At Rombei ECDE, Oinoptich ECDE, Ndoswa ECDE And Timoo ECDE | Classroom At Rombei ECDE, Oinoptich ECDE, Ndoswa ECDE And Timoo ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Mariashoni | -0.353645, 35.870354 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | N/A | 5200000 | 5200000 | 5200000 | Equitable | N/A | 5200000 | 0 | 2599800 | 50 | 2599800 | 5199600 | 2600200 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3480 | Construction Of ECDE Classroom At Block Ten | Construction Of ECDE Classroom At Block Ten | To construct ECDE Classroom At Block Ten | ECDE Classroom At Block Ten constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Mariashoni | -0.396822, 35.792966 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1177200 | 1177200 | Equitable | N/A | 1177200 | 0 | 801480 | 68.1 | 801480 | 1177200 | 375720 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3481 | Construction Of ECDE Classroom At Kapmungei | Construction Of ECDE Classroom At Kapmungei | To construct ECDE Classroom At Kapmungei | ECDE Classroom At Kapmungei constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Mariashoni | -0.396822, 35.792966 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1400000 | 260 | 260 | Equitable | N/A | 260 | 0 | 260 | 100 | 260 | 260 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3482 | Construction Of Kalyet ECDE Classroom | Construction Of Kalyet ECDE Classroom | To construct Kalyet ECDE Classroom | Kalyet ECDE Classroom constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Mariashoni | -0.353608 35.870252 2418.508656566576 7.5 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1177200 | 1177200 | Equitable | N/A | 1177200 | 0 | 1177200 | 100 | 1177200 | 1177200 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Poor flooring therefore not functioning.
3483 | Design And Construction Of Classroom At Lawina ECDE And Toilets | Design And Construction Of Classroom At Lawina ECDE And Toilets | To design and construct Classroom At Lawina ECDE And Toilets | Classroom At Lawina ECDE And Toilets designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Mariashoni | -0.341599 35.822118 2558.0320406425963 6.5 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 1900000 | 1900000 | Equitable | N/A | 1900000 | 0 | 1900000 | 100 | 1900000 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
3484 | Construction Of 2 ECDE Classrooms For Ngwataninro Primary School | Construction Of 2 ECDE Classrooms For Ngwataninro Primary School | To construct 2 ECDE Classrooms For Ngwataninro Primary School | 2 ECDE Classrooms For Ngwataninro Primary School constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Mau Narok | -0.597728 35.995954 0 20 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 2400000 | 2381998 | 2381998 | Equitable | N/A | 2381998 | 0 | 2381998 | 100 | 2381998 | 2400000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Viable. Assessor remarks: Need repair for door and windows.
3485 | Construction Of An ECDE Classroom And Pit Latrines At Ikinu | Construction Of An ECDE Classroom And Pit Latrines At Ikinu | To construct An ECDE Classroom And Pit Latrines At Ikinu | An ECDE Classroom And Pit Latrines At Ikinu constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Mau Narok | -0.5959, 36.0151 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | 2021/22 | 1800000 | 146540 | 146540 | Equitable | N/A | 146540 | 0 | 1799800 | 1228.2 | 1799800 | 146540 | -1653260 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: viable.
3486 | Completion and equipping of Sigor ECD | Completion and equipping of Sigor ECD | To complete and equip Sigor ECD | Sigor ECD completed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Mauche | -0.547133, 36.008833 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2017 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 992000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Not known.
3487 | Construction and equipping of Mauche ECD, Teret ECD, Tuiyotich and Tachasis ECD | Construction and equipping of Mauche ECD, Teret ECD, Tuiyotich and Tachasis ECD | To construct and equip Mauche ECD, Teret ECD, Tuiyotich and Tachasis ECD | Mauche ECD, Teret ECD, Tuiyotich and Tachasis ECD constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Mauche | -0.502886, 35.974852 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2023 | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 1984380 | 33.1 | 1984380 | 3711580 | 4015620 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Not known.
3488 | Design And Construction Classroom At Chesoen ECDE | Design And Construction Classroom At Chesoen ECDE | To design and construct Classroom At Chesoen ECDE | Classroom At Chesoen ECDE designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Mauche | -0.543632, 36.030652 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | 2021 | 1200000 | 1099992 | 1099992 | Equitable | N/A | 1099992 | 0 | 1099992 | 100 | 1099992 | 1200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known.
3489 | Building and equipping of a workshop in Mangu Polytechnic | Building and equipping of a workshop in Mangu Polytechnic | To implement building and equipping of a workshop in mangu polytechnic for access to quality education and training | Building and equipping of a workshop in Mangu Polytechnic completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Menengai West | -0.225332 35.972693 1934.5 10.600000381469727 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2022/23 | 3600000 | 3600000 | 3600000 | Equitable | N/A | 3600000 | 0 | 3423400 | 95.1 | 3423400 | 3423400 | 176600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need more chairs and desks.
3490 | Completion Of Stalled Classes And Rehabilitation Of Existing Classes At Ol Rongai Polytechnic | Completion Of Stalled Classes And Rehabilitation Of Existing Classes At Ol Rongai Polytechnic | To complete Stalled Classes And Rehabilitation Of Existing Classes At Ol Rongai Polytechnic | Stalled Classes And Rehabilitation Of Existing Classes At Ol Rongai Polytechnic completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Menengai West | -0.168652, 36.0002 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2995421 | 99.8 | 2995421 | 3000000 | 4579 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3491 | Construction Of 2. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Kiamungei ECD | Construction Of 2. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Kiamungei ECD | To construct 2. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Kiamungei ECD | 2. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Kiamungei ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Menengai West | -0.210933 36.023718 2043.9000244140625 5.300000190734863 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2400000 | 1144900 | 1144900 | Equitable | N/A | 1144900 | 0 | 2399880 | 209.6 | 2399880 | 1144900 | -1254980 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
3492 | Construction and equipping of ECDE classroom at Molo Academy | Construction and equipping of ECDE classroom at Molo Academy | To construct and equip ECDE classroom at Molo Academy | ECDE classroom at Molo Academy constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Molo | -0.380641 35.796196 2793.679531111378 6 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 874210 | 58.3 | 874210 | 1447082 | 625790 | Vired | 25 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Partially. Viable: Partially. Assessor remarks: The toilet is non existent.
3493 | Upgrading of Former Mukinyai Nursery school to be an Annex Polytechnic | Upgrading of Former Mukinyai Nursery school to be an Annex Polytechnic | To upgrade Former Mukinyai Nursery school to be an Annex Polytechnic through tarmacking for improved road connectivity | Former Mukinyai Nursery school to be an Annex Polytechnic tarmacked and upgraded | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Molo | -0.205493 35.796119 0 500 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 1963020 | 0 | Stalled | 0 | N/A | needs more allocation of funds | 2022 | N/A | N/A | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yet to be. Assessor remarks: Formerly ECD , converted to polytechnic.
3494 | Construction Of An ECDE Classroom And Water Tank At Borop And Nguzu River Primary School In Sachang'Wan | Construction Of An ECDE Classroom And Water Tank At Borop And Nguzu River Primary School In Sachang'Wan | To construct An ECDE Classroom And Water Tank At Borop And Nguzu River Primary School In Sachang'Wan | An ECDE Classroom And Water Tank At Borop And Nguzu River Primary School In Sachang'Wan constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Molo Central | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | N/A | 2600000 | 2600000 | 2600000 | Equitable | N/A | 2600000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
3495 | Construction Of ECDE Classroom, Toilets And Water Tank At Tayari Primary School In Molo Town | Construction Of ECDE Classroom, Toilets And Water Tank At Tayari Primary School In Molo Town | To construct ECDE Classroom, Toilets And Water Tank At Tayari Primary School In Molo Town | ECDE Classroom, Toilets And Water Tank At Tayari Primary School In Molo Town constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Molo Central | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | N/A | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
3496 | Construction Of Kabunia Highway ECD Classroom | Construction Of Kabunia Highway ECD Classroom | To construct Kabunia Highway ECD Classroom | Kabunia Highway ECD Classroom constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Molo Central | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1199779 | 1199779 | Equitable | N/A | 1199779 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
3497 | Completion of Chepseon ECDE Classroom | Completion of Chepseon ECDE Classroom | To complete Chepseon ECDE Classroom | Chepseon ECDE Classroom completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Mosop | -0.209656, 35.841459 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2023 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 1200000 | 240 | 1200000 | 500000 | -700000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Not viable. Contractor: Yet to start to advertise.
3498 | Construction and equipping of one ECDE Classroom at Kirobon primary school | Construction and equipping of one ECDE Classroom at Kirobon primary school | To construct and equip one ECDE Classroom at Kirobon primary school | One ECDE Classroom at Kirobon primary school constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Mosop | -0.290892, 35.986887 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2023 | 1700000 | 1700000 | 1700000 | Equitable | N/A | 1700000 | 0 | 1670660 | 98.3 | 1670660 | 1670660 | 29340 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yed. Viable: Viable. Contractor: M/s Gold.
3499 | Construction of Wardai Polytechnic | Construction of Wardai Polytechnic | To construct Wardai Polytechnic | Wardai Polytechnic constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Mosop | -0.285402 35.892338 2173.4 20.5 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 499994 | 25 | 499994 | 2000000 | 1500006 | Stalled | 90 | 25 | Stalled — reasons to be confirmed by department | 2022 | N/A | 1500006 | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Kefalice. Assessor remarks: Good.
3500 | Construction of Youth Polytechnic Classrooms at Mimwata Public Land | Construction of Youth Polytechnic Classrooms at Mimwata Public Land | To construct Youth Polytechnic Classrooms at Mimwata Public Land | Youth Polytechnic Classrooms at Mimwata Public Land constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Mosop | -0.241648, 35.909491 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2023 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2951680 | 98.4 | 2951680 | 2911820 | 48320 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: M/S Gold.
3501 | Construction of Nyairoko - Kairi ECDE | Construction of Nyairoko - Kairi ECDE | To construct Nyairoko - Kairi ECDE | Nyairoko - Kairi ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Murindat | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1200000 | 80 | 1200000 | 1500000 | 300000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
3502 | Construction Of One ECDE Classroom At Murindat Primary | Construction Of One ECDE Classroom At Murindat Primary | To construct One ECDE Classroom At Murindat Primary | One ECDE Classroom At Murindat Primary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Murindat | -0.412435, 36.311654 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | 2024/25 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1198820 | 99.9 | 1198820 | 1200000 | 1180 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yet to start. Viable: Not done l as a.
3503 | Wanguhu ECDE Classroom - Design And Construction Of Wanguhu ECDE 1 Classroom | Wanguhu ECDE Classroom - Design And Construction Of Wanguhu ECDE 1 Classroom | To implement wanguhu ecde classroom - design and construction of wanguhu ecde 1 classroom for access to quality education and training | Wanguhu ECDE Classroom - Design And Construction Of Wanguhu ECDE 1 Classroom completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Gilgil | Murindat | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 1500000 | 290000 | 290000 | Equitable | N/A | 290000 | 0 | 1210000 | 417.2 | 1210000 | 290000 | -920000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3504 | Construction and equipping of an ECD Classroom at Munyu | Construction and equipping of an ECD Classroom at Munyu | To construct and equip an ECD Classroom at Munyu | An ECD Classroom at Munyu constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Naivasha East | -0.826406 36.536507 2471.60009765625 5.800000190734863 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 2999064 | 199.9 | 2999064 | 1473625 | -1499064 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes. Assessor remarks: Project was not done.
3505 | Construction Of ECD Class At Karai | Construction Of ECD Class At Karai | To construct ECD Class At Karai | ECD Class At Karai constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Naivasha East | -0.760113, 36.49383 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2017-18 | 1000000 | 999532 | 999532 | Equitable | N/A | 999532 | 0 | 999352 | 100 | 999352 | 1000000 | 180 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3506 | Construction And Equipping Of Mwega Polytechnic | Construction And Equipping Of Mwega Polytechnic | To construct and equip Mwega Polytechnic | Mwega Polytechnic constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Naivasha East | -0.826406 36.536507 2471.60009765625 5.800000190734863 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2999064 | 100 | 2999064 | 3000000 | 936 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes. Assessor remarks: Project was not done.
3507 | Construction of Mzee Wanyama Polytechnic | Construction of Mzee Wanyama Polytechnic | To construct Mzee Wanyama Polytechnic | Mzee Wanyama Polytechnic constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru East | Nakuru East | -0.372659, 36.149715 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2023/2024 | 5445927 | 5445927 | 5445927 | Equitable | N/A | 5445927 | 0 | 5025850 | 92.3 | 5025850 | 5000000 | 420077 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Fino limited.
3508 | Construction Of Vocational Polytechnic At Free Area | Construction Of Vocational Polytechnic At Free Area | To construct Vocational Polytechnic At Free Area | Vocational Polytechnic At Free Area constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru East | Nakuru East | -0.293514 36.118728 1839.199951171875 37.99700164794922 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 10000000 | 4344590 | 4344590 | Equitable | N/A | 4344590 | 0 | 5025850 | 115.7 | 5025850 | 4344590 | -681260 | Stalled | 75 | 100 | Stalled — reasons to be confirmed by department | 2019 | N/A | -681260 | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Belistra enterprises ltd. Assessor remarks: No occupation certificate issued.
3509 | Construction Of One Classroom At James Mwaniki Primary School | Construction Of One Classroom At James Mwaniki Primary School | To construct One Classroom At James Mwaniki Primary School | One Classroom At James Mwaniki Primary School constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru East | Nakuru East | -0.445208, 36.146617 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | 2020/2021 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 2715032 | 226.3 | 2715032 | 1200000 | -1515032 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes.
3510 | Design And Construction Of 1 ECDE Classroom At Naka Primary | Design And Construction Of 1 ECDE Classroom At Naka Primary | To design and construct 1 ECDE Classroom At Naka Primary | 1 ECDE Classroom At Naka Primary designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru East | Nakuru East | -0.289113 36.103626 1817.699951171875 6.599999904632568 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | 2020/21 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 2715032 | 226.3 | 2715032 | 1200000 | -1515032 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require funds more funds for completion.
3511 | Completion of Inginge ECD | Completion of Inginge ECD | To complete Inginge ECD | Inginge ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Nessuit | -0.401883 35.907934 2429.297805547889 4.23799991607666 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 476480 | 0 | Vired | 25 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Classroom was constructed till the lintel stage and stalled, community members then demolished the structure. Another allocation of funds was done to redo the work.
3512 | Tiritagoi ECD - Construction Of 1 Classroom | Tiritagoi ECD - Construction Of 1 Classroom | To implement tiritagoi ecd - construction of 1 classroom for access to quality education and training | Tiritagoi ECD - Construction Of 1 Classroom completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Nessuit | -0.417516 35.906162 2476.5755676023055 30 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2017/18 | 2017/18 | N/A | 1300000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 1199431 | 92.3 | 1199431 | 1300000 | 100569 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: Yes. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The classroom is being used but not finished yet. The classroom environment is injurious to the pupils.
3513 | Design And Construction Of Kimugui ECDE Classroom | Design And Construction Of Kimugui ECDE Classroom | To design and construct Kimugui ECDE Classroom | Kimugui ECDE Classroom designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Nessuit | -0.433627 35.887802 2581.822998046875 4.065000057220459 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199431 | 100 | 1199431 | 569 | 569 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The ECDE is a stand alone school. The classroom construction did not meet the standards and therefore the amount allocated didn't meet the required scope of work..
3514 | Design And Construction Of Korovio ECDE Classroom | Design And Construction Of Korovio ECDE Classroom | To design and construct Korovio ECDE Classroom | Korovio ECDE Classroom designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Nessuit | -0.410761 35.899338 2463.547607421875 10.36299991607666 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1200000 | 1105445 | 1105445 | Equitable | N/A | 1105445 | 0 | 1199431 | 108.5 | 1199431 | 1105445 | -93986 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The contractor has never completed the project and is evasive. The ECDE started as a stand alone and after the primary school coming up it used a different name, therefore reconciliation of the school and ECDE name should done. Currently there pupils are using a temporary structure which was constructed by funds from parents..
3515 | Design And Construction Of Masaita ECDE Classroom And Toilets | Design And Construction Of Masaita ECDE Classroom And Toilets | To design and construct Masaita ECDE Classroom And Toilets | Masaita ECDE Classroom And Toilets designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Nessuit | -0.356677 35.883444 2389.259997959072 5.46999979019165 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1500000 | 1105445 | 1105445 | Equitable | N/A | 1105445 | 0 | 1199431 | 108.5 | 1199431 | 1105445 | -93986 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: MARKVEC ENT LIMITED. Assessor remarks: Poor workmanship and there is no latrine constructed.
3516 | Design And Construction Of Missipei ECDE Classroom And Toilets | Design And Construction Of Missipei ECDE Classroom And Toilets | To design and construct Missipei ECDE Classroom And Toilets | Missipei ECDE Classroom And Toilets designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Nessuit | -0.375545 35.875101 2486.6005859375 3.7899999618530273 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1500000 | 1105445 | 1105445 | Equitable | N/A | 1105445 | 0 | 1199431 | 108.5 | 1199431 | 1105445 | -93986 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Construction incomplete, no toilets constructed as per the description.
3517 | Completion and equipping of an ECDE at Tarakuet | Completion and equipping of an ECDE at Tarakuet | To complete and equip an ECDE at Tarakuet | An ECDE at Tarakuet completed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Njoro | -0.331569 35.953914 2141.900146484375 4.072999954223633 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 939950 | 94 | 939950 | 939950 | 60050 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Well done work.
3518 | Construction and equipping 1 ECD classroom at Njoro DEB Primary, Cheston Primary, Ndege Primary and Central Primary | Construction and equipping 1 ECD classroom at Njoro DEB Primary, Cheston Primary, Ndege Primary and Central Primary | To construct and equip 1 ECD classroom at Njoro DEB Primary, Cheston Primary, Ndege Primary and Central Primary | 1 ECD classroom at Njoro DEB Primary, Cheston Primary, Ndege Primary and Central Primary constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Njoro | -0.335879, 35.947758 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2023 | 6000000 | 6000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 5915880 | 98.6 | 5915880 | 5915880 | 84120 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Humble touch.
3519 | Construction Of ECD Classes In Mwigito Village | Construction Of ECD Classes In Mwigito Village | To construct ECD Classes In Mwigito Village | ECD Classes In Mwigito Village constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Njoro | -0.385759 35.95324 2212.000244140625 9.197999954223633 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1197000 | 99.8 | 1197000 | 1200000 | 3000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: Floor completely worn.
3520 | Construction Of ECD In Njokerio | Construction Of ECD In Njokerio | To construct ECD In Njokerio | ECD In Njokerio constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Njoro | -0.384841 35.935522 2275.121826171875 4.958000183105469 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 2996 | 2996 | Equitable | N/A | 2996 | 0 | 2996 | 100 | 2996 | 1199996 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: In good state.
3521 | Construction Of ECD In Njoro Township Primary | Construction Of ECD In Njoro Township Primary | To construct ECD In Njoro Township Primary | ECD In Njoro Township Primary constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Njoro | -0.326462, 35.954217 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2020 | 1200000 | 3396 | 3396 | Equitable | N/A | 3396 | 0 | 3396 | 100 | 3396 | 3396 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: No. Viable: Yes. Contractor: Weigh road Ltd.
3522 | Construction Of ECD In Sosiot Farm | Construction Of ECD In Sosiot Farm | To construct ECD In Sosiot Farm | ECD In Sosiot Farm constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Njoro | Njoro | -0.384685 35.935928 2293.6 10.100000381469727 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1800000 | 1798168 | 1798168 | Equitable | N/A | 1798168 | 0 | 1798168 | 100 | 1798168 | 1798168 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Contractor: na. Assessor remarks: good.
3523 | Completion Of Songo ECDE Classroom | Completion Of Songo ECDE Classroom | To complete Songo ECDE Classroom | Songo ECDE Classroom completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Nyota | -0.404183 35.662365 2637 14.899999618530273 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 261174 | 26.1 | 261174 | 998985 | 738826 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Sumcott Enterprises. Assessor remarks: Needs urgent painting.
3524 | Construction and Equipping of Githiriga ECDE | Construction and Equipping of Githiriga ECDE | To construct and equip Githiriga ECDE | Githiriga ECDE constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Nyota | -0.361508, 35.633747 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2023-2024 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 800000 | 53.3 | 800000 | 1469600 | 700000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3525 | Construction and Equipping of Kenjoketty ECDE | Construction and Equipping of Kenjoketty ECDE | To construct and equip Kenjoketty ECDE | Kenjoketty ECDE constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Nyota | -0.361508, 35.633747 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2023-2024 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 115000 | 7.7 | 115000 | 1469600 | 1385000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3526 | Construction and Equipping of Lelaitich ECDE | Construction and Equipping of Lelaitich ECDE | To construct and equip Lelaitich ECDE | Lelaitich ECDE constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Nyota | -0.361508, 35.633747 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2023-2024 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 115000 | 7.7 | 115000 | 1469600 | 1385000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3527 | Construction and Equipping of Nyongeres ECDE | Construction and Equipping of Nyongeres ECDE | To construct and equip Nyongeres ECDE | Nyongeres ECDE constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Nyota | -0.361508, 35.633747 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2023-2024 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 800000 | 53.3 | 800000 | 1469600 | 700000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3528 | Construction Of Mwahe ECDE | Construction Of Mwahe ECDE | To construct Mwahe ECDE | Mwahe ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Nyota | -0.377837 35.709362 2720.8 5.199999809265137 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | 2021/22 | 1319510 | 240600 | 240600 | Equitable | N/A | 240600 | 0 | 115000 | 47.8 | 115000 | 240600 | 125600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No- Was constructed far from other classes. Viable: No. Contractor: M/S WAMKONG CONSTRUCTION & SuPPLIES LTD. Assessor remarks: Needs renovation.
3529 | Construction Of One Class Room And Water Tank At Mukue, Matunda, Kumugul & Ndege/Kamuri ECDE | Construction Of One Class Room And Water Tank At Mukue, Matunda, Kumugul & Ndege/Kamuri ECDE | To construct One Class Room And Water Tank At Mukue, Matunda, Kumugul & Ndege/Kamuri ECDE | One Class Room And Water Tank At Mukue, Matunda, Kumugul & Ndege/Kamuri ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Nyota | -0.365508, 35.60519 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | 2023-2024 | 4800000 | 4800000 | 4800000 | Equitable | N/A | 4800000 | 0 | 2207393 | 46 | 2207393 | 2592607 | 2592607 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3530 | Construction Of Silibonik ECDE Classroom | Construction Of Silibonik ECDE Classroom | To construct Silibonik ECDE Classroom | Silibonik ECDE Classroom constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Nyota | -0.346288, 35.588013 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2021-2022 | 1200000 | 1199730 | 1199730 | Equitable | N/A | 1199730 | 0 | 1199975 | 100 | 1199975 | 1200000 | -245 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3531 | Design And Construction Of Kondamet ECDE Classroom | Design And Construction Of Kondamet ECDE Classroom | To design and construct Kondamet ECDE Classroom | Kondamet ECDE Classroom designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Nyota | -0.347828, 35.59568 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | 2021-2021 | 1200000 | 1147660 | 1147660 | Equitable | N/A | 1147660 | 0 | 1147660 | 100 | 1147660 | 1200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3532 | Design And Construction Of Teregena ECDE | Design And Construction Of Teregena ECDE | To design and construct Teregena ECDE | Teregena ECDE designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Nyota | -0.401607, 35.706659 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | 2021-2022 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199975 | 100 | 1199975 | 1200000 | 25 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3533 | Design And Construction Of Umoja ECDE Classroom | Design And Construction Of Umoja ECDE Classroom | To design and construct Umoja ECDE Classroom | Umoja ECDE Classroom designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Nyota | -0.347828, 35.59568 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | 2021-2021 | 1200000 | 1147660 | 1147660 | Equitable | N/A | 1147660 | 0 | 1147660 | 100 | 1147660 | 1200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3534 | Nyota Ward ECDs - Design And Construction Of 1.No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Chemorut, Mawingu, Masasita | Nyota Ward ECDs - Design And Construction Of 1.No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Chemorut, Mawingu, Masasita | To implement nyota ward ecds - design and construction of 1.no ecd classrooms, teachers toilet, pupils toilet and watering point at chemorut, mawingu, masasita for access to quality education and training | Nyota Ward ECDs - Design And Construction Of 1.No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Chemorut, Mawingu, Masasita completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Nyota | -0.3756, 35.726818 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2018-2019 | 4800000 | 800002 | 800002 | Equitable | N/A | 800002 | 0 | 1199999 | 150 | 1199999 | 800002 | -399997 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/S WESJOY GENERAL SUPPLIES..
3535 | Construction Of Olemayana Kubwa ECDE Class, Toilet Blocks And Equipping | Construction Of Olemayana Kubwa ECDE Class, Toilet Blocks And Equipping | To construct Olemayana Kubwa ECDE Class, Toilet Blocks And Equipping | Olemayana Kubwa ECDE Class, Toilet Blocks And Equipping constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Olkaria | -0.914466, 36.304362 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1195717 | 2491717 | 2491717 | Equitable | N/A | 2491717 | 0 | 2206597 | 88.6 | 2206597 | 285120 | 285120 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3536 | Mvuke ECD | Mvuke ECD | To implement mvuke ecd for access to quality education and training | Mvuke ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Olkaria | -0.836328 36.366422 1881.9000244140625 10.300000190734863 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1197887.77 | 1197888 | 1197888 | Equitable | N/A | 1197888 | 0 | 1151760 | 96.1 | 1151760 | 46128 | 46128 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No because it is not in use. Viable: Yes but doesn't meet the need of the residents. Assessor remarks: The class is complete but in a devastated state.
3537 | Construction and equipping of 3 ECDE classrooms at Maua Primary School, Shermoi Primary School and Oserian Primary school | Construction and equipping of 3 ECDE classrooms at Maua Primary School, Shermoi Primary School and Oserian Primary school | To construct and equip 3 ECDE classrooms at Maua Primary School, Shermoi Primary School and Oserian Primary school | 3 ECDE classrooms at Maua Primary School, Shermoi Primary School and Oserian Primary school constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Olkaria | -0.836914, 36.366297 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2022/23 | 4500000 | 4500000 | 4500000 | Equitable | N/A | 4500000 | 0 | 2633481 | 58.5 | 2633481 | 1765059 | 1866519 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes.the tank is being used from a different structure.
3538 | Construction and equipping of two ECDE Classrooms at Oldonyo Village | Construction and equipping of two ECDE Classrooms at Oldonyo Village | To construct and equip two ECDE Classrooms at Oldonyo Village | Two ECDE Classrooms at Oldonyo Village constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Olkaria | -0.835906 36.366334 1881.9000244140625 60 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2633481 | 87.8 | 2633481 | 2884850 | 366519 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes it was not in good status. Assessor remarks: Tank were used in different class.
3539 | Construction of a Vocational Training at Oldonyo Village | Construction of a Vocational Training at Oldonyo Village | To construct a Vocational Training at Oldonyo Village | A Vocational Training at Oldonyo Village constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Olkaria | -0.815472 36.322517 1881.300048828125 9.899999618530273 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | N/A | 12000000 | 12000000 | 12000000 | Equitable | N/A | 12000000 | 0 | 0 | 0 | 0 | 11890000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes if done it will benefit the youth. Assessor remarks: There was land issues thus not done.
3540 | Construction of Classroom and workshop at Mwariki Vocational Training Centre (one storey building) | Construction of Classroom and workshop at Mwariki Vocational Training Centre (one storey building) | To construct Classroom and workshop at Mwariki Vocational Training Centre (one storey building) | Classroom and workshop at Mwariki Vocational Training Centre (one storey building) constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | Rhonda | -0.313651, 36.067349 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 23/24 | 14000000 | 7000000 | 7000000 | Equitable | N/A | 7000000 | 0 | 6988412 | 99.8 | 6988412 | 0 | 11588 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/S CRANBERRY DESIGNERS LTD.
3541 | Construction and equipping of a high rise ECDE classroom block (3 classrooms) at Mama Ngina Primary | Construction and equipping of a high rise ECDE classroom block (3 classrooms) at Mama Ngina Primary | To construct and equip a high rise ECDE classroom block (3 classrooms) at Mama Ngina Primary | A high rise ECDE classroom block (3 classrooms) at Mama Ngina Primary constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | Shabab | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | N/A | 9000000 | 9000000 | 9000000 | Equitable | N/A | 9000000 | 0 | 0 | 0 | 0 | 8793630 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
3542 | Construction Of Three (3) ECDE Classrooms At Koinange Primary School, Equipping, Water Point And Toilets | Construction Of Three (3) ECDE Classrooms At Koinange Primary School, Equipping, Water Point And Toilets | To construct Three (3) ECDE Classrooms At Koinange Primary School, Equipping, Water Point And Toilets | Three (3) ECDE Classrooms At Koinange Primary School, Equipping, Water Point And Toilets constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | Shabab | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | N/A | 4500000 | 4500000 | 4500000 | Equitable | N/A | 4500000 | 0 | 2498895 | 55.5 | 2498895 | 4500000 | 2001105 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
3543 | Design And Construction Of ECDE Classroom, Toilet And Water Tank At Koinange Primary | Design And Construction Of ECDE Classroom, Toilet And Water Tank At Koinange Primary | To design and construct ECDE Classroom, Toilet And Water Tank At Koinange Primary | ECDE Classroom, Toilet And Water Tank At Koinange Primary designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Nakuru West | Shabab | -0.29293, 36.054277 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | 2020/21 | 1800000 | 746875 | 746875 | Equitable | N/A | 746875 | 0 | 744068 | 99.6 | 744068 | 746875 | 2807 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3544 | Construction & Equipping of Aeriol ECDE - 1 class | Construction & Equipping of Aeriol ECDE - 1 class | To construct & Equipping of Aeriol ECDE - 1 class | & Equipping of Aeriol ECDE - 1 class constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Sirikwa | -0.271818 35.668245 2737.4 4.400000095367432 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2022/23 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1880400 | 125.4 | 1880400 | 1959610 | -380400 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Njumuru Enterprises Ltd. Assessor remarks: The classroom is in use, however they have no county employed teacher, the classroom has terrazzo floor, well painted walls, electrical works done, however the roof appears to be leaking in some sections. The school has a small field, and no permanent water source.
3545 | Construction & Equipping of Kiletien ECDE - 1 class | Construction & Equipping of Kiletien ECDE - 1 class | To construct & Equipping of Kiletien ECDE - 1 class | & Equipping of Kiletien ECDE - 1 class constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Sirikwa | -0.235177 35.662557 2740.7999999999997 13.399999618530273 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2022/23 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1880400 | 125.4 | 1880400 | 1959610 | -380400 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Signs of leaking roof noted, peeling of Wall paint, gutters need fixing.
3546 | Construction Of Kiptenden Sirikwa ECD | Construction Of Kiptenden Sirikwa ECD | To construct Kiptenden Sirikwa ECD | Kiptenden Sirikwa ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi North | Sirikwa | -0.278465 35.661547 2738.7 13.399999618530273 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1199190 | 1199190 | Equitable | N/A | 1199190 | 0 | 1187070 | 99 | 1187070 | 1200000 | 12120 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The classroom is currently in use, however the classroom is being used by both PP1 and 2,pupils don't have ECD toilet, the classroom has some noticeable cracks and signs of leakage on the roof.
3547 | Classroom And Workshop Construction At Rongai Polytechnic | Classroom And Workshop Construction At Rongai Polytechnic | To implement classroom and workshop construction at rongai polytechnic for access to quality education and training | Classroom And Workshop Construction At Rongai Polytechnic completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Soin | -0.099944, 35.936673 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 2500000 | 1455 | 1455 | Equitable | N/A | 1455 | 0 | 1455 | 100 | 1455 | 1455 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3548 | Construction And Equipping Of Kabarnet Farm ECDE Classroom | Construction And Equipping Of Kabarnet Farm ECDE Classroom | To construct and equip Kabarnet Farm ECDE Classroom | Kabarnet Farm ECDE Classroom constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Soin | -0.10065 35.988127 1680.5 4.199999809265137 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1511226 | 1511226 | 1511226 | Equitable | N/A | 1511226 | 0 | 1163660 | 77 | 1163660 | 1511226 | 347566 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Installation of Terrazo, construction of a new classroom and installation of plastic Water Tank, installation of gutters, Construction of Learners and staff Toilets, Construction of a modern kitchen,Outdoor play materials and furniture.
3549 | Construction Of ECDE Classroom At Kapsetek, Kaptera, Kimugul, Sinendet And Athinai And 71 ECDE | Construction Of ECDE Classroom At Kapsetek, Kaptera, Kimugul, Sinendet And Athinai And 71 ECDE | To construct ECDE Classroom At Kapsetek, Kaptera, Kimugul, Sinendet And Athinai And 71 ECDE | ECDE Classroom At Kapsetek, Kaptera, Kimugul, Sinendet And Athinai And 71 ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Soin | -0.041548, 35.960845 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | 2021/22 | 7200000 | 7200000 | 7200000 | Equitable | N/A | 7200000 | 0 | 7045860 | 97.9 | 7045860 | 423576 | 154140 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3550 | Design And Construction Of Classroom At Koisamo ECDE | Design And Construction Of Classroom At Koisamo ECDE | To design and construct Classroom At Koisamo ECDE | Classroom At Koisamo ECDE designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Soin | 0.025025, 36.000957 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | FY2021 | 1200000 | 1199997 | 1199997 | Equitable | N/A | 1199997 | 0 | 1199997 | 100 | 1199997 | 1200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3551 | Design And Construction Of Classroom At Lomolo ECDE | Design And Construction Of Classroom At Lomolo ECDE | To design and construct Classroom At Lomolo ECDE | Classroom At Lomolo ECDE designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Soin | 0.025025, 36.000957 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | FY2021 | 1200000 | 1199997 | 1199997 | Equitable | N/A | 1199997 | 0 | 1199997 | 100 | 1199997 | 1199997 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3552 | Design And Construction Of Classroom At Losibil ECDE | Design And Construction Of Classroom At Losibil ECDE | To design and construct Classroom At Losibil ECDE | Classroom At Losibil ECDE designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Soin | 0.025025, 36.000957 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | FY2021 | 1200000 | 1132327 | 1132327 | Equitable | N/A | 1132327 | 0 | 1132000 | 100 | 1132000 | 1200000 | 327 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3553 | Design And Construction Of Classroom At Molok ECDE | Design And Construction Of Classroom At Molok ECDE | To design and construct Classroom At Molok ECDE | Classroom At Molok ECDE designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Soin | 0.025025, 36.000957 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | FY2021 | 1200000 | 1132327 | 1132327 | Equitable | N/A | 1132327 | 0 | 1132000 | 100 | 1132000 | 1200000 | 327 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3554 | Design And Construction Of Classroom At Testai ECDE | Design And Construction Of Classroom At Testai ECDE | To design and construct Classroom At Testai ECDE | Classroom At Testai ECDE designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Soin | 0.025025, 36.000957 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | FY2021 | 1200000 | 1199997 | 1199997 | Equitable | N/A | 1199997 | 0 | 1199997 | 100 | 1199997 | 1200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3555 | Kimamoi ECD Class Construction | Kimamoi ECD Class Construction | To implement kimamoi ecd class construction for access to quality education and training | Kimamoi ECD Class Construction completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Soin | -0.006494 36.041814 1611 8 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 200 | 200 | Equitable | N/A | 200 | 0 | 200 | 100 | 200 | 200 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: It was viable and met the needs. Assessor remarks: Repair and furniture required.
3556 | Majani Mingi 2 ECD Classes Construction | Majani Mingi 2 ECD Classes Construction | To implement majani mingi 2 ecd classes construction for access to quality education and training | Majani Mingi 2 ECD Classes Construction completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Soin | -0.006494 36.041814 1611 8 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 2400000 | 2398880 | 2398880 | Equitable | N/A | 2398880 | 0 | 2398880 | 100 | 2398880 | 2400000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: It was viable and met the needs. Assessor remarks: Repair and furniture required.
3557 | Sawaiti ECD Construction | Sawaiti ECD Construction | To implement sawaiti ecd construction for access to quality education and training | Sawaiti ECD Construction completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Soin | -0.006494 36.041814 1611 8 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1132327 | 1132327 | Equitable | N/A | 1132327 | 0 | 1132000 | 100 | 1132000 | 1200000 | 327 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: It was viable and met the needs. Assessor remarks: Repair and furniture required.
3558 | Sinendet ECD Class Construction | Sinendet ECD Class Construction | To implement sinendet ecd class construction for access to quality education and training | Sinendet ECD Class Construction completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Soin | -0.006494 36.041814 1611 8 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1199895 | 1199895 | Equitable | N/A | 1199895 | 0 | 1199895 | 100 | 1199895 | 1199895 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: It was viable and met the needs. Assessor remarks: Repair and furniture required.
3559 | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Kapkaturu ECD | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Kapkaturu ECD | To construct 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Kapkaturu ECD | 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Kapkaturu ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Solai | 0.099233, 36.173895 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2015 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 102253 | 5.7 | 102253 | 1800000 | 1697747 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
3560 | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Tuiyomoi ECD | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Tuiyomoi ECD | To construct 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Tuiyomoi ECD | 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Tuiyomoi ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Solai | 0.099233, 36.173895 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2015 | 1200000 | 436569 | 436569 | Equitable | N/A | 436569 | 0 | 102253 | 23.4 | 102253 | 436569 | 334316 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
3561 | Construction of classroom at Ruiyobei Vocational Training Centre | Construction of classroom at Ruiyobei Vocational Training Centre | To construct classroom at Ruiyobei Vocational Training Centre | Classroom at Ruiyobei Vocational Training Centre constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Solai | 0.099258 36.173883 1556.7939453125 3.808000087738037 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 0 | 0 | 0 | 2187090 | 0 | Stalled | 75 | N/A | Stalled — reasons to be confirmed by department | 2022 | N/A | N/A | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs renovation, ceiling infested with bats.
3562 | Mahinga ECD | Mahinga ECD | To implement mahinga ecd for access to quality education and training | Mahinga ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Solai | 0.023445, 36.146794 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2022 | 1799542.8 | 1100380.85 | 1100380.85 | Equitable | N/A | 1100380.85 | 0 | 699162 | 63.5 | 699162 | 1100381 | 401218.85 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3563 | Sigito ECD | Sigito ECD | To implement sigito ecd for access to quality education and training | Sigito ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Solai | 0.078648 36.19437 1940.5 6 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1799229.6 | 1799230 | 1799230 | Equitable | N/A | 1799230 | 0 | 699162 | 38.9 | 699162 | 1799230 | 1100068 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Solo m general enterprise. Assessor remarks: Good.
3564 | Construction Of 1 Class And Latrines At Subukia Primary ECDE | Construction Of 1 Class And Latrines At Subukia Primary ECDE | To construct 1 Class And Latrines At Subukia Primary ECDE | 1 Class And Latrines At Subukia Primary ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Subukia | Subukia | 0.003143, 36.229305 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 04/03/2020 | 1500000 | 2892 | 2892 | Equitable | N/A | 2892 | 0 | 2892 | 100 | 2892 | 2892 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: The project has many learning children. Viable: Yes.. Contractor: Information not available.
3565 | Construction Of 1 Class At Kamemo Primary ECDE | Construction Of 1 Class At Kamemo Primary ECDE | To construct 1 Class At Kamemo Primary ECDE | 1 Class At Kamemo Primary ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Subukia | Subukia | -0.030872, 36.196235 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2020 | 1200000 | 1183015 | 1183015 | Equitable | N/A | 1183015 | 0 | 2892 | 0.2 | 2892 | 1183015 | 1180123 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Not known.
3566 | Design And Construction Of Kianyoro Primary ECDE Classroom | Design And Construction Of Kianyoro Primary ECDE Classroom | To design and construct Kianyoro Primary ECDE Classroom | Kianyoro Primary ECDE Classroom designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Subukia | Subukia | -0.022576, 36.239011 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 13/01/2020 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1183015 | 78.9 | 1183015 | 1505000 | 316985 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: No.. Viable: The class was condemed. Contractor: Information not available.
3567 | Construction and Equipping Ngochopta ECDE classroom | Construction and Equipping Ngochopta ECDE classroom | To construct and equip Ngochopta ECDE classroom | Ngochopta ECDE classroom constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.438399 35.609035 0 1899.9990234375 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2022/23 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1457080 | 97.1 | 1457080 | 1457080 | 42920 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Potholes no teacher toilet and pupils toilet.
3568 | Construction and Equipping of Kiptongoton ECDE classroom | Construction and Equipping of Kiptongoton ECDE classroom | To construct and equip Kiptongoton ECDE classroom | Kiptongoton ECDE classroom constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.538982 35.643548 0 2799.9990234375 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2022/23 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1457080 | 97.1 | 1457080 | 1457080 | 42920 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
3569 | Construction and Equipping of Sibo ECDE classroom | Construction and Equipping of Sibo ECDE classroom | To construct and equip Sibo ECDE classroom | Sibo ECDE classroom constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.438399 35.609035 0 1899.9990234375 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2022/23 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1457080 | 97.1 | 1457080 | 1457080 | 42920 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Potholes no teacher toilet and pupils toilet.
3570 | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Ang'Urwet ECD | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Ang'Urwet ECD | To construct 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Ang'Urwet ECD | 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Ang'Urwet ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.544292 35.677364 0 2400 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 296998 | 296998 | Equitable | N/A | 296998 | 0 | 296992 | 100 | 296992 | 296998 | 6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
3571 | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Ngenda ECD | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Ngenda ECD | To construct 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Ngenda ECD | 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Ngenda ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.544292 35.677364 0 2400 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1999950 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 800000 | 100 | 800000 | 800000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
3572 | Construction Of A Classroom At Ogiek Polytechnic | Construction Of A Classroom At Ogiek Polytechnic | To construct A Classroom At Ogiek Polytechnic | A Classroom At Ogiek Polytechnic constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.478177, 35.670193 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | N/A | 1200000 | 1199900 | 1199900 | Equitable | N/A | 1199900 | 0 | 1151750 | 96 | 1151750 | 1199900 | 48150 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3573 | Construction Of Chebalungu ECDE | Construction Of Chebalungu ECDE | To construct Chebalungu ECDE | Chebalungu ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.511222 35.692048 0 1200 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | 2020/21 | 1200000 | 1199220 | 1199220 | Equitable | N/A | 1199220 | 0 | 1199220 | 100 | 1199220 | 1200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
3574 | Construction Of ECDE Classroom At Araret ECDE | Construction Of ECDE Classroom At Araret ECDE | To construct ECDE Classroom At Araret ECDE | ECDE Classroom At Araret ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.475432 35.583279 2524.075 2.687999963760376 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1319 | 0.1 | 1319 | 1200000 | 1198681 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes. Assessor remarks: Never started.
3575 | Construction Of ECDE Classroom At Barao | Construction Of ECDE Classroom At Barao | To construct ECDE Classroom At Barao | ECDE Classroom At Barao constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.475432 35.583279 2524.075 2.687999963760376 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1318.65 | 1318.65 | Equitable | N/A | 1318.65 | 0 | 1319 | 100 | 1319 | 1319 | -0.35 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes. Assessor remarks: Never started.
3576 | Construction Of ECDE Classroom At Busienkiruk | Construction Of ECDE Classroom At Busienkiruk | To construct ECDE Classroom At Busienkiruk | ECDE Classroom At Busienkiruk constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.497802 35.684536 0 1500 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1151750 | 1151750 | Equitable | N/A | 1151750 | 0 | 1151750 | 100 | 1151750 | 1151750 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Leaking roof and fading paints.
3577 | Construction Of ECDE Classroom At Geticha | Construction Of ECDE Classroom At Geticha | To construct ECDE Classroom At Geticha | ECDE Classroom At Geticha constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.497802 35.684536 0 1500 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1199730 | 1199730 | Equitable | N/A | 1199730 | 0 | 1151750 | 96 | 1151750 | 1199730 | 47980 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Leaking roof and fading paints.
3578 | Construction Of ECDE Classroom At Kabonqoi | Construction Of ECDE Classroom At Kabonqoi | To construct ECDE Classroom At Kabonqoi | ECDE Classroom At Kabonqoi constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.475432 35.583279 2524.075 2.687999963760376 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 690090 | 690090 | Equitable | N/A | 690090 | 0 | 690090 | 100 | 690090 | 690090 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes. Assessor remarks: Never started.
3579 | Construction Of ECDE Classroom At Kapkoi | Construction Of ECDE Classroom At Kapkoi | To construct ECDE Classroom At Kapkoi | ECDE Classroom At Kapkoi constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.475432 35.583279 2524.075 2.687999963760376 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 590910 | 590910 | Equitable | N/A | 590910 | 0 | 590910 | 100 | 590910 | 590910 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes. Assessor remarks: Never started.
3580 | Construction Of ECDE Classroom At Kapno | Construction Of ECDE Classroom At Kapno | To construct ECDE Classroom At Kapno | ECDE Classroom At Kapno constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.475432 35.583279 2524.075 2.687999963760376 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 590910 | 590910 | Equitable | N/A | 590910 | 0 | 590910 | 100 | 590910 | 590910 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes. Assessor remarks: Never started.
3581 | Construction Of ECDE Classroom At Korao | Construction Of ECDE Classroom At Korao | To construct ECDE Classroom At Korao | ECDE Classroom At Korao constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.475432 35.583279 2524.075 2.687999963760376 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1138490 | 1138490 | Equitable | N/A | 1138490 | 0 | 1319 | 0.1 | 1319 | 1138490 | 1137171 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes. Assessor remarks: Never started.
3582 | Construction Of ECDE Classroom At Ogiek | Construction Of ECDE Classroom At Ogiek | To construct ECDE Classroom At Ogiek | ECDE Classroom At Ogiek constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.497802 35.684536 0 1500 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1199730 | 1199730 | Equitable | N/A | 1199730 | 0 | 1151750 | 96 | 1151750 | 1199730 | 47980 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Leaking roof and fading paints.
3583 | Construction Of ECDE Classroom At Tach Asis | Construction Of ECDE Classroom At Tach Asis | To construct ECDE Classroom At Tach Asis | ECDE Classroom At Tach Asis constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.497802 35.684536 0 1500 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 1151750 | 1151750 | Equitable | N/A | 1151750 | 0 | 1151750 | 100 | 1151750 | 1151750 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Leaking roof and fading paints.
3584 | Construction Of ECDE Classroom At Tiriiqoi | Construction Of ECDE Classroom At Tiriiqoi | To construct ECDE Classroom At Tiriiqoi | ECDE Classroom At Tiriiqoi constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.475432 35.583279 2524.075 2.687999963760376 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 590910 | 590910 | Equitable | N/A | 590910 | 0 | 590910 | 100 | 590910 | 590910 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes. Assessor remarks: Never started.
3585 | Construction Of Magicheit ECD | Construction Of Magicheit ECD | To construct Magicheit ECD | Magicheit ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.511222 35.692048 0 1200 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 2099 | 2099 | Equitable | N/A | 2099 | 0 | 2099 | 100 | 2099 | 2099 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
3586 | Construction Of One Classroom Each At Sangawet ECD, Kapket ECD, Kiptenden ECD And Kapmondoi ECDE | Construction Of One Classroom Each At Sangawet ECD, Kapket ECD, Kiptenden ECD And Kapmondoi ECDE | To construct One Classroom Each At Sangawet ECD, Kapket ECD, Kiptenden ECD And Kapmondoi ECDE | One Classroom Each At Sangawet ECD, Kapket ECD, Kiptenden ECD And Kapmondoi ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.509537 35.634567 2510.2 5.699999809265137 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | 2021/22 | 4762794 | 4762794 | 4762794 | Equitable | N/A | 4762794 | 0 | 2387819 | 50.1 | 2387819 | 2374975 | 2374975 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Completed and operational.
3587 | Design And Construction Of 2 No ECDE Classroom At Marwa | Design And Construction Of 2 No ECDE Classroom At Marwa | To design and construct 2 No ECDE Classroom At Marwa | 2 No ECDE Classroom At Marwa designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.475432 35.583279 2524.075 2.687999963760376 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | 2020/21 | 2400000 | 2220440 | 2220440 | Equitable | N/A | 2220440 | 0 | 2316400 | 104.3 | 2316400 | 2400000 | -95960 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes. Assessor remarks: Never started.
3588 | Tinet Ward ECDs -Construction Of 1 ECD Classroom At Buchechet, Cheram, Kipsirat, Rwaget, Maluo, Kapnanda, Kamwaura And Kapnandi. | Tinet Ward ECDs -Construction Of 1 ECD Classroom At Buchechet, Cheram, Kipsirat, Rwaget, Maluo, Kapnanda, Kamwaura And Kapnandi. | To implement tinet ward ecds -construction of 1 ecd classroom at buchechet, cheram, kipsirat, rwaget, maluo, kapnanda, kamwaura and kapnandi. for access to quality education and training | Tinet Ward ECDs -Construction Of 1 ECD Classroom At Buchechet, Cheram, Kipsirat, Rwaget, Maluo, Kapnanda, Kamwaura And Kapnandi. completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Tinet | -0.513813 35.683561 2568.666 3.1989998817443848 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 8400000 | 359465 | 359465 | Equitable | N/A | 359465 | 0 | 519503 | 144.5 | 519503 | 359465 | -160038 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: No. Assessor remarks: Never started.
3589 | Construction and equipping of one Classroom at Rafiki ECD | Construction and equipping of one Classroom at Rafiki ECD | To construct and equip one Classroom at Rafiki ECD | One Classroom at Rafiki ECD constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Turi | -0.303263 35.728955 2630.6 8.5 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2022/23 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1199940 | 80 | 1199940 | 1473625 | 300060 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Completed. The compound needs fencing.
3590 | Construction Of ECDE Classroom At Saqaitim | Construction Of ECDE Classroom At Saqaitim | To construct ECDE Classroom At Saqaitim | ECDE Classroom At Saqaitim constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Turi | -0.34223 35.745215 2732.1 99.69999694824219 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 1199940 | 1199940 | Equitable | N/A | 1199940 | 0 | 1199940 | 100 | 1199940 | 1199996 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The classroom needs renovations.
3591 | Construction Of ECDE Classroom At Turi Farmers | Construction Of ECDE Classroom At Turi Farmers | To construct ECDE Classroom At Turi Farmers | ECDE Classroom At Turi Farmers constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Turi | -0.29662 35.755398 2422.2001953125 12.399999618530273 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1200000 | 6 | 6 | Equitable | N/A | 6 | 0 | 6 | 100 | 6 | 6 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: It needs to be equipped. The water gutters needs to be replaced. They are broken.
3592 | Mitoni ECD | Mitoni ECD | To implement mitoni ecd for access to quality education and training | Mitoni ECD completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Turi | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1195612 | 1195612 | 1195612 | Equitable | N/A | 1195612 | 0 | 1194630 | 99.9 | 1194630 | 982 | 982 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3593 | Construction Of ECD Classrooms At Mwangaza, Chesengele And Gathigi Primary School | Construction Of ECD Classrooms At Mwangaza, Chesengele And Gathigi Primary School | To construct ECD Classrooms At Mwangaza, Chesengele And Gathigi Primary School | ECD Classrooms At Mwangaza, Chesengele And Gathigi Primary School constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Molo | Turi | -0.32942 35.686729 2755.300048828125 96.13099670410156 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 2400000 | 1200006 | 1200006 | Equitable | N/A | 1200006 | 0 | 1199994 | 100 | 1199994 | 1200006 | 12 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The classroom is under the Chesingele, Gathigi and Mwangaza ECDs.
3594 | Completion Of Burgei ECD Classroom | Completion Of Burgei ECD Classroom | To complete Burgei ECD Classroom | Burgei ECD Classroom completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Visoi | -0.17174 35.922497 1749.5 8.645999908447266 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 1798100 | 299.7 | 1798100 | 600000 | -1198100 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
3595 | Construction and equipping of Surutia ECDE classroom, Umoja ECDE and Tumaini ECDE | Construction and equipping of Surutia ECDE classroom, Umoja ECDE and Tumaini ECDE | To construct and equip Surutia ECDE classroom, Umoja ECDE and Tumaini ECDE | Surutia ECDE classroom, Umoja ECDE and Tumaini ECDE constructed and equipped | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Visoi | -0.119997 35.933422 1746.5999755859375 6.900000095367432 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | N/A | 4500000 | 4500000 | 4500000 | Equitable | N/A | 4500000 | 0 | 3141914 | 69.8 | 3141914 | 1241431 | 1358086 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Merlins keys enterprises. Assessor remarks: Good.
3596 | Construction Of One Classroom At Rajuera ECDE | Construction Of One Classroom At Rajuera ECDE | To construct One Classroom At Rajuera ECDE | One Classroom At Rajuera ECDE constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Visoi | -0.17174 35.922497 1749.5 8.645999908447266 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | 2021/22 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1155310 | 96.3 | 1155310 | 1200000 | 44690 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
3597 | Design And Construction Of 1 ECDE Classroom At Kandutura Primary School | Design And Construction Of 1 ECDE Classroom At Kandutura Primary School | To design and construct 1 ECDE Classroom At Kandutura Primary School | 1 ECDE Classroom At Kandutura Primary School designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Visoi | -0.119997 35.933422 1746.5999755859375 6.900000095367432 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | 2021/22 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1174310 | 97.9 | 1174310 | 1200000 | 25690 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Merlins keys enterprises. Assessor remarks: Good.
3598 | Design And Construction Of 1 ECDE Classroom At Kayanet ECDE | Design And Construction Of 1 ECDE Classroom At Kayanet ECDE | To design and construct 1 ECDE Classroom At Kayanet ECDE | 1 ECDE Classroom At Kayanet ECDE designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Rongai | Visoi | -0.119997 35.933422 1746.5999755859375 6.900000095367432 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1174310 | 97.9 | 1174310 | 1200000 | 25690 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Merlins keys enterprises. Assessor remarks: Good.
3599 | Construction Of 2 Classrooms At Kabati ECD | Construction Of 2 Classrooms At Kabati ECD | To construct 2 Classrooms At Kabati ECD | 2 Classrooms At Kabati ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Viwandani | -0.71758, 36.442437 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | 2021/22 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2948620 | 98.3 | 2948620 | 3000000 | 51380 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3600 | Construction of 2 ECDE classrooms at Naivasha Central Primary School | Construction of 2 ECDE classrooms at Naivasha Central Primary School | To construct 2 ECDE classrooms at Naivasha Central Primary School | 2 ECDE classrooms at Naivasha Central Primary School constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Viwandani | -0.714838, 36.435556 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2022/23 | 3327369 | 3327369 | 3327369 | Equitable | N/A | 3327369 | 0 | 3208039 | 96.4 | 3208039 | 41 | 119330 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable.
3601 | Design And Construction And Equipping Of 2 No Special Need Classrooms At DEB School | Design And Construction And Equipping Of 2 No Special Need Classrooms At DEB School | To design and construct And Equipping Of 2 No Special Need Classrooms At DEB School | And Equipping Of 2 No Special Need Classrooms At DEB School designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Naivasha | Viwandani | -0.711536 36.435973 1906.69 0.621999979019165 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | 2020/21 | 3990000 | 3990000 | 3990000 | Equitable | N/A | 3990000 | 0 | 3542890 | 88.8 | 3542890 | 3990000 | 447110 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Assessor remarks: Has met minimum health requirements.
3602 | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Gatagati ECD | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Gatagati ECD | To construct 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Gatagati ECD | 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Gatagati ECD constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Subukia | Waseges | 0.168615 36.250903 1712.4 9 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 798025.2 | 798025.2 | Equitable | N/A | 798025.2 | 0 | 401975 | 50.4 | 401975 | 798025 | 396050.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Teacher Toilet and Pupils Not Constructed.
3603 | Construction Of Loremetta ECDE 1 No Block Toilet For Both Teachers And Pupils With Double Doors | Construction Of Loremetta ECDE 1 No Block Toilet For Both Teachers And Pupils With Double Doors | To construct Loremetta ECDE 1 No Block Toilet For Both Teachers And Pupils With Double Doors | Loremetta ECDE 1 No Block Toilet For Both Teachers And Pupils With Double Doors constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Subukia | Waseges | 0.0104, 36.23452 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 0 | 0 | 0 | 700000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: No. Viable: No.
3604 | Construction Of One Classroom And Toilet At Chania ECD And Ngerefu ECD Each | Construction Of One Classroom And Toilet At Chania ECD And Ngerefu ECD Each | To construct One Classroom And Toilet At Chania ECD And Ngerefu ECD Each | One Classroom And Toilet At Chania ECD And Ngerefu ECD Each constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Subukia | Waseges | 0.028085, 36.25811 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2364444 | 118.2 | 2364444 | 2000000 | -364444 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No.
3605 | Design And Construction Of One Classroom And A Toilet At Gitundaga B, Wiyumirire, Chania And Kavillila ECDEs | Design And Construction Of One Classroom And A Toilet At Gitundaga B, Wiyumirire, Chania And Kavillila ECDEs | To design and construct One Classroom And A Toilet At Gitundaga B, Wiyumirire, Chania And Kavillila ECDEs | One Classroom And A Toilet At Gitundaga B, Wiyumirire, Chania And Kavillila ECDEs designed and constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Subukia | Waseges | 0.188668, 36.235863 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | 2020/21 | 6000000 | 5763165 | 5763165 | Equitable | N/A | 5763165 | 0 | 5761409 | 100 | 5761409 | 5763165 | 1756 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3606 | Gitudaga ECDEs | Gitudaga ECDEs | To implement gitudaga ecdes for access to quality education and training | Gitudaga ECDEs completed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Subukia | Waseges | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1149769.96 | 1149770 | 1149770 | Equitable | N/A | 1149770 | 0 | 0 | 0 | 0 | 1149770 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3607 | Purchase Of ECDE Furniture For Wei ECDE, Kaptarakwa ECDE, Nairobi Ares ECDE, Wiyumiririe ECDE, Kiriko ECDE, Kavillila ECDE, Gitundaga B ECDE, Lari ECDE And Simboyon ECDE Plus Teachers Chair And Table For Each ECDE (Each ECDE To Consist Of 4 Wooden Tables And 24 Small Wooden Chairs, For Teachers 1 Wooden Chair And A Locker, Samples To Be Seen At Kamumo ECDE) | Purchase Of ECDE Furniture For Wei ECDE, Kaptarakwa ECDE, Nairobi Ares ECDE, Wiyumiririe ECDE, Kiriko ECDE, Kavillila ECDE, Gitundaga B ECDE, Lari ECDE And Simboyon ECDE Plus Teachers Chair And Table For Each ECDE (Each ECDE To Consist Of 4 Wooden Tables And 24 Small Wooden Chairs, For Teachers 1 Wooden Chair And A Locker, Samples To Be Seen At Kamumo ECDE) | To procure ECDE Furniture For Wei ECDE, Kaptarakwa ECDE, Nairobi Ares ECDE, Wiyumiririe ECDE, Kiriko ECDE, Kavillila ECDE, Gitundaga B ECDE, Lari ECDE And Simboyon ECDE Plus Teachers Chair And Table For Each ECDE (Each ECDE To Consist Of 4 Wooden Tables And 24 Small Wooden Chairs, For Teachers 1 Wooden Chair And A Locker, Samples To Be Seen At Kamumo ECDE) | ECDE Furniture For Wei ECDE, Kaptarakwa ECDE, Nairobi Ares ECDE, Wiyumiririe ECDE, Kiriko ECDE, Kavillila ECDE, Gitundaga B ECDE, Lari ECDE And Simboyon ECDE Plus Teachers Chair And Table For Each ECDE (Each ECDE To Consist Of 4 Wooden Tables And 24 Small Wooden Chairs, For Teachers 1 Wooden Chair And A Locker, Samples To Be Seen At Kamumo ECDE) procured | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Subukia | Waseges | 0.033498, 36.226888 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3608 | Completion of Data Center (HQ) | Completion of Data Center (HQ) | To complete Data Center (HQ) | Data Center (HQ) completed | 3110299 | Construction of Buildings - Ot | HQ | HQ | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | N/A | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 9787000 | 195.7 | 9787000 | 4986452 | -4787000 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
3609 | Completion of Resource Center Nakuru Phase 2 | Completion of Resource Center Nakuru Phase 2 | To complete Resource Center Nakuru Phase 2 | Resource Center Nakuru Phase 2 completed | 3110299 | Construction of Buildings - Ot | HQ | HQ | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | N/A | 10000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 0 | 0 | 0 | 4986452 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
3610 | Construction Of Workshops- Njoro VTC | Construction Of Workshops- Njoro VTC | To construct Workshops- Njoro VTC | Workshops- Njoro VTC constructed | 3110299 | Construction of Buildings - Ot | HQ | HQ | -0.337502, 35.952445 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2024 | 6000000 | 238078.95 | 238078.95 | Equitable | Equitable | 238078.95 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Ongoing. Viable: Yes. Contractor: Fabrica Building and construction company Ltd.
3611 | Set Up Of Digital Centres | Set Up Of Digital Centres | To implement set up of digital centres for access to quality education and training | Set Up Of Digital Centres completed | 3110299 | Construction of Buildings - Ot | HQ | HQ | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 15000000 | 2813994 | 2813994 | Equitable | N/A | 2813994 | 0 | 1897400 | 67.4 | 1897400 | 2813994 | 916594 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3612 | Renovation of Barut and Kiptenden ECDE classroom | Renovation of Barut and Kiptenden ECDE classroom | To rehabilitate Barut and Kiptenden ECDE classroom to restore functionality | Barut and Kiptenden ECDE classroom rehabilitated | 3110302 | Refurbishment of Non-Residential Buildings | Nakuru West | Barut | -0.324973, 36.053456 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2025 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 481200 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Primal company.
3613 | Refurbishment of St Paul and Gituru Primary ECD | Refurbishment of St Paul and Gituru Primary ECD | To implement refurbishment of st paul and gituru primary ecd for access to quality education and training | Refurbishment of St Paul and Gituru Primary ECD completed | 3110302 | Refurbishment of Non-Residential Buildings | Naivasha | Biashara-Naivasha | -0.639478, 36.494367 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | 2021 | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 692555 | 98.9 | 692555 | 700000 | 7445 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3614 | Kambi Somali ECD Floor renovation of two classrooms, veranda and painting and building of wall cupboards and toilets | Kambi Somali ECD Floor renovation of two classrooms, veranda and painting and building of wall cupboards and toilets | To implement kambi somali ecd floor renovation of two classrooms, veranda and painting and building of wall cupboards and toilets for access to quality education and training | Kambi Somali ECD Floor renovation of two classrooms, veranda and painting and building of wall cupboards and toilets completed | 3110302 | Refurbishment of Non-Residential Buildings | Gilgil | Gilgil | -0.509507, 36.315287 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | 2021/22 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3615 | Renovation of two (2) ECDE Classrooms & construction of Modern (PWLD) learner - friendly Toilet at Milimani Integrated Primary for Visually Impaired | Renovation of two (2) ECDE Classrooms & construction of Modern (PWLD) learner - friendly Toilet at Milimani Integrated Primary for Visually Impaired | To rehabilitate two (2) ECDE Classrooms & construction of Modern (PWLD) learner - friendly Toilet at Milimani Integrated Primary for Visually Impaired to restore functionality | Two (2) ECDE Classrooms & construction of Modern (PWLD) learner - friendly Toilet at Milimani Integrated Primary for Visually Impaired rehabilitated | 3110302 | Refurbishment of Non-Residential Buildings | Nakuru West | London | -0.274307, 36.057502 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 0 | 0 | 0 | 1200000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
3616 | Renovation Of Existing ECD Classroom At Rafiki ECD | Renovation Of Existing ECD Classroom At Rafiki ECD | To rehabilitate Existing ECD Classroom At Rafiki ECD to restore functionality | Existing ECD Classroom At Rafiki ECD rehabilitated | 3110302 | Refurbishment of Non-Residential Buildings | Molo | Turi | -0.303263 35.728955 2630.6 8.5 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 200000 | 199960 | 199960 | Equitable | N/A | 199960 | 0 | 1199940 | 600.1 | 1199940 | 199960 | -999980 | Vired | 90 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Completed. The compound needs fencing.
3617 | Renovation of Lelechwet ECDE Classroom and Construction of Toilet | Renovation of Lelechwet ECDE Classroom and Construction of Toilet | To rehabilitate Lelechwet ECDE Classroom and Construction of Toilet to restore functionality | Lelechwet ECDE Classroom and Construction of Toilet rehabilitated | 3110399 | Refurbishment of Buildgs - Oth | Rongai | Mosop | -0.259783 35.980463 2088.500244140625 9.699999809265137 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 993480 | 0 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: M/s Effective. Assessor remarks: In good condition.
3618 | Construction Of Toilets At Kaplamai Vocational Training Centre | Construction Of Toilets At Kaplamai Vocational Training Centre | To construct Toilets At Kaplamai Vocational Training Centre | Toilets At Kaplamai Vocational Training Centre constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Amalo | -0.663208 35.620325 2426.7999999999997 4.699999809265137 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | 2021/22 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 970030 | 97 | 970030 | 1000000 | 29970 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: no. Viable: no. Assessor remarks: project completed but facility not operational due to lack of medical staff.
3619 | Construction Of A Sanitary Facility, ECDE Class And Water Tank At Kahawa Nursery | Construction Of A Sanitary Facility, ECDE Class And Water Tank At Kahawa Nursery | To construct A Sanitary Facility, ECDE Class And Water Tank At Kahawa Nursery | A Sanitary Facility, ECDE Class And Water Tank At Kahawa Nursery constructed | 3110504 | Other Infrastructure and Civil Works | Bahati | Bahati | -0.147818 36.090577 1844.547607421875 6.189000129699707 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1997862 | 99.9 | 1997862 | 2000000 | 2138 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The water tank was broken and no toilet.
3620 | Supply Of Paints At Jakaranda Primary | Supply Of Paints At Jakaranda Primary | To implement supply of paints at jakaranda primary for access to quality education and training | Supply Of Paints At Jakaranda Primary completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Bahati | -0.154613 36.157595 2094.000244140625 6.599999904632568 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | N/A | 100000 | 100000 | 100000 | Equitable | N/A | 100000 | 0 | 0 | 0 | 0 | 100000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is good.
3621 | Leveling and Grading of ECDE play field of Parkview Primary | Leveling and Grading of ECDE play field of Parkview Primary | To implement leveling and grading of ecde play field of parkview primary for access to quality education and training | Leveling and Grading of ECDE play field of Parkview Primary completed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Barut | 0.353373, 36.04497 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2022 | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 0 | 0 | 0 | 300000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: No name.
3622 | Gituru Polytechnic Fencing, Latrines And Other Works | Gituru Polytechnic Fencing, Latrines And Other Works | To implement gituru polytechnic fencing, latrines and other works for access to quality education and training | Gituru Polytechnic Fencing, Latrines And Other Works completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Biashara-Naivasha | -0.7255, 36.486383 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2021 | 7300000 | 7300000 | 7300000 | Equitable | N/A | 7300000 | 0 | 7300000 | 100 | 7300000 | 7300000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known.
3623 | Kinamba Polytechnic Fencing, Latrines And Other Works | Kinamba Polytechnic Fencing, Latrines And Other Works | To implement kinamba polytechnic fencing, latrines and other works for access to quality education and training | Kinamba Polytechnic Fencing, Latrines And Other Works completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Biashara-Naivasha | -0.7255, 36.486383 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2021 | 3100000 | 3099310 | 3099310 | Equitable | N/A | 3099310 | 0 | 3099310 | 100 | 3099310 | 3100000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known.
3624 | Construction Of Toilets At St. Paul Primary School | Construction Of Toilets At St. Paul Primary School | To construct Toilets At St. Paul Primary School | Toilets At St. Paul Primary School constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | -0.296043, 36.079196 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 800000 | 10 | 10 | Equitable | N/A | 10 | 0 | 10 | 100 | 10 | 10 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3625 | Construction of an ECD Toilet at Giachonge Primary school | Construction of an ECD Toilet at Giachonge Primary school | To construct an ECD Toilet at Giachonge Primary school | An ECD Toilet at Giachonge Primary school constructed | 3110504 | Other Infrastructure and Civil Works | Bahati | Dundori | -0.252786 36.183911 2006.5999755859375 15 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 1199978 | 240 | 1199978 | 495760 | -699978 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Alidawn ltd. Assessor remarks: Good should be operationalized.
3626 | Construction Of ECDE Toilets At Kamburi And Mugwathi Primary | Construction Of ECDE Toilets At Kamburi And Mugwathi Primary | To construct ECDE Toilets At Kamburi And Mugwathi Primary | ECDE Toilets At Kamburi And Mugwathi Primary constructed | 3110504 | Other Infrastructure and Civil Works | Bahati | Dundori | -0.237781, 36.235615 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | 2021/2022 | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 793740 | 99.2 | 793740 | 800000 | 6260 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3627 | Construction Of Kasambara ECD Toilets | Construction Of Kasambara ECD Toilets | To construct Kasambara ECD Toilets | Kasambara ECD Toilets constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Eburru/Mbaruk | -0.3633633062, 36.24275068 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | No information | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 490250 | 98 | 490250 | 500000 | 9750 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes it was viable. Contractor: No details.
3628 | Construction Of Kiungururia Toilets ECDE | Construction Of Kiungururia Toilets ECDE | To construct Kiungururia Toilets ECDE | Kiungururia Toilets ECDE constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Eburru/Mbaruk | 0.347671, 36.185201 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | Not found | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 490250 | 98 | 490250 | 500000 | 9750 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: Not indcated.
3629 | Construction Of Staff Toilet And Fencing Of Lion Hill Polytechnic | Construction Of Staff Toilet And Fencing Of Lion Hill Polytechnic | To construct Staff Toilet And Fencing Of Lion Hill Polytechnic | Staff Toilet And Fencing Of Lion Hill Polytechnic constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Eburru/Mbaruk | -0.343459, 36.153688 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | Not indcated | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1963990 | 98.2 | 1963990 | 2000000 | 36010 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes, its value for money. Viable: Yes . Viable. Contractor: Unknown.
3630 | Connection of electricity at Ole Sultan Polytechnic | Connection of electricity at Ole Sultan Polytechnic | To implement connection of electricity at ole sultan polytechnic for access to quality education and training | Connection of electricity at Ole Sultan Polytechnic completed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Elementaita | -0.566712 36.114436 1944.02 7.9720001220703125 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | N/A | 500000 | 0 | 500000 | Equitable | N/A | 500000 | 0 | 2800000 | 0 | 2800000 | 500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
3631 | Construction of Toilets at Mahiga Ndibai Ebenezer, Matwiku, and Muriricua ECDEs | Construction of Toilets at Mahiga Ndibai Ebenezer, Matwiku, and Muriricua ECDEs | To construct Toilets at Mahiga Ndibai Ebenezer, Matwiku, and Muriricua ECDEs | Toilets at Mahiga Ndibai Ebenezer, Matwiku, and Muriricua ECDEs constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Elementaita | -0.566243 36.119887 1951.9 7.5 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | N/A | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 1199700 | 48 | 1199700 | 2500000 | 1300300 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
3632 | Proposed construction of 2no of toilet blocks at Racetrack Primary School | Proposed construction of 2no of toilet blocks at Racetrack Primary School | To undertake the proposed construction of 2no of toilet blocks at Racetrack Primary School | Proposed construction of 2no of toilet blocks at Racetrack Primary School implemented | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Flamingo | -0.310076, 36.06997 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | Fy-20232024 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1893220 | 94.7 | 1893220 | 1893220 | 106780 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3633 | Renovation of Lakeview and Langa langa primary ECDE and toilets | Renovation of Lakeview and Langa langa primary ECDE and toilets | To rehabilitate Lakeview and Langa langa primary ECDE and toilets to restore functionality | Lakeview and Langa langa primary ECDE and toilets rehabilitated | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Flamingo | -0.305188, 36.070628 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2017/18 | 2017/18 | FY2017/2018 | 2896270 | 0 | 896270 | Equitable | N/A | 896270 | 0 | 2084532 | 0 | 2084532 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: Not indicated.
3634 | Construction Of Chain Link Fence, Gate Installation And Play Equipment For Children At Teachers 'A' ECDE, Teachers 'B' ECDE | Construction Of Chain Link Fence, Gate Installation And Play Equipment For Children At Teachers 'A' ECDE, Teachers 'B' ECDE | To construct Chain Link Fence, Gate Installation And Play Equipment For Children At Teachers 'A' ECDE, Teachers 'B' ECDE | Chain Link Fence, Gate Installation And Play Equipment For Children At Teachers 'A' ECDE, Teachers 'B' ECDE constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Gilgil | -0.484539, 36.336483 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | 2021/22 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yed. Viable: Yes.
3635 | Construction of Chain-link fence, gate installation and play equipment for children and Teachers A&B ECD | Construction of Chain-link fence, gate installation and play equipment for children and Teachers A&B ECD | To construct Chain-link fence, gate installation and play equipment for children and Teachers A&B ECD | Chain-link fence, gate installation and play equipment for children and Teachers A&B ECD constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Gilgil | -0.484539, 36.336483 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | 2021/22 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yed. Viable: Yes.
3636 | Construction Of Toilets For Teachers And Children For Ngomongo ECDE And Murindu ECDEs | Construction Of Toilets For Teachers And Children For Ngomongo ECDE And Murindu ECDEs | To construct Toilets For Teachers And Children For Ngomongo ECDE And Murindu ECDEs | Toilets For Teachers And Children For Ngomongo ECDE And Murindu ECDEs constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Gilgil | -0.490006, 36.32 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | 2021/22 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 976920 | 97.7 | 976920 | 1000000 | 23080 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3637 | Construction of toilets for teachers and children for Ngomongo ECDE and Murindu ECDE | Construction of toilets for teachers and children for Ngomongo ECDE and Murindu ECDE | To construct toilets for teachers and children for Ngomongo ECDE and Murindu ECDE | Toilets for teachers and children for Ngomongo ECDE and Murindu ECDE constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Gilgil | -0.490006, 36.32 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | 2021/22 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 976920 | 97.7 | 976920 | 976920 | 23080 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3638 | Completion of Naigwet toilets in Visoi ward Rongai sub county | Completion of Naigwet toilets in Visoi ward Rongai sub county | To complete Naigwet toilets in Visoi ward Rongai sub county | Naigwet toilets in Visoi ward Rongai sub county completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2022/23 | 598560 | 598560 | 598560 | Equitable | N/A | 598560 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3639 | Construction of ECD sanitation facilities | Construction of ECD sanitation facilities | To construct ECD sanitation facilities | ECD sanitation facilities constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.222936, 35.771564 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2015/2016 | 13000000 | 0 | 13000000 | Equitable | N/A | 13000000 | 0 | 19900008 | 0 | 19900008 | 13000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Met but lack accompanying tank and water point. Viable: To some extent.
3640 | Digital Centres Internet Setup | Digital Centres Internet Setup | To implement digital centres internet setup for access to quality education and training | Digital Centres Internet Setup completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 4942144 | 4942144 | Equitable | N/A | 4942144 | 0 | 4672484 | 94.5 | 4672484 | 4942144 | 269660 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3641 | Installation of CCTV System At Digital Centres | Installation of CCTV System At Digital Centres | To install CCTV System At Digital Centres | CCTV System At Digital Centres installed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | 2021/22 | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 795000 | 99.4 | 795000 | 940000 | 5000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3642 | Reinforcement Of County Server Rooms And Digital Centres In All Sub Counties | Reinforcement Of County Server Rooms And Digital Centres In All Sub Counties | To implement reinforcement of county server rooms and digital centres in all sub counties for access to quality education and training | Reinforcement Of County Server Rooms And Digital Centres In All Sub Counties completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 5000000 | 414583 | 414583 | Equitable | N/A | 414583 | 0 | 2217197 | 534.8 | 2217197 | 414583 | -1802614 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
3643 | Revitalization Of Vocational Training Centres Of Excellence | Revitalization Of Vocational Training Centres Of Excellence | To implement revitalization of vocational training centres of excellence for access to quality education and training | Revitalization Of Vocational Training Centres Of Excellence completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 24000000 | 11157648 | 11157648 | Equitable | N/A | 11157648 | 0 | 3535000 | 31.7 | 3535000 | 11157648 | 7622648 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3644 | Revitalization Of Youth Polytechnics | Revitalization Of Youth Polytechnics | To implement revitalization of youth polytechnics for access to quality education and training | Revitalization Of Youth Polytechnics completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | 2020/21 | 11000000 | 22000000 | 22000000 | Equitable | N/A | 22000000 | 0 | 10193360 | 46.3 | 10193360 | 11000000 | 11806640 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3645 | Revitalization Of Youth Polytechnic | Revitalization Of Youth Polytechnic | To implement revitalization of youth polytechnic for access to quality education and training | Revitalization Of Youth Polytechnic completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 20000000 | 659133 | 659133 | Equitable | N/A | 659133 | 0 | 623800 | 94.6 | 623800 | 659133 | 35333 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3646 | Setting up of a Digital Centre in Njoro | Setting up of a Digital Centre in Njoro | To implement setting up of a digital centre in njoro for access to quality education and training | Setting up of a Digital Centre in Njoro completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | 2021/22 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 4989000 | 99.8 | 4989000 | 2813994 | 11000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3647 | Construction Of A Rehabilitation Centre At Ymca | Construction Of A Rehabilitation Centre At Ymca | To construct A Rehabilitation Centre At Ymca | A Rehabilitation Centre At Ymca constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Hells Gate | -0.778267, 36.429562 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 2988000 | 2988000 | Equitable | N/A | 2988000 | 0 | 2998000 | 100.3 | 2998000 | 2988000 | -10000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3648 | Installation of 3 Phase electricity in Wendo Polytechnic | Installation of 3 Phase electricity in Wendo Polytechnic | To install 3 Phase electricity in Wendo Polytechnic | 3 Phase electricity in Wendo Polytechnic installed | 3110504 | Other Infrastructure and Civil Works | Bahati | Kabatini | -0.181142, 36.180989 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | September 2025 | 3643843 | 3643843 | 3643843 | Equitable | N/A | 3643843 | 0 | 3533206 | 97 | 3533206 | 2135 | 110637 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
3649 | Fencing Of The Kapnandi ECDE Centre | Fencing Of The Kapnandi ECDE Centre | To secure The Kapnandi ECDE Centre through fencing | The Kapnandi ECDE Centre fenced and secured | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kapkures | -0.319831, 36.022557 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | 2021/22 | 1688025 | 1688025 | 1688025 | Equitable | N/A | 1688025 | 0 | 0 | 0 | 0 | 1688025 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No.
3650 | Installation of Solar Panels at Heshima and Kaptembwo ECDE | Installation of Solar Panels at Heshima and Kaptembwo ECDE | To install Solar Panels at Heshima and Kaptembwo ECDE | Solar Panels at Heshima and Kaptembwo ECDE installed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kaptembwo | -0.29789 36.052599 1812.199951171875 82.5 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2022/23 | 2024703 | 2024703 | 2024703 | Equitable | N/A | 2024703 | 0 | 0 | 0 | 0 | 2024703 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: M/S CIDER COLLECTION LIMITED. Assessor remarks: Was well done.
3651 | Installation of Solar panels at Kaptembwo / Heshima ECDE | Installation of Solar panels at Kaptembwo / Heshima ECDE | To install Solar panels at Kaptembwo / Heshima ECDE | Solar panels at Kaptembwo / Heshima ECDE installed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kaptembwo | -0.29789 36.052599 1812.199951171875 82.5 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | N/A | 998400 | 998400 | 998400 | Equitable | N/A | 998400 | 0 | 9999900 | 1001.6 | 9999900 | 998400 | -9001500 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: M/S CIDER COLLECTION LIMITED. Assessor remarks: Was well done.
3652 | Construction Of Modern ECD Toilets At Menengai Hills Primary And Baraka Primary ECD | Construction Of Modern ECD Toilets At Menengai Hills Primary And Baraka Primary ECD | To construct Modern ECD Toilets At Menengai Hills Primary And Baraka Primary ECD | Modern ECD Toilets At Menengai Hills Primary And Baraka Primary ECD constructed | 3110504 | Other Infrastructure and Civil Works | Bahati | Kiamaina | -0.250908 36.090625 2193.000244140625 3.4000000953674316 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | 2021/22 | 1045171 | 1045171 | 1045171 | Equitable | N/A | 1045171 | 0 | 968947 | 92.7 | 968947 | 1045171 | 76224 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is in use.
3653 | Constuction of a kitchen and equipping of Marela ECDE | Constuction of a kitchen and equipping of Marela ECDE | To implement constuction of a kitchen and equipping of marela ecde for access to quality education and training | Constuction of a kitchen and equipping of Marela ECDE completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Lakeview | -0.708776, 36.425023 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2022/23 | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3654 | Constuction of a kitchen and Lakeview ECDE | Constuction of a kitchen and Lakeview ECDE | To implement constuction of a kitchen and lakeview ecde for access to quality education and training | Constuction of a kitchen and Lakeview ECDE completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Lakeview | -0.734128, 36.435737 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | N/A | 2500000 | 0 | 2500000 | Equitable | N/A | 2500000 | 0 | 7157555 | 100 | 7157555 | 3000000 | -7157555 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: No. Viable: No was not done.
3655 | Fencing of Lare Polytechnic with concrete post, chain link and main gate | Fencing of Lare Polytechnic with concrete post, chain link and main gate | To secure Lare Polytechnic with concrete post, chain link and main gate through fencing | Lare Polytechnic with concrete post, chain link and main gate fenced and secured | 3110504 | Other Infrastructure and Civil Works | Njoro | Lare | -0.445005, 36.021978 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 23 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 900000 | 0 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
3656 | Construction and completion of 4 door pit latrines at Crater Nursery School (ECDE) | Construction and completion of 4 door pit latrines at Crater Nursery School (ECDE) | To construct and completion of 4 door pit latrines at Crater Nursery School (ECDE) | And completion of 4 door pit latrines at Crater Nursery School (ECDE) constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maiella | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | N/A | 600000 | 0 | 600000 | Equitable | N/A | 600000 | 0 | 584286 | 0 | 584286 | 600000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
3657 | Construction of 6 door plus Urinal at Kongoni ECD | Construction of 6 door plus Urinal at Kongoni ECD | To construct 6 door plus Urinal at Kongoni ECD | 6 door plus Urinal at Kongoni ECD constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maiella | -0.804803 36.246244 0 22.5 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2022/23 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 584286 | 97.4 | 584286 | 584286 | 15714 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Eruc Africa Ltd. Assessor remarks: In use.
3658 | Construction Of Toilets At Kipkonyo Polytechnics | Construction Of Toilets At Kipkonyo Polytechnics | To construct Toilets At Kipkonyo Polytechnics | Toilets At Kipkonyo Polytechnics constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maiella | -0.781462, 36.223325 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2019 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 497700 | 99.5 | 497700 | 500000 | 2300 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Fabrica Building Construction.
3659 | Construction Of Four Door Toilet At Kimonio ECDE | Construction Of Four Door Toilet At Kimonio ECDE | To construct Four Door Toilet At Kimonio ECDE | Four Door Toilet At Kimonio ECDE constructed | 3110504 | Other Infrastructure and Civil Works | Molo | Mariashoni | -0.328275, 35.867813 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 499952 | 100 | 499952 | 500000 | 48 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3660 | Levelling Of Playground At Lawina Primary School | Levelling Of Playground At Lawina Primary School | To implement levelling of playground at lawina primary school for access to quality education and training | Levelling Of Playground At Lawina Primary School completed | 3110504 | Other Infrastructure and Civil Works | Molo | Mariashoni | -0.327859, 35.86732 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3661 | Construction Of 2 Training Rooms At Mathangauta Polytechnic | Construction Of 2 Training Rooms At Mathangauta Polytechnic | To construct 2 Training Rooms At Mathangauta Polytechnic | 2 Training Rooms At Mathangauta Polytechnic constructed | 3110504 | Other Infrastructure and Civil Works | Njoro | Mau Narok | -0.522677 36.057881 2081 7 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | N/A | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 1198555 | 47.9 | 1198555 | 2500000 | 1301445 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good state of repair.
3662 | Construction Of Hyrax Primary School ECD Latrines Boys/Girls And Installation Of Hand Washing Tank | Construction Of Hyrax Primary School ECD Latrines Boys/Girls And Installation Of Hand Washing Tank | To construct Hyrax Primary School ECD Latrines Boys/Girls And Installation Of Hand Washing Tank | Hyrax Primary School ECD Latrines Boys/Girls And Installation Of Hand Washing Tank constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Menengai | -0.269251 36.099069 1908.0999755859375 57.066001892089844 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | N/A | 1068360 | 1068360 | 1068360 | Equitable | N/A | 1068360 | 0 | 0 | 0 | 0 | 1068360 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not functional.
3663 | Construction of ECDE Toilets in Menengai Pry Sch Mangu | Construction of ECDE Toilets in Menengai Pry Sch Mangu | To construct ECDE Toilets in Menengai Pry Sch Mangu | ECDE Toilets in Menengai Pry Sch Mangu constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Menengai West | -0.169922 36.025178 1957.8 13 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2022/23 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 944510 | 94.5 | 944510 | 944510 | 55490 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional but almost full.
3664 | Construction Of Kichwa ECDE Toilets | Construction Of Kichwa ECDE Toilets | To construct Kichwa ECDE Toilets | Kichwa ECDE Toilets constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Menengai West | -0.122242, 36.008073 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 999844 | 999844 | Equitable | N/A | 999844 | 0 | 999844 | 100 | 999844 | 999844 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Mbuma.
3665 | Construction Of Mangu ECDE Toilets | Construction Of Mangu ECDE Toilets | To construct Mangu ECDE Toilets | Mangu ECDE Toilets constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Menengai West | -0.122242, 36.008073 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999200 | 99.9 | 999200 | 1000000 | 800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Mbuma.
3666 | Purchase and supply of COVID mitigation equipments (water tanks, masks) in ECDE centre | Purchase and supply of COVID mitigation equipments (water tanks, masks) in ECDE centre | To procure and supply COVID mitigation equipments (water tanks, masks) in ECDE centre | COVID mitigation equipments (water tanks, masks) in ECDE centre procured and supplied | 3110504 | Other Infrastructure and Civil Works | Rongai | Menengai West | -0.157327 36.001343 1813.7 720.3189697265625 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | N/A | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 0 | 0 | 0 | 2400000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
3667 | Construction of 4 door Toilets at Nguzu River ECDE | Construction of 4 door Toilets at Nguzu River ECDE | To construct 4 door Toilets at Nguzu River ECDE | 4 door Toilets at Nguzu River ECDE constructed | 3110504 | Other Infrastructure and Civil Works | Molo | Molo | -0.380641 35.796196 2793.679531111378 6 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2022/23 | 520000 | 520000 | 520000 | Equitable | N/A | 520000 | 0 | 729740 | 140.3 | 729740 | 499970 | -209740 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Bad. Objective met: Partially. Viable: Partially. Assessor remarks: The toilet is non existent.
3668 | Construction Of Modern Toilets, Septic Tank, Completion Of Administration Block At Molo Polytechnic | Construction Of Modern Toilets, Septic Tank, Completion Of Administration Block At Molo Polytechnic | To construct Modern Toilets, Septic Tank, Completion Of Administration Block At Molo Polytechnic | Modern Toilets, Septic Tank, Completion Of Administration Block At Molo Polytechnic constructed | 3110504 | Other Infrastructure and Civil Works | Molo | Molo Central | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 5318447.4 | 2071906.6 | 2071906.6 | Equitable | N/A | 2071906.6 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3669 | Design And Construction Of Mugaa ECDE Toilets At Sachangwan | Design And Construction Of Mugaa ECDE Toilets At Sachangwan | To design and construct Mugaa ECDE Toilets At Sachangwan | Mugaa ECDE Toilets At Sachangwan designed and constructed | 3110504 | Other Infrastructure and Civil Works | Molo | Molo Central | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | 2020/21 | 800000 | 729740 | 729740 | Equitable | N/A | 729740 | 0 | 0 | 0 | 0 | 900000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3670 | Construction Of Baraka Youth Polytechnic Toilets | Construction Of Baraka Youth Polytechnic Toilets | To construct Baraka Youth Polytechnic Toilets | Baraka Youth Polytechnic Toilets constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Mosop | -0.285402 35.892338 2173.4 20.5 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 499994 | 100 | 499994 | 500000 | 6 | Vired | 90 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Kefalice. Assessor remarks: Good.
3671 | Construction Of Ex Magret ECDE Toilet | Construction Of Ex Magret ECDE Toilet | To construct Ex Magret ECDE Toilet | Ex Magret ECDE Toilet constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Mosop | -0.260493, 35.933902 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | Not indicated | 500000 | 694 | 694 | Equitable | N/A | 694 | 0 | 694 | 100 | 694 | 694 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes viable. Contractor: In procurement.
3672 | Construction Of Ngecha ECDE Toilets | Construction Of Ngecha ECDE Toilets | To construct Ngecha ECDE Toilets | Ngecha ECDE Toilets constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Mosop | -0.260493, 35.933902 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | Not indicated | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 499994 | 100 | 499994 | 500000 | 6 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes viable. Contractor: In procurement.
3673 | Construction of Ngecha ECDE Toilet | Construction of Ngecha ECDE Toilet | To construct Ngecha ECDE Toilet | Ngecha ECDE Toilet constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Mosop | -0.260493, 35.933902 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | Not indicated | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 694 | 0.1 | 694 | 500000 | 499306 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes viable. Contractor: In procurement.
3674 | Fencing at Ngondu ECDE Compound | Fencing at Ngondu ECDE Compound | To secure at Ngondu ECDE Compound through fencing | At Ngondu ECDE Compound fenced and secured | 3110504 | Other Infrastructure and Civil Works | Rongai | Mosop | -0.279523 35.883943 2125.1 17.100000381469727 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not awarded. Viable: Viable. Contractor: Not awarded. Assessor remarks: Not yet awarded.
3675 | Construction Of Toilet At Sision ECDE | Construction Of Toilet At Sision ECDE | To construct Toilet At Sision ECDE | Toilet At Sision ECDE constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Naivasha East | -0.862203, 36.540422 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 999352 | 199.9 | 999352 | 500000 | -499352 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes.
3676 | Construction of Toilet at Sision ECD | Construction of Toilet at Sision ECD | To construct Toilet at Sision ECD | Toilet at Sision ECD constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Naivasha East | -0.862203, 36.540422 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 999352 | 199.9 | 999352 | 500000 | -499352 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes.
3677 | Fencing And Construction Of Toilet For Kariokor Kinungi ECDE | Fencing And Construction Of Toilet For Kariokor Kinungi ECDE | To secure And Construction Of Toilet For Kariokor Kinungi ECDE through fencing | And Construction Of Toilet For Kariokor Kinungi ECDE fenced and secured | 3110504 | Other Infrastructure and Civil Works | Naivasha | Naivasha East | -0.818586 36.54497 2410.60009765625 10.039999961853027 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | N/A | 359377 | 359377 | 359377 | Equitable | N/A | 359377 | 0 | 3600022 | 1001.7 | 3600022 | 359377 | -3240645 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Partially met. Viable: Viable with 35 learners. Assessor remarks: ECD classroom done without a toilets and fencing.
3678 | Fencing and construction of toilet for Kariokor, Kinungi ECD | Fencing and construction of toilet for Kariokor, Kinungi ECD | To secure and construction of toilet for Kariokor, Kinungi ECD through fencing | And construction of toilet for Kariokor, Kinungi ECD fenced and secured | 3110504 | Other Infrastructure and Civil Works | Naivasha | Naivasha East | -0.818586 36.54497 2410.60009765625 10.039999961853027 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | N/A | 359377 | 359377 | 359377 | Equitable | N/A | 359377 | 0 | 3600022 | 1001.7 | 3600022 | 359377 | -3240645 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Partially met. Viable: Viable with 35 learners. Assessor remarks: ECD classroom done without a toilets and fencing.
3679 | Repairing Of Maraigushu ECDE | Repairing Of Maraigushu ECDE | To implement repairing of maraigushu ecde for access to quality education and training | Repairing Of Maraigushu ECDE completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Naivasha East | -0.75252, 36.527393 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes.
3680 | Construction Of Mburu Gichua ECD Toilet And Installation Of Water Tank | Construction Of Mburu Gichua ECD Toilet And Installation Of Water Tank | To construct Mburu Gichua ECD Toilet And Installation Of Water Tank | Mburu Gichua ECD Toilet And Installation Of Water Tank constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Nakuru East | -0.369549, 36.152299 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | 2021/2022 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 1500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes.
3681 | Construction Of Pit Latrine/Water Tank And Playing Materials For Temotta ECDE | Construction Of Pit Latrine/Water Tank And Playing Materials For Temotta ECDE | To construct Pit Latrine/Water Tank And Playing Materials For Temotta ECDE | Pit Latrine/Water Tank And Playing Materials For Temotta ECDE constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Nyota | -0.30645 35.64604 2711.2 4.400000095367432 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 2207393 | 147.2 | 2207393 | 1500000 | -707393 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: YES. Viable: YES. Assessor remarks: IT WILL BE BENEFICIAL TO COMMUNITY.
3682 | Construction Of Toilets, Fencing, Connecting Electricity And Purchase Of Equipments At Sitoito Polytechnic | Construction Of Toilets, Fencing, Connecting Electricity And Purchase Of Equipments At Sitoito Polytechnic | To construct Toilets, Fencing, Connecting Electricity And Purchase Of Equipments At Sitoito Polytechnic | Toilets, Fencing, Connecting Electricity And Purchase Of Equipments At Sitoito Polytechnic constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Nyota | -0.38946, 35.568755 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2015-2016 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes, if it's operationalized.
3683 | Fencing of Maua Primary School | Fencing of Maua Primary School | To secure Maua Primary School through fencing | Maua Primary School fenced and secured | 3110504 | Other Infrastructure and Civil Works | Naivasha | Olkaria | -0.837028 36.366705 1881.9000244140625 16.700000762939453 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | N/A | 1008393 | 1008393 | 1008393 | Equitable | N/A | 1008393 | 0 | 0 | 0 | 0 | 988874 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yet to start. Viable: Yet to start. Assessor remarks: Yet to start.
3684 | Construction Of Perimeter Wall And Razor Wire Along Mwariki ECDE Center | Construction Of Perimeter Wall And Razor Wire Along Mwariki ECDE Center | To construct Perimeter Wall And Razor Wire Along Mwariki ECDE Center | Perimeter Wall And Razor Wire Along Mwariki ECDE Center constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Rhonda | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1996330 | 99.8 | 1996330 | 2000000 | 3670 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
3685 | Partitioning And Equipping Of Special Needs Classroom At Koinange Primary School | Partitioning And Equipping Of Special Needs Classroom At Koinange Primary School | To implement partitioning and equipping of special needs classroom at koinange primary school for access to quality education and training | Partitioning And Equipping Of Special Needs Classroom At Koinange Primary School completed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Shabab | -0.293948, 36.055144 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 744068 | 37.2 | 744068 | 2000000 | 1255932 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3686 | Construction Of Toilet At Koilitit ECD School | Construction Of Toilet At Koilitit ECD School | To construct Toilet At Koilitit ECD School | Toilet At Koilitit ECD School constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.046432 36.033078 1632.3999999999999 9.300000190734863 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 350000 | 348930 | 348930 | Equitable | N/A | 348930 | 0 | 348930 | 100 | 348930 | 350000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Done.
3687 | Construction Of Toilets At Lelechwet And Molok ECDE | Construction Of Toilets At Lelechwet And Molok ECDE | To construct Toilets At Lelechwet And Molok ECDE | Toilets At Lelechwet And Molok ECDE constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.078562, 35.933468 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | N/A | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 348930 | 43.6 | 348930 | 800000 | 451070 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No.
3688 | Design And Construction Of 4-Door Toilets At Kokwomoi ECDE | Design And Construction Of 4-Door Toilets At Kokwomoi ECDE | To design and construct 4-Door Toilets At Kokwomoi ECDE | 4-Door Toilets At Kokwomoi ECDE designed and constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.045687 36.049197 1618.2 7.800000190734863 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | N/A | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 1199997 | 400 | 1199997 | 300000 | -899997 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The teacher needs an ablution block.
3689 | Design And Construction Of 4-Door Toilets At Ruyobei ECDE | Design And Construction Of 4-Door Toilets At Ruyobei ECDE | To design and construct 4-Door Toilets At Ruyobei ECDE | 4-Door Toilets At Ruyobei ECDE designed and constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.045687 36.049197 1618.2 7.800000190734863 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | N/A | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 1132000 | 377.3 | 1132000 | 300000 | -832000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The teacher needs an ablution block.
3690 | Design And Construction Of Koyumtich ECDE Toilet | Design And Construction Of Koyumtich ECDE Toilet | To design and construct Koyumtich ECDE Toilet | Koyumtich ECDE Toilet designed and constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.110025 35.94125 0 1700 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 400000 | 396354 | 396354 | Equitable | N/A | 396354 | 0 | 396354 | 100 | 396354 | 400000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs alot of repair,Needs more toilets for staffs.
3691 | Construction of 3 (4 door Toilet) at Ruiyobei ECDE School, 71 ECDE School and Sawaiti ECDE School | Construction of 3 (4 door Toilet) at Ruiyobei ECDE School, 71 ECDE School and Sawaiti ECDE School | To construct 3 (4 door Toilet) at Ruiyobei ECDE School, 71 ECDE School and Sawaiti ECDE School | 3 (4 door Toilet) at Ruiyobei ECDE School, 71 ECDE School and Sawaiti ECDE School constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.06765 36.022245 1607 8.5 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2022/23 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1492890 | 99.5 | 1492890 | 1492890 | 7110 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No,until enrolment is done. Viable: It is viable but without children. Assessor remarks: Project complete but no enrolment.
3692 | Construction of a Toilet block and purchase of a water tank at Our Lady of Victory Primary | Construction of a Toilet block and purchase of a water tank at Our Lady of Victory Primary | To construct a Toilet block and purchase of a water tank at Our Lady of Victory Primary | A Toilet block and purchase of a water tank at Our Lady of Victory Primary constructed | 3110504 | Other Infrastructure and Civil Works | Subukia | Subukia | 0.00426 36.23702 1995.800048828125 39.599998474121094 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes.. Viable: Yes. The toilet serves the ecde learners. Contractor: No information. Assessor remarks: The toilet looks good..
3693 | Construction of Morro ECD toilet and fencing | Construction of Morro ECD toilet and fencing | To construct Morro ECD toilet and fencing | Morro ECD toilet and fencing constructed | 3110504 | Other Infrastructure and Civil Works | Subukia | Subukia | 0.010383, 36.223597 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2022/2023 | 1500000 | 0 | 1500000 | Equitable | N/A | 1500000 | 0 | 999980 | 100 | 999980 | 1500000 | -999980 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed.
3694 | Githima ECDE Fencing And Toilet | Githima ECDE Fencing And Toilet | To implement githima ecde fencing and toilet for access to quality education and training | Githima ECDE Fencing And Toilet completed | 3110504 | Other Infrastructure and Civil Works | Subukia | Subukia | -0.012055, 36.21717 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | 09/01/2022 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1198900 | 99.9 | 1198900 | 1200000 | 1100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes.. Viable: The learners use the toilet and the facility is protected. Contractor: Information not available.
3695 | Karung'o ECDE Fencing, Toilet And Floor | Karung'o ECDE Fencing, Toilet And Floor | To implement karung'o ecde fencing, toilet and floor for access to quality education and training | Karung'o ECDE Fencing, Toilet And Floor completed | 3110504 | Other Infrastructure and Civil Works | Subukia | Subukia | -0.010599 36.228434 2016.9000244140625 82.5 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | 2021/22 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1496440 | 99.8 | 1496440 | 1500000 | 3560 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes.. Viable: Yes. The project serves the people. Contractor: Information not available. Assessor remarks: The projects are in use.
3696 | Construction Of Ogiek Polytechnic Toilets | Construction Of Ogiek Polytechnic Toilets | To construct Ogiek Polytechnic Toilets | Ogiek Polytechnic Toilets constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Tinet | -0.403875 35.693755 0 899.9990234375 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 644401 | 644401 | 644401 | Equitable | N/A | 644401 | 0 | 2099 | 0.3 | 2099 | 644401 | 642302 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational and good condition.
3697 | Construction Of A Toilet At Kimangu ECDE | Construction Of A Toilet At Kimangu ECDE | To construct A Toilet At Kimangu ECDE | A Toilet At Kimangu ECDE constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Visoi | -0.148577, 35.839572 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | 2021/22 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 970000 | 161.7 | 970000 | 600000 | -370000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3698 | Construction of Rongai ICT hub and equipping | Construction of Rongai ICT hub and equipping | To construct Rongai ICT hub and equipping | Rongai ICT hub and equipping constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Visoi | -0.112228 35.887368 1817.7 20.799999237060547 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1798100 | 119.9 | 1798100 | 1450695 | -298100 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
3699 | Construction Of Toilet, Fencing And Equipping Of Classroom At Waka ECDE | Construction Of Toilet, Fencing And Equipping Of Classroom At Waka ECDE | To construct Toilet, Fencing And Equipping Of Classroom At Waka ECDE | Toilet, Fencing And Equipping Of Classroom At Waka ECDE constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Visoi | -0.137395, 35.824605 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | 2017/18 | 800000 | 792600 | 792600 | Equitable | N/A | 792600 | 0 | 970000 | 122.4 | 970000 | 792600 | -177400 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Rynix investment limited.
3700 | Design And Construction Of Kayanet ECD Toilets | Design And Construction Of Kayanet ECD Toilets | To design and construct Kayanet ECD Toilets | Kayanet ECD Toilets designed and constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Visoi | -0.112228 35.887368 1817.7 20.799999237060547 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | 2020/21 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 598560 | 99.8 | 598560 | 600000 | 1440 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
3701 | Construction And Equipping Of ICT Hub Facility/Hub Estate | Construction And Equipping Of ICT Hub Facility/Hub Estate | To construct and equip ICT Hub Facility/Hub Estate | ICT Hub Facility/Hub Estate constructed and equipped | 3110504 | Other Infrastructure and Civil Works | Naivasha | Viwandani | -0.714882 36.432885 0 200 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 1499845 | 30 | 1499845 | 5000000 | 3500155 | Stalled | 90 | 30 | Stalled — reasons to be confirmed by department | 2019 | N/A | 3500155 | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Assessor remarks: Effective.
3702 | Electricity Installation at Lalwet ECDE | Electricity Installation at Lalwet ECDE | To implement electricity installation at lalwet ecde for access to quality education and training | Electricity Installation at Lalwet ECDE completed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Kapkures | -0.27027, 36.036437 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2022/23 | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 0 | 0 | 0 | 300000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Very viable and serving purpose.
3703 | Equipping of Nakuru Polytechnic - purchase and supply of Tablet computers | Equipping of Nakuru Polytechnic - purchase and supply of Tablet computers | To equip Nakuru Polytechnic - purchase and supply of Tablet computers with necessary facilities and equipment | Nakuru Polytechnic - purchase and supply of Tablet computers equipped | 3111002 | Purchase of Computers, Printers and other IT Equipment | Nakuru East | Biashara-Nakuru | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | 2021/22 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 974400 | 97.4 | 974400 | 1000000 | 25600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3704 | Equipping Of Chelelwet ECDE | Equipping Of Chelelwet ECDE | To equip Chelelwet ECDE with necessary facilities and equipment | Chelelwet ECDE equipped | 3111109 | Purchase of Educational Aids and Related Equipment | Nakuru West | Barut | -0.346802, 36.035114 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | N/A | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 0 | 0 | 0 | 300000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Is yet to start. Viable: It's yet to start.
3705 | Equipping Of Gituru Polytechnic | Equipping Of Gituru Polytechnic | To equip Gituru Polytechnic with necessary facilities and equipment | Gituru Polytechnic equipped | 3111109 | Purchase of Educational Aids and Related Equipment | Naivasha | Biashara-Naivasha | -0.725835, 36.486833 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2021 | 2500000 | 2498730 | 2498730 | Equitable | N/A | 2498730 | 0 | 2483000 | 99.4 | 2483000 | 2500000 | 15730 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: N/a.
3706 | Equipping Of Kinamba Polytechnic | Equipping Of Kinamba Polytechnic | To equip Kinamba Polytechnic with necessary facilities and equipment | Kinamba Polytechnic equipped | 3111109 | Purchase of Educational Aids and Related Equipment | Naivasha | Biashara-Naivasha | -0.725835, 36.486833 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2021 | 2500000 | 2498730 | 2498730 | Equitable | N/A | 2498730 | 0 | 2474525 | 99 | 2474525 | 2498730 | 24205 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: N/a.
3707 | Equipping of Nakuru VTC Departments | Equipping of Nakuru VTC Departments | To equip Nakuru VTC Departments with necessary facilities and equipment | Nakuru VTC Departments equipped | 3111109 | Purchase of Educational Aids and Related Equipment | Nakuru East | Biashara-Nakuru | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2022/23 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 0 | 0 | 0 | 2444091 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3708 | Equipping Of Kongasis Polytechnic | Equipping Of Kongasis Polytechnic | To equip Kongasis Polytechnic with necessary facilities and equipment | Kongasis Polytechnic equipped | 3111109 | Purchase of Educational Aids and Related Equipment | Gilgil | Eburru/Mbaruk | -0.554731, 36.153036 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | Unspecified | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 985800 | 98.6 | 985800 | 2000000 | 14200 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Unspecified.
3709 | Equipping Ole Sultan Polytechnic | Equipping Ole Sultan Polytechnic | To equip Ole Sultan Polytechnic with necessary facilities and equipment | Ole Sultan Polytechnic equipped | 3111109 | Purchase of Educational Aids and Related Equipment | Gilgil | Elementaita | -0.567565 36.114003 1993.429 1.6779999732971191 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 2800000 | 2800000 | 2800000 | Equitable | N/A | 2800000 | 0 | 2800000 | 100 | 2800000 | 2800000 | 0 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: Partially. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Not Functional.
3710 | Equipping Njoro Vocational training Center of Excellence | Equipping Njoro Vocational training Center of Excellence | To equip Njoro Vocational training Center of Excellence with necessary facilities and equipment | Njoro Vocational training Center of Excellence equipped | 3111109 | Purchase of Educational Aids and Related Equipment | HQ | HQ | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | N/A | 5084163 | 5084163 | 5084163 | Equitable | N/A | 5084163 | 0 | 3535000 | 69.5 | 3535000 | 11157648 | 1549163 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
3711 | Equipping Of ECD Centers | Equipping Of ECD Centers | To equip ECD Centers with necessary facilities and equipment | ECD Centers equipped | 3111109 | Purchase of Educational Aids and Related Equipment | HQ | HQ | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | N/A | 17611176 | 36865308 | 36865308 | Equitable | N/A | 36865308 | 0 | 9787000 | 26.5 | 9787000 | 165600 | 27078308 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
3712 | Equipping Of ECDE Classes | Equipping Of ECDE Classes | To equip ECDE Classes with necessary facilities and equipment | ECDE Classes equipped | 3111109 | Purchase of Educational Aids and Related Equipment | HQ | HQ | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 10000000 | 4043398 | 4043398 | Equitable | N/A | 4043398 | 0 | 1561000 | 38.6 | 1561000 | 4043398 | 2482398 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
3713 | Equipping Of ECD'S | Equipping Of ECD'S | To equip ECD'S with necessary facilities and equipment | ECD'S equipped | 3111109 | Purchase of Educational Aids and Related Equipment | HQ | HQ | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | N/A | 6099924 | 5502636.7 | 5502636.7 | Equitable | N/A | 5502636.7 | 0 | 9787000 | 177.9 | 9787000 | 5502637 | -4284363.3 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
3714 | Equipping of vocational training centers | Equipping of vocational training centers | To equip vocational training centers with necessary facilities and equipment | Vocational training centers equipped | 3111109 | Purchase of Educational Aids and Related Equipment | HQ | HQ | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | N/A | 10000000 | 0 | 10000000 | Equitable | N/A | 10000000 | 0 | 9787000 | 0 | 9787000 | 10000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
3715 | Equipping Youth Polytechnics Cheptuech, Molo, Kagoto, Mau Summit | Equipping Youth Polytechnics Cheptuech, Molo, Kagoto, Mau Summit | To equip Youth Polytechnics Cheptuech, Molo, Kagoto, Mau Summit with necessary facilities and equipment | Youth Polytechnics Cheptuech, Molo, Kagoto, Mau Summit equipped | 3111109 | Purchase of Educational Aids and Related Equipment | HQ | HQ | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2022/23 | 11548737 | 10200177 | 10200177 | Equitable | N/A | 10200177 | 0 | 4123683 | 40.4 | 4123683 | 8800000 | 6076494 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3716 | Purchase And Supply Of Desks For Nyondia Primary School | Purchase And Supply Of Desks For Nyondia Primary School | To procure and supply Desks For Nyondia Primary School | Desks For Nyondia Primary School procured and supplied | 3111109 | Purchase of Educational Aids and Related Equipment | Gilgil | Malewa West | -0.702703, 36.471211 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | 2021/22 | 1000000 | 960000 | 960000 | Equitable | N/A | 960000 | 0 | 0 | 0 | 0 | 960000 | 0 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
3717 | Equipping Of Baraka Youth Polytechnic | Equipping Of Baraka Youth Polytechnic | To equip Baraka Youth Polytechnic with necessary facilities and equipment | Baraka Youth Polytechnic equipped | 3111109 | Purchase of Educational Aids and Related Equipment | Rongai | Mosop | -0.284455, 35.96628 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | 2025 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes it was viable. Contractor: Not awarded.
3718 | Equipping Of Ogilgei Youth Polytechnic | Equipping Of Ogilgei Youth Polytechnic | To equip Ogilgei Youth Polytechnic with necessary facilities and equipment | Ogilgei Youth Polytechnic equipped | 3111109 | Purchase of Educational Aids and Related Equipment | Rongai | Mosop | -0.284455, 35.96628 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | 2025 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 1499996 | 300 | 1499996 | 500000 | -999996 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes it was viable. Contractor: Not awarded.
3719 | Equipping Of ECDE Classroom At Murindat Primary | Equipping Of ECDE Classroom At Murindat Primary | To equip ECDE Classroom At Murindat Primary with necessary facilities and equipment | ECDE Classroom At Murindat Primary equipped | 3111109 | Purchase of Educational Aids and Related Equipment | Gilgil | Murindat | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | 2021/22 | 204490 | 204490 | 204490 | Equitable | N/A | 204490 | 0 | 201000 | 98.3 | 201000 | 1200000 | 3490 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3720 | Equipping of Free Area Vocational Training Center (Polytechnic) | Equipping of Free Area Vocational Training Center (Polytechnic) | To equip Free Area Vocational Training Center (Polytechnic) with necessary facilities and equipment | Free Area Vocational Training Center (Polytechnic) equipped | 3111109 | Purchase of Educational Aids and Related Equipment | Nakuru East | Nakuru East | -0.293862, 36.118139 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2022/2023 | 5000000 | 5000000 | 5000000 | Equitable | N/A | 5000000 | 0 | 650940 | 13 | 650940 | 4806300 | 4349060 | Stalled | 0 | 13 | Stalled — reasons to be confirmed by department | 2022 | N/A | 4349060 | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes.
3721 | Equipping Of ECDE In Maua , Sher Moi , Oserian , Mvuke Olkaria Primary And Naivasha With The Following Slides, Swings And See Saws | Equipping Of ECDE In Maua , Sher Moi , Oserian , Mvuke Olkaria Primary And Naivasha With The Following Slides, Swings And See Saws | To equip ECDE In Maua , Sher Moi , Oserian , Mvuke Olkaria Primary And Naivasha With The Following Slides, Swings And See Saws with necessary facilities and equipment | ECDE In Maua , Sher Moi , Oserian , Mvuke Olkaria Primary And Naivasha With The Following Slides, Swings And See Saws equipped | 3111109 | Purchase of Educational Aids and Related Equipment | Naivasha | Olkaria | 0.833651, 36.341813 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2500000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1746200 | 87.3 | 1746200 | 253800 | 253800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3722 | Purchase And Supply Of Playing Equipments At Mwariki ECDE | Purchase And Supply Of Playing Equipments At Mwariki ECDE | To procure and supply Playing Equipments At Mwariki ECDE | Playing Equipments At Mwariki ECDE procured and supplied | 3111109 | Purchase of Educational Aids and Related Equipment | Nakuru West | Rhonda | -0.3162, 36.06627 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | 20/21 | 710352 | 710352 | 710352 | Equitable | N/A | 710352 | 0 | 0 | 0 | 0 | 710352 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated.
3723 | Equipping of Koimugul and Ruiyobei ECDE | Equipping of Koimugul and Ruiyobei ECDE | To equip Koimugul and Ruiyobei ECDE with necessary facilities and equipment | Koimugul and Ruiyobei ECDE equipped | 3111109 | Purchase of Educational Aids and Related Equipment | Rongai | Solai | 0.099285, 36.142945 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2022/23 | 2022/23 | 2024 | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 278420 | 92.8 | 278420 | 21580 | 21580 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3724 | Hardware And Software Platforms | Hardware And Software Platforms | To implement hardware and software platforms for access to quality education and training | Hardware And Software Platforms completed | 3111111 | Purchase of ICT networking and Communications Equipment | HQ | HQ | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 4066066 | 1121066 | 1121066 | Equitable | N/A | 1121066 | 0 | 1528500 | 136.3 | 1528500 | 1121066 | -407434 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
3725 | Equipping Of ICT Hub | Equipping Of ICT Hub | To equip ICT Hub with necessary facilities and equipment | ICT Hub equipped | 3111111 | Purchase of ICT networking and Communications Equipment | Naivasha | Viwandani | -0.71728, 36.432885 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | N/A | 1827369 | 1827369 | 1827369 | Equitable | N/A | 1827369 | 0 | 0 | 0 | 0 | 1827369 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable.
3726 | Installation Of Network Firewall Licenses | Installation Of Network Firewall Licenses | To install Network Firewall Licenses | Network Firewall Licenses installed | 3111112 | Purchase of Software | HQ | HQ | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | 2021/22 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 999990 | 100 | 999990 | 0 | 10 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3727 | Software Development - Email Solution, Bursary And Feeding Programme Management Software | Software Development - Email Solution, Bursary And Feeding Programme Management Software | To implement software development - email solution, bursary and feeding programme management software for access to quality education and training | Software Development - Email Solution, Bursary And Feeding Programme Management Software completed | 3111112 | Purchase of Software | HQ | HQ | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 10000000 | 723403 | 723403 | Equitable | N/A | 723403 | 0 | 884500 | 122.3 | 884500 | 723403 | -161097 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
3728 | Renovation Of Bahati Wanyororo Polytechnic | Renovation Of Bahati Wanyororo Polytechnic | To rehabilitate Bahati Wanyororo Polytechnic to restore functionality | Bahati Wanyororo Polytechnic rehabilitated | 3111299 | Rehabilitation & Renovation - | Bahati | Bahati | -0.158496, 36.104997 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | N/A | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 0 | 0 | 0 | 800000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: Partially. Condition: Bad. Objective met: No. Viable: No.
3729 | Refurbishment Of Ndoroto ECDE | Refurbishment Of Ndoroto ECDE | To implement refurbishment of ndoroto ecde for access to quality education and training | Refurbishment Of Ndoroto ECDE completed | 3111299 | Rehabilitation & Renovation - | Naivasha | Biashara-Naivasha | -0.692638, 36.521717 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | 2022 | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 693800 | 99.1 | 693800 | 700000 | 6200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3730 | Refurbishment Of St. Paul And Gituru Primary ECDE | Refurbishment Of St. Paul And Gituru Primary ECDE | To implement refurbishment of st. paul and gituru primary ecde for access to quality education and training | Refurbishment Of St. Paul And Gituru Primary ECDE completed | 3111299 | Rehabilitation & Renovation - | Naivasha | Biashara-Naivasha | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | N/A | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 692555 | 98.9 | 692555 | 700000 | 7445 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
3731 | Renovation of Harambee Khalsa ECDE | Renovation of Harambee Khalsa ECDE | To rehabilitate Harambee Khalsa ECDE to restore functionality | Harambee Khalsa ECDE rehabilitated | 3111299 | Rehabilitation & Renovation - | HQ | HQ | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | N/A | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 0 | 0 | 0 | 800000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
3732 | Renovation Of Teta Youth Polytechnic | Renovation Of Teta Youth Polytechnic | To rehabilitate Teta Youth Polytechnic to restore functionality | Teta Youth Polytechnic rehabilitated | 3111299 | Rehabilitation & Renovation - | Kuresoi South | Keringet | -0.472632 35.621178 2687.900146484375 10.699999809265137 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In operation.
3733 | Renovation Of Saptonok ECDE | Renovation Of Saptonok ECDE | To rehabilitate Saptonok ECDE to restore functionality | Saptonok ECDE rehabilitated | 3111299 | Rehabilitation & Renovation - | Kuresoi South | Kiptagich | -0.536993 35.578477 2446.5 5.900000095367432 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | N/A | 317560 | 317560 | 317560 | Equitable | N/A | 317560 | 0 | 0 | 0 | 0 | 317560 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes but didn't meet to he needs of the area residents. Assessor remarks: Project not started.
3734 | Refurbishment Of Lenana ECDE classroom, Furniture And Playing Equipments | Refurbishment Of Lenana ECDE classroom, Furniture And Playing Equipments | To implement refurbishment of lenana ecde classroom, furniture and playing equipments for access to quality education and training | Refurbishment Of Lenana ECDE classroom, Furniture And Playing Equipments completed | 3111299 | Rehabilitation & Renovation - | Nakuru East | Menengai | -0.282232, 36.078932 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | 2021/22 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No.
3735 | Rehabilitation Of Munyu ECDE | Rehabilitation Of Munyu ECDE | To rehabilitate Munyu ECDE to restore functionality | Munyu ECDE rehabilitated | 3111299 | Rehabilitation & Renovation - | Naivasha | Naivasha East | -0.784832 36.523693 2415.9 5.900000095367432 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Increase funding.
3736 | Renovation Of ECD Classroom At Sher Moi | Renovation Of ECD Classroom At Sher Moi | To rehabilitate ECD Classroom At Sher Moi to restore functionality | ECD Classroom At Sher Moi rehabilitated | 3111299 | Rehabilitation & Renovation - | Naivasha | Olkaria | -0.836906, 36.366216 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No.
3737 | Equipping Of Mwariki ECDE Administration Block And Classroom | Equipping Of Mwariki ECDE Administration Block And Classroom | To equip Mwariki ECDE Administration Block And Classroom with necessary facilities and equipment | Mwariki ECDE Administration Block And Classroom equipped | 3111299 | Rehabilitation & Renovation - | Nakuru West | Rhonda | -0.316268, 36.065952 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | 22/23 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 4978558 | 414.9 | 4978558 | 1200000 | -3778558 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated.
3738 | Equipping Of Ogiek Polytechnic | Equipping Of Ogiek Polytechnic | To equip Ogiek Polytechnic with necessary facilities and equipment | Ogiek Polytechnic equipped | 3111299 | Rehabilitation & Renovation - | Kuresoi South | Tinet | -0.478177, 35.670193 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2020/21 | 2020/21 | N/A | 1040698 | 1040698 | 1040698 | Equitable | N/A | 1040698 | 0 | 0 | 0 | 0 | 1040698 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3739 | Purchase Of 1 Acre Land For Kimugul ECDE | Purchase Of 1 Acre Land For Kimugul ECDE | To procure 1 Acre Land For Kimugul ECDE | 1 Acre Land For Kimugul ECDE procured | 3130101 | Acquisition of Land | Kuresoi South | Amalo | -0.640943, 35.623492 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2017 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Stalled | 75 | N/A | STALLED. TO BE SUPPLEMENTED | 2018 | N/A | N/A | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3740 | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Kwendo ECD | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Kwendo ECD | To construct 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Kwendo ECD | 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Kwendo ECD constructed | 4130299 | N/A | Kuresoi South | Amalo | -0.570768, 35.664825 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016 | 1000000 | 992345 | 992345 | Equitable | N/A | 992345 | 0 | 1499996 | 151.2 | 1499996 | 992345 | -507651 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: no. Viable: no.
3741 | Construction Of The Administration Block And Toilets At Kaplamai Polytechnic | Construction Of The Administration Block And Toilets At Kaplamai Polytechnic | To construct The Administration Block And Toilets At Kaplamai Polytechnic | The Administration Block And Toilets At Kaplamai Polytechnic constructed | 4130299 | N/A | Kuresoi South | Amalo | -0.658488, 35.639393 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2020 | 2000000 | 1996557 | 1996557 | Equitable | N/A | 1996557 | 0 | 1996557 | 100 | 1996557 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes.
3742 | Construction Of 2 ECDE Classroom At Kinamba ECDE | Construction Of 2 ECDE Classroom At Kinamba ECDE | To construct 2 ECDE Classroom At Kinamba ECDE | 2 ECDE Classroom At Kinamba ECDE constructed | 4130299 | N/A | Naivasha | Biashara-Naivasha | -0.718757, 36.483535 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2021 | 2400000 | 2389990 | 2389990 | Equitable | N/A | 2389990 | 0 | 2389990 | 100 | 2389990 | 2389990 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Dakuki.
3743 | Construction Of Gituru Polytechnic | Construction Of Gituru Polytechnic | To construct Gituru Polytechnic | Gituru Polytechnic constructed | 4130299 | N/A | Naivasha | Biashara-Naivasha | -0.661007, 36.50238 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2019/20 | 2020 | 16000000 | 21997 | 21997 | Equitable | N/A | 21997 | 0 | 8683480 | 39475.7 | 8683480 | 21997 | -8661483 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: Dakuki.
3744 | Construction Of An ECD Classroom At Dundori Primary School | Construction Of An ECD Classroom At Dundori Primary School | To construct An ECD Classroom At Dundori Primary School | An ECD Classroom At Dundori Primary School constructed | 4130299 | N/A | Bahati | Dundori | -0.25394, 36.238355 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/2019 | 1200000 | 22.05 | 22.05 | Equitable | N/A | 22.05 | 0 | 1199978 | 5442077.1 | 1199978 | 22 | -1199955.95 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Ms Top Notch.
3745 | Construction Of Mikeu ECDE Classroom | Construction Of Mikeu ECDE Classroom | To construct Mikeu ECDE Classroom | Mikeu ECDE Classroom constructed | 4130299 | N/A | Bahati | Dundori | -0.249596 36.231481 2331.10009765625 20 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1200000 | 1168060 | 1168060 | Equitable | N/A | 1168060 | 0 | 1168060 | 100 | 1168060 | 1200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Done under NKU/CITY/222/2013-2014 no septic tank constructed.
3746 | Kaburi ECDE - Construction Of I Classroom | Kaburi ECDE - Construction Of I Classroom | To implement kaburi ecde - construction of i classroom for access to quality education and training | Kaburi ECDE - Construction Of I Classroom completed | 4130299 | N/A | Bahati | Dundori | -0.237247 36.23572 2418 3.0999999046325684 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2017/18 | 2017/18 | N/A | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1168060 | 97.3 | 1168060 | 1200000 | 31940 | Vired | 25 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: M/s Tripple. Assessor remarks: The was not fully completed, lacks water tank , terrazzo and electricity..
3747 | Construction Of 1 No. ECD Classroom, Teachers Toilet, Pupils Toilet And Watering Point At Kapkures ECD | Construction Of 1 No. ECD Classroom, Teachers Toilet, Pupils Toilet And Watering Point At Kapkures ECD | To construct 1 No. ECD Classroom, Teachers Toilet, Pupils Toilet And Watering Point At Kapkures ECD | 1 No. ECD Classroom, Teachers Toilet, Pupils Toilet And Watering Point At Kapkures ECD constructed | 4130299 | N/A | Gilgil | Eburru/Mbaruk | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 156146 | 156146 | Equitable | N/A | 156146 | 0 | 1195536 | 765.7 | 1195536 | 156146 | -1039390 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3748 | Construction Of 3 ECD Classroom At Morop Primary And Kiungururia Primary | Construction Of 3 ECD Classroom At Morop Primary And Kiungururia Primary | To construct 3 ECD Classroom At Morop Primary And Kiungururia Primary | 3 ECD Classroom At Morop Primary And Kiungururia Primary constructed | 4130299 | N/A | Gilgil | Eburru/Mbaruk | -0.605373, 36.164023 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | Unspecified | 3600000 | 239110 | 239110 | Equitable | N/A | 239110 | 0 | 2160890 | 903.7 | 2160890 | 239110 | -1921780 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Yes. Contractor: Unspecified.
3749 | Construction Of Elburgon ECDE Classroom | Construction Of Elburgon ECDE Classroom | To construct Elburgon ECDE Classroom | Elburgon ECDE Classroom constructed | 4130299 | N/A | Molo | Elburgon | -0.292714, 35.791345 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2017/18 | 2017/18 | - | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1194994 | 99.6 | 1194994 | 1200000 | 5006 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3750 | Constuction Of Mutate Primary ECDE Classroom | Constuction Of Mutate Primary ECDE Classroom | To implement constuction of mutate primary ecde classroom for access to quality education and training | Constuction Of Mutate Primary ECDE Classroom completed | 4130299 | N/A | Molo | Elburgon | -0.294954, 35.766447 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | - | 1222382 | 1222382 | 1222382 | Equitable | N/A | 1222382 | 0 | 1194994 | 97.8 | 1194994 | 1222382 | 27388 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3751 | Construction Of 1No. Classroom At Kiambogo Township ECD | Construction Of 1No. Classroom At Kiambogo Township ECD | To construct 1No. Classroom At Kiambogo Township ECD | 1No. Classroom At Kiambogo Township ECD constructed | 4130299 | N/A | Gilgil | Elementaita | -0.595422 36.130154 0 98.4000015258789 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1166090 | 1166090 | Equitable | N/A | 1166090 | 0 | 1166090 | 100 | 1166090 | 1200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs renovation.
3752 | Construction Of 1No. Classroom At Muriricua Primary ECD | Construction Of 1No. Classroom At Muriricua Primary ECD | To construct 1No. Classroom At Muriricua Primary ECD | 1No. Classroom At Muriricua Primary ECD constructed | 4130299 | N/A | Gilgil | Elementaita | -0.566243 36.119887 1951.9 7.5 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1198280 | 409770 | 409770 | Equitable | N/A | 409770 | 0 | 1166090 | 284.6 | 1166090 | 409770 | -756320 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
3753 | Construction Of A Classroom At Gwachati ECD | Construction Of A Classroom At Gwachati ECD | To construct A Classroom At Gwachati ECD | A Classroom At Gwachati ECD constructed | 4130299 | N/A | Gilgil | Elementaita | -0.616893 36.148898 2042.8999999999999 16.5 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1200000 | 81930 | 81930 | Equitable | N/A | 81930 | 0 | 80430 | 98.2 | 80430 | 81930 | 1500 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In use.
3754 | Equipping Ole Sultan Polytechnic | Equipping Ole Sultan Polytechnic | To equip Ole Sultan Polytechnic with necessary facilities and equipment | Ole Sultan Polytechnic equipped | 4130299 | N/A | Gilgil | Elementaita | -0.567565 36.114003 1993.429 1.6779999732971191 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 2800000 | 0 | 2800000 | Equitable | N/A | 2800000 | 0 | 2800000 | 0 | 2800000 | 2800000 | 0 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: Partially. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Not Functional.
3755 | Installation Of Lightning Arresters At Elementaita ECD | Installation Of Lightning Arresters At Elementaita ECD | To install Lightning Arresters At Elementaita ECD | Lightning Arresters At Elementaita ECD installed | 4130299 | N/A | Gilgil | Elementaita | -0.616691, 36.125577 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 200000 | 200000 | 200000 | Equitable | N/A | 200000 | 0 | 0 | 0 | 0 | 200000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3756 | Njeru ECDE - Construction Of One Classrooms At Njeru ECDE | Njeru ECDE - Construction Of One Classrooms At Njeru ECDE | To implement njeru ecde - construction of one classrooms at njeru ecde for access to quality education and training | Njeru ECDE - Construction Of One Classrooms At Njeru ECDE completed | 4130299 | N/A | Gilgil | Elementaita | -0.585127 36.13751 2039.304 5.4679999351501465 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 1200000 | 119 | 119 | Equitable | N/A | 119 | 0 | 119 | 100 | 119 | 119 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
3757 | Ole Sultan Polytechnic Administration Blocks And Toilets | Ole Sultan Polytechnic Administration Blocks And Toilets | To implement ole sultan polytechnic administration blocks and toilets for access to quality education and training | Ole Sultan Polytechnic Administration Blocks And Toilets completed | 4130299 | N/A | Gilgil | Elementaita | -0.567384 36.1137 1948.66 1.1130000352859497 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2015/16 | 2015/16 | 2015/16 | 3799982.4 | 3800000 | 3800000 | Equitable | N/A | 3800000 | 0 | 3799733 | 100 | 3799733 | 3800000 | 267 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
3758 | Lakeview ECDE Center - Construction Of A Perimetre Wall And Gate | Lakeview ECDE Center - Construction Of A Perimetre Wall And Gate | To implement lakeview ecde center - construction of a perimetre wall and gate for access to quality education and training | Lakeview ECDE Center - Construction Of A Perimetre Wall And Gate completed | 4130299 | N/A | Nakuru East | Flamingo | -0.30524, 36.078817 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2017/18 | 2017/18 | fy2017/2018 | 5000000 | 135987 | 135987 | Equitable | N/A | 135987 | 0 | 135987 | 100 | 135987 | 135987 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Peshmac Enteprises.
3759 | Design And Construction Of 2 ECDE Classes At Race Track Primary School | Design And Construction Of 2 ECDE Classes At Race Track Primary School | To design and construct 2 ECDE Classes At Race Track Primary School | 2 ECDE Classes At Race Track Primary School designed and constructed | 4130299 | N/A | Nakuru East | Flamingo | -0.312617, 36.069464 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | Fy2018-2019 | 2400000 | 360243 | 360243 | Equitable | N/A | 360243 | 0 | 352009 | 97.7 | 352009 | 360243 | 8234 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Almaio Holdings.
3760 | Construction Of Workshops- Njoro VTC | Construction Of Workshops- Njoro VTC | To construct Workshops- Njoro VTC | Workshops- Njoro VTC constructed | 4130299 | N/A | HQ | HQ | -0.337502, 35.952445 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2024 | 6000000 | 2513599.95 | 2513599.95 | Equitable | Equitable | 2513599.95 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Ongoing. Viable: Yes. Contractor: Fabrica Building and construction company Ltd.
3761 | Digital Centres Internet Setup | Digital Centres Internet Setup | To implement digital centres internet setup for access to quality education and training | Digital Centres Internet Setup completed | 4130299 | N/A | HQ | HQ | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 2000000 | 8264400 | Equitable | N/A | 8264400 | 0 | 4672484 | 233.6 | 4672484 | 4942144 | -2672484 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3762 | Equiping Youth Polytechnics | Equiping Youth Polytechnics | To implement equiping youth polytechnics for access to quality education and training | Equiping Youth Polytechnics completed | 4130299 | N/A | HQ | HQ | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 4250360 | 4250360 | Equitable | N/A | 4250360 | 0 | 4123683 | 97 | 4123683 | 8800000 | 126677 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3763 | Improvement Of Learning Environment Through Equipping Of ECDE Centres In All Sub Counties | Improvement Of Learning Environment Through Equipping Of ECDE Centres In All Sub Counties | To implement improvement of learning environment through equipping of ecde centres in all sub counties for access to quality education and training | Improvement Of Learning Environment Through Equipping Of ECDE Centres In All Sub Counties completed | 4130299 | N/A | HQ | HQ | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 20597085 | 1745742 | 1745742 | Equitable | N/A | 1745742 | 0 | 1744000 | 99.9 | 1744000 | 1745742 | 1742 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3764 | Reinforcement Of County Server Rooms And Digital Centres In All Sub Counties | Reinforcement Of County Server Rooms And Digital Centres In All Sub Counties | To implement reinforcement of county server rooms and digital centres in all sub counties for access to quality education and training | Reinforcement Of County Server Rooms And Digital Centres In All Sub Counties completed | 4130299 | N/A | HQ | HQ | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 5000000 | 2631780 | 2631780 | Equitable | N/A | 2631780 | 0 | 2217197 | 84.2 | 2217197 | 414583 | 414583 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
3765 | Revitalization Of Youth Polytechnic | Revitalization Of Youth Polytechnic | To implement revitalization of youth polytechnic for access to quality education and training | Revitalization Of Youth Polytechnic completed | 4130299 | N/A | HQ | HQ | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 20000000 | 659133 | 659133 | Equitable | N/A | 659133 | 0 | 623800 | 94.6 | 623800 | 659133 | 35333 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3766 | Software Development - Email Solution, Bursary And Feeding Programme Management Software | Software Development - Email Solution, Bursary And Feeding Programme Management Software | To implement software development - email solution, bursary and feeding programme management software for access to quality education and training | Software Development - Email Solution, Bursary And Feeding Programme Management Software completed | 4130299 | N/A | HQ | HQ | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 10000000 | 1607903 | 1607903 | Equitable | N/A | 1607903 | 0 | 884500 | 55 | 884500 | 723403 | 723403 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
3767 | Airstrip ECDE - Construction Of One Classroom And Equiping | Airstrip ECDE - Construction Of One Classroom And Equiping | To implement airstrip ecde - construction of one classroom and equiping for access to quality education and training | Airstrip ECDE - Construction Of One Classroom And Equiping completed | 4130299 | N/A | Naivasha | Hells Gate | -0.778059, 36.42951 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2017/18 | 2017/18 | N/A | 2000000 | 1173036 | 1173036 | Equitable | N/A | 1173036 | 0 | 1171977 | 99.9 | 1171977 | 1173036 | 1059 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Good. Objective met: Somewhat. Viable: Yes.
3768 | Karagita ECDE - Construction Of One Classroom And Equiping | Karagita ECDE - Construction Of One Classroom And Equiping | To implement karagita ecde - construction of one classroom and equiping for access to quality education and training | Karagita ECDE - Construction Of One Classroom And Equiping completed | 4130299 | N/A | Naivasha | Hells Gate | -0.776669, 36.433058 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 1998654 | 1998654 | Equitable | N/A | 1998654 | 0 | 1998654 | 100 | 1998654 | 1998654 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yed.
3769 | Longonot DEB Pri School ECDE - Construction Of Two Classrooms And Equiping | Longonot DEB Pri School ECDE - Construction Of Two Classrooms And Equiping | To implement longonot deb pri school ecde - construction of two classrooms and equiping for access to quality education and training | Longonot DEB Pri School ECDE - Construction Of Two Classrooms And Equiping completed | 4130299 | N/A | Naivasha | Hells Gate | -0.814865, 36.399555 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2600000 | 86.7 | 2600000 | 3000000 | 400000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3770 | Construction Of ECDE Classroom, Toilets And Water Point At Cedar Lodge | Construction Of ECDE Classroom, Toilets And Water Point At Cedar Lodge | To construct ECDE Classroom, Toilets And Water Point At Cedar Lodge | ECDE Classroom, Toilets And Water Point At Cedar Lodge constructed | 4130299 | N/A | Bahati | Kabatini | -0.186813 36.177893 2119.520263671875 21.0049991607666 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 2400000 | 1650000 | 1650000 | Equitable | N/A | 1650000 | 0 | 1650000 | 100 | 1650000 | 1700000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/a EDROSE ventures limited. Assessor remarks: Project is complete and in use.
3771 | Construction Of Wendo Polytechnic | Construction Of Wendo Polytechnic | To construct Wendo Polytechnic | Wendo Polytechnic constructed | 4130299 | N/A | Bahati | Kabatini | -0.181071, 36.180736 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2019 | 2000000 | 2135 | 2135 | Equitable | N/A | 2135 | 0 | 2135 | 100 | 2135 | 2135 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: M/s Glazers general supplies and company.
3772 | Construction Of Mahinga ECDE Toilet - Construction Of Mahinga ECDE Toilet | Construction Of Mahinga ECDE Toilet - Construction Of Mahinga ECDE Toilet | To construct Mahinga ECDE Toilet - Construction Of Mahinga ECDE Toilet | Mahinga ECDE Toilet - Construction Of Mahinga ECDE Toilet constructed | 4130299 | N/A | Subukia | Kabazi | -0.12904 36.15429 0 220 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 700000 | 699162 | 699162 | Equitable | N/A | 699162 | 0 | 699162 | 100 | 699162 | 699162 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Requires renovations, additional classroom and furniture.
3773 | Construction Of Mika ECDE Toilet | Construction Of Mika ECDE Toilet | To construct Mika ECDE Toilet | Mika ECDE Toilet constructed | 4130299 | N/A | Subukia | Kabazi | -0.12904 36.15429 0 220 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2021/22 | 2021/22 | N/A | 472895 | 472895 | 472895 | Equitable | N/A | 472895 | 0 | 682652 | 144.4 | 682652 | 472895 | -209757 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Requires renovations, additional classroom and furniture.
3774 | Construction Of ECD Class At Bureti ECD | Construction Of ECD Class At Bureti ECD | To construct ECD Class At Bureti ECD | ECD Class At Bureti ECD constructed | 4130299 | N/A | Kuresoi North | Kamara | -0.092833 35.682177 2536.4 3.0999999046325684 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 800000 | 830 | 830 | Equitable | N/A | 830 | 0 | 830 | 100 | 830 | 830 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Partially. Contractor: Not indicated. Assessor remarks: Needs additional teachers, classrooms, furniture and pitlatrines.
3775 | Construction Of ECD Class At Choronok ECD | Construction Of ECD Class At Choronok ECD | To construct ECD Class At Choronok ECD | ECD Class At Choronok ECD constructed | 4130299 | N/A | Kuresoi North | Kamara | -0.210503 35.662043 2676.9 3.0999999046325684 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 800000 | 1199975 | 1199975 | Equitable | N/A | 1199975 | 0 | 1199975 | 100 | 1199975 | 1199975 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Kirgot Enterprises. Assessor remarks: Project needs more classrooms a pit latrines.
3776 | Construction Of ECD Class At Taban ECD | Construction Of ECD Class At Taban ECD | To construct ECD Class At Taban ECD | ECD Class At Taban ECD constructed | 4130299 | N/A | Kuresoi North | Kamara | -0.07866 35.672895 2565.1 2.9000000953674316 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 800000 | 2314 | 2314 | Equitable | N/A | 2314 | 0 | 2314 | 100 | 2314 | 2314 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Tank provided. No pitlatrines.
3777 | Equipping Of Kamara Polytechnic | Equipping Of Kamara Polytechnic | To equip Kamara Polytechnic with necessary facilities and equipment | Kamara Polytechnic equipped | 4130299 | N/A | Kuresoi North | Kamara | -0.167952 35.675978 2630.6 10.300000190734863 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 987900 | 98.8 | 987900 | 1000000 | 12100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Yes. Contractor: Not indicated. Assessor remarks: Needs more equipments.
3778 | Lalwet ECD Land | Lalwet ECD Land | To implement lalwet ecd land for access to quality education and training | Lalwet ECD Land completed | 4130299 | N/A | Nakuru West | Kapkures | -0.324324 36.036613 0 2000 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 7000000 | 7000000 | 7000000 | Equitable | N/A | 7000000 | 0 | 0 | 0 | 0 | 7000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. It's serving as school. Assessor remarks: About 1and quarter acreLand purchased and serving.
3779 | Toilet Desks,Desk And Washing Point Ingobor | Toilet Desks,Desk And Washing Point Ingobor | To implement toilet desks,desk and washing point ingobor for access to quality education and training | Toilet Desks,Desk And Washing Point Ingobor completed | 4130299 | N/A | Nakuru West | Kapkures | -0.306306 36.018533 0 2000 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2949834.6 | 1635 | 1635 | Equitable | N/A | 1635 | 0 | 1635 | 100 | 1635 | 1635 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Viable. But did not meet needs. Assessor remarks: Stalled. Not completed.
3780 | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Kapkores ECD | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Kapkores ECD | To construct 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Kapkores ECD | 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Kapkores ECD constructed | 4130299 | N/A | Kuresoi South | Keringet | -0.446097, 35.637505 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1199997.8 | 156143 | 156143 | Equitable | N/A | 156143 | 0 | 156143 | 100 | 156143 | 156143 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3781 | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Kipkoibet ECD | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Kipkoibet ECD | To construct 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Kipkoibet ECD | 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Kipkoibet ECD constructed | 4130299 | N/A | Kuresoi South | Keringet | -0.446097, 35.637505 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1199950 | 1199950 | 1199950 | Equitable | N/A | 1199950 | 0 | 1199950 | 100 | 1199950 | 1199950 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3782 | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Mwangate ECD | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Mwangate ECD | To construct 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Mwangate ECD | 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Mwangate ECD constructed | 4130299 | N/A | Kuresoi South | Keringet | -0.446097, 35.637505 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1000000 | 497952 | 497952 | Equitable | N/A | 497952 | 0 | 340868 | 68.5 | 340868 | 497952 | 157084 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3783 | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Tegat ECD | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Tegat ECD | To construct 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Tegat ECD | 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Tegat ECD constructed | 4130299 | N/A | Kuresoi South | Keringet | -0.446097, 35.637505 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1199997.8 | 340868 | 340868 | Equitable | N/A | 340868 | 0 | 340868 | 100 | 340868 | 340868 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3784 | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Tembwo ECD | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Tembwo ECD | To construct 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Tembwo ECD | 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Tembwo ECD constructed | 4130299 | N/A | Kuresoi South | Keringet | -0.421928 35.666268 2651.5 5.599999904632568 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1199990 | 1199990 | 1199990 | Equitable | N/A | 1199990 | 0 | 1199990 | 100 | 1199990 | 1199990 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
3785 | Construction Of 2 No Classrooms At Upendo | Construction Of 2 No Classrooms At Upendo | To construct 2 No Classrooms At Upendo | 2 No Classrooms At Upendo constructed | 4130299 | N/A | Kuresoi South | Keringet | -0.463932 35.69647 2646.3 6.5 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1693833 | 1693833 | 1693833 | Equitable | N/A | 1693833 | 0 | 667928 | 39.4 | 667928 | 1693833 | 1025905 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
3786 | Kibanguui ECD | Kibanguui ECD | To implement kibanguui ecd for access to quality education and training | Kibanguui ECD completed | 4130299 | N/A | Kuresoi South | Keringet | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2015/16 | 2015/16 | 2015/16 | 1190844 | 1190000 | 1190000 | Equitable | N/A | 1190000 | 0 | 0 | 0 | 0 | 1190000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3787 | Construction Of Saptet ECD Classroom | Construction Of Saptet ECD Classroom | To construct Saptet ECD Classroom | Saptet ECD Classroom constructed | 4130299 | N/A | Kuresoi South | Keringet | -0.485137 35.699573 2616.3 98.4000015258789 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1330000 | 851233 | 851233 | Equitable | N/A | 851233 | 0 | 667928 | 78.5 | 667928 | 183305 | 183305 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need another classroom.
3788 | Construction Of Tendwet ECD Classroom | Construction Of Tendwet ECD Classroom | To construct Tendwet ECD Classroom | Tendwet ECD Classroom constructed | 4130299 | N/A | Kuresoi South | Keringet | -0.50589, 35.698535 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1330000 | 851233 | 851233 | Equitable | N/A | 851233 | 0 | 312620 | 36.7 | 312620 | 538613 | 538613 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3789 | Cheptuech Polytechnic | Cheptuech Polytechnic | To implement cheptuech polytechnic for access to quality education and training | Cheptuech Polytechnic completed | 4130299 | N/A | Kuresoi South | Kiptagich | -0.59162 35.645365 2576.7 24.700000762939453 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 1500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: No. Viable: Viable but needs not met. Assessor remarks: Need concrete road for a permanent solution.
3790 | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Kibirech ECD | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Kibirech ECD | To construct 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Kibirech ECD | 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Kibirech ECD constructed | 4130299 | N/A | Kuresoi South | Kiptagich | -0.586967 35.633358 2444.3999999999996 12.399999618530273 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1500000 | 229823 | 229823 | Equitable | N/A | 229823 | 0 | 1270177 | 552.7 | 1270177 | 229823 | -1040354 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Don't. Assessor remarks: The project is complete but does not have toilets and windows are shattered.
3791 | Construction Of Ekabugunot ECDE | Construction Of Ekabugunot ECDE | To construct Ekabugunot ECDE | Ekabugunot ECDE constructed | 4130299 | N/A | Kuresoi South | Kiptagich | -0.536993 35.578477 2446.5 5.900000095367432 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2014/15 | 2014/15 | 2014/15 | 999363 | 999363 | 999363 | Equitable | N/A | 999363 | 0 | 1199995 | 120.1 | 1199995 | 999363 | -200632 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes but didn't meet to he needs of the area residents. Assessor remarks: Project not started.
3792 | Construction Of Emitik ECD Classroom | Construction Of Emitik ECD Classroom | To construct Emitik ECD Classroom | Emitik ECD Classroom constructed | 4130299 | N/A | Kuresoi South | Kiptagich | -0.63565 35.6059 2318.2000000000003 14.899999618530273 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1200000 | 1199740 | 1199740 | Equitable | N/A | 1199740 | 0 | 1199995 | 100 | 1199995 | 1799740 | -255 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Yes but needs not met. Assessor remarks: Uncompleted and can't be used.
3793 | Construction Of Konoin ECD Classroom | Construction Of Konoin ECD Classroom | To construct Konoin ECD Classroom | Konoin ECD Classroom constructed | 4130299 | N/A | Kuresoi South | Kiptagich | -0.57719, 35.57822 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1200000 | 1199995 | 1199995 | Equitable | N/A | 1199995 | 0 | 1199995 | 100 | 1199995 | 1200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable.
3794 | Construction Of Sitotwet ECD Classroom | Construction Of Sitotwet ECD Classroom | To construct Sitotwet ECD Classroom | Sitotwet ECD Classroom constructed | 4130299 | N/A | Kuresoi South | Kiptagich | -0.598048 35.611248 2413 13.800000190734863 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1200000 | 202597 | 202597 | Equitable | N/A | 202597 | 0 | 1199995 | 592.3 | 1199995 | 202597 | -997398 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Don't know. Assessor remarks: The project is complete but there are no toilets.
3795 | Ketitui Central ECDE Classroom - Design And Construction Of Ketitui ECDE Classroom | Ketitui Central ECDE Classroom - Design And Construction Of Ketitui ECDE Classroom | To implement ketitui central ecde classroom - design and construction of ketitui ecde classroom for access to quality education and training | Ketitui Central ECDE Classroom - Design And Construction Of Ketitui ECDE Classroom completed | 4130299 | N/A | Kuresoi South | Kiptagich | -0.63565 35.6059 2318.2000000000003 14.899999618530273 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 1200000 | 1147660 | 1147660 | Equitable | N/A | 1147660 | 0 | 1147660 | 100 | 1147660 | 1200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Yes but needs not met. Assessor remarks: Uncompleted and can't be used.
3796 | Chemare ECD - Design And Construction Of 1. No ECD Classroom At Kipkoimet ECD | Chemare ECD - Design And Construction Of 1. No ECD Classroom At Kipkoimet ECD | To implement chemare ecd - design and construction of 1. no ecd classroom at kipkoimet ecd for access to quality education and training | Chemare ECD - Design And Construction Of 1. No ECD Classroom At Kipkoimet ECD completed | 4130299 | N/A | Kuresoi North | Kiptororo | -0.374828 35.553043 2592.5 3.799999952316284 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2017/18 | 2017/18 | N/A | 1200000 | 376428 | 376428 | Equitable | N/A | 376428 | 0 | 648869 | 172.4 | 648869 | 376428 | -272441 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: No. Assessor remarks: The project is complete but poorly sited, structure not in use..
3797 | Chorwa ECD - Design And Construction Of 1. No ECD Classroom At Chorwa ECD | Chorwa ECD - Design And Construction Of 1. No ECD Classroom At Chorwa ECD | To implement chorwa ecd - design and construction of 1. no ecd classroom at chorwa ecd for access to quality education and training | Chorwa ECD - Design And Construction Of 1. No ECD Classroom At Chorwa ECD completed | 4130299 | N/A | Kuresoi North | Kiptororo | -0.374828 35.553043 2592.5 3.799999952316284 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 1200000 | 1624.9 | 1624.9 | Equitable | N/A | 1624.9 | 0 | 1625 | 100 | 1625 | 1625 | -0.1 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: No. Assessor remarks: The project is complete but poorly sited, structure not in use..
3798 | Construction Of An ECD Classroom At Chebuiyot | Construction Of An ECD Classroom At Chebuiyot | To construct An ECD Classroom At Chebuiyot | An ECD Classroom At Chebuiyot constructed | 4130299 | N/A | Kuresoi North | Kiptororo | -0.376802 35.529802 2495.7 15.600000381469727 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1499880 | 100 | 1499880 | 1000000 | 120 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The classroom is complete and in use.
3799 | Lemechonik ECD | Lemechonik ECD | To implement lemechonik ecd for access to quality education and training | Lemechonik ECD completed | 4130299 | N/A | Kuresoi North | Kiptororo | -0.35001 35.567448 2687.8 8.100000381469727 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2015/16 | 2015/16 | 2015/16 | 1495414 | 1495414 | 1495414 | Equitable | N/A | 1495414 | 0 | 1495414 | 100 | 1495414 | 1495414 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Renovations and painting of classrooms.
3800 | Lakeview ECD Classrooms Construction Of 4 ECD Classrooms | Lakeview ECD Classrooms Construction Of 4 ECD Classrooms | To implement lakeview ecd classrooms construction of 4 ecd classrooms for access to quality education and training | Lakeview ECD Classrooms Construction Of 4 ECD Classrooms completed | 4130299 | N/A | Naivasha | Lakeview | -0.734197, 36.435788 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2017/18 | 2017/18 | N/A | 5000000 | 1800284 | 1800284 | Equitable | N/A | 1800284 | 0 | 3199716 | 177.7 | 3199716 | 1800284 | -1399432 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3801 | Construction Of Perimeter Wall, Gate And Toilet At Ndege Polytechnic | Construction Of Perimeter Wall, Gate And Toilet At Ndege Polytechnic | To construct Perimeter Wall, Gate And Toilet At Ndege Polytechnic | Perimeter Wall, Gate And Toilet At Ndege Polytechnic constructed | 4130299 | N/A | Bahati | Lanet/Umoja | -0.302095, 36.172122 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2000000 | 1998040 | 1998040 | Equitable | N/A | 1998040 | 0 | 1998040 | 100 | 1998040 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3802 | Kamoronyo Primary ECDEs - Design And Construction Of 2No. ECDEs Classrooms At Kamoronyo Primary ECDEs | Kamoronyo Primary ECDEs - Design And Construction Of 2No. ECDEs Classrooms At Kamoronyo Primary ECDEs | To implement kamoronyo primary ecdes - design and construction of 2no. ecdes classrooms at kamoronyo primary ecdes for access to quality education and training | Kamoronyo Primary ECDEs - Design And Construction Of 2No. ECDEs Classrooms At Kamoronyo Primary ECDEs completed | 4130299 | N/A | Bahati | Lanet/Umoja | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2017/18 | 2017/18 | N/A | 2500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 1695002 | 339 | 1695002 | 500000 | -1195002 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
3803 | Ndege Ndimu Polytechnic - Design And Construction Of Of Ndege Ndimu Polytechnic | Ndege Ndimu Polytechnic - Design And Construction Of Of Ndege Ndimu Polytechnic | To implement ndege ndimu polytechnic - design and construction of of ndege ndimu polytechnic for access to quality education and training | Ndege Ndimu Polytechnic - Design And Construction Of Of Ndege Ndimu Polytechnic completed | 4130299 | N/A | Bahati | Lanet/Umoja | -0.299253, 36.17216 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 5500000 | 32853.2 | 32853.2 | Equitable | N/A | 32853.2 | 0 | 3163654 | 9629.7 | 3163654 | 32853 | -3130800.8 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3804 | ECDs Kapyemit | ECDs Kapyemit | To implement ecds kapyemit for access to quality education and training | ECDs Kapyemit completed | 4130299 | N/A | Njoro | Lare | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1199755 | 1127 | 1127 | Equitable | N/A | 1127 | 0 | 1127 | 100 | 1127 | 1127 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3805 | Mwenyere ECD | Mwenyere ECD | To implement mwenyere ecd for access to quality education and training | Mwenyere ECD completed | 4130299 | N/A | Njoro | Lare | -0.528065, 36.044693 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2017/18 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1198372 | 99.9 | 1198372 | 1200000 | 1628 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3806 | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Ereri ECD | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Ereri ECD | To construct 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Ereri ECD | 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Ereri ECD constructed | 4130299 | N/A | Naivasha | Maai Mahiu | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1200001 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1199672 | 100 | 1199672 | 1199240 | 328 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
3807 | Construction Of Toilets At Kipkonyo Polytechnics | Construction Of Toilets At Kipkonyo Polytechnics | To construct Toilets At Kipkonyo Polytechnics | Toilets At Kipkonyo Polytechnics constructed | 4130299 | N/A | Naivasha | Maiella | -0.781462, 36.223325 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2019 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 497700 | 99.5 | 497700 | 500000 | 2300 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Fabrica Building Construction.
3808 | Equipping Of Kipkonyo Polytechnics | Equipping Of Kipkonyo Polytechnics | To equip Kipkonyo Polytechnics with necessary facilities and equipment | Kipkonyo Polytechnics equipped | 4130299 | N/A | Naivasha | Maiella | -0.782163, 36.223265 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2019 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 2799119 | 279.9 | 2799119 | 1000000 | -1799119 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3809 | Equipping Of Ndabibi Polytechnics | Equipping Of Ndabibi Polytechnics | To equip Ndabibi Polytechnics with necessary facilities and equipment | Ndabibi Polytechnics equipped | 4130299 | N/A | Naivasha | Maiella | -0.782163, 36.223265 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2019 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 996500 | 99.7 | 996500 | 1000000 | 3500 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3810 | Ndabibi Polytechnic | Ndabibi Polytechnic | To implement ndabibi polytechnic for access to quality education and training | Ndabibi Polytechnic completed | 4130299 | N/A | Naivasha | Maiella | -0.892283 36.198894 2353.60009765625 10 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2015/16 | 2015/16 | 2015/16 | 1335596 | 1335596 | 1335596 | Equitable | N/A | 1335596 | 0 | 996500 | 74.6 | 996500 | 1335596 | 339096 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Damaged windows and floor.
3811 | Nkampani Nursery School | Nkampani Nursery School | To implement nkampani nursery school for access to quality education and training | Nkampani Nursery School completed | 4130299 | N/A | Naivasha | Maiella | -0.920628 36.204578 2270.4 7.5 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 2400000 | 2297135 | 2297135 | Equitable | N/A | 2297135 | 0 | 0 | 0 | 0 | 997135 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Fabrica Construction Co Ltd. Assessor remarks: Yet to be handed over.
3812 | Construction And Equipping Of Tuiyobei ECD Classrooms, Toilets And Water Tank | Construction And Equipping Of Tuiyobei ECD Classrooms, Toilets And Water Tank | To construct and equip Tuiyobei ECD Classrooms, Toilets And Water Tank | Tuiyobei ECD Classrooms, Toilets And Water Tank constructed and equipped | 4130299 | N/A | Molo | Mariashoni | -0.349579, 35.801559 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1914000 | 95.7 | 1914000 | 2000000 | 86000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes.
3813 | Construction Of 1 Kiplelmoi ECD Classrooms, Toilets, Purchase Of Equipments And Water Tank | Construction Of 1 Kiplelmoi ECD Classrooms, Toilets, Purchase Of Equipments And Water Tank | To construct 1 Kiplelmoi ECD Classrooms, Toilets, Purchase Of Equipments And Water Tank | 1 Kiplelmoi ECD Classrooms, Toilets, Purchase Of Equipments And Water Tank constructed | 4130299 | N/A | Molo | Mariashoni | -0.343994, 35.846228 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 499952 | 1999952 | Equitable | N/A | 1999952 | 0 | 1996707 | 399.4 | 1996707 | 1999952 | -1496755 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3814 | Construction Of ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Rombei ECDE | Construction Of ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Rombei ECDE | To construct ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Rombei ECDE | ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Rombei ECDE constructed | 4130299 | N/A | Molo | Mariashoni | -0.336003, 35.790239 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2000000 | 381278 | 381278 | Equitable | N/A | 381278 | 0 | 1996708 | 523.7 | 1996708 | 381278 | -1615430 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3815 | Constructon Of ECD Classroom At Gacembe Primary | Constructon Of ECD Classroom At Gacembe Primary | To implement constructon of ecd classroom at gacembe primary for access to quality education and training | Constructon Of ECD Classroom At Gacembe Primary completed | 4130299 | N/A | Njoro | Mau Narok | -0.674452, 35.969013 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1200000 | 1643 | 1643 | Equitable | N/A | 1643 | 0 | 1643 | 100 | 1643 | 1643 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3816 | Maji Mingi ECD | Maji Mingi ECD | To implement maji mingi ecd for access to quality education and training | Maji Mingi ECD completed | 4130299 | N/A | Njoro | Mau Narok | -0.624862 36.00766 2749.6 4.699999809265137 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2015/16 | 2015/16 | N/A | 1198002 | 790935 | 790935 | Equitable | N/A | 790935 | 0 | 0 | 0 | 0 | 790935 | 0 | Stalled | 25 | N/A | stalled and readvertised | 2015 | N/A | N/A | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: In bad condition.
3817 | Ngwataniro ECD | Ngwataniro ECD | To implement ngwataniro ecd for access to quality education and training | Ngwataniro ECD completed | 4130299 | N/A | Njoro | Mau Narok | -1.2841, 36.8155 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2015/16 | 2015/16 | 2020/21 | 1198002 | 1198002 | 1198002 | Equitable | N/A | 1198002 | 0 | 0 | 0 | 0 | 1198002 | 0 | Stalled | 25 | N/A | Stalled and readvertised | 2015 | N/A | N/A | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: yes. Viable: yes.
3818 | Construction Of 1 No ECD Classroom, Teachers Toilet, Pupils Toilet, Equipping And Watering Point At Chebitet ECDE | Construction Of 1 No ECD Classroom, Teachers Toilet, Pupils Toilet, Equipping And Watering Point At Chebitet ECDE | To construct 1 No ECD Classroom, Teachers Toilet, Pupils Toilet, Equipping And Watering Point At Chebitet ECDE | 1 No ECD Classroom, Teachers Toilet, Pupils Toilet, Equipping And Watering Point At Chebitet ECDE constructed | 4130299 | N/A | Njoro | Mauche | -0.558063 36.031755 2381.7999999999997 13.100000381469727 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 70 | 70 | Equitable | N/A | 70 | 0 | 70 | 100 | 70 | 70 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
3819 | Construction Of 1 No ECD Classroom, Teachers Toilet, Pupils Toilet, Equipping And Watering Point At Chemaluk ECDE | Construction Of 1 No ECD Classroom, Teachers Toilet, Pupils Toilet, Equipping And Watering Point At Chemaluk ECDE | To construct 1 No ECD Classroom, Teachers Toilet, Pupils Toilet, Equipping And Watering Point At Chemaluk ECDE | 1 No ECD Classroom, Teachers Toilet, Pupils Toilet, Equipping And Watering Point At Chemaluk ECDE constructed | 4130299 | N/A | Njoro | Mauche | -0.49448 35.97722 2413 13.399999618530273 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 567777 | 567777 | Equitable | N/A | 567777 | 0 | 70 | 0 | 70 | 567777 | 567707 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: No water tank & toilet for pupils & teachers & watering point needed.
3820 | Construction Of 1 No ECD Classroom, Teachers Toilet, Pupils Toilet, Equipping And Watering Point At Kamungei ECDE | Construction Of 1 No ECD Classroom, Teachers Toilet, Pupils Toilet, Equipping And Watering Point At Kamungei ECDE | To construct 1 No ECD Classroom, Teachers Toilet, Pupils Toilet, Equipping And Watering Point At Kamungei ECDE | 1 No ECD Classroom, Teachers Toilet, Pupils Toilet, Equipping And Watering Point At Kamungei ECDE constructed | 4130299 | N/A | Njoro | Mauche | -0.527288 35.981027 2478.8999999999996 15.399999618530273 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 4221 | 4221 | Equitable | N/A | 4221 | 0 | 70 | 1.7 | 70 | 4221 | 4151 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Don't know. Assessor remarks: Good.
3821 | Koilonget ECDE - Design And Construction Of 1 No ECD Classroom - Koilonget ECDE | Koilonget ECDE - Design And Construction Of 1 No ECD Classroom - Koilonget ECDE | To implement koilonget ecde - design and construction of 1 no ecd classroom - koilonget ecde for access to quality education and training | Koilonget ECDE - Design And Construction Of 1 No ECD Classroom - Koilonget ECDE completed | 4130299 | N/A | Njoro | Mauche | -0.481008 35.963225 2456.5 10 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 1200000 | 5542.2 | 5542.2 | Equitable | N/A | 5542.2 | 0 | 5542 | 100 | 5542 | 5542 | 0.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
3822 | Sigor ECDE | Sigor ECDE | To implement sigor ecde for access to quality education and training | Sigor ECDE completed | 4130299 | N/A | Njoro | Mauche | -0.547055 36.008958 2457 12.800000190734863 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2015/16 | 2015/16 | N/A | 1198002 | 1198002 | 1198002 | Equitable | N/A | 1198002 | 0 | 0 | 0 | 0 | 1198002 | 0 | Stalled | 25 | N/A | stalled and readvertised | 2015 | N/A | N/A | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: A fresh construction.
3823 | Construction Of 2. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Kiamungei ECD | Construction Of 2. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Kiamungei ECD | To construct 2. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Kiamungei ECD | 2. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Kiamungei ECD constructed | 4130299 | N/A | Rongai | Menengai West | -0.210933 36.023718 2043.9000244140625 5.300000190734863 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 2400000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 2399880 | 100 | 2399880 | 1144900 | 120 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
3824 | Olrongai Polytechnic - Design And Construction Of An Administration Block And Equipping | Olrongai Polytechnic - Design And Construction Of An Administration Block And Equipping | To implement olrongai polytechnic - design and construction of an administration block and equipping for access to quality education and training | Olrongai Polytechnic - Design And Construction Of An Administration Block And Equipping completed | 4130299 | N/A | Rongai | Menengai West | -0.168873, 36.000358 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2018 | 2500000 | 46335 | 46335 | Equitable | N/A | 46335 | 0 | 2453665 | 5295.5 | 2453665 | 46335 | -2407330 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
3825 | Construction Of Toilet At Ol-Rongai Polytechnic | Construction Of Toilet At Ol-Rongai Polytechnic | To construct Toilet At Ol-Rongai Polytechnic | Toilet At Ol-Rongai Polytechnic constructed | 4130299 | N/A | Rongai | Menengai West | -0.168652, 36.000173 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/2019 | 1000000 | 999240 | 999240 | Equitable | N/A | 999240 | 0 | 999240 | 100 | 999240 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3826 | Construction Of Kapcholola ECD Centre & Toilet | Construction Of Kapcholola ECD Centre & Toilet | To construct Kapcholola ECD Centre & Toilet | Kapcholola ECD Centre & Toilet constructed | 4130299 | N/A | Molo | Molo Central | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2014/15 | 2014/15 | 2014/15 | 1195000 | 1195000 | 1195000 | Equitable | N/A | 1195000 | 0 | 19900008 | 1665.3 | 19900008 | 3566331 | -18705008 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3827 | Construction Of Modern Toilets, Septic Tank, Completion Of Administration Block At Molo Polytechnic | Construction Of Modern Toilets, Septic Tank, Completion Of Administration Block At Molo Polytechnic | To construct Modern Toilets, Septic Tank, Completion Of Administration Block At Molo Polytechnic | Modern Toilets, Septic Tank, Completion Of Administration Block At Molo Polytechnic constructed | 4130299 | N/A | Molo | Molo Central | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 5318447.4 | 3695176.8 | 3695176.8 | Equitable | N/A | 3695176.8 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3828 | Baraka Youth Polytechnic | Baraka Youth Polytechnic | To implement baraka youth polytechnic for access to quality education and training | Baraka Youth Polytechnic completed | 4130299 | N/A | Rongai | Mosop | -0.213302 35.819547 1904.4000244140625 15.199999809265137 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | N/A | 1379950 | 1379950 | 1379950 | Equitable | N/A | 1379950 | 0 | 0 | 0 | 0 | 1379950 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: Good.
3829 | Chepseon ECD - Renovations And Toilets | Chepseon ECD - Renovations And Toilets | To implement chepseon ecd - renovations and toilets for access to quality education and training | Chepseon ECD - Renovations And Toilets completed | 4130299 | N/A | Rongai | Mosop | -0.265783 35.881283 2093.3 12.800000190734863 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2015/16 | 2015/16 | N/A | 1400000 | 1399853 | 1399853 | Equitable | N/A | 1399853 | 0 | 497999 | 35.6 | 497999 | 1400000 | 901854 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: It was viable. Contractor: Not awarded. Assessor remarks: Under procurement.
3830 | Construction And Equipping Of 1 Muthiga ECDE Classroom | Construction And Equipping Of 1 Muthiga ECDE Classroom | To construct and equip 1 Muthiga ECDE Classroom | 1 Muthiga ECDE Classroom constructed and equipped | 4130299 | N/A | Rongai | Mosop | -0.279457 35.88394 2110.2 6.099999904632568 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1400000 | 1198000 | 1198000 | Equitable | N/A | 1198000 | 0 | 1198000 | 100 | 1198000 | 1400000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Contractor: Not indicated. Assessor remarks: Good.
3831 | Design And Construction Of 3 No Classrooms At Ogilgei Polytechnic | Design And Construction Of 3 No Classrooms At Ogilgei Polytechnic | To design and construct 3 No Classrooms At Ogilgei Polytechnic | 3 No Classrooms At Ogilgei Polytechnic designed and constructed | 4130299 | N/A | Rongai | Mosop | -0.211275 35.852425 1887.3999999999999 15.899999618530273 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 3400000 | 968873 | 968873 | Equitable | N/A | 968873 | 0 | 1499996 | 154.8 | 1499996 | 968873 | -531123 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Viable. Contractor: Not indicated. Assessor remarks: Stalled.
3832 | Construction Of 1 No. ECD Classroom, Teachers Toilet, Pupils Toilet And Watering Point At Chemichemi Primary School ECD | Construction Of 1 No. ECD Classroom, Teachers Toilet, Pupils Toilet And Watering Point At Chemichemi Primary School ECD | To construct 1 No. ECD Classroom, Teachers Toilet, Pupils Toilet And Watering Point At Chemichemi Primary School ECD | 1 No. ECD Classroom, Teachers Toilet, Pupils Toilet And Watering Point At Chemichemi Primary School ECD constructed | 4130299 | N/A | Gilgil | Murindat | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1000000 | 100 | 1000000 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3833 | Equipping Of Mbegi Polytechnic | Equipping Of Mbegi Polytechnic | To equip Mbegi Polytechnic with necessary facilities and equipment | Mbegi Polytechnic equipped | 4130299 | N/A | Gilgil | Murindat | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1000000 | 2830 | 2830 | Equitable | N/A | 2830 | 0 | 2830 | 100 | 2830 | 2830 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3834 | Wanguhu ECDE Classroom - Design And Construction Of Wanguhu ECDE 1 Classroom | Wanguhu ECDE Classroom - Design And Construction Of Wanguhu ECDE 1 Classroom | To implement wanguhu ecde classroom - design and construction of wanguhu ecde 1 classroom for access to quality education and training | Wanguhu ECDE Classroom - Design And Construction Of Wanguhu ECDE 1 Classroom completed | 4130299 | N/A | Gilgil | Murindat | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1210000 | 80.7 | 1210000 | 290000 | 290000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3835 | Construction Of 2 ECD Classroom And Purchase Of Tank At Kigogo ECD And Shoka ECD | Construction Of 2 ECD Classroom And Purchase Of Tank At Kigogo ECD And Shoka ECD | To construct 2 ECD Classroom And Purchase Of Tank At Kigogo ECD And Shoka ECD | 2 ECD Classroom And Purchase Of Tank At Kigogo ECD And Shoka ECD constructed | 4130299 | N/A | Gilgil | Murindat | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 2400000 | 112 | 112 | Equitable | N/A | 112 | 0 | 112 | 100 | 112 | 112 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3836 | Construction Of Kinungi Primary School ECDE | Construction Of Kinungi Primary School ECDE | To construct Kinungi Primary School ECDE | Kinungi Primary School ECDE constructed | 4130299 | N/A | Naivasha | Naivasha East | -0.807496, 36.52903 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018-19 | 999352 | 999352 | 999352 | Equitable | N/A | 999352 | 0 | 999352 | 100 | 999352 | 999352 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes.
3837 | Construction Of Mwega Polytechnic | Construction Of Mwega Polytechnic | To construct Mwega Polytechnic | Mwega Polytechnic constructed | 4130299 | N/A | Naivasha | Naivasha East | -0.790247, 36.546362 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2020 | 3000000 | 936 | 936 | Equitable | N/A | 936 | 0 | 936 | 100 | 936 | 936 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: No.
3838 | Construction And Equipping Of Mwega Polytechnic | Construction And Equipping Of Mwega Polytechnic | To construct and equip Mwega Polytechnic | Mwega Polytechnic constructed and equipped | 4130299 | N/A | Naivasha | Naivasha East | -0.826406 36.536507 2471.60009765625 5.800000190734863 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2999064 | 100 | 2999064 | 3000000 | 936 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes. Assessor remarks: Project was not done.
3839 | Naivasha East Ward ECDs - Design And Construction Of 2 No ECD Classroom, At Nyakairu And Mweega Primary | Naivasha East Ward ECDs - Design And Construction Of 2 No ECD Classroom, At Nyakairu And Mweega Primary | To implement naivasha east ward ecds - design and construction of 2 no ecd classroom, at nyakairu and mweega primary for access to quality education and training | Naivasha East Ward ECDs - Design And Construction Of 2 No ECD Classroom, At Nyakairu And Mweega Primary completed | 4130299 | N/A | Naivasha | Naivasha East | -0.782198, 36.533643 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2017/18 | 2017/18 | Not done | 2400000 | 4260 | 4260 | Equitable | N/A | 4260 | 0 | 4260 | 100 | 4260 | 4260 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No.
3840 | Nginye ECD | Nginye ECD | To implement nginye ecd for access to quality education and training | Nginye ECD completed | 4130299 | N/A | Njoro | Nessuit | -0.401883 35.907934 2429.297805547889 4.23799991607666 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2015/16 | 2015/16 | N/A | 1198002 | 790935 | 790935 | Equitable | N/A | 790935 | 0 | 0 | 0 | 0 | 790935 | 0 | Stalled | 25 | N/A | stalled and readvertised | 2015 | N/A | N/A | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Classroom was constructed till the lintel stage and stalled, community members then demolished the structure. Another allocation of funds was done to redo the work.
3841 | Tiritagoi ECD - Construction Of 1 Classroom | Tiritagoi ECD - Construction Of 1 Classroom | To implement tiritagoi ecd - construction of 1 classroom for access to quality education and training | Tiritagoi ECD - Construction Of 1 Classroom completed | 4130299 | N/A | Njoro | Nessuit | -0.417516 35.906162 2476.5755676023055 30 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2017/18 | 2017/18 | N/A | 1300000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 1199431 | 92.3 | 1199431 | 1300000 | 100569 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: Yes. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The classroom is being used but not finished yet. The classroom environment is injurious to the pupils.
3842 | Design And Construction Of Korovio ECDE Classroom | Design And Construction Of Korovio ECDE Classroom | To design and construct Korovio ECDE Classroom | Korovio ECDE Classroom designed and constructed | 4130299 | N/A | Njoro | Nessuit | -0.410761 35.899338 2463.547607421875 10.36299991607666 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1200000 | 1105445 | 1105445 | Equitable | N/A | 1105445 | 0 | 1199431 | 108.5 | 1199431 | 1105445 | -93986 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The contractor has never completed the project and is evasive. The ECDE started as a stand alone and after the primary school coming up it used a different name, therefore reconciliation of the school and ECDE name should done. Currently there pupils are using a temporary structure which was constructed by funds from parents..
3843 | Design And Construction Of Masaita ECDE Classroom And Toilets | Design And Construction Of Masaita ECDE Classroom And Toilets | To design and construct Masaita ECDE Classroom And Toilets | Masaita ECDE Classroom And Toilets designed and constructed | 4130299 | N/A | Njoro | Nessuit | -0.356677 35.883444 2389.259997959072 5.46999979019165 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1500000 | 1105445 | 1105445 | Equitable | N/A | 1105445 | 0 | 1199431 | 108.5 | 1199431 | 1105445 | -93986 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: MARKVEC ENT LIMITED. Assessor remarks: Poor workmanship and there is no latrine constructed.
3844 | Design And Construction Of Missipei ECDE Classroom And Toilets | Design And Construction Of Missipei ECDE Classroom And Toilets | To design and construct Missipei ECDE Classroom And Toilets | Missipei ECDE Classroom And Toilets designed and constructed | 4130299 | N/A | Njoro | Nessuit | -0.375545 35.875101 2486.6005859375 3.7899999618530273 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 1500000 | 1105445 | 1105445 | Equitable | N/A | 1105445 | 0 | 1199431 | 108.5 | 1199431 | 1105445 | -93986 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Construction incomplete, no toilets constructed as per the description.
3845 | ECD Tengecha | ECD Tengecha | To implement ecd tengecha for access to quality education and training | ECD Tengecha completed | 4130299 | N/A | Njoro | Njoro | -0.369383 35.901138 1512.2 77.69999694824219 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1799960.4 | 1799960 | 1799960 | Equitable | N/A | 1799960 | 0 | 0 | 0 | 0 | 1799960 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Contractor: na. Assessor remarks: working well.
3846 | Njokerio ECD - Construction Of Toilet And Equiping | Njokerio ECD - Construction Of Toilet And Equiping | To implement njokerio ecd - construction of toilet and equiping for access to quality education and training | Njokerio ECD - Construction Of Toilet And Equiping completed | 4130299 | N/A | Njoro | Njoro | -0.384924, 35.935535 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2019 | 1800000 | 110660 | 110660 | Equitable | N/A | 110660 | 0 | 110660 | 100 | 110660 | 110660 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not available.
3847 | Construction Of Toilets, Fencing, Connecting Electricity And Purchase Of Equipments At Sitoito Polytechnic | Construction Of Toilets, Fencing, Connecting Electricity And Purchase Of Equipments At Sitoito Polytechnic | To construct Toilets, Fencing, Connecting Electricity And Purchase Of Equipments At Sitoito Polytechnic | Toilets, Fencing, Connecting Electricity And Purchase Of Equipments At Sitoito Polytechnic constructed | 4130299 | N/A | Kuresoi North | Nyota | -0.38946, 35.568755 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2015-2016 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes, if it's operationalized.
3848 | Langwenda Youth Polytechnic | Langwenda Youth Polytechnic | To implement langwenda youth polytechnic for access to quality education and training | Langwenda Youth Polytechnic completed | 4130299 | N/A | Kuresoi North | Nyota | -0.30101, 35.590975 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | _ | 2000000 | 800200 | 800200 | Equitable | N/A | 800200 | 0 | 689140 | 86.1 | 689140 | 800200 | 111060 | Vired | 25 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: YES. Viable: YES. Contractor: _.
3849 | Mworoto Youth Polytechnic | Mworoto Youth Polytechnic | To implement mworoto youth polytechnic for access to quality education and training | Mworoto Youth Polytechnic completed | 4130299 | N/A | Kuresoi North | Nyota | -0.30101, 35.590975 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | _ | 2000000 | 689140 | 689140 | Equitable | N/A | 689140 | 0 | 689140 | 100 | 689140 | 1374262 | 0 | Vired | 25 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: YES. Viable: YES. Contractor: _.
3850 | Nyota Ward ECDs - Design And Construction Of 1.No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Chemorut, Mawingu, Masasita | Nyota Ward ECDs - Design And Construction Of 1.No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Chemorut, Mawingu, Masasita | To implement nyota ward ecds - design and construction of 1.no ecd classrooms, teachers toilet, pupils toilet and watering point at chemorut, mawingu, masasita for access to quality education and training | Nyota Ward ECDs - Design And Construction Of 1.No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Chemorut, Mawingu, Masasita completed | 4130299 | N/A | Kuresoi North | Nyota | -0.3756, 35.726818 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2018-2019 | 4800000 | 800002 | 800002 | Equitable | N/A | 800002 | 0 | 1199999 | 150 | 1199999 | 800002 | -399997 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/S WESJOY GENERAL SUPPLIES..
3851 | Construction Of Olemayana Kubwa ECDE Class, Toilet Blocks And Equipping | Construction Of Olemayana Kubwa ECDE Class, Toilet Blocks And Equipping | To construct Olemayana Kubwa ECDE Class, Toilet Blocks And Equipping | Olemayana Kubwa ECDE Class, Toilet Blocks And Equipping constructed | 4130299 | N/A | Naivasha | Olkaria | -0.914466, 36.304362 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1195717 | 2491717 | 2491717 | Equitable | N/A | 2491717 | 0 | 2206597 | 88.6 | 2206597 | 285120 | 285120 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3852 | Mvuke ECD | Mvuke ECD | To implement mvuke ecd for access to quality education and training | Mvuke ECD completed | 4130299 | N/A | Naivasha | Olkaria | -0.836328 36.366422 1881.9000244140625 10.300000190734863 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1197887.77 | 1197888 | 1197888 | Equitable | N/A | 1197888 | 0 | 1151760 | 96.1 | 1151760 | 46128 | 46128 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No because it is not in use. Viable: Yes but doesn't meet the need of the residents. Assessor remarks: The class is complete but in a devastated state.
3853 | Olkaria Ward ECDE Classroom Refurbishments - Refurbishments Of Olkaria ECDEs At Narasha, Mvuke, Oserian, Maua, Sher Primary | Olkaria Ward ECDE Classroom Refurbishments - Refurbishments Of Olkaria ECDEs At Narasha, Mvuke, Oserian, Maua, Sher Primary | To implement olkaria ward ecde classroom refurbishments - refurbishments of olkaria ecdes at narasha, mvuke, oserian, maua, sher primary for access to quality education and training | Olkaria Ward ECDE Classroom Refurbishments - Refurbishments Of Olkaria ECDEs At Narasha, Mvuke, Oserian, Maua, Sher Primary completed | 4130299 | N/A | Naivasha | Olkaria | -0.836891 36.366302 1881.9000244140625 12.005999565124512 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 2000000 | 192163 | 192163 | Equitable | N/A | 192163 | 0 | 192163 | 100 | 192163 | 192163 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No not done. Assessor remarks: At sher moi not done.
3854 | Design And Construction Of Administration Block, Polytechnic, And Equipping Of Classrooms At Rhonda Resource Centre | Design And Construction Of Administration Block, Polytechnic, And Equipping Of Classrooms At Rhonda Resource Centre | To design and construct Administration Block, Polytechnic, And Equipping Of Classrooms At Rhonda Resource Centre | Administration Block, Polytechnic, And Equipping Of Classrooms At Rhonda Resource Centre designed and constructed | 4130299 | N/A | Nakuru West | Rhonda | -0.31321, 36.069056 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 16/17 | 7000000 | 9139 | 9139 | Equitable | N/A | 9139 | 0 | 9139 | 100 | 9139 | 9139 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/s Glazers General Supplies and Construction.
3855 | Completion and construction of Rhonda Vocational Centre | Completion and construction of Rhonda Vocational Centre | To complete and construction of Rhonda Vocational Centre | And construction of Rhonda Vocational Centre completed | 4130299 | N/A | Nakuru West | Rhonda | -0.314169, 36.067382 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2019/20 | 2019/20 | 2024 | 6000000 | 0 | 6000000 | Equitable | N/A | 6000000 | 0 | 0 | 0 | 0 | 6000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes.
3856 | Construction Of An ECD Classroom, Toilet And Tank At Mwariki Primary ECD | Construction Of An ECD Classroom, Toilet And Tank At Mwariki Primary ECD | To construct An ECD Classroom, Toilet And Tank At Mwariki Primary ECD | An ECD Classroom, Toilet And Tank At Mwariki Primary ECD constructed | 4130299 | N/A | Nakuru West | Rhonda | -0.752322, 36.527363 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 2000000 | 1996930 | 1996930 | Equitable | N/A | 1996930 | 0 | 1996330 | 100 | 1996330 | 2000000 | 600 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes.
3857 | Baringo ECD | Baringo ECD | To implement baringo ecd for access to quality education and training | Baringo ECD completed | 4130299 | N/A | Kuresoi North | Sirikwa | -0.289637 35.642573 2687.6 9.300000190734863 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1199442 | 73625 | 73625 | Equitable | N/A | 73625 | 0 | 407000 | 552.8 | 407000 | 73625 | -333375 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is complete and in use, however the school needs another classroom to accommodate pp1 and pp2. The roof needs repair as its leaking, blackboard needs repainting, it also electricity, gutters and tank for water collection needed, they also require a pit latrine, seats and tables needs maintenance.
3858 | Completion Of Upendo ECD, Kadenye ECD, And Ngenia ECD | Completion Of Upendo ECD, Kadenye ECD, And Ngenia ECD | To complete Upendo ECD, Kadenye ECD, And Ngenia ECD | Upendo ECD, Kadenye ECD, And Ngenia ECD completed | 4130299 | N/A | Kuresoi North | Sirikwa | -0.289225 35.684677 2731.4 4.699999809265137 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 28737 | 28737 | Equitable | N/A | 28737 | 0 | 28737 | 100 | 28737 | 28737 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is good and in use, however the ceiling needs some repairs, one classroom doesn't have ceiling.
3859 | Construction Of ECD Classrooms At Kiletten | Construction Of ECD Classrooms At Kiletten | To construct ECD Classrooms At Kiletten | ECD Classrooms At Kiletten constructed | 4130299 | N/A | Kuresoi North | Sirikwa | -0.235118, 35.662517 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1200000 | 402691 | 402691 | Equitable | N/A | 402691 | 0 | 402405 | 99.9 | 402405 | 402691 | 286 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3860 | Construction Of 2 No Classrooms And Equpping Of Majani Mingi Polytechnic | Construction Of 2 No Classrooms And Equpping Of Majani Mingi Polytechnic | To construct 2 No Classrooms And Equpping Of Majani Mingi Polytechnic | 2 No Classrooms And Equpping Of Majani Mingi Polytechnic constructed | 4130299 | N/A | Rongai | Soin | -0.041969 36.024345 1647 8 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 3999796 | 116000 | 116000 | Equitable | N/A | 116000 | 0 | 2230341 | 1922.7 | 2230341 | 116000 | -2114341 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: Yes but needs not met. Assessor remarks: Equipment transferred to Kipsyenan Polytechnic because Majani Mingi Polytechnic is hosting Athinai IDPs.
3861 | Kipsyenan Polytechnic - Design And Construction Of 2 No. Classrooms | Kipsyenan Polytechnic - Design And Construction Of 2 No. Classrooms | To implement kipsyenan polytechnic - design and construction of 2 no. classrooms for access to quality education and training | Kipsyenan Polytechnic - Design And Construction Of 2 No. Classrooms completed | 4130299 | N/A | Rongai | Soin | -0.061705 36.062868 1618.2 9.399999618530273 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 2400000 | 539.6 | 539.6 | Equitable | N/A | 539.6 | 0 | 540 | 100.1 | 540 | 540 | -0.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The class needs repairs, installation Terrazo,furniture's,ECDE Toilet, Electricity installation,Purchase of outdoor equipments and painting.
3862 | Chemachei ECD | Chemachei ECD | To implement chemachei ecd for access to quality education and training | Chemachei ECD completed | 4130299 | N/A | Rongai | Solai | -0.005736, 36.138072 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016 | 1799299.6 | 1799300 | 1799300 | Equitable | N/A | 1799300 | 0 | 699162 | 38.9 | 699162 | 1799300 | 1100138 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes.
3863 | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Kapkaturu ECD | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Kapkaturu ECD | To construct 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Kapkaturu ECD | 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Kapkaturu ECD constructed | 4130299 | N/A | Rongai | Solai | -0.025981 36.130112 1649.16064453125 25.464000701904297 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 102253 | 5.7 | 102253 | 1800000 | 1697747 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
3864 | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Tuiyomoi ECD | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Tuiyomoi ECD | To construct 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Tuiyomoi ECD | 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Tuiyomoi ECD constructed | 4130299 | N/A | Rongai | Solai | 0.099233, 36.173895 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2015 | 1200000 | 436569 | 436569 | Equitable | N/A | 436569 | 0 | 102253 | 23.4 | 102253 | 436569 | 334316 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
3865 | Kapndege ECD | Kapndege ECD | To implement kapndege ecd for access to quality education and training | Kapndege ECD completed | 4130299 | N/A | Rongai | Solai | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1799229.6 | 1799230 | 1799230 | Equitable | N/A | 1799230 | 0 | 699162 | 38.9 | 699162 | 1799230 | 1100068 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
3866 | Mahinga ECD | Mahinga ECD | To implement mahinga ecd for access to quality education and training | Mahinga ECD completed | 4130299 | N/A | Rongai | Solai | 0.023445, 36.146794 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2022 | 1799542.8 | 1100380.85 | 1100380.85 | Equitable | N/A | 1100380.85 | 0 | 699162 | 63.5 | 699162 | 1100381 | 401218.85 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3867 | Sigito ECD | Sigito ECD | To implement sigito ecd for access to quality education and training | Sigito ECD completed | 4130299 | N/A | Rongai | Solai | 0.078648 36.19437 1940.5 6 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1799229.6 | 1799230 | 1799230 | Equitable | N/A | 1799230 | 0 | 699162 | 38.9 | 699162 | 1799230 | 1100068 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Solo m general enterprise. Assessor remarks: Good.
3868 | Arash Primary School-ECD - Design And Construction Of 2 No. ECD Classroom | Arash Primary School-ECD - Design And Construction Of 2 No. ECD Classroom | To implement arash primary school-ecd - design and construction of 2 no. ecd classroom for access to quality education and training | Arash Primary School-ECD - Design And Construction Of 2 No. ECD Classroom completed | 4130299 | N/A | Subukia | Subukia | -0.016571, 36.209792 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 13/01/2018 | 2400000 | 406000 | 406000 | Equitable | N/A | 406000 | 0 | 1994000 | 491.1 | 1994000 | 406000 | -1588000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes.. Viable: Yes. The class is in a good state.. Contractor: Information not available.
3869 | Aon ECD | Aon ECD | To implement aon ecd for access to quality education and training | Aon ECD completed | 4130299 | N/A | Kuresoi South | Tinet | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2015/16 | 2015/16 | N/A | 1190844.4 | 1190844 | 1190844 | Equitable | N/A | 1190844 | 0 | 1190844 | 100 | 1190844 | 1190844 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
3870 | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Ang'Urwet ECD | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Ang'Urwet ECD | To construct 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Ang'Urwet ECD | 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Ang'Urwet ECD constructed | 4130299 | N/A | Kuresoi South | Tinet | -0.544292 35.677364 0 2400 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 296998 | 296998 | Equitable | N/A | 296998 | 0 | 296992 | 100 | 296992 | 296998 | 6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
3871 | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Cherokiet ECD | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Cherokiet ECD | To construct 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Cherokiet ECD | 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Cherokiet ECD constructed | 4130299 | N/A | Kuresoi South | Tinet | -0.544292 35.677364 0 2400 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1199220 | 1199220 | Equitable | N/A | 1199220 | 0 | 1199220 | 100 | 1199220 | 1200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
3872 | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Kaprengero ECD | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Kaprengero ECD | To construct 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Kaprengero ECD | 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Kaprengero ECD constructed | 4130299 | N/A | Kuresoi South | Tinet | -0.544292 35.677364 0 2400 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1186982 | 1186982 | Equitable | N/A | 1186982 | 0 | 1186982 | 100 | 1186982 | 1200000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
3873 | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Lelechwet ECD | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Lelechwet ECD | To construct 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Lelechwet ECD | 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Lelechwet ECD constructed | 4130299 | N/A | Kuresoi South | Tinet | -0.544292 35.677364 0 2400 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 803564.2 | 803564.2 | Equitable | N/A | 803564.2 | 0 | 803509 | 100 | 803509 | 803564 | 55.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
3874 | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Ngenda ECD | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Ngenda ECD | To construct 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Ngenda ECD | 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Ngenda ECD constructed | 4130299 | N/A | Kuresoi South | Tinet | -0.544292 35.677364 0 2400 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1999950 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 800000 | 100 | 800000 | 800000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good condition.
3875 | Construction Of 2 No ECD Classrooms At Kimomoroch | Construction Of 2 No ECD Classrooms At Kimomoroch | To construct 2 No ECD Classrooms At Kimomoroch | 2 No ECD Classrooms At Kimomoroch constructed | 4130299 | N/A | Kuresoi South | Tinet | -0.558447, 35.616554 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1269806.15 | 1269806 | 1269806 | Equitable | N/A | 1269806 | 0 | 1151750 | 90.7 | 1151750 | 1269806 | 118056 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3876 | Finishing Of 2. No ECD Classrooms At Kipleljin ECD | Finishing Of 2. No ECD Classrooms At Kipleljin ECD | To implement finishing of 2. no ecd classrooms at kipleljin ecd for access to quality education and training | Finishing Of 2. No ECD Classrooms At Kipleljin ECD completed | 4130299 | N/A | Kuresoi South | Tinet | -0.509537 35.634567 2510.2 5.699999809265137 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 998516.4 | 998516 | 998516 | Equitable | N/A | 998516 | 0 | 1199930 | 120.2 | 1199930 | 998516 | -201414 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Completed and operational.
3877 | Tinet Ward ECDs -Construction Of 1 ECD Classroom At Buchechet, Cheram, Kipsirat, Rwaget, Maluo, Kapnanda, Kamwaura And Kapnandi. | Tinet Ward ECDs -Construction Of 1 ECD Classroom At Buchechet, Cheram, Kipsirat, Rwaget, Maluo, Kapnanda, Kamwaura And Kapnandi. | To implement tinet ward ecds -construction of 1 ecd classroom at buchechet, cheram, kipsirat, rwaget, maluo, kapnanda, kamwaura and kapnandi. for access to quality education and training | Tinet Ward ECDs -Construction Of 1 ECD Classroom At Buchechet, Cheram, Kipsirat, Rwaget, Maluo, Kapnanda, Kamwaura And Kapnandi. completed | 4130299 | N/A | Kuresoi South | Tinet | -0.513813 35.683561 2568.666 3.1989998817443848 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 8400000 | 878968 | 878968 | Equitable | N/A | 878968 | 0 | 519503 | 59.1 | 519503 | 359465 | 359465 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: No. Assessor remarks: Never started.
3878 | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Mwangaza Primary ECD | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Mwangaza Primary ECD | To construct 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Mwangaza Primary ECD | 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Mwangaza Primary ECD constructed | 4130299 | N/A | Molo | Turi | -0.248077 35.730962 2517.6 200 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1199996.8 | 1199997 | 1199997 | Equitable | N/A | 1199997 | 0 | 1199994 | 100 | 1199994 | 1199997 | 3 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: There is no water tank at the facility. The ECD toilets are used by other students and has no toilets.
3879 | Migaa ECD | Migaa ECD | To implement migaa ecd for access to quality education and training | Migaa ECD completed | 4130299 | N/A | Molo | Turi | -0.273188 35.732858 2517.6 18 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2014/15 | 2014/15 | 2014/15 | 1186662.6 | 30 | 30 | Equitable | N/A | 30 | 0 | 30 | 100 | 30 | 30 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: The classroom is in dilapidated condition..
3880 | Mitoni ECD | Mitoni ECD | To implement mitoni ecd for access to quality education and training | Mitoni ECD completed | 4130299 | N/A | Molo | Turi | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1195612 | 1195612 | 1195612 | Equitable | N/A | 1195612 | 0 | 1194630 | 99.9 | 1194630 | 982 | 982 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3881 | Construction Of ECD Classrooms At Mwangaza, Chesengele And Gathigi Primary School | Construction Of ECD Classrooms At Mwangaza, Chesengele And Gathigi Primary School | To construct ECD Classrooms At Mwangaza, Chesengele And Gathigi Primary School | ECD Classrooms At Mwangaza, Chesengele And Gathigi Primary School constructed | 4130299 | N/A | Molo | Turi | -0.32942 35.686729 2755.300048828125 96.13099670410156 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 2400000 | 1200006 | 1200006 | Equitable | N/A | 1200006 | 0 | 1199994 | 100 | 1199994 | 1200006 | 12 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The classroom is under the Chesingele, Gathigi and Mwangaza ECDs.
3882 | Construction Of Toilet And Tank At Ndenderu B ECD And Construction Of Toilets At Ngwataniro And Ndenderu A ECD | Construction Of Toilet And Tank At Ndenderu B ECD And Construction Of Toilets At Ngwataniro And Ndenderu A ECD | To construct Toilet And Tank At Ndenderu B ECD And Construction Of Toilets At Ngwataniro And Ndenderu A ECD | Toilet And Tank At Ndenderu B ECD And Construction Of Toilets At Ngwataniro And Ndenderu A ECD constructed | 4130299 | N/A | Molo | Turi | -0.319855 35.739007 2667.3 8.600000381469727 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1100000 | 4229 | 4229 | Equitable | N/A | 4229 | 0 | 4229 | 100 | 4229 | 4229 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Has been painted afresh.
3883 | Renovation Of Existing ECD Classroom At Rafiki ECD | Renovation Of Existing ECD Classroom At Rafiki ECD | To rehabilitate Existing ECD Classroom At Rafiki ECD to restore functionality | Existing ECD Classroom At Rafiki ECD rehabilitated | 4130299 | N/A | Molo | Turi | -0.303263 35.728955 2630.6 8.5 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | N/A | 200000 | 199960 | 199960 | Equitable | N/A | 199960 | 0 | 1199940 | 600.1 | 1199940 | 199960 | -999980 | Vired | 90 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Completed. The compound needs fencing.
3884 | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Kanga ECD | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Kanga ECD | To construct 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Kanga ECD | 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Kanga ECD constructed | 4130299 | N/A | Rongai | Visoi | -0.119997 35.933422 1746.5999755859375 6.900000095367432 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1155310 | 96.3 | 1155310 | 1200000 | 44690 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Merlins keys enterprises. Assessor remarks: Good.
3885 | Lengenet ECD | Lengenet ECD | To implement lengenet ecd for access to quality education and training | Lengenet ECD completed | 4130299 | N/A | Rongai | Visoi | -0.136537, 35.896727 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2015/16 | 2015/16 | 2016/17 | 1183447.66 | 547290 | 547290 | Equitable | N/A | 547290 | 0 | 547290 | 100 | 547290 | 547290 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Menengai TUMAINI 4.
3886 | Naiswet ECDE -Construction Of Toilets | Naiswet ECDE -Construction Of Toilets | To implement naiswet ecde -construction of toilets for access to quality education and training | Naiswet ECDE -Construction Of Toilets completed | 4130299 | N/A | Rongai | Visoi | -0.119997 35.932339 1710.7 13.199999809265137 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2017/18 | 2017/18 | 2017/18 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 599592 | 99.9 | 599592 | 600000 | 408 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
3887 | Shalom ECD | Shalom ECD | To implement shalom ecd for access to quality education and training | Shalom ECD completed | 4130299 | N/A | Rongai | Visoi | -0.13549 35.794188 2186.6000000000004 22 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1160093.96 | 1160094 | 1160094 | Equitable | N/A | 1160094 | 0 | 178052 | 15.3 | 178052 | 1160094 | 982042 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Poor because no county project.
3888 | Construction Of A Classroom At Kipsaos ECD | Construction Of A Classroom At Kipsaos ECD | To construct A Classroom At Kipsaos ECD | A Classroom At Kipsaos ECD constructed | 4130299 | N/A | Rongai | Visoi | -0.101903, 35.857515 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2019/20 | 2019/20 | 1200000 | 1169247 | 1169247 | Equitable | N/A | 1169247 | 0 | 1155310 | 98.8 | 1155310 | 1200000 | 13937 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3889 | Central Pry Viwandani | Central Pry Viwandani | To implement central pry viwandani for access to quality education and training | Central Pry Viwandani completed | 4130299 | N/A | Naivasha | Viwandani | -0.710843 36.433726 1903.699951171875 7.052999973297119 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 77.44 | 77.44 | Equitable | N/A | 77.44 | 0 | 77 | 99.4 | 77 | 77 | 0.44 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Assessor remarks: Standard.
3890 | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Gatagati ECD | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Gatagati ECD | To construct 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Gatagati ECD | 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Gatagati ECD constructed | 4130299 | N/A | Subukia | Waseges | 0.168615 36.250903 1712.4 9 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1200000 | 798025.2 | 798025.2 | Equitable | N/A | 798025.2 | 0 | 401975 | 50.4 | 401975 | 798025 | 396050.2 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Teacher Toilet and Pupils Not Constructed.
3891 | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Loremeta ECD | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Loremeta ECD | To construct 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Loremeta ECD | 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Loremeta ECD constructed | 4130299 | N/A | Subukia | Waseges | 0.098807 36.2446 1851.5 13.199999809265137 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1200000 | 283577 | 283577 | Equitable | N/A | 283577 | 0 | 916423 | 323.2 | 916423 | 283577 | -632846 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs maintenance.
3892 | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Mikima ECD | Construction Of 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Mikima ECD | To construct 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Mikima ECD | 1. No ECD Classrooms, Teachers Toilet, Pupils Toilet And Watering Point At Mikima ECD constructed | 4130299 | N/A | Subukia | Waseges | 0.09978 36.263945 1824.8 12 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | N/A | 1200000 | 137 | 137 | Equitable | N/A | 137 | 0 | 137 | 100 | 137 | 137 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Equipping and maintenance.
3893 | Construction Of 2 Classroom At Kaptarakwa Nairobi Area ECDE And Kiriko ECDs | Construction Of 2 Classroom At Kaptarakwa Nairobi Area ECDE And Kiriko ECDs | To construct 2 Classroom At Kaptarakwa Nairobi Area ECDE And Kiriko ECDs | 2 Classroom At Kaptarakwa Nairobi Area ECDE And Kiriko ECDs constructed | 4130299 | N/A | Subukia | Waseges | 0.08177, 36.226511 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 2400000 | 35495.75 | 35495.75 | Equitable | N/A | 35495.75 | 0 | 2364444 | 6661.2 | 2364444 | 35496 | -2328948.25 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3894 | Equipping Of Gakingi Polytechnic | Equipping Of Gakingi Polytechnic | To equip Gakingi Polytechnic with necessary facilities and equipment | Gakingi Polytechnic equipped | 4130299 | N/A | Subukia | Waseges | 0.116708, 36.224264 | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2018/19 | 2018/19 | 2018/19 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 910200 | 91 | 910200 | 89800 | 89800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: No. Viable: Yes.
3895 | Gitudaga ECDEs | Gitudaga ECDEs | To implement gitudaga ecdes for access to quality education and training | Gitudaga ECDEs completed | 4130299 | N/A | Subukia | Waseges | N/A | 4575 | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | EDUCATION, VOCATIONAL TRAINING, ICT AND E-GOVERNMENT | N/A | 2016/17 | 2016/17 | 2016/17 | 1149769.96 | 1149770 | 1149770 | Equitable | N/A | 1149770 | 0 | 0 | 0 | 0 | 1149770 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
3896 | Administration, Planning and Support Services | Youth Outstanding Contract Retention - development | To implement youth outstanding contract retention - development for youth empowerment and social inclusion | Youth Outstanding Contract Retention - development completed | 2211314 | Write Offs/ Bad Debt Expenses from Previous Years (Pending Bills) | HQ | HQ | N/A | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2022/23 | 2022/23 | N/A | 396311.68 | 396311.68 | 396311.68 | N/A | - | 396311.68 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
3897 | Administration, Planning and Support Services | Construction of Karuchua multi purpose hall | To construct Karuchua multi purpose hall | Karuchua multi purpose hall constructed | 3110299 | Construction of Buildings - Ot | Bahati | Dundori | -0.262328, 36.187226 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2021/22 | 2021/22 | 2023/2024 | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 58 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Silent enterprise.
3898 | Administration, Planning and Support Services | Construction of Karuchua Multipurpose Hall | To construct Karuchua Multipurpose Hall | Karuchua Multipurpose Hall constructed | 3110299 | Construction of Buildings - Ot | Bahati | Dundori | -0.262328, 36.187226 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2021/22 | 2021/22 | 2023/2024 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 58 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Silent enterprise.
3899 | Construction Of A Kitchen, Caretaker House, Laundry, Expansion Of Rooms | Construction Of A Kitchen, Caretaker House, Laundry, Expansion Of Rooms | To construct A Kitchen, Caretaker House, Laundry, Expansion Of Rooms | A Kitchen, Caretaker House, Laundry, Expansion Of Rooms constructed | 3110299 | Construction of Buildings - Ot | HQ | HQ | -0.173672, 35.862823 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2019/20 | 2019/20 | 2019/20 | 6506105 | 3196623 | 3196623 | N/A | N/A | 3196623 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3900 | Enhanced Care And Support Of The Elderly Through Expansion Of New Rooms At Alms House | Enhanced Care And Support Of The Elderly Through Expansion Of New Rooms At Alms House | To implement enhanced care and support of the elderly through expansion of new rooms at alms house for youth empowerment and social inclusion | Enhanced Care And Support Of The Elderly Through Expansion Of New Rooms At Alms House completed | 3110299 | Construction of Buildings - Ot | HQ | HQ | -0.173672, 35.862823 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2018/19 | 2018/19 | 2018/19 | 2351783.6 | 2351783.6 | 2351783.6 | N/A | N/A | 2351783.6 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3901 | Expansion of the GBV rescue center in Gilgil | Expansion of the GBV rescue center in Gilgil | To expand the GBV rescue center in Gilgil to increase capacity | The GBV rescue center in Gilgil expanded | 3110299 | Construction of Buildings - Ot | HQ | HQ | -0.173672, 35.862823 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2021/22 | 2021/22 | 2021/22 | 13500000 | 10000000 | 7500000 | N/A | N/A | 7500000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3902 | Expansion of the GBV Rescue Center | Expansion of the GBV Rescue Center | To expand the GBV Rescue Center to increase capacity | The GBV Rescue Center expanded | 3110299 | Construction of Buildings - Ot | HQ | HQ | -0.173672, 35.862823 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2022/23 | 2022/23 | 2022/23 | 60000000 | 10000000 | 10000000 | N/A | N/A | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3903 | Partial Completion Of A GBV Centre | Partial Completion Of A GBV Centre | To implement partial completion of a gbv centre for youth empowerment and social inclusion | Partial Completion Of A GBV Centre completed | 3110299 | Construction of Buildings - Ot | HQ | HQ | -0.173672, 35.862823 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | 2020/21 | 7714075 | 7714075 | 7714075 | N/A | N/A | 7714075 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3904 | Administration, Planning and Support Services | Construction of social hall in Kabazi | To construct social hall in Kabazi | Social hall in Kabazi constructed | 3110299 | Construction of Buildings - Ot | Subukia | Kabazi | -0.077923 36.171018 0 215.28369140625 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2021/22 | 2021/22 | N/A | 5000000 | 4778705 | 4778705 | Equitable | - | 4778705 | 0 | 0 | 0 | 0 | 584 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Vertex general supplies and construction enterprises ltd. Assessor remarks: Requires equipping.
3905 | Administration, Planning and Support Services | Construction Of Social Hall Capacity Minimum 500 People,Innovative Hub And Music Recording Studio Room, Construction Of Perimeter Wall With Razor Wire And Installation Of Standard Gate And Equipping Of Social Hall In Kaptembwo Resourse Center | To construct Social Hall Capacity Minimum 500 People,Innovative Hub And Music Recording Studio Room, Construction Of Perimeter Wall With Razor Wire And Installation Of Standard Gate And Equipping Of Social Hall In Kaptembwo Resourse Center | Social Hall Capacity Minimum 500 People,Innovative Hub And Music Recording Studio Room, Construction Of Perimeter Wall With Razor Wire And Installation Of Standard Gate And Equipping Of Social Hall In Kaptembwo Resourse Center constructed | 3110299 | Construction of Buildings - Ot | Nakuru West | Kaptembwo | -0.29996 36.051202 1804.199951171875 26.304000854492188 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2019/20 | 2019/20 | N/A | 8145259 | 4505260 | 4505260 | Equitable | - | 4505260 | 0 | 788 | 0 | 788 | 1311 | 4504472 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Contractor: Not awarded. Assessor remarks: The school have all the amenities pertaining classes the money should do another project.
3906 | Administration, Planning and Support Services | Construction Of Kuresoi Social Hall | To construct Kuresoi Social Hall | Kuresoi Social Hall constructed | 3110299 | Construction of Buildings - Ot | Kuresoi North | Kiptororo | -0.301128, 35.532976 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | 2020/21 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 1329 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Yes.
3907 | Administration, Planning and Support Services | Construction Of Jua Kali Social Hall | To construct Jua Kali Social Hall | Jua Kali Social Hall constructed | 3110299 | Construction of Buildings - Ot | Njoro | Mau Narok | -0.574654, 35.693519 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | 2017 | 2000000 | 1971270 | 1971270 | Equitable | 1,971,270 | 1971270 | 0 | 0 | 0 | 0 | 1306 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3908 | Administration, Planning and Support Services | Completion Of Youths Center At Kiamunyi | To complete Youths Center At Kiamunyi | Youths Center At Kiamunyi completed | 3110299 | Construction of Buildings - Ot | Rongai | Menengai West | -0.166762 36.007934 0 600 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | N/A | 2000000 | 2000000 | 2000000 | Equitable | 1,725,210 | 2000000 | 0 | 0 | 0 | 0 | 1331 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs renovation.
3909 | Administration, Planning and Support Services | Construction Of Youth Centre At Kiamunyi | To construct Youth Centre At Kiamunyi | Youth Centre At Kiamunyi constructed | 3110299 | Construction of Buildings - Ot | Rongai | Menengai West | -0.2466 36.013657 2010.9 9.5 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2018/19 | 2018/19 | N/A | 3500000 | 3500000 | 3500000 | Equitable | 1,725,210 | 3500000 | 0 | 0 | 0 | 0 | 1331 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
3910 | Construction Of Library Molo Town | Construction Of Library Molo Town | To construct Library Molo Town | Library Molo Town constructed | 3110299 | Construction of Buildings - Ot | Molo | Molo Central | -0.173672, 35.862823 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2014/15 | 2014/15 | 2014/15 | 1036883 | 1036883 | 1036883 | Equitable | N/A | 1036883 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3911 | Administration, Planning and Support Services | Construction of a Social Hall at Kamere Beach | To construct a Social Hall at Kamere Beach | A Social Hall at Kamere Beach constructed | 3110299 | Construction of Buildings - Ot | Naivasha | Olkaria | -0.815646, 36.322503 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2022/23 | 2022/23 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes but not yet done.
3912 | Administration, Planning and Support Services | Construction Of Toilet ,Changing Room And Shade At Mwariki Playing Ground | To construct Toilet ,Changing Room And Shade At Mwariki Playing Ground | Toilet ,Changing Room And Shade At Mwariki Playing Ground constructed | 3110299 | Construction of Buildings - Ot | Nakuru West | Rhonda | -0.315828, 36.063965 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | 19/20 | 2000000 | 1999900 | 1999900 | Equitable | 1,999,900 | 1999900 | 0 | 0 | 0 | 0 | 1319 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: N/a. Viable: N/a. Contractor: N/a.
3913 | Administration, Planning and Support Services | Construction Of Sotiki Resource Center | To construct Sotiki Resource Center | Sotiki Resource Center constructed | 3110299 | Construction of Buildings - Ot | Kuresoi South | Tinet | -0.529565 35.610744 0 2900 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2021/22 | 2021/22 | N/A | 2000000 | 2000000 | 2000000 | Equitable | - | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: Ongoing.
3914 | Administration, Planning and Support Services | Completion Of Viwandani Social Hall | To complete Viwandani Social Hall | Viwandani Social Hall completed | 3110299 | Construction of Buildings - Ot | Naivasha | Viwandani | -0.713021 36.435682 1907.4000244140625 18.20400047302246 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2021/22 | 2021/22 | N/A | 500000 | 500000 | 500000 | Equitable | - | 500000 | 0 | 0 | 0 | 0 | 28 | 0 | N/A | 90 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Very viable. Assessor remarks: Operational.
3915 | Administration, Planning and Support Services | Rehabilitation Of London Social Hall | To rehabilitate London Social Hall to restore functionality | London Social Hall rehabilitated | 3110302 | Refurbishment of Non-Residential Buildings | Nakuru West | London | -0.275133 36.049587 1857.5 9.5 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2019/20 | 2019/20 | N/A | 6800000 | 3400000 | 3400000 | Equitable | 3,400,000 | 3400000 | 0 | 0 | 0 | 0 | 1318 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs repainting and provide an alternative access road from the one at gioto direct to the hall.
3916 | Administration, Planning and Support Services | Renovation And Rehabilitation Of Bondeni Social Hall, Doors, Windows And Window Panes And Painting | To rehabilitate Rehabilitation Of Bondeni Social Hall, Doors, Windows And Window Panes And Painting to restore functionality | Rehabilitation Of Bondeni Social Hall, Doors, Windows And Window Panes And Painting rehabilitated | 3110399 | Refurbishment of Buildgs - Oth | Gilgil | Gilgil | -0.505151, 36.327373 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2021/22 | 2021/22 | 2021/22 | 500000 | 500000 | 500000 | Equitable | - | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No.
3917 | Rehabilitation and Equipping of the drop-in centre at Njoro Homecraft | Rehabilitation and Equipping of the drop-in centre at Njoro Homecraft | To rehabilitate Equipping of the drop-in centre at Njoro Homecraft to restore functionality | Equipping of the drop-in centre at Njoro Homecraft rehabilitated | 3110399 | Refurbishment of Buildgs - Oth | HQ | HQ | -0.173672, 35.862823 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2022/23 | 2022/23 | 2022/23 | 60000000 | 10000000 | 10000000 | N/A | N/A | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3918 | Administration, Planning and Support Services | Equipping Of Bondeni Gym | To equip Bondeni Gym with necessary facilities and equipment | Bondeni Gym equipped | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | N/A | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2021/22 | 2021/22 | N/A | 500000 | 600000 | 600000 | Equitable | - | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
3919 | Completion works and facelifting of Kirathimo stadium, Gituamba Kiamaina | Completion works and facelifting of Kirathimo stadium, Gituamba Kiamaina | To complete works and facelifting of Kirathimo stadium, Gituamba Kiamaina | Works and facelifting of Kirathimo stadium, Gituamba Kiamaina completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2021/22 | 2021/22 | 2021/22 | 5000000 | 0 | 5000000 | N/A | N/A | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3920 | Construction of Art Center in Rongai Subcounty | Construction of Art Center in Rongai Subcounty | To construct Art Center in Rongai Subcounty | Art Center in Rongai Subcounty constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2021/22 | 2021/22 | 2021/22 | 2500000 | 0 | 2500000 | N/A | N/A | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3921 | Construction of backstop, levelling, installation of goal posts and renovation of changing rooms at Gilgil stadium | Construction of backstop, levelling, installation of goal posts and renovation of changing rooms at Gilgil stadium | To construct backstop, levelling, installation of goal posts and renovation of changing rooms at Gilgil stadium | Backstop, levelling, installation of goal posts and renovation of changing rooms at Gilgil stadium constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2022/23 | 2022/23 | 2022/23 | 2500000 | 0 | 2500000 | N/A | N/A | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3922 | Construction Of Gilgil Stadium | Construction Of Gilgil Stadium | To construct Gilgil Stadium | Gilgil Stadium constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2021/22 | 2021/22 | 2021/22 | 10000000 | 9950000 | 9950000 | N/A | N/A | 9950000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3923 | Construction Of Kamukunji Stadium | Construction Of Kamukunji Stadium | To construct Kamukunji Stadium | Kamukunji Stadium constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2021/22 | 2021/22 | 2021/22 | 10000000 | 9990616 | 9990616 | N/A | N/A | 9990616 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3924 | Construction Of Molo Stadium | Construction Of Molo Stadium | To construct Molo Stadium | Molo Stadium constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2021/22 | 2021/22 | 2021/22 | 15000000 | 15000000 | 10000000 | N/A | N/A | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3925 | Construction Of St. Theresa Stadium | Construction Of St. Theresa Stadium | To construct St. Theresa Stadium | St. Theresa Stadium constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2021/22 | 2021/22 | 2021/22 | 5000000 | 5000000 | 5000000 | N/A | N/A | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3926 | Construction Of Toilets In Muriricua Sport Ground And Levelling Of Miti Mingi, Makongo And Tangi Tano Sport Grounds In Elementaita Ward | Construction Of Toilets In Muriricua Sport Ground And Levelling Of Miti Mingi, Makongo And Tangi Tano Sport Grounds In Elementaita Ward | To construct Toilets In Muriricua Sport Ground And Levelling Of Miti Mingi, Makongo And Tangi Tano Sport Grounds In Elementaita Ward | Toilets In Muriricua Sport Ground And Levelling Of Miti Mingi, Makongo And Tangi Tano Sport Grounds In Elementaita Ward constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2021/22 | 2021/22 | 2021/22 | 3000000 | 3000000 | 3000000 | N/A | N/A | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3927 | Construction Perimetre Wall Rongai Stadium | Construction Perimetre Wall Rongai Stadium | To construct Perimetre Wall Rongai Stadium | Perimetre Wall Rongai Stadium constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2018/19 | 2018/19 | 2018/19 | 3480711.08 | 1172087.18 | 1172087.18 | N/A | N/A | 1172087.18 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3928 | Enhanced Care And Support Of The Elderly Through completion of perimeter wall and Gate At Alms House | Enhanced Care And Support Of The Elderly Through completion of perimeter wall and Gate At Alms House | To implement enhanced care and support of the elderly through completion of perimeter wall and gate at alms house for youth empowerment and social inclusion | Enhanced Care And Support Of The Elderly Through completion of perimeter wall and Gate At Alms House completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | 2020/21 | 1000000 | 0 | 1000000 | N/A | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3929 | Equipping of Alms house, boarding facility, Kitchen, laundry, caretakers house | Equipping of Alms house, boarding facility, Kitchen, laundry, caretakers house | To equip Alms house, boarding facility, Kitchen, laundry, caretakers house with necessary facilities and equipment | Alms house, boarding facility, Kitchen, laundry, caretakers house equipped | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2022/23 | 2022/23 | 2022/23 | 10000000 | 2000000 | 2000000 | N/A | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3930 | Establishment Of A Sports Centre At Keringet (Phase 1) | Establishment Of A Sports Centre At Keringet (Phase 1) | To implement establishment of a sports centre at keringet (phase 1) for youth empowerment and social inclusion | Establishment Of A Sports Centre At Keringet (Phase 1) completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2022/23 | 2021/22 | 2021/22 | 121000000 | 10583282.75 | 10583282.75 | N/A | N/A | 10583282.75 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3931 | Establishment Of A Sports Centre At Keringet (Phase 3) | Establishment Of A Sports Centre At Keringet (Phase 3) | To implement establishment of a sports centre at keringet (phase 3) for youth empowerment and social inclusion | Establishment Of A Sports Centre At Keringet (Phase 3) completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2021/22 | 2021/22 | 2021/22 | 121000000 | 50000000 | 50000000 | N/A | N/A | 50000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3932 | Establishment Of Sports Centre At Keringet (Phase 2) | Establishment Of Sports Centre At Keringet (Phase 2) | To implement establishment of sports centre at keringet (phase 2) for youth empowerment and social inclusion | Establishment Of Sports Centre At Keringet (Phase 2) completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | 2020/21 | 35000000 | 7634270.2 | 7634270.2 | N/A | N/A | 7634270.2 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3933 | Partial Fence, Reroofing, Electrical Works , Plumbing, General Repairs And Renovation | Partial Fence, Reroofing, Electrical Works , Plumbing, General Repairs And Renovation | To implement partial fence, reroofing, electrical works , plumbing, general repairs and renovation for youth empowerment and social inclusion | Partial Fence, Reroofing, Electrical Works , Plumbing, General Repairs And Renovation completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2019/20 | 2019/20 | 2019/20 | 9503720 | 9503720 | 9503720 | N/A | N/A | 9503720 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3934 | Renovation And Equipping And Refurbishment Of Menengai Social Complex | Renovation And Equipping And Refurbishment Of Menengai Social Complex | To rehabilitate Equipping And Refurbishment Of Menengai Social Complex to restore functionality | Equipping And Refurbishment Of Menengai Social Complex rehabilitated | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2018/19 | 2018/19 | 2018/19 | 5900000 | 2400250 | 2400250 | N/A | N/A | 2400250 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3935 | Renovation of the Textile Hub for the Nakuru County Youth Engagement Programme | Renovation of the Textile Hub for the Nakuru County Youth Engagement Programme | To rehabilitate the Textile Hub for the Nakuru County Youth Engagement Programme to restore functionality | The Textile Hub for the Nakuru County Youth Engagement Programme rehabilitated | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2022/23 | 2022/23 | 2022/23 | 50000000 | 5000000 | 5000000 | N/A | N/A | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3936 | Administration, Planning and Support Services | Land Levelling Of Resource Centre At Sewage Village | To implement land levelling of resource centre at sewage village for youth empowerment and social inclusion | Land Levelling Of Resource Centre At Sewage Village completed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kaptembwo | -0.318516 36.05296 1768.8572483399244 12.072999954223633 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2016/17 | 2016/17 | N/A | 3000000 | 3000000 | 3000000 | Equitable | 2,750,000 | 3000000 | 0 | 0 | 0 | 0 | 1311 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes but the gate was in wrong position. Contractor: U40. Assessor remarks: the gate was not well positioned hence it was relocated to an accessible place.
3937 | Administration, Planning and Support Services | Women And Youth Groups Empowerment | To implement women and youth groups empowerment for youth empowerment and social inclusion | Women And Youth Groups Empowerment completed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Kaptembwo | N/A | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | N/A | 5000000 | 1184531 | 1184531 | Equitable | 820,700 | 1184531 | 0 | 0 | 0 | 0 | 42289 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
3938 | Administration, Planning and Support Services | Construction Of A Perimeter Fence At Kirathimo Grounds | To construct A Perimeter Fence At Kirathimo Grounds | A Perimeter Fence At Kirathimo Grounds constructed | 3110504 | Other Infrastructure and Civil Works | Bahati | Kiamaina | -0.23708, 36.123315 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2021/22 | 2021/22 | N/A | 2500000 | 2500000 | 2500000 | Equitable | - | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: The project not in existence. Viable: No.
3939 | Administration, Planning and Support Services | Construction Of Modern Washrooms, Water Point, Football And Volleyball Posts, Security Light And Installation Of Wifi At Kirathimo Grounds | To construct Modern Washrooms, Water Point, Football And Volleyball Posts, Security Light And Installation Of Wifi At Kirathimo Grounds | Modern Washrooms, Water Point, Football And Volleyball Posts, Security Light And Installation Of Wifi At Kirathimo Grounds constructed | 3110504 | Other Infrastructure and Civil Works | Bahati | Kiamaina | -0.236885, 36.123922 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | 2020/21 | 2000000 | 1999900 | 1999900 | Equitable | 1,999,900 | 1999900 | 0 | 0 | 0 | 0 | 1317 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: Yes.
3940 | Administration, Planning and Support Services | Playfield Levelling And Fencing | To implement playfield levelling and fencing for youth empowerment and social inclusion | Playfield Levelling And Fencing completed | 3110504 | Other Infrastructure and Civil Works | Njoro | Kihingo | -0.443013 35.969212 2274.8 8.800000190734863 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2021/22 | 2021/22 | N/A | 1500000 | 1493200 | 1493200 | Equitable | - | 1493200 | 0 | 0 | 0 | 0 | 775 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Requires fencing, levelling and installation of goalposts.
3941 | Administration, Planning and Support Services | Construction of PWDs modern toilets at public facilities in Lakeview Ward | To construct PWDs modern toilets at public facilities in Lakeview Ward | PWDs modern toilets at public facilities in Lakeview Ward constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Lakeview | -0.733758, 36.435868 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2022/23 | 2022/23 | 2022/23 | 3019243 | 3019243 | 3019243 | Equitable | 2,820,080 | 3019243 | 0 | 673 | 0 | 673 | 0 | 3018570 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes but not in use.
3942 | Administration, Planning and Support Services | Fencing Of Kayole Social Hall | To secure Kayole Social Hall through fencing | Kayole Social Hall fenced and secured | 3110504 | Other Infrastructure and Civil Works | Naivasha | Lakeview | -0.757211, 36.463806 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2021/22 | 2021/22 | 2021/22 | 2180757 | 2125060 | 2125060 | Equitable | 2,928,770 | 2125060 | 0 | 669 | 0 | 669 | 454 | 2124391 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3943 | Administration, Planning and Support Services | Construction of toilet at Kasarani Stadium, water kiosk with 10,000 litres water tank | To construct toilet at Kasarani Stadium, water kiosk with 10,000 litres water tank | Toilet at Kasarani Stadium, water kiosk with 10,000 litres water tank constructed | 3110504 | Other Infrastructure and Civil Works | Njoro | Lare | -0.512937 36.024443 2326.4 6.800000190734863 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2022/23 | 2022/23 | N/A | 1000000 | 1000000 | 1000000 | Equitable | - | 1000000 | 0 | 655 | 0.1 | 655 | 63 | 999345 | N/A | 90 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need more durable piping's for distribution.
3944 | Administration, Planning and Support Services | Construction of modern (PLWD) special needs toilet 4 door and handwashing point at Nakuru Hills Special School | To construct modern (PLWD) special needs toilet 4 door and handwashing point at Nakuru Hills Special School | Modern (PLWD) special needs toilet 4 door and handwashing point at Nakuru Hills Special School constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | London | -0.271878, 36.056708 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2022/23 | 2022/23 | 2022/23 | 1200000 | 1200000 | 1200000 | Equitable | 1,189,030 | 1200000 | 0 | 664 | 0.1 | 664 | 0 | 1199336 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3945 | Administration, Planning and Support Services | Refurbishment Of Railways Estate Football Pitch (Levelling, Grass Planting And Goal Post Installation) | To implement refurbishment of railways estate football pitch (levelling, grass planting and goal post installation) for youth empowerment and social inclusion | Refurbishment Of Railways Estate Football Pitch (Levelling, Grass Planting And Goal Post Installation) completed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | London | N/A | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2021/22 | 2021/22 | N/A | 900000 | 900000 | 900000 | Equitable | - | 900000 | 0 | 0 | 0 | 0 | 53 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
3946 | Administration, Planning and Support Services | Refurbishment of Railways Pitch (Phase two); changing rooms, fencing & pavilion shed 50pax) | To implement refurbishment of railways pitch (phase two); changing rooms, fencing & pavilion shed 50pax) for youth empowerment and social inclusion | Refurbishment of Railways Pitch (Phase two); changing rooms, fencing & pavilion shed 50pax) completed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | London | N/A | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2022/23 | 2022/23 | N/A | 858699 | 858699 | 858699 | Equitable | N/A | 858699 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
3947 | Administration, Planning and Support Services | Completion Of Fencing Of Maai Mahiu Social Hall | To complete Fencing Of Maai Mahiu Social Hall | Fencing Of Maai Mahiu Social Hall completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maai Mahiu | -0.978956, 36.585812 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | 2020/21 | 1500000 | 1500000 | 1500000 | Equitable | 1,660,750 | 1500000 | 0 | 789 | 0.1 | 789 | 0 | 1499211 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
3948 | Administration, Planning and Support Services | Fencing Of Maai Mahiu Social Hall | To secure Maai Mahiu Social Hall through fencing | Maai Mahiu Social Hall fenced and secured | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maai Mahiu | -0.978956, 36.585812 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | 2020/21 | 2500000 | 3500000 | 3500000 | Equitable | 1,660,750 | 3500000 | 0 | 789 | 0 | 789 | 0 | 3499211 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
3949 | Administration, Planning and Support Services | Grading, Levelling and Installation Of Goal Post In Kariandusi Playground | To implement grading, levelling and installation of goal post in kariandusi playground for youth empowerment and social inclusion | Grading, Levelling and Installation Of Goal Post In Kariandusi Playground completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maai Mahiu | N/A | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2022/23 | 2022/23 | N/A | 5000000 | 5000000 | 5000000 | Equitable | 3,636,850 | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
3950 | Administration, Planning and Support Services | Construction Of A Multipurpose Hall And Equipping At Mau Old Town | To construct A Multipurpose Hall And Equipping At Mau Old Town | A Multipurpose Hall And Equipping At Mau Old Town constructed | 3110504 | Other Infrastructure and Civil Works | Njoro | Mau Narok | -0.599977, 36.005543 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2021/22 | 2021/22 | 2021/22 | 5800000 | 5635760 | 5635760 | Equitable | - | 5635760 | 0 | 0 | 0 | 0 | 453 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable.
3951 | Administration, Planning and Support Services | Installation Of Internal And External CCTV At Teachers Social Hall | To install Internal And External CCTV At Teachers Social Hall | Internal And External CCTV At Teachers Social Hall installed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Menengai | -0.275828, 36.115286 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2021/22 | 2021/22 | 2021/21 | 150000 | 150000 | 150000 | Equitable | - | 150000 | 0 | 0 | 0 | 0 | 11822 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3952 | Administration, Planning and Support Services | Grading, levelling and Installation of Goal posts in Mercy Njeri Primary/ECDE playground | To implement grading, levelling and installation of goal posts in mercy njeri primary/ecde playground for youth empowerment and social inclusion | Grading, levelling and Installation of Goal posts in Mercy Njeri Primary/ECDE playground completed | 3110504 | Other Infrastructure and Civil Works | Rongai | Menengai West | -0.257143 36.0155 1964.0999755859375 56.099998474121094 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2022/23 | 2022/23 | N/A | 1022740 | 1022740 | 1022740 | Equitable | N/A | 1022740 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
3953 | Administration, Planning and Support Services | Construction of Free Area (Lanet) Social Hall Perimeter Wall and gate | To construct Free Area (Lanet) Social Hall Perimeter Wall and gate | Free Area (Lanet) Social Hall Perimeter Wall and gate constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Nakuru East | -0.293675, 36.118709 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2022/23 | 2022/23 | 2022/2023 | 3000000 | 3000000 | 3000000 | Equitable | - | 3000000 | 0 | 663 | 0 | 663 | 0 | 2999337 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Fino ltd.
3954 | Administration, Planning and Support Services | Construction of a Sanitation Block, water connection and installation of floodlights at Jewathu Stadium | To construct a Sanitation Block, water connection and installation of floodlights at Jewathu Stadium | A Sanitation Block, water connection and installation of floodlights at Jewathu Stadium constructed | 3110504 | Other Infrastructure and Civil Works | Njoro | Njoro | -0.333229 35.947302 2147.7001953125 4.48799991607666 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2022/23 | 2022/23 | N/A | 7000000 | 7000000 | 7000000 | Equitable | N/A | 7000000 | 0 | 662 | 0 | 662 | 652 | 6999338 | N/A | 25 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: Yes. Contractor: N/ A. Assessor remarks: Manhole covers missing.
3955 | Administration, Planning and Support Services | Construction of PWDs toilets within Olkaria Ward | To construct PWDs toilets within Olkaria Ward | PWDs toilets within Olkaria Ward constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Olkaria | -0.819481 36.32143 1931.300048828125 68.4000015258789 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2022/23 | 2022/23 | N/A | 2000000 | 2000000 | 2000000 | Equitable | - | 2000000 | 0 | 0 | 0 | 0 | 73 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes if finished. Assessor remarks: The structure is complete but no septic pit.
3956 | Administration, Planning and Support Services | Levelling, compacting, grass planting, installation of goal posts, perimiter wall, cage and construction of pavillion with dias | To implement levelling, compacting, grass planting, installation of goal posts, perimiter wall, cage and construction of pavillion with dias for youth empowerment and social inclusion | Levelling, compacting, grass planting, installation of goal posts, perimiter wall, cage and construction of pavillion with dias completed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Rhonda | N/A | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2019/20 | 2019/20 | N/A | 5000000 | 0 | 5000000 | Equitable | - | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
3957 | Administration, Planning and Support Services | Construction Of Perimeter Wall In Rongai Stadium | To construct Perimeter Wall In Rongai Stadium | Perimeter Wall In Rongai Stadium constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Visoi | -0.173526 35.860517 1868.199951171875 54.09400177001953 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2019/20 | 2019/20 | N/A | 1899318 | 1899318 | 1899318 | Equitable | 286,567 | 1899318 | 0 | 0 | 0 | 0 | 314 | 0 | N/A | 90 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Rongai town. Viable: Yes. Assessor remarks: Good.
3958 | Administration, Planning and Support Services | Construction Of Artificial Turf In Viwandani Ward Sports Ground | To construct Artificial Turf In Viwandani Ward Sports Ground | Artificial Turf In Viwandani Ward Sports Ground constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Viwandani | -0.718855 36.435314 1899.9000244140625 6.821000099182129 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2021/22 | 2021/22 | N/A | 5000000 | 5000000 | 5000000 | Equitable | - | 5000000 | 0 | 0 | 0 | 0 | 91 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Assessor remarks: Operation.
3959 | Administration, Planning and Support Services | Construction of Youth friendly centre in Viwandani | To construct Youth friendly centre in Viwandani | Youth friendly centre in Viwandani constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Viwandani | -0.712569, 36.435681 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2022/23 | 2022/23 | 2022/23 | 3000000 | 3000000 | 3000000 | Equitable | - | 3000000 | 0 | 0 | 0 | 0 | 91 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable.
3960 | Administration, Planning and Support Services | Installation and fencing of Artificial Turf in Viwandani Ward | To install and fencing of Artificial Turf in Viwandani Ward | And fencing of Artificial Turf in Viwandani Ward installed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Viwandani | -0.701181 36.426027 1889.699951171875 1.3339999914169312 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2022/23 | 2022/23 | N/A | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 90 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Assessor remarks: Operational.
3961 | Administration, Planning and Support Services | Renovation Of Studio And Amphitheatre In Industrial Area | To rehabilitate Studio And Amphitheatre In Industrial Area to restore functionality | Studio And Amphitheatre In Industrial Area rehabilitated | 3110504 | Other Infrastructure and Civil Works | Naivasha | Viwandani | -0.71298 36.435601 1906.300048828125 20.15399932861328 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | N/A | 1500000 | 1500000 | 1500000 | Equitable | - | 1500000 | 0 | 0 | 0 | 0 | 1329 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Very viable. Assessor remarks: Complete.
3962 | Administration, Planning and Support Services | Completion Of Kimathi Football Dressing Room | To complete Kimathi Football Dressing Room | Kimathi Football Dressing Room completed | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Flamingo | -0.303692 36.07859 1814.5 4.699999809265137 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | N/A | 1500000 | 1500000 | 1500000 | Equitable | 1,485,500 | 1500000 | 0 | 0 | 0 | 0 | 1320 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Callbest logistics. Assessor remarks: Complete.
3963 | Administration, Planning and Support Services | Construction Of 6 Door Stardard Toilet Disabilities Friendly And Construction Of Underground Water Tank 100,000 Litres And Installation Of Raised Water Tanlk 10,000 Litres In Kaptembwo Resourse Center | To construct 6 Door Stardard Toilet Disabilities Friendly And Construction Of Underground Water Tank 100,000 Litres And Installation Of Raised Water Tanlk 10,000 Litres In Kaptembwo Resourse Center | 6 Door Stardard Toilet Disabilities Friendly And Construction Of Underground Water Tank 100,000 Litres And Installation Of Raised Water Tanlk 10,000 Litres In Kaptembwo Resourse Center constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Kaptembwo | -0.29996 36.051202 1804.199951171875 26.304000854492188 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2019/20 | 2019/20 | N/A | 2500000 | 2500000 | 2500000 | Equitable | 2,439,980 | 2500000 | 0 | 0 | 0 | 0 | 1838 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Contractor: Not awarded. Assessor remarks: The school have all the amenities pertaining classes the money should do another project.
3964 | Administration, Planning and Support Services | Construction of perimeter wall and gate in the resource centre at Sewage Village | To construct perimeter wall and gate in the resource centre at Sewage Village | Perimeter wall and gate in the resource centre at Sewage Village constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru West | Kaptembwo | -0.318516 36.05296 1768.8572483399244 12.072999954223633 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | N/A | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 13330 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes but the gate was in wrong position. Contractor: U40. Assessor remarks: the gate was not well positioned hence it was relocated to an accessible place.
3965 | Administration, Planning and Support Services | Construction Of A Sport Centre At St Teresa Ecde - Swimming Pool, Basket Ball Court, Netball Court, Volleyball Court | To construct A Sport Centre At St Teresa Ecde - Swimming Pool, Basket Ball Court, Netball Court, Volleyball Court | A Sport Centre At St Teresa Ecde - Swimming Pool, Basket Ball Court, Netball Court, Volleyball Court constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Kivumbini | -0.29986, 36.084106 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2017/18 | 2017/18 | N/A | 8133044 | 256260.6 | 256260.6 | Equitable | 252,416 | 256260.6 | 0 | 0 | 0 | 0 | 11803 | 0 | Stalled | 0 | N/A | Stalled — reasons to be confirmed by department | 2017 | N/A | N/A | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No.
3966 | Administration, Planning and Support Services | Heavy Bush Clearing, Levelling, Fencing With Concrete Posts And Two Main Gates And Construction Of Toilets At Kasarani Playground. | To implement heavy bush clearing, levelling, fencing with concrete posts and two main gates and construction of toilets at kasarani playground. for youth empowerment and social inclusion | Heavy Bush Clearing, Levelling, Fencing With Concrete Posts And Two Main Gates And Construction Of Toilets At Kasarani Playground. completed | 3110599 | Other Infrastructure and Civil Works | Njoro | Lare | -0.442944, 36.011884 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2021/22 | 2021/22 | 2023 | 1900000 | 1794550 | 1794550 | Equitable | - | 1794550 | 0 | 0 | 0 | 0 | 520 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3967 | Administration, Planning and Support Services | Renovation and Equipping of London Social Hall | To rehabilitate Equipping of London Social Hall to restore functionality | Equipping of London Social Hall rehabilitated | 3110599 | Other Infrastructure and Civil Works | Nakuru West | London | -0.27499, 36.049414 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2022/23 | 2022/23 | N/A | 9800000 | 0 | 9800000 | Equitable | N/A | 9800000 | 0 | 0 | 0 | 0 | 41 | 0 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
3968 | Equipping Of Alms House, Boarding Facility, Kitchen, Laundry, Caretakers House | Equipping Of Alms House, Boarding Facility, Kitchen, Laundry, Caretakers House | To equip Alms House, Boarding Facility, Kitchen, Laundry, Caretakers House with necessary facilities and equipment | Alms House, Boarding Facility, Kitchen, Laundry, Caretakers House equipped | 3110999 | N/A | HQ | HQ | -0.173672, 35.862823 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2021/22 | 2021/22 | 2021/22 | 10000000 | 3380437 | 3380437 | N/A | N/A | 3380437 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3969 | Equipping Of Drop In Centre At Njoro Homecraft (Dormitories, Workshops, Kitchen, Classrooms And Dining Hall) | Equipping Of Drop In Centre At Njoro Homecraft (Dormitories, Workshops, Kitchen, Classrooms And Dining Hall) | To equip Drop In Centre At Njoro Homecraft (Dormitories, Workshops, Kitchen, Classrooms And Dining Hall) with necessary facilities and equipment | Drop In Centre At Njoro Homecraft (Dormitories, Workshops, Kitchen, Classrooms And Dining Hall) equipped | 3110999 | N/A | HQ | HQ | -0.173672, 35.862823 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2021/22 | 2021/22 | 2021/22 | 10000000 | 5000000 | 5000000 | N/A | N/A | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3970 | Administration, Planning and Support Services | Purchase of assistive devices for PLWDs | To procure assistive devices for PLWDs | Assistive devices for PLWDs procured | 3111101 | Purchase of Medical and Dental Equipment | Nakuru West | Shabab | N/A | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2022/23 | 2022/23 | N/A | 591031 | 591031 | 591031 | Equitable | - | 591031 | 0 | 0 | 0 | 0 | 96 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
3971 | Development Of Socio-Cultural Diversity, Economic Empowerment and Responsible Gaming | Equipping Of Molo, Kwa Amos, Viwandani, Gilgil, Lanet and Baharini Social Halls | To equip Molo, Kwa Amos, Viwandani, Gilgil, Lanet and Baharini Social Halls with necessary facilities and equipment | Molo, Kwa Amos, Viwandani, Gilgil, Lanet and Baharini Social Halls equipped | 3111109 | Purchase of Educational Aids and Related Equipment | HQ | HQ | N/A | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2021/22 | 2021/22 | N/A | 5000000 | 2036000 | 2036000 | Equitable | 2,964,000 | 2036000 | 0 | 0 | 0 | 0 | 184 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
3972 | Administration, Planning and Support Services | Equipping of Mogoon Resource Centre | To equip Mogoon Resource Centre with necessary facilities and equipment | Mogoon Resource Centre equipped | 3111109 | Purchase of Educational Aids and Related Equipment | Nakuru West | Kapkures | -0.324324, 36.036613 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2022/23 | 2022/23 | 2024/25 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 0 | 0 | 0 | 316 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not. Viable: Viable. But yet tobe implemented.
3973 | Administration, Planning and Support Services | Equipping Of Kasarani Social Hall And Shade Extention For Darts, Pool Table And Chess | To equip Kasarani Social Hall And Shade Extention For Darts, Pool Table And Chess with necessary facilities and equipment | Kasarani Social Hall And Shade Extention For Darts, Pool Table And Chess equipped | 3111109 | Purchase of Educational Aids and Related Equipment | Gilgil | Malewa West | -0.702703, 36.291018 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | 2021/22 | 2000000 | 1980000 | 1980000 | Equitable | 1,980,000 | 1980000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: Yes. Viable: Partly.
3974 | Administration, Planning and Support Services | Equipping Of Kianjoya Social Hall | To equip Kianjoya Social Hall with necessary facilities and equipment | Kianjoya Social Hall equipped | 3111109 | Purchase of Educational Aids and Related Equipment | Njoro | Mau Narok | -0.542058, 36.057445 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2021/22 | 2021/22 | 2021/22 | 344806 | 344806 | 344806 | Equitable | - | 344806 | 0 | 0 | 0 | 0 | 1306 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Partially. Viable: Viable.
3975 | Administration, Planning and Support Services | Equipping Of Menengai Social Hall | To equip Menengai Social Hall with necessary facilities and equipment | Menengai Social Hall equipped | 3111109 | Purchase of Educational Aids and Related Equipment | Nakuru East | Menengai | -0.275724, 36.115352 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2019/20 | 2019/20 | 2021/22 | 2000000 | 2000000 | 2000000 | Equitable | - | 2000000 | 0 | 0 | 0 | 0 | 326 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3976 | Administration, Planning and Support Services | Purchase and supply of sport equipments | To procure and supply sport equipments | Sport equipments procured and supplied | 3111109 | Purchase of Educational Aids and Related Equipment | Rongai | Menengai West | -0.157327 36.001343 1813.7 720.3189697265625 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2021/22 | 2021/22 | N/A | 1000000 | 0 | 1000000 | Equitable | - | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
3977 | Administration, Planning and Support Services | Equipping Of ICT Hub | To equip ICT Hub with necessary facilities and equipment | ICT Hub equipped | 3111109 | Purchase of Educational Aids and Related Equipment | Naivasha | Viwandani | -0.715125 36.432547 0 300 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | N/A | 2000000 | 1999200 | 1999200 | Equitable | N/A | 1999200 | 0 | 0 | 0 | 0 | 42640 | 0 | N/A | 90 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Assessor remarks: Operational.
3978 | Administration, Planning and Support Services | Equipping Of Studio And Amphitheatre In Industrial Area | To equip Studio And Amphitheatre In Industrial Area with necessary facilities and equipment | Studio And Amphitheatre In Industrial Area equipped | 3111109 | Purchase of Educational Aids and Related Equipment | Naivasha | Viwandani | -0.714444, 36.434114 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | 2020/21 | 3500000 | 3497100 | 3497100 | Equitable | 3,497,100 | 3497100 | 0 | 0 | 0 | 0 | 1329 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable.
3979 | Administration, Planning and Support Services | Purchase Of Land For Social Hall In Barut Ward | To acquire land for Social Hall In Barut Ward | Land for Social Hall In Barut Ward acquired | 3130101 | Acquisition of Land | Nakuru West | Barut | -0.324324, 36.054632 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2016/17 | 2016/17 | 2017 | 2000000 | 2000000 | 2000000 | Equitable | 2,000,000 | 2000000 | 0 | 0 | 0 | 0 | 836 | 0 | Stalled | 75 | N/A | Stalled — reasons to be confirmed by department | 2016 | N/A | N/A | No | Review — Complete, Defer or Cancel | Financial/funding gap; contractual/legal disputes; scope creep | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Good. Objective met: No. Viable: No.
3980 | Administration, Planning and Support Services | Purchase Of Manyere Football Pitch | To procure Manyere Football Pitch | Manyere Football Pitch procured | 3130101 | Acquisition of Land | Nakuru West | Barut | -0.34908, 36.056053 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2020/21 | 2020/21 | N/A | 7200000 | 259283 | 259283 | Equitable | - | 259283 | 0 | 0 | 0 | 0 | 837 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: RODI OREGE AND CO ADVOCATES.
3981 | Completion Of London Social Hall | Completion Of London Social Hall | To complete London Social Hall | London Social Hall completed | 4130299 | N/A | HQ | HQ | -0.173672, 35.862823 | 4576 | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | YOUTH, GENDER, CULTURE, SOCIAL SERVICES AND SPORTS | N/A | 2018/19 | 2018/19 | 2018/19 | 100000 | 97945 | 97945 | N/A | N/A | 97945 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3982 | Construction of Naivasha Municipality Office Block at Naivasha Sub County HQ | Construction of Naivasha Municipality Office Block at Naivasha Sub County HQ | To construct Naivasha Municipality Office Block at Naivasha Sub County HQ | Naivasha Municipality Office Block at Naivasha Sub County HQ constructed | 3110299 | Construction of Buildings - Ot | HQ | HQ | -0.173672, 35.862823 | 4577 | NAIVASHA MUNICIPALITY | NAIVASHA MUNICIPALITY | N/A | 2021/22 | 2021/22 | 2021/22 | 3300000 | 0 | 3300000 | N/A | N/A | 3300000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3983 | 3km Grading and Murruming of roads at Kinungi Center | 3km Grading and Murruming of roads at Kinungi Center | To implement 3km grading and murruming of roads at kinungi center for improved service delivery | 3km Grading and Murruming of roads at Kinungi Center completed | 3110499 | Construction of Roads - Other | HQ | HQ | -0.173672, 35.862823 | 4577 | NAIVASHA MUNICIPALITY | NAIVASHA MUNICIPALITY | N/A | 2021/22 | 2021/22 | 2021/22 | 3000000 | 0 | 3000000 | N/A | N/A | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3984 | Naivasha Municipal Services | Construction of roads in Naivasha Municipality | To construct roads in Naivasha Municipality | Roads in Naivasha Municipality constructed | 3110499 | Construction of Roads - Other | HQ | HQ | N/A | 4577 | NAIVASHA MUNICIPALITY | NAIVASHA MUNICIPALITY | N/A | 2022/23 | 2022/23 | N/A | 8000000 | 0 | 1073772.7 | N/A | N/A | 1073772.7 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
3985 | Grading and Murruming and Installation of new street lights at Karagita Center | Grading and Murruming and Installation of new street lights at Karagita Center | To improve road infrastructure by grading and murraming and Installation of new street lights at Karagita Center | And Installation of new street lights at Karagita Center graded and murramed | 3110499 | Construction of Roads - Other | HQ | HQ | -0.173672, 35.862823 | 4577 | NAIVASHA MUNICIPALITY | NAIVASHA MUNICIPALITY | N/A | 2021/22 | 2021/22 | 2021/22 | 2500000 | 0 | 2500000 | N/A | N/A | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3986 | Grading and Murruming of 2 km road in Kayole Estate | Grading and Murruming of 2 km road in Kayole Estate | To improve road infrastructure by grading and murraming 2 km road in Kayole Estate | 2 km road in Kayole Estate graded and murramed | 3110499 | Construction of Roads - Other | HQ | HQ | -0.173672, 35.862823 | 4577 | NAIVASHA MUNICIPALITY | NAIVASHA MUNICIPALITY | N/A | 2021/22 | 2021/22 | 2021/22 | 3000000 | 0 | 3000000 | N/A | N/A | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3987 | Improvement of 3km roads in Lakeview ward to bitumen standards and construction of related infrastructure | Improvement of 3km roads in Lakeview ward to bitumen standards and construction of related infrastructure | To implement improvement of 3km roads in lakeview ward to bitumen standards and construction of related infrastructure for improved service delivery | Improvement of 3km roads in Lakeview ward to bitumen standards and construction of related infrastructure completed | 3110499 | Construction of Roads - Other | HQ | HQ | -0.173672, 35.862823 | 4577 | NAIVASHA MUNICIPALITY | NAIVASHA MUNICIPALITY | N/A | 2021/22 | 2021/22 | 2021/22 | 89133075 | 0 | 0 | N/A | N/A | 0 | 6652495.19 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3988 | Improvement of roads to bitumen standards within Naivasha Municipality (3.7km)(Industrial Area, Site & Service and Kabati) | Improvement of roads to bitumen standards within Naivasha Municipality (3.7km)(Industrial Area, Site & Service and Kabati) | To implement improvement of roads to bitumen standards within naivasha municipality (3.7km)(industrial area, site & service and kabati) for improved service delivery | Improvement of roads to bitumen standards within Naivasha Municipality (3.7km)(Industrial Area, Site & Service and Kabati) completed | 3110499 | Construction of Roads - Other | HQ | HQ | -0.173672, 35.862823 | 4577 | NAIVASHA MUNICIPALITY | NAIVASHA MUNICIPALITY | N/A | 2021/22 | 2021/22 | 2021/22 | 6700000 | 0 | 6700000 | N/A | N/A | 6700000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3989 | Improvement Of Roads To Bitumen Standards Within Naivasha Municipality In Viwandani | Improvement Of Roads To Bitumen Standards Within Naivasha Municipality In Viwandani | To implement improvement of roads to bitumen standards within naivasha municipality in viwandani for improved service delivery | Improvement Of Roads To Bitumen Standards Within Naivasha Municipality In Viwandani completed | 3110499 | Construction of Roads - Other | HQ | HQ | -0.173672, 35.862823 | 4577 | NAIVASHA MUNICIPALITY | NAIVASHA MUNICIPALITY | N/A | 2024/25 | 2024/25 | 2024/25 | 6500000 | 0 | 6500000 | N/A | N/A | 6500000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
3990 | Naivasha Municipal Services | Completion of Construction of Naivasha Municipal park, construction of drainage and NMT facilities on adjoining Roads | To complete Construction of Naivasha Municipal park, construction of drainage and NMT facilities on adjoining Roads | Construction of Naivasha Municipal park, construction of drainage and NMT facilities on adjoining Roads completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4577 | NAIVASHA MUNICIPALITY | NAIVASHA MUNICIPALITY | N/A | 2021/22 | 2021/22 | N/A | 47165592 | 24958376 | 0 | N/A | N/A | 0 | 24958376 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
3991 | Naivasha Municipal Services | Construction of fish Banda's at Kamere Beach | To construct fish Banda's at Kamere Beach | Fish Banda's at Kamere Beach constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4577 | NAIVASHA MUNICIPALITY | NAIVASHA MUNICIPALITY | N/A | 2021/22 | 2021/22 | N/A | 4000000 | 0 | 4000000 | N/A | N/A | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
3992 | Naivasha Municipal Services | Construction of Naivasha Market Phase 2 | To construct Naivasha Market Phase 2 | Naivasha Market Phase 2 constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4577 | NAIVASHA MUNICIPALITY | NAIVASHA MUNICIPALITY | N/A | 2019/20 | 2019/20 | N/A | 260000000 | 0 | 0 | N/A | N/A | 0 | 12094566.04 | 0 | 0 | 0 | 246096145 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
3993 | Naivasha Municipal Services | Construction of NMT and paved parking along Kenyatta Avenue and Mama Ngina Street in Lakeview and Viwandani Wards | To construct NMT and paved parking along Kenyatta Avenue and Mama Ngina Street in Lakeview and Viwandani Wards | NMT and paved parking along Kenyatta Avenue and Mama Ngina Street in Lakeview and Viwandani Wards constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4577 | NAIVASHA MUNICIPALITY | NAIVASHA MUNICIPALITY | N/A | 2022/23 | 2022/23 | N/A | 20000000 | 0 | 1990343.25 | N/A | N/A | 1990343.25 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
3994 | Naivasha Municipal Services | Installation of Kayole and Lakeview Estate Streetlights | To install Kayole and Lakeview Estate Streetlights | Kayole and Lakeview Estate Streetlights installed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4577 | NAIVASHA MUNICIPALITY | NAIVASHA MUNICIPALITY | N/A | 2021/22 | 2021/22 | N/A | 2000000 | 0 | 2000000 | N/A | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
3995 | Naivasha Municipal Services | Installation of pump, construction of tower, supply of 4No. Plastic tanks for Gicheha Community borehole | To install pump, construction of tower, supply of 4No. Plastic tanks for Gicheha Community borehole | Pump, construction of tower, supply of 4No. Plastic tanks for Gicheha Community borehole installed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4577 | NAIVASHA MUNICIPALITY | NAIVASHA MUNICIPALITY | N/A | 2021/22 | 2021/22 | N/A | 3000000 | 0 | 3000000 | N/A | N/A | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
3996 | Naivasha Municipal Services | Installation of Street Lights at Kinungi Centre | To install Street Lights at Kinungi Centre | Street Lights at Kinungi Centre installed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4577 | NAIVASHA MUNICIPALITY | NAIVASHA MUNICIPALITY | N/A | 2021/22 | 2021/22 | N/A | 2000000 | 0 | 2000000 | N/A | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
3997 | Naivasha Municipal Services | Paved parking, Drainage, NMT and beautification along Mama Ngina Road | To implement paved parking, drainage, nmt and beautification along mama ngina road for improved service delivery | Paved parking, Drainage, NMT and beautification along Mama Ngina Road completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4577 | NAIVASHA MUNICIPALITY | NAIVASHA MUNICIPALITY | N/A | 2024/25 | 2024/25 | N/A | 10000000 | 10000000 | 13500000 | N/A | N/A | 13500000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
3998 | Naivasha Municipal Services | Rehabilitation of Naivasha Municipal Park | To rehabilitate Naivasha Municipal Park to restore functionality | Naivasha Municipal Park rehabilitated | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4577 | NAIVASHA MUNICIPALITY | NAIVASHA MUNICIPALITY | N/A | 2019/20 | 2019/20 | N/A | 22064368 | 0 | 0 | N/A | N/A | 0 | 729121.54 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
3999 | Naivasha Municipal Services | Rehabilitation of Sewerage system | To rehabilitate Sewerage system to restore functionality | Sewerage system rehabilitated | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4577 | NAIVASHA MUNICIPALITY | NAIVASHA MUNICIPALITY | N/A | 2023/24 | 2023/24 | N/A | 16000000 | 16000000 | 14957578.38 | N/A | N/A | 14957578.38 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
4000 | Naivasha Municipal Services | Relocation of existing street lights and installation of new street lights at Karagita | To implement relocation of existing street lights and installation of new street lights at karagita for improved service delivery | Relocation of existing street lights and installation of new street lights at Karagita completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4577 | NAIVASHA MUNICIPALITY | NAIVASHA MUNICIPALITY | N/A | 2021/22 | 2021/22 | N/A | 2500000 | 0 | 2500000 | N/A | N/A | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
4001 | Naivasha Municipal Services | Supply and Installation of security street lights at Kamere beach | To procure and install security street lights at Kamere beach | Security street lights at Kamere beach procured and installed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4577 | NAIVASHA MUNICIPALITY | NAIVASHA MUNICIPALITY | N/A | 2021/22 | 2021/22 | N/A | 1000000 | 0 | 1000000 | N/A | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
4002 | Naivasha Municipal Services | Supply and Installation of Solar Panels for Gicheha Community borehole | To procure and install Solar Panels for Gicheha Community borehole | Solar Panels for Gicheha Community borehole procured and installed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4577 | NAIVASHA MUNICIPALITY | NAIVASHA MUNICIPALITY | N/A | 2021/22 | 2021/22 | N/A | 2000000 | 0 | 2000000 | N/A | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
4003 | Beautification of Naivasha CBD and Installation of solid waste management facilities | Beautification of Naivasha CBD and Installation of solid waste management facilities | To implement beautification of naivasha cbd and installation of solid waste management facilities for improved service delivery | Beautification of Naivasha CBD and Installation of solid waste management facilities completed | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4577 | NAIVASHA MUNICIPALITY | NAIVASHA MUNICIPALITY | N/A | 2021/22 | 2021/22 | 2021/22 | 5000000 | 0 | 5000000 | N/A | N/A | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4004 | Naivasha Municipal Services | Consultancy services for Construction of Naivasha Market Phase 2 | To provide professional services for Construction of Naivasha Market Phase 2 | Professional services for Construction of Naivasha Market Phase 2 delivered | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4577 | NAIVASHA MUNICIPALITY | NAIVASHA MUNICIPALITY | N/A | 2019/20 | 2019/20 | N/A | 13000000 | 0 | 0 | N/A | N/A | 0 | 1125125.82 | 0 | 0 | 0 | 246096145 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4005 | Naivasha Municipal Services | Consultancy services for Rehabilitation of Naivasha Municipal Park | To provide professional services for Rehabilitation of Naivasha Municipal Park | Professional services for Rehabilitation of Naivasha Municipal Park delivered | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4577 | NAIVASHA MUNICIPALITY | NAIVASHA MUNICIPALITY | N/A | 2019/20 | 2019/20 | N/A | 1845493 | 1845493 | 0 | N/A | N/A | 0 | 1845493 | 0 | 0 | 0 | 246096145 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4006 | Mashindano Road and Drainage, CBD roads tarmacking and drainage and streetlights | Mashindano Road and Drainage, CBD roads tarmacking and drainage and streetlights | To implement mashindano road and drainage, cbd roads tarmacking and drainage and streetlights for improved service delivery | Mashindano Road and Drainage, CBD roads tarmacking and drainage and streetlights completed | 3110499 | Construction of Roads - Other | HQ | HQ | -0.173672, 35.862823 | 4577 | NAKURU MUNICIPALITY | NAKURU MUNICIPALITY | N/A | 2021/22 | 2021/22 | 2021/22 | 99768411.4 | 49768411.4 | 0 | N/A | N/A | 0 | 56768411.4 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4007 | Mbugua and Mbugua Road and drainage | Mbugua and Mbugua Road and drainage | To implement mbugua and mbugua road and drainage for improved service delivery | Mbugua and Mbugua Road and drainage completed | 3110499 | Construction of Roads - Other | HQ | HQ | -0.173672, 35.862823 | 4577 | NAKURU MUNICIPALITY | NAKURU MUNICIPALITY | N/A | 2021/22 | 2021/22 | 2021/22 | 60000000 | 60000000 | 0 | N/A | N/A | 0 | 60000000 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4008 | Proposed construction of Free Area loop road 1.2km | Proposed construction of Free Area loop road 1.2km | To undertake the proposed construction of Free Area loop road 1.2km | Proposed construction of Free Area loop road 1.2km implemented | 3110499 | Construction of Roads - Other | HQ | HQ | -0.173672, 35.862823 | 4577 | NAKURU MUNICIPALITY | NAKURU MUNICIPALITY | N/A | 2019/20 | 2019/20 | 2019/20 | 60334575 | 60334575 | 0 | N/A | N/A | 0 | 54334575 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4009 | Proposed construction of Kipchoge Keino road, Matundu Road and Crater Climb | Proposed construction of Kipchoge Keino road, Matundu Road and Crater Climb | To undertake the proposed construction of Kipchoge Keino road, Matundu Road and Crater Climb | Proposed construction of Kipchoge Keino road, Matundu Road and Crater Climb implemented | 3110499 | Construction of Roads - Other | HQ | HQ | -0.173672, 35.862823 | 4577 | NAKURU MUNICIPALITY | NAKURU MUNICIPALITY | N/A | 2019/20 | 2019/20 | 2019/20 | 105163195 | 0 | 0 | N/A | N/A | 0 | 105163195 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4010 | Recarpeting and drainage maintenance of Kakamega Road | Recarpeting and drainage maintenance of Kakamega Road | To upgrade and drainage maintenance of Kakamega Road through tarmacking for improved road connectivity | And drainage maintenance of Kakamega Road tarmacked and upgraded | 3110499 | Construction of Roads - Other | HQ | HQ | -0.173672, 35.862823 | 4577 | NAKURU MUNICIPALITY | NAKURU MUNICIPALITY | N/A | 2021/22 | 2021/22 | 2021/22 | 6800000 | 6800000 | 6800000 | N/A | N/A | 6800000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4011 | Recarpeting of bargain road | Recarpeting of bargain road | To upgrade bargain road through tarmacking for improved road connectivity | Bargain road tarmacked and upgraded | 3110499 | Construction of Roads - Other | HQ | HQ | -0.173672, 35.862823 | 4577 | NAKURU MUNICIPALITY | NAKURU MUNICIPALITY | N/A | 2021/22 | 2021/22 | 2021/22 | 6000000 | 6000000 | 6000000 | N/A | N/A | 6000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4012 | Road Tarmacking - Tarmacking of 1.12km of Nanyuki road off Mashindano road to Agape Church, Thika road off Mashindano road to Lake view primary and Kibezi road off Othaya road to Kisumu road | Road Tarmacking - Tarmacking of 1.12km of Nanyuki road off Mashindano road to Agape Church, Thika road off Mashindano road to Lake view primary and Kibezi road off Othaya road to Kisumu road | To implement road tarmacking - tarmacking of 1.12km of nanyuki road off mashindano road to agape church, thika road off mashindano road to lake view primary and kibezi road off othaya road to kisumu road for improved service delivery | Road Tarmacking - Tarmacking of 1.12km of Nanyuki road off Mashindano road to Agape Church, Thika road off Mashindano road to Lake view primary and Kibezi road off Othaya road to Kisumu road completed | 3110499 | Construction of Roads - Other | HQ | HQ | -0.173672, 35.862823 | 4577 | NAKURU MUNICIPALITY | NAKURU MUNICIPALITY | N/A | 2021/22 | 2021/22 | 2021/22 | 52600000 | 50400000 | 0 | N/A | N/A | 0 | 52600000 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4013 | Naivasha Municipal Services | Construction of the road behind Standard Chartered Bank, behind Gilanis to KPLC road and street lights installation and repair works within the Municipality | To construct the road behind Standard Chartered Bank, behind Gilanis to KPLC road and street lights installation and repair works within the Municipality | The road behind Standard Chartered Bank, behind Gilanis to KPLC road and street lights installation and repair works within the Municipality constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4577 | NAKURU MUNICIPALITY | NAKURU MUNICIPALITY | N/A | 2021/22 | 2021/22 | N/A | 60000000 | 0 | 0 | N/A | N/A | 0 | 60000000 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
4014 | Naivasha Municipal Services | Lower Mburu Gichua, Flamingo and Kivumbini drainage | To implement lower mburu gichua, flamingo and kivumbini drainage for improved service delivery | Lower Mburu Gichua, Flamingo and Kivumbini drainage completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4577 | NAKURU MUNICIPALITY | NAKURU MUNICIPALITY | N/A | 2021/22 | 2021/22 | N/A | 50400000 | 0 | 0 | N/A | N/A | 0 | 50400000 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
4015 | Naivasha Municipal Services | Municipal drainage construction and repair at Kaptembwo and White House | To implement municipal drainage construction and repair at kaptembwo and white house for improved service delivery | Municipal drainage construction and repair at Kaptembwo and White House completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4577 | NAKURU MUNICIPALITY | NAKURU MUNICIPALITY | N/A | 2021/22 | 2021/22 | N/A | 12400000 | 0 | 6400000 | N/A | N/A | 6400000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
4016 | Naivasha Municipal Services | Municipal market sheds and repair works at Barut and Pipeline | To implement municipal market sheds and repair works at barut and pipeline for improved service delivery | Municipal market sheds and repair works at Barut and Pipeline completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4577 | NAKURU MUNICIPALITY | NAKURU MUNICIPALITY | N/A | 2021/22 | 2021/22 | N/A | 9000000 | 0 | 6000000 | N/A | N/A | 6000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
4017 | Naivasha Municipal Services | Municipal road marking and furniture works | To implement municipal road marking and furniture works for improved service delivery | Municipal road marking and furniture works completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4577 | NAKURU MUNICIPALITY | NAKURU MUNICIPALITY | N/A | 2021/22 | 2021/22 | N/A | 4300000 | 4300000 | 4300000 | N/A | N/A | 4300000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
4018 | Naivasha Municipal Services | Municipality solid waste collection bins (estates and neighbourhood) | To implement municipality solid waste collection bins (estates and neighbourhood) for improved service delivery | Municipality solid waste collection bins (estates and neighbourhood) completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4577 | NAKURU MUNICIPALITY | NAKURU MUNICIPALITY | N/A | 2021/22 | 2021/22 | N/A | 4500000 | 2500000 | 2500000 | N/A | N/A | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
4019 | Naivasha Municipal Services | Proposed Construction of Afraha Stadium Phase 1 | To undertake the proposed Construction of Afraha Stadium Phase 1 | Proposed Construction of Afraha Stadium Phase 1 implemented | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4577 | NAKURU MUNICIPALITY | NAKURU MUNICIPALITY | N/A | 2019/20 | 2019/20 | N/A | 348000000 | 219603423 | 0 | N/A | N/A | 0 | 219603423 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
4020 | Naivasha Municipal Services | Proposed NMT, streetlighting and drainage within Nakuru CBD | To undertake the proposed NMT, streetlighting and drainage within Nakuru CBD | Proposed NMT, streetlighting and drainage within Nakuru CBD implemented | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4577 | NAKURU MUNICIPALITY | NAKURU MUNICIPALITY | N/A | 2019/20 | 2019/20 | N/A | 95000000 | 95000000 | 0 | N/A | N/A | 0 | 85000000 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
4021 | Naivasha Municipal Services | Public space furniture and wash stations works at Main bus park (Top Market) | To implement public space furniture and wash stations works at main bus park (top market) for improved service delivery | Public space furniture and wash stations works at Main bus park (Top Market) completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4577 | NAKURU MUNICIPALITY | NAKURU MUNICIPALITY | N/A | 2021/22 | 2021/22 | N/A | 2000000 | 2000000 | 2000000 | N/A | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
4022 | CBD street lighting and repair works | CBD street lighting and repair works | To implement cbd street lighting and repair works for improved service delivery | CBD street lighting and repair works completed | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4577 | NAKURU MUNICIPALITY | NAKURU MUNICIPALITY | N/A | 2021/22 | 2021/22 | 2021/22 | 8000000 | 8000000 | 8000000 | N/A | N/A | 8000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4023 | Completion of Afraha Stadium consultancy fee | Completion of Afraha Stadium consultancy fee | To complete Afraha Stadium consultancy fee | Afraha Stadium consultancy fee completed | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4577 | NAKURU MUNICIPALITY | NAKURU MUNICIPALITY | N/A | 2021/22 | 2021/22 | 2021/22 | 15000000 | 15000000 | 0 | N/A | N/A | 0 | 15000000 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | Yes | Done | Yes | Done | Yes | Done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4024 | Naivasha Municipal Services | Consultancy services (ESIA and design) for proposed construction of Kipchoge Keino. | To provide professional services for (ESIA and design) for proposed construction of Kipchoge Keino | Professional services for (ESIA and design) for proposed construction of Kipchoge Keino delivered | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4577 | NAKURU MUNICIPALITY | NAKURU MUNICIPALITY | N/A | 2019/20 | 2019/20 | N/A | 5469903 | 5469903 | 0 | N/A | N/A | 0 | 5469903 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4025 | Consultancy services for design documentation supervision for construction of non motorised transport street lighting and drainage in Nakuru CBD | Consultancy services for design documentation supervision for construction of non motorised transport street lighting and drainage in Nakuru CBD | To provide professional services for design documentation supervision for construction of non motorised transport street lighting and drainage in Nakuru CBD | Professional services for design documentation supervision for construction of non motorised transport street lighting and drainage in Nakuru CBD delivered | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4577 | NAKURU MUNICIPALITY | NAKURU MUNICIPALITY | N/A | 2019/20 | 2019/20 | 2019/20 | 4477000 | 2399700 | 0 | N/A | N/A | 0 | 2399700 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4026 | Consultancy services for provision of environmental and social impact assessment on construction of free area loop road in Nakuru county | Consultancy services for provision of environmental and social impact assessment on construction of free area loop road in Nakuru county | To provide professional services for provision of environmental and social impact assessment on construction of free area loop road in Nakuru county | Professional services for provision of environmental and social impact assessment on construction of free area loop road in Nakuru county delivered | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4577 | NAKURU MUNICIPALITY | NAKURU MUNICIPALITY | N/A | 2019/20 | 2019/20 | 2019/20 | 1461020 | 876612 | 0 | N/A | N/A | 0 | 876612 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4027 | Consultancy services for provision of environmental and social impact assessment on construction of non motorised transport streetlighting and drainage within Nakuru CBD. | Consultancy services for provision of environmental and social impact assessment on construction of non motorised transport streetlighting and drainage within Nakuru CBD. | To provide professional services for provision of environmental and social impact assessment on construction of non motorised transport streetlighting and drainage within Nakuru CBD | Professional services for provision of environmental and social impact assessment on construction of non motorised transport streetlighting and drainage within Nakuru CBD delivered | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4577 | NAKURU MUNICIPALITY | NAKURU MUNICIPALITY | N/A | 2019/20 | 2019/20 | 2019/20 | 1818300 | 1090980 | 0 | N/A | N/A | 0 | 1090980 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4028 | Counterpart funding for UN Habitat Municipal Vision 2050 Programme | Counterpart funding for UN Habitat Municipal Vision 2050 Programme | To implement counterpart funding for un habitat municipal vision 2050 programme for improved service delivery | Counterpart funding for UN Habitat Municipal Vision 2050 Programme completed | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4577 | NAKURU MUNICIPALITY | NAKURU MUNICIPALITY | N/A | 2021/22 | 2021/22 | 2021/22 | 10000000 | 5000000 | 5000000 | N/A | N/A | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4029 | Design and ESIA consultancy (5% of 293,440,433) | Design and ESIA consultancy (5% of 293,440,433) | To implement design and esia consultancy (5% of 293,440,433) for improved service delivery | Design and ESIA consultancy (5% of 293,440,433) completed | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4577 | NAKURU MUNICIPALITY | NAKURU MUNICIPALITY | N/A | 2021/22 | 2021/22 | 2021/22 | 14672021.6 | 14672021.6 | 0 | N/A | N/A | 0 | 14672021.6 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4030 | Top Market floor rehabilitation | Top Market floor rehabilitation | To implement top market floor rehabilitation for improved service delivery | Top Market floor rehabilitation completed | 3111299 | Rehabilitation & Renovation - | HQ | HQ | -0.173672, 35.862823 | 4577 | NAKURU MUNICIPALITY | NAKURU MUNICIPALITY | N/A | 2021/22 | 2021/22 | 2021/22 | 10000000 | 10000000 | 10000000 | N/A | N/A | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4031 | Establishment of a Legal Resource Centre | Establishment of a Legal Resource Centre | To implement establishment of a legal resource centre for improved service delivery | Establishment of a Legal Resource Centre completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | -0.173672, 35.862823 | 4579 | OFFICE OF THE COUNTY ATTORNEY | OFFICE OF THE COUNTY ATTORNEY | N/A | 2023/24 | 2023/24 | 2023/24 | 6000000 | 4000000 | 4000000 | N/A | N/A | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4032 | Equipping of Legal Resource Centre | Equipping of Legal Resource Centre | To equip Legal Resource Centre with necessary facilities and equipment | Legal Resource Centre equipped | 3111109 | Purchase of Educational Aids and Related Equipment | HQ | HQ | -0.173672, 35.862823 | 4579 | OFFICE OF THE COUNTY ATTORNEY | OFFICE OF THE COUNTY ATTORNEY | N/A | 2024/25 | 2024/25 | 2024/25 | 6000000 | 3000000 | 3000000 | N/A | N/A | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4033 | Nakuru City Services | Conditional Fund -Kenya Urban Support Project (KUSP) | To implement conditional fund -kenya urban support project (kusp) for improved service delivery | Conditional Fund -Kenya Urban Support Project (KUSP) completed | 2640503 | N/A | HQ | HQ | N/A | 4580 | NAKURU CITY | NAKURU CITY | N/A | 2022/23 | 2022/23 | N/A | 3534474.2 | 0 | 0 | KUSP | N/A | 0 | 3534474.2 | 0 | 0 | 0 | 34979395 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4034 | Reroofing Of Old Town Hall | Reroofing Of Old Town Hall | To implement reroofing of old town hall for improved service delivery | Reroofing Of Old Town Hall completed | 3110302 | Refurbishment of Non-Residential Buildings | HQ | HQ | -0.173672, 35.862823 | 4580 | NAKURU CITY | NAKURU CITY | N/A | 2022/23 | 2022/23 | 2022/23 | 10000000 | 9239410 | 0 | N/A | N/A | 0 | 8478820 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4035 | Nakuru City Services | Mashindano Road and Drainage, CBD roads tarmacking and drainage and streetlights | To implement mashindano road and drainage, cbd roads tarmacking and drainage and streetlights for improved service delivery | Mashindano Road and Drainage, CBD roads tarmacking and drainage and streetlights completed | 3110499 | Construction of Roads - Other | HQ | HQ | N/A | 4580 | NAKURU CITY | NAKURU CITY | N/A | 2021/22 | 2021/22 | N/A | 99768411.4 | 2473995 | 0 | Grant | Grants | 0 | 2379495 | 0 | 0 | 0 | 49480935 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4036 | Nakuru City Services | Mbugua and Mbugua Road and drainage | To implement mbugua and mbugua road and drainage for improved service delivery | Mbugua and Mbugua Road and drainage completed | 3110499 | Construction of Roads - Other | HQ | HQ | N/A | 4580 | NAKURU CITY | NAKURU CITY | N/A | 2021/22 | 2021/22 | N/A | 60000000 | 21668259.1 | 0 | KUSP | KUSP | 0 | 20124374 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4037 | Nakuru City Services | Proposed construction of Free Area loop road 1.2km | To undertake the proposed construction of Free Area loop road 1.2km | Proposed construction of Free Area loop road 1.2km implemented | 3110499 | Construction of Roads - Other | HQ | HQ | N/A | 4580 | NAKURU CITY | NAKURU CITY | N/A | 2019/20 | 2019/20 | N/A | 60334575 | 5127888.68 | 0 | KUSP | KUSP | 0 | 5127888.68 | 13676171 | 266.7 | 13676171 | 60334575 | -8548282.32 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4038 | Nakuru City Services | Proposed construction of Kipchoge Keino road, Matundu Road and Crater Climb | To undertake the proposed construction of Kipchoge Keino road, Matundu Road and Crater Climb | Proposed construction of Kipchoge Keino road, Matundu Road and Crater Climb implemented | 3110499 | Construction of Roads - Other | HQ | HQ | N/A | 4580 | NAKURU CITY | NAKURU CITY | N/A | 2019/20 | 2019/20 | N/A | 105163195 | 13676170.66 | 0 | KUSP | KUSP | 0 | 13676170.66 | 13676171 | 100 | 13676171 | 84727500 | -0.34 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4039 | Nakuru City Services | Recarpeting and drainage maintenance of Kakamega Road | To upgrade and drainage maintenance of Kakamega Road through tarmacking for improved road connectivity | And drainage maintenance of Kakamega Road tarmacked and upgraded | 3110499 | Construction of Roads - Other | HQ | HQ | N/A | 4580 | NAKURU CITY | NAKURU CITY | N/A | 2021/22 | 2021/22 | N/A | 6800000 | 3286086 | 3286086 | Equitable | N/A | 3286086 | 0 | 3323814 | 101.1 | 3323814 | 3286086 | -37728 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4040 | Nakuru City Services | Recarpeting of bargain road | To upgrade bargain road through tarmacking for improved road connectivity | Bargain road tarmacked and upgraded | 3110499 | Construction of Roads - Other | HQ | HQ | N/A | 4580 | NAKURU CITY | NAKURU CITY | N/A | 2021/22 | 2021/22 | N/A | 6000000 | 5613160 | 5613160 | Equitable | N/A | 5613160 | 0 | 3323814 | 59.2 | 3323814 | 5613160 | 2289346 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4041 | Nakuru City Services | Rehabilitation of access roads to Baringo road | To rehabilitate access roads to Baringo road to restore functionality | Access roads to Baringo road rehabilitated | 3110499 | Construction of Roads - Other | HQ | HQ | N/A | 4580 | NAKURU CITY | NAKURU CITY | N/A | 2023/24 | 2023/24 | N/A | 4000000 | 3000000 | 3812827 | KUSP | KUSP | 3812827 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4042 | Nakuru City Services | Construction Of Market Shed at Lion Hill | To construct Market Shed at Lion Hill | Market Shed at Lion Hill constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4580 | NAKURU CITY | NAKURU CITY | N/A | 2022/23 | 2022/23 | N/A | 3000000 | 0 | 3000000 | Equitable | Equitble | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4043 | Nakuru City Services | Construction of the road behind Standard Chartered Bank, behind Gilanis to KPLC road and street lights installation and repair works within the Municipality | To construct the road behind Standard Chartered Bank, behind Gilanis to KPLC road and street lights installation and repair works within the Municipality | The road behind Standard Chartered Bank, behind Gilanis to KPLC road and street lights installation and repair works within the Municipality constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4580 | NAKURU CITY | NAKURU CITY | N/A | 2021/22 | 2021/22 | N/A | 60000000 | 2480929 | 0 | Equitable | Equitble | 0 | 2480929 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4044 | Nakuru City Services | Installation and Maintenance Of Streetlights Within the City | To install and Maintenance Of Streetlights Within the City | And Maintenance Of Streetlights Within the City installed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4580 | NAKURU CITY | NAKURU CITY | N/A | 2022/23 | 2022/23 | N/A | 6000000 | 0 | 0 | N/A | N/A | 0 | 6000000 | 0 | 0 | 0 | 1000000 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
4045 | Nakuru City Services | Installation of Street lights for markets, matatu stages and CBD | To install Street lights for markets, matatu stages and CBD | Street lights for markets, matatu stages and CBD installed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4580 | NAKURU CITY | NAKURU CITY | N/A | 2024/25 | 2024/25 | N/A | 40000000 | 40000000 | 14031983 | N/A | N/A | 14031983 | 0 | 0 | 0 | 0 | 0 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
4046 | Nakuru City Services | Installation Of Streetlights Within the City | To improve lighting and safety through installation of solar streetlights at Within the City | Solar streetlights installed at Within the City | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4580 | NAKURU CITY | NAKURU CITY | N/A | 2023/24 | 2023/24 | N/A | 6438100.1 | 3200000 | 0 | N/A | N/A | 0 | 6438100.1 | 0 | 0 | 0 | 1000000 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
4047 | Nakuru City Services | Lower Mburu Gichua, Flamingo and Kivumbini drainage | To implement lower mburu gichua, flamingo and kivumbini drainage for improved service delivery | Lower Mburu Gichua, Flamingo and Kivumbini drainage completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4580 | NAKURU CITY | NAKURU CITY | N/A | 2021/22 | 2021/22 | N/A | 50400000 | 18456300.15 | 0 | Equitable | Equitble | 0 | 18456300.15 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4048 | Nakuru City Services | Municipal drainage construction and repair at Kaptembwo and White House | To implement municipal drainage construction and repair at kaptembwo and white house for improved service delivery | Municipal drainage construction and repair at Kaptembwo and White House completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4580 | NAKURU CITY | NAKURU CITY | N/A | 2021/22 | 2021/22 | N/A | 12400000 | 3239279 | 3239279 | Equitable | N/A | 3239279 | 0 | 0 | 0 | 0 | 6101750 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4049 | Nakuru City Services | Municipal road marking and furniture works | To implement municipal road marking and furniture works for improved service delivery | Municipal road marking and furniture works completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4580 | NAKURU CITY | NAKURU CITY | N/A | 2021/22 | 2021/22 | 2021/22 | 4300000 | 4200360 | 4200360 | Equitable | Equtable | 4200360 | 0 | 4167767 | 99.2 | 4167767 | 4200360 | 32593 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4050 | Nakuru City Services | Municipality solid waste collection bins (estates and neighbourhood) | To implement municipality solid waste collection bins (estates and neighbourhood) for improved service delivery | Municipality solid waste collection bins (estates and neighbourhood) completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4580 | NAKURU CITY | NAKURU CITY | N/A | 2021/22 | 2021/22 | 2021/22 | 4500000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 2400000 | 100 | 2400000 | 2400000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4051 | Nakuru City Services | Proposed Construction of Afraha Stadium Phase 1 | To undertake the proposed Construction of Afraha Stadium Phase 1 | Proposed Construction of Afraha Stadium Phase 1 implemented | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4580 | NAKURU CITY | NAKURU CITY | N/A | 2019/20 | 2019/20 | 2019/20 | 348000000 | 0 | 0 | KUSP | KUSP | 0 | 23034546 | 17500000 | 100 | 17500000 | 60334575 | -17500000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4052 | Nakuru City Services | Proposed NMT, streetlighting and drainage within Nakuru CBD | To undertake the proposed NMT, streetlighting and drainage within Nakuru CBD | Proposed NMT, streetlighting and drainage within Nakuru CBD implemented | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4580 | NAKURU CITY | NAKURU CITY | N/A | 2019/20 | 2019/20 | N/A | 95000000 | 17836863 | 0 | N/A | N/A | 0 | 17836863 | 7940100 | 44.5 | 7940100 | 0 | 9896763 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
4053 | Nakuru City Services | Purchase of tartan track for Afraha Stadium - counterpart funding | To procure tartan track for Afraha Stadium - counterpart funding | Tartan track for Afraha Stadium - counterpart funding procured | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4580 | NAKURU CITY | NAKURU CITY | N/A | 2022/23 | 2022/23 | N/A | 100000000 | 0 | 12365750 | Equitable | Equitble | 12365750 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4054 | Nakuru City Services | Purchase of tartan track for Afraha Stadium | To procure tartan track for Afraha Stadium | Tartan track for Afraha Stadium procured | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4580 | NAKURU CITY | NAKURU CITY | N/A | 2022/23 | 2022/23 | N/A | 100000000 | 54839125 | 0 | Equitable | Equitble | 0 | 54000000 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4055 | Nakuru City Services | Rehabilitation of drainages within the CBD | To rehabilitate drainages within the CBD to restore functionality | Drainages within the CBD rehabilitated | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4580 | NAKURU CITY | NAKURU CITY | N/A | 2024/25 | 2024/25 | N/A | 15000000 | 15000000 | 5000000 | N/A | N/A | 5000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
4056 | Nakuru City Services | Temporary Sanitation Facility at Menengai Garden | To implement temporary sanitation facility at menengai garden for improved service delivery | Temporary Sanitation Facility at Menengai Garden completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4580 | NAKURU CITY | NAKURU CITY | N/A | 2023/24 | 2023/24 | N/A | 1500000 | 1500000 | 1420485 | Equitable | Equitble | 1420485 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4057 | Nakuru City Services | Completion of Afraha Stadium consultancy fee | To complete Afraha Stadium consultancy fee | Afraha Stadium consultancy fee completed | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4580 | NAKURU CITY | NAKURU CITY | N/A | 2021/22 | 2021/22 | N/A | 15000000 | 1050000 | 0 | Equitable | N/A | 0 | 1050000 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4058 | Nakuru City Services | Consultancy services (ESIA and design) for proposed construction of Kipchoge Keino. | To provide professional services for (ESIA and design) for proposed construction of Kipchoge Keino | Professional services for (ESIA and design) for proposed construction of Kipchoge Keino delivered | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4580 | NAKURU CITY | NAKURU CITY | N/A | 2019/20 | 2019/20 | N/A | 5469903 | 3973545 | 0 | Grant | Grants | 0 | 3973545 | 1496358 | 37.7 | 1496358 | 3973545 | 2477187 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4059 | Nakuru City Services | Consultancy services for design documentation supervision for construction of non motorised transport street lighting and drainage in Nakuru CBD | To provide professional services for design documentation supervision for construction of non motorised transport street lighting and drainage in Nakuru CBD | Professional services for design documentation supervision for construction of non motorised transport street lighting and drainage in Nakuru CBD delivered | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4580 | NAKURU CITY | NAKURU CITY | N/A | 2019/20 | 2019/20 | N/A | 4477000 | 841704 | 0 | Grant | Grants | 0 | 841704 | 1557996 | 185.1 | 1557996 | 841704 | -716292 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4060 | Nakuru City Services | Consultancy services for provision of environmental and social impact assessment on construction of non motorised transport streetlighting and drainage within Nakuru CBD. | To provide professional services for provision of environmental and social impact assessment on construction of non motorised transport streetlighting and drainage within Nakuru CBD | Professional services for provision of environmental and social impact assessment on construction of non motorised transport streetlighting and drainage within Nakuru CBD delivered | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4580 | NAKURU CITY | NAKURU CITY | N/A | 2019/20 | 2019/20 | N/A | 1818300 | 148450 | 0 | Grant | Grants | 0 | 148450 | 942530 | 634.9 | 942530 | 148450 | -794080 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4061 | Nakuru City Services | Counterpart funding for UN Habitat Municipal Vision 2050 Programme | To implement counterpart funding for un habitat municipal vision 2050 programme for improved service delivery | Counterpart funding for UN Habitat Municipal Vision 2050 Programme completed | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4580 | NAKURU CITY | NAKURU CITY | N/A | 2021/22 | 2021/22 | N/A | 10000000 | 0 | 1454100 | Equitable | N/A | 1454100 | 0 | 969400 | 100 | 969400 | 1454100 | -969400 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4062 | Nakuru City Services | Design and ESIA consultancy (5% of 293,440,433) | To implement design and esia consultancy (5% of 293,440,433) for improved service delivery | Design and ESIA consultancy (5% of 293,440,433) completed | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4580 | NAKURU CITY | NAKURU CITY | N/A | 2021/22 | 2021/22 | 2021/22 | 14672021.6 | 7660326 | 0 | KUSP | KUSP | 0 | 7660326 | 7660326 | 100 | 7660326 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4063 | Nakuru City Services | Establishment of a GIS and Data Centre for Nakuru City | To implement establishment of a gis and data centre for nakuru city for improved service delivery | Establishment of a GIS and Data Centre for Nakuru City completed | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4580 | NAKURU CITY | NAKURU CITY | N/A | 2023/24 | 2023/24 | N/A | 11000000 | 0 | 2392000 | N/A | N/A | 2392000 | 0 | 0 | 0 | 0 | 0 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
4064 | Nakuru City Services | Installation of litter bins within the City | To install litter bins within the City | Litter bins within the City installed | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4580 | NAKURU CITY | NAKURU CITY | N/A | 2022/23 | 2022/23 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4065 | Nakuru City Services | Solarization of Mlima Ugali Borehole | To implement solarization of mlima ugali borehole for improved service delivery | Solarization of Mlima Ugali Borehole completed | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4580 | NAKURU CITY | NAKURU CITY | N/A | 2022/23 | 2022/23 | N/A | 2885132 | 0 | 2885132 | Equitable | N/A | 2885132 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4066 | Top Market floor rehabilitation | Top Market floor rehabilitation | To implement top market floor rehabilitation for improved service delivery | Top Market floor rehabilitation completed | 3111299 | Rehabilitation & Renovation - | HQ | HQ | -0.173672, 35.862823 | 4580 | NAKURU CITY | NAKURU CITY | N/A | 2021/22 | 2021/22 | 2021/22 | 10000000 | 9601900 | 9601900 | N/A | N/A | 9601900 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4067 | Conditional grant on Aggregated Industrial Park Programme | Conditional grant on Aggregated Industrial Park Programme | To implement conditional grant on aggregated industrial park programme for economic growth and market access | Conditional grant on Aggregated Industrial Park Programme completed | 2630203 | N/A | HQ | HQ | -0.173672, 35.862823 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 250000000 | 100000000 | 0 | Conditional Grant | N/A | 0 | 366631578.9 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4068 | County Aggregation Centres and Industrial Parks counterpart funding | County Aggregation Centres and Industrial Parks counterpart funding | To implement county aggregation centres and industrial parks counterpart funding for economic growth and market access | County Aggregation Centres and Industrial Parks counterpart funding completed | 2630203 | N/A | HQ | HQ | -0.173672, 35.862823 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 198972616.4 | 250000000 | 448972616.4 | N/A | N/A | 448972616.4 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4069 | Development and Management of Markets | Construction of Tourism Management office at Lake Solai | To construct Tourism Management office at Lake Solai | Tourism Management office at Lake Solai constructed | 3110299 | Construction of Buildings - Ot | Rongai | Solai | 0.04827, 36.17021 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2024/25 | 2024/25 | 2025 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Humble Touch investment. Assessor remarks: The office needs equipment.
4070 | Refurbishment of Weights and measures building and extension of seized goods store. | Refurbishment of Weights and measures building and extension of seized goods store. | To implement refurbishment of weights and measures building and extension of seized goods store. for economic growth and market access | Refurbishment of Weights and measures building and extension of seized goods store. completed | 3110399 | Refurbishment of Buildgs - Oth | HQ | HQ | N/A | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2023/24 | 2023/24 | N/A | 4000000 | 1999300 | 1999300 | N/A | N/A | 1999300 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
4071 | Rehabilitation of Weights and Measures Office | Rehabilitation of Weights and Measures Office | To rehabilitate Weights and Measures Office to restore functionality | Weights and Measures Office rehabilitated | 3110399 | Refurbishment of Buildgs - Oth | HQ | HQ | N/A | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 4000000 | 2974300 | 2974300 | N/A | N/A | 2974300 | 0 | 2000000 | 67.2 | 2000000 | 18483845 | 974300 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4072 | Renovation and equipping of CO'S Office | Renovation and equipping of CO'S Office | To rehabilitate equipping of CO'S Office to restore functionality | Equipping of CO'S Office rehabilitated | 3110399 | Refurbishment of Buildgs - Oth | HQ | HQ | N/A | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2023/24 | 2023/24 | N/A | 10000000 | 1530890 | 942890 | N/A | N/A | 942890 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
4073 | Drilling, Equipping Karai Market Borehole and Construction of Water Tower at Naivasha East, Naivasha Sub County | Drilling, Equipping Karai Market Borehole and Construction of Water Tower at Naivasha East, Naivasha Sub County | To implement drilling, equipping karai market borehole and construction of water tower at naivasha east, naivasha sub county for economic growth and market access | Drilling, Equipping Karai Market Borehole and Construction of Water Tower at Naivasha East, Naivasha Sub County completed | 3110502 | Water Supplies and Sewerage | HQ | HQ | -0.173672, 35.862823 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 10000000 | 9968504 | 9968504 | N/A | N/A | 9968504 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4074 | Purchase of two (2) 10000 litres plastic water tanks and construction of water tower at Rongai Acacia Dairy Cooperative Society | Purchase of two (2) 10000 litres plastic water tanks and construction of water tower at Rongai Acacia Dairy Cooperative Society | To procure two (2) 10000 litres plastic water tanks and construction of water tower at Rongai Acacia Dairy Cooperative Society | Two (2) 10000 litres plastic water tanks and construction of water tower at Rongai Acacia Dairy Cooperative Society procured | 3110502 | Water Supplies and Sewerage | HQ | HQ | -0.173672, 35.862823 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 3000000 | 0 | 1434550 | N/A | N/A | 1434550 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4075 | Market Rehabilitation and Development | Construction of a toilet at Wanyororo Market, Bahati Market and Ahero Market | To construct a toilet at Wanyororo Market, Bahati Market and Ahero Market | A toilet at Wanyororo Market, Bahati Market and Ahero Market constructed | 3110504 | Other Infrastructure and Civil Works | Bahati | Bahati | -0.157108, 36.104851 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2022/23 | 2022/23 | N/A | 1800000 | 1789690 | 540230 | Equitable | N/A | 540230 | 0 | 1249460 | 69.8 | 1249460 | 540230 | 540230 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
4076 | Market Rehabilitation and Development | Construction of market sheds at Ahero and Wanyororo Markets | To construct market sheds at Ahero and Wanyororo Markets | Market sheds at Ahero and Wanyororo Markets constructed | 3110504 | Other Infrastructure and Civil Works | Bahati | Bahati | -0.157415, 36.105226 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2022/23 | 2022/23 | N/A | 2000000 | 0 | 1805990 | Equitable | N/A | 1805990 | 0 | 1249460 | 0 | 1249460 | 1805990 | 0 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Project properly done.
4077 | Market Rehabilitation and Development | Construction of chain link fence and a gate at Barut Market | To construct chain link fence and a gate at Barut Market | Chain link fence and a gate at Barut Market constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Barut | -0.324324, 36.054632 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2022/23 | 2022/23 | 2022 | 3000000 | 2800000 | 3000000 | Equitable | N/A | 3000000 | 0 | 1850000 | 66.1 | 1850000 | 3000000 | 950000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Lemyna works. Assessor remarks: The fencing is good.
4078 | Construction of market stalls at Barut center | Construction of market stalls at Barut center | To construct market stalls at Barut center | Market stalls at Barut center constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Barut | -0.324324, 36.054632 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2022/23 | 2022/23 | 2023 | 1500000 | 1472370 | 1472370 | Equitable | N/A | 1472370 | 0 | 1472370 | 100 | 1472370 | 1472370 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Amperi Limited. Assessor remarks: The stalls are in good working condition.
4079 | Fencing and construction of a gate at Kinamba Market | Fencing and construction of a gate at Kinamba Market | To secure and construction of a gate at Kinamba Market through fencing | And construction of a gate at Kinamba Market fenced and secured | 3110504 | Other Infrastructure and Civil Works | Naivasha | Biashara - Naivasha | -0.722662, 36.47459 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2023/24 | 2023/24 | 2024 | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 1893480 | 100 | 1893480 | 106520 | -1893480 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Fairly. Viable: Fairly. Contractor: Not known. Assessor remarks: Chain link needs replacement with stone walls..
4080 | Construction Of 15 Banana Stalls at Wakulima Market | Construction Of 15 Banana Stalls at Wakulima Market | To construct 15 Banana Stalls at Wakulima Market | 15 Banana Stalls at Wakulima Market constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | -0.285383, 36.077348 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 2100000 | 1898750 | 2100000 | Equitable | N/A | 2100000 | 0 | 4981650 | 262.4 | 4981650 | 2100000 | -3082900 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Need for more stalls.
4081 | Development and Management of Markets | Installation of Cabros floor at Section 58 Market | To install Cabros floor at Section 58 Market | Cabros floor at Section 58 Market installed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | -0.284012, 36.093776 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2024/25 | 2024/25 | 2024/25 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1889767 | 94.5 | 1889767 | 2000000 | 110233 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Wanjip general enterprises. Assessor remarks: Functional.
4082 | Development and Management of Markets | Raising of high roof at nyanya traders | To implement raising of high roof at nyanya traders for economic growth and market access | Raising of high roof at nyanya traders completed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | N/A | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2024/25 | 2024/25 | N/A | 1500000 | 0 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 1500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4083 | Development and Management of Markets | Renovation and installation of doors and grills at Muthurwa Market shed (Mashambani stage) | To rehabilitate installation of doors and grills at Muthurwa Market shed (Mashambani stage) to restore functionality | Installation of doors and grills at Muthurwa Market shed (Mashambani stage) rehabilitated | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | -0.284069, 36.075805 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2024/25 | 2024/25 | 2024/25 | 725000 | 725000 | 725000 | Equitable | N/A | 725000 | 0 | 0 | 0 | 0 | 725000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Lejomu enterprise limited. Assessor remarks: Meeting threshold.
4084 | Construction Of Market Stalls at Upper Dundori Center | Construction Of Market Stalls at Upper Dundori Center | To construct Market Stalls at Upper Dundori Center | Market Stalls at Upper Dundori Center constructed | 3110504 | Other Infrastructure and Civil Works | Bahati | Dundori | -0.255343, 36.233905 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2023/24 | 2023/24 | 2023/2024 | 1000000 | 998250 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Lahigs holdings. Assessor remarks: Electricity connection needed, not easily accessible.
4085 | Construction of Elementaita youth stalls | Construction of Elementaita youth stalls | To construct Elementaita youth stalls | Elementaita youth stalls constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Elementaita | -0.489341, 36.156986 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2020/21 | 2020/21 | N/A | 1400000 | 1299600 | 1299600 | Equitable | N/A | 1299600 | 0 | 3870671 | 297.8 | 3870671 | 1299600 | -2571071 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Veried.
4086 | Construction of market shades | Construction of market shades | To construct market shades | Market shades constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Gilgil | -0.504716, 36.328314 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 1925610 | 1925610 | Equitable | N/A | 1925610 | 0 | 1925610 | 100 | 1925610 | 1925610 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Cider collections. Assessor remarks: In good state.
4087 | Construction of Mitumba sheds in Gilgil Mitumba market | Construction of Mitumba sheds in Gilgil Mitumba market | To construct Mitumba sheds in Gilgil Mitumba market | Mitumba sheds in Gilgil Mitumba market constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Gilgil | -0.503915, 36.327841 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2022/23 | 2022/23 | 2023/24 | 4000000 | 3924356 | 3924356 | Equitable | N/A | 3924356 | 0 | 3924356 | 100 | 3924356 | 3924356 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: Yes. Assessor remarks: Demolished to pave way for ESP market.
4088 | Construction of youth lockups in Gilgil Ward | Construction of youth lockups in Gilgil Ward | To construct youth lockups in Gilgil Ward | Youth lockups in Gilgil Ward constructed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Gilgil | -0.499145, 36.322475 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 1300000 | 1202810 | 1202810 | Equitable | N/A | 1202810 | 0 | 1202810 | 100 | 1202810 | 1202810 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Raindrop contractors. Assessor remarks: Functional.
4089 | Development and Management of Markets | Gilgil market perimeter wall Construction | To implement gilgil market perimeter wall construction for economic growth and market access | Gilgil market perimeter wall Construction completed | 3110504 | Other Infrastructure and Civil Works | Gilgil | Gilgil | -0.504783, 36.328293 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2024/25 | 2024/25 | 2024/25 | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 0 | 0 | 0 | 4000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Ongoing.
4090 | Completion of Karai Market | Completion of Karai Market | To complete Karai Market | Karai Market completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2024/25 | 2024/25 | N/A | 20000000 | 20000000 | 20000000 | Equitable | N/A | 20000000 | 0 | 5989050 | 29.9 | 5989050 | 800000 | 14010950 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4091 | Completion of Kiptangwanyi Market existing Shed | Completion of Kiptangwanyi Market existing Shed | To complete Kiptangwanyi Market existing Shed | Kiptangwanyi Market existing Shed completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2022/23 | 2022/23 | N/A | 1000000 | 995000 | 995000 | Equitable | N/A | 995000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4092 | Completion of Njoro market sheds | Completion of Njoro market sheds | To complete Njoro market sheds | Njoro market sheds completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2022/23 | 2022/23 | N/A | 10000000 | 2999770 | 2999770 | Equitable | N/A | 2999770 | 0 | 5989050 | 199.7 | 5989050 | 800000 | -2989280 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4093 | Market Rehabilitation and Development | Construction of Market Sheds at Old Kijabe Town market in Mai Mahiu Ward | To construct Market Sheds at Old Kijabe Town market in Mai Mahiu Ward | Market Sheds at Old Kijabe Town market in Mai Mahiu Ward constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2023/24 | 2023/24 | N/A | 2936930 | 0 | 2936930 | N/A | N/A | 2936930 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
4094 | Construction of Muchorwe Market | Construction of Muchorwe Market | To construct Muchorwe Market | Muchorwe Market constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2024/25 | 2024/25 | N/A | 14000000 | 0 | 7000000 | Equitable | N/A | 7000000 | 0 | 0 | 0 | 0 | 800000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4095 | Construction of Naivasha Fish Market | Construction of Naivasha Fish Market | To construct Naivasha Fish Market | Naivasha Fish Market constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2020/21 | 2020/21 | N/A | 10000000 | 0 | 3631685 | Equitable | N/A | 3631685 | 0 | 0 | 0 | 0 | 800000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4096 | Construction of New Modern Markets | Construction of New Modern Markets | To construct New Modern Markets | New Modern Markets constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2023/24 | 2023/24 | N/A | 100000000 | 0 | 800000 | Equitable | N/A | 800000 | 0 | 0 | 0 | 0 | 800000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4097 | Market Rehabilitation and Development | Market rehabilitation | To implement market rehabilitation for economic growth and market access | Market rehabilitation completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2022/23 | 2022/23 | N/A | 15268250 | 580000 | 580000 | N/A | N/A | 580000 | 0 | 2700072 | 465.5 | 2700072 | 580000 | -2120072 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4098 | Market Rehabilitation and Development | Proposed completion of existing Kiptangwany market shed and construction of 3No. door toilets at Elementaita Ward, Gilgil Sub-County. | To undertake the proposed completion of existing Kiptangwany market shed and construction of 3No. door toilets at Elementaita Ward, Gilgil Sub-County | Proposed completion of existing Kiptangwany market shed and construction of 3No. door toilets at Elementaita Ward, Gilgil Sub-County implemented | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2023/24 | 2023/24 | N/A | 1800000 | 0 | 1698240 | N/A | N/A | 1698240 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
4099 | Market Rehabilitation and Development | Proposed construction of 4 no. door toilets at Eburru trading centre market in Eburru Mbaruk Ward, Gilgil Sub-County. | To undertake the proposed construction of 4 no. door toilets at Eburru trading centre market in Eburru Mbaruk Ward, Gilgil Sub-County | Proposed construction of 4 no. door toilets at Eburru trading centre market in Eburru Mbaruk Ward, Gilgil Sub-County implemented | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2023/24 | 2023/24 | N/A | 950000 | 0 | 924870 | N/A | N/A | 924870 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
4100 | Market Rehabilitation and Development | Proposed Construction of 4 No. Market Shed, Pavilion, Animal Paddocks, 2 No Office Block and Chain link Fencing at Banita Market, Soin Ward, Rongai Sub County | To undertake the proposed Construction of 4 No. Market Shed, Pavilion, Animal Paddocks, 2 No Office Block and Chain link Fencing at Banita Market, Soin Ward, Rongai Sub County | Proposed Construction of 4 No. Market Shed, Pavilion, Animal Paddocks, 2 No Office Block and Chain link Fencing at Banita Market, Soin Ward, Rongai Sub County implemented | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2018/19 | 2020/21 | N/A | 10283413.1 | 1435479 | 1435479 | N/A | N/A | 1435479 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
4101 | Market Rehabilitation and Development | Proposed Construction of 4 No. Market Shed, Pavillion, Animal Paddocks, 2 No Office Block and Chainlink Fencing at Banita Market, Soin Ward, Rongai Sub County | To undertake the proposed Construction of 4 No. Market Shed, Pavillion, Animal Paddocks, 2 No Office Block and Chainlink Fencing at Banita Market, Soin Ward, Rongai Sub County | Proposed Construction of 4 No. Market Shed, Pavillion, Animal Paddocks, 2 No Office Block and Chainlink Fencing at Banita Market, Soin Ward, Rongai Sub County implemented | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2018/19 | 2020/21 | N/A | 10283413.1 | 1435479 | 1435479 | N/A | N/A | 1435479 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
4102 | Market Rehabilitation and Development | Proposed construction of 4 no. toilet door at Kanyotu Market in Waseges Ward, Subukia Sub-County. | To undertake the proposed construction of 4 no. toilet door at Kanyotu Market in Waseges Ward, Subukia Sub-County | Proposed construction of 4 no. toilet door at Kanyotu Market in Waseges Ward, Subukia Sub-County implemented | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2023/24 | 2023/24 | N/A | 950000 | 0 | 949995 | N/A | N/A | 949995 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
4103 | Market Rehabilitation and Development | Proposed construction of 4 toilets door at Raplands Market in Olkaria Ward, Naivasha Sub-County. | To undertake the proposed construction of 4 toilets door at Raplands Market in Olkaria Ward, Naivasha Sub-County | Proposed construction of 4 toilets door at Raplands Market in Olkaria Ward, Naivasha Sub-County implemented | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2023/24 | 2023/24 | N/A | 950000 | 0 | 899995 | N/A | N/A | 899995 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
4104 | Market Rehabilitation and Development | Proposed construction of 4No. toilet door at Narasha Market in Olkaria Ward, Naivasha Sub-County. | To undertake the proposed construction of 4No. toilet door at Narasha Market in Olkaria Ward, Naivasha Sub-County | Proposed construction of 4No. toilet door at Narasha Market in Olkaria Ward, Naivasha Sub-County implemented | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2023/24 | 2023/24 | N/A | 950000 | 0 | 865120 | N/A | N/A | 865120 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
4105 | Market Rehabilitation and Development | Proposed construction of 4No. toilet door at Polepole Market in Waseges Ward, Subukia Sub-County. | To undertake the proposed construction of 4No. toilet door at Polepole Market in Waseges Ward, Subukia Sub-County | Proposed construction of 4No. toilet door at Polepole Market in Waseges Ward, Subukia Sub-County implemented | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2023/24 | 2023/24 | N/A | 950000 | 0 | 897300 | N/A | N/A | 897300 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
4106 | Market Rehabilitation and Development | Proposed construction of 4No. toilets door at Simboyon Market in Waseges Ward, Subukia Sub-County. | To undertake the proposed construction of 4No. toilets door at Simboyon Market in Waseges Ward, Subukia Sub-County | Proposed construction of 4No. toilets door at Simboyon Market in Waseges Ward, Subukia Sub-County implemented | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2023/24 | 2023/24 | N/A | 950000 | 0 | 949995 | N/A | N/A | 949995 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
4107 | Market Rehabilitation and Development | Proposed construction of a Market Shed at City stage London ward Nakuru west Sub-County. | To undertake the proposed construction of a Market Shed at City stage London ward Nakuru west Sub-County | Proposed construction of a Market Shed at City stage London ward Nakuru west Sub-County implemented | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2023/24 | 2023/24 | N/A | 2200000 | 0 | 1975550 | N/A | N/A | 1975550 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
4108 | Market Rehabilitation and Development | Proposed construction of a Market Shed at Naivasha modern Market Viwandani ward, Naivasha Sub-County. | To undertake the proposed construction of a Market Shed at Naivasha modern Market Viwandani ward, Naivasha Sub-County | Proposed construction of a Market Shed at Naivasha modern Market Viwandani ward, Naivasha Sub-County implemented | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2023/24 | 2023/24 | N/A | 3000000 | 0 | 2973532 | N/A | N/A | 2973532 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
4109 | Market Rehabilitation and Development | Proposed construction of Bahati Market Sheds at Bahati Ward, Bahati Sub-County. | To undertake the proposed construction of Bahati Market Sheds at Bahati Ward, Bahati Sub-County | Proposed construction of Bahati Market Sheds at Bahati Ward, Bahati Sub-County implemented | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2023/24 | 2023/24 | N/A | 3000000 | 0 | 2915160 | N/A | N/A | 2915160 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
4110 | Market Rehabilitation and Development | Proposed fencing of Njoro Market and installation of a gate in Njoro Ward, Njoro Sub County. | To undertake the proposed fencing of Njoro Market and installation of a gate in Njoro Ward, Njoro Sub County | Proposed fencing of Njoro Market and installation of a gate in Njoro Ward, Njoro Sub County implemented | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2023/24 | 2023/24 | N/A | 2200000 | 0 | 1995980 | N/A | N/A | 1995980 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
4111 | Market Rehabilitation and Development | Proposed Renovation of Nasher Market in Biashara Ward Nakuru Town East subcounty | To undertake the proposed Renovation of Nasher Market in Biashara Ward Nakuru Town East subcounty | Proposed Renovation of Nasher Market in Biashara Ward Nakuru Town East subcounty implemented | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2023/24 | 2023/24 | N/A | 2200000 | 0 | 2000000 | N/A | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
4112 | Market Rehabilitation and Development | Proposed Renovation of wakulima market in Biashara Nakuru town East | To undertake the proposed Renovation of wakulima market in Biashara Nakuru town East | Proposed Renovation of wakulima market in Biashara Nakuru town East implemented | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2023/24 | 2023/24 | N/A | 2000000 | 0 | 1900000 | N/A | N/A | 1900000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
4113 | Rehabilitation of Bus Station/Stage Office | Rehabilitation of Bus Station/Stage Office | To rehabilitate Bus Station/Stage Office to restore functionality | Bus Station/Stage Office rehabilitated | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 751000 | 751000 | 751000 | Equitable | N/A | 751000 | 0 | 2000000 | 266.3 | 2000000 | 18483845 | -1249000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4114 | Rehabilitation of coffee factory at Mutungati Farmers’ Cooperative in Bahati | Rehabilitation of coffee factory at Mutungati Farmers’ Cooperative in Bahati | To rehabilitate coffee factory at Mutungati Farmers’ Cooperative in Bahati to restore functionality | Coffee factory at Mutungati Farmers’ Cooperative in Bahati rehabilitated | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2021/22 | 2021/22 | N/A | 6000000 | 2909460 | 601735 | Equitable | N/A | 601735 | 0 | 0 | 0 | 0 | 0 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
4115 | Development and Management of Markets | Rehabilitation of existing markets | To rehabilitate existing markets to restore functionality | Existing markets rehabilitated | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2023/24 | 2023/24 | N/A | 25000000 | 12800000 | 12800000 | Equitable | N/A | 12800000 | 0 | 5989050 | 46.8 | 5989050 | 18483845 | 6810950 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4116 | Rehabilitation of Gilgil Market | Rehabilitation of Gilgil Market | To rehabilitate Gilgil Market to restore functionality | Gilgil Market rehabilitated | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2022/23 | 2022/23 | N/A | 1747460 | 1747460 | 1747460 | Equitable | N/A | 1747460 | 0 | 5989050 | 342.7 | 5989050 | 18483845 | -4241590 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4117 | Rehabilitation of Molo Market | Rehabilitation of Molo Market | To rehabilitate Molo Market to restore functionality | Molo Market rehabilitated | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2022/23 | 2022/23 | N/A | 3533200 | 3533200 | 3533200 | Equitable | N/A | 3533200 | 0 | 5989050 | 169.5 | 5989050 | 18483845 | -2455850 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4118 | Rehabilitation of Rajuela Market | Rehabilitation of Rajuela Market | To rehabilitate Rajuela Market to restore functionality | Rajuela Market rehabilitated | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2022/23 | 2022/23 | N/A | 506100 | 506100 | 506100 | Equitable | N/A | 506100 | 0 | 5989050 | 1183.4 | 5989050 | 18483845 | -5482950 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4119 | Rehabilitation of Rongai Market | Rehabilitation of Rongai Market | To rehabilitate Rongai Market to restore functionality | Rongai Market rehabilitated | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2022/23 | 2022/23 | N/A | 115000 | 115000 | 115000 | Equitable | N/A | 115000 | 0 | 5989050 | 5207.9 | 5989050 | 18483845 | -5874050 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4120 | Rehabilitation of Wakulima Market | Rehabilitation of Wakulima Market | To rehabilitate Wakulima Market to restore functionality | Wakulima Market rehabilitated | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2022/23 | 2022/23 | N/A | 1424200 | 1424200 | 1424200 | Equitable | N/A | 1424200 | 0 | 5989050 | 420.5 | 5989050 | 18483845 | -4564850 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4121 | Market Rehabilitation and Development | Solarization of Borehole At Kiremba Farmers Cooperative Society | To implement solarization of borehole at kiremba farmers cooperative society for economic growth and market access | Solarization of Borehole At Kiremba Farmers Cooperative Society completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2022/23 | 2022/23 | N/A | 5000000 | 4400056.32 | 4400056.32 | N/A | N/A | 4400056.32 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
4122 | Solarization of Markets Phase One | Solarization of Markets Phase One | To implement solarization of markets phase one for economic growth and market access | Solarization of Markets Phase One completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2023/24 | 2023/24 | N/A | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 5989050 | 100 | 5989050 | 0 | -5989050 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
4123 | Construction of Arahuka Market | Construction of Arahuka Market | To construct Arahuka Market | Arahuka Market constructed | 3110504 | Other Infrastructure and Civil Works | Subukia | Kabazi | -0.159188 36.045365 2081.3 10.899999618530273 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2022/23 | 2022/23 | 2022/23 | 3000000 | 2970700 | 2970700 | Equitable | N/A | 2970700 | 0 | 2970700 | 100 | 2970700 | 2970700 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: Peca services ltd. Assessor remarks: To be operationalized.
4124 | Market Rehabilitation and Development | Construction of sheds, toilets, pit latrines at Keringet bus park | To construct sheds, toilets, pit latrines at Keringet bus park | Sheds, toilets, pit latrines at Keringet bus park constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Keringet | -0.427113 35.692842 2683.500244140625 57.48400115966797 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2021/22 | 2021/22 | N/A | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 499837 | 100 | 499837 | 1000000 | -499837 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Not constructed.
4125 | Completion of Burma stalls | Completion of Burma stalls | To complete Burma stalls | Burma stalls completed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Kivumbini | -0.297885, 36.08281 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 1000000 | 996100 | 996100 | Equitable | N/A | 996100 | 0 | 996100 | 100 | 996100 | 996100 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Protect traders from harsh weather conditions.
4126 | Construction And Repair of Toilets at Maai Mahiu Market | Construction And Repair of Toilets at Maai Mahiu Market | To construct And Repair of Toilets at Maai Mahiu Market | And Repair of Toilets at Maai Mahiu Market constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maai Mahiu | -0.98138, 36.58487 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2023/24 | 2023/24 | N/A | 2081772 | 1811190 | 2032772 | Equitable | N/A | 2032772 | 0 | 5000000 | 276.1 | 5000000 | 2032772 | -3188810 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Some repairs needed..
4127 | Market Rehabilitation and Development | Construction of fence and shade at Hillstop for maai mahiu sand harvesters cabro making machine | To construct fence and shade at Hillstop for maai mahiu sand harvesters cabro making machine | Fence and shade at Hillstop for maai mahiu sand harvesters cabro making machine constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maai Mahiu | -0.904195, 36.513372 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2023/24 | 2023/24 | N/A | 1500000 | 0 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 1500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: To be demolished for the construction of ESP Market..
4128 | Market Rehabilitation and Development | Construction of Ndabibi Market | To construct Ndabibi Market | Ndabibi Market constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maiella | -0.804803 36.246244 0 22.5 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2022/23 | 2022/23 | N/A | 3500000 | 3134970 | 842845.8 | Equitable | N/A | 842845.8 | 0 | 2657154 | 84.8 | 2657154 | 842846 | 477816 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Eruc Africa Ltd. Assessor remarks: In use.
4129 | Development and Management of Markets | Construction of Kapsininendet market shed and stalls | To construct Kapsininendet market shed and stalls | Kapsininendet market shed and stalls constructed | 3110504 | Other Infrastructure and Civil Works | Molo | Mariashoni | -0.379517, 35.79494 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2024/25 | 2024/25 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Yes. Assessor remarks: Yet to start.
4130 | Development and Management of Markets | Completion of Natewa Market toilets | To complete Natewa Market toilets | Natewa Market toilets completed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Menengai | -0.284345, 36.074608 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2024/25 | 2024/25 | 2022/23 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 499910 | 50 | 499910 | 1000000 | 500090 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Cityking realators. Assessor remarks: Factional.
4131 | Construction Of Gates at Natewa Market | Construction Of Gates at Natewa Market | To construct Gates at Natewa Market | Gates at Natewa Market constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Menengai | -0.275544, 36.114246 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 499910 | 100 | 499910 | 90 | 90 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Perimeter wall needs to be constructed to attach to the gate.
4132 | Development and Management of Markets | Construction of Kiambogo markets cubical/stalls | To construct Kiambogo markets cubical/stalls | Kiambogo markets cubical/stalls constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Naivasha East | -0.871027, 36.51096 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2024/25 | 2024/25 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 6026905 | 301.3 | 6026905 | 2000000 | -4026905 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Ongoing.
4133 | Development and Management of Markets | Construction of Maraigushu markets cubical/stalls | To construct Maraigushu markets cubical/stalls | Maraigushu markets cubical/stalls constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Naivasha East | -0.871027, 36.51096 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2024/25 | 2024/25 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 6026905 | 301.3 | 6026905 | 2000000 | -4026905 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Ongoing.
4134 | Kinungi Market Phase I | Kinungi Market Phase I | To implement kinungi market phase i for economic growth and market access | Kinungi Market Phase I completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Naivasha East | -0.803698, 36.53251 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2022/23 | 2022/23 | 2024 | 15000000 | 0 | 10000000 | Equitable | N/A | 10000000 | 0 | 0 | 0 | 0 | 10000000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
4135 | Development and Management of Markets | Extension of Free-Area market shade | To expand Free-Area market shade to increase capacity | Free-Area market shade expanded | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Nakuru East | -0.292571, 36.119354 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2024/25 | 2024/25 | 2024/2025 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 4827143 | 482.7 | 4827143 | 1000000 | -3827143 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Needs urgent completion.
4136 | Development and Management of Markets | Construction of mitumba market shade, security light and latrine in Njoro Ward | To construct mitumba market shade, security light and latrine in Njoro Ward | Mitumba market shade, security light and latrine in Njoro Ward constructed | 3110504 | Other Infrastructure and Civil Works | Njoro | Njoro | -0.32763, 35.941896 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2024/25 | 2024/25 | 2025 | 6000000 | 5000000 | 6000000 | Equitable | N/A | 6000000 | 0 | 0 | 0 | 0 | 6000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: M/S Samues merchants. Assessor remarks: In good state.
4137 | Development and Management of Markets | Construction of toilets and solar lights in markets | To construct toilets and solar lights in markets | Toilets and solar lights in markets constructed | 3110504 | Other Infrastructure and Civil Works | Njoro | Njoro | -0.327576, 35.942033 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2024/25 | 2024/25 | 2025 | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 1099800 | 100 | 1099800 | 2000000 | -1099800 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Yes. Contractor: M/S Samues merchants. Assessor remarks: Work going on well.
4138 | Building of Market Shed at narasha | Building of Market Shed at narasha | To implement building of market shed at narasha for economic growth and market access | Building of Market Shed at narasha completed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Olkaria | -0.91605, 36.26702 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2021/22 | 2021/22 | N/A | 998770 | 0 | 286881 | Equitable | N/A | 286881 | 0 | 711889 | 100 | 711889 | 286881 | -711889 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional and well built.
4139 | Market Rehabilitation and Development | Construction Of Fish Bandas at Kamere Beach | To construct Fish Bandas at Kamere Beach | Fish Bandas at Kamere Beach constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Olkaria | -0.816924, 36.325814 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2023/24 | 2023/24 | N/A | 4500000 | 0 | 4500000 | Equitable | N/A | 4500000 | 0 | 4209000 | 100 | 4209000 | 4500000 | -4209000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Bnc design and building concepts. Assessor remarks: Finalised with good standared.
4140 | Market Rehabilitation and Development | Construction of fish market stalls | To construct fish market stalls | Fish market stalls constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Olkaria | -0.817264, 36.326217 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2019/20 | 2019/20 | 2019/20 | 4834865 | 0 | 612400 | Equitable | N/A | 612400 | 0 | 4209000 | 100 | 4209000 | 612400 | -4209000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Viable but the model is not secure for the purpose. Contractor: Northern city. Assessor remarks: Completed but not operational.
4141 | Construction of Market stalls at Narasha centre | Construction of Market stalls at Narasha centre | To construct Market stalls at Narasha centre | Market stalls at Narasha centre constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Olkaria | -0.915578 36.268129 2000.88 1.8179999589920044 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 3000000 | 2854600 | 2854600 | Equitable | N/A | 2854600 | 0 | 2854600 | 100 | 2854600 | 2854600 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional few people have business there.
4142 | Construction of market stalls at Rapland area | Construction of market stalls at Rapland area | To construct market stalls at Rapland area | Market stalls at Rapland area constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Olkaria | -0.938128 36.364994 1907.631103515625 14.281000137329102 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 2500000 | 2404700 | 2404700 | Equitable | N/A | 2404700 | 0 | 2854600 | 118.7 | 2854600 | 2404700 | -449900 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Tes. Assessor remarks: Completed awaiting electricity.
4143 | Development and Management of Markets | construction of curio shop at pembe mbili and relocation of curio shops | To construct curio shop at pembe mbili and relocation of curio shops | Curio shop at pembe mbili and relocation of curio shops constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Rhonda | -0.312665, 36.064747 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2024/25 | 2024/25 | Not started | 2500000 | 0 | 2500000 | Equitable | N/A | 2500000 | 0 | 0 | 0 | 0 | 2500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not started. Viable: Not started. Contractor: Not indicated. Assessor remarks: Not started.
4144 | Development and Management of Markets | Renovation of Toilet at Fish Market in Rhonda Ward | To rehabilitate Toilet at Fish Market in Rhonda Ward to restore functionality | Toilet at Fish Market in Rhonda Ward rehabilitated | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Rhonda | -0.306454, 36.063687 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2024/25 | 2024/25 | 24/25 | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 0 | 0 | 0 | 700000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Yet to start.
4145 | Construction of Garage sheds along Bamba road | Construction of Garage sheds along Bamba road | To construct Garage sheds along Bamba road | Garage sheds along Bamba road constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Shabab | N/A | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2024/25 | 2024/25 | N/A | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 0 | 0 | 0 | 4000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4146 | Construction of market shed at Gilanis | Construction of market shed at Gilanis | To construct market shed at Gilanis | Market shed at Gilanis constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Shabab | N/A | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2024/25 | 2024/25 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 5799981 | 386.7 | 5799981 | 1500000 | -4299981 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4147 | Construction Of Stalls at Githima Estate | Construction Of Stalls at Githima Estate | To construct Stalls at Githima Estate | Stalls at Githima Estate constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Shabab | N/A | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2023/24 | 2023/24 | N/A | 1000000 | 989960 | 1000000 | Equitable | N/A | 1000000 | 0 | 5799981 | 585.9 | 5799981 | 1000000 | -4810021 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4148 | Market Rehabilitation and Development | Gate repair at Shabab Market and tunnels unclogging & cleaning | To implement gate repair at shabab market and tunnels unclogging & cleaning for economic growth and market access | Gate repair at Shabab Market and tunnels unclogging & cleaning completed | 3110504 | Other Infrastructure and Civil Works | Nakuru West | Shabab | N/A | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2024/25 | 2024/25 | N/A | 639954 | 639954 | 639954 | Equitable | N/A | 639954 | 0 | 0 | 0 | 0 | 639954 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4149 | Development and Management of Markets | Completion of Lomolo market | To complete Lomolo market | Lomolo market completed | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.008758, 36.039327 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2024/25 | 2024/25 | FY 2025 | 1800000 | 1800000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: The contractor needs to hasten the works.
4150 | Market Rehabilitation and Development | Construction Of Athinai Market Including Fencing, Construction of A 8-Door Toilet and Streetlights) | To construct Athinai Market Including Fencing, Construction of A 8-Door Toilet and Streetlights) | Athinai Market Including Fencing, Construction of A 8-Door Toilet and Streetlights) constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.008859, 36.039406 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2023/24 | 2023/24 | 2023/2024 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2446800 | 97.9 | 2446800 | 53200 | 53200 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Bad. Objective met: If complete the objective will be met. Viable: It is viable and will meet needs once it's made operational. Assessor remarks: The market is yet to be operational.
4151 | Market Rehabilitation and Development | Construction Of Lomolo Market Including Fencing, Construction of A 8-Door Toilet and Streetlights) | To construct Lomolo Market Including Fencing, Construction of A 8-Door Toilet and Streetlights) | Lomolo Market Including Fencing, Construction of A 8-Door Toilet and Streetlights) constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.008859, 36.039406 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2023/24 | 2023/24 | 2023/2024 | 1700000 | 1699350 | 1700000 | Equitable | N/A | 1700000 | 0 | 2446800 | 144 | 2446800 | 1700000 | -747450 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Bad. Objective met: If complete the objective will be met. Viable: It is viable and will meet needs once it's made operational. Assessor remarks: The market is yet to be operational.
4152 | Development and Management of Markets | Construction Of Market Sheds at Majitamu Shopping Centre | To construct Market Sheds at Majitamu Shopping Centre | Market Sheds at Majitamu Shopping Centre constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Solai | 0.001937 36.155355 1712.5999755859375 18.322999954223633 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2023/24 | 2023/24 | 2023/24 | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 1711590 | 100 | 1711590 | 3000000 | -1711590 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ms Laron investment limited. Assessor remarks: Complete and operational.
4153 | Market Rehabilitation and Development | Construction of market toilets and lockups in Kivoronjo center | To construct market toilets and lockups in Kivoronjo center | Market toilets and lockups in Kivoronjo center constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Solai | 0.115358 36.222233 1849.1999999999998 6.300000190734863 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 1800000 | 1711590 | 1711590 | Equitable | N/A | 1711590 | 0 | 1711590 | 100 | 1711590 | 1711590 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
4154 | Development and Management of Markets | Renovation of Arutani Cooperative society | To rehabilitate Arutani Cooperative society to restore functionality | Arutani Cooperative society rehabilitated | 3110504 | Other Infrastructure and Civil Works | Rongai | Solai | -0.060102, 36.104518 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2024/25 | 2024/25 | December 2025 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 1500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Bad. Objective met: Yes. Viable: Yes. Assessor remarks: Contractor on site.
4155 | Market Rehabilitation and Development | Solarization of Kamarus Dairy Cooperative Society | To implement solarization of kamarus dairy cooperative society for economic growth and market access | Solarization of Kamarus Dairy Cooperative Society completed | 3110504 | Other Infrastructure and Civil Works | Rongai | Solai | 0.012337, 36.159166 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2023/24 | 2023/24 | 2025 | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
4156 | Market Rehabilitation and Development | Construction Of Taita Market 6-Door Toilets | To construct Taita Market 6-Door Toilets | Taita Market 6-Door Toilets constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Tinet | -0.403875 35.693755 0 899.9990234375 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2023/24 | 2023/24 | N/A | 1200000 | 0 | 1200000 | Equitable | N/A | 1200000 | 0 | 0 | 0 | 0 | 1200000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational and good condition.
4157 | Market Rehabilitation and Development | Fencing Of Taita Market Gate Chain link | To secure Taita Market Gate Chain link through fencing | Taita Market Gate Chain link fenced and secured | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Tinet | -0.521267 35.632365 2593 5 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2023/24 | 2023/24 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
4158 | Market Rehabilitation and Development | Rehabilitation of muricho market toilet | To rehabilitate muricho market toilet to restore functionality | Muricho market toilet rehabilitated | 3110504 | Other Infrastructure and Civil Works | Rongai | Visoi | -0.149943 35.881463 1841.6 9.300000190734863 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 400000 | 399500 | 399500 | Equitable | N/A | 399500 | 0 | 399500 | 100 | 399500 | 399500 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Very good.
4159 | Construction of market shed at open air market at Viwandani Ward | Construction of market shed at open air market at Viwandani Ward | To construct market shed at open air market at Viwandani Ward | Market shed at open air market at Viwandani Ward constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Viwandani | -0.714783, 36.433901 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 4000000 | 2995000 | 2995000 | Equitable | N/A | 2995000 | 0 | 2995000 | 100 | 2995000 | 2995000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable. Assessor remarks: Operational.
4160 | Market Rehabilitation and Development | Construction of market shed at Ndatho IDP Farm | To construct market shed at Ndatho IDP Farm | Market shed at Ndatho IDP Farm constructed | 3110504 | Other Infrastructure and Civil Works | Subukia | Waseges | 0.080873 36.244899 0 20.445999145507812 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2022/23 | 2022/23 | N/A | 1500000 | 0 | 1368340 | Equitable | N/A | 1368340 | 0 | 1300000 | 100 | 1300000 | 1368340 | -1300000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
4161 | Construction of market Sheds at Polepole Centre, Kahuruko and Mumoi centers | Construction of market Sheds at Polepole Centre, Kahuruko and Mumoi centers | To construct market Sheds at Polepole Centre, Kahuruko and Mumoi centers | Market Sheds at Polepole Centre, Kahuruko and Mumoi centers constructed | 3110504 | Other Infrastructure and Civil Works | Subukia | Waseges | 0.188127 36.235617 1657.3 12.899999618530273 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 4000000 | 3850000 | 3850000 | Equitable | N/A | 3850000 | 0 | 3850000 | 100 | 3850000 | 3850000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
4162 | Development and Management of Markets | Construction of a lockable Shutter doors at Nasher Market | To construct a lockable Shutter doors at Nasher Market | A lockable Shutter doors at Nasher Market constructed | 3110599 | Other Infrastructure and Civil Works | Nakuru East | Biashara-Nakuru | -0.285509, 36.075099 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2024/25 | 2024/25 | 2024/25 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2997058 | 149.9 | 2997058 | 2000000 | -997058 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: M/S soloem general supplies. Assessor remarks: Meeting threshold.
4163 | Development and Management of Markets | Construction of thirty (30) steel Coffee beds in Ndemu Farmers Cooperative Society Ltd | To construct thirty (30) steel Coffee beds in Ndemu Farmers Cooperative Society Ltd | Thirty (30) steel Coffee beds in Ndemu Farmers Cooperative Society Ltd constructed | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2023/24 | 2023/24 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4164 | Development and Management of Markets | Fencing of Elementaita Hot springs and establishment of ablution block | To secure Elementaita Hot springs and establishment of ablution block through fencing | Elementaita Hot springs and establishment of ablution block fenced and secured | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2021/22 | 2021/22 | N/A | 5000000 | 0 | 4998000 | Equitable | N/A | 4998000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4165 | Development and Management of Markets | Rehabilitation of Existing Markets | To rehabilitate Existing Markets to restore functionality | Existing Markets rehabilitated | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2024/25 | 2024/25 | N/A | 46477848 | 4000000 | 18483845 | Equitable | N/A | 18483845 | 0 | 5989050 | 149.7 | 5989050 | 18483845 | -1989050 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4166 | Development and Management of Markets | Construction of modern toilet at Duro Market | To construct modern toilet at Duro Market | Modern toilet at Duro Market constructed | 3110599 | Other Infrastructure and Civil Works | Naivasha | Maiella | -0.832803 36.203925 1761.6 19.399999618530273 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2024/25 | 2024/25 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 2995150 | 199.7 | 2995150 | 1500000 | -1495150 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Maintenance Required.
4167 | Development and Management of Markets | Construction of modern toilet at Sero Market | To construct modern toilet at Sero Market | Modern toilet at Sero Market constructed | 3110599 | Other Infrastructure and Civil Works | Naivasha | Maiella | -0.832803 36.203925 1761.6 19.399999618530273 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2024/25 | 2024/25 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 2995150 | 199.7 | 2995150 | 1500000 | -1495150 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Maintenance Required.
4168 | Purchase and installation of 3000 litre milk cooler in Mukasu Farmers Cooperative in Kuresoi North | Purchase and installation of 3000 litre milk cooler in Mukasu Farmers Cooperative in Kuresoi North | To procure and install 3000 litre milk cooler in Mukasu Farmers Cooperative in Kuresoi North | 3000 litre milk cooler in Mukasu Farmers Cooperative in Kuresoi North procured and installed | 3111120 | Purchase of Specialized Plant. - | HQ | HQ | -0.173672, 35.862823 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 8000000 | 7702500 | 7702500 | N/A | N/A | 7702500 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4169 | Purchase and installation of 3000 litre milk cooler in Soitaran and Arutani Farmers Cooperative Society | Purchase and installation of 3000 litre milk cooler in Soitaran and Arutani Farmers Cooperative Society | To procure and install 3000 litre milk cooler in Soitaran and Arutani Farmers Cooperative Society | 3000 litre milk cooler in Soitaran and Arutani Farmers Cooperative Society procured and installed | 3111120 | Purchase of Specialized Plant. - | HQ | HQ | -0.173672, 35.862823 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2021/22 | 2021/22 | 2021/22 | 8000000 | 7702500 | 7702500 | N/A | N/A | 7702500 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4170 | Rehabilitation of coffee factory at Mutungati Farmers Cooperative in Bahati | Rehabilitation of coffee factory at Mutungati Farmers Cooperative in Bahati | To rehabilitate coffee factory at Mutungati Farmers Cooperative in Bahati to restore functionality | Coffee factory at Mutungati Farmers Cooperative in Bahati rehabilitated | 3111299 | Rehabilitation & Renovation - | HQ | HQ | N/A | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2021/22 | 2021/22 | N/A | 6000000 | 5799010 | 5799010 | N/A | N/A | 5799010 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | No | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
4171 | Purchase of land for Langalanga Centre Market | Purchase of land for Langalanga Centre Market | To acquire land for Langalanga Centre Market | Land for Langalanga Centre Market acquired | 3130101 | Acquisition of Land | Gilgil | Murindat | -0.49925, 36.370528 | 4581 | TRADE, COOPERATIVES, TOURISM AND CULTURE | TRADE, COOPERATIVES, TOURISM AND CULTURE | N/A | 2018/19 | 2018/19 | 2018/19 | 7000000 | 2400000 | 2400000 | Equitable | N/A | 2400000 | 0 | 2400000 | 100 | 2400000 | 2400000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: Peter Wambugu. Assessor remarks: Land purchased.
4172 | Crop Development and Management | Agricultural Sector Development Support Projects (ASDSP II) | To implement agricultural sector development support projects (asdsp ii) for agricultural development and food production | Agricultural Sector Development Support Projects (ASDSP II) completed | 2640503 | N/A | HQ | HQ | N/A | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2023/24 | 2022/23 | 2022/23 | 5252658 | 10838353.3 | 0 | ASDSP II | ASDSP II | 0 | 10838353.3 | 1083629 | 10 | 1083629 | 5252658 | 9754724.3 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4173 | Crop Development and Management | Conditional Grant for the provision of fertilizer subsidy programme | To implement conditional grant for the provision of fertilizer subsidy programme for agricultural development and food production | Conditional Grant for the provision of fertilizer subsidy programme completed | 2640503 | N/A | HQ | HQ | N/A | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2023/24 | 2024/25 | N/A | 234883209 | 234883209 | 0 | National Government | National Government | 0 | 234883209 | 234883209 | 100 | 234883209 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
4174 | Crop Development and Management | Counterpart funding- Agricultural Sector Development Support Projects (ASDSP) | To implement counterpart funding- agricultural sector development support projects (asdsp) for agricultural development and food production | Counterpart funding- Agricultural Sector Development Support Projects (ASDSP) completed | 2640503 | N/A | HQ | HQ | N/A | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2023/24 | 2023/24 | 2023/24 | 1500000 | 1500000 | 1500000 | ASDSP II | ASDSP II | 1500000 | 0 | 1500000 | 100 | 1500000 | 4500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4175 | Administration, Planning and Support Services | Counterpart funding- Kenya Livestock Commercialization Project (KELCOP) | To implement counterpart funding- kenya livestock commercialization project (kelcop) for agricultural development and food production | Counterpart funding- Kenya Livestock Commercialization Project (KELCOP) completed | 2640503 | N/A | HQ | HQ | N/A | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2023/24 | 2023/24 | N/A | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 17000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4176 | Crop Development and Management | Counterpart funding- National Agricultural and Rural Inclusive growth Project (NARIGP) | To implement counterpart funding- national agricultural and rural inclusive growth project (narigp) for agricultural development and food production | Counterpart funding- National Agricultural and Rural Inclusive growth Project (NARIGP) completed | 2640503 | N/A | HQ | HQ | N/A | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2023/24 | 2023/24 | 2023/24 | 2000000 | 2000000 | 2000000 | NARIGP | NARIGP | 2000000 | 0 | 2000000 | 100 | 2000000 | 3910461 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4177 | Crop Development and Management | Counterpart funding - National Agricultural Value Chain Development Project - NAVCDP | To implement counterpart funding - national agricultural value chain development project - navcdp for agricultural development and food production | Counterpart funding - National Agricultural Value Chain Development Project - NAVCDP completed | 2640503 | N/A | HQ | HQ | N/A | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2024/25 | 2024/25 | 2024/25 | 6500000 | 6500000 | 5500000 | Equitable | N/A | 5500000 | 0 | 5500000 | 84.6 | 5500000 | 66492404 | 1000000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4178 | Crop Development and Management | Counterpart funding- National Agriculture Value Chain Development Project (NAVCDP) | To implement counterpart funding- national agriculture value chain development project (navcdp) for agricultural development and food production | Counterpart funding- National Agriculture Value Chain Development Project (NAVCDP) completed | 2640503 | N/A | HQ | HQ | N/A | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2023/24 | 2023/24 | 2023/24 | 5500000 | 5500000 | 5500000 | Equitable | N/A | 5500000 | 0 | 5500000 | 100 | 5500000 | 133938776 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4179 | Administration, Planning and Support Services | IFAD Conditional Grant - Kenya Livestock Commercialization Project | To implement ifad conditional grant - kenya livestock commercialization project for agricultural development and food production | IFAD Conditional Grant - Kenya Livestock Commercialization Project completed | 2640503 | N/A | HQ | HQ | N/A | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2024/25 | 2024/25 | N/A | 38280000 | 38280000 | 0 | Equitable | N/A | 0 | 38280000 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4180 | Administration, Planning and Support Services | Kenya Livestock Commercialization Project (KELCOP) | To implement kenya livestock commercialization project (kelcop) for agricultural development and food production | Kenya Livestock Commercialization Project (KELCOP) completed | 2640503 | N/A | HQ | HQ | N/A | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2023/24 | 2023/24 | N/A | 34800000 | 0 | 0 | Equitable | N/A | 0 | 11802360.1 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4181 | Livestock Resource Management and Development | Kenya Livestock Value Chain Project | To implement kenya livestock value chain project for agricultural development and food production | Kenya Livestock Value Chain Project completed | 2640503 | N/A | HQ | HQ | N/A | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2023/24 | 2023/24 | N/A | 121315800 | 121315800 | 0 | National Government | NATIONAL GOVT | 0 | 121315800 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4182 | Crop Development and Management | National Agricultural and Rural Inclusive Growth Projects (NARIGP) | To implement national agricultural and rural inclusive growth projects (narigp) for agricultural development and food production | National Agricultural and Rural Inclusive Growth Projects (NARIGP) completed | 2640503 | N/A | HQ | HQ | N/A | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2023/24 | 2023/24 | 2023/24 | 150000000 | 229340663 | 0 | NARIGP | NARIGP | 0 | 88251123.7 | 351365 | 0.2 | 351365 | 3910461 | 228989298 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4183 | Crop Development and Management | National Agricultural Value Chain Development Project (NAVCDP) | To implement national agricultural value chain development project (navcdp) for agricultural development and food production | National Agricultural Value Chain Development Project (NAVCDP) completed | 2640503 | N/A | HQ | HQ | N/A | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2022/23 | 2024/25 | 2024/25 | 151515152 | 218007556.4 | 0 | Equitable | N/A | 0 | 218007556.4 | 66492404 | 30.5 | 66492404 | 66492404 | 151515152.4 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4184 | Crop Development and Management | National Agriculture Value Chain Development Project (NAVCDP) | To implement national agriculture value chain development project (navcdp) for agricultural development and food production | National Agriculture Value Chain Development Project (NAVCDP) completed | 2640503 | N/A | HQ | HQ | N/A | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2023/24 | 2023/24 | N/A | 250000000 | 0 | 0 | Equitable | N/A | 0 | 133938776.44 | 65007608 | 0 | 65007608 | 133938776 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4185 | Administration, Planning and Support Services | Construction of Offices for Saptet Dairy Farmers | To construct Offices for Saptet Dairy Farmers | Offices for Saptet Dairy Farmers constructed | 3110202 | Non-Residential Buildings (offices, schools, hospitals, | Kuresoi South | Keringet | -0.488183, 35.706568 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2022/23 | 2022/23 | 2023 | 1800000 | 1758000 | 1758000 | Equitable | Equitable | 1758000 | 0 | 1758000 | 100 | 1758000 | 1758000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: No electric ity.
4186 | Administration, Planning and Support Services | Completion Of Chepakundi and Lelaitich Tea Buying Centres | To complete Chepakundi and Lelaitich Tea Buying Centres | Chepakundi and Lelaitich Tea Buying Centres completed | 3110299 | Construction of Buildings - Ot | Kuresoi South | Amalo | -0.678333, 35.654262 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2023/24 | 2023/24 | 2024 | 2800000 | 0 | 2800000 | Equitable | EQUITABLE | 2800000 | 0 | 1297450 | 100 | 1297450 | 2800000 | -1297450 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: not yet started. Viable: not yet. Assessor remarks: construction work on progress.
4187 | Administration, Planning and Support Services | Completion of Chorwet Tea buying Centre | To complete Chorwet Tea buying Centre | Chorwet Tea buying Centre completed | 3110299 | Construction of Buildings - Ot | Kuresoi South | Amalo | -0.665317, 35.625033 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2023/24 | 2023/24 | 2024 | 950000 | 0 | 950000 | Equitable | EQUITABLE | 950000 | 0 | 1000000 | 100 | 1000000 | 950000 | -1000000 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: no. Viable: no. Assessor remarks: project stalled due to allocation of inadequate funds.
4188 | Administration, Planning and Support Services | Completion Of Kaplamai, Bondet Tea Buying Centres | To complete Kaplamai, Bondet Tea Buying Centres | Kaplamai, Bondet Tea Buying Centres completed | 3110299 | Construction of Buildings - Ot | Kuresoi South | Amalo | -0.665317, 35.625033 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2023/24 | 2023/24 | 2024 | 2000000 | 0 | 2000000 | Equitable | EQUITABLE | 2000000 | 0 | 680540 | 100 | 680540 | 2000000 | -680540 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: no. Viable: no. Assessor remarks: project stalled due to allocation of inadequate funds.
4189 | Administration, Planning and Support Services | Completion of Tebeswet, Saptet Kapkwen, Taachasis Nukiat, Baragewet Tea buying centres | To complete Tebeswet, Saptet Kapkwen, Taachasis Nukiat, Baragewet Tea buying centres | Tebeswet, Saptet Kapkwen, Taachasis Nukiat, Baragewet Tea buying centres completed | 3110299 | Construction of Buildings - Ot | Kuresoi South | Amalo | -0.682723, 35.627042 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2022/23 | 2022/23 | 2023 | 4277890 | 0 | 1319820.2 | Equitable | Equitable | 1319820.2 | 0 | 1947508 | 100 | 1947508 | 2222993 | -1947508 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: project completed.
4190 | Administration, Planning and Support Services | Completion Of Tuiyobei Tea Buying Centres | To complete Tuiyobei Tea Buying Centres | Tuiyobei Tea Buying Centres completed | 3110299 | Construction of Buildings - Ot | Kuresoi South | Amalo | -0.665317, 35.625033 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2023/24 | 2023/24 | 2024 | 500000 | 0 | 500000 | Equitable | EQUITABLE | 500000 | 0 | 1000000 | 100 | 1000000 | 500000 | -1000000 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: no. Viable: no. Assessor remarks: project stalled due to allocation of inadequate funds.
4191 | Administration, Planning and Support Services | Construction of Chorwet & Kapkures Tea Buying Centres | To construct Chorwet & Kapkures Tea Buying Centres | Chorwet & Kapkures Tea Buying Centres constructed | 3110299 | Construction of Buildings - Ot | Kuresoi South | Amalo | -0.671477, 35.61856 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2022/23 | 2022/23 | 2024 | 2700000 | 2685300 | 2685300 | Equitable | EQUITABLE | 2685300 | 0 | 2685300 | 100 | 2685300 | 2685300 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: no. Viable: no. Assessor remarks: project stalled due to allocation of inadequate funds.
4192 | Administration, Planning and Support Services | Construction Of Taachasis Nukiat Tea Buying Centres | To construct Taachasis Nukiat Tea Buying Centres | Taachasis Nukiat Tea Buying Centres constructed | 3110299 | Construction of Buildings - Ot | Kuresoi South | Amalo | -0.671477, 35.61856 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2023/24 | 2023/24 | 2024 | 1450000 | 0 | 742175 | Equitable | EQUITABLE | 742175 | 0 | 978270 | 100 | 978270 | 1450000 | -978270 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: no. Viable: no. Assessor remarks: project stalled due to allocation of inadequate funds.
4193 | Administration, Planning and Support Services | Construction of Tea Buying Centres in Amalo ward | To construct Tea Buying Centres in Amalo ward | Tea Buying Centres in Amalo ward constructed | 3110299 | Construction of Buildings - Ot | Kuresoi South | Amalo | -0.615343 35.656623 2472.1 55.29999923706055 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2024/25 | 2024/25 | N/A | 8800000 | 8800000 | 8800000 | Equitable | N/A | 8800000 | 0 | 1215610 | 13.8 | 1215610 | 83560 | 7584390 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Complete.
4194 | Administration, Planning and Support Services | Construction Of Tea Buying Centres At Ambusket, Chelalang, Saosa And Tuiyobei | To construct Tea Buying Centres At Ambusket, Chelalang, Saosa And Tuiyobei | Tea Buying Centres At Ambusket, Chelalang, Saosa And Tuiyobei constructed | 3110299 | Construction of Buildings - Ot | Kuresoi South | Amalo | -0.664247, 35.635138 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2018/19 | 2018/19 | 2025 | 2761228.5 | 1171199.5 | 1171199.5 | Equitable | equitable | 1171199.5 | 0 | 891679 | 76.1 | 891679 | 279520 | 279520.5 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: not yet. Viable: not yet. Assessor remarks: project not complete.
4195 | Administration, Planning and Support Services | Expansion of Mutamuiyu Milk Cooler House | To expand Mutamuiyu Milk Cooler House to increase capacity | Mutamuiyu Milk Cooler House expanded | 3110299 | Construction of Buildings - Ot | Molo | Elburgon | -0.284884 35.845889 0 1399.9990234375 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2022/23 | 2022/23 | N/A | 800000 | 1200000 | 1200000 | Equitable | EQUITABLE | 1200000 | 0 | 1371380 | 114.3 | 1371380 | 1200000 | -171380 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: No Maternity wing-externsion of opd block.
4196 | Livestock Resource Management and Development | Completion of ATC Kitchen and Dining | To complete ATC Kitchen and Dining | ATC Kitchen and Dining completed | 3110299 | Construction of Buildings - Ot | HQ | HQ | N/A | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2022/23 | 2022/23 | 2022/23 | 5891064 | 1416026.4 | 1416026.4 | Equitable | N/A | 1416026.4 | 0 | 2386000 | 168.5 | 2386000 | 0 | -969973.6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4197 | Administration, Planning and Support Services | Completion of Bondet, Sukutek, Kapchorwa, Chigamba, Banana, Kondamet Kiptagich Tea buying centres | To complete Bondet, Sukutek, Kapchorwa, Chigamba, Banana, Kondamet Kiptagich Tea buying centres | Bondet, Sukutek, Kapchorwa, Chigamba, Banana, Kondamet Kiptagich Tea buying centres completed | 3110299 | Construction of Buildings - Ot | Kuresoi South | Kiptagich | -0.63122 35.606292 2395.7000000000003 10.899999618530273 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2022/23 | 2022/23 | 2022/23 | 3500000 | 3487800 | 3487800 | Equitable | EQUITABLE | 3487800 | 0 | 3427272 | 98.3 | 3427272 | 60528 | 60528 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: No. Viable: Viable and needs met. Assessor remarks: The project is still under construction. No table tops, no painting, and no toilets..
4198 | Administration, Planning and Support Services | Completion of Chepnyalilo kwenet, Kondamet, mulango,Rehema, chepkiswet and arorwet tea buying centre | To complete Chepnyalilo kwenet, Kondamet, mulango,Rehema, chepkiswet and arorwet tea buying centre | Chepnyalilo kwenet, Kondamet, mulango,Rehema, chepkiswet and arorwet tea buying centre completed | 3110299 | Construction of Buildings - Ot | Kuresoi South | Kiptagich | -0.587461, 35.595227 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2024/25 | 2024/25 | N/A | 2800000 | 2800000 | 2800000 | Equitable | N/A | 2800000 | 0 | 1198750 | 42.8 | 1198750 | 3100000 | 1601250 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: It could be viable if it was completed. Assessor remarks: Project vandalized.
4199 | Administration, Planning and Support Services | Construction of Kanoin school, Sapmsola simotwet,cheptuech central and kap cheluch Tea buying centres | To construct Kanoin school, Sapmsola simotwet,cheptuech central and kap cheluch Tea buying centres | Kanoin school, Sapmsola simotwet,cheptuech central and kap cheluch Tea buying centres constructed | 3110299 | Construction of Buildings - Ot | Kuresoi South | Kiptagich | -0.643778, 35.602382 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2024/25 | 2024/25 | Not yet started | 4400000 | 4400000 | 4400000 | Equitable | N/A | 4400000 | 0 | 349980 | 8 | 349980 | 5100000 | 4050020 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Viable but not yet started. Contractor: Don't know. Assessor remarks: The project has not been started.
4200 | Administration, Planning and Support Services | Construction of saptonok seger,angelica sacret,kipkebei and singoriet tea buying centre | To construct saptonok seger,angelica sacret,kipkebei and singoriet tea buying centre | Saptonok seger,angelica sacret,kipkebei and singoriet tea buying centre constructed | 3110299 | Construction of Buildings - Ot | Kuresoi South | Kiptagich | -0.599537 35.609858 2621.7000000000003 7.800000190734863 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2024/25 | 2024/25 | N/A | 4800000 | 4800000 | 4800000 | Equitable | N/A | 4800000 | 0 | 349980 | 7.3 | 349980 | 5100000 | 4450020 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes, expected to meet the needs of the residents. Assessor remarks: Ongoing.
4201 | Administration, Planning and Support Services | Construction Of Sitotwet, Kipkwe, Konoin, Simotwet Kiletien-Tea Buying Centres | To construct Sitotwet, Kipkwe, Konoin, Simotwet Kiletien-Tea Buying Centres | Sitotwet, Kipkwe, Konoin, Simotwet Kiletien-Tea Buying Centres constructed | 3110299 | Construction of Buildings - Ot | Kuresoi South | Kiptagich | -0.6617, 35.604763 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2023/24 | 2023/24 | 2025 | 5100000 | 5100000 | 10200000 | Equitable | N/A | 10200000 | 0 | 730923 | 14.3 | 730923 | 5100000 | 4369077 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: No. Viable: Viable but not complete. Contractor: Don't know. Assessor remarks: The project is under construction.
4202 | Administration, Planning and Support Services | Completion Of Burgei Tea Buying Centre | To complete Burgei Tea Buying Centre | Burgei Tea Buying Centre completed | 3110299 | Construction of Buildings - Ot | Kuresoi North | Kiptororo | -0.313807 35.483757 2526.6 10.5 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2023/24 | 2023/24 | 2023/24 | 1500920 | 0 | 1500920 | Equitable | N/A | 1500920 | 0 | 197800 | 100 | 197800 | 1500920 | -197800 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: It is operational.
4203 | Administration, Planning and Support Services | Completion of Chorwa tea buying centre | To complete Chorwa tea buying centre | Chorwa tea buying centre completed | 3110299 | Construction of Buildings - Ot | Kuresoi North | Kiptororo | -0.313807 35.483757 2526.6 10.5 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2024/25 | 2024/25 | 2024/25 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 197800 | 33 | 197800 | 200000 | 402200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: It is operational.
4204 | Administration, Planning and Support Services | Completion of Kio, Githima, Mwarangia, Arorwet, Korabariet, Chebitok, Tumoiyot and Chebkoburot Tea buying centres | To complete Kio, Githima, Mwarangia, Arorwet, Korabariet, Chebitok, Tumoiyot and Chebkoburot Tea buying centres | Kio, Githima, Mwarangia, Arorwet, Korabariet, Chebitok, Tumoiyot and Chebkoburot Tea buying centres completed | 3110299 | Construction of Buildings - Ot | Kuresoi North | Kiptororo | -0.301145, 35.52038 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2022/23 | 2022/23 | 2022/23 | 6000000 | 0 | 2175000 | Equitable | EQUITABLE | 2175000 | 0 | 3625000 | 100 | 3625000 | 2175000 | -3625000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Accessibility to the tea buying center is a challenge.the roads should be maintained.
4205 | Administration, Planning and Support Services | Completion of Ogilgei tea buying centre and Construction of 2 door toilet | To complete Ogilgei tea buying centre and Construction of 2 door toilet | Ogilgei tea buying centre and Construction of 2 door toilet completed | 3110299 | Construction of Buildings - Ot | Kuresoi North | Kiptororo | -0.357854 35.554497 2608.293 0.6869999766349792 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2024/25 | 2024/25 | 2024/25 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1378824 | 137.9 | 1378824 | 1500920 | -378824 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The toilets are complete no skeptic tank.
4206 | Administration, Planning and Support Services | Construction Of Chebitoik,Burgei Ogilgei, Tumoiyot And Completion Of Chematichtea Buying Centre | To construct Chebitoik,Burgei Ogilgei, Tumoiyot And Completion Of Chematichtea Buying Centre | Chebitoik,Burgei Ogilgei, Tumoiyot And Completion Of Chematichtea Buying Centre constructed | 3110299 | Construction of Buildings - Ot | Kuresoi North | Kiptororo | -0.309289, 35.516698 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2021/22 | 2021/22 | N/A | 4400000 | 2143240 | 2143240 | Equitable | N/A | 2143240 | 0 | 2106760 | 98.3 | 2106760 | 2143240 | 36480 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: The is in complete,without roof and all other finishings.
4207 | Administration, Planning and Support Services | Construction of Kapno Tea Buying Centre | To construct Kapno Tea Buying Centre | Kapno Tea Buying Centre constructed | 3110299 | Construction of Buildings - Ot | Kuresoi South | Tinet | -0.520868 35.620393 2526.8999999999996 4 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2024/25 | 2024/25 | 2024/25 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 852725 | 34.1 | 852725 | 100 | 1647275 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
4208 | Administration, Planning and Support Services | Construction of Three Ways Tea Buying Centre | To construct Three Ways Tea Buying Centre | Three Ways Tea Buying Centre constructed | 3110299 | Construction of Buildings - Ot | Kuresoi South | Tinet | -0.529565 35.610744 0 2900 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2024/25 | 2024/25 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 852725 | 42.6 | 852725 | 2000000 | 1147275 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: Ongoing.
4209 | Administration, Planning and Support Services | Construction Of Timbwalo Tea Buying Centres | To construct Timbwalo Tea Buying Centres | Timbwalo Tea Buying Centres constructed | 3110299 | Construction of Buildings - Ot | Kuresoi South | Tinet | -0.570268 35.61587 0 500 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2023/24 | 2023/24 | N/A | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 852725 | 100 | 852725 | 2000000 | -852725 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Ongoing almost complete.
4210 | Administration, Planning and Support Services | Renovation Of Ambusket-Saptet, Cheptalgulge, Kabigeriet Tea Buying Centres | To rehabilitate Ambusket-Saptet, Cheptalgulge, Kabigeriet Tea Buying Centres to restore functionality | Ambusket-Saptet, Cheptalgulge, Kabigeriet Tea Buying Centres rehabilitated | 3110399 | Refurbishment of Buildgs - Oth | Kuresoi South | Amalo | -0.62805, 35.664602 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2023/24 | 2023/24 | 2025 | 2400000 | 0 | 2400000 | Equitable | N/A | 2400000 | 0 | 1451750 | 100 | 1451750 | 2400000 | -1451750 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: project completed.
4211 | Administration, Planning and Support Services | Completion Of Kaptembwa Tea Buying Center | To complete Kaptembwa Tea Buying Center | Kaptembwa Tea Buying Center completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Amalo | -0.635302, 35.657887 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2021/22 | 2021/22 | 2024 | 1000000 | 530015 | 530015 | Equitable | EQUITABLE | 530015 | 0 | 530015 | 100 | 530015 | 530015 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: project completed.
4212 | Administration, Planning and Support Services | Erecting Of A Fence Around Olenguruone Dairies Society | To implement erecting of a fence around olenguruone dairies society for agricultural development and food production | Erecting Of A Fence Around Olenguruone Dairies Society completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Amalo | -0.592109, 35.684406 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2017/18 | 2017/18 | 2023 | 2000000 | 0 | 1999608 | Equitable | Equitable | 1999608 | 0 | 0 | 0 | 0 | 1999608 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: yes. Assessor remarks: project on progress.
4213 | Administration, Planning and Support Services | Fencing and electrification of Bavuni Migwathi dairy co-operative | To secure and electrification of Bavuni Migwathi dairy co-operative through fencing | And electrification of Bavuni Migwathi dairy co-operative fenced and secured | 3110504 | Other Infrastructure and Civil Works | Bahati | Dundori | -0.236828, 36.178061 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2024/25 | 2024/25 | 2024/2025 | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not started. Viable: Yes. Assessor remarks: The contractor has delayed in implementing the project.
4214 | Administration, Planning and Support Services | Completion and equipping of slaughter House in Naivasha, Hells Gate ward | To complete and equip slaughter House in Naivasha, Hells Gate ward | Slaughter House in Naivasha, Hells Gate ward completed and equipped | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2022/23 | 2022/23 | 2022/23 | 15000000 | 2750551.4 | 2750551.4 | Equitable | EQUITABLE | 2750551.4 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4215 | Administration, Planning and Support Services | Completion of Eburru/Mbaruk Slaughter House | To complete Eburru/Mbaruk Slaughter House | Eburru/Mbaruk Slaughter House completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2022/23 | 2022/23 | 2022/23 | 38396882 | 5886478 | 5886478 | Equitable | EQUITABLE | 5886478 | 0 | 5668369 | 96.3 | 5668369 | 0 | 218109 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4216 | Administration, Planning and Support Services | Completion of security wall and machinery shed at AMS for securing procured machinery and implements | To complete security wall and machinery shed at AMS for securing procured machinery and implements | Security wall and machinery shed at AMS for securing procured machinery and implements completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2022/23 | 2022/23 | 2022/23 | 22000000 | 585940.8 | 585940.8 | Equitable | EQUITABLE | 585940.8 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4217 | Administration, Planning and Support Services | Construction of 2 feed store/Hayban (Rongai Acacia) | To construct 2 feed store/Hayban (Rongai Acacia) | 2 feed store/Hayban (Rongai Acacia) constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2023/24 | 2023/24 | 2023/24 | 10000000 | 0 | 2000000 | Equitable | EQUITABLE | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4218 | Administration, Planning and Support Services | Construction of Eburru/Mbaruk slaughter House and Auction Yard | To construct Eburru/Mbaruk slaughter House and Auction Yard | Eburru/Mbaruk slaughter House and Auction Yard constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2021/22 | 2021/22 | 2021/22 | 50000000 | 10309855 | 10309855 | Equitable | EQUITABLE | 10309855 | 0 | 2980492 | 28.9 | 2980492 | 0 | 7329363 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4219 | Administration, Planning and Support Services | Equipping and furnishing of ATC Kitchen and Dining | To equip and furnishing of ATC Kitchen and Dining with necessary facilities and equipment | And furnishing of ATC Kitchen and Dining equipped | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2023/24 | 2023/24 | 2023/24 | 7000000 | 3000000 | 3000000 | Equitable | EQUITABLE | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4220 | Fisheries Development | Fishing and safety Gears in Lake Naivasha | To implement fishing and safety gears in lake naivasha for agricultural development and food production | Fishing and safety Gears in Lake Naivasha completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2022/23 | 2022/23 | 2022/23 | 10000000 | 978216 | 978216 | Equitable | N/A | 978216 | 0 | 3994966 | 408.4 | 3994966 | 4533338 | -3016750 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4221 | Administration, Planning and Support Services | Potato Stores In Kuresoi South And Njoro | To implement potato stores in kuresoi south and njoro for agricultural development and food production | Potato Stores In Kuresoi South And Njoro completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 2998855.2 | 0 | 1998855 | Equitable | EQUITABLE | 1998855 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4222 | Administration, Planning and Support Services | Purchase of livestock support equipments | To procure livestock support equipments | Livestock support equipments procured | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2021/22 | 2021/22 | 2021/22 | 20000000 | 13846768 | 13846768 | Equitable | EQUITABLE | 13846768 | 0 | 3749520 | 27.1 | 3749520 | 13846768 | 10097248 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4223 | Administration, Planning and Support Services | Construction Of Cut Off Drains In Agricultural Farm Lands | To construct Cut Off Drains In Agricultural Farm Lands | Cut Off Drains In Agricultural Farm Lands constructed | 3110504 | Other Infrastructure and Civil Works | Njoro | Kihingo | -0.451828, 35.976993 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2020/21 | 2020/21 | 2022 | 2500000 | 1175000 | 1175000 | Equitable | equitable | 1175000 | 0 | 1160000 | 98.7 | 1160000 | 15000 | 15000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yea. Viable: Yes. Assessor remarks: Requires maintenance.
4224 | Administration, Planning and Support Services | Completion Of Banana Tea Buying Center | To complete Banana Tea Buying Center | Banana Tea Buying Center completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.592825, 35.636085 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2020/21 | 2020/21 | N/A | 400000 | 0 | 399310 | Equitable | EQUITABLE | 399310 | 0 | 400000 | 100 | 400000 | 399310 | -400000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and needs met. Assessor remarks: Functional.
4225 | Administration, Planning and Support Services | Completion Of Kiborowa Tea Buying Center | To complete Kiborowa Tea Buying Center | Kiborowa Tea Buying Center completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.592825, 35.636085 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2021/22 | 2021/22 | N/A | 800000 | 800000 | 800000 | Equitable | EQUITABLE | 800000 | 0 | 800000 | 100 | 800000 | 800000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and needs met. Assessor remarks: Functional.
4226 | Administration, Planning and Support Services | Completion Of Kipsunyam-Table Tops Tea Buying Center | To complete Kipsunyam-Table Tops Tea Buying Center | Kipsunyam-Table Tops Tea Buying Center completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.638423, 35.60739 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2021/22 | 2021/22 | 2023 | 300000 | 300000 | 300000 | Equitable | Equitable | 300000 | 0 | 300000 | 100 | 300000 | 300000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Viable and it meets the needs of the residents. Contractor: Don't know. Assessor remarks: The project is complete.
4227 | Administration, Planning and Support Services | Completion Of Seger, Kapsilibwo, Tebeswet, Kondamet Tea Buying Centres | To complete Seger, Kapsilibwo, Tebeswet, Kondamet Tea Buying Centres | Seger, Kapsilibwo, Tebeswet, Kondamet Tea Buying Centres completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.63122 35.606292 2395.7000000000003 10.899999618530273 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2023/24 | 2023/24 | N/A | 3100000 | 0 | 3100000 | Equitable | EQUITABLE | 3100000 | 0 | 399272 | 100 | 399272 | 3100000 | -399272 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: No. Viable: Viable and needs met. Assessor remarks: The project is still under construction. No table tops, no painting, and no toilets..
4228 | Administration, Planning and Support Services | Completion Of Working Tops-Chepnyalilo TBC Tea Buying Centres | To complete Working Tops-Chepnyalilo TBC Tea Buying Centres | Working Tops-Chepnyalilo TBC Tea Buying Centres completed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.582347 35.648972 2505.2999999999997 6.900000095367432 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2023/24 | 2023/24 | N/A | 200000 | 0 | 200000 | Equitable | EQUITABLE | 200000 | 0 | 600000 | 100 | 600000 | 200000 | -600000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable and it meets the residents needs. Contractor: Don't know. Assessor remarks: The project is complete but there are no toilets.
4229 | Administration, Planning and Support Services | Construction Of Ararwet Mbaley Tea Buying Center | To construct Ararwet Mbaley Tea Buying Center | Ararwet Mbaley Tea Buying Center constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.562995, 35.589517 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2020/21 | 2020/21 | Not yet started | 1000000 | 927290 | 927290 | Equitable | EQUITABLE | 927290 | 0 | 396390 | 42.7 | 396390 | 927290 | 530900 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: The project was viable but it never met the objectives of the residents.. Contractor: Don't know. Assessor remarks: The project has not started.
4230 | Administration, Planning and Support Services | Construction Of Chepkiswet Tea Buying Centre | To construct Chepkiswet Tea Buying Centre | Chepkiswet Tea Buying Centre constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.599537 35.609858 2621.7000000000003 7.800000190734863 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2018/19 | 2018/19 | 2018/19 | 1198687 | 0 | 698687 | Equitable | EQUITABLE | 698687 | 0 | 600000 | 100 | 600000 | 698687 | -600000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes, expected to meet the needs of the residents. Assessor remarks: Ongoing.
4231 | Administration, Planning and Support Services | Construction Of Kanoin Tea Buying Center | To construct Kanoin Tea Buying Center | Kanoin Tea Buying Center constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Kiptagich | -0.579408 35.574193 2412.1 4.199999809265137 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2021/22 | 2021/22 | 2021/22 | 800000 | 800000 | 800000 | Equitable | EQUITABLE | 800000 | 0 | 730923 | 91.4 | 730923 | 69077 | 69077 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: The project is viable but it doesn't meet the needs of the residents. Contractor: Don't know. Assessor remarks: The project is at lintel level and has stalled..
4232 | Administration, Planning and Support Services | Construction Of Chebitoik,Burgei Ogilgei, Tumoiyot And Completion Of Chematichtea Buying Centre | To construct Chebitoik,Burgei Ogilgei, Tumoiyot And Completion Of Chematichtea Buying Centre | Chebitoik,Burgei Ogilgei, Tumoiyot And Completion Of Chematichtea Buying Centre constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi North | Kiptororo | -0.309289, 35.516698 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2021/22 | 2021/22 | N/A | 4400000 | 2143240 | 2143240 | Equitable | N/A | 2143240 | 0 | 2106760 | 98.3 | 2106760 | 2143240 | 36480 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: The is in complete,without roof and all other finishings.
4233 | Administration, Planning and Support Services | Installation of water tanks, electricity and ablution block for coolers in Ndabibi and Maiella | To install water tanks, electricity and ablution block for coolers in Ndabibi and Maiella | Water tanks, electricity and ablution block for coolers in Ndabibi and Maiella installed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Maiella | N/A | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2023/24 | 2023/24 | N/A | 1500000 | 0 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 1500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4234 | Administration, Planning and Support Services | Rehabilitation of Tarambete fisheries | To rehabilitate Tarambete fisheries to restore functionality | Tarambete fisheries rehabilitated | 3110504 | Other Infrastructure and Civil Works | Gilgil | Malewa West | -0.702703, 36.471211 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2024/25 | 2024/25 | 2024/25 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good project.
4235 | Administration, Planning and Support Services | Equiping and maintainance of Taret cattle dip | To implement equiping and maintainance of taret cattle dip for agricultural development and food production | Equiping and maintainance of Taret cattle dip completed | 3110504 | Other Infrastructure and Civil Works | Njoro | Mauche | -0.451494, 35.952388 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2024/25 | 2024/25 | 2025 | 300000 | 300000 | 300000 | Equitable | N/A | 300000 | 0 | 1700000 | 566.7 | 1700000 | 3413 | -1400000 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Not fenced.
4236 | Administration, Planning and Support Services | Fencing, improvement and construction of communal water point and cattle trough at Teret Dam | To implement fencing, improvement and construction of communal water point and cattle trough at teret dam for agricultural development and food production | Fencing, improvement and construction of communal water point and cattle trough at Teret Dam completed | 3110504 | Other Infrastructure and Civil Works | Njoro | Mauche | -0.450946, 35.951439 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2024/25 | 2024/25 | 2025 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not known. Assessor remarks: Good.
4237 | Administration, Planning and Support Services | Construction of a Vegetable Value addition Plant at Munyu | To construct a Vegetable Value addition Plant at Munyu | A Vegetable Value addition Plant at Munyu constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Naivasha East | -0.738739, 36.435461 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2022/23 | 2022/23 | 2022 | 3137509 | 0 | 1512663 | Equitable | Equitable | 1512663 | 0 | 1285567 | 100 | 1285567 | 1512663 | -1285567 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Funds used to buy land instead ofbuilding.
4238 | Administration, Planning and Support Services | Construction of Value Addition Factory Phase I | To construct Value Addition Factory Phase I | Value Addition Factory Phase I constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Naivasha East | -0.825465, 36.532288 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2021/22 | 2021/22 | 2023/24 | 3000000 | 2000000 | 2000000 | Equitable | EQUITABLE | 2000000 | 0 | 1285567 | 64.3 | 1285567 | 2000000 | 714433 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Not yet. Assessor remarks: Not yet complete.
4239 | Administration, Planning and Support Services | Construction of Kamere Beach kiosk phase II | To construct Kamere Beach kiosk phase II | Kamere Beach kiosk phase II constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Olkaria | -0.817132 36.32586 1922.199951171875 24.67099952697754 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2021/22 | 2021/22 | N/A | 5000000 | 4000000 | 4000000 | Equitable | Equitable | 4000000 | 0 | 1499994 | 37.5 | 1499994 | 4000000 | 2500006 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Viable when completed it will serve the purpose. Contractor: Willpo solutions. Assessor remarks: Ground handed over.
4240 | Administration, Planning and Support Services | Construction of Kamere Market stalls | To construct Kamere Market stalls | Kamere Market stalls constructed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Olkaria | -0.938098 36.365078 1907.1000000000001 8.300000190734863 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2021/22 | 2021/22 | N/A | 5000000 | 0 | 4000000 | Equitable | N/A | 4000000 | 0 | 1499994 | 100 | 1499994 | 4000000 | -1499994 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Not yet. Viable: Not yet because no business are. Assessor remarks: The stalls are in good condition but not operational.
4241 | Administration, Planning and Support Services | Installation of power to Kamere Beach kiosk and fish freezer | To install power to Kamere Beach kiosk and fish freezer | Power to Kamere Beach kiosk and fish freezer installed | 3110504 | Other Infrastructure and Civil Works | Naivasha | Olkaria | -0.817274, 36.326042 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2021/22 | 2021/22 | N/A | 1500000 | 1500000 | 1500000 | Equitable | EQUITABLE | 1500000 | 0 | 1998705 | 133.2 | 1998705 | 1500000 | -498705 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes.not yet since installation us not been done. Assessor remarks: Installation of power not done.
4242 | Administration, Planning and Support Services | Construction of kipsyenan cattle dip | To construct kipsyenan cattle dip | Kipsyenan cattle dip constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.08633, 35.937677 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2024/25 | 2024/25 | 2024/2025 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1986750 | 99.3 | 1986750 | 1882696 | 13250 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require fencing and construction of a public toilet.
4243 | Administration, Planning and Support Services | Renovation of Mauande cattle dip | To rehabilitate Mauande cattle dip to restore functionality | Mauande cattle dip rehabilitated | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.06361, 35.941616 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2024/25 | 2024/25 | 2024-2025 | 1100000 | 1100000 | 1100000 | Equitable | N/A | 1100000 | 0 | 672000 | 61.1 | 672000 | 1882696 | 428000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Cyntak Ventures ltd. Assessor remarks: A toilet required and a shade.
4244 | Administration, Planning and Support Services | Renovation of Sarambei cattle dip | To rehabilitate Sarambei cattle dip to restore functionality | Sarambei cattle dip rehabilitated | 3110504 | Other Infrastructure and Civil Works | Rongai | Soin | -0.06361, 35.941616 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2024/25 | 2024/25 | 2024-2025 | 1100000 | 1100000 | 1100000 | Equitable | N/A | 1100000 | 0 | 672000 | 61.1 | 672000 | 1882696 | 428000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Cyntak Ventures ltd. Assessor remarks: A toilet required and a shade.
4245 | Administration, Planning and Support Services | Construction Of Koimugul, Machine And Chelitit Cattle Dips | To construct Koimugul, Machine And Chelitit Cattle Dips | Koimugul, Machine And Chelitit Cattle Dips constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Solai | 0.151219, 36.19544 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2021/22 | 2021/22 | 2022 | 4000000 | 3999100 | 3999100 | Equitable | equitable | 3999100 | 0 | 3999100 | 100 | 3999100 | 3999100 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Functional.
4246 | Administration, Planning and Support Services | Construction of Limuru Cattle Dip and Renovation of Tuiyomoi cattle dip | To construct Limuru Cattle Dip and Renovation of Tuiyomoi cattle dip | Limuru Cattle Dip and Renovation of Tuiyomoi cattle dip constructed | 3110504 | Other Infrastructure and Civil Works | Rongai | Solai | 0.124977, 36.224388 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2022/23 | 2022/23 | 2025 | 2500000 | 2360000 | 402050 | Equitable | EQUITABLE | 402050 | 0 | 1957950 | 83 | 1957950 | 402050 | 402050 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: The cattle dip is broken down all the posts have been eaten by termites.
4247 | Administration, Planning and Support Services | Construction Of Kapket Tea Buying Centre | To construct Kapket Tea Buying Centre | Kapket Tea Buying Centre constructed | 3110504 | Other Infrastructure and Civil Works | Kuresoi South | Tinet | -0.520868 35.620393 2526.8999999999996 4 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2021/22 | 2021/22 | 2021/22 | 1500000 | 852825 | 852825 | Equitable | EQUITABLE | 852825 | 0 | 852725 | 100 | 852725 | 100 | 100 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
4248 | Administration, Planning and Support Services | Construction Of Tea Buying Centre At Saptet Kapkwen | To construct Tea Buying Centre At Saptet Kapkwen | Tea Buying Centre At Saptet Kapkwen constructed | 3110599 | Other Infrastructure and Civil Works | Kuresoi South | Amalo | -0.584673 35.680673 2593.1 4.800000190734863 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2019/20 | 2019/20 | 2019/20 | 1299170 | 1299170 | 1299170 | Equitable | EQUITABLE | 1299170 | 0 | 1215610 | 93.6 | 1215610 | 83560 | 83560 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: not yet. Viable: not yet. Assessor remarks: project ongoing.
4249 | Administration, Planning and Support Services | Fencing and installation of two gates at Gilgil slaughterhouse | To secure and installation of two gates at Gilgil slaughterhouse through fencing | And installation of two gates at Gilgil slaughterhouse fenced and secured | 3110599 | Other Infrastructure and Civil Works | Gilgil | Gilgil | -0.459991, 36.296639 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2022/23 | 2022/23 | 2022/23 | 2000000 | 1974364 | 1974364 | Equitable | EQUITABLE | 1974364 | 0 | 1974364 | 100 | 1974364 | 1974364 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Macknox contractors. Assessor remarks: In good state.
4250 | Administration, Planning and Support Services | Kikopey Slaughter House-Connecting Water and Electricity | To implement kikopey slaughter house-connecting water and electricity for agricultural development and food production | Kikopey Slaughter House-Connecting Water and Electricity completed | 3110599 | Other Infrastructure and Civil Works | Gilgil | Gilgil | -0.45999, 36.296642 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2023/24 | 2023/24 | 2023/24 | 500000 | 0 | 500000 | Equitable | EQUITABLE | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Partially. Viable: Not operational. Contractor: Willy samwa suppliers ltd. Assessor remarks: No water connection done.
4251 | Administration, Planning and Support Services | Connection of electricity at Saptet farmers cooperative | To implement connection of electricity at saptet farmers cooperative for agricultural development and food production | Connection of electricity at Saptet farmers cooperative completed | 3110599 | Other Infrastructure and Civil Works | Kuresoi South | Keringet | -0.488112, 35.706482 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2022/23 | 2022/23 | 2024 | 300000 | 300000 | 300000 | Equitable | Equitable | 300000 | 0 | 1758000 | 586 | 1758000 | 300000 | -1458000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Underfunded.
4252 | Administration, Planning and Support Services | Connection of electricity at Teta Cooperative Society Milk Coolant | To implement connection of electricity at teta cooperative society milk coolant for agricultural development and food production | Connection of electricity at Teta Cooperative Society Milk Coolant completed | 3110599 | Other Infrastructure and Civil Works | Kuresoi South | Keringet | -0.465005, 35.623853 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2022/23 | 2022/23 | N/A | 800000 | 0 | 800000 | Equitable | N/A | 800000 | 0 | 0 | 0 | 0 | 800000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Ongoing.
4253 | Administration, Planning and Support Services | Construction Of 6 Door Toilet at Oloiden Beach | To construct 6 Door Toilet at Oloiden Beach | 6 Door Toilet at Oloiden Beach constructed | 3110599 | Other Infrastructure and Civil Works | Naivasha | Maiella | -0.804803 36.246244 0 22.5 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2023/24 | 2023/24 | 2023/24 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Eruc Africa Ltd. Assessor remarks: In use.
4254 | Administration, Planning and Support Services | Construction Of Taita Slaughter Slab | To construct Taita Slaughter Slab | Taita Slaughter Slab constructed | 3110599 | Other Infrastructure and Civil Works | Kuresoi South | Tinet | -0.570268 35.61587 0 500 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2019/20 | 2019/20 | N/A | 1999838.44 | 0 | 1699838 | Equitable | N/A | 1699838 | 0 | 852725 | 100 | 852725 | 1699838 | -852725 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Ongoing almost complete.
4255 | Administration, Planning and Support Services | Purchase of 2 motorboats at Karagita Beach | To procure 2 motorboats at Karagita Beach | 2 motorboats at Karagita Beach procured | 3110702 | N/A | Naivasha | Hells Gate | -0.76238, 36.427085 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2022/23 | 2022/23 | 2022/23 | 3000000 | 2939000 | 2939000 | Equitable | EQUITABLE | 2939000 | 0 | 2939000 | 100 | 2939000 | 2939000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The boats are really helping the BMU to cater for major needs in the lake.
4256 | Administration, Planning and Support Services | Purchase Of Fishing Boats and Nets with Engines | To procure Fishing Boats and Nets with Engines | Fishing Boats and Nets with Engines procured | 3110702 | N/A | Naivasha | Lake View | -0.751714 36.457225 2030.9000244140625 39.599998474121094 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2023/24 | 2023/24 | 2023/24 | 3500000 | 7000000 | 7000000 | Equitable | N/A | 7000000 | 0 | 0 | 0 | 0 | 3500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Provide beanches, the floor is not smooth for proper cleaning..
4257 | Administration, Planning and Support Services | Purchase and supply of fishing gears, live jackets,etc | To procure and supply fishing gears, live jackets,etc | Fishing gears, live jackets,etc procured and supplied | 3110702 | N/A | Naivasha | Maiella | N/A | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2023/24 | 2023/24 | N/A | 400000 | 0 | 400000 | Equitable | N/A | 400000 | 0 | 0 | 0 | 0 | 1802000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4258 | Administration, Planning and Support Services | Purchase of two motorboats and engine at Oloiden beach | To procure two motorboats and engine at Oloiden beach | Two motorboats and engine at Oloiden beach procured | 3110702 | N/A | Naivasha | Maiella | -0.816635 36.262152 1868 19.700000762939453 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2023/24 | 2023/24 | 2023/24 | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Willpo Solutions Ltd. Assessor remarks: In Use.
4259 | Administration, Planning and Support Services | Purchase of a fishing boat for Arash dam | To procure a fishing boat for Arash dam | A fishing boat for Arash dam procured | 3110702 | N/A | Subukia | Subukia | -0.015297, 36.222267 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2024/25 | 2024/25 | 2024/2025 | 600000 | 600000 | 600000 | Equitable | N/A | 600000 | 0 | 3840551 | 640.1 | 3840551 | 0 | -3240551 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Details not availed. Assessor remarks: Boat in good working condition.
4260 | Procurement of potato value addition equipment (peeler, vacuum sealer, fryer, chipper) at ATC | Procurement of potato value addition equipment (peeler, vacuum sealer, fryer, chipper) at ATC | To procure and supply potato value addition equipment (peeler, vacuum sealer, fryer, chipper) at ATC | Potato value addition equipment (peeler, vacuum sealer, fryer, chipper) at ATC procured and supplied | 3110902 | Purchase of Household and Institutional Appliances | HQ | HQ | -0.173672, 35.862823 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2023/24 | 2023/24 | 2023/24 | 4000000 | 1000000 | 1000000 | N/A | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4261 | Equipping of ATC Soilo - acquisition of ICT equipment | Equipping of ATC Soilo - acquisition of ICT equipment | To equip ATC Soilo - acquisition of ICT equipment with necessary facilities and equipment | ATC Soilo - acquisition of ICT equipment equipped | 3111002 | Purchase of Computers, Printers and other IT Equipment | HQ | HQ | -0.173672, 35.862823 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2022/23 | 2022/23 | 2022/23 | 3000000 | 2553160 | 2553160 | N/A | N/A | 2553160 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4262 | Livestock Resource Management and Development | Procurement of potato value addition equipment (peeler, vacuum sealer, fryer, chipper) at ATC | To procure and supply potato value addition equipment (peeler, vacuum sealer, fryer, chipper) at ATC | Potato value addition equipment (peeler, vacuum sealer, fryer, chipper) at ATC procured and supplied | 3111103 | Purchase of Agricultural Machinery and Equipment | HQ | HQ | N/A | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2023/24 | 2023/24 | N/A | 4000000 | 1000000 | 1000000 | Equitable | Equitable | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
4263 | Administration, Planning and Support Services | Purchase of animals food mixer for Tulwobmoi farmers | To procure animals food mixer for Tulwobmoi farmers | Animals food mixer for Tulwobmoi farmers procured | 3111103 | Purchase of Agricultural Machinery and Equipment | Rongai | Menengai West | -0.16778, 36.01238 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2024/25 | 2024/25 | 2024/25 | 800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Item not yet delivered.
4264 | Administration, Planning and Support Services | Purchase And Supply of Incubator for Solai Poultry Groups | To procure and supply Incubator for Solai Poultry Groups | Incubator for Solai Poultry Groups procured and supplied | 3111103 | Purchase of Agricultural Machinery and Equipment | Rongai | Solai | 0.012178 36.158958 1583.535400390625 19.145000457763672 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2023/24 | 2023/24 | 2023/24 | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Fully functional.
4265 | Administration, Planning and Support Services | Operationalization of existing coolers - purchase of backup Generators for milk coolers | To implement operationalization of existing coolers - purchase of backup generators for milk coolers for agricultural development and food production | Operationalization of existing coolers - purchase of backup Generators for milk coolers completed | 3111120 | Purchase of Specialized Plant. - | HQ | HQ | N/A | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2023/24 | 2023/24 | N/A | 19500000 | 19500000 | 19500000 | Equitable | N/A | 19500000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4266 | Administration, Planning and Support Services | Completion of Kiptagich Milk cooling plant | To complete Kiptagich Milk cooling plant | Kiptagich Milk cooling plant completed | 3111120 | Purchase of Specialized Plant. - | Kuresoi South | Kiptagich | -0.574248, 35.617453 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2024/25 | 2024/25 | 15 June 2025 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 1974700 | 131.6 | 1974700 | 1974700 | -474700 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Not yet. Viable: Viable. Assessor remarks: Need electricity for cooling plant to be operational.
4267 | Administration, Planning and Support Services | Construction of Kiptagich milk cooling plant | To construct Kiptagich milk cooling plant | Kiptagich milk cooling plant constructed | 3111120 | Purchase of Specialized Plant. - | Kuresoi South | Kiptagich | -0.574248, 35.617453 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2022/23 | 2022/23 | 15 June 2025 | 2000000 | 1974700 | 1974700 | Equitable | N/A | 1974700 | 0 | 1974700 | 100 | 1974700 | 1974700 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Not yet. Viable: Viable. Assessor remarks: Need electricity for cooling plant to be operational.
4268 | Administration, Planning and Support Services | Purchase And Supply Of Incubators | To procure and supply Incubators | Incubators procured and supplied | 3111120 | Purchase of Specialized Plant. - | Naivasha | Maiella | -0.816635 36.262152 1868 19.700000762939453 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2021/22 | 2021/22 | 2021/22 | 2000000 | 1802000 | 1802000 | Equitable | N/A | 1802000 | 0 | 0 | 0 | 0 | 1802000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Willpo Solutions Ltd. Assessor remarks: In Use.
4269 | Administration, Planning and Support Services | Purchase of Incubators for Youth poultry Project at Mosop Ward | To procure Incubators for Youth poultry Project at Mosop Ward | Incubators for Youth poultry Project at Mosop Ward procured | 3111120 | Purchase of Specialized Plant. - | Rongai | Mosop | -0.299893 35.954843 2191.6000000000004 5 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2022/23 | 2022/23 | 2022/23 | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 0 | 0 | 0 | 700000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: Viable. Contractor: Not indicated. Assessor remarks: Not functioning.
4270 | Administration, Planning and Support Services | Renovation Of Mulango Tea Buying Centre | To rehabilitate Mulango Tea Buying Centre to restore functionality | Mulango Tea Buying Centre rehabilitated | 3111299 | Rehabilitation & Renovation - | Kuresoi South | Kiptagich | -0.59592, 35.589018 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2021/22 | 2021/22 | 2021/22 | 800000 | 800000 | 800000 | Equitable | EQUITABLE | 800000 | 0 | 800000 | 100 | 800000 | 800000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Assessor remarks: Need table and electrification.
4271 | Administration, Planning and Support Services | Purchase and Supply of Pyrethrum seedlings | To procure and supply Pyrethrum seedlings | Pyrethrum seedlings procured and supplied | 3111301 | Purchase of Certified Crop Seed | Gilgil | Eburru mbaruk | N/A | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2024/25 | 2024/25 | N/A | 1800000 | 0 | 1800000 | Equitable | N/A | 1800000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
4272 | Administration, Planning and Support Services | Purchase and supply of pyrethrum seedlings | To procure and supply pyrethrum seedlings | Pyrethrum seedlings procured and supplied | 3111301 | Purchase of Certified Crop Seed | Gilgil | Elementaita | -0.59591, 36.11219 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2023/24 | 2023/24 | 2023/24 | 4000000 | 1600000 | 9600000 | Equitable | N/A | 9600000 | 0 | 1600000 | 100 | 1600000 | 4000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Well done.
4273 | Crop Development and Management | Purchase and Distribution of maize seeds for vulnerable farmers | To procure and Distribution of maize seeds for vulnerable farmers | And Distribution of maize seeds for vulnerable farmers procured | 3111301 | Purchase of Certified Crop Seed | HQ | HQ | N/A | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2024/25 | 2024/25 | 2024/25 | 12610260 | 0 | 12610260 | Equitable | N/A | 12610260 | 0 | 37299997 | 100 | 37299997 | 2700003 | -37299997 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4274 | Administration, Planning and Support Services | Purchase and distribution of pyrethrum seedlings to farmers in Nakuru county | To procure and distribution of pyrethrum seedlings to farmers in Nakuru county | And distribution of pyrethrum seedlings to farmers in Nakuru county procured | 3111301 | Purchase of Certified Crop Seed | HQ | HQ | N/A | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2022/23 | 2022/23 | 2022/23 | 50000000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 37299997 | 1065.7 | 37299997 | 2700003 | -33799997 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4275 | Administration, Planning and Support Services | Purchase and distribution of Pyrethrum seedlings to farmers | To procure and distribution of Pyrethrum seedlings to farmers | And distribution of Pyrethrum seedlings to farmers procured | 3111301 | Purchase of Certified Crop Seed | HQ | HQ | N/A | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2023/24 | 2023/24 | 2023/24 | 40000000 | 0 | 2999997 | Equitable | N/A | 2999997 | 0 | 37299997 | 100 | 37299997 | 2700003 | -37299997 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4276 | Crop Development and Management | Supply and Distribution of Pyrethrum seedlings | To implement supply and distribution of pyrethrum seedlings for agricultural development and food production | Supply and Distribution of Pyrethrum seedlings completed | 3111301 | Purchase of Certified Crop Seed | HQ | HQ | N/A | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2024/25 | 2024/25 | 2024/25 | 40000000 | 30000000 | 27500000 | Equitable | N/A | 27500000 | 0 | 37299997 | 124.3 | 37299997 | 2700003 | -7299997 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4277 | Administration, Planning and Support Services | Supply Of Pyrethrum Seedlings Across the Ward | To implement supply of pyrethrum seedlings across the ward for agricultural development and food production | Supply Of Pyrethrum Seedlings Across the Ward completed | 3111301 | Purchase of Certified Crop Seed | Njoro | Kihingo | -0.481317, 35.982887 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2023/24 | 2023/24 | 2025 | 3992580 | 3992580 | 3992580 | Equitable | N/A | 3992580 | 0 | 1000000 | 25 | 1000000 | 3992580 | 2992580 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Farmers were given ten seedlings each.
4278 | Administration, Planning and Support Services | Purchase and Supply of Pyrethrum seedlings | To procure and supply Pyrethrum seedlings | Pyrethrum seedlings procured and supplied | 3111301 | Purchase of Certified Crop Seed | Naivasha | Naivasha East | -0.783307, 36.533136 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2024/25 | 2024/25 | 2025 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 799800 | 53.3 | 799800 | 0 | 700200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Projects successful to farmers should target more farmers.
4279 | Administration, Planning and Support Services | Purchase of Onion seeds (melbone F1) | To procure Onion seeds (melbone F1) | Onion seeds (melbone F1) procured | 3111301 | Purchase of Certified Crop Seed | Naivasha | Naivasha East | -0.817942, 36.545027 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2024/25 | 2024/25 | 2025 | 1200000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 799800 | 66.6 | 799800 | 0 | 400200 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Onion supply was done during dry season n.
4280 | Administration, Planning and Support Services | Purchase and Supply of Pyrethrum seedlings | To procure and supply Pyrethrum seedlings | Pyrethrum seedlings procured and supplied | 3111301 | Purchase of Certified Crop Seed | Kuresoi North | Nyota | -0.309268 35.575838 2618.7000000000003 10.600000381469727 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2024/25 | 2024/25 | 2024/25 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1474566 | 147.5 | 1474566 | 0 | -474566 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: Partially. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
4281 | Administration, Planning and Support Services | Purchase of one month old improved kienyeji chicks for empowement in biashara naivasha | To procure one month old improved kienyeji chicks for empowement in biashara naivasha | One month old improved kienyeji chicks for empowement in biashara naivasha procured | 3111302 | Purchase of Animals and Breeding Stock | Naivasha | Biashara naivasha | N/A | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2024/25 | 2024/25 | N/A | 1500000 | 0 | 1500000 | Equitable | N/A | 1500000 | 0 | 3999880 | 100 | 3999880 | 3999880 | -3999880 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4282 | Administration, Planning and Support Services | Purchase and Supply of Dorper Sheep | To procure and supply Dorper Sheep | Dorper Sheep procured and supplied | 3111302 | Purchase of Animals and Breeding Stock | Gilgil | Elementaita | -0.59588, 36.112035 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2022/23 | 2022/23 | N/A | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 1600000 | 100 | 1600000 | 2000000 | -1600000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Well done.
4283 | Administration, Planning and Support Services | Purchase and supply of one month old chicks | To procure and supply one month old chicks | One month old chicks procured and supplied | 3111302 | Purchase of Animals and Breeding Stock | Gilgil | Elementaita | -0.566368, 36.116833 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2022/23 | 2022/23 | 2022/23 | 4000000 | 3716300 | 3716300 | Equitable | N/A | 3716300 | 0 | 3716290 | 100 | 3716290 | 10 | 10 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational.
4284 | Administration, Planning and Support Services | Purchase and supply of daily goats for women groups | To procure and supply daily goats for women groups | Daily goats for women groups procured and supplied | 3111302 | Purchase of Animals and Breeding Stock | Gilgil | Gilgil | -0.448634 36.282639 1893.47802734375 12.605999946594238 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2023/24 | 2023/24 | 2023/24 | 800000 | 800000 | 800000 | Equitable | EQUITABLE | 800000 | 0 | 800000 | 100 | 800000 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Ripasol enterprises. Assessor remarks: In good state.
4285 | Administration, Planning and Support Services | Purchase of one month old improved kienyeji chicks for empowement in Gilgil ward | To procure one month old improved kienyeji chicks for empowement in Gilgil ward | One month old improved kienyeji chicks for empowement in Gilgil ward procured | 3111302 | Purchase of Animals and Breeding Stock | Gilgil | Gilgil | -0.507865, 36.323621 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2024/25 | 2024/25 | N/A | 1400000 | 0 | 1400000 | Equitable | N/A | 1400000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Chickens in good health.
4286 | Fisheries Development | Restocking of fingerlings to Lake Naivasha | To implement restocking of fingerlings to lake naivasha for agricultural development and food production | Restocking of fingerlings to Lake Naivasha completed | 3111302 | Purchase of Animals and Breeding Stock | HQ | HQ | N/A | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2022/23 | 2022/23 | 2022/23 | 10000000 | 4533338 | 4533338 | Equitable | equitable | 4533338 | 0 | 2386000 | 52.6 | 2386000 | 4533338 | 2147338 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4287 | Livestock Resource Management and Development | Subsidized AI programme | To implement subsidized ai programme for agricultural development and food production | Subsidized AI programme completed | 3111302 | Purchase of Animals and Breeding Stock | HQ | HQ | N/A | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2024/25 | 2024/25 | N/A | 15000000 | 8110067 | 6610067 | Equitable | N/A | 6610067 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
4288 | Administration, Planning and Support Services | Supple of one month old chicks | To implement supple of one month old chicks for agricultural development and food production | Supple of one month old chicks completed | 3111302 | Purchase of Animals and Breeding Stock | Nakuru East | Menengai | -0.266298 36.100687 1913.5 100 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2022/23 | 2022/23 | 2022/23 | 1000000 | 947850 | 947850 | Equitable | EQUITABLE | 947850 | 0 | 947850 | 100 | 947850 | 947850 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: Lumiseal enterprise. Assessor remarks: Complete.
4289 | Administration, Planning and Support Services | Supply of one month old chicks for Menengai Ward PLWD Group | To implement supply of one month old chicks for menengai ward plwd group for agricultural development and food production | Supply of one month old chicks for Menengai Ward PLWD Group completed | 3111302 | Purchase of Animals and Breeding Stock | Nakuru East | Menengai | -0.266245 36.100625 1913.5 20 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2022/23 | 2022/23 | 2022/23 | 1000000 | 3795250 | 3795250 | Equitable | EQUITABLE | 3795250 | 0 | 3715250 | 97.9 | 3715250 | 80000 | 80000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Lewamu construction. Assessor remarks: Completed.
4290 | Administration, Planning and Support Services | Purchase of one month old improved kienyeji chicks for empowement | To procure one month old improved kienyeji chicks for empowement | One month old improved kienyeji chicks for empowement procured | 3111302 | Purchase of Animals and Breeding Stock | Nakuru East | Menengai | -0.274685, 36.113265 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2024/25 | 2024/25 | 2024/25 | 7000000 | 0 | 7000000.41 | Equitable | N/A | 7000000.41 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
4291 | Administration, Planning and Support Services | Purchase of 3 months improved Kienyeji chicks | To procure 3 months improved Kienyeji chicks | 3 months improved Kienyeji chicks procured | 3111302 | Purchase of Animals and Breeding Stock | Naivasha | Naivasha East | -0.805083, 36.532995 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2024/25 | 2024/25 | June 2025 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 1435600 | 47.9 | 1435600 | 0 | 1564400 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Successful project.
4292 | Administration, Planning and Support Services | Purchase And Supply of One-Month Old Chicks to groups | To procure and supply One-Month Old Chicks to groups | One-Month Old Chicks to groups procured and supplied | 3111302 | Purchase of Animals and Breeding Stock | Nakuru East | Nakuru East | -0.40938, 36.141373 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2023/24 | 2023/24 | 2023/2024 | 1000000 | 1000000 | 1000000 | Equitable | EQUITABLE | 1000000 | 0 | 894784 | 89.5 | 894784 | 105216 | 105216 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Restocking needed.
4293 | Administration, Planning and Support Services | Buying and distribution of one month old layers breeds | To procure and distribution of one month old layers breeds | And distribution of one month old layers breeds procured | 3111302 | Purchase of Animals and Breeding Stock | Naivasha | Olkaria | 0.833945, 36.342031 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2023/24 | 2023/24 | 2023/24 | 988874 | 0 | 988874 | Equitable | N/A | 988874 | 0 | 0 | 0 | 0 | 988874 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Chicks have grown and laying eggs improving nutrition value and income generation. Assessor remarks: Chick's distributed to 32 farmers.
4294 | Administration, Planning and Support Services | Purchase Of One (1) Month Old Improved Kienyeji Chicks | To procure One (1) Month Old Improved Kienyeji Chicks | One (1) Month Old Improved Kienyeji Chicks procured | 3111302 | Purchase of Animals and Breeding Stock | Naivasha | Olkaria | 0.830138 36.338593 1895.69951171875 27.18400001525879 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2023/24 | 2023/24 | N/A | 1896500 | 0 | 1896500 | Equitable | EQUITABLE | 1896500 | 0 | 1996616 | 100 | 1996616 | 1896500 | -1996616 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Sports equipment supplied and delivered to olkaria teams.
4295 | Administration, Planning and Support Services | Promotion of livestock (purchase of acaricides) | To implement promotion of livestock (purchase of acaricides) for agricultural development and food production | Promotion of livestock (purchase of acaricides) completed | 3111302 | Purchase of Animals and Breeding Stock | Rongai | Soin | -0.076048 36.07639 1656.8 8.5 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2024/25 | 2024/25 | N/A | 500000 | 0 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Luki Contractors. Assessor remarks: In good condition.
4296 | Administration, Planning and Support Services | Purchase & Supply of Jersey cow breeds at Kapsetek | To procure & Supply of Jersey cow breeds at Kapsetek | & Supply of Jersey cow breeds at Kapsetek procured | 3111302 | Purchase of Animals and Breeding Stock | Rongai | Soin | -0.035155 35.977 1537.2 61.029998779296875 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2024/25 | 2024/25 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 1924100 | 384.8 | 1924100 | 1924100 | -1424100 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The bridge needs guard rails.
4297 | Administration, Planning and Support Services | Purchase and supply of one month old chicks | To procure and supply one month old chicks | One month old chicks procured and supplied | 3111302 | Purchase of Animals and Breeding Stock | Molo | Turi | -0.279395 35.753738 2477.9 9.800000190734863 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2024/25 | 2024/25 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 98570 | 9.9 | 98570 | 0 | 901430 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The land was bought by the county, the title of the land to be confirmed by the department.
4298 | Administration, Planning and Support Services | Purchase of Avocado seedlings for farmers in Bahati ward | To procure Avocado seedlings for farmers in Bahati ward | Avocado seedlings for farmers in Bahati ward procured | 3111305 | Beautification and Tree Planting | Bahati | Bahati | -0.156442, 36.146429 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2024/25 | 2024/25 | 2024/25 | 2000000 | 2000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 1999950 | 100 | 1999950 | 0 | 50 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: 4437 seedlings were distributed.
4299 | Administration, Planning and Support Services | Purchase of Avocado seedlings | To procure Avocado seedlings | Avocado seedlings procured | 3111305 | Beautification and Tree Planting | Bahati | Dundori | -0.22946, 36.184972 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2024/25 | 2024/25 | 2024/2025 | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Survival rate of avocado seedlings is low.
4300 | Administration, Planning and Support Services | Purchase and supply of Avocado seedlings in Eburru Mbaruk Ward | To procure and supply Avocado seedlings in Eburru Mbaruk Ward | Avocado seedlings in Eburru Mbaruk Ward procured and supplied | 3111305 | Beautification and Tree Planting | Gilgil | Eburru mbaruk | N/A | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2024/25 | 2024/25 | N/A | 1800000 | 0 | 1800000 | Equitable | N/A | 1800000 | 0 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | N/A
4301 | Administration, Planning and Support Services | Supply and delivery of Avocado seedlings to farmers | To implement supply and delivery of avocado seedlings to farmers for agricultural development and food production | Supply and delivery of Avocado seedlings to farmers completed | 3111305 | Beautification and Tree Planting | HQ | HQ | N/A | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2023/24 | 2023/24 | 2023/24 | 35000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 32480684 | 100 | 32480684 | 2519316 | -32480684 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4302 | Crop Development and Management | Supply of Avocado seedlings | To implement supply of avocado seedlings for agricultural development and food production | Supply of Avocado seedlings completed | 3111305 | Beautification and Tree Planting | HQ | HQ | N/A | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2024/25 | 2024/25 | 2024/25 | 27000000 | 15000000 | 20500000 | Equitable | N/A | 20500000 | 0 | 32480684 | 216.5 | 32480684 | 2519316 | -17480684 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4303 | Administration, Planning and Support Services | Purchase and supply of Avocado seedlings in Kabatini Ward | To procure and supply Avocado seedlings in Kabatini Ward | Avocado seedlings in Kabatini Ward procured and supplied | 3111305 | Beautification and Tree Planting | Bahati | Kabatini | -0.199095, 36.181172 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2024/25 | 2024/25 | 2025 | 1300000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 1500000 | 115.4 | 1500000 | 0 | -200000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Very good project since it helps in agroforestry and economic empowerment.
4304 | Administration, Planning and Support Services | Purchase Of Tree Seedlings for Youth groups across Maiella Ward | To procure Tree Seedlings for Youth groups across Maiella Ward | Tree Seedlings for Youth groups across Maiella Ward procured | 3111305 | Beautification and Tree Planting | Naivasha | Maiella | -0.816635 36.262152 1868 19.700000762939453 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2023/24 | 2023/24 | N/A | 300000 | 0 | 300000 | Equitable | N/A | 300000 | 0 | 2999272 | 100 | 2999272 | 300000 | -2999272 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Willpo Solutions Ltd. Assessor remarks: In Use.
4305 | Administration, Planning and Support Services | Supply of hass Avocado, Pyrethrum and Onion Seedling for Malewa West farmers | To implement supply of hass avocado, pyrethrum and onion seedling for malewa west farmers for agricultural development and food production | Supply of hass Avocado, Pyrethrum and Onion Seedling for Malewa West farmers completed | 3111305 | Beautification and Tree Planting | Gilgil | Malewa West | -0.540541 36.34396 0 2000 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2023/24 | 2023/24 | 2023/24 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good project.
4306 | Administration, Planning and Support Services | Supply Of Avocado Seedlings Across the Ward | To implement supply of avocado seedlings across the ward for agricultural development and food production | Supply Of Avocado Seedlings Across the Ward completed | 3111305 | Beautification and Tree Planting | Molo | Mariashoni | -0.342268, 35.808096 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2023/24 | 2023/24 | 2023/24 | 881000 | 881000 | 881000 | Equitable | EQUITABLE | 881000 | 0 | 999999 | 113.5 | 999999 | 881000 | -118999 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Not yet. Viable: Not yet. Assessor remarks: Weather conditions not favourable.
4307 | Administration, Planning and Support Services | Purchase and supply of Avocado seedlings | To procure and supply Avocado seedlings | Avocado seedlings procured and supplied | 3111305 | Beautification and Tree Planting | Njoro | Nessuit | -0.409479, 35.870666 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2024/25 | 2024/25 | 2024/25 | 2000000 | 2000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 4979840 | 249 | 4979840 | 0 | -2979840 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is doing well. Farmers request that seedlings should be distributed during the rains and regular visits by agricultural extension officers.
4308 | Administration, Planning and Support Services | Supply Of Avocado Seedlings Across the Ward | To implement supply of avocado seedlings across the ward for agricultural development and food production | Supply Of Avocado Seedlings Across the Ward completed | 3111305 | Beautification and Tree Planting | Subukia | Subukia | -0.047792, 36.233353 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2023/24 | 2024/25 | 2023/2024 | 4000197 | 6000000 | 8000197 | Equitable | N/A | 8000197 | 0 | 4000000 | 66.7 | 4000000 | 0 | 2000000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: Not availed. Assessor remarks: The avocado trees doing well in the farms.
4309 | Administration, Planning and Support Services | Purchase of Avocado seedlings | To procure Avocado seedlings | Avocado seedlings procured | 3111305 | Beautification and Tree Planting | Subukia | Waseges | 0.02338 36.262172 1995.300048828125 5.199999809265137 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2024/25 | 2024/25 | N/A | 2000000 | 2000000 | 1500000 | Equitable | N/A | 1500000 | 0 | 4762700 | 238.1 | 4762700 | 0 | -2762700 | N/A | 75 | N/A | N/A | N/A | N/A | N/A | Yes | N/A | N/A | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The land has already been purchased.
4310 | Administration, Planning and Support Services | Purchase and supply of bio fertilizer | To procure and supply bio fertilizer | Bio fertilizer procured and supplied | 3111399 | Purchase. of Certified Seeds - Ot | Gilgil | Elementaita | -0.584117 36.108603 2110.400146484375 1.0089999437332153 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2022/23 | 2022/23 | 2022/23 | 1700000 | 1700000 | 6200000 | Equitable | EQUITABLE | 6200000 | 0 | 6099940 | 358.8 | 6099940 | 100060 | -4399940 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: Doing well.
4311 | Administration, Planning and Support Services | Supply Of Coffee Seedlings to Farmers in Kabazi Ward | To implement supply of coffee seedlings to farmers in kabazi ward for agricultural development and food production | Supply Of Coffee Seedlings to Farmers in Kabazi Ward completed | 3111399 | Purchase. of Certified Seeds - Ot | Subukia | Kabazi | -0.04596, 35.94188 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2023/24 | 2023/24 | 2024/25 | 2016621 | 2016621 | 2016621 | Equitable | N/A | 2016621 | 0 | 0 | 0 | 0 | 2016621 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated. Assessor remarks: Farmers requested for additional seedlings.
4312 | Administration, Planning and Support Services | Supply Of Pyrethrum Seedlings Across the Ward | To implement supply of pyrethrum seedlings across the ward for agricultural development and food production | Supply Of Pyrethrum Seedlings Across the Ward completed | 3111399 | Purchase. of Certified Seeds - Ot | Molo | Mariashoni | -0.378629, 35.800637 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2023/24 | 2023/24 | 2023/24 | 1000000 | 1000000 | 1000000 | Equitable | EQUITABLE | 1000000 | 0 | 999999 | 100 | 999999 | 1 | 1 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
4313 | Administration, Planning and Support Services | Purchase of Bio Fertilizer | To procure Bio Fertilizer | Bio Fertilizer procured | 3111399 | Purchase. of Certified Seeds - Ot | Njoro | Mau Narok | -0.597785 35.999365 2574.8999999999996 3.4000000953674316 | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2022/23 | 2022/23 | 2022/23 | 4400000 | 4400000 | 4400000 | Equitable | EQUITABLE | 4400000 | 0 | 4400000 | 100 | 4400000 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: Not viable. Assessor remarks: Bad state of repair.
4314 | Administration, Planning and Support Services | Supply Of Pyrethrum Seedlings Across the Ward | To implement supply of pyrethrum seedlings across the ward for agricultural development and food production | Supply Of Pyrethrum Seedlings Across the Ward completed | 3111399 | Purchase. of Certified Seeds - Ot | Kuresoi North | Nyota | N/A | 4582 | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | AGRICULTURE, LIVESTOCK, FISHERIES AND VETERINARY SERVICES | N/A | 2023/24 | 2023/24 | 2023/24 | 2800000 | 2800000 | 2800000 | Equitable | N/A | 2800000 | 0 | 2800000 | 100 | 2800000 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4315 | Development of regeneration masterplan for two Townships - Njoro and Maai Mahiu | Development of regeneration masterplan for two Townships - Njoro and Maai Mahiu | To develop regeneration masterplan for two Townships - Njoro and Maai Mahiu | Regeneration masterplan for two Townships - Njoro and Maai Mahiu developed | 2211310 | Contracted Professional Services | HQ | HQ | N/A | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2024/25 | 2024/25 | N/A | 8338233 | 0 | 4964411 | Equitable | N/A | 4964411 | 0 | 0 | 0 | 0 | 0 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
4316 | Planning of four trading centres (Banita-Soin, Kiptagich, Mutaita-Elementaita) | Planning of four trading centres (Banita-Soin, Kiptagich, Mutaita-Elementaita) | To develop of four trading centres (Banita-Soin, Kiptagich, Mutaita-Elementaita) | Of four trading centres (Banita-Soin, Kiptagich, Mutaita-Elementaita) developed | 2211310 | Contracted Professional Services | HQ | HQ | N/A | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2024/25 | 2024/25 | N/A | 10000000 | 0 | 8000000 | Equitable | N/A | 8000000 | 0 | 0 | 0 | 0 | 0 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
4317 | Surveying of Trading Centres (Subukia, Salgaa, Moi Ndabibi) | Surveying of Trading Centres (Subukia, Salgaa, Moi Ndabibi) | To survey Trading Centres (Subukia, Salgaa, Moi Ndabibi) for planning and development | Trading Centres (Subukia, Salgaa, Moi Ndabibi) surveyed | 2211310 | Contracted Professional Services | HQ | HQ | N/A | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2024/25 | 2024/25 | N/A | 10600000 | 0 | 8000000 | Equitable | N/A | 8000000 | 0 | 2710014 | 100 | 2710014 | 16185696 | -2710014 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
4318 | Planning of Olrongai trading center | Planning of Olrongai trading center | To develop of Olrongai trading center | Of Olrongai trading center developed | 2211310 | Contracted Professional Services | Rongai | Menengai West | -0.146657, 36.009242 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2024/25 | 2024/25 | 2024/25 | 2500000 | 0 | 2500000 | Equitable | N/A | 2500000 | 0 | 0 | 0 | 0 | 2500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Not yet seen then viability.
4319 | Conditional Fund - World Bank Kenya Informal Settlement Improvement Project II (KISIP II) | Conditional Fund - World Bank Kenya Informal Settlement Improvement Project II (KISIP II) | To implement conditional fund - world bank kenya informal settlement improvement project ii (kisip ii) for orderly land use and housing provision | Conditional Fund - World Bank Kenya Informal Settlement Improvement Project II (KISIP II) completed | 2630203 | N/A | HQ | HQ | -0.173672, 35.862823 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2024/25 | 2024/25 | 2024/25 | 550000000 | 550000000 | 0 | N/A | N/A | 0 | 550000000 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4320 | Construction of Karagita Settlement Water Supply Pipeline for Nakuru County Settlement Infrastructure Improvement Works | Construction of Karagita Settlement Water Supply Pipeline for Nakuru County Settlement Infrastructure Improvement Works | To construct Karagita Settlement Water Supply Pipeline for Nakuru County Settlement Infrastructure Improvement Works | Karagita Settlement Water Supply Pipeline for Nakuru County Settlement Infrastructure Improvement Works constructed | 2630203 | N/A | HQ | HQ | -0.173672, 35.862823 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2023/24 | 2023/24 | 2023/24 | 107228702 | 0 | 0 | N/A | N/A | 0 | 66174363.5 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4321 | Construction of Roads Footpaths, Non-Motorized Transport Facilities, Storm Water Drainage, High Mast Floodlights and Sewer Works In Lakeview, London/Hilton and Kwa Murogi Settlements for the Nakuru County Settlements Infrastructure Improvement Works | Construction of Roads Footpaths, Non-Motorized Transport Facilities, Storm Water Drainage, High Mast Floodlights and Sewer Works In Lakeview, London/Hilton and Kwa Murogi Settlements for the Nakuru County Settlements Infrastructure Improvement Works | To construct Roads Footpaths, Non-Motorized Transport Facilities, Storm Water Drainage, High Mast Floodlights and Sewer Works In Lakeview, London/Hilton and Kwa Murogi Settlements for the Nakuru County Settlements Infrastructure Improvement Works | Roads Footpaths, Non-Motorized Transport Facilities, Storm Water Drainage, High Mast Floodlights and Sewer Works In Lakeview, London/Hilton and Kwa Murogi Settlements for the Nakuru County Settlements Infrastructure Improvement Works constructed | 2630203 | N/A | HQ | HQ | -0.173672, 35.862823 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2023/24 | 2023/24 | 2023/24 | 475999332 | 0 | 0 | N/A | N/A | 0 | 227965839.02 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4322 | Reroofing of Flamingo Estate County Houses | Reroofing of Flamingo Estate County Houses | To implement reroofing of flamingo estate county houses for orderly land use and housing provision | Reroofing of Flamingo Estate County Houses completed | 3110301 | Refurbishment of Residential Buildings | Nakuru East | Flamingo | -0.302183, 36.079475 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2022/23 | 2022/23 | 2024/25 | 2696440 | 2442400 | 2696440 | Equitable | N/A | 2696440 | 0 | 2996976 | 122.7 | 2996976 | 2696440 | -554576 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: ECRAT merchants ltd.
4323 | Re-roofing of houses at Flamingo Estate Section 4 | Re-roofing of houses at Flamingo Estate Section 4 | To implement re-roofing of houses at flamingo estate section 4 for orderly land use and housing provision | Re-roofing of houses at Flamingo Estate Section 4 completed | 3110301 | Refurbishment of Residential Buildings | Nakuru East | Flamingo | -0.302255, 36.079451 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2024/25 | 2024/25 | 2024/25 | 4718000 | 4718000 | 4718000 | Equitable | N/A | 4718000 | 0 | 850000 | 18 | 850000 | 4718000 | 3868000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
4324 | Re-roofing of Ojuka and Kaloleni A Estates in Kivumbini Ward | Re-roofing of Ojuka and Kaloleni A Estates in Kivumbini Ward | To implement re-roofing of ojuka and kaloleni a estates in kivumbini ward for orderly land use and housing provision | Re-roofing of Ojuka and Kaloleni A Estates in Kivumbini Ward completed | 3110301 | Refurbishment of Residential Buildings | Nakuru East | Kivumbini | -0.298701, 36.082235 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2024/25 | 2024/25 | N/A | 2600000 | 2600000 | 2600000 | Equitable | N/A | 2600000 | 0 | 1925746 | 74.1 | 1925746 | 2600000 | 674254 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4325 | Survey, Valuation, Mapping And Conveyancing Cost (Ahero market 0.045ha, Maili kumi market 0.0419ha, Wanyororo market 0.0888ha, Wanyororo market 0.0878ha) | Survey, Valuation, Mapping And Conveyancing Cost (Ahero market 0.045ha, Maili kumi market 0.0419ha, Wanyororo market 0.0888ha, Wanyororo market 0.0878ha) | To implement survey, valuation, mapping and conveyancing cost (ahero market 0.045ha, maili kumi market 0.0419ha, wanyororo market 0.0888ha, wanyororo market 0.0878ha) for orderly land use and housing provision | Survey, Valuation, Mapping And Conveyancing Cost (Ahero market 0.045ha, Maili kumi market 0.0419ha, Wanyororo market 0.0888ha, Wanyororo market 0.0878ha) completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Bahati | N/A | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2019/20 | 2019/20 | N/A | 1580000 | 0 | 1580000 | Equitable | N/A | 1580000 | 0 | 0 | 0 | 0 | 1580000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4326 | Survey And Mapping (Titling Of Land) | Survey And Mapping (Titling Of Land) | To survey And Mapping (Titling Of Land) for planning and development | And Mapping (Titling Of Land) surveyed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2018/19 | 2018/19 | N/A | 12991330 | 0 | 5740580 | Equitable | N/A | 5740580 | 0 | 2250750 | 100 | 2250750 | 10740580 | -2250750 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4327 | Upgrading of sewer line at Naivasha Sub County Estate | Upgrading of sewer line at Naivasha Sub County Estate | To upgrade sewer line at Naivasha Sub County Estate through tarmacking for improved road connectivity | Sewer line at Naivasha Sub County Estate tarmacked and upgraded | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2022/23 | 2022/23 | 2022/23 | 20500000 | 5722476 | 842585.3 | Equitable | N/A | 842585.3 | 0 | 4879891 | 85.3 | 4879891 | 842585 | 842585 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4328 | Surveying Of Trading Centres | Surveying Of Trading Centres | To survey Trading Centres for planning and development | Trading Centres surveyed | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2019/20 | 2019/20 | N/A | 18895710 | 0 | 6185695.75 | Equitable | N/A | 6185695.75 | 0 | 2710014 | 100 | 2710014 | 16185696 | -2710014 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4329 | Equipping of 2 Semi Automated Block Making Machines | Equipping of 2 Semi Automated Block Making Machines | To equip 2 Semi Automated Block Making Machines with necessary facilities and equipment | 2 Semi Automated Block Making Machines equipped | 3111120 | Purchase of Specialized Plant. - | HQ | HQ | -0.173672, 35.862823 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2023/24 | 2023/24 | 2023/24 | 4000000 | 4000000 | 4000000 | N/A | N/A | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4330 | Purchase of 1 additional Semi Automated Block Making Machine | Purchase of 1 additional Semi Automated Block Making Machine | To procure 1 additional Semi Automated Block Making Machine | 1 additional Semi Automated Block Making Machine procured | 3111120 | Purchase of Specialized Plant. - | HQ | HQ | -0.173672, 35.862823 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2023/24 | 2023/24 | 2023/24 | 2000000 | 0 | 2000000 | N/A | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4331 | Survey and planning of New game mutukanio | Survey and planning of New game mutukanio | To survey and planning of New game mutukanio for planning and development | And planning of New game mutukanio surveyed | 3111401 | Pre-Feasibility, Feasibility & Appraisal Studies | Gilgil | Elementaita | -0.586295 36.086254 2013.107 0.7870000004768372 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2024/25 | 2024/25 | N/A | 7000000 | 7000000 | 7000000 | Equitable | N/A | 7000000 | 0 | 0 | 0 | 0 | 7000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Assessor remarks: Needs urgent attention.
4332 | Survey and titling of plots within Manyani Estate in Kivumbini Ward | Survey and titling of plots within Manyani Estate in Kivumbini Ward | To survey and titling of plots within Manyani Estate in Kivumbini Ward for planning and development | And titling of plots within Manyani Estate in Kivumbini Ward surveyed | 3111401 | Pre-Feasibility, Feasibility & Appraisal Studies | Nakuru East | Kivumbini | -0.302808 36.083735 1792.199951171875 100 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2024/25 | 2024/25 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Enhanced security.
4333 | Surveying and Planning of Sero and Moi Ndabi | Surveying and Planning of Sero and Moi Ndabi | To survey and Planning of Sero and Moi Ndabi for planning and development | And Planning of Sero and Moi Ndabi surveyed | 3111401 | Pre-Feasibility, Feasibility & Appraisal Studies | Naivasha | Maiella | -0.796872 36.250812 1882.2 6.900000095367432 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2024/25 | 2024/25 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Bad. Objective met: Not at all. Viable: Not at all. Contractor: Em Hech investment ltd.. Assessor remarks: Poorly done.
4334 | Njokerio dispensary title Processing | Njokerio dispensary title Processing | To implement njokerio dispensary title processing for orderly land use and housing provision | Njokerio dispensary title Processing completed | 3111401 | Pre-Feasibility, Feasibility & Appraisal Studies | Njoro | Njoro | -0.333564 35.947411 2149.10009765625 60 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2024/25 | 2024/25 | N/A | 70000 | 70000 | 70000 | Equitable | N/A | 70000 | 0 | 0 | 0 | 0 | 70000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Bad. Objective met: Yes. Viable: Yes. Contractor: Not available. Assessor remarks: Theft of wires and concrete poles.
4335 | Planning, surveying and mapping of Kamere, DCK and Kwa Muhia Centres | Planning, surveying and mapping of Kamere, DCK and Kwa Muhia Centres | To implement planning, surveying and mapping of kamere, dck and kwa muhia centres for orderly land use and housing provision | Planning, surveying and mapping of Kamere, DCK and Kwa Muhia Centres completed | 3111401 | Pre-Feasibility, Feasibility & Appraisal Studies | Naivasha | Olkaria | -0.838536 36.360488 1883.0999755859375 7.800000190734863 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2023/24 | 2023/24 | N/A | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good status.
4336 | Preparation Of Physical Development Plans For Lare, and Site and Service (Viwandani Naivasha) | Preparation Of Physical Development Plans For Lare, and Site and Service (Viwandani Naivasha) | To implement preparation of physical development plans for lare, and site and service (viwandani naivasha) for orderly land use and housing provision | Preparation Of Physical Development Plans For Lare, and Site and Service (Viwandani Naivasha) completed | 3111499 | Research & Feasibility Studies | HQ | HQ | N/A | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2021/22 | 2021/22 | N/A | 45159756 | 0 | 6056590 | Equitable | N/A | 6056590 | 0 | 0 | 0 | 0 | 1000000 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
4337 | Processing of Land Ownership documents (Manyani, Dundori and Bahati) | Processing of Land Ownership documents (Manyani, Dundori and Bahati) | To implement processing of land ownership documents (manyani, dundori and bahati) for orderly land use and housing provision | Processing of Land Ownership documents (Manyani, Dundori and Bahati) completed | 3111499 | Research & Feasibility Studies | HQ | HQ | N/A | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2024/25 | 2024/25 | N/A | 10000000 | 0 | 9776255 | Equitable | N/A | 9776255 | 0 | 0 | 0 | 0 | 0 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
4338 | Purchase Of Land to Access Mutukanio Dam | Purchase Of Land to Access Mutukanio Dam | To acquire land for Access Mutukanio Dam | Land for Access Mutukanio Dam acquired | 3130101 | Acquisition of Land | Bahati | Bahati | -0.157265 36.10699 1849.5 28.100000381469727 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2023/24 | 2023/24 | N/A | 1500000 | 0 | 1500000 | Equitable | N/A | 1500000 | 0 | 5200000 | 100 | 5200000 | 1500000 | -5200000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Very Good. Objective met: No. Viable: No. Assessor remarks: The two plots are sperated.
4339 | Purchase Of Land for Wangu Dispensary | Purchase Of Land for Wangu Dispensary | To acquire land for Wangu Dispensary | Land for Wangu Dispensary acquired | 3130101 | Acquisition of Land | Naivasha | Biashara-Naivasha | N/A | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2023/24 | 2023/24 | N/A | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 700000 | 100 | 700000 | 1000000 | -700000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4340 | Purchase of Land at Witemere area for construction of ECDE and Waterpoint | Purchase of Land at Witemere area for construction of ECDE and Waterpoint | To acquire land for Witemere area for construction of ECDE and Waterpoint | Land for Witemere area for construction of ECDE and Waterpoint acquired | 3130101 | Acquisition of Land | Gilgil | Eburru/Mbaruk | -0.393269, 36.141933 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2023/24 | 2023/24 | N/A | 1500000 | 0 | 1300000 | Equitable | N/A | 1300000 | 0 | 0 | 0 | 0 | 1300000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Good. Objective met: Yes. Viable: It's viable. Contractor: Not known. Assessor remarks: Fairly in Good place.
4341 | Purchase of land for construction of a water tower in kirima | Purchase of land for construction of a water tower in kirima | To acquire land for construction of a water tower in kirima | Land for construction of a water tower in kirima acquired | 3130101 | Acquisition of Land | Gilgil | Eburru/Mbaruk | -0.335469, 36.176732 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2024/25 | 2024/25 | N/A | 750780 | 0 | 750780 | Equitable | N/A | 750780 | 0 | 0 | 0 | 0 | 750780 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes. Assessor remarks: Land not yet bought..
4342 | Purchase of Land for Mwaki Mugi water project | Purchase of Land for Mwaki Mugi water project | To acquire land for Mwaki Mugi water project | Land for Mwaki Mugi water project acquired | 3130101 | Acquisition of Land | Bahati | Kabatini | -0.232477 36.147302 1941.300048828125 51.319000244140625 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2023/24 | 2023/24 | N/A | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational,but need installation of electricity.
4343 | Purchase of land for construction of storage tank at Kamuohi Water Project | Purchase of land for construction of storage tank at Kamuohi Water Project | To acquire land for construction of storage tank at Kamuohi Water Project | Land for construction of storage tank at Kamuohi Water Project acquired | 3130101 | Acquisition of Land | Subukia | Kabazi | -0.09011, 36.16711 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2022/23 | 2022/23 | 2024/25 | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Mr. Njoroge.
4344 | Acquisition of land to used for roadlink mau summit and masaiden villages | Acquisition of land to used for roadlink mau summit and masaiden villages | To acquire land for used for roadlink mau summit and masaiden villages | Land for used for roadlink mau summit and masaiden villages acquired | 3130101 | Acquisition of Land | Kuresoi North | Kamara | -0.169962 35.689027 2522.8 13.899999618530273 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2024/25 | 2024/25 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 1500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes if implemented. Assessor remarks: Needs to be started.
4345 | Acquisition of land for Kapkures center ECDE | Acquisition of land for Kapkures center ECDE | To acquire land for Kapkures center ECDE | Land for Kapkures center ECDE acquired | 3130101 | Acquisition of Land | Nakuru West | Kapkures | -0.306306, 36.036551 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2024/25 | 2024/25 | 2024/25 | 16800000 | 16800000 | 16800000 | Equitable | N/A | 16800000 | 0 | 5000000 | 29.8 | 5000000 | 16800000 | 11800000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Very viable. It will provide space for creating an Ecde center.
4346 | Purchase of land at Kapkures Center for construction of market stalls and public toilet | Purchase of land at Kapkures Center for construction of market stalls and public toilet | To acquire land for Kapkures Center for construction of market stalls and public toilet | Land for Kapkures Center for construction of market stalls and public toilet acquired | 3130101 | Acquisition of Land | Nakuru West | Kapkures | -0.306306, 36.036551 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2022/23 | 2022/23 | 2022/23 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 0 | 0 | 0 | 2500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Viable. But land has not been found.
4347 | Purchase Of Land for Expansion of Ingobor Community Water Project Phase 2 | Purchase Of Land for Expansion of Ingobor Community Water Project Phase 2 | To acquire land for Expansion of Ingobor Community Water Project Phase 2 | Land for Expansion of Ingobor Community Water Project Phase 2 acquired | 3130101 | Acquisition of Land | Nakuru West | Kapkures | -0.288288, 36.000456 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2023/24 | 2023/24 | 2023/24 | 1500000 | 0 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 1500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Viable. If complete it will improve access to clean water.
4348 | Purchase of land for Lalwet ECD playing ground | Purchase of land for Lalwet ECD playing ground | To acquire land for Lalwet ECD playing ground | Land for Lalwet ECD playing ground acquired | 3130101 | Acquisition of Land | Nakuru West | Kapkures | -0.324324, 36.036613 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2024/25 | 2024/25 | 2024/25 | 7000000 | 7000000 | 7000000 | Equitable | N/A | 7000000 | 0 | 5000000 | 71.4 | 5000000 | 7000000 | 2000000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Viable. Improved learning environment.
4349 | Purchase Of Land for Lalwet Market | Purchase Of Land for Lalwet Market | To acquire land for Lalwet Market | Land for Lalwet Market acquired | 3130101 | Acquisition of Land | Nakuru West | Kapkures | -0.324324, 36.018595 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2023/24 | 2023/24 | 2023/24 | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 2000000 | 100 | 2000000 | 3000000 | -2000000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Viable. Provide space for trading and job opportunity.
4350 | Purchase of land for Lawlet water tanks reservoir | Purchase of land for Lawlet water tanks reservoir | To acquire land for Lawlet water tanks reservoir | Land for Lawlet water tanks reservoir acquired | 3130101 | Acquisition of Land | Nakuru West | Kapkures | -0.288288, 36.000456 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2022/23 | 2022/23 | 2022/23 | 2788025 | 0 | 2788025 | Equitable | N/A | 2788025 | 0 | 5000000 | 100 | 5000000 | 2500000 | -5000000 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Very viable. It will improve access to clean water.
4351 | Purchase Of Land for construction of VTC in upper Kaptembwa | Purchase Of Land for construction of VTC in upper Kaptembwa | To acquire land for construction of VTC in upper Kaptembwa | Land for construction of VTC in upper Kaptembwa acquired | 3130101 | Acquisition of Land | Nakuru West | Kaptembwo | -0.302961 36.040787 1814.9000244140625 6.9710001945495605 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2023/24 | 2023/24 | N/A | 10000000 | 0 | 10000000 | Equitable | N/A | 10000000 | 0 | 4000000 | 100 | 4000000 | 10000000 | -4000000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: It's functional.
4352 | Purchase Of Land For Public Use In Upper Kaptembwo | Purchase Of Land For Public Use In Upper Kaptembwo | To acquire land for Public Use In Upper Kaptembwo | Land for Public Use In Upper Kaptembwo acquired | 3130101 | Acquisition of Land | Nakuru West | Kaptembwo | -0.315776 36.052811 0 0 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 8000000 | 0 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not yet levelled.
4353 | Purchase of 1/2 acre of land for Kosimbei ECD | Purchase of 1/2 acre of land for Kosimbei ECD | To procure 1/2 acre of land for Kosimbei ECD | 1/2 acre of land for Kosimbei ECD procured | 3130101 | Acquisition of Land | Kuresoi south | Keringet | -0.427111 35.693151 2683.500244140625 40.32899856567383 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2024/25 | 2024/25 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: 2017. Assessor remarks: Bought but no bus park.
4354 | Purchase of land for Construction of Burugo water tank | Purchase of land for Construction of Burugo water tank | To acquire land for Construction of Burugo water tank | Land for Construction of Burugo water tank acquired | 3130101 | Acquisition of Land | Bahati | Kiamaina | -0.240665, 36.110522 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2022/23 | 2022/23 | N/A | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 19250000 | 100 | 19250000 | 2000000 | -19250000 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
4355 | Purchase Of Land for Aggregation Center Kamungei | Purchase Of Land for Aggregation Center Kamungei | To acquire land for Aggregation Center Kamungei | Land for Aggregation Center Kamungei acquired | 3130101 | Acquisition of Land | Rongai | Menengai West | -0.157327 36.001343 1813.7 720.3189697265625 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2023/24 | 2023/24 | N/A | 5000000 | 0 | 5000000 | Equitable | N/A | 5000000 | 0 | 0 | 0 | 0 | 5000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
4356 | Purchase Of Land in Kamungei for Construction of Water Tank | Purchase Of Land in Kamungei for Construction of Water Tank | To acquire land for in Kamungei for Construction of Water Tank | Land for in Kamungei for Construction of Water Tank acquired | 3130101 | Acquisition of Land | Rongai | Menengai West | -0.168207 35.999097 1886.9 728.802001953125 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2023/24 | 2023/24 | N/A | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Partially. Viable: Partially. Assessor remarks: Not equipped as in the description.
4357 | Purchase Of Land in Mercy Njeri for Construction of Market and Public Toilets | Purchase Of Land in Mercy Njeri for Construction of Market and Public Toilets | To acquire land for in Mercy Njeri for Construction of Market and Public Toilets | Land for in Mercy Njeri for Construction of Market and Public Toilets acquired | 3130101 | Acquisition of Land | Rongai | Menengai West | -0.213222 35.952263 2010.5 11.100000381469727 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2023/24 | 2023/24 | N/A | 7000000 | 0 | 7000000 | Equitable | N/A | 7000000 | 0 | 0 | 0 | 0 | 7000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Yet to start.
4358 | Acquisition of Kibera land for the Construction of ECDE | Acquisition of Kibera land for the Construction of ECDE | To procure Kibera land for the Construction of ECDE | Kibera land for the Construction of ECDE procured | 3130101 | Acquisition of Land | Molo | Molo Central | -0.173672, 35.862823 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2024/25 | 2024/25 | 2024/25 | 1300000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4359 | Purchase Of Land and fencing for Ogilgei borehole | Purchase Of Land and fencing for Ogilgei borehole | To acquire land for and fencing for Ogilgei borehole | Land for and fencing for Ogilgei borehole acquired | 3130101 | Acquisition of Land | Rongai | Mosop | -0.302657, 35.953047 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2023/24 | 2023/24 | 2025 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 0 | 0 | 0 | 1800000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Viable. Contractor: Not yet.
4360 | Purchase of land (I acre ) for Sossion ECD | Purchase of land (I acre ) for Sossion ECD | To acquire land for (I acre ) for Sossion ECD | Land for (I acre ) for Sossion ECD acquired | 3130101 | Acquisition of Land | Naivasha | Naivasha East | -0.87416 36.540758 2116.800048828125 3.299999952316284 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2020/21 | 2020/21 | N/A | 2500000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require fencing to mark boundary.
4361 | Purchase Of Land for culture center in Njoro | Purchase Of Land for culture center in Njoro | To acquire land for culture center in Njoro | Land for culture center in Njoro acquired | 3130101 | Acquisition of Land | Njoro | Njoro | -0.309282, 35.91528 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2023/24 | 2023/24 | 2024 | 2000000 | 0 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: Not available.
4362 | Purchase of land for mwariki ponda mali market | Purchase of land for mwariki ponda mali market | To acquire land for mwariki ponda mali market | Land for mwariki ponda mali market acquired | 3130101 | Acquisition of Land | Nakuru West | Rhonda | -0.307109, 36.062727 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2024/25 | 2024/25 | 24/25 | 15500000 | 14500000 | 15500000 | Equitable | N/A | 15500000 | 0 | 0 | 0 | 0 | 15500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Not indicated.
4363 | Purchase Of Land For Expansion of Arus Dispensary | Purchase Of Land For Expansion of Arus Dispensary | To acquire land for Expansion of Arus Dispensary | Land for Expansion of Arus Dispensary acquired | 3130101 | Acquisition of Land | Rongai | Solai | 0.013051 36.159552 1574.0458984375 4.935999870300293 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 0 | 800000 | Equitable | N/A | 800000 | 0 | 900000 | 100 | 900000 | 800000 | -900000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Purchased.
4364 | Purchase of land for ward aggregated center | Purchase of land for ward aggregated center | To acquire land for ward aggregated center | Land for ward aggregated center acquired | 3130101 | Acquisition of Land | Rongai | Solai | 0.01305, 36.159479 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2024/25 | 2024/25 | 2025 | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 900000 | 100 | 900000 | 3000000 | -900000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4365 | Acquisition of land for Subukia valley water project | Acquisition of land for Subukia valley water project | To acquire land for Subukia valley water project | Land for Subukia valley water project acquired | 3130101 | Acquisition of Land | Subukia | Subukia | -0.04678 36.170557 2107.6 2.5 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2024/25 | 2024/25 | N/A | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 500000 | 71.4 | 500000 | 700000 | 200000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: GREATRIFT GENERAL MERCHANT. Assessor remarks: Completed and functional.
4366 | Kirengoro Water Borehole - Plot Compensation | Kirengoro Water Borehole - Plot Compensation | To implement kirengoro water borehole - plot compensation for orderly land use and housing provision | Kirengoro Water Borehole - Plot Compensation completed | 3130101 | Acquisition of Land | Subukia | Subukia | -0.041156 36.220377 2150.7001953125 56.099998474121094 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2022/23 | 2022/23 | N/A | 3600000 | 0 | 3600000 | Equitable | N/A | 3600000 | 0 | 0 | 0 | 0 | 3600000 | 0 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes.. Viable: Sure. The community now uses the water. Contractor: Information not available. Assessor remarks: Good work..
4367 | Purchase Of Muthaiga Plot For Construction Of Tank For Kware Water Project | Purchase Of Muthaiga Plot For Construction Of Tank For Kware Water Project | To procure Muthaiga Plot For Construction Of Tank For Kware Water Project | Muthaiga Plot For Construction Of Tank For Kware Water Project procured | 3130101 | Acquisition of Land | Subukia | Subukia | -0.006188, 36.235553 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2021/22 | 2021/22 | 2021/2022 | 1600000 | 0 | 1600000 | Equitable | N/A | 1600000 | 0 | 500000 | 100 | 500000 | 1600000 | -500000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: No. Community blocked accessing the water till the matter of payment for the landis resolved. Viable: Yes. Contractor: Details not availed.
4368 | Purchase of Muya's Land To Connect Kamigutha and Kirengero | Purchase of Muya's Land To Connect Kamigutha and Kirengero | To procure Muya's Land To Connect Kamigutha and Kirengero | Muya's Land To Connect Kamigutha and Kirengero procured | 3130101 | Acquisition of Land | Subukia | Subukia | 0.002545 36.22944 2004.1999999999998 1 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2022/23 | 2022/23 | N/A | 750000 | 0 | 750000 | Equitable | N/A | 750000 | 0 | 900000 | 100 | 900000 | 750000 | -900000 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: Not known. Assessor remarks: Further interventions.
4369 | Compensation for acquisation of land for muchorwe center | Compensation for acquisation of land for muchorwe center | To implement compensation for acquisation of land for muchorwe center for orderly land use and housing provision | Compensation for acquisation of land for muchorwe center completed | 3130101 | Acquisition of Land | Molo | Turi | -0.32968, 35.687164 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2024/25 | 2024/25 | N/A | 2300000 | 2300000 | 2300000 | Equitable | N/A | 2300000 | 0 | 0 | 0 | 0 | 2300000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: Partially. Condition: Yet to start. Objective met: The centre is in existence. Viable: Yes.
4370 | Purchase Of Land for Ngano-Ini Water Project | Purchase Of Land for Ngano-Ini Water Project | To acquire land for Ngano-Ini Water Project | Land for Ngano-Ini Water Project acquired | 3130101 | Acquisition of Land | Subukia | Waseges | -0.818938, 36.32092 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING AND URBAN DEVELOPMENT | N/A | 2023/24 | 2023/24 | N/A | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes.
4371 | Conditional Fund - World Bank Kenya Informal Settlement Improvement Project II (KISIP II) | Conditional Fund - World Bank Kenya Informal Settlement Improvement Project II (KISIP II) | To implement conditional fund - world bank kenya informal settlement improvement project ii (kisip ii) for orderly land use and housing provision | Conditional Fund - World Bank Kenya Informal Settlement Improvement Project II (KISIP II) completed | 2630203 | N/A | HQ | HQ | -0.173672, 35.862823 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2023/24 | 2023/24 | 2023/24 | 400000000 | 400000000 | 0 | N/A | N/A | 0 | 250000000 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4372 | Conditional Fund - World Bank—Kenya Informal Settlement Improvement Project II (KISIP II) | Conditional Fund - World Bank—Kenya Informal Settlement Improvement Project II (KISIP II) | To implement conditional fund - world bank—kenya informal settlement improvement project ii (kisip ii) for orderly land use and housing provision | Conditional Fund - World Bank—Kenya Informal Settlement Improvement Project II (KISIP II) completed | 2630203 | N/A | HQ | HQ | -0.173672, 35.862823 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2022/23 | 2022/23 | 2022/23 | 200000000 | 200000000 | 0 | N/A | N/A | 0 | 200000000 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4373 | Renovation of Lumumba estate (fisher boards) | Renovation of Lumumba estate (fisher boards) | To rehabilitate Lumumba estate (fisher boards) to restore functionality | Lumumba estate (fisher boards) rehabilitated | 3110301 | Refurbishment of Residential Buildings | Nakuru East | Biashara-Nakuru | N/A | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2023/24 | 2023/24 | 2023/24 | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 659000 | 94.1 | 659000 | 41000 | 41000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4374 | Reroofing of Flamingo Estate County Houses | Reroofing of Flamingo Estate County Houses | To implement reroofing of flamingo estate county houses for orderly land use and housing provision | Reroofing of Flamingo Estate County Houses completed | 3110301 | Refurbishment of Residential Buildings | Nakuru East | Flamingo | -0.302183, 36.079475 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2022/23 | 2022/23 | 2024/25 | 2696440 | 2696440 | 2696440 | Equitable | N/A | 2696440 | 0 | 2996976 | 111.1 | 2996976 | 2696440 | -300536 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Contractor: ECRAT merchants ltd.
4375 | Proposed reroofing of Kaloleni A and Baharini 2 Estates | Proposed reroofing of Kaloleni A and Baharini 2 Estates | To undertake the proposed reroofing of Kaloleni A and Baharini 2 Estates | Proposed reroofing of Kaloleni A and Baharini 2 Estates implemented | 3110301 | Refurbishment of Residential Buildings | Nakuru East | Kivumbini | -0.300694, 36.086594 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2022/23 | 2022/23 | 2022/23 | 3500000 | 3422860 | 3422860 | Equitable | N/A | 3422860 | 0 | 3261159 | 95.3 | 3261159 | 161701 | 161701 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4376 | Re-Roofing of Kaloleni C Estate | Re-Roofing of Kaloleni C Estate | To implement re-roofing of kaloleni c estate for orderly land use and housing provision | Re-Roofing of Kaloleni C Estate completed | 3110301 | Refurbishment of Residential Buildings | Nakuru East | Kivumbini | -0.30025, 36.087203 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2023/24 | 2023/24 | 2023/24 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 1950000 | 97.5 | 1950000 | 50000 | 50000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4377 | Survey, Valuation, Mapping And Conveyancing Cost (Ahero market 0.045ha, Maili kumi market 0.0419ha, Wanyororo market 0.0888ha, Wanyororo market 0.0878ha) | Survey, Valuation, Mapping And Conveyancing Cost (Ahero market 0.045ha, Maili kumi market 0.0419ha, Wanyororo market 0.0888ha, Wanyororo market 0.0878ha) | To implement survey, valuation, mapping and conveyancing cost (ahero market 0.045ha, maili kumi market 0.0419ha, wanyororo market 0.0888ha, wanyororo market 0.0878ha) for orderly land use and housing provision | Survey, Valuation, Mapping And Conveyancing Cost (Ahero market 0.045ha, Maili kumi market 0.0419ha, Wanyororo market 0.0888ha, Wanyororo market 0.0878ha) completed | 3110504 | Other Infrastructure and Civil Works | Bahati | Bahati | N/A | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2019/20 | 2019/20 | N/A | 1580000 | 1580000 | 1580000 | Equitable | N/A | 1580000 | 0 | 0 | 0 | 0 | 1580000 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4378 | Construction and equipping of ABMT Demonstration Centre in Cheptuech VTC in Kuresoi South | Construction and equipping of ABMT Demonstration Centre in Cheptuech VTC in Kuresoi South | To construct and equip ABMT Demonstration Centre in Cheptuech VTC in Kuresoi South | ABMT Demonstration Centre in Cheptuech VTC in Kuresoi South constructed and equipped | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2022/23 | 2022/23 | 2022/23 | 3500000 | 3234650 | 3234650 | Equitable | N/A | 3234650 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4379 | Construction of ABMT Centres in Begi Polytechnic | Construction of ABMT Centres in Begi Polytechnic | To construct ABMT Centres in Begi Polytechnic | ABMT Centres in Begi Polytechnic constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2021/22 | 2021/22 | 2021/22 | 3122430 | 3122430 | 3122430 | Equitable | N/A | 3122430 | 0 | 0 | 0 | 0 | 5300000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4380 | Construction of ABMT Centres in Kamara Polytechnic | Construction of ABMT Centres in Kamara Polytechnic | To construct ABMT Centres in Kamara Polytechnic | ABMT Centres in Kamara Polytechnic constructed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2021/22 | 2021/22 | 2021/22 | 2999900 | 947740 | 947740 | Equitable | N/A | 947740 | 0 | 0 | 0 | 0 | 5300000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4381 | Establishment Of G.I.S Laboratory (Land Information Management (LIMS)) | Establishment Of G.I.S Laboratory (Land Information Management (LIMS)) | To implement establishment of g.i.s laboratory (land information management (lims)) for orderly land use and housing provision | Establishment Of G.I.S Laboratory (Land Information Management (LIMS)) completed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2014/15 | 2014/15 | 2014/15 | 4244494.5 | 4244495 | 4244495 | Equitable | N/A | 4244495 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4382 | Survey And Mapping (Titling Of Land) | Survey And Mapping (Titling Of Land) | To survey And Mapping (Titling Of Land) for planning and development | And Mapping (Titling Of Land) surveyed | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2018/19 | 2018/19 | N/A | 12991330 | 5740580 | 5740580 | Equitable | N/A | 5740580 | 0 | 2250750 | 39.2 | 2250750 | 10740580 | 3489830 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4383 | Upgrading of sewer line at Naivasha Sub County Estate | Upgrading of sewer line at Naivasha Sub County Estate | To upgrade sewer line at Naivasha Sub County Estate through tarmacking for improved road connectivity | Sewer line at Naivasha Sub County Estate tarmacked and upgraded | 3110504 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2022/23 | 2022/23 | 2022/23 | 20500000 | 5722476 | 5722476 | Equitable | N/A | 5722476 | 0 | 4879891 | 85.3 | 4879891 | 842585 | 842585 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4384 | Construction of 5 sanitation blocks at Kivumbini 1 and 2 Estates | Construction of 5 sanitation blocks at Kivumbini 1 and 2 Estates | To construct 5 sanitation blocks at Kivumbini 1 and 2 Estates | 5 sanitation blocks at Kivumbini 1 and 2 Estates constructed | 3110504 | Other Infrastructure and Civil Works | Nakuru East | Kivumbini | -0.299264, 36.082708 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2022/23 | 2022/23 | 2022/23 | 10000000 | 9452200 | 9452200 | Equitable | N/A | 9452200 | 0 | 8958027 | 94.8 | 8958027 | 494173 | 494173 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4385 | Surveying Of Trading Centres | Surveying Of Trading Centres | To survey Trading Centres for planning and development | Trading Centres surveyed | 3110599 | Other Infrastructure and Civil Works | HQ | HQ | N/A | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2019/20 | 2019/20 | N/A | 18895710 | 6185695.75 | 6185695.75 | Equitable | N/A | 6185695.75 | 0 | 2710014 | 43.8 | 2710014 | 16185696 | 3475681.75 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4386 | GIS Land Resource Data mapping | GIS Land Resource Data mapping | To implement gis land resource data mapping for orderly land use and housing provision | GIS Land Resource Data mapping completed | 3111112 | Purchase of Software | HQ | HQ | N/A | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2023/24 | 2023/24 | N/A | 18107245 | 7107245 | 7107245 | Equitable | N/A | 7107245 | 0 | 0 | 0 | 0 | 0 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4387 | Purchase of survey equipment | Purchase of survey equipment | To procure survey equipment | Survey equipment procured | 3111114 | N/A | HQ | HQ | -0.173672, 35.862823 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2023/24 | 2023/24 | 2023/24 | 3000000 | 3000000 | 3000000 | N/A | N/A | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4388 | Equipping of 2 Semi Automated Block Making Machines | Equipping of 2 Semi Automated Block Making Machines | To equip 2 Semi Automated Block Making Machines with necessary facilities and equipment | 2 Semi Automated Block Making Machines equipped | 3111120 | Purchase of Specialized Plant. - | HQ | HQ | -0.173672, 35.862823 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2023/24 | 2023/24 | 2023/24 | 4000000 | 0 | 4000000 | N/A | N/A | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4389 | Purchase of 1 additional Semi Automated Block Making Machine | Purchase of 1 additional Semi Automated Block Making Machine | To procure 1 additional Semi Automated Block Making Machine | 1 additional Semi Automated Block Making Machine procured | 3111401 | Pre-Feasibility, Feasibility & Appraisal Studies | HQ | HQ | -0.173672, 35.862823 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2023/24 | 2023/24 | 2023/24 | 2000000 | 0 | 2000000 | N/A | N/A | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4390 | Planning, surveying and mapping of Kamere, DCK and Kwa Muhia Centres | Planning, surveying and mapping of Kamere, DCK and Kwa Muhia Centres | To implement planning, surveying and mapping of kamere, dck and kwa muhia centres for orderly land use and housing provision | Planning, surveying and mapping of Kamere, DCK and Kwa Muhia Centres completed | 3111401 | Pre-Feasibility, Feasibility & Appraisal Studies | Naivasha | Olkaria | -0.838536 36.360488 1883.0999755859375 7.800000190734863 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2023/24 | 2023/24 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good status.
4391 | Preparation Of Physical Development Plans For Lare, Piave, Rongai Township Kianjoya and Banita Centres | Preparation Of Physical Development Plans For Lare, Piave, Rongai Township Kianjoya and Banita Centres | To implement preparation of physical development plans for lare, piave, rongai township kianjoya and banita centres for orderly land use and housing provision | Preparation Of Physical Development Plans For Lare, Piave, Rongai Township Kianjoya and Banita Centres completed | 3111499 | Research & Feasibility Studies | HQ | HQ | N/A | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2021/22 | 2021/22 | N/A | 45159756 | 0 | 7056590 | Equitable | N/A | 7056590 | 0 | 0 | 0 | 0 | 0 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Status: Vired. Recommendation: Close and write off.
4392 | Purchase Of Land to Access Mutukanio Dam | Purchase Of Land to Access Mutukanio Dam | To acquire land for Access Mutukanio Dam | Land for Access Mutukanio Dam acquired | 3130101 | Acquisition of Land | Bahati | Bahati | -0.157265 36.10699 1849.5 28.100000381469727 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2023/24 | 2023/24 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 5200000 | 346.7 | 5200000 | 1500000 | -3700000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Very Good. Objective met: No. Viable: No. Assessor remarks: The two plots are sperated.
4393 | Purchase Of Land for Soimet ECD | Purchase Of Land for Soimet ECD | To acquire land for Soimet ECD | Land for Soimet ECD acquired | 3130101 | Acquisition of Land | Nakuru West | Barut | -0.3425 36.042 0 2000 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2023/24 | 2023/24 | 2023/24 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 750000 | 25 | 750000 | 3000000 | 2250000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: No. Viable: No. Assessor remarks: No land has been purchased for soimet ecd.
4394 | Purchase Of Land for Wangu Dispensary | Purchase Of Land for Wangu Dispensary | To acquire land for Wangu Dispensary | Land for Wangu Dispensary acquired | 3130101 | Acquisition of Land | Naivasha | Biashara-Naivasha | N/A | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2023/24 | 2023/24 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 700000 | 70 | 700000 | 1000000 | 300000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4395 | Purchase of Land at Witemere area for construction of ECDE and Waterpoint | Purchase of Land at Witemere area for construction of ECDE and Waterpoint | To acquire land for Witemere area for construction of ECDE and Waterpoint | Land for Witemere area for construction of ECDE and Waterpoint acquired | 3130101 | Acquisition of Land | Gilgil | Eburru/Mbaruk | -0.393269, 36.141933 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2023/24 | 2023/24 | N/A | 1500000 | 1300000 | 1300000 | Equitable | N/A | 1300000 | 0 | 0 | 0 | 0 | 1300000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Good. Objective met: Yes. Viable: It's viable. Contractor: Not known. Assessor remarks: Fairly in Good place.
4396 | Purchase of land for Kasarani dispensary - additional allocation | Purchase of land for Kasarani dispensary - additional allocation | To acquire land for Kasarani dispensary - additional allocation | Land for Kasarani dispensary - additional allocation acquired | 3130101 | Acquisition of Land | Molo | Elburgon | -0.284884 35.845889 0 1399.9990234375 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2022/23 | 2022/23 | 2022/23 | 1000000 | 1200000 | 1200000 | Equitable | N/A | 1200000 | 0 | 1000000 | 83.3 | 1000000 | 1000000 | 200000 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Construction of 2.no consultation rooms.
4397 | Purchase Of Land For Mbombo ECDE | Purchase Of Land For Mbombo ECDE | To acquire land for Mbombo ECDE | Land for Mbombo ECDE acquired | 3130101 | Acquisition of Land | Gilgil | Elementaita | -0.556018 36.104887 1961.0999755859375 18.899999618530273 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2016/17 | 2016/17 | N/A | 5500000 | 4490000 | 4490000 | Equitable | N/A | 4490000 | 0 | 4490000 | 100 | 4490000 | 4200000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Owners are yet to be paid..
4398 | Completion of purchase of land for St. John's Water project in Malewa West | Completion of purchase of land for St. John's Water project in Malewa West | To complete purchase of land for St. John's Water project in Malewa West | Purchase of land for St. John's Water project in Malewa West completed | 3130101 | Acquisition of Land | HQ | HQ | -0.173672, 35.862823 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2023/24 | 2023/24 | 2023/24 | 4000000 | 4000000 | 4000000 | N/A | N/A | 4000000 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes.
4399 | Purchase of Land for Mwaki Mugi water project | Purchase of Land for Mwaki Mugi water project | To acquire land for Mwaki Mugi water project | Land for Mwaki Mugi water project acquired | 3130101 | Acquisition of Land | Bahati | Kabatini | -0.232477 36.147302 1941.300048828125 51.319000244140625 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2023/24 | 2023/24 | N/A | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Operational,but need installation of electricity.
4400 | Purchase of land for a Playfield in Arahuka | Purchase of land for a Playfield in Arahuka | To acquire land for a Playfield in Arahuka | Land for a Playfield in Arahuka acquired | 3130101 | Acquisition of Land | Subukia | Kabazi | -0.08223 36.16987 0 1381 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2022/23 | 2022/23 | N/A | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 0 | 0 | 0 | 2500000 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Contractor: Not indicated. Assessor remarks: Machine was brought but transferred to subukia Valley coffee factory.
4401 | Purchase of land for construction of storage tank at Kamuohi Water Project | Purchase of land for construction of storage tank at Kamuohi Water Project | To acquire land for construction of storage tank at Kamuohi Water Project | Land for construction of storage tank at Kamuohi Water Project acquired | 3130101 | Acquisition of Land | Subukia | Kabazi | -0.09011, 36.16711 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2022/23 | 2022/23 | 2024/25 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Mr. Njoroge.
4402 | Purchase of land at Kapkures Center for construction of market stalls and public toilet | Purchase of land at Kapkures Center for construction of market stalls and public toilet | To acquire land for Kapkures Center for construction of market stalls and public toilet | Land for Kapkures Center for construction of market stalls and public toilet acquired | 3130101 | Acquisition of Land | Nakuru West | Kapkures | -0.306306, 36.036551 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2022/23 | 2022/23 | 2022/23 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 0 | 0 | 0 | 2500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: Viable. But land has not been found.
4403 | Purchase Of Land for Expansion of Ingobor Community Water Project Phase 2 | Purchase Of Land for Expansion of Ingobor Community Water Project Phase 2 | To acquire land for Expansion of Ingobor Community Water Project Phase 2 | Land for Expansion of Ingobor Community Water Project Phase 2 acquired | 3130101 | Acquisition of Land | Nakuru West | Kapkures | -0.288288, 36.000456 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2023/24 | 2023/24 | 2023/24 | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 1500000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: Not yet. Viable: Viable. If complete it will improve access to clean water.
4404 | Purchase Of Land for Lalwet Market | Purchase Of Land for Lalwet Market | To acquire land for Lalwet Market | Land for Lalwet Market acquired | 3130101 | Acquisition of Land | Nakuru West | Kapkures | -0.324324, 36.018595 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2023/24 | 2023/24 | 2023/24 | 3000000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 2000000 | 66.7 | 2000000 | 3000000 | 1000000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Viable. Provide space for trading and job opportunity.
4405 | Purchase of land for Lawlet water tanks reservoir | Purchase of land for Lawlet water tanks reservoir | To acquire land for Lawlet water tanks reservoir | Land for Lawlet water tanks reservoir acquired | 3130101 | Acquisition of Land | Nakuru West | Kapkures | -0.288288, 36.000456 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2022/23 | 2022/23 | 2022/23 | 2788025 | 2788025 | 2788025 | Equitable | N/A | 2788025 | 0 | 5000000 | 179.3 | 5000000 | 2500000 | -2211975 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Very viable. It will improve access to clean water.
4406 | Purchase Of Land for construction of VTC in upper Kaptembwa | Purchase Of Land for construction of VTC in upper Kaptembwa | To acquire land for construction of VTC in upper Kaptembwa | Land for construction of VTC in upper Kaptembwa acquired | 3130101 | Acquisition of Land | Nakuru West | Kaptembwo | -0.302961 36.040787 1814.9000244140625 6.9710001945495605 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2023/24 | 2023/24 | N/A | 10000000 | 10000000 | 10000000 | Equitable | N/A | 10000000 | 0 | 4000000 | 40 | 4000000 | 10000000 | 6000000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: It's functional.
4407 | Purchase Of Land For Public Use In Upper Kaptembwo | Purchase Of Land For Public Use In Upper Kaptembwo | To acquire land for Public Use In Upper Kaptembwo | Land for Public Use In Upper Kaptembwo acquired | 3130101 | Acquisition of Land | Nakuru West | Kaptembwo | -0.315776 36.052811 0 0 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2019/20 | 2019/20 | 2019/20 | 8000000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Not yet levelled.
4408 | Purchase of land for Construction of Burugo water tank | Purchase of land for Construction of Burugo water tank | To acquire land for Construction of Burugo water tank | Land for Construction of Burugo water tank acquired | 3130101 | Acquisition of Land | Bahati | Kiamaina | -0.240665, 36.110522 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2022/23 | 2022/23 | N/A | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 19250000 | 962.5 | 19250000 | 2000000 | -17250000 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
4409 | Purchase of road opening parcel in Gathengera / St Joan Community | Purchase of road opening parcel in Gathengera / St Joan Community | To procure road opening parcel in Gathengera / St Joan Community | Road opening parcel in Gathengera / St Joan Community procured | 3130101 | Acquisition of Land | Gilgil | Malewa West | -0.666667, 36.434899 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2023/24 | 2023/24 | 2023/24 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 2000000 | 100 | 2000000 | 0 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes.
4410 | Purchase Of Land for Muhoro-Kiratina Link Road | Purchase Of Land for Muhoro-Kiratina Link Road | To acquire land for Muhoro-Kiratina Link Road | Land for Muhoro-Kiratina Link Road acquired | 3130101 | Acquisition of Land | Nakuru East | Menengai | -0.273152 36.107904 1867.699951171875 10.253000259399414 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2023/24 | 2023/24 | N/A | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 0 | 0 | 0 | 4000000 | 0 | Vired | 0 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: The school doesn't have a special needs unit. The items were never supplied.
4411 | Purchase Of Land for Aggregation Center Kamungei | Purchase Of Land for Aggregation Center Kamungei | To acquire land for Aggregation Center Kamungei | Land for Aggregation Center Kamungei acquired | 3130101 | Acquisition of Land | Rongai | Menengai West | -0.157327 36.001343 1813.7 720.3189697265625 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2023/24 | 2023/24 | N/A | 5000000 | 0 | 5000000 | Equitable | N/A | 5000000 | 0 | 0 | 0 | 0 | 5000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: In good condition.
4412 | Purchase Of Land in Kamungei for Construction of Water Tank | Purchase Of Land in Kamungei for Construction of Water Tank | To acquire land for in Kamungei for Construction of Water Tank | Land for in Kamungei for Construction of Water Tank acquired | 3130101 | Acquisition of Land | Rongai | Menengai West | -0.168207 35.999097 1886.9 728.802001953125 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2023/24 | 2023/24 | N/A | 2500000 | 3000000 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 3000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Partially. Viable: Partially. Assessor remarks: Not equipped as in the description.
4413 | Purchase Of Land in Mercy Njeri for Construction of Market and Public Toilets | Purchase Of Land in Mercy Njeri for Construction of Market and Public Toilets | To acquire land for in Mercy Njeri for Construction of Market and Public Toilets | Land for in Mercy Njeri for Construction of Market and Public Toilets acquired | 3130101 | Acquisition of Land | Rongai | Menengai West | -0.213222 35.952263 2010.5 11.100000381469727 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2023/24 | 2023/24 | N/A | 7000000 | 7000000 | 7000000 | Equitable | N/A | 7000000 | 0 | 0 | 0 | 0 | 7000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Yet to start.
4414 | Purchase Of Land and fencing for Ogilgei borehole | Purchase Of Land and fencing for Ogilgei borehole | To acquire land for and fencing for Ogilgei borehole | Land for and fencing for Ogilgei borehole acquired | 3130101 | Acquisition of Land | Rongai | Mosop | -0.302657, 35.953047 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2023/24 | 2023/24 | 2025 | 1800000 | 1800000 | 1800000 | Equitable | N/A | 1800000 | 0 | 0 | 0 | 0 | 1800000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Viable. Contractor: Not yet.
4415 | Purchase of land (I acre ) for Sossion ECD | Purchase of land (I acre ) for Sossion ECD | To acquire land for (I acre ) for Sossion ECD | Land for (I acre ) for Sossion ECD acquired | 3130101 | Acquisition of Land | Naivasha | Naivasha East | -0.87416 36.540758 2116.800048828125 3.299999952316284 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2020/21 | 2020/21 | N/A | 2500000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require fencing to mark boundary.
4416 | Purchase Of Land for culture center in Njoro | Purchase Of Land for culture center in Njoro | To acquire land for culture center in Njoro | Land for culture center in Njoro acquired | 3130101 | Acquisition of Land | Njoro | Njoro | -0.309282, 35.91528 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2023/24 | 2023/24 | 2024 | 2000000 | 2000000 | 2000000 | Equitable | N/A | 2000000 | 0 | 0 | 0 | 0 | 2000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Contractor: Not available.
4417 | Purchase Of Public Land at Rafiki | Purchase Of Public Land at Rafiki | To procure Public Land at Rafiki | Public Land at Rafiki procured | 3130101 | Acquisition of Land | Rongai | Soin | -0.046127 36.049341 1647 9.5 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2023/24 | 2023/24 | N/A | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 0 | 0 | 0 | 2500000 | 0 | Vired | 75 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Require Renovation and additional class.
4418 | Purchase Of Land For Expansion of Arus Dispensary | Purchase Of Land For Expansion of Arus Dispensary | To acquire land for Expansion of Arus Dispensary | Land for Expansion of Arus Dispensary acquired | 3130101 | Acquisition of Land | Rongai | Solai | 0.013051 36.159552 1574.0458984375 4.935999870300293 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2019/20 | 2019/20 | N/A | 1200000 | 0 | 800000 | Equitable | N/A | 800000 | 0 | 900000 | 0 | 900000 | 800000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Purchased.
4419 | Kirengoro Water Borehole - Plot Compensation | Kirengoro Water Borehole - Plot Compensation | To implement kirengoro water borehole - plot compensation for orderly land use and housing provision | Kirengoro Water Borehole - Plot Compensation completed | 3130101 | Acquisition of Land | Subukia | Subukia | -0.041156 36.220377 2150.7001953125 56.099998474121094 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2022/23 | 2022/23 | N/A | 3600000 | 3600000 | 3600000 | Equitable | N/A | 3600000 | 0 | 0 | 0 | 0 | 3600000 | 0 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes.. Viable: Sure. The community now uses the water. Contractor: Information not available. Assessor remarks: Good work..
4420 | Purchase Of Muthaiga Plot For Construction Of Tank For Kware Water Project | Purchase Of Muthaiga Plot For Construction Of Tank For Kware Water Project | To procure Muthaiga Plot For Construction Of Tank For Kware Water Project | Muthaiga Plot For Construction Of Tank For Kware Water Project procured | 3130101 | Acquisition of Land | Subukia | Subukia | -0.006188, 36.235553 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2021/22 | 2021/22 | 2021/2022 | 1000000 | 1600000 | 1600000 | Equitable | N/A | 1600000 | 0 | 500000 | 31.2 | 500000 | 1600000 | 1100000 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Good. Objective met: No. Community blocked accessing the water till the matter of payment for the landis resolved. Viable: Yes. Contractor: Details not availed.
4421 | Purchase of Muya's Land To Connect Kamigutha and Kirengero | Purchase of Muya's Land To Connect Kamigutha and Kirengero | To procure Muya's Land To Connect Kamigutha and Kirengero | Muya's Land To Connect Kamigutha and Kirengero procured | 3130101 | Acquisition of Land | Subukia | Subukia | 0.002545 36.22944 2004.1999999999998 1 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2022/23 | 2022/23 | N/A | 750000 | 750000 | 750000 | Equitable | N/A | 750000 | 0 | 900000 | 120 | 900000 | 750000 | -150000 | Ongoing | 25 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Bad. Objective met: No. Viable: No. Contractor: Not known. Assessor remarks: Further interventions.
4422 | Purchase Of Land for Road Network At Kiangwaci | Purchase Of Land for Road Network At Kiangwaci | To acquire land for Road Network At Kiangwaci | Land for Road Network At Kiangwaci acquired | 3130101 | Acquisition of Land | Molo | Turi | -0.279395 35.753738 2477.9 9.800000190734863 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2019/20 | 2019/20 | N/A | 500000 | 500000 | 500000 | Equitable | N/A | 500000 | 0 | 2900000 | 580 | 2900000 | 500000 | -2400000 | Vired | 90 | N/A | N/A | N/A | N/A | N/A | No | Close and write off | Possible pending obligations or incomplete commitments | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: Yes. Viable: Yes. Assessor remarks: The land was bought by the county, the title of the land to be confirmed by the department.
4423 | Purchase of land for Igana Water Project | Purchase of land for Igana Water Project | To acquire land for Igana Water Project | Land for Igana Water Project acquired | 3130101 | Acquisition of Land | Subukia | Waseges | -0.818938, 36.32092 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2022/23 | 2022/23 | N/A | 400000 | 0 | 400000 | Equitable | N/A | 400000 | 0 | 0 | 0 | 0 | 400000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes.
4424 | Purchase Of Land for Ngano-Ini Water Project | Purchase Of Land for Ngano-Ini Water Project | To acquire land for Ngano-Ini Water Project | Land for Ngano-Ini Water Project acquired | 3130101 | Acquisition of Land | Subukia | Waseges | -0.818938, 36.32092 | 4583 | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | LANDS, PHYSICAL PLANNING, HOUSING & URBAN DEVELOPMENT | N/A | 2023/24 | 2023/24 | N/A | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 0 | 0 | 0 | 1000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Stalled. Operational: No. Condition: Yet to start. Objective met: No. Viable: Yes.
4425 | Water and Sewerage Management | Water Outstanding Contract Retention - development | To implement water outstanding contract retention - development for access to clean water and environmental sustainability | Water Outstanding Contract Retention - development completed | 2211314 | Write Offs/ Bad Debt Expenses from Previous Years (Pending Bills) | HQ | HQ | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | N/A | 4679515.56 | 2957515.56 | 2957515.56 | Equitable | N/A | 2957515.56 | 0 | 2858049 | 96.6 | 2858049 | 0 | 99466.56 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Status: Ongoing. Recommendation: Continue to completion.
4426 | Climate Change Resilience and County Energy Development | Climate Change Mitigation Programme (1% Of Equitable Development) | To implement climate change mitigation programme (1% of equitable development) for access to clean water and environmental sustainability | Climate Change Mitigation Programme (1% Of Equitable Development) completed | 2630203 | N/A | HQ | HQ | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | N/A | 33312923.13 | 33312923.13 | 0 | Equitable | N/A | 0 | 33312923.13 | 0 | 0 | 0 | 33312923 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4427 | Climate Change Resilience and County Energy Development | Climate Change Mitigation Programme (1.5% Of Equitable Development) | To implement climate change mitigation programme (1.5% of equitable development) for access to clean water and environmental sustainability | Climate Change Mitigation Programme (1.5% Of Equitable Development) completed | 2630203 | N/A | HQ | HQ | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 65500000 | 55000000 | 62500000 | Equitable | N/A | 62500000 | 0 | 0 | 0 | 0 | 33312923 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4428 | Climate Change Resilience and County Energy Development | Conditional allocation from a World Bank credit to Finance Locally-Led Climate Action Program (FLLoCA) | To implement conditional allocation from a world bank credit to finance locally-led climate action program (flloca) for access to clean water and environmental sustainability | Conditional allocation from a World Bank credit to Finance Locally-Led Climate Action Program (FLLoCA) completed | 2630203 | N/A | HQ | HQ | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 276524007.9 | 250000000 | 0 | Grant | Grant | 0 | 652946177.67 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4429 | Climate Change Resilience and County Energy Development | County Climate Change Mitigation Programme - Counterpart funding | To implement county climate change mitigation programme - counterpart funding for access to clean water and environmental sustainability | County Climate Change Mitigation Programme - Counterpart funding completed | 2630203 | N/A | HQ | HQ | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 100707177 | 0 | 100707177 | Equitable | N/A | 100707177 | 0 | 4997450 | 100 | 4997450 | 33312923 | -4997450 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4430 | Climate Change Resilience and County Energy Development | County Climate Change Mitigation Programme | To implement county climate change mitigation programme for access to clean water and environmental sustainability | County Climate Change Mitigation Programme completed | 2630203 | N/A | HQ | HQ | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | N/A | 65500000 | 0 | 7500000 | Equitable | N/A | 7500000 | 0 | 4997450 | 100 | 4997450 | 14983207.38 | -4997450 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4431 | Climate Change Resilience and County Energy Development | Drilling and equipping of borehole at Banita Secondary school grounds in Kokwomoi sub location | To implement drilling and equipping of borehole at banita secondary school grounds in kokwomoi sub location for access to clean water and environmental sustainability | Drilling and equipping of borehole at Banita Secondary school grounds in Kokwomoi sub location completed | 2630203 | N/A | HQ | HQ | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 6435119 | 6435119 | 0 | Grant | Grant | 0 | 6435119 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4432 | Water and Sewerage Management | Salgaa Area Programme (World Vision) Counterpart funding | To implement salgaa area programme (world vision) counterpart funding for access to clean water and environmental sustainability | Salgaa Area Programme (World Vision) Counterpart funding completed | 2630203 | N/A | HQ | HQ | -0.391082, 35.742475 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | N/A | 23000000 | 0 | 6552463.28 | N/A | N/A | 6552463.28 | 0 | 0 | 0 | 0 | 16970338 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Project moved from baraget to baseline.
4433 | Water and Sewerage Management | Salgaa Counterpart Funding (World Vision) - Counterpart funding/Kandutura water project (Visoi/Soin) | To implement salgaa counterpart funding (world vision) - counterpart funding/kandutura water project (visoi/soin) for access to clean water and environmental sustainability | Salgaa Counterpart Funding (World Vision) - Counterpart funding/Kandutura water project (Visoi/Soin) completed | 2640503 | N/A | HQ | HQ | -0.391082, 35.742475 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 20000000 | 22000000 | 9000000 | N/A | N/A | 9000000 | 0 | 0 | 0 | 0 | 16970338 | 0 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: No. Viable: No. Assessor remarks: Project moved from baraget to baseline.
4434 | Refurbishment of Offices (HQs) WEENR) | Refurbishment of Offices (HQs) WEENR) | To implement refurbishment of offices (hqs) weenr) for access to clean water and environmental sustainability | Refurbishment of Offices (HQs) WEENR) completed | 3110302 | Refurbishment of Non-Residential Buildings | HQ | HQ | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 3134474 | 0 | 1525329 | N/A | N/A | 1525329 | 0 | 2456688 | 100 | 2456688 | 0 | -2456688 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4435 | Water and Sewerage Management | Construction Of A Water Tank And Piping At Ambusket And Singorwet | To construct A Water Tank And Piping At Ambusket And Singorwet | A Water Tank And Piping At Ambusket And Singorwet constructed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Amalo | -0.576578 35.700243 2542.400146484375 11.399999618530273 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2021/22 | 2021/22 | 2021/22 | 5327890 | 2261672.8 | 2261672.8 | Equitable | N/A | 2261672.8 | 0 | 2159970 | 95.5 | 2159970 | 101703 | 101702.8 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: yes. Viable: yes. Assessor remarks: project completed.
4436 | Water and Sewerage Management | Construction Of A Water Tank At Olenguruone | To construct A Water Tank At Olenguruone | A Water Tank At Olenguruone constructed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Amalo | -0.67954 35.639677 2420.475341796875 5.486999988555908 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2021/22 | 2021/22 | 2021/22 | 1000000 | 980775.36 | 980775.36 | Equitable | N/A | 980775.36 | 0 | 980775 | 100 | 980775 | 980775 | 0.36 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: not yet done. Viable: yes. Assessor remarks: not done.
4437 | Water and Sewerage Management | Construction of Bondet water tank project | To construct Bondet water tank project | Bondet water tank project constructed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Amalo | -0.590476 35.686102 2581.1123046875 9.741999626159668 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | N/A | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 599824 | 100 | 599824 | 1000000 | -599824 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: yes. Viable: yes. Contractor: m/s koros. Assessor remarks: works going on well.
4438 | Water and Sewerage Management | Construction Of Water Tank At Sinerindet | To construct Water Tank At Sinerindet | Water Tank At Sinerindet constructed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Amalo | -0.632512 35.664773 2513.7 10.5 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2019/20 | 2019/20 | 2019/20 | 1000000 | 1000000 | 1000000 | Equitable | N/A | 1000000 | 0 | 960712 | 96.1 | 960712 | 39288 | 39288 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Ongoing. Operational: No. Condition: Yet to start. Objective met: not yet in use. Viable: yet to start. Assessor remarks: project ongoing.
4439 | Water and Sewerage Management | Installation of pump and laying of pipes at Ndasiata | To install pump and laying of pipes at Ndasiata | Pump and laying of pipes at Ndasiata installed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Amalo | -0.638923, 35.65338 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2021/22 | 2021/22 | 2025 | 1500000 | 1480098 | 1480098 | Equitable | N/A | 1480098 | 0 | 0 | 0 | 0 | 1480098 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: project completed.
4440 | Water and Sewerage Management | Kiptaragon water project -piping | To implement kiptaragon water project -piping for access to clean water and environmental sustainability | Kiptaragon water project -piping completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Amalo | -0.603628, 35.675373 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2025 | 1200000 | 0 | 1200000 | Equitable | N/A | 1200000 | 0 | 0 | 0 | 0 | 1200000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: not yet. Viable: not yet. Assessor remarks: project not started.
4441 | Water and Sewerage Management | Laying of waterpipes at Kabigeriet from Ndasiata | To implement laying of waterpipes at kabigeriet from ndasiata for access to clean water and environmental sustainability | Laying of waterpipes at Kabigeriet from Ndasiata completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Amalo | -0.639938, 35.658435 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2021/22 | 2021/22 | 2025 | 1500000 | 0 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 1500000 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: yes. Viable: yes. Assessor remarks: completed.
4442 | Water and Sewerage Management | Piping of Chesoin water project | To provide water distribution infrastructure at Chesoin water project | Water piping at Chesoin water project completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Amalo | -0.603628, 35.675373 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | 2025 | 1100000 | 1100000 | 1100000 | Equitable | N/A | 1100000 | 0 | 300000 | 27.3 | 300000 | 847082 | 800000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: not yet. Viable: not yet. Assessor remarks: project not started.
4443 | Water and Sewerage Management | Piping of Kitoben water project | To provide water distribution infrastructure at Kitoben water project | Water piping at Kitoben water project completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Amalo | -0.603628, 35.675373 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2025 | 1000000 | 0 | 847082.2 | Equitable | N/A | 847082.2 | 0 | 300000 | 100 | 300000 | 847082 | -300000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: not yet. Viable: not yet. Assessor remarks: project not started.
4444 | Water and Sewerage Management | Rehabilitation Of Kasarani Water Spring | To rehabilitate Kasarani Water Spring to restore functionality | Kasarani Water Spring rehabilitated | 3110502 | Water Supplies and Sewerage | Kuresoi South | Amalo | -0.596908, 35.68512 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2025 | 650000 | 0 | 650000 | Equitable | N/A | 650000 | 0 | 0 | 0 | 0 | 650000 | 0 | Ongoing | 90 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Very Good. Objective met: yes. Viable: yes. Assessor remarks: project completed.
4445 | Water and Sewerage Management | Sinendet water project & piping | To implement sinendet water project & piping for access to clean water and environmental sustainability | Sinendet water project & piping completed | 3110502 | Water Supplies and Sewerage | Kuresoi South | Amalo | -0.603628, 35.675373 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2025 | 4200000 | 0 | 4200000 | Equitable | N/A | 4200000 | 0 | 400000 | 100 | 400000 | 4200000 | -400000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — New/Yet to start. Operational: No. Condition: Yet to start. Objective met: not yet. Viable: not yet. Assessor remarks: project not started.
4446 | Water and Sewerage Management | Bahati Ward Water Works | To implement bahati ward water works for access to clean water and environmental sustainability | Bahati Ward Water Works completed | 3110502 | Water Supplies and Sewerage | Bahati | Bahati | -0.174075, 36.135411 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2021/22 | 2023/24 | 2023/24 | 5200000 | 12015555.6 | 18866316.43 | Equitable | N/A | 18866316.43 | 0 | 3157845 | 26.3 | 3157845 | 3042155 | 8857710.6 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Well done.
4447 | Water and Sewerage Management | Bahati Water Works Project | To implement bahati water works project for access to clean water and environmental sustainability | Bahati Water Works Project completed | 3110502 | Water Supplies and Sewerage | Bahati | Bahati | -0.174193, 36.135371 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2019/20 | 2019/20 | N/A | 14124449 | 1197584 | 1197584 | Equitable | N/A | 1197584 | 0 | 1197584 | 100 | 1197584 | 1197584 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes it is viable. Viable: Yes it did. Assessor remarks: Nicely done.
4448 | Water and Sewerage Management | Bahati water works | To implement bahati water works for access to clean water and environmental sustainability | Bahati water works completed | 3110502 | Water Supplies and Sewerage | Bahati | Bahati | -0.174075, 36.135411 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | 2024/25 | 8000000 | 8000000 | 8000000 | Equitable | N/A | 8000000 | 0 | 2991652 | 37.4 | 2991652 | 2008348 | 5008348 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | Yes | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Well done.
4449 | Water and Sewerage Management | Equipping and piping of Bahati Ward water works | To equip and piping of Bahati Ward water works with necessary facilities and equipment | And piping of Bahati Ward water works equipped | 3110502 | Water Supplies and Sewerage | Bahati | Bahati | -0.174075, 36.135411 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2022/23 | 8000000 | 8000000 | 8000000 | Equitable | N/A | 8000000 | 0 | 7659858 | 95.7 | 7659858 | 340142 | 340142 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Well done.
4450 | Water and Sewerage Management | Purchase and supply of water pipes in Bahati ward | To procure and supply water pipes in Bahati ward | Water pipes in Bahati ward procured and supplied | 3110502 | Water Supplies and Sewerage | Bahati | Bahati | -0.150455 36.146665 2036.32080078125 5.013999938964844 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2022/23 | 1800000 | 800000 | 800000 | Equitable | N/A | 800000 | 0 | 788916 | 98.6 | 788916 | 11084 | 11084 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: It is in use.
4451 | Water and Sewerage Management | Drilling of Bongo borehole | To implement drilling of bongo borehole for access to clean water and environmental sustainability | Drilling of Bongo borehole completed | 3110502 | Water Supplies and Sewerage | Nakuru West | Barut | 0.353373, 36.049497 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | 2025 | 3500000 | 3500000 | 3500000 | Equitable | N/A | 3500000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The project is complete.
4452 | Water and Sewerage Management | Mlima Ugali Borehole Water works | To implement mlima ugali borehole water works for access to clean water and environmental sustainability | Mlima Ugali Borehole Water works completed | 3110502 | Water Supplies and Sewerage | Nakuru West | Barut | 0.3533, 36.0494 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2024 | 4484442 | 0 | 4444442 | Equitable | N/A | 4444442 | 0 | 0 | 0 | 0 | 4484442 | 0 | Ongoing | 75 | N/A | N/A | N/A | N/A | N/A | Yes | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: AQUASAN SYSTEMS LIMITED. Assessor remarks: Completed.
4453 | Water and Sewerage Management | Purchase and supply of two large garbage bin | To procure and supply two large garbage bin | Two large garbage bin procured and supplied | 3110502 | Water Supplies and Sewerage | Nakuru West | Barut | -0.327118, 36.056358 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | 2024 | 1500000 | 0 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: The pipes have been bought.
4454 | Water and Sewerage Management | Purchase and supply of water pipes at parkview sublocation | To procure and supply water pipes at parkview sublocation | Water pipes at parkview sublocation procured and supplied | 3110502 | Water Supplies and Sewerage | Nakuru West | Barut | 0.0353373 36.049 1834 2000 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: No. Viable: No. Assessor remarks: It's yet to start.
4455 | Water and Sewerage Management | Repair of water tanks and Purchase of water pipes at tangi tatu, tangi saba in kigonor | To rehabilitate water tanks and Purchase of water pipes at tangi tatu, tangi saba in kigonor to restore functionality | Water tanks and Purchase of water pipes at tangi tatu, tangi saba in kigonor rehabilitated | 3110502 | Water Supplies and Sewerage | Nakuru West | Barut | 0.0353373 36.049 1834 2000 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 1500000 | 1500000 | 1500000 | Equitable | N/A | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: No. Viable: No. Assessor remarks: It's yet to start.
4456 | Water and Sewerage Management | Construction of Water Tower and Tank Installation at Good Faith | To construct Water Tower and Tank Installation at Good Faith | Water Tower and Tank Installation at Good Faith constructed | 3110502 | Water Supplies and Sewerage | Naivasha | Biashara-Naivasha | -0.662673, 36.50857 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2025 | 1300000 | 0 | 1300000 | Equitable | N/A | 1300000 | 0 | 0 | 0 | 0 | 1300000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: The project management committee yet to put constitutional operation in place for start, solarization required since a generator is in use..
4457 | Water and Sewerage Management | Drilling Of Kahuruko Borehole | To implement drilling of kahuruko borehole for access to clean water and environmental sustainability | Drilling Of Kahuruko Borehole completed | 3110502 | Water Supplies and Sewerage | Naivasha | Biashara-Naivasha | -0.728758, 36.502177 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2024 | 3750000 | 3750000 | 3750000 | Equitable | N/A | 3750000 | 0 | 3694855 | 98.5 | 3694855 | 55145 | 55145 | Ongoing | 0 | N/A | N/A | N/A | N/A | N/A | No | Continue to completion | Contractor performance; cost overrun; delayed completion | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: No. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: The project is ongoing ,solarisation and pumbing ,tower..and tanks.
4458 | Water and Sewerage Management | Gicheha Borehole water works | To implement gicheha borehole water works for access to clean water and environmental sustainability | Gicheha Borehole water works completed | 3110502 | Water Supplies and Sewerage | Naivasha | Biashara-Naivasha | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | N/A | 4000000 | 4000000 | 4000000 | Equitable | N/A | 4000000 | 0 | 4000000 | 100 | 4000000 | 4000000 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4459 | Water and Sewerage Management | Piping at Kambi Ndoro | To provide water distribution infrastructure at Kambi Ndoro | Water piping at Kambi Ndoro completed | 3110502 | Water Supplies and Sewerage | Naivasha | Biashara-Naivasha | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2022/23 | 2220746 | 1000000 | 2220746 | Equitable | N/A | 2220746 | 0 | 965306 | 96.5 | 965306 | 1255440 | 34694 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Status: Complete. Recommendation: Retain and archive.
4460 | Water and Sewerage Management | Piping at Muteithia borehole | To provide water distribution infrastructure at Muteithia borehole | Water piping at Muteithia borehole completed | 3110502 | Water Supplies and Sewerage | Naivasha | Biashara-Naivasha | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | N/A | 3000000 | 2990776.8 | 2990776.8 | Equitable | N/A | 2990776.8 | 0 | 2857880 | 95.6 | 2857880 | 132896 | 132896.8 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | No | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4461 | Water and Sewerage Management | Piping of Gituru Wendani Water Project | To provide water distribution infrastructure at Gituru Wendani Water Project | Water piping at Gituru Wendani Water Project completed | 3110502 | Water Supplies and Sewerage | Naivasha | Biashara-Naivasha | -0.662673, 36.50857 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | 2025 | 2500000 | 2500000 | 2500000 | Equitable | N/A | 2500000 | 0 | 2897000 | 115.9 | 2897000 | 2897000 | -397000 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Partially. Condition: Yet to start. Objective met: Yes. Viable: Yes. Assessor remarks: The project management committee yet to put constitutional operation in place for start, solarization required since a generator is in use..
4462 | Water and Sewerage Management | Water piping at highland | To implement water piping at highland for access to clean water and environmental sustainability | Water piping at highland completed | 3110502 | Water Supplies and Sewerage | Naivasha | Biashara-Naivasha | -0.707568, 36.511453 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | 2025 | 1000000 | 0 | 1000000 | Equitable | N/A | 1000000 | 0 | 965306 | 0 | 965306 | 1255440 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: No. Viable: No. Contractor: M/s JOWICH INTERNATIONAL LIMITED. Assessor remarks: Need for bigger pipes, extension for more coverage..
4463 | Water and Sewerage Management | Water works at Nyonjoro area | To implement water works at nyonjoro area for access to clean water and environmental sustainability | Water works at Nyonjoro area completed | 3110502 | Water Supplies and Sewerage | Naivasha | Biashara-Naivasha | N/A | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2024/25 | 2024/25 | N/A | 3000000 | 0 | 3000000 | Equitable | N/A | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Status: Yet to start/New. Recommendation: Prioritise and initiate.
4464 | Water and Sewerage Management | Construction of a water tank 100cm3 at Chiefs Office ground in Giachonge | To construct a water tank 100cm3 at Chiefs Office ground in Giachonge | A water tank 100cm3 at Chiefs Office ground in Giachonge constructed | 3110502 | Water Supplies and Sewerage | Bahati | Dundori | -0.246032 36.239455 2322.7001953125 23.299999237060547 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | N/A | 1500000 | 0 | 1500000 | Equitable | N/A | 1500000 | 0 | 1467220 | 100 | 1467220 | 1500000 | -1467220 | Yet to start/New | 0 | N/A | N/A | N/A | N/A | N/A | Yes | Prioritise and initiate | Procurement delays; budget availability | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Sodys general. Assessor remarks: In good state.
4465 | Water and Sewerage Management | Construction of a water tank at upper Dundori | To construct a water tank at upper Dundori | A water tank at upper Dundori constructed | 3110502 | Water Supplies and Sewerage | Bahati | Dundori | -0.246032 36.239455 2322.7001953125 23.299999237060547 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2022/23 | 2022/23 | 2022/23 | 1500000 | 1467220 | 1467220 | Equitable | N/A | 1467220 | 0 | 1467220 | 100 | 1467220 | 1467220 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Sodys general. Assessor remarks: In good state.
4466 | Water and Sewerage Management | Drilling, Equipping And Water Works At Dundori Water Projects | To implement drilling, equipping and water works at dundori water projects for access to clean water and environmental sustainability | Drilling, Equipping And Water Works At Dundori Water Projects completed | 3110502 | Water Supplies and Sewerage | Bahati | Dundori | -0.24679, 36.2379 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2019/20 | 2019/20 | 2019/2020 | 3500000 | 621700 | 621700 | Equitable | N/A | 621700 | 0 | 621700 | 100 | 621700 | 621700 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Contractor: Nemoca enterprise. Assessor remarks: In good state.
4467 | Water and Sewerage Management | Dundori Water Works | To implement dundori water works for access to clean water and environmental sustainability | Dundori Water Works completed | 3110502 | Water Supplies and Sewerage | Bahati | Dundori | -0.239802 36.241437 2324.000244140625 5.599999904632568 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 1700000 | 1700000 | 1700000 | Equitable | N/A | 1700000 | 0 | 1559761 | 91.8 | 1559761 | 140239 | 140239 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.
4468 | Water and Sewerage Management | Purchase & Supply of Pipes at Cura Water Project | To procure & Supply of Pipes at Cura Water Project | & Supply of Pipes at Cura Water Project procured | 3110502 | Water Supplies and Sewerage | Bahati | Dundori | -0.261988 36.17999 1980.9000244140625 100 | 4584 | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | WATER, ENERGY, ENVIRONMENT, NATURAL RESOURCES AND CLIMATE CHANGE | N/A | 2023/24 | 2023/24 | 2023/24 | 700000 | 700000 | 700000 | Equitable | N/A | 700000 | 0 | 700000 | 100 | 700000 | 49795 | 0 | Complete | 100 | N/A | N/A | N/A | N/A | N/A | No | Retain and archive | Pending bills / retention claims outstanding | No | Not done | No | Not done | No | Not done | Field verification: Status — Complete. Operational: Yes. Condition: Good. Objective met: Yes. Viable: Yes. Assessor remarks: Good.